## Sheet1
Planning Partner | Dist | County | Project | Title | SR | Sec | Project Class | Phase | Fund | Est Let | Actual Let | 2025 Tot | 2026 Tot | 2027 Tot | 2028 Tot | 2029 Tot | 2030 Tot | 2031 Tot | 2032 Tot | 2033-36 Tot | Total
Adams | 8 | Adams | 18086 | Country Club Road Bridge | 7401 | BRG | Bridge Replacement | FD | BOF | 2027-04-01 |  | 2897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2897
Adams | 8 | Adams | 18086 | Country Club Road Bridge | 7401 | BRG | Bridge Replacement | FD | STP | 2027-04-01 |  | 213103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213103
Adams | 8 | Adams | 18086 | Country Club Road Bridge | 7401 | BRG | Bridge Replacement | FD | 183 | 2027-04-01 |  | 3000 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40500
Adams | 8 | Adams | 18086 | Country Club Road Bridge | 7401 | BRG | Bridge Replacement | FD | LOC | 2027-04-01 |  | 1000 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500
Adams | 8 | Adams | 18086 | Country Club Road Bridge | 7401 | BRG | Bridge Replacement | ROW | BOF | 2027-04-01 |  | 96000 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112000
Adams | 8 | Adams | 18086 | Country Club Road Bridge | 7401 | BRG | Bridge Replacement | ROW | 183 | 2027-04-01 |  | 18000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000
Adams | 8 | Adams | 18086 | Country Club Road Bridge | 7401 | BRG | Bridge Replacement | ROW | LOC | 2027-04-01 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Adams | 8 | Adams | 18086 | Country Club Road Bridge | 7401 | BRG | Bridge Replacement | UTL | BOF | 2027-04-01 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Adams | 8 | Adams | 18086 | Country Club Road Bridge | 7401 | BRG | Bridge Replacement | UTL | 183 | 2027-04-01 |  | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500
Adams | 8 | Adams | 18086 | Country Club Road Bridge | 7401 | BRG | Bridge Replacement | UTL | LOC | 2027-04-01 |  | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500
Adams | 8 | Adams | 18086 | Country Club Road Bridge | 7401 | BRG | Bridge Replacement | CON | BOF | 2027-04-01 |  | 0 | 0 | 0 | 0 | 552000 | 0 | 0 | 0 | 0 | 552000
Adams | 8 | Adams | 18086 | Country Club Road Bridge | 7401 | BRG | Bridge Replacement | CON | 183 | 2027-04-01 |  | 0 | 0 | 0 | 0 | 103500 | 0 | 0 | 0 | 0 | 103500
Adams | 8 | Adams | 18154 | Stoney Point Road Bridge | 7218 | BRG | Bridge Replacement | FD | BOF | 2028-11-02 |  | 202112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202112
Adams | 8 | Adams | 18154 | Stoney Point Road Bridge | 7218 | BRG | Bridge Replacement | FD | 183 | 2028-11-02 |  | 37896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37896
Adams | 8 | Adams | 18154 | Stoney Point Road Bridge | 7218 | BRG | Bridge Replacement | FD | LOC | 2028-11-02 |  | 12632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12632
Adams | 8 | Adams | 18154 | Stoney Point Road Bridge | 7218 | BRG | Bridge Replacement | ROW | BOF | 2028-11-02 |  | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000
Adams | 8 | Adams | 18154 | Stoney Point Road Bridge | 7218 | BRG | Bridge Replacement | ROW | 183 | 2028-11-02 |  | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000
Adams | 8 | Adams | 18154 | Stoney Point Road Bridge | 7218 | BRG | Bridge Replacement | ROW | LOC | 2028-11-02 |  | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
Adams | 8 | Adams | 18154 | Stoney Point Road Bridge | 7218 | BRG | Bridge Replacement | UTL | BOF | 2028-11-02 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Adams | 8 | Adams | 18154 | Stoney Point Road Bridge | 7218 | BRG | Bridge Replacement | UTL | 183 | 2028-11-02 |  | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
Adams | 8 | Adams | 18154 | Stoney Point Road Bridge | 7218 | BRG | Bridge Replacement | UTL | LOC | 2028-11-02 |  | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
Adams | 8 | Adams | 18154 | Stoney Point Road Bridge | 7218 | BRG | Bridge Replacement | CON | BOF | 2028-11-02 |  | 0 | 0 | 691000 | 0 | 0 | 0 | 0 | 0 | 0 | 691000
Adams | 8 | Adams | 18154 | Stoney Point Road Bridge | 7218 | BRG | Bridge Replacement | CON | BRIP | 2028-11-02 |  | 0 | 0 | 342405 | 0 | 0 | 0 | 0 | 0 | 0 | 342405
Adams | 8 | Adams | 18154 | Stoney Point Road Bridge | 7218 | BRG | Bridge Replacement | CON | 183 | 2028-11-02 |  | 0 | 0 | 193765 | 0 | 0 | 0 | 0 | 0 | 0 | 193765
Adams | 8 | Adams | 18154 | Stoney Point Road Bridge | 7218 | BRG | Bridge Replacement | CON | LOC | 2028-11-02 |  | 0 | 0 | 64588 | 0 | 0 | 0 | 0 | 0 | 0 | 64588
Adams | 8 | Adams | 58137 | Eisenhower Drive Extension | 0 | RWY | Highway Reconstruction | FD | BRIP | 2027-06-24 |  | 636991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636991
Adams | 8 | Adams | 58137 | Eisenhower Drive Extension | 0 | RWY | Highway Reconstruction | FD | STP | 2027-06-24 |  | 1036147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036147
Adams | 8 | Adams | 58137 | Eisenhower Drive Extension | 0 | RWY | Highway Reconstruction | FD | 185 | 2027-06-24 |  | 266200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266200
Adams | 8 | Adams | 58137 | Eisenhower Drive Extension | 0 | RWY | Highway Reconstruction | FD | 581 | 2027-06-24 |  | 1244795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1244795
Adams | 8 | Adams | 58137 | Eisenhower Drive Extension | 0 | RWY | Highway Reconstruction | ROW | 185 | 2027-06-24 |  | 256864 | 936271 | 293382 | 270034 | 350000 | 0 | 0 | 0 | 0 | 2106551
Adams | 8 | Adams | 58137 | Eisenhower Drive Extension | 0 | RWY | Highway Reconstruction | ROW | 581 | 2027-06-24 |  | 797226 | 3342000 | 2172383 | 417020 | 3433087 | 4731733 | 0 | 0 | 0 | 14893449
Adams | 8 | Adams | 58137 | Eisenhower Drive Extension | 0 | RWY | Highway Reconstruction | UTL | STP | 2027-06-24 |  | 0 | 768230 | 373059 | 958480 | 1027000 | 0 | 0 | 0 | 0 | 3126769
Adams | 8 | Adams | 58137 | Eisenhower Drive Extension | 0 | RWY | Highway Reconstruction | UTL | 185 | 2027-06-24 |  | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Adams | 8 | Adams | 58137 | Eisenhower Drive Extension | 0 | RWY | Highway Reconstruction | UTL | 581 | 2027-06-24 |  | 0 | 0 | 1149000 | 3330696 | 708515 | 0 | 0 | 0 | 0 | 5188211
Adams | 8 | Adams | 58137 | Eisenhower Drive Extension | 0 | RWY | Highway Reconstruction | CON | BRIP | 2027-06-24 |  | 0 | 0 | 0 | 0 | 0 | 374767 | 1409000 | 1409000 | 5624016 | 8816783
Adams | 8 | Adams | 58137 | Eisenhower Drive Extension | 0 | RWY | Highway Reconstruction | CON | STP | 2027-06-24 |  | 0 | 0 | 0 | 0 | 0 | 1627000 | 2027000 | 2027000 | 7564864 | 13245864
Adams | 8 | Adams | 58137 | Eisenhower Drive Extension | 0 | RWY | Highway Reconstruction | CON | 581 | 2027-06-24 |  | 0 | 0 | 2500000 | 2500000 | 5000000 | 5000000 | 0 | 0 | 0 | 15000000
Adams | 8 | Adams | 58137 | Eisenhower Drive Extension | 0 | RWY | Highway Reconstruction | CON | 185 | 2027-06-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1228000 | 1226000 | 2028289 | 4482289
Adams | 8 | Adams | 58137 | Eisenhower Drive Extension | 0 | RWY | Highway Reconstruction | CON | 581 | 2027-06-24 |  | 0 | 0 | 0 | 0 | 956676 | 366162 | 5099000 | 5097000 | 18986226 | 30505064
Adams | 8 | Adams | 78642 | Red Bridge Rd over Conewago Creek | 1017 | 006 | Bridge Restoration | PE | BOF | 2028-01-13 |  | 0 | 8207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8207
Adams | 8 | Adams | 78642 | Red Bridge Rd over Conewago Creek | 1017 | 006 | Bridge Restoration | FD | BOF | 2028-01-13 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Adams | 8 | Adams | 78642 | Red Bridge Rd over Conewago Creek | 1017 | 006 | Bridge Restoration | ROW | BOF | 2028-01-13 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Adams | 8 | Adams | 78642 | Red Bridge Rd over Conewago Creek | 1017 | 006 | Bridge Restoration | CON | BOF | 2028-01-13 |  | 0 | 0 | 0 | 0 | 13661 | 986339 | 0 | 0 | 0 | 1000000
Adams | 8 | Adams | 78642 | Red Bridge Rd over Conewago Creek | 1017 | 006 | Bridge Restoration | CON | BRIP | 2028-01-13 |  | 0 | 521380 | 221490 | 221489 | 873641 | 400000 | 387000 | 0 | 0 | 2625000
Adams | 8 | Adams | 78672 | PA 94 and Berlin Road | 94 | 029 | Highway Reconstruction | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394136 | 394136
Adams | 8 | Adams | 80962 | Chapel Rd over Plum Crk | 2009 | 017 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Adams | 8 | Adams | 80962 | Chapel Rd over Plum Crk | 2009 | 017 | Bridge Restoration | FD | BRIP |  |  | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000
Adams | 8 | Adams | 80962 | Chapel Rd over Plum Crk | 2009 | 017 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
Adams | 8 | Adams | 82372 | SRTP Rideshare Program |  | RSP | Reserve Line Item | PE | STP |  |  | 0 | 71521 | 65441 | 66095 | 0 | 0 | 0 | 0 | 0 | 203057
Adams | 8 | Adams | 87432 | State Street Bridge | 3001 | 052 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Adams | 8 | Adams | 87432 | State Street Bridge | 3001 | 052 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654000 | 654000
Adams | 8 | Adams | 87433 | Carlisle Road Bridge 4 | 34 | 046 | Bridge Replacement | CON | 185 | 2025-03-13 | 2025-03-13 | 4604 | 107915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112519
Adams | 8 | Adams | 87433 | Carlisle Road Bridge 4 | 34 | 046 | Bridge Replacement | CON | 581 | 2025-03-13 | 2025-03-13 | 801574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801574
Adams | 8 | Adams | 87792 | Bridge Reserve |  |  | Reserve Line Item | CON | BOF |  |  | 127991 | 341520 | 106000 | 909236 | 471339 | 400661 | 0 | 435888 | 3596112 | 6388747
Adams | 8 | Adams | 87792 | Bridge Reserve |  |  | Reserve Line Item | CON | BRIP |  |  | 272009 | 0 | 32149 | 500632 | 535359 | 134233 | 0 | 0 | 9984 | 1484366
Adams | 8 | Adams | 87792 | Bridge Reserve |  |  | Reserve Line Item | CON | 185 |  |  | 5436 | 0 | 0 | 17502 | 48895 | 7189 | 0 | 0 | 420711 | 499733
Adams | 8 | Adams | 87793 | Highway Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 257000 | 208000 | 2461000 | 2461000 | 2461000 | 2461000 | 2461000 | 9683000 | 22453000
Adams | 8 | Adams | 87793 | Highway Reserve |  |  | Reserve Line Item | CON | STP |  |  | 223792 | 228650 | 455925 | 0 | 0 | 400000 | 0 | 0 | 150000 | 1458367
Adams | 8 | Adams | 87793 | Highway Reserve |  |  | Reserve Line Item | CON | 581 |  |  | 2125 | 0 | 0 | 2002 | 4722 | 3105 | 0 | 0 | 1384774 | 1396728
Adams | 8 | Adams | 87807 | Delivery / Consult Assist |  |  | Reserve Line Item | PE | 185 |  |  | 0 | 7836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7836
Adams | 8 | Adams | 87807 | Delivery / Consult Assist |  |  | Reserve Line Item | PE | 581 |  |  | 400000 | 400000 | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 1600000
Adams | 8 | Adams | 87807 | Delivery / Consult Assist |  |  | Reserve Line Item | CON | 581 |  |  | 200000 | 200000 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 800000
Adams | 8 | Adams | 87811 | HSIP Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 172982 | 837309 | 0 | 0 | 0 | 0 | 208940 | 1019000 | 4076000 | 6314231
Adams | 8 | Adams | 90686 | Piney Creek Bridge - 1 | 97 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355000 | 355000
Adams | 8 | Adams | 90698 | Hunterstown Hampton Rd ov Conewago Cr | 394 | 010 | Bridge Restoration | PE | STP | 2027-01-28 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Adams | 8 | Adams | 90698 | Hunterstown Hampton Rd ov Conewago Cr | 394 | 010 | Bridge Restoration | FD | BOF | 2027-01-28 |  | 0 | 308273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308273
Adams | 8 | Adams | 90698 | Hunterstown Hampton Rd ov Conewago Cr | 394 | 010 | Bridge Restoration | ROW | BOF | 2027-01-28 |  | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000
Adams | 8 | Adams | 90698 | Hunterstown Hampton Rd ov Conewago Cr | 394 | 010 | Bridge Restoration | ROW | STP | 2027-01-28 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Adams | 8 | Adams | 90698 | Hunterstown Hampton Rd ov Conewago Cr | 394 | 010 | Bridge Restoration | UTL | STP | 2027-01-28 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Adams | 8 | Adams | 90698 | Hunterstown Hampton Rd ov Conewago Cr | 394 | 010 | Bridge Restoration | CON | 185 | 2027-01-28 |  | 0 | 0 | 570666 | 536529 | 0 | 0 | 0 | 0 | 0 | 1107195
Adams | 8 | Adams | 90698 | Hunterstown Hampton Rd ov Conewago Cr | 394 | 010 | Bridge Restoration | CON | 581 | 2027-01-28 |  | 0 | 0 | 708617 | 754282 | 0 | 0 | 0 | 0 | 0 | 1462899
Adams | 8 | Adams | 90699 | Latimore Creek Bridge | 1005 | 0 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Adams | 8 | Adams | 90699 | Latimore Creek Bridge | 1005 | 0 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1053000 | 1053000
Adams | 8 | Adams | 90740 | Alloway Creek Bridge | 2014 | 021 | Bridge Restoration | FD | BOF | 2026-06-18 |  | 12900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12900
Adams | 8 | Adams | 90740 | Alloway Creek Bridge | 2014 | 021 | Bridge Restoration | FD | BRIP | 2026-06-18 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Adams | 8 | Adams | 90740 | Alloway Creek Bridge | 2014 | 021 | Bridge Restoration | FD | STP | 2026-06-18 |  | 63100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63100
Adams | 8 | Adams | 90740 | Alloway Creek Bridge | 2014 | 021 | Bridge Restoration | ROW | BOF | 2026-06-18 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Adams | 8 | Adams | 90740 | Alloway Creek Bridge | 2014 | 021 | Bridge Restoration | UTL | BOF | 2026-06-18 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Adams | 8 | Adams | 90740 | Alloway Creek Bridge | 2014 | 021 | Bridge Restoration | CON | BOF | 2026-06-18 |  | 0 | 0 | 0 | 477764 | 0 | 0 | 0 | 0 | 0 | 477764
Adams | 8 | Adams | 90740 | Alloway Creek Bridge | 2014 | 021 | Bridge Restoration | CON | BRIP | 2026-06-18 |  | 0 | 274801 | 512956 | 436879 | 0 | 0 | 0 | 0 | 0 | 1224636
Adams | 8 | Adams | 90740 | Alloway Creek Bridge | 2014 | 021 | Bridge Restoration | CON | 185 | 2026-06-18 |  | 0 | 171478 | 177187 | 76935 | 0 | 0 | 0 | 0 | 0 | 425600
Adams | 8 | Adams | 90752 | Pumping Station Rd ov Trib to Marsh Cr | 3005 | 013 | Bridge Replacement | PE | BOF |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Adams | 8 | Adams | 90752 | Pumping Station Rd ov Trib to Marsh Cr | 3005 | 013 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Adams | 8 | Adams | 90752 | Pumping Station Rd ov Trib to Marsh Cr | 3005 | 013 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 424605 | 588811 | 0 | 0 | 0 | 1013416
Adams | 8 | Adams | 90782 | Brysonia Rd over Conwago Cr | 4008 | 033 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 440000
Adams | 8 | Adams | 90782 | Brysonia Rd over Conwago Cr | 4008 | 033 | Bridge Restoration | FD | BOF |  |  | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000
Adams | 8 | Adams | 90782 | Brysonia Rd over Conwago Cr | 4008 | 033 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 951112 | 748888 | 2700000
Adams | 8 | Adams | 99727 | US 15 Bridge PM#2 | 15 | 041 | Bridge Preservation - Federal | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161000 | 161000
Adams | 8 | Adams | 99743 | Centenial Road Bridge PM | 2006 | 005 | Bridge Preservation - Federal | PE | 185 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 120000
Adams | 8 | Adams | 99751 | Brickcrafters Road Bridge | 2015 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205000 | 205000
Adams | 8 | Adams | 99751 | Brickcrafters Road Bridge | 2015 | 0 | Bridge Preservation - Federal | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000
Adams | 8 | Adams | 99751 | Brickcrafters Road Bridge | 2015 | 0 | Bridge Preservation - Federal | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672000 | 672000
Adams | 8 | Adams | 99756 | Bollinger Road Bridge PM | 2027 | 008 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104000 | 104000
Adams | 8 | Adams | 99756 | Bollinger Road Bridge PM | 2027 | 008 | Bridge Preservation - Federal | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161000 | 161000
Adams | 8 | Adams | 99832 | Rock Creek Bridge | 3002 | 016 | Bridge Replacement | FD | PRTCT | 2026-08-27 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Adams | 8 | Adams | 99832 | Rock Creek Bridge | 3002 | 016 | Bridge Replacement | ROW | PRTCT | 2026-08-27 |  | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
Adams | 8 | Adams | 99832 | Rock Creek Bridge | 3002 | 016 | Bridge Replacement | CON | BOF | 2026-08-27 |  | 0 | 671000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671000
Adams | 8 | Adams | 99832 | Rock Creek Bridge | 3002 | 016 | Bridge Replacement | CON | BRIP | 2026-08-27 |  | 0 | 940819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 940819
Adams | 8 | Adams | 99832 | Rock Creek Bridge | 3002 | 016 | Bridge Replacement | CON | PRTCT | 2026-08-27 |  | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
Adams | 8 | Adams | 99832 | Rock Creek Bridge | 3002 | 016 | Bridge Replacement | CON | STP | 2026-08-27 |  | 0 | 710599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 710599
Adams | 8 | Adams | 106665 | PA 116 over Trib Marsh Crk | 116 | 043 | Bridge Replacement | CON | STP | 2024-05-09 | 2024-05-09 | 67455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67455
Adams | 8 | Adams | 113255 | SR 2008 Elm Ave Resurface | 2008 | 013 | General Maintenance | PE | 581 | 2026-10-22 |  | 81747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81747
Adams | 8 | Adams | 113255 | SR 2008 Elm Ave Resurface | 2008 | 013 | General Maintenance | UTL | 581 | 2026-10-22 |  | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
Adams | 8 | Adams | 113256 | PA 116 Main Street Resurface | 116 | 055 | 409 Expanded Maintenance | CON | 185 | 2024-06-06 | 2024-06-06 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Adams | 8 | Adams | 115745 | Carlisle Pike Resurface 2 | 94 | 032 | Highway Restoration | PE | 581 | 2026-02-12 | 2026-02-12 | 64533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64533
Adams | 8 | Adams | 115745 | Carlisle Pike Resurface 2 | 94 | 032 | Highway Restoration | CON | NHPP | 2026-02-12 | 2026-02-12 | 0 | 2076000 | 2516000 | 0 | 0 | 0 | 0 | 0 | 0 | 4592000
Adams | 8 | Adams | 116268 | East Berlin and Stoney Pt Int | 234 | 027 | Safety Improvement | FD | HSIP | 2029-01-01 |  | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
Adams | 8 | Adams | 116268 | East Berlin and Stoney Pt Int | 234 | 027 | Safety Improvement | ROW | HSIP | 2029-01-01 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Adams | 8 | Adams | 116268 | East Berlin and Stoney Pt Int | 234 | 027 | Safety Improvement | UTL | HSIP | 2029-01-01 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Adams | 8 | Adams | 116268 | East Berlin and Stoney Pt Int | 234 | 027 | Safety Improvement | CON | HSIP | 2029-01-01 |  | 0 | 0 | 648130 | 1019000 | 1019000 | 1019000 | 810060 | 0 | 0 | 4515190
Adams | 8 | Adams | 116269 | Hanover Street and Red Hill Rd Int | 1015 | 019 | Safety Improvement | PE | HSIP | 2027-01-01 |  | 151018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151018
Adams | 8 | Adams | 116269 | Hanover Street and Red Hill Rd Int | 1015 | 019 | Safety Improvement | FD | HSIP | 2027-01-01 |  | 0 | 31060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31060
Adams | 8 | Adams | 116269 | Hanover Street and Red Hill Rd Int | 1015 | 019 | Safety Improvement | ROW | HSIP | 2027-01-01 |  | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
Adams | 8 | Adams | 116269 | Hanover Street and Red Hill Rd Int | 1015 | 019 | Safety Improvement | UTL | HSIP | 2027-01-01 |  | 0 | 23620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23620
Adams | 8 | Adams | 116269 | Hanover Street and Red Hill Rd Int | 1015 | 019 | Safety Improvement | CON | HSIP | 2027-01-01 |  | 0 | 0 | 370870 | 0 | 0 | 0 | 0 | 0 | 0 | 370870
Adams | 8 | Adams | 116594 | East Berlin Rd and Peepytown Rd Int | 234 | 029 | New Alignment | FD | STP | 2029-01-01 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Adams | 8 | Adams | 116594 | East Berlin Rd and Peepytown Rd Int | 234 | 029 | New Alignment | ROW | STP | 2029-01-01 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Adams | 8 | Adams | 116594 | East Berlin Rd and Peepytown Rd Int | 234 | 029 | New Alignment | UTL | STP | 2029-01-01 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Adams | 8 | Adams | 116594 | East Berlin Rd and Peepytown Rd Int | 234 | 029 | New Alignment | CON | STP | 2029-01-01 |  | 0 | 0 | 1133575 | 1002425 | 1000000 | 0 | 0 | 0 | 0 | 3136000
Adams | 8 | Adams | 116595 | US 15 Preservation NorthBound | 15 | 059 | Highway Restoration | CON | BRIP | 2023-12-14 | 2023-12-14 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Adams | 8 | Adams | 116595 | US 15 Preservation NorthBound | 15 | 059 | Highway Restoration | CON | NHPP | 2023-12-14 | 2023-12-14 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Adams | 8 | Adams | 117174 | Cunningham Rd ovr Trib Marsh Creek | 3008 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 232000 | 0 | 0 | 0 | 0 | 0 | 232000
Adams | 8 | Adams | 117174 | Cunningham Rd ovr Trib Marsh Creek | 3008 | 0 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 185000 | 0 | 0 | 0 | 0 | 185000
Adams | 8 | Adams | 117174 | Cunningham Rd ovr Trib Marsh Creek | 3008 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 634000 | 0 | 0 | 0 | 634000
Adams | 8 | Adams | 117593 | Biglerville Rd and Goldenville Rd Int | 34 | 066 | Safety Improvement | CON | HSIP |  |  | 0 | 37011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37011
Adams | 8 | Adams | 119288 | Carbon Reduction Program (CRP) Hanover RSL |  |  | Reserve Line Item | CON | CRP |  |  | 385000 | 395000 | 395000 | 395000 | 395000 | 395000 | 395000 | 395000 | 1581000 | 4731000
Adams | 8 | Adams | 119288 | Carbon Reduction Program (CRP) Hanover RSL |  |  | Reserve Line Item | CON | CRPU |  |  | 263807 | 269103 | 269103 | 269103 | 0 | 0 | 0 | 0 | 0 | 1071116
Adams | 8 | Adams | 122312 | US 15 Paving | 15 | 061 | Highway Restoration | CON | NHPP | 2026-01-08 | 2026-01-08 | 2757000 | 743000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000
Adams | 8 | Cumberland | 118734 | A-409 Bridge Maint Contract 2024-2027 | 11 | 0 | Reserve Line Item | CON | 185 | 2024-01-25 | 2024-01-25 | 975000 | 340001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1315001
Altoona | 9 | Blair | 21905 | T-349 over Frankstown Branch Juniata River | 7206 | 349 | Bridge Removal | PE | BOF | 2027-12-09 |  | 28336 | 144000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172336
Altoona | 9 | Blair | 21905 | T-349 over Frankstown Branch Juniata River | 7206 | 349 | Bridge Removal | PE | 183 | 2027-12-09 |  | 5313 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32313
Altoona | 9 | Blair | 21905 | T-349 over Frankstown Branch Juniata River | 7206 | 349 | Bridge Removal | PE | LOC | 2027-12-09 |  | 1771 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10771
Altoona | 9 | Blair | 21905 | T-349 over Frankstown Branch Juniata River | 7206 | 349 | Bridge Removal | FD | BOF | 2027-12-09 |  | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68000
Altoona | 9 | Blair | 21905 | T-349 over Frankstown Branch Juniata River | 7206 | 349 | Bridge Removal | FD | 183 | 2027-12-09 |  | 12750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12750
Altoona | 9 | Blair | 21905 | T-349 over Frankstown Branch Juniata River | 7206 | 349 | Bridge Removal | FD | LOC | 2027-12-09 |  | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4250
Altoona | 9 | Blair | 21905 | T-349 over Frankstown Branch Juniata River | 7206 | 349 | Bridge Removal | ROW | BOF | 2027-12-09 |  | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
Altoona | 9 | Blair | 21905 | T-349 over Frankstown Branch Juniata River | 7206 | 349 | Bridge Removal | ROW | 183 | 2027-12-09 |  | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250
Altoona | 9 | Blair | 21905 | T-349 over Frankstown Branch Juniata River | 7206 | 349 | Bridge Removal | UTL | BOF | 2027-12-09 |  | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400
Altoona | 9 | Blair | 21905 | T-349 over Frankstown Branch Juniata River | 7206 | 349 | Bridge Removal | UTL | 185 | 2027-12-09 |  | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900
Altoona | 9 | Blair | 21905 | T-349 over Frankstown Branch Juniata River | 7206 | 349 | Bridge Removal | CON | BOF | 2027-12-09 |  | 0 | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
Altoona | 9 | Blair | 21905 | T-349 over Frankstown Branch Juniata River | 7206 | 349 | Bridge Removal | CON | 183 | 2027-12-09 |  | 0 | 0 | 67500 | 0 | 0 | 0 | 0 | 0 | 0 | 67500
Altoona | 9 | Blair | 21905 | T-349 over Frankstown Branch Juniata River | 7206 | 349 | Bridge Removal | CON | LOC | 2027-12-09 |  | 0 | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 22500
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | PE | BOF | 2028-11-09 |  | 100438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100438
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | PE | 183 | 2028-11-09 |  | 18832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18832
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | PE | LOC | 2028-11-09 |  | 6278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6278
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | FD | BOF | 2028-11-09 |  | 201689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201689
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | FD | 183 | 2028-11-09 |  | 37817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37817
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | FD | LOC | 2028-11-09 |  | 12606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12606
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | ROW | BOF | 2028-11-09 |  | 46200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46200
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | ROW | 183 | 2028-11-09 |  | 8663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | ROW | LOC | 2028-11-09 |  | 2888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2888
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | UTL | BOF | 2028-11-09 |  | 80000 | 2645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82645
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | UTL | 183 | 2028-11-09 |  | 15000 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15496
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | UTL | LOC | 2028-11-09 |  | 5000 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5164
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | CON | BOF | 2028-11-09 |  | 0 | 360000 | 423906 | 383085 | 0 | 0 | 0 | 0 | 0 | 1166991
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | CON | 183 | 2028-11-09 |  | 0 | 67500 | 79482 | 71828 | 0 | 0 | 0 | 0 | 0 | 218810
Altoona | 9 | Blair | 21946 | 13th Street Over Gillans Run | 7402 | 13S | Bridge Restoration | CON | LOC | 2028-11-09 |  | 0 | 22500 | 26494 | 0 | 0 | 0 | 0 | 0 | 0 | 48994
Altoona | 9 | Blair | 21952 | PA36 Brush Run Bridge | 36 | 29B | Bridge Replacement | ROW | BRIP | 2016-07-14 | 2016-07-14 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Altoona | 9 | Blair | 21964 | Blair Gap Run Bridge | 3013 | 09B | Bridge Replacement | CON | 185 | 2025-01-09 | 2025-01-09 | 389060 | 793223 | 785255 | 1556288.9 | 0 | 0 | 0 | 0 | 0 | 3523826.9
Altoona | 9 | Blair | 21988 | SR 4041 over Nittany and Bald Eagle RR | 4041 | 05B | Bridge Restoration | UTL | BRIP | 2027-10-07 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Altoona | 9 | Blair | 21988 | SR 4041 over Nittany and Bald Eagle RR | 4041 | 05B | Bridge Restoration | CON | BRIP | 2027-10-07 |  | 0 | 0 | 0 | 540244 | 0 | 0 | 0 | 0 | 0 | 540244
Altoona | 9 | Blair | 22076 | T-364 over Bobs Creek | 7209 | 364 | Bridge Restoration | PE | BOF | 2029-10-18 |  | 0 | 0 | 238400 | 0 | 0 | 0 | 0 | 0 | 0 | 238400
Altoona | 9 | Blair | 22076 | T-364 over Bobs Creek | 7209 | 364 | Bridge Restoration | PE | 183 | 2029-10-18 |  | 0 | 0 | 28950 | 15750 | 0 | 0 | 0 | 0 | 0 | 44700
Altoona | 9 | Blair | 22076 | T-364 over Bobs Creek | 7209 | 364 | Bridge Restoration | PE | LOC | 2029-10-18 |  | 0 | 0 | 14900 | 0 | 0 | 0 | 0 | 0 | 0 | 14900
Altoona | 9 | Blair | 22076 | T-364 over Bobs Creek | 7209 | 364 | Bridge Restoration | FD | BOF | 2029-10-18 |  | 0 | 0 | 0 | 154400 | 0 | 0 | 0 | 0 | 0 | 154400
Altoona | 9 | Blair | 22076 | T-364 over Bobs Creek | 7209 | 364 | Bridge Restoration | FD | 183 | 2029-10-18 |  | 0 | 0 | 0 | 28950 | 0 | 0 | 0 | 0 | 0 | 28950
Altoona | 9 | Blair | 22076 | T-364 over Bobs Creek | 7209 | 364 | Bridge Restoration | FD | LOC | 2029-10-18 |  | 0 | 0 | 0 | 9650 | 0 | 0 | 0 | 0 | 0 | 9650
Altoona | 9 | Blair | 22076 | T-364 over Bobs Creek | 7209 | 364 | Bridge Restoration | ROW | BOF | 2029-10-18 |  | 0 | 0 | 0 | 52000 | 0 | 0 | 0 | 0 | 0 | 52000
Altoona | 9 | Blair | 22076 | T-364 over Bobs Creek | 7209 | 364 | Bridge Restoration | ROW | 183 | 2029-10-18 |  | 0 | 0 | 0 | 9750 | 0 | 0 | 0 | 0 | 0 | 9750
Altoona | 9 | Blair | 22076 | T-364 over Bobs Creek | 7209 | 364 | Bridge Restoration | ROW | LOC | 2029-10-18 |  | 0 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 3250
Altoona | 9 | Blair | 22077 | W Chestnut Ave over Mill Run | 7301 | WCA | Bridge Restoration | PE | BOF | 2028-02-03 |  | 392000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392000
Altoona | 9 | Blair | 22077 | W Chestnut Ave over Mill Run | 7301 | WCA | Bridge Restoration | PE | 183 | 2028-02-03 |  | 73500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73500
Altoona | 9 | Blair | 22077 | W Chestnut Ave over Mill Run | 7301 | WCA | Bridge Restoration | PE | LOC | 2028-02-03 |  | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24500
Altoona | 9 | Blair | 22077 | W Chestnut Ave over Mill Run | 7301 | WCA | Bridge Restoration | FD | BOF | 2028-02-03 |  | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Altoona | 9 | Blair | 22077 | W Chestnut Ave over Mill Run | 7301 | WCA | Bridge Restoration | FD | 183 | 2028-02-03 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Altoona | 9 | Blair | 22077 | W Chestnut Ave over Mill Run | 7301 | WCA | Bridge Restoration | FD | LOC | 2028-02-03 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Altoona | 9 | Blair | 22077 | W Chestnut Ave over Mill Run | 7301 | WCA | Bridge Restoration | ROW | BOF | 2028-02-03 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Altoona | 9 | Blair | 22077 | W Chestnut Ave over Mill Run | 7301 | WCA | Bridge Restoration | ROW | 183 | 2028-02-03 |  | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
Altoona | 9 | Blair | 22077 | W Chestnut Ave over Mill Run | 7301 | WCA | Bridge Restoration | UTL | BOF | 2028-02-03 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Altoona | 9 | Blair | 22077 | W Chestnut Ave over Mill Run | 7301 | WCA | Bridge Restoration | UTL | 183 | 2028-02-03 |  | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
Altoona | 9 | Blair | 22077 | W Chestnut Ave over Mill Run | 7301 | WCA | Bridge Restoration | CON | BOF | 2028-02-03 |  | 0 | 0 | 0 | 371515 | 668455 | 0 | 0 | 0 | 0 | 1039970
Altoona | 9 | Blair | 22077 | W Chestnut Ave over Mill Run | 7301 | WCA | Bridge Restoration | CON | 183 | 2028-02-03 |  | 0 | 0 | 0 | 69659 | 125335 | 0 | 0 | 0 | 0 | 194994
Altoona | 9 | Blair | 22083 | SR 4027 over UNT to Bald Eagle Creek | 4027 | 11B | Bridge Replacement | FD | 185 | 2026-08-27 |  | 206707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206707
Altoona | 9 | Blair | 22083 | SR 4027 over UNT to Bald Eagle Creek | 4027 | 11B | Bridge Replacement | ROW | 185 | 2026-08-27 |  | 24135 | 15865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Altoona | 9 | Blair | 22083 | SR 4027 over UNT to Bald Eagle Creek | 4027 | 11B | Bridge Replacement | UTL | 185 | 2026-08-27 |  | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
Altoona | 9 | Blair | 22083 | SR 4027 over UNT to Bald Eagle Creek | 4027 | 11B | Bridge Replacement | CON | BRIP | 2026-08-27 |  | 0 | 496750 | 673505 | 0 | 0 | 0 | 0 | 0 | 0 | 1170255
Altoona | 9 | Blair | 22086 | Roaring Spring Cabbage Cr | 867 | 01B | Bridge Replacement | FD | 185 | 2027-12-09 |  | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000
Altoona | 9 | Blair | 22086 | Roaring Spring Cabbage Cr | 867 | 01B | Bridge Replacement | ROW | BRIP | 2027-12-09 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Altoona | 9 | Blair | 22086 | Roaring Spring Cabbage Cr | 867 | 01B | Bridge Replacement | UTL | 185 | 2027-12-09 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 22086 | Roaring Spring Cabbage Cr | 867 | 01B | Bridge Replacement | CON | BRIP | 2027-12-09 |  | 0 | 0 | 547304 | 281973 | 0 | 0 | 0 | 0 | 0 | 829277
Altoona | 9 | Blair | 22103 | SR 164 over UNT Plum Creek | 164 | 14B | Bridge Replacement | FD | 185 | 2027-12-09 |  | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
Altoona | 9 | Blair | 22103 | SR 164 over UNT Plum Creek | 164 | 14B | Bridge Replacement | CON | 185 | 2027-12-09 |  | 0 | 0 | 0 | 100000 | 348961 | 21039 | 0 | 0 | 0 | 470000
Altoona | 9 | Blair | 22127 | Three Springs Run Bridge | 4023 | 03B | Bridge Restoration | ROW | 185 | 2027-09-30 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Altoona | 9 | Blair | 22127 | Three Springs Run Bridge | 4023 | 03B | Bridge Restoration | CON | 185 | 2027-09-30 |  | 0 | 0 | 922000.69 | 0 | 0 | 0 | 0 | 0 | 0 | 922000.69
Altoona | 9 | Blair | 22617 | T-456 Old Mill Run Bridge | 7210 | 456 | Bridge Replacement | FD | BOF | 2026-03-12 | 2026-03-12 | 144000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144000
Altoona | 9 | Blair | 22617 | T-456 Old Mill Run Bridge | 7210 | 456 | Bridge Replacement | FD | 183 | 2026-03-12 | 2026-03-12 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000
Altoona | 9 | Blair | 22617 | T-456 Old Mill Run Bridge | 7210 | 456 | Bridge Replacement | FD | LOC | 2026-03-12 | 2026-03-12 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000
Altoona | 9 | Blair | 22617 | T-456 Old Mill Run Bridge | 7210 | 456 | Bridge Replacement | ROW | BOF | 2026-03-12 | 2026-03-12 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Altoona | 9 | Blair | 22617 | T-456 Old Mill Run Bridge | 7210 | 456 | Bridge Replacement | ROW | 183 | 2026-03-12 | 2026-03-12 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
Altoona | 9 | Blair | 22617 | T-456 Old Mill Run Bridge | 7210 | 456 | Bridge Replacement | ROW | LOC | 2026-03-12 | 2026-03-12 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250
Altoona | 9 | Blair | 22617 | T-456 Old Mill Run Bridge | 7210 | 456 | Bridge Replacement | UTL | BOF | 2026-03-12 | 2026-03-12 | 84000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84000
Altoona | 9 | Blair | 22617 | T-456 Old Mill Run Bridge | 7210 | 456 | Bridge Replacement | UTL | 183 | 2026-03-12 | 2026-03-12 | 15750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15750
Altoona | 9 | Blair | 22617 | T-456 Old Mill Run Bridge | 7210 | 456 | Bridge Replacement | UTL | LOC | 2026-03-12 | 2026-03-12 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250
Altoona | 9 | Blair | 22617 | T-456 Old Mill Run Bridge | 7210 | 456 | Bridge Replacement | CON | BOF | 2026-03-12 | 2026-03-12 | 405548 | 351252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 756800
Altoona | 9 | Blair | 22617 | T-456 Old Mill Run Bridge | 7210 | 456 | Bridge Replacement | CON | 183 | 2026-03-12 | 2026-03-12 | 88473 | 53427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141900
Altoona | 9 | Blair | 22617 | T-456 Old Mill Run Bridge | 7210 | 456 | Bridge Replacement | CON | LOC | 2026-03-12 | 2026-03-12 | 29490 | 17810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47300
Altoona | 9 | Blair | 50604 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | BOF |  |  | 0 | 175308 | 137623 | 185854 | 0 | 0 | 0 | 0 | 0 | 498785
Altoona | 9 | Blair | 50604 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | BRIP |  |  | 0 | 176078.4 | 259116 | 0 | 0 | 0 | 0 | 0 | 0 | 435194.4
Altoona | 9 | Blair | 50604 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | CRP |  |  | 0 | 0 | 17914 | 0 | 0 | 0 | 0 | 0 | 0 | 17914
Altoona | 9 | Blair | 50604 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | CRPU |  |  | 0 | 205000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205000
Altoona | 9 | Blair | 50604 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | HSIP |  |  | 0 | 10896 | 253929 | 484454 | 282000 | 0 | 282000 | 282000 | 5127000 | 6722279
Altoona | 9 | Blair | 50604 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 198823 | 600000 | 666500 | 2000000 | 2000000 | 1500000 | 5499000 | 12464323
Altoona | 9 | Blair | 50604 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | STP |  |  | 0 | 1316251 | 1084324 | 1007428 | 50000 | 50000 | 834310 | 0 | 553000 | 4895313
Altoona | 9 | Blair | 50604 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | 183 |  |  | 0 | 0 | 15750 | 0 | 0 | 0 | 0 | 0 | 0 | 15750
Altoona | 9 | Blair | 50604 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | 581 |  |  | 0 | 61560 | 550000 | 866273 | 630491 | 0 | 309195 | 1232000 | 1893000 | 5542519
Altoona | 9 | Blair | 50604 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | LOC |  |  | 0 | 53602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53602
Altoona | 9 | Blair | 73194 | SR 4003 Logan Boulevard over NSRR | 4003 | 07B | Bridge Restoration | UTL | 185 | 2026-09-03 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Altoona | 9 | Blair | 73194 | SR 4003 Logan Boulevard over NSRR | 4003 | 07B | Bridge Restoration | CON | NHPP | 2026-09-03 |  | 0 | 111121 | 444625 | 155375 | 0 | 0 | 0 | 0 | 0 | 711121
Altoona | 9 | Blair | 74362 | Tyrone Sink Run Culvert 2 | 453 | 007 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 310000 | 0 | 0 | 0 | 0 | 310000
Altoona | 9 | Blair | 74362 | Tyrone Sink Run Culvert 2 | 453 | 007 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 230000 | 0 | 0 | 0 | 230000
Altoona | 9 | Blair | 74362 | Tyrone Sink Run Culvert 2 | 453 | 007 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
Altoona | 9 | Blair | 74362 | Tyrone Sink Run Culvert 2 | 453 | 007 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
Altoona | 9 | Blair | 74362 | Tyrone Sink Run Culvert 2 | 453 | 007 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 963000 | 0 | 963000
Altoona | 9 | Blair | 75709 | Local Bridge Line Item |  | LBI | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 515200 | 960000 | 960000 | 2880000 | 5315200
Altoona | 9 | Blair | 75709 | Local Bridge Line Item |  | LBI | Reserve Line Item | CON | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 28000 | 180000 | 180000 | 533000 | 921000
Altoona | 9 | Blair | 75709 | Local Bridge Line Item |  | LBI | Reserve Line Item | CON | LOC |  |  | 0 | 0 | 0 | 0 | 0 | 60000 | 60000 | 60000 | 180000 | 360000
Altoona | 9 | Blair | 92607 | SR 3013 Dry Run Bridge | 3013 | 10B | Bridge Replacement | CON | BRIP | 2025-01-09 | 2025-01-09 | 2125921.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2125921.6
Altoona | 9 | Blair | 92642 | Sinking Run Bridge #1 | 1013 | 13B | Bridge Replacement | PE | 185 | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 92642 | Sinking Run Bridge #1 | 1013 | 13B | Bridge Replacement | ROW | 185 | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
Altoona | 9 | Blair | 92642 | Sinking Run Bridge #1 | 1013 | 13B | Bridge Replacement | UTL | 185 | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
Altoona | 9 | Blair | 92642 | Sinking Run Bridge #1 | 1013 | 13B | Bridge Replacement | CON | 185 | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 822007 | 822007
Altoona | 9 | Blair | 92643 | Sinking Run Bridge #3 | 1013 | 14B | Bridge Replacement | PE | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 450000 | 30000 | 0 | 0 | 0 | 480000
Altoona | 9 | Blair | 92643 | Sinking Run Bridge #3 | 1013 | 14B | Bridge Replacement | ROW | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 119000 | 0 | 0 | 119000
Altoona | 9 | Blair | 92643 | Sinking Run Bridge #3 | 1013 | 14B | Bridge Replacement | UTL | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 119000 | 0 | 0 | 119000
Altoona | 9 | Blair | 92643 | Sinking Run Bridge #3 | 1013 | 14B | Bridge Replacement | CON | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2547000 | 450000 | 2997000
Altoona | 9 | Blair | 92644 | Sinking Run Bridge #5 | 1013 | 15B | Bridge Replacement | PE | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 532000 | 0 | 0 | 0 | 532000
Altoona | 9 | Blair | 92644 | Sinking Run Bridge #5 | 1013 | 15B | Bridge Replacement | ROW | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000
Altoona | 9 | Blair | 92644 | Sinking Run Bridge #5 | 1013 | 15B | Bridge Replacement | UTL | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000
Altoona | 9 | Blair | 92644 | Sinking Run Bridge #5 | 1013 | 15B | Bridge Replacement | CON | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3138000 | 3138000
Altoona | 9 | Blair | 92661 | PA764 Culvert Replacement | 764 | 01B | Bridge Restoration | PE | 185 | 2031-02-06 |  | 0 | 0 | 0 | 0 | 115345 | 324655 | 0 | 0 | 0 | 440000
Altoona | 9 | Blair | 92661 | PA764 Culvert Replacement | 764 | 01B | Bridge Restoration | FD | 185 | 2031-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 320000
Altoona | 9 | Blair | 92661 | PA764 Culvert Replacement | 764 | 01B | Bridge Restoration | ROW | 185 | 2031-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
Altoona | 9 | Blair | 92661 | PA764 Culvert Replacement | 764 | 01B | Bridge Restoration | UTL | 185 | 2031-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
Altoona | 9 | Blair | 92661 | PA764 Culvert Replacement | 764 | 01B | Bridge Restoration | CON | 185 | 2031-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1240000 | 1037825 | 2277825
Altoona | 9 | Blair | 92662 | PA 865 over Lloydsville Run | 865 | 06B | Bridge Restoration | PE | 185 | 2030-10-24 |  | 0 | 1211 | 248789 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Altoona | 9 | Blair | 92662 | PA 865 over Lloydsville Run | 865 | 06B | Bridge Restoration | FD | 185 | 2030-10-24 |  | 0 | 0 | 0 | 90824 | 24000 | 0 | 0 | 0 | 0 | 114824
Altoona | 9 | Blair | 92662 | PA 865 over Lloydsville Run | 865 | 06B | Bridge Restoration | CON | 185 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 202000 | 828000 | 0 | 0 | 0 | 1030000
Altoona | 9 | Blair | 94437 | Hburg Brush Run Bridge | 36 | 41B | Bridge Restoration | CON | BRIP | 2026-09-03 |  | 107465.4 | 1036992.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1144458
Altoona | 9 | Blair | 94441 | SR 2017 over Yellow Spring Run | 2017 | 03B | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 94441 | SR 2017 over Yellow Spring Run | 2017 | 03B | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
Altoona | 9 | Blair | 94441 | SR 2017 over Yellow Spring Run | 2017 | 03B | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
Altoona | 9 | Blair | 94441 | SR 2017 over Yellow Spring Run | 2017 | 03B | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782864 | 782864
Altoona | 9 | Blair | 94442 | SR 2017 over Fox Run | 2017 | 05B | Bridge Replacement | PE | 185 | 2029-02-08 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 94442 | SR 2017 over Fox Run | 2017 | 05B | Bridge Replacement | ROW | 185 | 2029-02-08 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 94442 | SR 2017 over Fox Run | 2017 | 05B | Bridge Replacement | UTL | 185 | 2029-02-08 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 94442 | SR 2017 over Fox Run | 2017 | 05B | Bridge Replacement | CON | 185 | 2029-02-08 |  | 0 | 0 | 0 | 0 | 950000 | 0 | 0 | 0 | 0 | 950000
Altoona | 9 | Blair | 94443 | SR 3006 over Boiling Spring Run | 3006 | 01B | Bridge Restoration | PE | 185 | 2028-01-27 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 94443 | SR 3006 over Boiling Spring Run | 3006 | 01B | Bridge Restoration | ROW | 185 | 2028-01-27 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 94443 | SR 3006 over Boiling Spring Run | 3006 | 01B | Bridge Restoration | UTL | 185 | 2028-01-27 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
Altoona | 9 | Blair | 94443 | SR 3006 over Boiling Spring Run | 3006 | 01B | Bridge Restoration | CON | 185 | 2028-01-27 |  | 0 | 0 | 0 | 43571 | 456429 | 0 | 0 | 0 | 0 | 500000
Altoona | 9 | Blair | 94446 | SR 4015 Riggles Gap Run | 4015 | 05B | Bridge Restoration | ROW | BRIP | 2028-04-06 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 94446 | SR 4015 Riggles Gap Run | 4015 | 05B | Bridge Restoration | UTL | BRIP | 2028-04-06 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 94446 | SR 4015 Riggles Gap Run | 4015 | 05B | Bridge Restoration | CON | BRIP | 2028-04-06 |  | 0 | 0 | 0 | 245000 | 0 | 0 | 0 | 0 | 0 | 245000
Altoona | 9 | Blair | 96410 | SR 2007 - SR 2014 to US 22 | 2007 | 004 | Highway Restoration | CON | 581 | 2025-11-06 | 2025-11-06 | 0 | 12233 | 196602 | 122805 | 277698 | 0 | 0 | 0 | 0 | 609338
Altoona | 9 | Blair | 96456 | SR 3003 - PA 164 to T-611 | 3003 | 000 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 200000 | 0 | 950000
Altoona | 9 | Blair | 96456 | SR 3003 - PA 164 to T-611 | 3003 | 000 | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 550000
Altoona | 9 | Blair | 96456 | SR 3003 - PA 164 to T-611 | 3003 | 000 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100000 | 4100000
Altoona | 9 | Blair | 98732 | PA 453 Sink Run Culvert | 453 | 14B | Bridge Replacement | CON | 185 | 2024-10-10 | 2024-10-10 | 226168 | 512818.69 | 295207.31 | 187129 | 128000 | 0 | 0 | 0 | 0 | 1349323
Altoona | 9 | Blair | 98737 | SR 1001 over Tributary to Mill Run | 1001 | 01B | Bridge Restoration | FD | 185 | 2029-12-13 |  | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0 | 170000
Altoona | 9 | Blair | 98737 | SR 1001 over Tributary to Mill Run | 1001 | 01B | Bridge Restoration | ROW | 185 | 2029-12-13 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 98737 | SR 1001 over Tributary to Mill Run | 1001 | 01B | Bridge Restoration | UTL | 185 | 2029-12-13 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 98737 | SR 1001 over Tributary to Mill Run | 1001 | 01B | Bridge Restoration | CON | 185 | 2029-12-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1096000 | 370000 | 0 | 1466000
Altoona | 9 | Blair | 106320 | EVRR Claysburg Line Corridor South |  |  | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 50000 | 1400000 | 350000 | 0 | 0 | 0 | 0 | 0 | 1800000
Altoona | 9 | Blair | 107234 | SR 4013 - Tenth Street to Greely Street | 4013 | 007 | Highway Restoration | CON | CRP | 2022-12-08 | 2022-12-08 | 197503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197503
Altoona | 9 | Blair | 107493 | Frankstown Road to Mill Run Road | 36 | 034 | Highway Restoration | CON | STP | 2024-09-12 | 2024-09-12 | 4036058 | 488867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4524925
Altoona | 9 | Blair | 108201 | SR 1009 - SR 1021 to PA 36 | 1009 | 10S | Safety Improvement | CON | STP | 2023-09-14 | 2023-09-14 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Altoona | 9 | Blair | 108201 | SR 1009 - SR 1021 to PA 36 | 1009 | 10S | Safety Improvement | CON | 581 | 2023-09-14 | 2023-09-14 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Altoona | 9 | Blair | 108203 | SR 4003 - PA 36 to SR 4024 | 4003 | 005 | Highway Restoration | PE | NHPP | 2027-10-07 |  | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000
Altoona | 9 | Blair | 108203 | SR 4003 - PA 36 to SR 4024 | 4003 | 005 | Highway Restoration | CON | NHPP | 2027-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 2500000 | 3000000
Altoona | 9 | Blair | 108209 | PA 453 - Huntingdon Co Line to I-99 | 453 | 015 | Highway Restoration | PE | 581 | 2028-12-14 |  | 450000 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Altoona | 9 | Blair | 108209 | PA 453 - Huntingdon Co Line to I-99 | 453 | 015 | Highway Restoration | FD | 581 | 2028-12-14 |  | 0 | 0 | 355000 | 0 | 0 | 0 | 0 | 0 | 0 | 355000
Altoona | 9 | Blair | 108209 | PA 453 - Huntingdon Co Line to I-99 | 453 | 015 | Highway Restoration | ROW | 581 | 2028-12-14 |  | 0 | 0 | 67000 | 0 | 0 | 0 | 0 | 0 | 0 | 67000
Altoona | 9 | Blair | 108209 | PA 453 - Huntingdon Co Line to I-99 | 453 | 015 | Highway Restoration | UTL | 581 | 2028-12-14 |  | 0 | 0 | 67000 | 0 | 0 | 0 | 0 | 0 | 0 | 67000
Altoona | 9 | Blair | 108209 | PA 453 - Huntingdon Co Line to I-99 | 453 | 015 | Highway Restoration | CON | 581 | 2028-12-14 |  | 0 | 0 | 0 | 355549 | 1027845 | 2783000 | 1000000 | 0 | 0 | 5166394
Altoona | 9 | Blair | 108219 | PA 453 - I-99 to Beastons Road | 453 | 016 | Highway Restoration | ROW | 581 | 2025-09-11 | 2025-09-11 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Altoona | 9 | Blair | 108219 | PA 453 - I-99 to Beastons Road | 453 | 016 | Highway Restoration | UTL | 581 | 2025-09-11 | 2025-09-11 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Altoona | 9 | Blair | 108219 | PA 453 - I-99 to Beastons Road | 453 | 016 | Highway Restoration | CON | PRTCT | 2025-09-11 | 2025-09-11 | 5052801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5052801
Altoona | 9 | Blair | 108219 | PA 453 - I-99 to Beastons Road | 453 | 016 | Highway Restoration | CON | 581 | 2025-09-11 | 2025-09-11 | 0 | 775767 | 2230593 | 1524316 | 95226 | 0 | 0 | 0 | 0 | 4625902
Altoona | 9 | Blair | 108221 | PA 36 - US 22 to Plank Road | 36 | 043 | Highway Restoration | UTL | 581 | 2025-12-11 | 2025-12-11 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 108221 | PA 36 - US 22 to Plank Road | 36 | 043 | Highway Restoration | CON | NHPP | 2025-12-11 | 2025-12-11 | 1787310 | 2855866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4643176
Altoona | 9 | Blair | 108221 | PA 36 - US 22 to Plank Road | 36 | 043 | Highway Restoration | CON | STP | 2025-12-11 | 2025-12-11 | 0 | 0 | 1350724 | 0 | 0 | 0 | 0 | 0 | 0 | 1350724
Altoona | 9 | Blair | 108226 | SR 4031 - PA 453 to Snyder Twp Line | 4031 | 001 | Highway Restoration | PE | 581 | 2029-07-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 150000 | 0 | 250000
Altoona | 9 | Blair | 108226 | SR 4031 - PA 453 to Snyder Twp Line | 4031 | 001 | Highway Restoration | CON | 581 | 2029-07-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880000 | 880000
Altoona | 9 | Blair | 109160 | T-376 over Oldtown Run | 7205 | 376 | Bridge Restoration | PE | BOF | 2029-08-09 |  | 0 | 328000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328000
Altoona | 9 | Blair | 109160 | T-376 over Oldtown Run | 7205 | 376 | Bridge Restoration | PE | 183 | 2029-08-09 |  | 0 | 61500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61500
Altoona | 9 | Blair | 109160 | T-376 over Oldtown Run | 7205 | 376 | Bridge Restoration | PE | LOC | 2029-08-09 |  | 0 | 20500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20500
Altoona | 9 | Blair | 109160 | T-376 over Oldtown Run | 7205 | 376 | Bridge Restoration | FD | BOF | 2029-08-09 |  | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000
Altoona | 9 | Blair | 109160 | T-376 over Oldtown Run | 7205 | 376 | Bridge Restoration | FD | 183 | 2029-08-09 |  | 0 | 0 | 0 | 33750 | 0 | 0 | 0 | 0 | 0 | 33750
Altoona | 9 | Blair | 109160 | T-376 over Oldtown Run | 7205 | 376 | Bridge Restoration | ROW | BOF | 2029-08-09 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Altoona | 9 | Blair | 109160 | T-376 over Oldtown Run | 7205 | 376 | Bridge Restoration | ROW | 183 | 2029-08-09 |  | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750
Altoona | 9 | Blair | 109160 | T-376 over Oldtown Run | 7205 | 376 | Bridge Restoration | UTL | BOF | 2029-08-09 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Altoona | 9 | Blair | 109160 | T-376 over Oldtown Run | 7205 | 376 | Bridge Restoration | UTL | 183 | 2029-08-09 |  | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750
Altoona | 9 | Blair | 109160 | T-376 over Oldtown Run | 7205 | 376 | Bridge Restoration | CON | BOF | 2029-08-09 |  | 0 | 0 | 0 | 0 | 927419 | 0 | 0 | 0 | 0 | 927419
Altoona | 9 | Blair | 109160 | T-376 over Oldtown Run | 7205 | 376 | Bridge Restoration | CON | 183 | 2029-08-09 |  | 0 | 0 | 0 | 0 | 173891 | 0 | 0 | 0 | 0 | 173891
Altoona | 9 | Blair | 109162 | T-484 over Sinking Run | 7214 | 484 | Bridge Restoration | CON | BOF | 2026-12-10 |  | 0 | 0 | 211860 | 0 | 0 | 0 | 0 | 0 | 0 | 211860
Altoona | 9 | Blair | 109167 | South 12th Street Bridge | 7301 | 12S | Bridge Restoration | CON | BOF | 2024-07-11 | 2024-10-10 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Altoona | 9 | Blair | 109168 | 13th Street Over Brush Run | 7301 | 13S | Bridge Restoration | CON | BOF | 2026-12-10 |  | 0 | 0 | 211234 | 0 | 0 | 0 | 0 | 0 | 0 | 211234
Altoona | 9 | Blair | 109169 | South 16th Street Bridge | 7301 | 16S | Bridge Restoration | CON | BOF | 2024-07-11 | 2024-10-10 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Altoona | 9 | Blair | 110134 | PA 36 - PA 164 Intersection Improvements | 36 | 035 | Safety Improvement | CON | HSIP | 2025-01-09 | 2025-01-09 | 1641972 | 473028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2115000
Altoona | 9 | Blair | 110134 | PA 36 - PA 164 Intersection Improvements | 36 | 035 | Safety Improvement | CON | STP | 2025-01-09 | 2025-01-09 | 0 | 214532.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214532.41
Altoona | 9 | Blair | 110159 | PA 764 - 17th St to Pleasant Valley | 764 | 024 | Highway Restoration | PE | 581 | 2031-07-10 |  | 0 | 0 | 0 | 470349 | 22805 | 0 | 0 | 0 | 0 | 493154
Altoona | 9 | Blair | 110159 | PA 764 - 17th St to Pleasant Valley | 764 | 024 | Highway Restoration | CON | STP | 2031-07-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 1200000 | 0 | 1950000
Altoona | 9 | Blair | 111991 | SR 3001 over Bobs Creek | 3001 | 02B | Bridge Restoration | PE | 185 | 2035-01-04 |  | 0 | 0 | 0 | 150000 | 100000 | 0 | 0 | 0 | 0 | 250000
Altoona | 9 | Blair | 111991 | SR 3001 over Bobs Creek | 3001 | 02B | Bridge Restoration | FD | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
Altoona | 9 | Blair | 111991 | SR 3001 over Bobs Creek | 3001 | 02B | Bridge Restoration | ROW | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 111991 | SR 3001 over Bobs Creek | 3001 | 02B | Bridge Restoration | UTL | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 111991 | SR 3001 over Bobs Creek | 3001 | 02B | Bridge Restoration | CON | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 638000 | 0 | 0 | 638000
Altoona | 9 | Blair | 111997 | SR 2013 over Schmucker Run | 2013 | 02B | Bridge Restoration | PE | 185 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 111997 | SR 2013 over Schmucker Run | 2013 | 02B | Bridge Restoration | ROW | 185 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
Altoona | 9 | Blair | 111997 | SR 2013 over Schmucker Run | 2013 | 02B | Bridge Restoration | UTL | 185 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
Altoona | 9 | Blair | 111997 | SR 2013 over Schmucker Run | 2013 | 02B | Bridge Restoration | CON | 185 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825921 | 825921
Altoona | 9 | Blair | 112021 | PA 866 - Williamsburg Resurfacing | 866 | 008 | Stormwater Management | ROW | 581 | 2025-12-11 | 2025-12-11 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
Altoona | 9 | Blair | 112021 | PA 866 - Williamsburg Resurfacing | 866 | 008 | Stormwater Management | UTL | 581 | 2025-12-11 | 2025-12-11 | 0 | 431000 | 47805 | 0 | 0 | 0 | 0 | 0 | 0 | 478805
Altoona | 9 | Blair | 112021 | PA 866 - Williamsburg Resurfacing | 866 | 008 | Stormwater Management | CON | 581 | 2025-12-11 | 2025-12-11 | 1792000 | 1161440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2953440
Altoona | 9 | Blair | 114147 | SR 4003 Logan Boulevard over Mill Run | 4003 | 06B | Bridge Restoration | UTL | 185 | 2026-09-03 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Altoona | 9 | Blair | 114147 | SR 4003 Logan Boulevard over Mill Run | 4003 | 06B | Bridge Restoration | CON | BRIP | 2026-09-03 |  | 0 | 575000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575000
Altoona | 9 | Blair | 114148 | Tyrone McCoy Street over I-99 Rehab | 4104 | 01B | Bridge Restoration | UTL | BRIP | 2026-10-22 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Altoona | 9 | Blair | 114148 | Tyrone McCoy Street over I-99 Rehab | 4104 | 01B | Bridge Restoration | CON | BRIP | 2026-10-22 |  | 0 | 0 | 271973 | 711481 | 0 | 0 | 0 | 0 | 0 | 983454
Altoona | 9 | Blair | 114149 | Convention Center Blvd Brush Run | 7201 | 201 | Bridge Restoration | CON | BRIP | 2025-11-06 | 2025-11-06 | 248612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248612
Altoona | 9 | Blair | 114149 | Convention Center Blvd Brush Run | 7201 | 201 | Bridge Restoration | CON | 183 | 2025-11-06 | 2025-11-06 | 30865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30865
Altoona | 9 | Blair | 114149 | Convention Center Blvd Brush Run | 7201 | 201 | Bridge Restoration | CON | LOC | 2025-11-06 | 2025-11-06 | 15538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15538
Altoona | 9 | Blair | 114151 | 37th Street over Norfolk Southern RR | 7301 | 301 | Bridge Restoration | CON | BOF | 2026-09-03 |  | 242688 | 230672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 473360
Altoona | 9 | Blair | 114151 | 37th Street over Norfolk Southern RR | 7301 | 301 | Bridge Restoration | CON | 183 | 2026-09-03 |  | 45504 | 43251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88755
Altoona | 9 | Blair | 114151 | 37th Street over Norfolk Southern RR | 7301 | 301 | Bridge Restoration | CON | LOC | 2026-09-03 |  | 4630 | 24955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29585
Altoona | 9 | Blair | 116905 | PA 36 - SR 4005 to Cambria County Line | 36 | 044 | Highway Restoration | UTL | 581 | 2027-12-09 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Altoona | 9 | Blair | 116905 | PA 36 - SR 4005 to Cambria County Line | 36 | 044 | Highway Restoration | CON | 581 | 2027-12-09 |  | 0 | 0 | 0 | 413260 | 728935 | 1022805 | 0 | 0 | 0 | 2165000
Altoona | 9 | Blair | 116911 | PA 866 - US 22 to High Street | 866 | 009 | Highway Restoration | CON | STP | 2027-06-24 |  | 0 | 384000 | 0 | 1255572 | 1866427 | 0 | 0 | 0 | 0 | 3505999
Altoona | 9 | Blair | 117018 | Decker Hollow Road Over Vansoyoc Run | 4033 | 02B | Bridge Replacement | FD | BOF | 2026-08-27 |  | 206707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206707
Altoona | 9 | Blair | 117018 | Decker Hollow Road Over Vansoyoc Run | 4033 | 02B | Bridge Replacement | ROW | BOF | 2026-08-27 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Altoona | 9 | Blair | 117018 | Decker Hollow Road Over Vansoyoc Run | 4033 | 02B | Bridge Replacement | UTL | BOF | 2026-08-27 |  | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
Altoona | 9 | Blair | 117018 | Decker Hollow Road Over Vansoyoc Run | 4033 | 02B | Bridge Replacement | CON | BOF | 2026-08-27 |  | 89996 | 858401 | 275850 | 0 | 0 | 0 | 0 | 0 | 0 | 1224247
Altoona | 9 | Blair | 117019 | SR 3013 Over Beaverdam Creek | 3013 | 12B | Bridge Restoration | FD | 185 | 2028-03-23 |  | 0 | 131280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131280
Altoona | 9 | Blair | 117019 | SR 3013 Over Beaverdam Creek | 3013 | 12B | Bridge Restoration | UTL | 185 | 2028-03-23 |  | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000
Altoona | 9 | Blair | 117019 | SR 3013 Over Beaverdam Creek | 3013 | 12B | Bridge Restoration | CON | BRIP | 2028-03-23 |  | 0 | 0 | 895102 | 178106 | 0 | 0 | 0 | 0 | 0 | 1073208
Altoona | 9 | Blair | 117020 | SR 3009 Over Blair Gap Run | 3009 | 02B | Bridge Restoration | ROW | 185 | 2025-05-08 | 2025-05-08 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 117020 | SR 3009 Over Blair Gap Run | 3009 | 02B | Bridge Restoration | CON | 185 | 2025-05-08 | 2025-05-08 | 1144492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1144492
Altoona | 9 | Blair | 117021 | SR 1012 Over Bald Eagle Creek | 1012 | 03B | Bridge Restoration | FD | 185 | 2028-01-13 |  | 121571 | 228429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Altoona | 9 | Blair | 117021 | SR 1012 Over Bald Eagle Creek | 1012 | 03B | Bridge Restoration | ROW | 185 | 2028-01-13 |  | 0 | 136840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136840
Altoona | 9 | Blair | 117021 | SR 1012 Over Bald Eagle Creek | 1012 | 03B | Bridge Restoration | UTL | 185 | 2028-01-13 |  | 15000 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 117021 | SR 1012 Over Bald Eagle Creek | 1012 | 03B | Bridge Restoration | CON | BOF | 2028-01-13 |  | 0 | 0 | 249127 | 806073 | 0 | 444800 | 0 | 0 | 0 | 1500000
Altoona | 9 | Blair | 117021 | SR 1012 Over Bald Eagle Creek | 1012 | 03B | Bridge Restoration | CON | 581 | 2028-01-13 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 117026 | Bridge PM Reserve Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 182126 | 118000 | 0 | 250000 | 1731000 | 2281126
Altoona | 9 | Blair | 117026 | Bridge PM Reserve Line Item |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 232306 | 0 | 0 | 0 | 232306
Altoona | 9 | Blair | 117028 | SR 4041 Bald Eagle Creek Bridge | 4041 | 06B | Bridge Restoration | UTL | BRIP | 2027-10-07 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Altoona | 9 | Blair | 117028 | SR 4041 Bald Eagle Creek Bridge | 4041 | 06B | Bridge Restoration | CON | BRIP | 2027-10-07 |  | 0 | 0 | 0 | 441199 | 0 | 0 | 0 | 0 | 0 | 441199
Altoona | 9 | Blair | 117088 | SR 3008 Over Polecat Run | 3008 | 01B | Bridge Restoration | CON | BRIP | 2026-12-10 |  | 0 | 212180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212180
Altoona | 9 | Blair | 117090 | Meadow Street over Brush Run | 7301 | MSB | Bridge Restoration | CON | 183 | 2026-12-10 |  | 0 | 0 | 163855 | 0 | 0 | 0 | 0 | 0 | 0 | 163855
Altoona | 9 | Blair | 117090 | Meadow Street over Brush Run | 7301 | MSB | Bridge Restoration | CON | LOC | 2026-12-10 |  | 0 | 0 | 40964 | 0 | 0 | 0 | 0 | 0 | 0 | 40964
Altoona | 9 | Blair | 117707 | US 22 - Cambria Co to PA 764 EB | 22 | 058 | Highway Restoration | CON | NHPP | 2024-09-12 | 2024-09-12 | 600000 | 297000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 897000
Altoona | 9 | Blair | 117709 | US 22 - Cambria Co to PA 764 WB | 22 | 059 | Highway Restoration | CON | NHPP | 2026-11-05 |  | 0 | 0 | 1569552 | 1244625 | 1333500 | 0 | 0 | 0 | 0 | 4147677
Altoona | 9 | Blair | 117709 | US 22 - Cambria Co to PA 764 WB | 22 | 059 | Highway Restoration | CON | STP | 2026-11-05 |  | 0 | 0 | 0 | 130448 | 0 | 0 | 0 | 0 | 0 | 130448
Altoona | 9 | Blair | 117767 | SR 2011 over Clover Creek | 2011 | 02B | Bridge Restoration | PE | BOF | 2031-01-09 |  | 0 | 0 | 0 | 155073 | 200000 | 0 | 0 | 0 | 0 | 355073
Altoona | 9 | Blair | 117767 | SR 2011 over Clover Creek | 2011 | 02B | Bridge Restoration | FD | BOF | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
Altoona | 9 | Blair | 117767 | SR 2011 over Clover Creek | 2011 | 02B | Bridge Restoration | ROW | BOF | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 125000
Altoona | 9 | Blair | 117767 | SR 2011 over Clover Creek | 2011 | 02B | Bridge Restoration | UTL | BOF | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 125000
Altoona | 9 | Blair | 117767 | SR 2011 over Clover Creek | 2011 | 02B | Bridge Restoration | CON | BOF | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 718000 | 382000 | 0 | 1100000
Altoona | 9 | Blair | 117773 | Fox Run Rd over Roaring Run | 2017 | 04B | Bridge Restoration | CON | BOF | 2024-01-11 | 2024-01-11 | 5000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
Altoona | 9 | Blair | 118385 | McMahon Road Extension and Improvements |  | MRE | New Alignment | CON | APL | 2027-12-09 |  | 0 | 2296377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2296377
Altoona | 9 | Blair | 118411 | 2025 RPM Installation Blair County |  |  | Safety Improvement | CON | 581 | 2025-02-13 | 2025-02-13 | 64233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64233
Altoona | 9 | Blair | 119219 | US 22 over Carson Valley Road | 22 | 61B | Bridge Restoration | CON | BRIP | 2023-10-05 | 2023-10-05 | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000
Altoona | 9 | Blair | 119314 | Altoona CRP Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 0 | 0 | 392000 | 392000 | 392000 | 392000 | 392000 | 1569000 | 3529000
Altoona | 9 | Blair | 119314 | Altoona CRP Line Item |  |  | Reserve Line Item | CON | CRPU |  |  | 0 | 0 | 0 | 205000 | 205000 | 205000 | 205000 | 205000 | 820000 | 1845000
Altoona | 9 | Blair | 120322 | PA 865 - SR 1008 to Cambria County Line | 865 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 50000 | 750000 | 0 | 0 | 800000
Altoona | 9 | Blair | 120322 | PA 865 - SR 1008 to Cambria County Line | 865 | 0 | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 0 | 650000
Altoona | 9 | Blair | 120322 | PA 865 - SR 1008 to Cambria County Line | 865 | 0 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600000 | 3600000
Altoona | 9 | Blair | 120323 | SR 4043 - PA 865 to East Main Street | 4043 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 27195 | 372805 | 0 | 0 | 400000
Altoona | 9 | Blair | 120323 | SR 4043 - PA 865 to East Main Street | 4043 | 0 | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 250000
Altoona | 9 | Blair | 120323 | SR 4043 - PA 865 to East Main Street | 4043 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Altoona | 9 | Blair | 120324 | SR 4027 - SR 1001 to Railroad Bridge | 4027 | 012 | Highway Restoration | PE | 581 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 150000 | 0 | 250000
Altoona | 9 | Blair | 120324 | SR 4027 - SR 1001 to Railroad Bridge | 4027 | 012 | Highway Restoration | CON | STP | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700000 | 1700000
Altoona | 9 | Blair | 120325 | SR 3012 - Cambria County to Mule Shoe Tunnel | 3012 | 004 | Highway Restoration | PE | STP | 2029-11-08 |  | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 120325 | SR 3012 - Cambria County to Mule Shoe Tunnel | 3012 | 004 | Highway Restoration | CON | STP | 2029-11-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 1313000 | 0 | 2063000
Altoona | 9 | Blair | 120327 | PA 164 - Roaring Spring to Huntingdon County | 164 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 150000 | 0 | 250000
Altoona | 9 | Blair | 120327 | PA 164 - Roaring Spring to Huntingdon County | 164 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000
Altoona | 9 | Blair | 120328 | PA 866 - Martinsburg Boro to T-357 | 866 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 150000 | 0 | 250000
Altoona | 9 | Blair | 120328 | PA 866 - Martinsburg Boro to T-357 | 866 | 0 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000 | 2100000
Altoona | 9 | Blair | 120333 | PA 164 - SR 3003 to SR 3013 | 164 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 700000 | 0 | 800000
Altoona | 9 | Blair | 120333 | PA 164 - SR 3003 to SR 3013 | 164 | 0 | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Altoona | 9 | Blair | 120333 | PA 164 - SR 3003 to SR 3013 | 164 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800000 | 3800000
Altoona | 9 | Blair | 120341 | PA 453 - Clearfield County Line to Beastons Road | 453 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 250000 | 0 | 450000
Altoona | 9 | Blair | 120341 | PA 453 - Clearfield County Line to Beastons Road | 453 | 0 | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
Altoona | 9 | Blair | 120341 | PA 453 - Clearfield County Line to Beastons Road | 453 | 0 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000 | 2100000
Altoona | 9 | Blair | 120405 | PA 350 over Bald Eagle Creek | 350 | 04B | Bridge Restoration | PE | 185 | 2028-11-02 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 120405 | PA 350 over Bald Eagle Creek | 350 | 04B | Bridge Restoration | ROW | 185 | 2028-11-02 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 120405 | PA 350 over Bald Eagle Creek | 350 | 04B | Bridge Restoration | UTL | 185 | 2028-11-02 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 120405 | PA 350 over Bald Eagle Creek | 350 | 04B | Bridge Restoration | CON | BRIP | 2028-11-02 |  | 0 | 0 | 0 | 0 | 700000 | 700000 | 0 | 0 | 0 | 1400000
Altoona | 9 | Blair | 120406 | PA 164 over South Dry Run | 164 | 15B | Bridge Restoration | PE | 185 | 2029-01-18 |  | 10000 | 51160 | 306961 | 21039 | 0 | 0 | 0 | 0 | 0 | 389160
Altoona | 9 | Blair | 120406 | PA 164 over South Dry Run | 164 | 15B | Bridge Restoration | FD | 185 | 2029-01-18 |  | 0 | 0 | 0 | 178961 | 21039 | 0 | 0 | 0 | 0 | 200000
Altoona | 9 | Blair | 120406 | PA 164 over South Dry Run | 164 | 15B | Bridge Restoration | ROW | 185 | 2029-01-18 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 120406 | PA 164 over South Dry Run | 164 | 15B | Bridge Restoration | UTL | 185 | 2029-01-18 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 120406 | PA 164 over South Dry Run | 164 | 15B | Bridge Restoration | CON | BRIP | 2029-01-18 |  | 0 | 0 | 0 | 0 | 1335000 | 1335000 | 0 | 0 | 0 | 2670000
Altoona | 9 | Blair | 120407 | SR 4008 over Glenwhite Run | 4008 | 07B | Bridge Restoration | PE | BOF | 2032-01-15 |  | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000
Altoona | 9 | Blair | 120407 | SR 4008 over Glenwhite Run | 4008 | 07B | Bridge Restoration | FD | BOF | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 400000
Altoona | 9 | Blair | 120407 | SR 4008 over Glenwhite Run | 4008 | 07B | Bridge Restoration | ROW | BOF | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 125000
Altoona | 9 | Blair | 120407 | SR 4008 over Glenwhite Run | 4008 | 07B | Bridge Restoration | UTL | BOF | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 125000
Altoona | 9 | Blair | 120407 | SR 4008 over Glenwhite Run | 4008 | 07B | Bridge Restoration | CON | BOF | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 1300000 | 1486000
Altoona | 9 | Blair | 120408 | SR 4013 over Railroad | 4013 | 02B | Bridge Restoration | PE | 185 | 2032-10-14 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 120408 | SR 4013 over Railroad | 4013 | 02B | Bridge Restoration | FD | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 370000 | 0 | 0 | 0 | 370000
Altoona | 9 | Blair | 120408 | SR 4013 over Railroad | 4013 | 02B | Bridge Restoration | ROW | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 120408 | SR 4013 over Railroad | 4013 | 02B | Bridge Restoration | UTL | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 120408 | SR 4013 over Railroad | 4013 | 02B | Bridge Restoration | CON | BRIP | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000000 | 7000000
Altoona | 9 | Blair | 120408 | SR 4013 over Railroad | 4013 | 02B | Bridge Restoration | CON | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500000 | 6500000
Altoona | 9 | Blair | 120411 | SR 4001 over US 22 | 4001 | 02B | Bridge Restoration | PE | BOF | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 600000
Altoona | 9 | Blair | 120411 | SR 4001 over US 22 | 4001 | 02B | Bridge Restoration | FD | BOF | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 550000
Altoona | 9 | Blair | 120411 | SR 4001 over US 22 | 4001 | 02B | Bridge Restoration | ROW | BOF | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Altoona | 9 | Blair | 120411 | SR 4001 over US 22 | 4001 | 02B | Bridge Restoration | UTL | BOF | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Altoona | 9 | Blair | 120411 | SR 4001 over US 22 | 4001 | 02B | Bridge Restoration | CON | BOF | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
Altoona | 9 | Blair | 120416 | SR 4027 over Bald Eagle Creek | 4027 | 0 | Bridge Restoration | PE | BRIP | 2031-01-09 |  | 0 | 0 | 0 | 248997 | 162000 | 0 | 0 | 0 | 0 | 410997
Altoona | 9 | Blair | 120416 | SR 4027 over Bald Eagle Creek | 4027 | 0 | Bridge Restoration | ROW | BRIP | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 120416 | SR 4027 over Bald Eagle Creek | 4027 | 0 | Bridge Restoration | UTL | BRIP | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 120416 | SR 4027 over Bald Eagle Creek | 4027 | 0 | Bridge Restoration | CON | BRIP | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2409000 | 0 | 0 | 2409000
Altoona | 9 | Blair | 120419 | SR 4013 over Crab Run | 4013 | 0 | Bridge Restoration | ROW | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 120419 | SR 4013 over Crab Run | 4013 | 0 | Bridge Restoration | UTL | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Altoona | 9 | Blair | 120419 | SR 4013 over Crab Run | 4013 | 0 | Bridge Restoration | CON | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 620000 | 0 | 0 | 620000
Altoona | 9 | Blair | 120420 | SR 2002 over Cabbage Creek | 2002 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 120420 | SR 2002 over Cabbage Creek | 2002 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
Altoona | 9 | Blair | 120420 | SR 2002 over Cabbage Creek | 2002 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
Altoona | 9 | Blair | 120420 | SR 2002 over Cabbage Creek | 2002 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307383 | 1307383
Altoona | 9 | Blair | 120468 | PA 36 - SR 2004 Intersection Improvement | 36 | 46S | Safety Improvement | PE | HSIP | 2030-01-17 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Altoona | 9 | Blair | 120468 | PA 36 - SR 2004 Intersection Improvement | 36 | 46S | Safety Improvement | PE | HSIP | 2030-01-17 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Altoona | 9 | Blair | 120468 | PA 36 - SR 2004 Intersection Improvement | 36 | 46S | Safety Improvement | FD | HSIP | 2030-01-17 |  | 0 | 0 | 111000 | 189000 | 0 | 0 | 0 | 0 | 0 | 300000
Altoona | 9 | Blair | 120468 | PA 36 - SR 2004 Intersection Improvement | 36 | 46S | Safety Improvement | ROW | HSIP | 2030-01-17 |  | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000
Altoona | 9 | Blair | 120468 | PA 36 - SR 2004 Intersection Improvement | 36 | 46S | Safety Improvement | UTL | HSIP | 2030-01-17 |  | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 75000
Altoona | 9 | Blair | 120468 | PA 36 - SR 2004 Intersection Improvement | 36 | 46S | Safety Improvement | CON | HSIP | 2030-01-17 |  | 0 | 0 | 0 | 0 | 0 | 282000 | 1000000 | 1000000 | 0 | 2282000
Altoona | 9 | Blair | 120540 | 2025 Blair TSMO | 99 | 01T | Intelligent Transportation System | PE | CRP | 2026-02-12 | 2026-02-12 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Altoona | 9 | Blair | 120540 | 2025 Blair TSMO | 99 | 01T | Intelligent Transportation System | PE | CRP | 2026-02-12 | 2026-02-12 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Altoona | 9 | Blair | 120540 | 2025 Blair TSMO | 99 | 01T | Intelligent Transportation System | CON | CRP | 2026-02-12 | 2026-02-12 | 873600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 873600
Altoona | 9 | Blair | 120540 | 2025 Blair TSMO | 99 | 01T | Intelligent Transportation System | CON | CRP | 2026-02-12 | 2026-02-12 | 198400 | 307827 | 374086 | 0 | 0 | 0 | 0 | 0 | 0 | 880313
Altoona | 9 | Blair | 120540 | 2025 Blair TSMO | 99 | 01T | Intelligent Transportation System | CON | CRPU | 2026-02-12 | 2026-02-12 | 0 | 0 | 205000 | 0 | 0 | 0 | 0 | 0 | 0 | 205000
Altoona | 9 | Blair | 120543 | 2025 Blair County D/B Under 8ft Culvts | 4015 | 005 | Stormwater Management | ROW | STP | 2025-08-21 | 2025-08-21 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Altoona | 9 | Blair | 120543 | 2025 Blair County D/B Under 8ft Culvts | 4015 | 005 | Stormwater Management | ROW | 581 | 2025-08-21 | 2025-08-21 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Altoona | 9 | Blair | 120543 | 2025 Blair County D/B Under 8ft Culvts | 4015 | 005 | Stormwater Management | CON | STP | 2025-08-21 | 2025-08-21 | 308867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308867
Altoona | 9 | Blair | 120546 | PA 36/PA 164 Woodbury Pike Safety Improvements | 36 | 47S | Safety Improvement | PE | HSIP | 2029-07-12 |  | 0 | 419000 | 77071 | 0 | 0 | 0 | 0 | 0 | 0 | 496071
Altoona | 9 | Blair | 120546 | PA 36/PA 164 Woodbury Pike Safety Improvements | 36 | 47S | Safety Improvement | FD | HSIP | 2029-07-12 |  | 0 | 0 | 140000 | 283546 | 0 | 0 | 0 | 0 | 0 | 423546
Altoona | 9 | Blair | 120546 | PA 36/PA 164 Woodbury Pike Safety Improvements | 36 | 47S | Safety Improvement | ROW | HSIP | 2029-07-12 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Altoona | 9 | Blair | 120546 | PA 36/PA 164 Woodbury Pike Safety Improvements | 36 | 47S | Safety Improvement | UTL | HSIP | 2029-07-12 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 120546 | PA 36/PA 164 Woodbury Pike Safety Improvements | 36 | 47S | Safety Improvement | CON | HSIP | 2029-07-12 |  | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 2000000
Altoona | 9 | Blair | 120546 | PA 36/PA 164 Woodbury Pike Safety Improvements | 36 | 47S | Safety Improvement | CON | STP | 2029-07-12 |  | 0 | 0 | 0 | 0 | 546573 | 1153427 | 0 | 0 | 0 | 1700000
Altoona | 9 | Blair | 120714 | PA 453 - SR 1013 to Huntingdon County | 453 | 017 | Highway Restoration | PE | 581 | 2028-08-10 |  | 75000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Altoona | 9 | Blair | 120714 | PA 453 - SR 1013 to Huntingdon County | 453 | 017 | Highway Restoration | ROW | STP | 2028-08-10 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Altoona | 9 | Blair | 120714 | PA 453 - SR 1013 to Huntingdon County | 453 | 017 | Highway Restoration | UTL | STP | 2028-08-10 |  | 0 | 21049 | 28951 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Altoona | 9 | Blair | 120714 | PA 453 - SR 1013 to Huntingdon County | 453 | 017 | Highway Restoration | CON | STP | 2028-08-10 |  | 0 | 0 | 0 | 250000 | 0 | 1259573 | 178690 | 0 | 0 | 1688263
Altoona | 9 | Blair | 120817 | 2026 RPM Installation Blair County |  |  | Safety Improvement | CON | 581 | 2026-03-12 | 2026-03-12 | 0 | 110442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110442
Altoona | 9 | Blair | 121386 | PA 453 14th Street Corridor - NBE | 453 | 0 | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 0 | 0 | 0 | 800000 | 1200000 | 1076209 | 0 | 0 | 3076209
Altoona | 9 | Blair | 121388 | Blair County EVRR Corridor | 3013 | 0 | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 4000000
Altoona | 9 | Blair | 121824 | PA 164 - PA 36 to PA 866 | 164 | 005 | Highway Restoration | CON | 409 | 2032-07-15 |  | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
Altoona | 9 | Blair | 122233 | 2026 Blair Interchange Lighting | 99 | L30 | Congestion Reduction | CON | CRP | 2025-10-09 | 2025-10-09 | 173600 | 84173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257773
Altoona | 9 | Blair | 122233 | 2026 Blair Interchange Lighting | 99 | L30 | Congestion Reduction | CON | CRPU | 2025-10-09 | 2025-10-09 | 201000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201000
Altoona | 9 | Blair | 122377 | Juniata N 8th Street Bridge Study | 7210 | 02B | Bridge Restoration | PE | 183 |  |  | 0 | 408000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408000
Altoona | 9 | Blair | 122377 | Juniata N 8th Street Bridge Study | 7210 | 02B | Bridge Restoration | PE | LOC |  |  | 0 | 102000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102000
Altoona | 9 | Blair | 123310 | Bus 220 / Stadium Drive Signal | 1001 | 16T | Safety Improvement | CON | HSIP | 2026-01-08 | 2026-01-08 | 0 | 379076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379076
Centre | 2 | Centre | 2759 | Park Avenue Widening | 3007 | 165 | Safety Improvement | PE | STP | 2034-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2150266 | 2150266
Centre | 2 | Centre | 2759 | Park Avenue Widening | 3007 | 165 | Safety Improvement | PE | 581 | 2034-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537567 | 537567
Centre | 2 | Centre | 2759 | Park Avenue Widening | 3007 | 165 | Safety Improvement | FD | STP | 2034-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075133 | 1075133
Centre | 2 | Centre | 2759 | Park Avenue Widening | 3007 | 165 | Safety Improvement | FD | 581 | 2034-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268783 | 268783
Centre | 2 | Centre | 2759 | Park Avenue Widening | 3007 | 165 | Safety Improvement | ROW | STP | 2034-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996121 | 1996121
Centre | 2 | Centre | 2759 | Park Avenue Widening | 3007 | 165 | Safety Improvement | ROW | 581 | 2034-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499030 | 499030
Centre | 2 | Centre | 2759 | Park Avenue Widening | 3007 | 165 | Safety Improvement | UTL | STP | 2034-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075133 | 1075133
Centre | 2 | Centre | 2759 | Park Avenue Widening | 3007 | 165 | Safety Improvement | UTL | 581 | 2034-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268273 | 268273
Centre | 2 | Centre | 2759 | Park Avenue Widening | 3007 | 165 | Safety Improvement | CON | 581 | 2034-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8867390 | 8867390
Centre | 2 | Centre | 2898 | T-633, Potter Run Bridge | 7218 | 000 | Bridge Restoration | CON | STP | 2025-01-30 | 2025-01-30 | 707824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 707824
Centre | 2 | Centre | 2898 | T-633, Potter Run Bridge | 7218 | 000 | Bridge Restoration | CON | BOF | 2025-01-30 | 2025-01-30 | 176576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176576
Centre | 2 | Centre | 2898 | T-633, Potter Run Bridge | 7218 | 000 | Bridge Restoration | CON | LOC | 2025-01-30 | 2025-01-30 | 267731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267731
Centre | 2 | Centre | 2963 | T-467, Fishing Creek Bridge | 7224 | 000 | Bridge Replacement | CON | STP | 2024-10-10 | 2024-10-10 | 655636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 655636
Centre | 2 | Centre | 2963 | T-467, Fishing Creek Bridge | 7224 | 000 | Bridge Replacement | CON | BOF | 2024-10-10 | 2024-10-10 | 233853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233853
Centre | 2 | Centre | 2963 | T-467, Fishing Creek Bridge | 7224 | 000 | Bridge Replacement | CON | BRIP | 2024-10-10 | 2024-10-10 | 279075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279075
Centre | 2 | Centre | 2963 | T-467, Fishing Creek Bridge | 7224 | 000 | Bridge Replacement | CON | LOC | 2024-10-10 | 2024-10-10 | 248479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248479
Centre | 2 | Centre | 2975 | T-400,Wallace Run Br. |  | BR | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 696000 | 0 | 0 | 0 | 696000
Centre | 2 | Centre | 3185 | T-300 Big Fill Run |  | BR | Bridge Replacement | CON | 183 |  |  | 223700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223700
Centre | 2 | Centre | 3185 | T-300 Big Fill Run |  | BR | Bridge Replacement | CON | LOC |  |  | 55925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55925
Centre | 2 | Centre | 3188 | Centre 2024 Br. Preserv. | 879 | A02 | Bridge Preservation - Federal | PE | STP | 2026-03-26 | 2026-03-26 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Centre | 2 | Centre | 3188 | Centre 2024 Br. Preserv. | 879 | A02 | Bridge Preservation - Federal | FD | 581 | 2026-03-26 | 2026-03-26 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Centre | 2 | Centre | 3188 | Centre 2024 Br. Preserv. | 879 | A02 | Bridge Preservation - Federal | CON | BRIP | 2026-03-26 | 2026-03-26 | 0 | 811128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 811128
Centre | 2 | Centre | 3188 | Centre 2024 Br. Preserv. | 879 | A02 | Bridge Preservation - Federal | CON | STP | 2026-03-26 | 2026-03-26 | 0 | 955579 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 1085579
Centre | 2 | Centre | 47617 | Little Fishing Creek II | 64 | A02 | Bridge Restoration | PE | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581378 | 581378
Centre | 2 | Centre | 47617 | Little Fishing Creek II | 64 | A02 | Bridge Restoration | FD | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534660 | 534660
Centre | 2 | Centre | 47617 | Little Fishing Creek II | 64 | A02 | Bridge Restoration | ROW | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178220 | 178220
Centre | 2 | Centre | 47617 | Little Fishing Creek II | 64 | A02 | Bridge Restoration | UTL | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178220 | 178220
Centre | 2 | Centre | 47617 | Little Fishing Creek II | 64 | A02 | Bridge Restoration | CON | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2491621 | 2491621
Centre | 2 | Centre | 69381 | SR 64 ov Lil Fishn Crk III | 64 | A03 | Bridge Restoration | PE | STP | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 413238 | 0 | 0 | 0 | 413238
Centre | 2 | Centre | 69381 | SR 64 ov Lil Fishn Crk III | 64 | A03 | Bridge Restoration | PE | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 153309 | 0 | 0 | 0 | 153309
Centre | 2 | Centre | 69381 | SR 64 ov Lil Fishn Crk III | 64 | A03 | Bridge Restoration | FD | STP | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 354696 | 0 | 0 | 354696
Centre | 2 | Centre | 69381 | SR 64 ov Lil Fishn Crk III | 64 | A03 | Bridge Restoration | FD | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 120597 | 0 | 0 | 120597
Centre | 2 | Centre | 69381 | SR 64 ov Lil Fishn Crk III | 64 | A03 | Bridge Restoration | ROW | STP | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50671 | 0 | 0 | 50671
Centre | 2 | Centre | 69381 | SR 64 ov Lil Fishn Crk III | 64 | A03 | Bridge Restoration | ROW | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12668 | 0 | 0 | 12668
Centre | 2 | Centre | 69381 | SR 64 ov Lil Fishn Crk III | 64 | A03 | Bridge Restoration | UTL | STP | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50671 | 0 | 0 | 50671
Centre | 2 | Centre | 69381 | SR 64 ov Lil Fishn Crk III | 64 | A03 | Bridge Restoration | UTL | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12668 | 0 | 0 | 12668
Centre | 2 | Centre | 69381 | SR 64 ov Lil Fishn Crk III | 64 | A03 | Bridge Restoration | CON | STP | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977000 | 0 | 1977000
Centre | 2 | Centre | 69381 | SR 64 ov Lil Fishn Crk III | 64 | A03 | Bridge Restoration | CON | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490595 | 0 | 490595
Centre | 2 | Centre | 72400 | T-334 over Spring Creek | 7204 | A01 | Bridge Replacement | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 348000 | 0 | 0 | 348000
Centre | 2 | Centre | 72400 | T-334 over Spring Creek | 7204 | A01 | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 0 | 240000
Centre | 2 | Centre | 72400 | T-334 over Spring Creek | 7204 | A01 | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 0 | 54000
Centre | 2 | Centre | 72400 | T-334 over Spring Creek | 7204 | A01 | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 0 | 54000
Centre | 2 | Centre | 72400 | T-334 over Spring Creek | 7204 | A01 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1392500 | 1392500
Centre | 2 | Centre | 75808 | Line Item Safety |  | SAF | Reserve Line Item | CON | HSIP |  |  | 0 | 0 | 818318 | 1098000 | 867000 | 867000 | 867000 | 867000 | 3468000 | 8852318
Centre | 2 | Centre | 76162 | Mill Race Bridge | 3006 | A04 | Bridge Replacement | FD | 185 | 2026-03-12 | 2026-03-12 | 367284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367284
Centre | 2 | Centre | 76162 | Mill Race Bridge | 3006 | A04 | Bridge Replacement | ROW | 185 | 2026-03-12 | 2026-03-12 | 84413 | 135587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000
Centre | 2 | Centre | 76162 | Mill Race Bridge | 3006 | A04 | Bridge Replacement | UTL | 185 | 2026-03-12 | 2026-03-12 | 10609 | 14391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Centre | 2 | Centre | 76162 | Mill Race Bridge | 3006 | A04 | Bridge Replacement | CON | NHPP | 2026-03-12 | 2026-03-12 | 800000 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280000
Centre | 2 | Centre | 76162 | Mill Race Bridge | 3006 | A04 | Bridge Replacement | CON | STP | 2026-03-12 | 2026-03-12 | 760000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760000
Centre | 2 | Centre | 76162 | Mill Race Bridge | 3006 | A04 | Bridge Replacement | CON | 185 | 2026-03-12 | 2026-03-12 | 464080 | 114413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578493
Centre | 2 | Centre | 84085 | Trib to Trout Run BOX | 3027 | A02 | Bridge Restoration | PE | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 474405 | 0 | 0 | 0 | 0 | 474405
Centre | 2 | Centre | 84085 | Trib to Trout Run BOX | 3027 | A02 | Bridge Restoration | ROW | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 36896 | 0 | 0 | 0 | 36896
Centre | 2 | Centre | 84085 | Trib to Trout Run BOX | 3027 | A02 | Bridge Restoration | UTL | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 61494 | 0 | 0 | 0 | 61494
Centre | 2 | Centre | 84085 | Trib to Trout Run BOX | 3027 | A02 | Bridge Restoration | CON | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 776431 | 0 | 0 | 0 | 776431
Centre | 2 | Centre | 84343 | Poor Bridge/Betterment Line Item |  | 000 | Reserve Line Item | CON | BOF |  |  | 0 | 113604 | 937091 | 0 | 0 | 0 | 0 | 0 | 0 | 1050695
Centre | 2 | Centre | 84343 | Poor Bridge/Betterment Line Item |  | 000 | Reserve Line Item | CON | NHPP |  |  | 0 | 303052 | 0 | 0 | 1333458 | 0 | 0 | 0 | 0 | 1636510
Centre | 2 | Centre | 84343 | Poor Bridge/Betterment Line Item |  | 000 | Reserve Line Item | CON | STP |  |  | 0 | 53299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53299
Centre | 2 | Centre | 84343 | Poor Bridge/Betterment Line Item |  | 000 | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 209897 | 0 | 0 | 0 | 0 | 0 | 0 | 209897
Centre | 2 | Centre | 84343 | Poor Bridge/Betterment Line Item |  | 000 | Reserve Line Item | CON | 581 |  |  | 0 | 412055 | 750000 | 750000 | 2500000 | 0 | 0 | 0 | 0 | 4412055
Centre | 2 | Centre | 84515 | Local Retro Bridges |  |  | Bridge Preservation - Federal | CON | 183 |  |  | 0 | 86822 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 686822
Centre | 2 | Centre | 84515 | Local Retro Bridges |  |  | Bridge Preservation - Federal | CON | LOC |  |  | 0 | 21705 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 171705
Centre | 2 | Centre | 85133 | SR 504 over Wallace Run | 504 | A07 | Bridge Restoration | PE | NHPP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483810 | 483810
Centre | 2 | Centre | 85133 | SR 504 over Wallace Run | 504 | A07 | Bridge Restoration | PE | 185 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120953 | 120953
Centre | 2 | Centre | 85133 | SR 504 over Wallace Run | 504 | A07 | Bridge Restoration | FD | NHPP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448492 | 448492
Centre | 2 | Centre | 85133 | SR 504 over Wallace Run | 504 | A07 | Bridge Restoration | FD | 185 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112123 | 112123
Centre | 2 | Centre | 85133 | SR 504 over Wallace Run | 504 | A07 | Bridge Restoration | ROW | NHPP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55370 | 55370
Centre | 2 | Centre | 85133 | SR 504 over Wallace Run | 504 | A07 | Bridge Restoration | ROW | 185 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13843 | 13843
Centre | 2 | Centre | 85133 | SR 504 over Wallace Run | 504 | A07 | Bridge Restoration | UTL | NHPP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55370 | 55370
Centre | 2 | Centre | 85133 | SR 504 over Wallace Run | 504 | A07 | Bridge Restoration | UTL | 185 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13843 | 13843
Centre | 2 | Centre | 85133 | SR 504 over Wallace Run | 504 | A07 | Bridge Restoration | CON | NHPP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 953549 | 953549
Centre | 2 | Centre | 85133 | SR 504 over Wallace Run | 504 | A07 | Bridge Restoration | CON | 185 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238388 | 238388
Centre | 2 | Centre | 85145 | SR 144 over Potter Run | 144 | A17 | Bridge Restoration | PE | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581378 | 581378
Centre | 2 | Centre | 85145 | SR 144 over Potter Run | 144 | A17 | Bridge Restoration | FD | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391432 | 391432
Centre | 2 | Centre | 85145 | SR 144 over Potter Run | 144 | A17 | Bridge Restoration | ROW | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65239 | 65239
Centre | 2 | Centre | 85145 | SR 144 over Potter Run | 144 | A17 | Bridge Restoration | UTL | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65239 | 65239
Centre | 2 | Centre | 85145 | SR 144 over Potter Run | 144 | A17 | Bridge Restoration | CON | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1043819 | 1043819
Centre | 2 | Centre | 88169 | SEDA-COG/Nit & Bald Eagle | 26 | A06 | Bridge Restoration | PE | STP | 2027-10-21 |  | 357332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357332
Centre | 2 | Centre | 88169 | SEDA-COG/Nit & Bald Eagle | 26 | A06 | Bridge Restoration | PE | 185 | 2027-10-21 |  | 89333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89333
Centre | 2 | Centre | 88169 | SEDA-COG/Nit & Bald Eagle | 26 | A06 | Bridge Restoration | FD | STP | 2027-10-21 |  | 0 | 273181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273181
Centre | 2 | Centre | 88169 | SEDA-COG/Nit & Bald Eagle | 26 | A06 | Bridge Restoration | ROW | STP | 2027-10-21 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
Centre | 2 | Centre | 88169 | SEDA-COG/Nit & Bald Eagle | 26 | A06 | Bridge Restoration | UTL | STP | 2027-10-21 |  | 0 | 81955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81955
Centre | 2 | Centre | 88169 | SEDA-COG/Nit & Bald Eagle | 26 | A06 | Bridge Restoration | CON | BRIP | 2027-10-21 |  | 0 | 0 | 316418 | 1706662 | 0 | 0 | 0 | 0 | 0 | 2023080
Centre | 2 | Centre | 88169 | SEDA-COG/Nit & Bald Eagle | 26 | A06 | Bridge Restoration | CON | 185 | 2027-10-21 |  | 0 | 0 | 226546 | 448759 | 0 | 0 | 0 | 0 | 0 | 675305
Centre | 2 | Centre | 88170 | South Fork Beech Creek | 144 | A13 | Bridge Replacement | FD | 581 | 2018-06-21 | 2018-06-21 | 0 | 1587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1587
Centre | 2 | Centre | 88187 | Sparrow Run Bridge. | 3040 | A07 | Bridge Replacement | PE | STP |  |  | 0 | 0 | 0 | 0 | 401202 | 0 | 0 | 0 | 0 | 401202
Centre | 2 | Centre | 88187 | Sparrow Run Bridge. | 3040 | A07 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 100300 | 0 | 0 | 0 | 0 | 100300
Centre | 2 | Centre | 88187 | Sparrow Run Bridge. | 3040 | A07 | Bridge Replacement | FD | STP |  |  | 0 | 0 | 0 | 0 | 0 | 295170 | 0 | 0 | 0 | 295170
Centre | 2 | Centre | 88187 | Sparrow Run Bridge. | 3040 | A07 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 73793 | 0 | 0 | 0 | 73793
Centre | 2 | Centre | 88187 | Sparrow Run Bridge. | 3040 | A07 | Bridge Replacement | ROW | STP |  |  | 0 | 0 | 0 | 0 | 0 | 49195 | 0 | 0 | 0 | 49195
Centre | 2 | Centre | 88187 | Sparrow Run Bridge. | 3040 | A07 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 12299 | 0 | 0 | 0 | 12299
Centre | 2 | Centre | 88187 | Sparrow Run Bridge. | 3040 | A07 | Bridge Replacement | UTL | STP |  |  | 0 | 0 | 0 | 0 | 0 | 49195 | 0 | 0 | 0 | 49195
Centre | 2 | Centre | 88187 | Sparrow Run Bridge. | 3040 | A07 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 12299 | 0 | 0 | 0 | 12299
Centre | 2 | Centre | 88187 | Sparrow Run Bridge. | 3040 | A07 | Bridge Replacement | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 156000 | 156000 | 0 | 0 | 312000
Centre | 2 | Centre | 88187 | Sparrow Run Bridge. | 3040 | A07 | Bridge Replacement | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 186303 | 1520962 | 0 | 0 | 1707265
Centre | 2 | Centre | 88187 | Sparrow Run Bridge. | 3040 | A07 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 604817 | 0 | 0 | 604817
Centre | 2 | Centre | 88206 | SR 3040 Laurel Run Br #2 | 3040 | A03 | Bridge Restoration | PE | NHPP | 2028-08-30 |  | 0 | 0 | 0 | 0 | 0 | 358037 | 0 | 0 | 0 | 358037
Centre | 2 | Centre | 88206 | SR 3040 Laurel Run Br #2 | 3040 | A03 | Bridge Restoration | PE | 185 | 2028-08-30 |  | 0 | 0 | 0 | 0 | 0 | 89510 | 0 | 0 | 0 | 89510
Centre | 2 | Centre | 88206 | SR 3040 Laurel Run Br #2 | 3040 | A03 | Bridge Restoration | FD | NHPP | 2028-08-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 383050 | 0 | 0 | 383050
Centre | 2 | Centre | 88206 | SR 3040 Laurel Run Br #2 | 3040 | A03 | Bridge Restoration | FD | 185 | 2028-08-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 95763 | 0 | 0 | 95763
Centre | 2 | Centre | 88206 | SR 3040 Laurel Run Br #2 | 3040 | A03 | Bridge Restoration | ROW | NHPP | 2028-08-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 49195 | 0 | 0 | 49195
Centre | 2 | Centre | 88206 | SR 3040 Laurel Run Br #2 | 3040 | A03 | Bridge Restoration | ROW | 185 | 2028-08-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12299 | 0 | 0 | 12299
Centre | 2 | Centre | 88206 | SR 3040 Laurel Run Br #2 | 3040 | A03 | Bridge Restoration | UTL | NHPP | 2028-08-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 49195 | 0 | 0 | 49195
Centre | 2 | Centre | 88206 | SR 3040 Laurel Run Br #2 | 3040 | A03 | Bridge Restoration | UTL | 185 | 2028-08-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12299 | 0 | 0 | 12299
Centre | 2 | Centre | 88206 | SR 3040 Laurel Run Br #2 | 3040 | A03 | Bridge Restoration | CON | NHPP | 2028-08-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1503409 | 1503409
Centre | 2 | Centre | 88206 | SR 3040 Laurel Run Br #2 | 3040 | A03 | Bridge Restoration | CON | STP | 2028-08-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
Centre | 2 | Centre | 88206 | SR 3040 Laurel Run Br #2 | 3040 | A03 | Bridge Restoration | CON | 185 | 2028-08-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450852 | 450852
Centre | 2 | Centre | 88217 | SR 4005 Bridge over I-80. | 4005 | A02 | Bridge Restoration | PE | BRIP | 2026-09-17 |  | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000
Centre | 2 | Centre | 88217 | SR 4005 Bridge over I-80. | 4005 | A02 | Bridge Restoration | FD | BRIP | 2026-09-17 |  | 99883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99883
Centre | 2 | Centre | 88217 | SR 4005 Bridge over I-80. | 4005 | A02 | Bridge Restoration | FD | NHPP | 2026-09-17 |  | 476117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476117
Centre | 2 | Centre | 88217 | SR 4005 Bridge over I-80. | 4005 | A02 | Bridge Restoration | FD | STP | 2026-09-17 |  | 125578 | 14422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Centre | 2 | Centre | 88217 | SR 4005 Bridge over I-80. | 4005 | A02 | Bridge Restoration | FD | 581 | 2026-09-17 |  | 179000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179000
Centre | 2 | Centre | 88217 | SR 4005 Bridge over I-80. | 4005 | A02 | Bridge Restoration | ROW | 581 | 2026-09-17 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Centre | 2 | Centre | 88217 | SR 4005 Bridge over I-80. | 4005 | A02 | Bridge Restoration | UTL | 581 | 2026-09-17 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Centre | 2 | Centre | 88217 | SR 4005 Bridge over I-80. | 4005 | A02 | Bridge Restoration | CON | BRIP | 2026-09-17 |  | 0 | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500000
Centre | 2 | Centre | 88217 | SR 4005 Bridge over I-80. | 4005 | A02 | Bridge Restoration | CON | NHPP | 2026-09-17 |  | 0 | 1262542 | 2761857 | 3000000 | 0 | 0 | 0 | 0 | 0 | 7024399
Centre | 2 | Centre | 88217 | SR 4005 Bridge over I-80. | 4005 | A02 | Bridge Restoration | CON | STP | 2026-09-17 |  | 0 | 0 | 484857 | 0 | 0 | 0 | 0 | 0 | 0 | 484857
Centre | 2 | Centre | 88222 | Holt Hollow Run Bridge | 150 | A01 | Bridge Restoration | PE | STP | 2028-03-30 |  | 458947 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508947
Centre | 2 | Centre | 88222 | Holt Hollow Run Bridge | 150 | A01 | Bridge Restoration | FD | STP | 2028-03-30 |  | 0 | 0 | 270122 | 0 | 0 | 0 | 0 | 0 | 0 | 270122
Centre | 2 | Centre | 88222 | Holt Hollow Run Bridge | 150 | A01 | Bridge Restoration | FD | 581 | 2028-03-30 |  | 0 | 0 | 67531 | 0 | 0 | 0 | 0 | 0 | 0 | 67531
Centre | 2 | Centre | 88222 | Holt Hollow Run Bridge | 150 | A01 | Bridge Restoration | ROW | STP | 2028-03-30 |  | 0 | 0 | 67531 | 0 | 0 | 0 | 0 | 0 | 0 | 67531
Centre | 2 | Centre | 88222 | Holt Hollow Run Bridge | 150 | A01 | Bridge Restoration | ROW | 581 | 2028-03-30 |  | 0 | 0 | 16883 | 0 | 0 | 0 | 0 | 0 | 0 | 16883
Centre | 2 | Centre | 88222 | Holt Hollow Run Bridge | 150 | A01 | Bridge Restoration | UTL | STP | 2028-03-30 |  | 0 | 0 | 67531 | 0 | 0 | 0 | 0 | 0 | 0 | 67531
Centre | 2 | Centre | 88222 | Holt Hollow Run Bridge | 150 | A01 | Bridge Restoration | UTL | 581 | 2028-03-30 |  | 0 | 0 | 16883 | 0 | 0 | 0 | 0 | 0 | 0 | 16883
Centre | 2 | Centre | 88222 | Holt Hollow Run Bridge | 150 | A01 | Bridge Restoration | CON | 581 | 2028-03-30 |  | 0 | 0 | 0 | 956402 | 0 | 0 | 0 | 0 | 0 | 956402
Centre | 2 | Centre | 88333 | Branch Pine Creek Bridge. | 45 | A06 | Bridge Replacement | PE | 581 | 2030-03-28 |  | 0 | 0 | 0 | 347783 | 0 | 0 | 0 | 0 | 0 | 347783
Centre | 2 | Centre | 88333 | Branch Pine Creek Bridge. | 45 | A06 | Bridge Replacement | ROW | 185 | 2030-03-28 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
Centre | 2 | Centre | 88333 | Branch Pine Creek Bridge. | 45 | A06 | Bridge Replacement | UTL | 185 | 2030-03-28 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
Centre | 2 | Centre | 88333 | Branch Pine Creek Bridge. | 45 | A06 | Bridge Replacement | CON | 581 | 2030-03-28 |  | 0 | 0 | 0 | 0 | 0 | 676431 | 0 | 0 | 0 | 676431
Centre | 2 | Centre | 88349 | Sinking Creek Bridge | 322 | A06 | Bridge Restoration | PE | STP | 2028-08-31 |  | 458947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458947
Centre | 2 | Centre | 88349 | Sinking Creek Bridge | 322 | A06 | Bridge Restoration | FD | STP | 2028-08-31 |  | 0 | 0 | 270122 | 0 | 0 | 0 | 0 | 0 | 0 | 270122
Centre | 2 | Centre | 88349 | Sinking Creek Bridge | 322 | A06 | Bridge Restoration | FD | 185 | 2028-08-31 |  | 0 | 0 | 67531 | 0 | 0 | 0 | 0 | 0 | 0 | 67531
Centre | 2 | Centre | 88349 | Sinking Creek Bridge | 322 | A06 | Bridge Restoration | ROW | STP | 2028-08-31 |  | 0 | 0 | 45021 | 0 | 0 | 0 | 0 | 0 | 0 | 45021
Centre | 2 | Centre | 88349 | Sinking Creek Bridge | 322 | A06 | Bridge Restoration | ROW | 581 | 2028-08-31 |  | 0 | 0 | 11255 | 0 | 0 | 0 | 0 | 0 | 0 | 11255
Centre | 2 | Centre | 88349 | Sinking Creek Bridge | 322 | A06 | Bridge Restoration | CON | STP | 2028-08-31 |  | 0 | 0 | 0 | 1391129 | 0 | 0 | 0 | 0 | 0 | 1391129
Centre | 2 | Centre | 88349 | Sinking Creek Bridge | 322 | A06 | Bridge Restoration | CON | 185 | 2028-08-31 |  | 0 | 0 | 0 | 372161 | 0 | 0 | 0 | 0 | 0 | 372161
Centre | 2 | Centre | 88356 | Steel Hollow Run Bridge. | 3040 | A08 | Bridge Replacement | PE | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 516963 | 0 | 0 | 0 | 516963
Centre | 2 | Centre | 88356 | Steel Hollow Run Bridge. | 3040 | A08 | Bridge Replacement | FD | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 295170 | 0 | 0 | 295170
Centre | 2 | Centre | 88356 | Steel Hollow Run Bridge. | 3040 | A08 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 73793 | 0 | 0 | 73793
Centre | 2 | Centre | 88356 | Steel Hollow Run Bridge. | 3040 | A08 | Bridge Replacement | ROW | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 49195 | 0 | 0 | 49195
Centre | 2 | Centre | 88356 | Steel Hollow Run Bridge. | 3040 | A08 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 12299 | 0 | 0 | 12299
Centre | 2 | Centre | 88356 | Steel Hollow Run Bridge. | 3040 | A08 | Bridge Replacement | UTL | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 49195 | 0 | 0 | 49195
Centre | 2 | Centre | 88356 | Steel Hollow Run Bridge. | 3040 | A08 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 12299 | 0 | 0 | 12299
Centre | 2 | Centre | 88356 | Steel Hollow Run Bridge. | 3040 | A08 | Bridge Replacement | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875000 | 0 | 875000
Centre | 2 | Centre | 88356 | Steel Hollow Run Bridge. | 3040 | A08 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218750 | 0 | 218750
Centre | 2 | Centre | 88360 | Roaring Run Bridge. | 45 | A07 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 616547 | 0 | 0 | 616547
Centre | 2 | Centre | 88360 | Roaring Run Bridge. | 45 | A07 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373905 | 0 | 373905
Centre | 2 | Centre | 88360 | Roaring Run Bridge. | 45 | A07 | Bridge Replacement | ROW | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178220 | 0 | 178220
Centre | 2 | Centre | 88360 | Roaring Run Bridge. | 45 | A07 | Bridge Replacement | UTL | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178220 | 0 | 178220
Centre | 2 | Centre | 88360 | Roaring Run Bridge. | 45 | A07 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1636792 | 1636792
Centre | 2 | Centre | 88362 | Logan Branch Bridge | 150 | A02 | Bridge Restoration | PE | STP | 2030-02-01 |  | 0 | 0 | 0 | 429859 | 0 | 0 | 0 | 0 | 0 | 429859
Centre | 2 | Centre | 88362 | Logan Branch Bridge | 150 | A02 | Bridge Restoration | PE | 581 | 2030-02-01 |  | 0 | 0 | 0 | 107465 | 0 | 0 | 0 | 0 | 0 | 107465
Centre | 2 | Centre | 88362 | Logan Branch Bridge | 150 | A02 | Bridge Restoration | ROW | STP | 2030-02-01 |  | 0 | 0 | 0 | 0 | 47762 | 0 | 0 | 0 | 0 | 47762
Centre | 2 | Centre | 88362 | Logan Branch Bridge | 150 | A02 | Bridge Restoration | ROW | 185 | 2030-02-01 |  | 0 | 0 | 0 | 0 | 11940 | 0 | 0 | 0 | 0 | 11940
Centre | 2 | Centre | 88362 | Logan Branch Bridge | 150 | A02 | Bridge Restoration | CON | STP | 2030-02-01 |  | 0 | 0 | 0 | 0 | 0 | 983899 | 0 | 0 | 0 | 983899
Centre | 2 | Centre | 88362 | Logan Branch Bridge | 150 | A02 | Bridge Restoration | CON | 185 | 2030-02-01 |  | 0 | 0 | 0 | 0 | 0 | 245975 | 0 | 0 | 0 | 245975
Centre | 2 | Centre | 91500 | SR 2005 Sinking Cr Bridge | 2005 | A01 | Bridge Restoration | CON | BOF | 2024-11-07 | 2024-11-07 | 1325000 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329500
Centre | 2 | Centre | 91500 | SR 2005 Sinking Cr Bridge | 2005 | A01 | Bridge Restoration | CON | 581 | 2024-11-07 | 2024-11-07 | 332375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332375
Centre | 2 | Centre | 92422 | CEN Bridge Plank/Channel Program |  |  | Bridge Preservation - Federal | CON | 185 |  | 2020-08-20 | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 500000
Centre | 2 | Centre | 93262 | Howard Intersection | 26 | N41 | Safety Improvement | CON | HSIP | 2024-05-09 | 2024-05-09 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Centre | 2 | Centre | 93268 | Hayes Run Bridge BOX | 2006 | A02 | Bridge Restoration | PE | 185 | 2031-08-21 |  | 0 | 0 | 0 | 197783 | 0 | 0 | 0 | 0 | 0 | 197783
Centre | 2 | Centre | 93268 | Hayes Run Bridge BOX | 2006 | A02 | Bridge Restoration | ROW | 185 | 2031-08-21 |  | 0 | 0 | 0 | 57963 | 0 | 0 | 0 | 0 | 0 | 57963
Centre | 2 | Centre | 93268 | Hayes Run Bridge BOX | 2006 | A02 | Bridge Restoration | UTL | 581 | 2031-08-21 |  | 0 | 0 | 0 | 57963 | 0 | 0 | 0 | 0 | 0 | 57963
Centre | 2 | Centre | 93268 | Hayes Run Bridge BOX | 2006 | A02 | Bridge Restoration | CON | 185 | 2031-08-21 |  | 0 | 0 | 0 | 0 | 797026 | 0 | 0 | 0 | 0 | 797026
Centre | 2 | Centre | 93332 | Trib to Muddy Run BOX | 2010 | A01 | Bridge Restoration | PE | 185 | 2029-12-01 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
Centre | 2 | Centre | 93332 | Trib to Muddy Run BOX | 2010 | A01 | Bridge Restoration | ROW | 185 | 2029-12-01 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
Centre | 2 | Centre | 93332 | Trib to Muddy Run BOX | 2010 | A01 | Bridge Restoration | UTL | 185 | 2029-12-01 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
Centre | 2 | Centre | 93332 | Trib to Muddy Run BOX | 2010 | A01 | Bridge Restoration | CON | 185 | 2029-12-01 |  | 0 | 0 | 0 | 0 | 0 | 717994 | 0 | 0 | 0 | 717994
Centre | 2 | Centre | 95386 | Kato Road Bridge | 7220 | A01 | Bridge Replacement | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 348000 | 0 | 0 | 348000
Centre | 2 | Centre | 95386 | Kato Road Bridge | 7220 | A01 | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 0 | 240000
Centre | 2 | Centre | 95386 | Kato Road Bridge | 7220 | A01 | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 0 | 54000
Centre | 2 | Centre | 95386 | Kato Road Bridge | 7220 | A01 | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 0 | 54000
Centre | 2 | Centre | 95386 | Kato Road Bridge | 7220 | A01 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1392500 | 1392500
Centre | 2 | Centre | 95800 | T-867 Eagleville Road | 7213 | 0 | Bridge Replacement | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156000 | 625000 | 781000
Centre | 2 | Centre | 98881 | Trib Wallace Run Bridge | 144 | A14 | Bridge Replacement | FD | 581 | 2018-06-21 | 2018-06-21 | 0 | 1376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1376
Centre | 2 | Centre | 100583 | SR 322 Bypass-Boalsbrg EB | 322 | 0 | Highway Restoration | CON | 581 | 2029-01-30 |  | 0 | 0 | 0 | 0 | 0 | 1442100 | 2425500 | 0 | 0 | 3867600
Centre | 2 | Centre | 100586 | SR 322 Bypass-Boalsbrg WB | 322 | 0 | Highway Restoration | CON | 581 | 2029-01-30 |  | 0 | 0 | 0 | 0 | 0 | 1442101 | 2425500 | 0 | 0 | 3867601
Centre | 2 | Centre | 101003 | SR 26 Ferguson-College NB | 26 | 0 | Highway Restoration | CON | 581 | 2017-03-23 | 2017-03-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5172072 | 5172072
Centre | 2 | Centre | 101008 | SR 26 Ferguson-College SB | 26 | 0 | Highway Restoration | CON | 581 | 2017-03-23 | 2017-03-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448048 | 3448048
Centre | 2 | Centre | 101026 | SR 45 Cedar Rn to Old Fort | 45 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 614937 | 0 | 0 | 0 | 614937
Centre | 2 | Centre | 101026 | SR 45 Cedar Rn to Old Fort | 45 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4493560 | 0 | 4493560
Centre | 2 | Centre | 101028 | Centre Hall Resurfacing | 144 | 0 | Highway Restoration | CON | STP | 2029-03-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1311347 | 1311347
Centre | 2 | Centre | 101028 | Centre Hall Resurfacing | 144 | 0 | Highway Restoration | CON | 581 | 2029-03-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327837 | 327837
Centre | 2 | Centre | 101961 | Atherton Street Phase IV | 3014 | 154 | Highway Restoration | PE | NHPP | 2028-02-17 |  | 82415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82415
Centre | 2 | Centre | 101961 | Atherton Street Phase IV | 3014 | 154 | Highway Restoration | FD | NHPP | 2028-02-17 |  | 0 | 327000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327000
Centre | 2 | Centre | 101961 | Atherton Street Phase IV | 3014 | 154 | Highway Restoration | FD | 581 | 2028-02-17 |  | 0 | 106090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106090
Centre | 2 | Centre | 101961 | Atherton Street Phase IV | 3014 | 154 | Highway Restoration | ROW | NHPP | 2028-02-17 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Centre | 2 | Centre | 101961 | Atherton Street Phase IV | 3014 | 154 | Highway Restoration | UTL | NHPP | 2028-02-17 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Centre | 2 | Centre | 106365 | SR 150 and Phoenix Ave Intersection | 150 | N40 | Highway Reconstruction | PE | NHPP | 2028-11-30 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Centre | 2 | Centre | 106365 | SR 150 and Phoenix Ave Intersection | 150 | N40 | Highway Reconstruction | PE | 581 | 2028-11-30 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Centre | 2 | Centre | 106365 | SR 150 and Phoenix Ave Intersection | 150 | N40 | Highway Reconstruction | FD | 581 | 2028-11-30 |  | 0 | 0 | 576123 | 0 | 0 | 0 | 0 | 0 | 0 | 576123
Centre | 2 | Centre | 106365 | SR 150 and Phoenix Ave Intersection | 150 | N40 | Highway Reconstruction | ROW | STP | 2028-11-30 |  | 0 | 0 | 185143 | 0 | 0 | 0 | 0 | 0 | 0 | 185143
Centre | 2 | Centre | 106365 | SR 150 and Phoenix Ave Intersection | 150 | N40 | Highway Reconstruction | ROW | 581 | 2028-11-30 |  | 0 | 0 | 78786 | 0 | 0 | 0 | 0 | 0 | 0 | 78786
Centre | 2 | Centre | 106365 | SR 150 and Phoenix Ave Intersection | 150 | N40 | Highway Reconstruction | UTL | NHPP | 2028-11-30 |  | 0 | 0 | 15143 | 0 | 0 | 0 | 0 | 0 | 0 | 15143
Centre | 2 | Centre | 106365 | SR 150 and Phoenix Ave Intersection | 150 | N40 | Highway Reconstruction | UTL | 581 | 2028-11-30 |  | 0 | 0 | 78786 | 0 | 0 | 0 | 0 | 0 | 0 | 78786
Centre | 2 | Centre | 106365 | SR 150 and Phoenix Ave Intersection | 150 | N40 | Highway Reconstruction | CON | NHPP | 2028-11-30 |  | 0 | 0 | 0 | 142000 | 875000 | 0 | 0 | 0 | 0 | 1017000
Centre | 2 | Centre | 106365 | SR 150 and Phoenix Ave Intersection | 150 | N40 | Highway Reconstruction | CON | STP | 2028-11-30 |  | 0 | 0 | 0 | 451012 | 327592 | 0 | 0 | 0 | 0 | 778604
Centre | 2 | Centre | 106365 | SR 150 and Phoenix Ave Intersection | 150 | N40 | Highway Reconstruction | CON | 581 | 2028-11-30 |  | 0 | 0 | 0 | 2286604 | 2354000 | 0 | 0 | 0 | 0 | 4640604
Centre | 2 | Centre | 108455 | Group 2-26-ST1 | 550 | ST1 | Highway Restoration | CON | 581 | 2026-04-09 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Centre | 2 | Centre | 109581 | Bridge ov Trib Wallace Run | 4004 | A05 | Bridge Restoration | PE | 185 | 2026-08-13 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Centre | 2 | Centre | 109581 | Bridge ov Trib Wallace Run | 4004 | A05 | Bridge Restoration | FD | 581 | 2026-08-13 |  | 0 | 281378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281378
Centre | 2 | Centre | 109581 | Bridge ov Trib Wallace Run | 4004 | A05 | Bridge Restoration | ROW | 581 | 2026-08-13 |  | 0 | 26523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26523
Centre | 2 | Centre | 109581 | Bridge ov Trib Wallace Run | 4004 | A05 | Bridge Restoration | UTL | 581 | 2026-08-13 |  | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57964
Centre | 2 | Centre | 109581 | Bridge ov Trib Wallace Run | 4004 | A05 | Bridge Restoration | CON | 185 | 2026-08-13 |  | 0 | 911526 | 22756 | 0 | 0 | 0 | 0 | 0 | 0 | 934282
Centre | 2 | Centre | 109582 | Steel Arch Culvert | 504 | A06 | Bridge Restoration | CON | 581 | 2023-10-05 | 2023-10-05 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Centre | 2 | Centre | 110305 | 2024 Bridge Preservation | 504 | P36 | Bridge Restoration | CON | BRIP | 2024-04-18 | 2024-04-18 | 283685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283685
Centre | 2 | Centre | 110305 | 2024 Bridge Preservation | 504 | P36 | Bridge Restoration | CON | 185 | 2024-04-18 | 2024-04-18 | 70922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70922
Centre | 2 | Centre | 110368 | 2026 Centre Bridge Preservation | 26 | P35 | Bridge Restoration | PE | BRIP | 2026-09-03 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Centre | 2 | Centre | 110368 | 2026 Centre Bridge Preservation | 26 | P35 | Bridge Restoration | PE | STP | 2026-09-03 |  | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
Centre | 2 | Centre | 110368 | 2026 Centre Bridge Preservation | 26 | P35 | Bridge Restoration | UTL | BRIP | 2026-09-03 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Centre | 2 | Centre | 110368 | 2026 Centre Bridge Preservation | 26 | P35 | Bridge Restoration | CON | BRIP | 2026-09-03 |  | 108517 | 1148964 | 722525 | 0 | 0 | 0 | 0 | 0 | 0 | 1980006
Centre | 2 | Centre | 110368 | 2026 Centre Bridge Preservation | 26 | P35 | Bridge Restoration | CON | NHPP | 2026-09-03 |  | 329452 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1129452
Centre | 2 | Centre | 110368 | 2026 Centre Bridge Preservation | 26 | P35 | Bridge Restoration | CON | STP | 2026-09-03 |  | 0 | 824437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824437
Centre | 2 | Centre | 110368 | 2026 Centre Bridge Preservation | 26 | P35 | Bridge Restoration | CON | 581 | 2026-09-03 |  | 0 | 0 | 459000 | 0 | 0 | 0 | 0 | 0 | 0 | 459000
Centre | 2 | Centre | 112588 | Jacksonville Road Betterment | 26 | 147 | Highway Restoration | UTL | NHPP | 2024-08-22 | 2024-08-22 | 179780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179780
Centre | 2 | Centre | 112588 | Jacksonville Road Betterment | 26 | 147 | Highway Restoration | CON | 581 | 2024-08-22 | 2024-08-22 | 353433 | 27733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381166
Centre | 2 | Centre | 112784 | State College Area Connector | 322 | D10 | New Alignment | PE | 581 | 2030-01-24 |  | 6648527 | 10703425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17351952
Centre | 2 | Centre | 112784 | State College Area Connector | 322 | D10 | New Alignment | FD | 581 | 2030-01-24 |  | 0 | 0 | 22000000 | 13000000 | 0 | 0 | 0 | 0 | 0 | 35000000
Centre | 2 | Centre | 112784 | State College Area Connector | 322 | D10 | New Alignment | ROW | 581 | 2030-01-24 |  | 350000 | 0 | 0 | 0 | 0 | 15400000 | 0 | 0 | 0 | 15750000
Centre | 2 | Centre | 112784 | State College Area Connector | 322 | D10 | New Alignment | UTL | 581 | 2030-01-24 |  | 0 | 0 | 10000000 | 10000000 | 9000000 | 0 | 0 | 0 | 0 | 29000000
Centre | 2 | Centre | 112784 | State College Area Connector | 322 | D10 | New Alignment | CON | 581 | 2030-01-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 39000000 | 40000000 | 161000000 | 240000000
Centre | 2 | Centre | 113123 | SR 3030 over Branch Dix Run BOX | 3030 | A01 | Bridge Restoration | PE | 185 | 2026-10-01 |  | 176275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176275
Centre | 2 | Centre | 113123 | SR 3030 over Branch Dix Run BOX | 3030 | A01 | Bridge Restoration | ROW | 581 | 2026-10-01 |  | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57964
Centre | 2 | Centre | 113123 | SR 3030 over Branch Dix Run BOX | 3030 | A01 | Bridge Restoration | UTL | 581 | 2026-10-01 |  | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57964
Centre | 2 | Centre | 113123 | SR 3030 over Branch Dix Run BOX | 3030 | A01 | Bridge Restoration | CON | 581 | 2026-10-01 |  | 0 | 0 | 922918 | 0 | 0 | 0 | 0 | 0 | 0 | 922918
Centre | 2 | Centre | 113550 | SR 144 Runville Area, Drainage Imp. | 144 | 164 | Study Phase of Project | PE | 581 | 2026-01-08 | 2025-12-11 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Centre | 2 | Centre | 113550 | SR 144 Runville Area, Drainage Imp. | 144 | 164 | Study Phase of Project | ROW | 581 | 2026-01-08 | 2025-12-11 | 65540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65540
Centre | 2 | Centre | 113550 | SR 144 Runville Area, Drainage Imp. | 144 | 164 | Study Phase of Project | UTL | 581 | 2026-01-08 | 2025-12-11 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Centre | 2 | Centre | 113550 | SR 144 Runville Area, Drainage Imp. | 144 | 164 | Study Phase of Project | CON | 581 | 2026-01-08 | 2025-12-11 | 490000 | 249583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 739583
Centre | 2 | Centre | 113890 | Struble Rd RR Warn Device |  | R17 | Rail Highway Grade Crossing | CON | RRX | 2021-08-19 | 2021-06-23 | 63500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63500
Centre | 2 | Centre | 114728 | Centre Co Local Bridge Bundle II | 7401 | MTF | MultiModal | CON | LOC | 2023-08-18 |  | 663117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 663117
Centre | 2 | Centre | 115653 | SR 445 Bridge Restoration | 445 | A05 | Bridge Restoration | PE | BRIP | 2032-03-18 |  | 0 | 0 | 378171 | 0 | 0 | 0 | 0 | 0 | 0 | 378171
Centre | 2 | Centre | 115653 | SR 445 Bridge Restoration | 445 | A05 | Bridge Restoration | PE | 185 | 2032-03-18 |  | 0 | 0 | 94543 | 0 | 0 | 0 | 0 | 0 | 0 | 94543
Centre | 2 | Centre | 115653 | SR 445 Bridge Restoration | 445 | A05 | Bridge Restoration | FD | BRIP | 2032-03-18 |  | 0 | 0 | 0 | 278226 | 0 | 0 | 0 | 0 | 0 | 278226
Centre | 2 | Centre | 115653 | SR 445 Bridge Restoration | 445 | A05 | Bridge Restoration | FD | 185 | 2032-03-18 |  | 0 | 0 | 0 | 69556 | 0 | 0 | 0 | 0 | 0 | 69556
Centre | 2 | Centre | 115653 | SR 445 Bridge Restoration | 445 | A05 | Bridge Restoration | ROW | BRIP | 2032-03-18 |  | 0 | 0 | 0 | 69556 | 0 | 0 | 0 | 0 | 0 | 69556
Centre | 2 | Centre | 115653 | SR 445 Bridge Restoration | 445 | A05 | Bridge Restoration | ROW | 185 | 2032-03-18 |  | 0 | 0 | 0 | 17389 | 0 | 0 | 0 | 0 | 0 | 17389
Centre | 2 | Centre | 115653 | SR 445 Bridge Restoration | 445 | A05 | Bridge Restoration | UTL | BRIP | 2032-03-18 |  | 0 | 0 | 0 | 69556 | 0 | 0 | 0 | 0 | 0 | 69556
Centre | 2 | Centre | 115653 | SR 445 Bridge Restoration | 445 | A05 | Bridge Restoration | UTL | 185 | 2032-03-18 |  | 0 | 0 | 0 | 17389 | 0 | 0 | 0 | 0 | 0 | 17389
Centre | 2 | Centre | 115653 | SR 445 Bridge Restoration | 445 | A05 | Bridge Restoration | CON | BRIP | 2032-03-18 |  | 0 | 0 | 0 | 0 | 156000 | 0 | 0 | 0 | 0 | 156000
Centre | 2 | Centre | 115653 | SR 445 Bridge Restoration | 445 | A05 | Bridge Restoration | CON | STP | 2032-03-18 |  | 0 | 0 | 0 | 0 | 799242 | 0 | 0 | 0 | 0 | 799242
Centre | 2 | Centre | 115653 | SR 445 Bridge Restoration | 445 | A05 | Bridge Restoration | CON | 185 | 2032-03-18 |  | 0 | 0 | 0 | 0 | 338811 | 0 | 0 | 0 | 0 | 338811
Centre | 2 | Centre | 116319 | Group 2-25-ST1 | 144 | 0 | Highway Restoration | CON | 581 | 2025-02-13 | 2025-02-13 | 207706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207706
Centre | 2 | Centre | 116739 | SR 144 Potter Run Concrete Arch Culvert | 144 | A16 | Bridge Restoration | PE | 185 | 2027-10-21 |  | 445578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445578
Centre | 2 | Centre | 116739 | SR 144 Potter Run Concrete Arch Culvert | 144 | A16 | Bridge Restoration | FD | 581 | 2027-10-21 |  | 0 | 0 | 393929 | 0 | 0 | 0 | 0 | 0 | 0 | 393929
Centre | 2 | Centre | 116739 | SR 144 Potter Run Concrete Arch Culvert | 144 | A16 | Bridge Restoration | ROW | 581 | 2027-10-21 |  | 0 | 0 | 61494 | 0 | 0 | 0 | 0 | 0 | 0 | 61494
Centre | 2 | Centre | 116739 | SR 144 Potter Run Concrete Arch Culvert | 144 | A16 | Bridge Restoration | UTL | 581 | 2027-10-21 |  | 0 | 0 | 61494 | 0 | 0 | 0 | 0 | 0 | 0 | 61494
Centre | 2 | Centre | 116739 | SR 144 Potter Run Concrete Arch Culvert | 144 | A16 | Bridge Restoration | CON | 185 | 2027-10-21 |  | 0 | 0 | 1125509 | 0 | 0 | 0 | 0 | 0 | 0 | 1125509
Centre | 2 | Centre | 116747 | SR 3036 over Mulligan Run | 3036 | A01 | Bridge Restoration | PE | 185 | 2026-12-10 |  | 36191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36191
Centre | 2 | Centre | 116747 | SR 3036 over Mulligan Run | 3036 | A01 | Bridge Restoration | FD | 581 | 2026-12-10 |  | 0 | 281377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281377
Centre | 2 | Centre | 116747 | SR 3036 over Mulligan Run | 3036 | A01 | Bridge Restoration | ROW | 581 | 2026-12-10 |  | 0 | 59703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59703
Centre | 2 | Centre | 116747 | SR 3036 over Mulligan Run | 3036 | A01 | Bridge Restoration | UTL | 581 | 2026-12-10 |  | 0 | 59703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59703
Centre | 2 | Centre | 116747 | SR 3036 over Mulligan Run | 3036 | A01 | Bridge Restoration | CON | 581 | 2026-12-10 |  | 0 | 0 | 922918 | 0 | 0 | 0 | 0 | 0 | 0 | 922918
Centre | 2 | Centre | 116791 | SR 1009 over Lick Run | 1009 | A01 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 227841 | 209250 | 0 | 0 | 0 | 0 | 0 | 437091
Centre | 2 | Centre | 116791 | SR 1009 over Lick Run | 1009 | A01 | Bridge Restoration | FD | BOF |  |  | 0 | 0 | 0 | 298513 | 0 | 0 | 0 | 0 | 0 | 298513
Centre | 2 | Centre | 116791 | SR 1009 over Lick Run | 1009 | A01 | Bridge Restoration | ROW | BOF |  |  | 0 | 0 | 0 | 59702 | 0 | 0 | 0 | 0 | 0 | 59702
Centre | 2 | Centre | 116791 | SR 1009 over Lick Run | 1009 | A01 | Bridge Restoration | UTL | BOF |  |  | 0 | 0 | 0 | 59702 | 0 | 0 | 0 | 0 | 0 | 59702
Centre | 2 | Centre | 116791 | SR 1009 over Lick Run | 1009 | A01 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 747833 | 696000 | 0 | 0 | 0 | 0 | 1443833
Centre | 2 | Centre | 116881 | 2024 Centre Bridge Preservation | 3022 | P48 | Bridge Restoration | CON | BRIP | 2024-04-18 | 2024-04-18 | 131885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131885
Centre | 2 | Centre | 116881 | 2024 Centre Bridge Preservation | 3022 | P48 | Bridge Restoration | CON | NHPP | 2024-04-18 | 2024-04-18 | 0 | 757458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757458
Centre | 2 | Centre | 116881 | 2024 Centre Bridge Preservation | 3022 | P48 | Bridge Restoration | CON | 185 | 2024-04-18 | 2024-04-18 | 0 | 126000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000
Centre | 2 | Centre | 116885 | SR 26 over Spring Creek | 26 | P53 | Bridge Restoration | PE | STP | 2026-02-26 | 2026-02-26 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Centre | 2 | Centre | 116885 | SR 26 over Spring Creek | 26 | P53 | Bridge Restoration | PE | 581 | 2026-02-26 | 2026-02-26 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Centre | 2 | Centre | 116885 | SR 26 over Spring Creek | 26 | P53 | Bridge Restoration | ROW | 581 | 2026-02-26 | 2026-02-26 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Centre | 2 | Centre | 116885 | SR 26 over Spring Creek | 26 | P53 | Bridge Restoration | UTL | 581 | 2026-02-26 | 2026-02-26 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Centre | 2 | Centre | 116885 | SR 26 over Spring Creek | 26 | P53 | Bridge Restoration | CON | BRIP | 2026-02-26 | 2026-02-26 | 1230150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230150
Centre | 2 | Centre | 116885 | SR 26 over Spring Creek | 26 | P53 | Bridge Restoration | CON | NHPP | 2026-02-26 | 2026-02-26 | 590236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590236
Centre | 2 | Centre | 116885 | SR 26 over Spring Creek | 26 | P53 | Bridge Restoration | CON | STP | 2026-02-26 | 2026-02-26 | 220196 | 45658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265854
Centre | 2 | Centre | 116885 | SR 26 over Spring Creek | 26 | P53 | Bridge Restoration | CON | 185 | 2026-02-26 | 2026-02-26 | 379315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379315
Centre | 2 | Centre | 116891 | 2027 Centre Bridge Preservation | 3042 | P55 | Bridge Restoration | PE | 185 | 2027-04-29 |  | 0 | 287583 | 186218 | 0 | 0 | 0 | 0 | 0 | 0 | 473801
Centre | 2 | Centre | 116891 | 2027 Centre Bridge Preservation | 3042 | P55 | Bridge Restoration | CON | STP | 2027-04-29 |  | 0 | 0 | 752673 | 0 | 0 | 0 | 0 | 0 | 0 | 752673
Centre | 2 | Centre | 117920 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 679000 | 679000 | 679000 | 679000 | 2716000 | 5432000
Centre | 2 | Centre | 117920 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 1968000 | 1968000 | 1968000 | 1968000 | 7872000 | 15744000
Centre | 2 | Centre | 117920 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 366930 | 0 | 0 | 483000 | 483000 | 483000 | 483000 | 1934000 | 4232930
Centre | 2 | Centre | 117920 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | CRPU |  |  | 0 | 0 | 0 | 0 | 230000 | 230000 | 230000 | 230000 | 922000 | 1842000
Centre | 2 | Centre | 117920 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 0 | 0 | 0 | 231000 | 231000 | 231000 | 231000 | 925000 | 1849000
Centre | 2 | Centre | 117920 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 933542 | 2267000 | 2267000 | 2267000 | 9067000 | 16801542
Centre | 2 | Centre | 117920 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 0 | 0 | 0 | 295000 | 295000 | 295000 | 295000 | 1181000 | 2361000
Centre | 2 | Centre | 118401 | St College Shared Use Path, TASA |  |  | Bicycle Pedestrian Highway | CON | TAP | 2026-02-26 | 2026-02-26 | 1725000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1725000
Centre | 2 | Centre | 118402 | Pine Grove Mills Bike/Ped Improvements, TASA | 45 | TSA | Bicycle Pedestrian Highway | PE | STP | 2025-01-30 | 2025-01-30 | 1943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1943
Centre | 2 | Centre | 118402 | Pine Grove Mills Bike/Ped Improvements, TASA | 45 | TSA | Bicycle Pedestrian Highway | CON | CRP | 2025-01-30 | 2025-01-30 | 173600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173600
Centre | 2 | Centre | 118402 | Pine Grove Mills Bike/Ped Improvements, TASA | 45 | TSA | Bicycle Pedestrian Highway | CON | TAP | 2025-01-30 | 2025-01-30 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
Centre | 2 | Centre | 118402 | Pine Grove Mills Bike/Ped Improvements, TASA | 45 | TSA | Bicycle Pedestrian Highway | CON | 581 | 2025-01-30 | 2025-01-30 | 22550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22550
Centre | 2 | Centre | 118402 | Pine Grove Mills Bike/Ped Improvements, TASA | 45 | TSA | Bicycle Pedestrian Highway | CON | LOC | 2025-01-30 | 2025-01-30 | 111033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111033
Centre | 2 | Centre | 119318 | Centre County VRU Project 2026 | 26 | 0 | Safety Improvement | PE | HVRU | 2027-10-21 |  | 620555 | 179445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Centre | 2 | Centre | 119468 | Centre Concrete Preservation | 99 | 166 | Preventive Maintenance | FD | NHPP | 2025-09-25 | 2025-09-25 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Centre | 2 | Centre | 119468 | Centre Concrete Preservation | 99 | 166 | Preventive Maintenance | CON | NHPP | 2025-09-25 | 2025-09-25 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000
Centre | 2 | Centre | 119687 | SR 26 Allen Street Improvements TIIF | 26 | 169 | Transportation Enhancement | CON | 581 | 2027-06-24 |  | 0 | 0 | 1600000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 3100000
Centre | 2 | Centre | 119880 | SR's 26, 45 & 3011 Bridge Preservations | 45 | P59 | Bridge Restoration | PE | BRIP | 2027-09-30 |  | 69205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69205
Centre | 2 | Centre | 119880 | SR's 26, 45 & 3011 Bridge Preservations | 45 | P59 | Bridge Restoration | PE | STP | 2027-09-30 |  | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Centre | 2 | Centre | 119880 | SR's 26, 45 & 3011 Bridge Preservations | 45 | P59 | Bridge Restoration | ROW | BRIP | 2027-09-30 |  | 0 | 81954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81954
Centre | 2 | Centre | 119880 | SR's 26, 45 & 3011 Bridge Preservations | 45 | P59 | Bridge Restoration | UTL | BRIP | 2027-09-30 |  | 0 | 71954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71954
Centre | 2 | Centre | 119880 | SR's 26, 45 & 3011 Bridge Preservations | 45 | P59 | Bridge Restoration | CON | BRIP | 2027-09-30 |  | 0 | 0 | 706886 | 0 | 0 | 0 | 0 | 0 | 0 | 706886
Centre | 2 | Centre | 119880 | SR's 26, 45 & 3011 Bridge Preservations | 45 | P59 | Bridge Restoration | CON | NHPP | 2027-09-30 |  | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
Centre | 2 | Centre | 119885 | SR 3021 Steele Hollow Rd Bridge | 3021 | A01 | Bridge Replacement | PE | 581 | 2030-06-27 |  | 0 | 0 | 0 | 347783 | 0 | 0 | 0 | 0 | 0 | 347783
Centre | 2 | Centre | 119885 | SR 3021 Steele Hollow Rd Bridge | 3021 | A01 | Bridge Replacement | ROW | 185 | 2030-06-27 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
Centre | 2 | Centre | 119885 | SR 3021 Steele Hollow Rd Bridge | 3021 | A01 | Bridge Replacement | UTL | 185 | 2030-06-27 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
Centre | 2 | Centre | 119885 | SR 3021 Steele Hollow Rd Bridge | 3021 | A01 | Bridge Replacement | CON | 581 | 2030-06-27 |  | 0 | 0 | 0 | 0 | 0 | 676431 | 0 | 0 | 0 | 676431
Centre | 2 | Centre | 119970 | Centre Co. Carbon Reduction | 99 | CRP | General Maintenance | CON | CRP | 2024-10-10 | 2024-10-10 | 28970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28970
Centre | 2 | Centre | 120117 | I-99 High-Tension Cable Median Barrier | 99 | CMB | Safety Improvement | PE | 581 | 2026-09-03 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Centre | 2 | Centre | 120117 | I-99 High-Tension Cable Median Barrier | 99 | CMB | Safety Improvement | CON | HSIP | 2026-09-03 |  | 0 | 1372014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1372014
Centre | 2 | Centre | 120117 | I-99 High-Tension Cable Median Barrier | 99 | CMB | Safety Improvement | CON | HSIP | 2026-09-03 |  | 0 | 1627986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1627986
Centre | 2 | Centre | 120171 | SR 150 Drainage Pipe | 150 | 166 | General Maintenance | PE | 581 | 2027-01-28 |  | 140000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Centre | 2 | Centre | 120171 | SR 150 Drainage Pipe | 150 | 166 | General Maintenance | FD | 581 | 2027-01-28 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Centre | 2 | Centre | 120171 | SR 150 Drainage Pipe | 150 | 166 | General Maintenance | ROW | 581 | 2027-01-28 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Centre | 2 | Centre | 120547 | SR 3040 over Reese Hollow | 3040 | A09 | Bridge Replacement | PE | STP |  |  | 0 | 0 | 0 | 0 | 401202 | 0 | 0 | 0 | 0 | 401202
Centre | 2 | Centre | 120547 | SR 3040 over Reese Hollow | 3040 | A09 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 100300 | 0 | 0 | 0 | 0 | 100300
Centre | 2 | Centre | 120547 | SR 3040 over Reese Hollow | 3040 | A09 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 468963 | 0 | 0 | 468963
Centre | 2 | Centre | 120547 | SR 3040 over Reese Hollow | 3040 | A09 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 61494 | 0 | 0 | 61494
Centre | 2 | Centre | 120547 | SR 3040 over Reese Hollow | 3040 | A09 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 61494 | 0 | 0 | 61494
Centre | 2 | Centre | 120547 | SR 3040 over Reese Hollow | 3040 | A09 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1093750 | 0 | 1093750
Centre | 2 | Centre | 120550 | SR 2011 over Penns Creek | 2011 | A08 | Bridge Restoration | PE | 581 | 2026-03-26 | 2026-03-26 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Centre | 2 | Centre | 120550 | SR 2011 over Penns Creek | 2011 | A08 | Bridge Restoration | FD | 581 | 2026-03-26 | 2026-03-26 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000
Centre | 2 | Centre | 120550 | SR 2011 over Penns Creek | 2011 | A08 | Bridge Restoration | CON | BOF | 2026-03-26 | 2026-03-26 | 0 | 1256896 | 210068 | 0 | 0 | 0 | 0 | 0 | 0 | 1466964
Centre | 2 | Centre | 120568 | SR 144/192 Centre Hall Drainage Improvement | 144 | 167 | Highway Restoration | PE | 581 | 2026-08-13 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Centre | 2 | Centre | 120568 | SR 144/192 Centre Hall Drainage Improvement | 144 | 167 | Highway Restoration | FD | 581 | 2026-08-13 |  | 160000 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000
Centre | 2 | Centre | 120568 | SR 144/192 Centre Hall Drainage Improvement | 144 | 167 | Highway Restoration | ROW | 581 | 2026-08-13 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Centre | 2 | Centre | 120568 | SR 144/192 Centre Hall Drainage Improvement | 144 | 167 | Highway Restoration | UTL | 581 | 2026-08-13 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Centre | 2 | Centre | 120568 | SR 144/192 Centre Hall Drainage Improvement | 144 | 167 | Highway Restoration | CON | 581 | 2026-08-13 |  | 0 | 1140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1140000
Centre | 2 | Centre | 121068 | Presqueisle Street Bridge Phase II |  | 168 | Bridge Removal | FD | PRTCT | 2026-06-18 |  | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
Centre | 2 | Centre | 121068 | Presqueisle Street Bridge Phase II |  | 168 | Bridge Removal | CON | PRTCT | 2026-06-18 |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Centre | 2 | Centre | 121321 | Atherton/University/E. Branch Rd Intersections | 3014 | CRP | Safety Improvement | PE | CRP | 2027-01-28 |  | 224000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224000
Centre | 2 | Centre | 121321 | Atherton/University/E. Branch Rd Intersections | 3014 | CRP | Safety Improvement | PE | CRPU | 2027-01-28 |  | 226000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226000
Centre | 2 | Centre | 121321 | Atherton/University/E. Branch Rd Intersections | 3014 | CRP | Safety Improvement | FD | CRP | 2027-01-28 |  | 44430 | 34570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79000
Centre | 2 | Centre | 121321 | Atherton/University/E. Branch Rd Intersections | 3014 | CRP | Safety Improvement | FD | CRPU | 2027-01-28 |  | 0 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000
Centre | 2 | Centre | 121321 | Atherton/University/E. Branch Rd Intersections | 3014 | CRP | Safety Improvement | ROW | CRP | 2027-01-28 |  | 0 | 51500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51500
Centre | 2 | Centre | 121321 | Atherton/University/E. Branch Rd Intersections | 3014 | CRP | Safety Improvement | UTL | CRP | 2027-01-28 |  | 0 | 30000 | 76090 | 0 | 0 | 0 | 0 | 0 | 0 | 106090
Centre | 2 | Centre | 121321 | Atherton/University/E. Branch Rd Intersections | 3014 | CRP | Safety Improvement | CON | CRP | 2027-01-28 |  | 0 | 0 | 406910 | 483000 | 0 | 0 | 0 | 0 | 0 | 889910
Centre | 2 | Centre | 121321 | Atherton/University/E. Branch Rd Intersections | 3014 | CRP | Safety Improvement | CON | CRPU | 2027-01-28 |  | 0 | 0 | 230000 | 230000 | 0 | 0 | 0 | 0 | 0 | 460000
Centre | 2 | Centre | 121370 | Lemont Corridor RR Warning Devices | 3006 | R18 | Safety Improvement | CON | RRX | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 2333489 | 0 | 3333489
Centre | 2 | Centre | 121373 | West Maple & Reed Street RR Upgrade | 53 | R19 | Safety Improvement | CON | RRX | 2025-12-11 |  | 0 | 400000 | 160000 | 229000 | 0 | 0 | 0 | 0 | 0 | 789000
Centre | 2 | Centre | 121493 | T-604 Lake Rd Bridge | 7218 | 0 | Bridge Restoration | CON | 183 |  |  | 0 | 289478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289478
Centre | 2 | Centre | 121493 | T-604 Lake Rd Bridge | 7218 | 0 | Bridge Restoration | CON | LOC |  |  | 0 | 72370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72370
Centre | 2 | Centre | 121546 | College Twp Bike/Ped Path, TASA | 26 | TSA | Bicycle Pedestrian Highway | CON | TAP | 2027-01-28 |  | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Centre | 2 | Centre | 121643 | Centre County Rumble Strip Project | 322 | RMB | Safety Improvement | CON | HSIP | 2025-04-10 | 2025-04-10 | 161000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161000
Centre | 2 | Centre | 122338 | Beaver Ave Resurfacing | 26 | 170 | Highway Restoration | PE | 581 | 2026-08-13 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Centre | 2 | Centre | 122338 | Beaver Ave Resurfacing | 26 | 170 | Highway Restoration | CON | 581 | 2026-08-13 |  | 1151936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1151936
Centre | 2 | Centre | 122482 | Centre County Resilient Routes |  |  | Study Phase of Project | STUDY | PRTCT | 2028-04-27 |  | 1348900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1348900
Centre | 2 | Centre | 122536 | SR 322 Surface Mount Delineators | 322 | N49 | Safety Improvement | CON | HSIP | 2025-07-24 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Centre | 2 | Centre | 122631 | 2026 Centre HFST-Lane Departures | 350 | HFS | Safety Improvement | PE | 581 | 2026-04-23 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Centre | 2 | Centre | 122631 | 2026 Centre HFST-Lane Departures | 350 | HFS | Safety Improvement | CON | HSIP | 2026-04-23 |  | 454000 | 0 | 279682 | 0 | 0 | 0 | 0 | 0 | 0 | 733682
Centre | 2 | Centre | 122631 | 2026 Centre HFST-Lane Departures | 350 | HFS | Safety Improvement | CON | STP | 2026-04-23 |  | 0 | 350682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350682
Centre | 2 | Centre | 123075 | SR 3009 ov Roaring Run | 3009 | A01 | Bridge Restoration | UTL | 581 | 2026-04-23 |  | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Centre | 2 | Centre | 123081 | Port Mountain Pull-Off | 322 | OFF | Safety Improvement | PE | NHPP | 2026-06-18 |  | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
Centre | 2 | Centre | 123081 | Port Mountain Pull-Off | 322 | OFF | Safety Improvement | PE | 581 | 2026-06-18 |  | 0 | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93000
Centre | 2 | Centre | 123081 | Port Mountain Pull-Off | 322 | OFF | Safety Improvement | CON | NHPP | 2026-06-18 |  | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Centre | 2 | Centre | 123507 | 2026 District 2 Bridge Epoxy | 2005 | EPX | General Maintenance | CON | 185 | 2026-04-09 |  | 0 | 824000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824000
DVRPC | 6 | Bucks | 12923 | Bristol Road Extension: Butler Ave to Park Ave | 2025 | 002 | New Alignment | PE | 581 | 2028-09-28 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
DVRPC | 6 | Bucks | 12923 | Bristol Road Extension: Butler Ave to Park Ave | 2025 | 002 | New Alignment | FD | STU | 2028-09-28 |  | 0 | 1520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1520000
DVRPC | 6 | Bucks | 12923 | Bristol Road Extension: Butler Ave to Park Ave | 2025 | 002 | New Alignment | FD | 581 | 2028-09-28 |  | 0 | 380000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380000
DVRPC | 6 | Bucks | 12923 | Bristol Road Extension: Butler Ave to Park Ave | 2025 | 002 | New Alignment | ROW | STU | 2028-09-28 |  | 2652000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2652000
DVRPC | 6 | Bucks | 12923 | Bristol Road Extension: Butler Ave to Park Ave | 2025 | 002 | New Alignment | UTL | STU | 2028-09-28 |  | 0 | 2295000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295000
DVRPC | 6 | Bucks | 12923 | Bristol Road Extension: Butler Ave to Park Ave | 2025 | 002 | New Alignment | CON | STP | 2028-09-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5184000 | 0 | 5184000
DVRPC | 6 | Bucks | 12923 | Bristol Road Extension: Butler Ave to Park Ave | 2025 | 002 | New Alignment | CON | STU | 2028-09-28 |  | 0 | 0 | 4001000 | 4001000 | 3001000 | 3001000 | 3000000 | 3816000 | 4001000 | 24821000
DVRPC | 6 | Bucks | 12923 | Bristol Road Extension: Butler Ave to Park Ave | 2025 | 002 | New Alignment | CON | 581 | 2028-09-28 |  | 0 | 0 | 1000000 | 1000000 | 750000 | 750000 | 750000 | 2250000 | 1000000 | 7500000
DVRPC | 6 | Bucks | 12965 | Lawn Ave:Maple-Farmers | 4033 | 01P | Highway Reconstruction | CON | STU | 2028-11-09 |  | 0 | 0 | 0 | 1985000 | 1985000 | 985000 | 1985000 | 2985000 | 3970000 | 13895000
DVRPC | 6 | Bucks | 12965 | Lawn Ave:Maple-Farmers | 4033 | 01P | Highway Reconstruction | CON | 581 | 2028-11-09 |  | 0 | 0 | 0 | 496000 | 496000 | 246000 | 496000 | 746000 | 992000 | 3472000
DVRPC | 6 | Bucks | 13233 | Randall Ave over Amtrak | 7101 | RAN | Bridge Replacement | PE | BOF |  |  | 0 | 1430000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1430000
DVRPC | 6 | Bucks | 13240 | Old Bethlehem Rd over Kimples Creek | 4101 | 76S | Bridge Replacement | CON | 185 | 2028-01-27 |  | 0 | 0 | 0 | 657000 | 250000 | 250000 | 250000 | 250000 | 3878000 | 5535000
DVRPC | 6 | Bucks | 13440 | PA 663 @ Allentown Road (2 Br) | 663 | VY2 | Congestion Reduction | CON | NHPP | 2026-10-22 |  | 1500000 | 3280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4780000
DVRPC | 6 | Bucks | 13440 | PA 663 @ Allentown Road (2 Br) | 663 | VY2 | Congestion Reduction | CON | STP | 2026-10-22 |  | 1017000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1017000
DVRPC | 6 | Bucks | 13440 | PA 663 @ Allentown Road (2 Br) | 663 | VY2 | Congestion Reduction | CON | STU | 2026-10-22 |  | 5871000 | 1132000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7003000
DVRPC | 6 | Bucks | 13440 | PA 663 @ Allentown Road (2 Br) | 663 | VY2 | Congestion Reduction | CON | 185 | 2026-10-22 |  | 2097000 | 1103000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200000
DVRPC | 6 | Bucks | 13549 | US1: Old Linc - PA413 | 1 | 03S | Highway Reconstruction | FD | NHPP |  |  | 1395000 | 3395000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4790000
DVRPC | 6 | Bucks | 13549 | US1: Old Linc - PA413 | 1 | 03S | Highway Reconstruction | FD | 581 |  |  | 349000 | 849000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1198000
DVRPC | 6 | Bucks | 13635 | OxfordVallyRd: Lincoln Hwy -BristolOxfrdVally Road | 2029 | S99 | Congestion Reduction | FD | STU | 2026-12-10 |  | 0 | 784000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 784000
DVRPC | 6 | Bucks | 13635 | OxfordVallyRd: Lincoln Hwy -BristolOxfrdVally Road | 2029 | S99 | Congestion Reduction | UTL | STU | 2026-12-10 |  | 796000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 796000
DVRPC | 6 | Bucks | 13635 | OxfordVallyRd: Lincoln Hwy -BristolOxfrdVally Road | 2029 | S99 | Congestion Reduction | CON | STU | 2026-12-10 |  | 0 | 1460000 | 2460000 | 2460000 | 2000000 | 2000000 | 0 | 0 | 3460000 | 13840000
DVRPC | 6 | Bucks | 13716 | Headquarters Road over Tinicum Creek(D) | 1012 | BRC | Bridge Replacement | CON | BOF |  |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Bucks | 13727 | Brstl Rd: Hulm-Old Linc (C) | 2025 | 001 | Highway Restoration | UTL | STU | 2022-01-13 | 2022-01-13 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
DVRPC | 6 | Bucks | 13727 | Brstl Rd: Hulm-Old Linc (C) | 2025 | 001 | Highway Restoration | UTL | 581 | 2022-01-13 | 2022-01-13 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
DVRPC | 6 | Bucks | 13727 | Brstl Rd: Hulm-Old Linc (C) | 2025 | 001 | Highway Restoration | CON | STU | 2022-01-13 | 2022-01-13 | 1100000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600000
DVRPC | 6 | Bucks | 50634 | CountyLine Rd: Kulp Rd to PA 611(C) | 2038 | M04 | Highway Restoration | FD | STU | 2020-10-22 | 2020-10-22 | 296000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296000
DVRPC | 6 | Bucks | 50634 | CountyLine Rd: Kulp Rd to PA 611(C) | 2038 | M04 | Highway Restoration | FD | 581 | 2020-10-22 | 2020-10-22 | 74000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74000
DVRPC | 6 | Bucks | 50634 | CountyLine Rd: Kulp Rd to PA 611(C) | 2038 | M04 | Highway Restoration | CON | NHPP | 2020-10-22 | 2020-10-22 | 352718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352718
DVRPC | 6 | Bucks | 50634 | CountyLine Rd: Kulp Rd to PA 611(C) | 2038 | M04 | Highway Restoration | CON | 581 | 2020-10-22 | 2020-10-22 | 88000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88000
DVRPC | 6 | Bucks | 57619 | PA 313: Ferry Road - Old Dublin Street | 313 | B02 | Highway Reconstruction | PE | 581 | 2030-01-31 |  | 382788 | 328212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711000
DVRPC | 6 | Bucks | 57619 | PA 313: Ferry Road - Old Dublin Street | 313 | B02 | Highway Reconstruction | CON | NHPP | 2030-01-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3544000 | 5000000 | 0 | 8544000
DVRPC | 6 | Bucks | 57619 | PA 313: Ferry Road - Old Dublin Street | 313 | B02 | Highway Reconstruction | CON | STU | 2030-01-31 |  | 0 | 0 | 557000 | 4228000 | 4000000 | 0 | 0 | 0 | 742000 | 9527000
DVRPC | 6 | Bucks | 57635 | Quakertown Closed Loop (C) | 309 | QCL | Congestion Reduction | UTL | CAQ | 2018-11-01 | 2018-11-01 | 30673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30673
DVRPC | 6 | Bucks | 64778 | State Road: Neshaminy Creek - PA 413 | 2002 | BE1 | Highway Restoration | PE | 581 | 2028-12-14 |  | 0 | 738000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738000
DVRPC | 6 | Bucks | 64778 | State Road: Neshaminy Creek - PA 413 | 2002 | BE1 | Highway Restoration | FD | 581 | 2028-12-14 |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Bucks | 64778 | State Road: Neshaminy Creek - PA 413 | 2002 | BE1 | Highway Restoration | ROW | STU | 2028-12-14 |  | 2476000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2476000
DVRPC | 6 | Bucks | 64778 | State Road: Neshaminy Creek - PA 413 | 2002 | BE1 | Highway Restoration | UTL | 581 | 2028-12-14 |  | 0 | 0 | 0 | 0 | 2425000 | 869000 | 0 | 0 | 0 | 3294000
DVRPC | 6 | Bucks | 64778 | State Road: Neshaminy Creek - PA 413 | 2002 | BE1 | Highway Restoration | CON | 581 | 2028-12-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 394000 | 1000000 | 31586000 | 32980000
DVRPC | 6 | Bucks | 64781 | Swamp Road over Br Neshaminy Creek | 2036 | BS1 | Bridge Restoration | PE | STU | 2028-04-06 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
DVRPC | 6 | Bucks | 64781 | Swamp Road over Br Neshaminy Creek | 2036 | BS1 | Bridge Restoration | PE | 185 | 2028-04-06 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
DVRPC | 6 | Bucks | 64781 | Swamp Road over Br Neshaminy Creek | 2036 | BS1 | Bridge Restoration | ROW | 185 | 2028-04-06 |  | 396000 | 396000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792000
DVRPC | 6 | Bucks | 64781 | Swamp Road over Br Neshaminy Creek | 2036 | BS1 | Bridge Restoration | UTL | STP | 2028-04-06 |  | 0 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000
DVRPC | 6 | Bucks | 64781 | Swamp Road over Br Neshaminy Creek | 2036 | BS1 | Bridge Restoration | UTL | 185 | 2028-04-06 |  | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000
DVRPC | 6 | Bucks | 64781 | Swamp Road over Br Neshaminy Creek | 2036 | BS1 | Bridge Restoration | CON | 185 | 2028-04-06 |  | 0 | 1912000 | 392000 | 1520000 | 0 | 0 | 0 | 0 | 0 | 3824000
DVRPC | 6 | Bucks | 69823 | Rosedale Rd o/ Br Unami Creek | 4059 | BB1 | Bridge Replacement | CON | 185 | 2028-01-27 |  | 0 | 0 | 0 | 2283000 | 0 | 0 | 0 | 0 | 0 | 2283000
DVRPC | 6 | Bucks | 74827 | Delaware Canal Enhance | 7935 | 0 | Air Quality | CON | STU | 2027-11-04 |  | 0 | 1093000 | 1093000 | 0 | 0 | 0 | 0 | 0 | 0 | 2186000
DVRPC | 6 | Bucks | 75854 | Dist Proj Management "A" |  |  | Planning/Research/Administration | PRA | 581 |  |  | 3000000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000
DVRPC | 6 | Bucks | 75855 | Dist Project Mgt "B"&"C" |  |  | Planning/Research/Administration | PRA | 581 |  |  | 3000000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000
DVRPC | 6 | Bucks | 78516 | Brownsville Rd o/ Neshaminy Ck(C) | 2043 | BBR | Bridge Replacement | CON | 185 | 2024-10-10 | 2024-10-10 | 2946000 | 4161661 | 3161662 | 3054000 | 0 | 0 | 0 | 0 | 0 | 13323323
DVRPC | 6 | Bucks | 79927 | S T P Reserve Line Item |  | SSS | Reserve Line Item | CON | STP |  |  | 0 | 2629179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2629179
DVRPC | 6 | Bucks | 79927 | S T P Reserve Line Item |  | SSS | Reserve Line Item | CON | 581 |  |  | 0 | 461000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461000
DVRPC | 6 | Bucks | 79927 | S T P Reserve Line Item |  | SSS | Reserve Line Item | CON | LOC |  |  | 0 | 398000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398000
DVRPC | 6 | Bucks | 79929 | Bridge Reserve Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 558107 | 995000 | 407000 | 400000 | 0 | 0 | 0 | 1724000 | 4084107
DVRPC | 6 | Bucks | 79929 | Bridge Reserve Line Item |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 1859339 | 660338 | 810000 | 51000 | 189000 | 0 | 0 | 42830714 | 46400391
DVRPC | 6 | Bucks | 79929 | Bridge Reserve Line Item |  |  | Reserve Line Item | CON | LOC |  |  | 1450500 | 241000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1691500
DVRPC | 6 | Bucks | 79980 | S T U Reserve Line Item |  | SSS | Reserve Line Item | CON | STU |  |  | 0 | 3345377 | 4720000 | 1944000 | 1400000 | 2585000 | 1229000 | 868000 | 384600 | 16475977
DVRPC | 6 | Bucks | 79980 | S T U Reserve Line Item |  | SSS | Reserve Line Item | CON | 581 |  |  | 0 | 872959 | 1646000 | 1564000 | 0 | 0 | 0 | 0 | 629000 | 4711959
DVRPC | 6 | Bucks | 81166 | US 13 & Tyburn Rd ITS Deployment | 13 | ITS | Intelligent Transportation System | PE | CRPU |  |  | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
DVRPC | 6 | Bucks | 81166 | US 13 & Tyburn Rd ITS Deployment | 13 | ITS | Intelligent Transportation System | CON | CRP |  |  | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 2000000
DVRPC | 6 | Bucks | 81294 | South Easton Road Trail | 1001 | SET | Bicycle Pedestrian Highway | CON | TAP | 2027-05-13 |  | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
DVRPC | 6 | Bucks | 81295 | Hulmeville Rd & Brown Ave Intersection Improvement | 513 | BBT | Congestion Reduction | PE | 581 |  |  | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
DVRPC | 6 | Bucks | 81295 | Hulmeville Rd & Brown Ave Intersection Improvement | 513 | BBT | Congestion Reduction | FD | STP |  |  | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
DVRPC | 6 | Bucks | 81295 | Hulmeville Rd & Brown Ave Intersection Improvement | 513 | BBT | Congestion Reduction | ROW | STP |  |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
DVRPC | 6 | Bucks | 81295 | Hulmeville Rd & Brown Ave Intersection Improvement | 513 | BBT | Congestion Reduction | UTL | STU |  |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Bucks | 81295 | Hulmeville Rd & Brown Ave Intersection Improvement | 513 | BBT | Congestion Reduction | CON | STP |  |  | 0 | 0 | 800000 | 800000 | 0 | 0 | 0 | 0 | 0 | 1600000
DVRPC | 6 | Bucks | 81721 | Bike Education/Safety Assemblies and Programs |  |  | Bicycle Pedestrian Highway | CON | TAP |  |  | 102029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102029
DVRPC | 6 | Bucks | 81881 | Valley Road Bridge R10 |  | MTF | Bridge Replacement | PE | LOC |  |  | 297449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297449
DVRPC | 6 | Bucks | 81881 | Valley Road Bridge R10 |  | MTF | Bridge Replacement | UTL | LOC |  |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
DVRPC | 6 | Bucks | 81881 | Valley Road Bridge R10 |  | MTF | Bridge Replacement | CON | 411 |  |  | 1547000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547000
DVRPC | 6 | Bucks | 81881 | Valley Road Bridge R10 |  | MTF | Bridge Replacement | CON | LOC |  |  | 132318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132318
DVRPC | 6 | Bucks | 82028 | Bucks County Electric Vehicle Charging Program |  | BEV | Electric Vehicle Charging Infrastructure | PE | CRP |  |  | 0 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
DVRPC | 6 | Bucks | 82028 | Bucks County Electric Vehicle Charging Program |  | BEV | Electric Vehicle Charging Infrastructure | FD | CRP |  |  | 0 | 79000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79000
DVRPC | 6 | Bucks | 82028 | Bucks County Electric Vehicle Charging Program |  | BEV | Electric Vehicle Charging Infrastructure | FD | CRPU |  |  | 0 | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111000
DVRPC | 6 | Bucks | 82028 | Bucks County Electric Vehicle Charging Program |  | BEV | Electric Vehicle Charging Infrastructure | CON | CRPU |  |  | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
DVRPC | 6 | Bucks | 84256 | Old Street Rd o/ SEPTA | 2043 | BOS | Bridge Replacement | ROW | STP | 2028-09-14 |  | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000
DVRPC | 6 | Bucks | 84256 | Old Street Rd o/ SEPTA | 2043 | BOS | Bridge Replacement | ROW | 185 | 2028-09-14 |  | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000
DVRPC | 6 | Bucks | 84256 | Old Street Rd o/ SEPTA | 2043 | BOS | Bridge Replacement | UTL | STP | 2028-09-14 |  | 0 | 437000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437000
DVRPC | 6 | Bucks | 84256 | Old Street Rd o/ SEPTA | 2043 | BOS | Bridge Replacement | UTL | 185 | 2028-09-14 |  | 0 | 109000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109000
DVRPC | 6 | Bucks | 84256 | Old Street Rd o/ SEPTA | 2043 | BOS | Bridge Replacement | CON | STP | 2028-09-14 |  | 0 | 874000 | 1748000 | 874000 | 0 | 0 | 0 | 0 | 0 | 3496000
DVRPC | 6 | Bucks | 84256 | Old Street Rd o/ SEPTA | 2043 | BOS | Bridge Replacement | CON | 185 | 2028-09-14 |  | 0 | 219000 | 438000 | 219000 | 0 | 0 | 0 | 0 | 0 | 876000
DVRPC | 6 | Bucks | 84258 | Pennsylvania Avenue over Delaware Canal | 2073 | BPA | Bridge Replacement | FD | STU | 2026-10-01 |  | 68000 | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262000
DVRPC | 6 | Bucks | 84258 | Pennsylvania Avenue over Delaware Canal | 2073 | BPA | Bridge Replacement | FD | 185 | 2026-10-01 |  | 17000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000
DVRPC | 6 | Bucks | 84258 | Pennsylvania Avenue over Delaware Canal | 2073 | BPA | Bridge Replacement | UTL | STU | 2026-10-01 |  | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99000
DVRPC | 6 | Bucks | 84258 | Pennsylvania Avenue over Delaware Canal | 2073 | BPA | Bridge Replacement | UTL | 185 | 2026-10-01 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
DVRPC | 6 | Bucks | 84258 | Pennsylvania Avenue over Delaware Canal | 2073 | BPA | Bridge Replacement | CON | BRIP | 2026-10-01 |  | 0 | 0 | 796000 | 796000 | 0 | 0 | 0 | 0 | 0 | 1592000
DVRPC | 6 | Bucks | 84258 | Pennsylvania Avenue over Delaware Canal | 2073 | BPA | Bridge Replacement | CON | STU | 2026-10-01 |  | 1591000 | 1591000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3182000
DVRPC | 6 | Bucks | 84258 | Pennsylvania Avenue over Delaware Canal | 2073 | BPA | Bridge Replacement | CON | 185 | 2026-10-01 |  | 398000 | 398000 | 299000 | 299000 | 0 | 0 | 0 | 0 | 0 | 1394000
DVRPC | 6 | Bucks | 84318 | CMAQ Reserve Line Item |  | SSS | Reserve Line Item | CON | CAQ |  |  | 0 | 9776314 | 6195000 | 3000000 | 808000 | 0 | 4345000 | 7407000 | 56986000 | 88517314
DVRPC | 6 | Bucks | 86244 | River Rd @GldnPheasnt o/ Del Canal | 32 | BDC | Bridge Replacement | FD | 185 | 2028-03-02 |  | 701000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 701000
DVRPC | 6 | Bucks | 86244 | River Rd @GldnPheasnt o/ Del Canal | 32 | BDC | Bridge Replacement | ROW | 185 | 2028-03-02 |  | 0 | 345000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345000
DVRPC | 6 | Bucks | 86244 | River Rd @GldnPheasnt o/ Del Canal | 32 | BDC | Bridge Replacement | UTL | 185 | 2028-03-02 |  | 0 | 0 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 157000
DVRPC | 6 | Bucks | 86244 | River Rd @GldnPheasnt o/ Del Canal | 32 | BDC | Bridge Replacement | CON | 185 | 2028-03-02 |  | 0 | 0 | 417000 | 3024000 | 0 | 0 | 0 | 0 | 0 | 3441000
DVRPC | 6 | Bucks | 86244 | River Rd @GldnPheasnt o/ Del Canal | 32 | BDC | Bridge Replacement | CON | 581 | 2028-03-02 |  | 0 | 0 | 2692000 | 0 | 0 | 0 | 0 | 0 | 0 | 2692000
DVRPC | 6 | Bucks | 86939 | US 202/PA 611 (Doylestown Byp) Preventative Maint | 611 | PM2 | Preventive Maintenance | PE | STU | 2027-04-29 |  | 1000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
DVRPC | 6 | Bucks | 88083 | Stoopville Phase II(D) | 2028 | SP2 | Bicycle Pedestrian Highway | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 802000 | 802000
DVRPC | 6 | Bucks | 88083 | Stoopville Phase II(D) | 2028 | SP2 | Bicycle Pedestrian Highway | ROW | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242000 | 242000
DVRPC | 6 | Bucks | 88083 | Stoopville Phase II(D) | 2028 | SP2 | Bicycle Pedestrian Highway | UTL | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263000 | 263000
DVRPC | 6 | Bucks | 88083 | Stoopville Phase II(D) | 2028 | SP2 | Bicycle Pedestrian Highway | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4442000 | 4442000
DVRPC | 6 | Bucks | 90550 | Creamery Rd over Tohickon Cr | 1014 | ERH | Bridge Replacement | PE | 185 | 2028-06-08 |  | 325000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675000
DVRPC | 6 | Bucks | 90550 | Creamery Rd over Tohickon Cr | 1014 | ERH | Bridge Replacement | ROW | STP | 2028-06-08 |  | 297000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297000
DVRPC | 6 | Bucks | 90550 | Creamery Rd over Tohickon Cr | 1014 | ERH | Bridge Replacement | ROW | 185 | 2028-06-08 |  | 74000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74000
DVRPC | 6 | Bucks | 90550 | Creamery Rd over Tohickon Cr | 1014 | ERH | Bridge Replacement | UTL | STP | 2028-06-08 |  | 0 | 46000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000
DVRPC | 6 | Bucks | 90550 | Creamery Rd over Tohickon Cr | 1014 | ERH | Bridge Replacement | UTL | 185 | 2028-06-08 |  | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
DVRPC | 6 | Bucks | 90550 | Creamery Rd over Tohickon Cr | 1014 | ERH | Bridge Replacement | CON | 185 | 2028-06-08 |  | 0 | 0 | 0 | 784000 | 2101000 | 3398000 | 0 | 0 | 0 | 6283000
DVRPC | 6 | Bucks | 92641 | Dublin Pike o/ Morgan Creek | 313 | BMC | Bridge Replacement | PE | 185 | 2027-12-16 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
DVRPC | 6 | Bucks | 92641 | Dublin Pike o/ Morgan Creek | 313 | BMC | Bridge Replacement | FD | STU | 2027-12-16 |  | 424000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000
DVRPC | 6 | Bucks | 92641 | Dublin Pike o/ Morgan Creek | 313 | BMC | Bridge Replacement | FD | 185 | 2027-12-16 |  | 106000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106000
DVRPC | 6 | Bucks | 92641 | Dublin Pike o/ Morgan Creek | 313 | BMC | Bridge Replacement | ROW | STU | 2027-12-16 |  | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000
DVRPC | 6 | Bucks | 92641 | Dublin Pike o/ Morgan Creek | 313 | BMC | Bridge Replacement | ROW | 185 | 2027-12-16 |  | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000
DVRPC | 6 | Bucks | 92641 | Dublin Pike o/ Morgan Creek | 313 | BMC | Bridge Replacement | UTL | STU | 2027-12-16 |  | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000
DVRPC | 6 | Bucks | 92641 | Dublin Pike o/ Morgan Creek | 313 | BMC | Bridge Replacement | UTL | 185 | 2027-12-16 |  | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000
DVRPC | 6 | Bucks | 92641 | Dublin Pike o/ Morgan Creek | 313 | BMC | Bridge Replacement | CON | BRIP | 2027-12-16 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 2884000 | 4384000
DVRPC | 6 | Bucks | 92641 | Dublin Pike o/ Morgan Creek | 313 | BMC | Bridge Replacement | CON | 185 | 2027-12-16 |  | 0 | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 721000 | 1096000
DVRPC | 6 | Bucks | 93445 | Route 1 Improvement-North (C) | 1 | RC2 | Highway Reconstruction | UTL | NHPP | 2021-01-14 | 2021-01-14 | 5920000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5920000
DVRPC | 6 | Bucks | 93445 | Route 1 Improvement-North (C) | 1 | RC2 | Highway Reconstruction | UTL | 581 | 2021-01-14 | 2021-01-14 | 1480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1480000
DVRPC | 6 | Bucks | 93445 | Route 1 Improvement-North (C) | 1 | RC2 | Highway Reconstruction | CON | NHPP | 2021-01-14 | 2021-01-14 | 0 | 1281000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1281000
DVRPC | 6 | Bucks | 93445 | Route 1 Improvement-North (C) | 1 | RC2 | Highway Reconstruction | CON | STP | 2021-01-14 | 2021-01-14 | 3389000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3389000
DVRPC | 6 | Bucks | 93445 | Route 1 Improvement-North (C) | 1 | RC2 | Highway Reconstruction | CON | STU | 2021-01-14 | 2021-01-14 | 8878690 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10878690
DVRPC | 6 | Bucks | 93445 | Route 1 Improvement-North (C) | 1 | RC2 | Highway Reconstruction | CON | SXF | 2021-01-14 | 2021-01-14 | 538567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538567
DVRPC | 6 | Bucks | 93445 | Route 1 Improvement-North (C) | 1 | RC2 | Highway Reconstruction | CON | 581 | 2021-01-14 | 2021-01-14 | 480000 | 820000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000
DVRPC | 6 | Bucks | 93446 | US 1: CSX to Corn Crib Rd (Frontage) | 1 | RC3 | Highway Reconstruction | ROW | 581 | 2029-06-28 |  | 0 | 0 | 1428000 | 1106000 | 250000 | 0 | 0 | 8500000 | 7563000 | 18847000
DVRPC | 6 | Bucks | 93446 | US 1: CSX to Corn Crib Rd (Frontage) | 1 | RC3 | Highway Reconstruction | UTL | NHPP | 2029-06-28 |  | 0 | 0 | 4052000 | 0 | 0 | 0 | 0 | 0 | 0 | 4052000
DVRPC | 6 | Bucks | 93446 | US 1: CSX to Corn Crib Rd (Frontage) | 1 | RC3 | Highway Reconstruction | CON | NHPP | 2029-06-28 |  | 0 | 0 | 0 | 14587000 | 10962000 | 0 | 0 | 16207000 | 61521000 | 103277000
DVRPC | 6 | Bucks | 93446 | US 1: CSX to Corn Crib Rd (Frontage) | 1 | RC3 | Highway Reconstruction | CON | STP | 2029-06-28 |  | 0 | 0 | 0 | 0 | 0 | 4020000 | 703000 | 0 | 0 | 4723000
DVRPC | 6 | Bucks | 93446 | US 1: CSX to Corn Crib Rd (Frontage) | 1 | RC3 | Highway Reconstruction | CON | STU | 2029-06-28 |  | 0 | 0 | 8962000 | 2755000 | 7231000 | 4172000 | 4239000 | 3000000 | 10311000 | 40670000
DVRPC | 6 | Bucks | 93446 | US 1: CSX to Corn Crib Rd (Frontage) | 1 | RC3 | Highway Reconstruction | CON | 581 | 2029-06-28 |  | 0 | 0 | 2241000 | 4336000 | 4548000 | 2043000 | 1236000 | 4802000 | 17959000 | 37165000
DVRPC | 6 | Bucks | 95447 | County/City Brdg Reserv |  |  | Reserve Line Item | CON | 183 |  |  | 0 | 251387 | 863000 | 504137 | 2918000 | 2937375 | 2109437 | 3146000 | 8332000 | 21061336
DVRPC | 6 | Bucks | 95447 | County/City Brdg Reserv |  |  | Reserve Line Item | CON | LOC |  |  | 1237760 | 0 | 331000 | 720534 | 896000 | 841125 | 630814 | 896000 | 3896000 | 9449233
DVRPC | 6 | Bucks | 99431 | John Fries Hwy: Rosenberger Rd - Allentown Rd | 663 | BRA | Additional Lanes | PE | 581 |  |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Bucks | 99431 | John Fries Hwy: Rosenberger Rd - Allentown Rd | 663 | BRA | Additional Lanes | FD | STP |  |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
DVRPC | 6 | Bucks | 99431 | John Fries Hwy: Rosenberger Rd - Allentown Rd | 663 | BRA | Additional Lanes | ROW | STP |  |  | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 350000
DVRPC | 6 | Bucks | 99431 | John Fries Hwy: Rosenberger Rd - Allentown Rd | 663 | BRA | Additional Lanes | UTL | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
DVRPC | 6 | Bucks | 99431 | John Fries Hwy: Rosenberger Rd - Allentown Rd | 663 | BRA | Additional Lanes | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
DVRPC | 6 | Bucks | 102272 | Holland Rd @ Buck Rd over Mill Creek | 532 | PH1 | Bridge Replacement | FD | 185 | 2027-03-11 |  | 310000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310000
DVRPC | 6 | Bucks | 102272 | Holland Rd @ Buck Rd over Mill Creek | 532 | PH1 | Bridge Replacement | ROW | 581 | 2027-03-11 |  | 457000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457000
DVRPC | 6 | Bucks | 102272 | Holland Rd @ Buck Rd over Mill Creek | 532 | PH1 | Bridge Replacement | CON | NHPP | 2027-03-11 |  | 0 | 0 | 2702000 | 1351000 | 0 | 0 | 0 | 0 | 0 | 4053000
DVRPC | 6 | Bucks | 102272 | Holland Rd @ Buck Rd over Mill Creek | 532 | PH1 | Bridge Replacement | CON | STU | 2027-03-11 |  | 0 | 0 | 0 | 0 | 2000000 | 4081000 | 0 | 0 | 0 | 6081000
DVRPC | 6 | Bucks | 102309 | PA 309 over Morgan Creek | 309 | MCB | Bridge Replacement | FD | NHPP | 2028-06-29 |  | 501000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501000
DVRPC | 6 | Bucks | 102309 | PA 309 over Morgan Creek | 309 | MCB | Bridge Replacement | FD | STP | 2028-06-29 |  | 0 | 699000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 699000
DVRPC | 6 | Bucks | 102309 | PA 309 over Morgan Creek | 309 | MCB | Bridge Replacement | FD | 185 | 2028-06-29 |  | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
DVRPC | 6 | Bucks | 102309 | PA 309 over Morgan Creek | 309 | MCB | Bridge Replacement | FD | 581 | 2028-06-29 |  | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
DVRPC | 6 | Bucks | 102309 | PA 309 over Morgan Creek | 309 | MCB | Bridge Replacement | ROW | STP | 2028-06-29 |  | 0 | 219000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000
DVRPC | 6 | Bucks | 102309 | PA 309 over Morgan Creek | 309 | MCB | Bridge Replacement | ROW | 581 | 2028-06-29 |  | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
DVRPC | 6 | Bucks | 102309 | PA 309 over Morgan Creek | 309 | MCB | Bridge Replacement | CON | BRIP | 2028-06-29 |  | 0 | 0 | 1000000 | 1351000 | 1702000 | 1351000 | 0 | 0 | 0 | 5404000
DVRPC | 6 | Bucks | 102309 | PA 309 over Morgan Creek | 309 | MCB | Bridge Replacement | CON | 581 | 2028-06-29 |  | 0 | 0 | 250000 | 338000 | 426000 | 338000 | 0 | 0 | 0 | 1352000
DVRPC | 6 | Bucks | 102664 | PA 309 over Beaver Run | 309 | BRB | Bridge Replacement | FD | NHPP | 2028-06-29 |  | 521000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521000
DVRPC | 6 | Bucks | 102664 | PA 309 over Beaver Run | 309 | BRB | Bridge Replacement | FD | STP | 2028-06-29 |  | 679000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679000
DVRPC | 6 | Bucks | 102664 | PA 309 over Beaver Run | 309 | BRB | Bridge Replacement | FD | 185 | 2028-06-29 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
DVRPC | 6 | Bucks | 102664 | PA 309 over Beaver Run | 309 | BRB | Bridge Replacement | ROW | STP | 2028-06-29 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
DVRPC | 6 | Bucks | 102664 | PA 309 over Beaver Run | 309 | BRB | Bridge Replacement | ROW | 581 | 2028-06-29 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
DVRPC | 6 | Bucks | 102664 | PA 309 over Beaver Run | 309 | BRB | Bridge Replacement | UTL | STP | 2028-06-29 |  | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
DVRPC | 6 | Bucks | 102664 | PA 309 over Beaver Run | 309 | BRB | Bridge Replacement | UTL | 581 | 2028-06-29 |  | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 56000
DVRPC | 6 | Bucks | 102664 | PA 309 over Beaver Run | 309 | BRB | Bridge Replacement | CON | 185 | 2028-06-29 |  | 0 | 0 | 1351000 | 2444000 | 3121000 | 0 | 0 | 0 | 0 | 6916000
DVRPC | 6 | Bucks | 104746 | W Bridge St o/Trib Delaware | 32 | BWB | Bridge Restoration | FD | BRIP | 2027-10-21 |  | 509000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 509000
DVRPC | 6 | Bucks | 104746 | W Bridge St o/Trib Delaware | 32 | BWB | Bridge Restoration | FD | 185 | 2027-10-21 |  | 127000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127000
DVRPC | 6 | Bucks | 104746 | W Bridge St o/Trib Delaware | 32 | BWB | Bridge Restoration | ROW | BRIP | 2027-10-21 |  | 0 | 109000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109000
DVRPC | 6 | Bucks | 104746 | W Bridge St o/Trib Delaware | 32 | BWB | Bridge Restoration | UTL | BRIP | 2027-10-21 |  | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 60000
DVRPC | 6 | Bucks | 104746 | W Bridge St o/Trib Delaware | 32 | BWB | Bridge Restoration | CON | BRIP | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2688000 | 2688000
DVRPC | 6 | Bucks | 104746 | W Bridge St o/Trib Delaware | 32 | BWB | Bridge Restoration | CON | 185 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672000 | 672000
DVRPC | 6 | Bucks | 110091 | King Road over Herkaken Creek | 7009 | MAP | Bridge Replacement | FD | BOF | 2026-08-13 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
DVRPC | 6 | Bucks | 110091 | King Road over Herkaken Creek | 7009 | MAP | Bridge Replacement | CON | STP | 2026-08-13 |  | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000
DVRPC | 6 | Bucks | 110091 | King Road over Herkaken Creek | 7009 | MAP | Bridge Replacement | CON | STP | 2026-08-13 |  | 653041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 653041
DVRPC | 6 | Bucks | 110091 | King Road over Herkaken Creek | 7009 | MAP | Bridge Replacement | CON | STU | 2026-08-13 |  | 346959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346959
DVRPC | 6 | Bucks | 110309 | I-95-US13/132 Slip Ramp | 13 | SLP | Congestion Reduction | FD | NHPP | 2028-10-05 |  | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
DVRPC | 6 | Bucks | 110309 | I-95-US13/132 Slip Ramp | 13 | SLP | Congestion Reduction | FD | 581 | 2028-10-05 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
DVRPC | 6 | Bucks | 110309 | I-95-US13/132 Slip Ramp | 13 | SLP | Congestion Reduction | ROW | 581 | 2028-10-05 |  | 752000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752000
DVRPC | 6 | Bucks | 110309 | I-95-US13/132 Slip Ramp | 13 | SLP | Congestion Reduction | CON | NHPP | 2028-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1843000 | 1843000
DVRPC | 6 | Bucks | 110309 | I-95-US13/132 Slip Ramp | 13 | SLP | Congestion Reduction | CON | STP | 2028-10-05 |  | 0 | 0 | 0 | 0 | 1686000 | 2843000 | 0 | 0 | 0 | 4529000
DVRPC | 6 | Bucks | 110309 | I-95-US13/132 Slip Ramp | 13 | SLP | Congestion Reduction | CON | STU | 2028-10-05 |  | 0 | 0 | 1843000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 2843000
DVRPC | 6 | Bucks | 110309 | I-95-US13/132 Slip Ramp | 13 | SLP | Congestion Reduction | CON | 581 | 2028-10-05 |  | 0 | 0 | 461000 | 250000 | 422000 | 711000 | 0 | 0 | 461000 | 2305000
DVRPC | 6 | Bucks | 110310 | Almshouse & Jacksonville Rd Roundabout | 2089 | ALM | Congestion Reduction | FD | 581 | 2026-12-10 |  | 637000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637000
DVRPC | 6 | Bucks | 110310 | Almshouse & Jacksonville Rd Roundabout | 2089 | ALM | Congestion Reduction | ROW | STP | 2026-12-10 |  | 637000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637000
DVRPC | 6 | Bucks | 110310 | Almshouse & Jacksonville Rd Roundabout | 2089 | ALM | Congestion Reduction | ROW | STU | 2026-12-10 |  | 0 | 163000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163000
DVRPC | 6 | Bucks | 110310 | Almshouse & Jacksonville Rd Roundabout | 2089 | ALM | Congestion Reduction | UTL | STU | 2026-12-10 |  | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
DVRPC | 6 | Bucks | 110310 | Almshouse & Jacksonville Rd Roundabout | 2089 | ALM | Congestion Reduction | CON | STP | 2026-12-10 |  | 0 | 875000 | 875000 | 375000 | 375000 | 1000000 | 0 | 0 | 0 | 3500000
DVRPC | 6 | Bucks | 110660 | Bridge Group V(C) | 4059 | HBV | Bridge Replacement | CON | 185 | 2021-12-16 | 2021-12-16 | 500000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000
DVRPC | 6 | Bucks | 110763 | Cold Spring Creamery Rd o/ Br Pine Run | 1004 | BB2 | Bridge Replacement | ROW | 185 | 2028-03-23 |  | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
DVRPC | 6 | Bucks | 110763 | Cold Spring Creamery Rd o/ Br Pine Run | 1004 | BB2 | Bridge Replacement | UTL | 185 | 2028-03-23 |  | 0 | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31000
DVRPC | 6 | Bucks | 110763 | Cold Spring Creamery Rd o/ Br Pine Run | 1004 | BB2 | Bridge Replacement | CON | 185 | 2028-03-23 |  | 0 | 867000 | 978000 | 0 | 0 | 0 | 0 | 0 | 0 | 1845000
DVRPC | 6 | Bucks | 110773 | Neshaminy Greenway Trail(C) |  | CCP | Bicycle Pedestrian Highway | CON | TAU | 2024-12-12 | 2025-01-16 | 136000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136000
DVRPC | 6 | Bucks | 111565 | Chapman Road over Pine Run(C) | 7205 | CPR | Bridge Replacement | CON | BOF | 2025-06-26 | 2025-06-26 | 634000 | 81200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715200
DVRPC | 6 | Bucks | 111565 | Chapman Road over Pine Run(C) | 7205 | CPR | Bridge Replacement | CON | BRIP | 2025-06-26 | 2025-06-26 | 560000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1060000
DVRPC | 6 | Bucks | 114096 | Falls Twp. Adaptive Signals(C) | 2037 | BFT | Congestion Reduction | CON | CAQ | 2025-12-11 | 2025-12-11 | 550000 | 1072000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1622000
DVRPC | 6 | Bucks | 115418 | PA 113 & Minsi Trail Road Roundabout | 113 | SIP | Safety Improvement | ROW | HSIP | 2027-01-15 |  | 263000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263000
DVRPC | 6 | Bucks | 115418 | PA 113 & Minsi Trail Road Roundabout | 113 | SIP | Safety Improvement | UTL | HSIP | 2027-01-15 |  | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000
DVRPC | 6 | Bucks | 115418 | PA 113 & Minsi Trail Road Roundabout | 113 | SIP | Safety Improvement | CON | HSIP | 2027-01-15 |  | 0 | 0 | 1093000 | 0 | 0 | 0 | 0 | 0 | 0 | 1093000
DVRPC | 6 | Bucks | 115419 | US 202 & York Rd Roundabout | 202 | SIP | Safety Improvement | FD | HSIP | 2027-01-15 |  | 470000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470000
DVRPC | 6 | Bucks | 115419 | US 202 & York Rd Roundabout | 202 | SIP | Safety Improvement | ROW | HSIP | 2027-01-15 |  | 1115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1115000
DVRPC | 6 | Bucks | 115419 | US 202 & York Rd Roundabout | 202 | SIP | Safety Improvement | UTL | HSIP | 2027-01-15 |  | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000
DVRPC | 6 | Bucks | 115419 | US 202 & York Rd Roundabout | 202 | SIP | Safety Improvement | CON | HSIP | 2027-01-15 |  | 0 | 0 | 1629000 | 0 | 0 | 0 | 0 | 0 | 0 | 1629000
DVRPC | 6 | Bucks | 115754 | Pennsylvania & Trenton Aves R6 & R7 | 2073 | MTF | MultiModal | PE | LOC |  |  | 47000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47000
DVRPC | 6 | Bucks | 115754 | Pennsylvania & Trenton Aves R6 & R7 | 2073 | MTF | MultiModal | CON | 411 |  |  | 377805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377805
DVRPC | 6 | Bucks | 115754 | Pennsylvania & Trenton Aves R6 & R7 | 2073 | MTF | MultiModal | CON | LOC |  |  | 66342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66342
DVRPC | 6 | Bucks | 116061 | Rockhill Dr & Neshaminy Blvd Intersection Imprvmnt | 2044 | RC3 | Additional Lanes | FD | NHPP | 2026-12-10 |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
DVRPC | 6 | Bucks | 116061 | Rockhill Dr & Neshaminy Blvd Intersection Imprvmnt | 2044 | RC3 | Additional Lanes | FD | 581 | 2026-12-10 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Bucks | 116061 | Rockhill Dr & Neshaminy Blvd Intersection Imprvmnt | 2044 | RC3 | Additional Lanes | ROW | STP | 2026-12-10 |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
DVRPC | 6 | Bucks | 116061 | Rockhill Dr & Neshaminy Blvd Intersection Imprvmnt | 2044 | RC3 | Additional Lanes | UTL | 581 | 2026-12-10 |  | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000
DVRPC | 6 | Bucks | 116728 | Callowhill Rd o/Br Pleasant Spring(C) | 4017 | IDA | Disaster Permanent Repair | CON | FFL | 2023-12-07 | 2023-12-07 | 12455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12455
DVRPC | 6 | Bucks | 116728 | Callowhill Rd o/Br Pleasant Spring(C) | 4017 | IDA | Disaster Permanent Repair | CON | 582 | 2023-12-07 | 2023-12-07 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
DVRPC | 6 | Bucks | 116893 | Edison Furlong Road over Pebble Creek | 2079 | BPC | Bridge Replacement | CON | 185 | 2027-11-04 |  | 0 | 0 | 550000 | 300000 | 0 | 0 | 0 | 0 | 0 | 850000
DVRPC | 6 | Bucks | 117953 | Newtown Rail Trail P2 |  | NRT | Bicycle Pedestrian Highway | CON | TAP | 2026-09-17 |  | 0 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000
DVRPC | 6 | Bucks | 117953 | Newtown Rail Trail P2 |  | NRT | Bicycle Pedestrian Highway | CON | TAU | 2026-09-17 |  | 0 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
DVRPC | 6 | Bucks | 118020 | 2nd Street & Bustleton Pikes Intersection Imprvmnt | 232 | BNR | Congestion Reduction | FD | STU | 2028-09-14 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
DVRPC | 6 | Bucks | 118020 | 2nd Street & Bustleton Pikes Intersection Imprvmnt | 232 | BNR | Congestion Reduction | ROW | 581 | 2028-09-14 |  | 0 | 0 | 0 | 405000 | 0 | 0 | 0 | 0 | 0 | 405000
DVRPC | 6 | Bucks | 118020 | 2nd Street & Bustleton Pikes Intersection Imprvmnt | 232 | BNR | Congestion Reduction | UTL | 581 | 2028-09-14 |  | 0 | 0 | 141000 | 0 | 0 | 0 | 0 | 0 | 0 | 141000
DVRPC | 6 | Bucks | 118020 | 2nd Street & Bustleton Pikes Intersection Imprvmnt | 232 | BNR | Congestion Reduction | CON | STU | 2028-09-14 |  | 0 | 0 | 1415000 | 0 | 0 | 0 | 0 | 0 | 3282000 | 4697000
DVRPC | 6 | Bucks | 118020 | 2nd Street & Bustleton Pikes Intersection Imprvmnt | 232 | BNR | Congestion Reduction | CON | 581 | 2028-09-14 |  | 0 | 0 | 354000 | 0 | 0 | 0 | 0 | 0 | 820000 | 1174000
DVRPC | 6 | Bucks | 118022 | US 202 & PA 179 Roundabout | 202 | BSR | Safety Improvement | PE | STU | 2028-03-02 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Bucks | 118022 | US 202 & PA 179 Roundabout | 202 | BSR | Safety Improvement | FD | STU | 2028-03-02 |  | 255000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000
DVRPC | 6 | Bucks | 118022 | US 202 & PA 179 Roundabout | 202 | BSR | Safety Improvement | FD | 581 | 2028-03-02 |  | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64000
DVRPC | 6 | Bucks | 118022 | US 202 & PA 179 Roundabout | 202 | BSR | Safety Improvement | ROW | STU | 2028-03-02 |  | 212000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212000
DVRPC | 6 | Bucks | 118022 | US 202 & PA 179 Roundabout | 202 | BSR | Safety Improvement | ROW | 581 | 2028-03-02 |  | 53000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53000
DVRPC | 6 | Bucks | 118022 | US 202 & PA 179 Roundabout | 202 | BSR | Safety Improvement | UTL | STU | 2028-03-02 |  | 0 | 219000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000
DVRPC | 6 | Bucks | 118022 | US 202 & PA 179 Roundabout | 202 | BSR | Safety Improvement | UTL | 581 | 2028-03-02 |  | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
DVRPC | 6 | Bucks | 118022 | US 202 & PA 179 Roundabout | 202 | BSR | Safety Improvement | CON | STU | 2028-03-02 |  | 0 | 748000 | 1748000 | 1748000 | 2748000 | 0 | 0 | 0 | 0 | 6992000
DVRPC | 6 | Bucks | 118022 | US 202 & PA 179 Roundabout | 202 | BSR | Safety Improvement | CON | 581 | 2028-03-02 |  | 0 | 187000 | 437000 | 437000 | 687000 | 0 | 0 | 0 | 0 | 1748000
DVRPC | 6 | Bucks | 118190 | Fairview Rd RR Xing |  | 401 | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 125000 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
DVRPC | 6 | Bucks | 120275 | Middletown Twp School Zone Pedestrian Safety R9 | 2029 | MTF | Bicycle and Pedestrian Facilities Transit | PE | LOC |  |  | 55062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55062
DVRPC | 6 | Bucks | 120275 | Middletown Twp School Zone Pedestrian Safety R9 | 2029 | MTF | Bicycle and Pedestrian Facilities Transit | CON | 411 |  |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
DVRPC | 6 | Bucks | 120275 | Middletown Twp School Zone Pedestrian Safety R9 | 2029 | MTF | Bicycle and Pedestrian Facilities Transit | CON | LOC |  |  | 35883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35883
DVRPC | 6 | Bucks | 120912 | Trumbauersville Road o/ Unami Creek | 4051 | TUC | Bridge Replacement | PE | BOF | 2028-09-14 |  | 500000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000
DVRPC | 6 | Bucks | 120912 | Trumbauersville Road o/ Unami Creek | 4051 | TUC | Bridge Replacement | FD | BOF | 2028-09-14 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Bucks | 120912 | Trumbauersville Road o/ Unami Creek | 4051 | TUC | Bridge Replacement | ROW | BOF | 2028-09-14 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Bucks | 120912 | Trumbauersville Road o/ Unami Creek | 4051 | TUC | Bridge Replacement | UTL | BOF | 2028-09-14 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Bucks | 120912 | Trumbauersville Road o/ Unami Creek | 4051 | TUC | Bridge Replacement | CON | BOF | 2028-09-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
DVRPC | 6 | Chester | 14134 | W Bridge St O/AMTRAK | 7410 | BRG | Bridge Replacement | FD | BOF | 2027-03-11 |  | 416000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416000
DVRPC | 6 | Chester | 14134 | W Bridge St O/AMTRAK | 7410 | BRG | Bridge Replacement | FD | 183 | 2027-03-11 |  | 78000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78000
DVRPC | 6 | Chester | 14134 | W Bridge St O/AMTRAK | 7410 | BRG | Bridge Replacement | FD | LOC | 2027-03-11 |  | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000
DVRPC | 6 | Chester | 14134 | W Bridge St O/AMTRAK | 7410 | BRG | Bridge Replacement | UTL | 183 | 2027-03-11 |  | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
DVRPC | 6 | Chester | 14134 | W Bridge St O/AMTRAK | 7410 | BRG | Bridge Replacement | UTL | LOC | 2027-03-11 |  | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
DVRPC | 6 | Chester | 14134 | W Bridge St O/AMTRAK | 7410 | BRG | Bridge Replacement | CON | BOF | 2027-03-11 |  | 0 | 1132000 | 970000 | 1940000 | 1940000 | 808000 | 0 | 0 | 0 | 6790000
DVRPC | 6 | Chester | 14134 | W Bridge St O/AMTRAK | 7410 | BRG | Bridge Replacement | CON | 183 | 2027-03-11 |  | 0 | 212000 | 182000 | 364000 | 364000 | 152000 | 0 | 0 | 0 | 1274000
DVRPC | 6 | Chester | 14134 | W Bridge St O/AMTRAK | 7410 | BRG | Bridge Replacement | CON | LOC | 2027-03-11 |  | 0 | 72000 | 61000 | 122000 | 122000 | 50000 | 0 | 0 | 0 | 427000
DVRPC | 6 | Chester | 14330 | Garrett Mill Road (T-695) over Ridley Creek | 7256 | BRG | Bridge Restoration | FD | 183 |  |  | 0 | 0 | 134400 | 0 | 0 | 0 | 0 | 0 | 0 | 134400
DVRPC | 6 | Chester | 14330 | Garrett Mill Road (T-695) over Ridley Creek | 7256 | BRG | Bridge Restoration | FD | LOC |  |  | 0 | 0 | 33600 | 0 | 0 | 0 | 0 | 0 | 0 | 33600
DVRPC | 6 | Chester | 14330 | Garrett Mill Road (T-695) over Ridley Creek | 7256 | BRG | Bridge Restoration | CON | 183 |  |  | 0 | 0 | 486400 | 0 | 0 | 0 | 0 | 0 | 0 | 486400
DVRPC | 6 | Chester | 14330 | Garrett Mill Road (T-695) over Ridley Creek | 7256 | BRG | Bridge Restoration | CON | LOC |  |  | 0 | 0 | 121600 | 0 | 0 | 0 | 0 | 0 | 0 | 121600
DVRPC | 6 | Chester | 14484 | PA 41 Imprvmnt Study (Parent) | 41 | STY | Study Phase of Project | PE | STU |  |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Chester | 14532 | US 30: PA 10 - Exton Byp (Parent) | 30 | 100 | Highway Reconstruction | PE | NHPP |  |  | 0 | 5029000 | 1084000 | 2771000 | 0 | 0 | 0 | 0 | 0 | 8884000
DVRPC | 6 | Chester | 14532 | US 30: PA 10 - Exton Byp (Parent) | 30 | 100 | Highway Reconstruction | PE | STU |  |  | 2000000 | 0 | 2116000 | 0 | 5000000 | 0 | 0 | 0 | 0 | 9116000
DVRPC | 6 | Chester | 14541 | US 1: Partnership Phs 2(C) | 1 | H02 | Additional Lanes | CON | NHPP | 2022-08-25 | 2022-08-25 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
DVRPC | 6 | Chester | 14580 | US 1: PA 472 - PA 896 | 1 | 100 | Highway Reconstruction | ROW | STU | 2028-08-24 |  | 2701000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2701000
DVRPC | 6 | Chester | 14580 | US 1: PA 472 - PA 896 | 1 | 100 | Highway Reconstruction | UTL | STU | 2028-08-24 |  | 546000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546000
DVRPC | 6 | Chester | 14580 | US 1: PA 472 - PA 896 | 1 | 100 | Highway Reconstruction | CON | BOF | 2028-08-24 |  | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 2000000
DVRPC | 6 | Chester | 14580 | US 1: PA 472 - PA 896 | 1 | 100 | Highway Reconstruction | CON | NHPP | 2028-08-24 |  | 0 | 1632000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1632000
DVRPC | 6 | Chester | 14580 | US 1: PA 472 - PA 896 | 1 | 100 | Highway Reconstruction | CON | STU | 2028-08-24 |  | 0 | 799000 | 3431000 | 3431000 | 10757000 | 3431000 | 6105000 | 12431000 | 48724000 | 89109000
DVRPC | 6 | Chester | 14580 | US 1: PA 472 - PA 896 | 1 | 100 | Highway Reconstruction | CON | 581 | 2028-08-24 |  | 0 | 608000 | 858000 | 858000 | 2689000 | 1358000 | 1526000 | 3108000 | 12182000 | 23187000
DVRPC | 6 | Chester | 14581 | US 1: PA 896 - PA 41 | 1 | 200 | Highway Reconstruction | FD | NHPP | 2029-04-12 |  | 5628000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5628000
DVRPC | 6 | Chester | 14581 | US 1: PA 896 - PA 41 | 1 | 200 | Highway Reconstruction | FD | 581 | 2029-04-12 |  | 1407000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1407000
DVRPC | 6 | Chester | 14581 | US 1: PA 896 - PA 41 | 1 | 200 | Highway Reconstruction | ROW | STU | 2029-04-12 |  | 1521000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1521000
DVRPC | 6 | Chester | 14581 | US 1: PA 896 - PA 41 | 1 | 200 | Highway Reconstruction | UTL | STU | 2029-04-12 |  | 0 | 0 | 0 | 277000 | 0 | 0 | 0 | 0 | 0 | 277000
DVRPC | 6 | Chester | 14581 | US 1: PA 896 - PA 41 | 1 | 200 | Highway Reconstruction | UTL | 581 | 2029-04-12 |  | 0 | 0 | 0 | 69000 | 0 | 0 | 0 | 0 | 0 | 69000
DVRPC | 6 | Chester | 14581 | US 1: PA 896 - PA 41 | 1 | 200 | Highway Reconstruction | CON | NHPP | 2029-04-12 |  | 0 | 0 | 0 | 15000000 | 15000000 | 0 | 0 | 0 | 0 | 30000000
DVRPC | 6 | Chester | 14581 | US 1: PA 896 - PA 41 | 1 | 200 | Highway Reconstruction | CON | BOF | 2029-04-12 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Chester | 14581 | US 1: PA 896 - PA 41 | 1 | 200 | Highway Reconstruction | CON | NHPP | 2029-04-12 |  | 0 | 0 | 0 | 0 | 0 | 4867000 | 15492000 | 3654000 | 26242000 | 50255000
DVRPC | 6 | Chester | 14581 | US 1: PA 896 - PA 41 | 1 | 200 | Highway Reconstruction | CON | STU | 2029-04-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12213000 | 0 | 12213000
DVRPC | 6 | Chester | 14581 | US 1: PA 896 - PA 41 | 1 | 200 | Highway Reconstruction | CON | 581 | 2029-04-12 |  | 0 | 0 | 0 | 3750000 | 3750000 | 1467000 | 3873000 | 3966000 | 6560000 | 23366000
DVRPC | 6 | Chester | 14652 | Dutton Mill Rd o/ Ridley Crk (CB #157) | 7015 | 157 | Bridge Replacement | FD | 183 | 2027-12-16 |  | 656000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656000
DVRPC | 6 | Chester | 14652 | Dutton Mill Rd o/ Ridley Crk (CB #157) | 7015 | 157 | Bridge Replacement | ROW | 183 | 2027-12-16 |  | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56000
DVRPC | 6 | Chester | 14652 | Dutton Mill Rd o/ Ridley Crk (CB #157) | 7015 | 157 | Bridge Replacement | UTL | 183 | 2027-12-16 |  | 0 | 0 | 0 | 0 | 61000 | 0 | 0 | 0 | 0 | 61000
DVRPC | 6 | Chester | 14652 | Dutton Mill Rd o/ Ridley Crk (CB #157) | 7015 | 157 | Bridge Replacement | CON | BRIP | 2027-12-16 |  | 0 | 0 | 0 | 0 | 0 | 4687000 | 0 | 0 | 0 | 4687000
DVRPC | 6 | Chester | 14698 | US422: Schuylkill River Brg to W of Keim St. | 422 | M2B | Highway Reconstruction | FD | NHPP | 2027-12-16 |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
DVRPC | 6 | Chester | 14698 | US422: Schuylkill River Brg to W of Keim St. | 422 | M2B | Highway Reconstruction | FD | 581 | 2027-12-16 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
DVRPC | 6 | Chester | 14698 | US422: Schuylkill River Brg to W of Keim St. | 422 | M2B | Highway Reconstruction | ROW | NHPP | 2027-12-16 |  | 2122000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2122000
DVRPC | 6 | Chester | 14698 | US422: Schuylkill River Brg to W of Keim St. | 422 | M2B | Highway Reconstruction | ROW | 581 | 2027-12-16 |  | 530000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530000
DVRPC | 6 | Chester | 14698 | US422: Schuylkill River Brg to W of Keim St. | 422 | M2B | Highway Reconstruction | UTL | NHPP | 2027-12-16 |  | 2546000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2546000
DVRPC | 6 | Chester | 14698 | US422: Schuylkill River Brg to W of Keim St. | 422 | M2B | Highway Reconstruction | UTL | 581 | 2027-12-16 |  | 637000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637000
DVRPC | 6 | Chester | 14698 | US422: Schuylkill River Brg to W of Keim St. | 422 | M2B | Highway Reconstruction | CON | NHPP | 2027-12-16 |  | 0 | 20000000 | 20000000 | 16000000 | 0 | 0 | 0 | 0 | 0 | 56000000
DVRPC | 6 | Chester | 14698 | US422: Schuylkill River Brg to W of Keim St. | 422 | M2B | Highway Reconstruction | CON | NHPP | 2027-12-16 |  | 0 | 0 | 17545000 | 17545000 | 8773000 | 8773000 | 0 | 0 | 0 | 52636000
DVRPC | 6 | Chester | 14698 | US422: Schuylkill River Brg to W of Keim St. | 422 | M2B | Highway Reconstruction | CON | 581 | 2027-12-16 |  | 9000000 | 5000000 | 4386000 | 4386000 | 2193000 | 2193000 | 0 | 0 | 0 | 27158000
DVRPC | 6 | Chester | 47979 | Relocated N Valley Rd over Amtrak | 1005 | PTC | Bridge Replacement | CON | BRIP | 2027-07-15 |  | 0 | 0 | 2416000 | 4416000 | 6000000 | 0 | 0 | 0 | 9627200 | 22459200
DVRPC | 6 | Chester | 47979 | Relocated N Valley Rd over Amtrak | 1005 | PTC | Bridge Replacement | CON | STU | 2027-07-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800000 | 3800000
DVRPC | 6 | Chester | 47979 | Relocated N Valley Rd over Amtrak | 1005 | PTC | Bridge Replacement | CON | 185 | 2027-07-15 |  | 0 | 0 | 604000 | 1104000 | 1500000 | 0 | 0 | 0 | 3356800 | 6564800
DVRPC | 6 | Chester | 48203 | Aerial Photography |  |  | Safety Improvement | STUDY | STU |  |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
DVRPC | 6 | Chester | 57677 | Doe Run Road over Doe Run(C) | 82 | CDR | Bridge Restoration | CON | 185 | 2025-01-16 | 2025-01-16 | 1448160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448160
DVRPC | 6 | Chester | 61936 | Structure Hardening Group 2026 (Scour) | 202 | SCR | Bridge Restoration | PE | PRTCT | 2026-07-02 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
DVRPC | 6 | Chester | 61936 | Structure Hardening Group 2026 (Scour) | 202 | SCR | Bridge Restoration | CON | PRTCT | 2026-07-02 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Chester | 64220 | US 422: Keim St & PA 724 Interchanges | 422 | M03 | Highway Reconstruction | ROW | NHPP | 2028-08-24 |  | 0 | 2623000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2623000
DVRPC | 6 | Chester | 64220 | US 422: Keim St & PA 724 Interchanges | 422 | M03 | Highway Reconstruction | ROW | 581 | 2028-08-24 |  | 0 | 656000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656000
DVRPC | 6 | Chester | 64220 | US 422: Keim St & PA 724 Interchanges | 422 | M03 | Highway Reconstruction | UTL | NHPP | 2028-08-24 |  | 0 | 0 | 0 | 0 | 608000 | 0 | 0 | 0 | 0 | 608000
DVRPC | 6 | Chester | 64220 | US 422: Keim St & PA 724 Interchanges | 422 | M03 | Highway Reconstruction | UTL | 581 | 2028-08-24 |  | 0 | 0 | 0 | 0 | 152000 | 0 | 0 | 0 | 0 | 152000
DVRPC | 6 | Chester | 64220 | US 422: Keim St & PA 724 Interchanges | 422 | M03 | Highway Reconstruction | CON | NHPP | 2028-08-24 |  | 0 | 0 | 0 | 0 | 8735000 | 0 | 0 | 3693000 | 58940000 | 71368000
DVRPC | 6 | Chester | 64220 | US 422: Keim St & PA 724 Interchanges | 422 | M03 | Highway Reconstruction | CON | STP | 2028-08-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9042000 | 0 | 9042000
DVRPC | 6 | Chester | 64220 | US 422: Keim St & PA 724 Interchanges | 422 | M03 | Highway Reconstruction | CON | STU | 2028-08-24 |  | 0 | 0 | 0 | 0 | 0 | 3735000 | 6735000 | 0 | 10000000 | 20470000
DVRPC | 6 | Chester | 64220 | US 422: Keim St & PA 724 Interchanges | 422 | M03 | Highway Reconstruction | CON | 581 | 2028-08-24 |  | 0 | 0 | 0 | 0 | 2184000 | 934000 | 1684000 | 3184000 | 17486000 | 25472000
DVRPC | 6 | Chester | 78530 | Forest Manor Rd over Branch Elk Creek | 7015 | 318 | Bridge Replacement | PE | BOF |  |  | 0 | 227000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227000
DVRPC | 6 | Chester | 78530 | Forest Manor Rd over Branch Elk Creek | 7015 | 318 | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 300000
DVRPC | 6 | Chester | 78530 | Forest Manor Rd over Branch Elk Creek | 7015 | 318 | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
DVRPC | 6 | Chester | 78530 | Forest Manor Rd over Branch Elk Creek | 7015 | 318 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 940000 | 940000
DVRPC | 6 | Chester | 78617 | PA 41 over E Br White Clay Ck | 41 | B41 | Bridge Restoration | PE | STP | 2028-03-15 |  | 478000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 478000
DVRPC | 6 | Chester | 78617 | PA 41 over E Br White Clay Ck | 41 | B41 | Bridge Restoration | PE | 185 | 2028-03-15 |  | 119000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119000
DVRPC | 6 | Chester | 78617 | PA 41 over E Br White Clay Ck | 41 | B41 | Bridge Restoration | FD | 185 | 2028-03-15 |  | 0 | 100000 | 250000 | 415000 | 0 | 0 | 0 | 0 | 0 | 765000
DVRPC | 6 | Chester | 78617 | PA 41 over E Br White Clay Ck | 41 | B41 | Bridge Restoration | ROW | 185 | 2028-03-15 |  | 0 | 311000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 1311000
DVRPC | 6 | Chester | 78617 | PA 41 over E Br White Clay Ck | 41 | B41 | Bridge Restoration | UTL | STP | 2028-03-15 |  | 0 | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
DVRPC | 6 | Chester | 78617 | PA 41 over E Br White Clay Ck | 41 | B41 | Bridge Restoration | UTL | 185 | 2028-03-15 |  | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
DVRPC | 6 | Chester | 78617 | PA 41 over E Br White Clay Ck | 41 | B41 | Bridge Restoration | CON | BRIP | 2028-03-15 |  | 0 | 0 | 460144 | 676000 | 2849000 | 1014856 | 0 | 0 | 0 | 5000000
DVRPC | 6 | Chester | 81744 | Chester Valley Trail: Whitford Rd - Old Trolley Rd |  | CV3 | Air Quality | CON | CRPU |  |  | 0 | 0 | 0 | 2000000 | 3096000 | 904000 | 0 | 0 | 0 | 6000000
DVRPC | 6 | Chester | 81794 | Route 100 Trail: Graphite Mine Rd - Fellowship Rd |  | RPP | Bicycle Pedestrian Highway | CON | TAP | 2027-05-13 |  | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
DVRPC | 6 | Chester | 81887 | Bridge and Starr Streets R10 | 29 | MT3 | Congestion Reduction | CON | 411 |  |  | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
DVRPC | 6 | Chester | 81887 | Bridge and Starr Streets R10 | 29 | MT3 | Congestion Reduction | CON | LOC |  |  | 1716729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1716729
DVRPC | 6 | Chester | 81888 | Niblock Alley R10 | 7409 | MTF | Highway Reconstruction | CON | 411 |  |  | 0 | 854356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 854356
DVRPC | 6 | Chester | 81889 | Prospect Ave Pedestrian Improvements R10 | 841 | MTF | Safety Improvement | CON | 411 |  |  | 513530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513530
DVRPC | 6 | Chester | 82015 | North Valley Road Caisson Installation(C) | 1005 | CAI | Bridge Replacement | CON | STU | 2026-03-26 | 2026-03-26 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
DVRPC | 6 | Chester | 82018 | Harmony Hill Road over Valley Creek | 7015 | 278 | Bridge Replacement | PE | BOF |  |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
DVRPC | 6 | Chester | 82018 | Harmony Hill Road over Valley Creek | 7015 | 278 | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 0 | 0 | 240000
DVRPC | 6 | Chester | 82018 | Harmony Hill Road over Valley Creek | 7015 | 278 | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
DVRPC | 6 | Chester | 82018 | Harmony Hill Road over Valley Creek | 7015 | 278 | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
DVRPC | 6 | Chester | 82018 | Harmony Hill Road over Valley Creek | 7015 | 278 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000 | 1300000
DVRPC | 6 | Chester | 82031 | Chester County EV Charging Program - Phase II |  | CE2 | Electric Vehicle Charging Infrastructure | PE | CRPU |  |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Chester | 82031 | Chester County EV Charging Program - Phase II |  | CE2 | Electric Vehicle Charging Infrastructure | FD | CRPU |  |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
DVRPC | 6 | Chester | 82031 | Chester County EV Charging Program - Phase II |  | CE2 | Electric Vehicle Charging Infrastructure | CON | CRPU |  |  | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000
DVRPC | 6 | Chester | 82075 | Pocopson Road @ Street Rd | 3023 | CPR | Congestion Reduction | PE | 581 |  |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
DVRPC | 6 | Chester | 82075 | Pocopson Road @ Street Rd | 3023 | CPR | Congestion Reduction | FD | STP |  |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
DVRPC | 6 | Chester | 82075 | Pocopson Road @ Street Rd | 3023 | CPR | Congestion Reduction | ROW | STP |  |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Chester | 82075 | Pocopson Road @ Street Rd | 3023 | CPR | Congestion Reduction | UTL | STP |  |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Chester | 82075 | Pocopson Road @ Street Rd | 3023 | CPR | Congestion Reduction | CON | 581 |  |  | 0 | 0 | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 1750000
DVRPC | 6 | Chester | 84284 | Doe Run Road over Buck Run | 82 | DRR | Bridge Replacement | FD | STU | 2026-11-05 |  | 780000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780000
DVRPC | 6 | Chester | 84284 | Doe Run Road over Buck Run | 82 | DRR | Bridge Replacement | ROW | 185 | 2026-11-05 |  | 0 | 164000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164000
DVRPC | 6 | Chester | 84284 | Doe Run Road over Buck Run | 82 | DRR | Bridge Replacement | UTL | 185 | 2026-11-05 |  | 0 | 0 | 113000 | 0 | 0 | 0 | 0 | 0 | 0 | 113000
DVRPC | 6 | Chester | 84284 | Doe Run Road over Buck Run | 82 | DRR | Bridge Replacement | CON | 185 | 2026-11-05 |  | 0 | 0 | 602000 | 1000000 | 2000000 | 0 | 0 | 0 | 0 | 3602000
DVRPC | 6 | Chester | 85949 | PA 896 Safety: Elbow Ln - Shepherd Ln | 896 | SIP | Safety Improvement | CON | HSIP | 2026-09-17 |  | 11670000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11670000
DVRPC | 6 | Chester | 85949 | PA 896 Safety: Elbow Ln - Shepherd Ln | 896 | SIP | Safety Improvement | CON | STP | 2026-09-17 |  | 3029000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3029000
DVRPC | 6 | Chester | 86064 | Hadfield Road o/ Beaver Creek(C) | 7015 | 244 | Bridge Replacement | CON | BOF | 2024-01-25 | 2024-01-25 | 236000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236000
DVRPC | 6 | Chester | 86064 | Hadfield Road o/ Beaver Creek(C) | 7015 | 244 | Bridge Replacement | CON | 183 | 2024-01-25 | 2024-01-25 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44000
DVRPC | 6 | Chester | 86064 | Hadfield Road o/ Beaver Creek(C) | 7015 | 244 | Bridge Replacement | CON | LOC | 2024-01-25 | 2024-01-25 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
DVRPC | 6 | Chester | 86272 | Coventryville Rd over French Ck | 7015 | 198 | Bridge Replacement | PE | BOF |  |  | 0 | 537000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537000
DVRPC | 6 | Chester | 86272 | Coventryville Rd over French Ck | 7015 | 198 | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000
DVRPC | 6 | Chester | 86272 | Coventryville Rd over French Ck | 7015 | 198 | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000
DVRPC | 6 | Chester | 86272 | Coventryville Rd over French Ck | 7015 | 198 | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
DVRPC | 6 | Chester | 86272 | Coventryville Rd over French Ck | 7015 | 198 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1610000 | 1610000
DVRPC | 6 | Chester | 86276 | Township Rd o/ W Br Big Elk Crk(C) | 7015 | 297 | Bridge Replacement | CON | STP | 2025-09-11 | 2025-09-11 | 1270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000
DVRPC | 6 | Chester | 86276 | Township Rd o/ W Br Big Elk Crk(C) | 7015 | 297 | Bridge Replacement | CON | BOF | 2025-09-11 | 2025-09-11 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000
DVRPC | 6 | Chester | 86288 | Skelp Level Road over former NS Rail(R) | 7205 | BRG | Bridge Replacement | FD | 183 |  | 2024-06-13 | 0 | 102000 | 228400 | 0 | 0 | 0 | 0 | 0 | 0 | 330400
DVRPC | 6 | Chester | 86288 | Skelp Level Road over former NS Rail(R) | 7205 | BRG | Bridge Replacement | FD | LOC |  | 2024-06-13 | 0 | 22500 | 57100 | 0 | 0 | 0 | 0 | 0 | 0 | 79600
DVRPC | 6 | Chester | 86288 | Skelp Level Road over former NS Rail(R) | 7205 | BRG | Bridge Replacement | CON | 183 |  | 2024-06-13 | 0 | 0 | 3440000 | 0 | 0 | 0 | 0 | 0 | 0 | 3440000
DVRPC | 6 | Chester | 86288 | Skelp Level Road over former NS Rail(R) | 7205 | BRG | Bridge Replacement | CON | LOC |  | 2024-06-13 | 0 | 0 | 860000 | 0 | 0 | 0 | 0 | 0 | 0 | 860000
DVRPC | 6 | Chester | 86301 | Lancaster Ave over E Br Brandywine Ck | 322 | DOW | Bridge Restoration | CON | STP | 2030-01-17 |  | 0 | 0 | 1242000 | 621000 | 863000 | 1242000 | 2242000 | 0 | 0 | 6210000
DVRPC | 6 | Chester | 86301 | Lancaster Ave over E Br Brandywine Ck | 322 | DOW | Bridge Restoration | CON | 581 | 2030-01-17 |  | 0 | 0 | 311000 | 155000 | 216000 | 311000 | 561000 | 0 | 0 | 1554000
DVRPC | 6 | Chester | 86302 | Ewing Rd Bridges o/ Middle Br White Clay Cr | 3044 | CBA | Bridge Replacement | FD | 185 | 2027-07-29 |  | 149000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149000
DVRPC | 6 | Chester | 86302 | Ewing Rd Bridges o/ Middle Br White Clay Cr | 3044 | CBA | Bridge Replacement | ROW | 185 | 2027-07-29 |  | 119000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119000
DVRPC | 6 | Chester | 86302 | Ewing Rd Bridges o/ Middle Br White Clay Cr | 3044 | CBA | Bridge Replacement | UTL | 185 | 2027-07-29 |  | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000
DVRPC | 6 | Chester | 86302 | Ewing Rd Bridges o/ Middle Br White Clay Cr | 3044 | CBA | Bridge Replacement | CON | 185 | 2027-07-29 |  | 0 | 0 | 1131000 | 500000 | 0 | 0 | 0 | 0 | 0 | 1631000
DVRPC | 6 | Chester | 87781 | US 30: Reeceville to Quarry Rd | 30 | CER | Highway Reconstruction | PE | STP | 2033-11-10 |  | 0 | 0 | 3938000 | 3995000 | 0 | 0 | 0 | 0 | 0 | 7933000
DVRPC | 6 | Chester | 87781 | US 30: Reeceville to Quarry Rd | 30 | CER | Highway Reconstruction | PE | STU | 2033-11-10 |  | 2957000 | 2957000 | 3024000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 13938000
DVRPC | 6 | Chester | 87781 | US 30: Reeceville to Quarry Rd | 30 | CER | Highway Reconstruction | FD | STU | 2033-11-10 |  | 0 | 0 | 0 | 1643000 | 4889000 | 12500000 | 12500000 | 0 | 0 | 31532000
DVRPC | 6 | Chester | 87781 | US 30: Reeceville to Quarry Rd | 30 | CER | Highway Reconstruction | FD | 581 | 2033-11-10 |  | 0 | 0 | 0 | 411000 | 1222000 | 3125000 | 3125000 | 0 | 0 | 7883000
DVRPC | 6 | Chester | 87781 | US 30: Reeceville to Quarry Rd | 30 | CER | Highway Reconstruction | ROW | STU | 2033-11-10 |  | 0 | 0 | 0 | 0 | 4864000 | 0 | 0 | 0 | 0 | 4864000
DVRPC | 6 | Chester | 87781 | US 30: Reeceville to Quarry Rd | 30 | CER | Highway Reconstruction | ROW | 581 | 2033-11-10 |  | 0 | 0 | 0 | 0 | 1216000 | 0 | 0 | 0 | 0 | 1216000
DVRPC | 6 | Chester | 87781 | US 30: Reeceville to Quarry Rd | 30 | CER | Highway Reconstruction | UTL | STU | 2033-11-10 |  | 0 | 0 | 0 | 0 | 0 | 984000 | 0 | 0 | 0 | 984000
DVRPC | 6 | Chester | 87781 | US 30: Reeceville to Quarry Rd | 30 | CER | Highway Reconstruction | UTL | 581 | 2033-11-10 |  | 0 | 0 | 0 | 0 | 0 | 246000 | 0 | 0 | 0 | 246000
DVRPC | 6 | Chester | 87781 | US 30: Reeceville to Quarry Rd | 30 | CER | Highway Reconstruction | CON | 185 | 2033-11-10 |  | 0 | 0 | 0 | 0 | 6326000 | 8326000 | 20408000 | 20408000 | 64221000 | 119689000
DVRPC | 6 | Chester | 87781 | US 30: Reeceville to Quarry Rd | 30 | CER | Highway Reconstruction | CON | 581 | 2033-11-10 |  | 0 | 0 | 0 | 0 | 3582000 | 2082000 | 0 | 0 | 0 | 5664000
DVRPC | 6 | Chester | 98035 | Water Works Rd o/Rock Run | 4003 | CB1 | Bridge Replacement | ROW | BOF | 2027-08-26 |  | 101000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101000
DVRPC | 6 | Chester | 98035 | Water Works Rd o/Rock Run | 4003 | CB1 | Bridge Replacement | ROW | 185 | 2027-08-26 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
DVRPC | 6 | Chester | 98035 | Water Works Rd o/Rock Run | 4003 | CB1 | Bridge Replacement | UTL | BOF | 2027-08-26 |  | 0 | 0 | 74000 | 0 | 0 | 0 | 0 | 0 | 0 | 74000
DVRPC | 6 | Chester | 98035 | Water Works Rd o/Rock Run | 4003 | CB1 | Bridge Replacement | UTL | 185 | 2027-08-26 |  | 0 | 0 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 19000
DVRPC | 6 | Chester | 98035 | Water Works Rd o/Rock Run | 4003 | CB1 | Bridge Replacement | CON | BOF | 2027-08-26 |  | 0 | 0 | 1545000 | 0 | 0 | 0 | 0 | 0 | 0 | 1545000
DVRPC | 6 | Chester | 98035 | Water Works Rd o/Rock Run | 4003 | CB1 | Bridge Replacement | CON | 185 | 2027-08-26 |  | 0 | 0 | 386000 | 0 | 0 | 0 | 0 | 0 | 0 | 386000
DVRPC | 6 | Chester | 98039 | Ship Rd over Valley Creek | 1001 | CB2 | Bridge Replacement | UTL | STU | 2026-07-02 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
DVRPC | 6 | Chester | 98039 | Ship Rd over Valley Creek | 1001 | CB2 | Bridge Replacement | CON | 185 | 2026-07-02 |  | 0 | 1476000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1476000
DVRPC | 6 | Chester | 98041 | Birchrun Road over Birch Run | 1030 | CB7 | Bridge Replacement | CON | 185 | 2027-10-21 |  | 0 | 0 | 0 | 1268000 | 0 | 0 | 0 | 0 | 0 | 1268000
DVRPC | 6 | Chester | 98042 | Conestoga Road over Br Pickering Creek | 401 | CB4 | Bridge Replacement | ROW | 185 | 2027-01-28 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Chester | 98042 | Conestoga Road over Br Pickering Creek | 401 | CB4 | Bridge Replacement | CON | BRIP | 2027-01-28 |  | 0 | 0 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000
DVRPC | 6 | Chester | 98223 | Creek Road over Pickering Creek(C) | 7015 | 175 | Bridge Replacement | CON | BRIP | 2025-05-08 | 2025-05-08 | 3184000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3184000
DVRPC | 6 | Chester | 98224 | Spring City Rd over Stony Run(C) | 7015 | 205 | Bridge Replacement | CON | BRIP | 2025-09-25 | 2025-09-25 | 2047000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2047000
DVRPC | 6 | Chester | 102708 | PA 41 & PA 841 Improvements | 41 | 841 | Highway Reconstruction | FD | STU | 2028-08-10 |  | 0 | 0 | 601000 | 0 | 0 | 0 | 0 | 0 | 0 | 601000
DVRPC | 6 | Chester | 102708 | PA 41 & PA 841 Improvements | 41 | 841 | Highway Reconstruction | ROW | STU | 2028-08-10 |  | 0 | 0 | 1469000 | 0 | 0 | 0 | 0 | 0 | 0 | 1469000
DVRPC | 6 | Chester | 102708 | PA 41 & PA 841 Improvements | 41 | 841 | Highway Reconstruction | UTL | STU | 2028-08-10 |  | 0 | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93000
DVRPC | 6 | Chester | 102708 | PA 41 & PA 841 Improvements | 41 | 841 | Highway Reconstruction | UTL | 581 | 2028-08-10 |  | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000
DVRPC | 6 | Chester | 102708 | PA 41 & PA 841 Improvements | 41 | 841 | Highway Reconstruction | CON | STP | 2028-08-10 |  | 0 | 1163000 | 1163000 | 1163000 | 1163000 | 1163000 | 0 | 0 | 0 | 5815000
DVRPC | 6 | Chester | 102708 | PA 41 & PA 841 Improvements | 41 | 841 | Highway Reconstruction | CON | 581 | 2028-08-10 |  | 0 | 291000 | 291000 | 291000 | 291000 | 291000 | 0 | 0 | 0 | 1455000
DVRPC | 6 | Chester | 102709 | PA 41 & PA 926 Roundabout(C) | 41 | 926 | Highway Reconstruction | CON | STU | 2023-11-02 | 2023-11-02 | 975000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975000
DVRPC | 6 | Chester | 103589 | Pusey Mill Road over E Br Big Elk Creek | 7015 | 038 | Bridge Restoration | PE | 185 |  |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Chester | 103589 | Pusey Mill Road over E Br Big Elk Creek | 7015 | 038 | Bridge Restoration | FD | STP |  |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
DVRPC | 6 | Chester | 103589 | Pusey Mill Road over E Br Big Elk Creek | 7015 | 038 | Bridge Restoration | ROW | STP |  |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
DVRPC | 6 | Chester | 103589 | Pusey Mill Road over E Br Big Elk Creek | 7015 | 038 | Bridge Restoration | UTL | STP |  |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
DVRPC | 6 | Chester | 103589 | Pusey Mill Road over E Br Big Elk Creek | 7015 | 038 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
DVRPC | 6 | Chester | 104807 | US 30 Sinkhole Remediation 2025(C) | 30 | SK2 | Highway Reconstruction | CON | PRTCT | 2025-06-26 | 2025-06-26 | 7634164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7634164
DVRPC | 6 | Chester | 107551 | US 30/PA 10 to Business 30 Int. Imp | 30 | 010 | Highway Reconstruction | FD | NHPP | 2031-11-06 |  | 0 | 0 | 1431000 | 739000 | 0 | 0 | 0 | 3009349 | 325851 | 5505200
DVRPC | 6 | Chester | 107551 | US 30/PA 10 to Business 30 Int. Imp | 30 | 010 | Highway Reconstruction | FD | 581 | 2031-11-06 |  | 0 | 0 | 383000 | 161000 | 0 | 0 | 0 | 800000 | 33800 | 1377800
DVRPC | 6 | Chester | 107551 | US 30/PA 10 to Business 30 Int. Imp | 30 | 010 | Highway Reconstruction | ROW | 581 | 2031-11-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9695000 | 9695000
DVRPC | 6 | Chester | 107551 | US 30/PA 10 to Business 30 Int. Imp | 30 | 010 | Highway Reconstruction | UTL | NHPP | 2031-11-06 |  | 0 | 0 | 0 | 0 | 2128000 | 0 | 0 | 0 | 0 | 2128000
DVRPC | 6 | Chester | 107551 | US 30/PA 10 to Business 30 Int. Imp | 30 | 010 | Highway Reconstruction | UTL | 581 | 2031-11-06 |  | 0 | 0 | 0 | 0 | 532000 | 0 | 0 | 0 | 0 | 532000
DVRPC | 6 | Chester | 107551 | US 30/PA 10 to Business 30 Int. Imp | 30 | 010 | Highway Reconstruction | CON | NHPP | 2031-11-06 |  | 0 | 0 | 0 | 0 | 20000000 | 20000000 | 0 | 0 | 0 | 40000000
DVRPC | 6 | Chester | 107551 | US 30/PA 10 to Business 30 Int. Imp | 30 | 010 | Highway Reconstruction | CON | NHPP | 2031-11-06 |  | 0 | 0 | 0 | 0 | 0 | 9501000 | 9001000 | 9001000 | 18002000 | 45505000
DVRPC | 6 | Chester | 107551 | US 30/PA 10 to Business 30 Int. Imp | 30 | 010 | Highway Reconstruction | CON | 581 | 2031-11-06 |  | 0 | 0 | 0 | 0 | 5000000 | 7375000 | 2250000 | 2250000 | 4500000 | 21375000
DVRPC | 6 | Chester | 107553 | US 30 & Airport Rd Interchange Imp. | 30 | AIR | Highway Reconstruction | FD | NHPP | 2029-04-12 |  | 9000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000000
DVRPC | 6 | Chester | 107553 | US 30 & Airport Rd Interchange Imp. | 30 | AIR | Highway Reconstruction | ROW | NHPP | 2029-04-12 |  | 0 | 5979000 | 3500000 | 2479000 | 0 | 0 | 0 | 0 | 0 | 11958000
DVRPC | 6 | Chester | 107553 | US 30 & Airport Rd Interchange Imp. | 30 | AIR | Highway Reconstruction | ROW | STU | 2029-04-12 |  | 0 | 0 | 850000 | 644000 | 0 | 0 | 0 | 0 | 0 | 1494000
DVRPC | 6 | Chester | 107553 | US 30 & Airport Rd Interchange Imp. | 30 | AIR | Highway Reconstruction | UTL | NHPP | 2029-04-12 |  | 0 | 0 | 6496000 | 0 | 0 | 0 | 0 | 0 | 0 | 6496000
DVRPC | 6 | Chester | 107553 | US 30 & Airport Rd Interchange Imp. | 30 | AIR | Highway Reconstruction | UTL | 581 | 2029-04-12 |  | 0 | 0 | 1624000 | 0 | 0 | 0 | 0 | 0 | 0 | 1624000
DVRPC | 6 | Chester | 107553 | US 30 & Airport Rd Interchange Imp. | 30 | AIR | Highway Reconstruction | CON | NHPP | 2029-04-12 |  | 0 | 0 | 10000000 | 15000000 | 5000000 | 0 | 0 | 0 | 0 | 30000000
DVRPC | 6 | Chester | 107553 | US 30 & Airport Rd Interchange Imp. | 30 | AIR | Highway Reconstruction | CON | NHPP | 2029-04-12 |  | 0 | 0 | 5979000 | 5979000 | 0 | 9873000 | 0 | 0 | 0 | 21831000
DVRPC | 6 | Chester | 107553 | US 30 & Airport Rd Interchange Imp. | 30 | AIR | Highway Reconstruction | CON | STP | 2029-04-12 |  | 0 | 0 | 2477000 | 3019000 | 4367000 | 5760000 | 3129000 | 0 | 31073000 | 49825000
DVRPC | 6 | Chester | 107553 | US 30 & Airport Rd Interchange Imp. | 30 | AIR | Highway Reconstruction | CON | STU | 2029-04-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7873000 | 21851000 | 32199000 | 61923000
DVRPC | 6 | Chester | 107553 | US 30 & Airport Rd Interchange Imp. | 30 | AIR | Highway Reconstruction | CON | 581 | 2029-04-12 |  | 0 | 1494000 | 4614000 | 5244000 | 1250000 | 3908000 | 1968000 | 5463000 | 19973000 | 43914000
DVRPC | 6 | Chester | 107554 | US 30 & PA 82 Interchange Imp. | 30 | 082 | Highway Reconstruction | FD | NHPP | 2030-10-10 |  | 0 | 0 | 0 | 3000000 | 2085000 | 0 | 0 | 0 | 0 | 5085000
DVRPC | 6 | Chester | 107554 | US 30 & PA 82 Interchange Imp. | 30 | 082 | Highway Reconstruction | FD | STU | 2030-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4766400 | 4766400
DVRPC | 6 | Chester | 107554 | US 30 & PA 82 Interchange Imp. | 30 | 082 | Highway Reconstruction | FD | 581 | 2030-10-10 |  | 0 | 0 | 0 | 750000 | 521000 | 0 | 0 | 0 | 1192000 | 2463000
DVRPC | 6 | Chester | 107554 | US 30 & PA 82 Interchange Imp. | 30 | 082 | Highway Reconstruction | ROW | NHPP | 2030-10-10 |  | 0 | 0 | 0 | 0 | 6081000 | 6081000 | 0 | 0 | 0 | 12162000
DVRPC | 6 | Chester | 107554 | US 30 & PA 82 Interchange Imp. | 30 | 082 | Highway Reconstruction | ROW | 581 | 2030-10-10 |  | 0 | 0 | 0 | 0 | 1520000 | 1520000 | 0 | 0 | 0 | 3040000
DVRPC | 6 | Chester | 107554 | US 30 & PA 82 Interchange Imp. | 30 | 082 | Highway Reconstruction | UTL | 581 | 2030-10-10 |  | 0 | 0 | 0 | 0 | 0 | 4697000 | 0 | 0 | 0 | 4697000
DVRPC | 6 | Chester | 107554 | US 30 & PA 82 Interchange Imp. | 30 | 082 | Highway Reconstruction | CON | NHPP | 2030-10-10 |  | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000 | 10000000 | 0 | 30000000
DVRPC | 6 | Chester | 107554 | US 30 & PA 82 Interchange Imp. | 30 | 082 | Highway Reconstruction | CON | NHPP | 2030-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 28416000 | 0 | 16326000 | 44742000
DVRPC | 6 | Chester | 107554 | US 30 & PA 82 Interchange Imp. | 30 | 082 | Highway Reconstruction | CON | STP | 2030-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11642000 | 11642000
DVRPC | 6 | Chester | 107554 | US 30 & PA 82 Interchange Imp. | 30 | 082 | Highway Reconstruction | CON | STU | 2030-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95451000 | 95451000
DVRPC | 6 | Chester | 107554 | US 30 & PA 82 Interchange Imp. | 30 | 082 | Highway Reconstruction | CON | 581 | 2030-10-10 |  | 0 | 0 | 0 | 0 | 0 | 2500000 | 9604000 | 2500000 | 50731000 | 65335000
DVRPC | 6 | Chester | 107945 | Art School Road o/ Br Pickering Ck (2 Bridges)(C) | 1024 | CB8 | Bridge Replacement | CON | BOF | 2025-10-23 | 2025-10-23 | 995000 | 2319080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3314080
DVRPC | 6 | Chester | 109599 | Bridge Group U (C) | 3003 | HBU | Bridge Replacement | CON | 185 | 2020-09-24 | 2020-09-24 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000
DVRPC | 6 | Chester | 110311 | PA 41 & State/1st Streets Intersection Improvement | 41 | STA | Highway Restoration | FD | 581 | 2028-03-23 |  | 563000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563000
DVRPC | 6 | Chester | 110311 | PA 41 & State/1st Streets Intersection Improvement | 41 | STA | Highway Restoration | ROW | STU | 2028-03-23 |  | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
DVRPC | 6 | Chester | 110311 | PA 41 & State/1st Streets Intersection Improvement | 41 | STA | Highway Restoration | UTL | 581 | 2028-03-23 |  | 0 | 232000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232000
DVRPC | 6 | Chester | 110311 | PA 41 & State/1st Streets Intersection Improvement | 41 | STA | Highway Restoration | CON | 581 | 2028-03-23 |  | 0 | 3650000 | 3306000 | 0 | 0 | 0 | 0 | 0 | 0 | 6956000
DVRPC | 6 | Chester | 110312 | Baltimore Pike & Newark Road | 3033 | OBP | Highway Restoration | FD | 581 | 2028-06-29 |  | 1451000 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1581000
DVRPC | 6 | Chester | 110312 | Baltimore Pike & Newark Road | 3033 | OBP | Highway Restoration | ROW | STU | 2028-06-29 |  | 0 | 1353000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1353000
DVRPC | 6 | Chester | 110312 | Baltimore Pike & Newark Road | 3033 | OBP | Highway Restoration | UTL | 581 | 2028-06-29 |  | 0 | 0 | 0 | 0 | 849000 | 764000 | 0 | 0 | 0 | 1613000
DVRPC | 6 | Chester | 110312 | Baltimore Pike & Newark Road | 3033 | OBP | Highway Restoration | CON | 581 | 2028-06-29 |  | 0 | 0 | 0 | 0 | 0 | 5469000 | 4397000 | 0 | 0 | 9866000
DVRPC | 6 | Chester | 110765 | Pickerng Dam Rd o/ Br Pickering Creek | 1017 | CB9 | Bridge Replacement | FD | 185 | 2027-02-25 |  | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
DVRPC | 6 | Chester | 110765 | Pickerng Dam Rd o/ Br Pickering Creek | 1017 | CB9 | Bridge Replacement | ROW | 185 | 2027-02-25 |  | 82000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82000
DVRPC | 6 | Chester | 110765 | Pickerng Dam Rd o/ Br Pickering Creek | 1017 | CB9 | Bridge Replacement | UTL | 185 | 2027-02-25 |  | 0 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000
DVRPC | 6 | Chester | 110765 | Pickerng Dam Rd o/ Br Pickering Creek | 1017 | CB9 | Bridge Replacement | CON | 185 | 2027-02-25 |  | 0 | 1107000 | 1107000 | 0 | 0 | 0 | 0 | 0 | 0 | 2214000
DVRPC | 6 | Chester | 110963 | Manor Rd & Reeceville Rd Roundabout(C) | 82 | SIP | Safety Improvement | CON | HSIP | 2022-10-20 | 2022-10-20 | 227922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227922
DVRPC | 6 | Chester | 111572 | St. Peters Rd Retaining Wall(C) | 4041 | SLP | Highway Restoration | FD | 581 | 2028-03-23 | 2025-01-16 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
DVRPC | 6 | Chester | 111572 | St. Peters Rd Retaining Wall(C) | 4041 | SLP | Highway Restoration | ROW | 581 | 2028-03-23 | 2025-01-16 | 76000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76000
DVRPC | 6 | Chester | 111572 | St. Peters Rd Retaining Wall(C) | 4041 | SLP | Highway Restoration | UTL | 581 | 2028-03-23 | 2025-01-16 | 0 | 79000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79000
DVRPC | 6 | Chester | 111572 | St. Peters Rd Retaining Wall(C) | 4041 | SLP | Highway Restoration | CON | 581 | 2028-03-23 | 2025-01-16 | 0 | 1712000 | 1785000 | 1639000 | 0 | 0 | 0 | 0 | 0 | 5136000
DVRPC | 6 | Chester | 111761 | Lincoln Highway Streetscape R10 | 3070 | DCA | Transportation Enhancement | PE | 581 |  |  | 0 | 357000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357000
DVRPC | 6 | Chester | 111761 | Lincoln Highway Streetscape R10 | 3070 | DCA | Transportation Enhancement | PE | LOC |  |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
DVRPC | 6 | Chester | 111761 | Lincoln Highway Streetscape R10 | 3070 | DCA | Transportation Enhancement | UTL | LOC |  |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
DVRPC | 6 | Chester | 111761 | Lincoln Highway Streetscape R10 | 3070 | DCA | Transportation Enhancement | CON | 581 |  |  | 0 | 924158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 924158
DVRPC | 6 | Chester | 111761 | Lincoln Highway Streetscape R10 | 3070 | DCA | Transportation Enhancement | CON | 411 |  |  | 0 | 121955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121955
DVRPC | 6 | Chester | 111761 | Lincoln Highway Streetscape R10 | 3070 | DCA | Transportation Enhancement | CON | LOC |  |  | 0 | 676730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 676730
DVRPC | 6 | Chester | 113307 | US 1: PA/MD Line- PA 472 | 1 | 110 | Highway Reconstruction | FD | NHPP | 2029-10-18 |  | 5304000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5304000
DVRPC | 6 | Chester | 113307 | US 1: PA/MD Line- PA 472 | 1 | 110 | Highway Reconstruction | ROW | 581 | 2029-10-18 |  | 0 | 811000 | 515000 | 0 | 0 | 0 | 0 | 0 | 0 | 1326000
DVRPC | 6 | Chester | 113307 | US 1: PA/MD Line- PA 472 | 1 | 110 | Highway Reconstruction | UTL | STP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261000 | 0 | 261000
DVRPC | 6 | Chester | 113307 | US 1: PA/MD Line- PA 472 | 1 | 110 | Highway Reconstruction | UTL | 581 | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 0 | 65000
DVRPC | 6 | Chester | 113307 | US 1: PA/MD Line- PA 472 | 1 | 110 | Highway Reconstruction | CON | STP | 2029-10-18 |  | 0 | 0 | 1663000 | 2748000 | 2663000 | 7915000 | 8663000 | 13663000 | 26652000 | 63967000
DVRPC | 6 | Chester | 113307 | US 1: PA/MD Line- PA 472 | 1 | 110 | Highway Reconstruction | CON | STU | 2029-10-18 |  | 0 | 0 | 0 | 2663000 | 0 | 0 | 0 | 0 | 0 | 2663000
DVRPC | 6 | Chester | 113307 | US 1: PA/MD Line- PA 472 | 1 | 110 | Highway Reconstruction | CON | 581 | 2029-10-18 |  | 0 | 0 | 416000 | 1353000 | 666000 | 1979000 | 2166000 | 3416000 | 6664000 | 16660000
DVRPC | 6 | Chester | 113312 | US 1: PA 41 - Schoolhouse Road | 1 | 210 | Highway Reconstruction | FD | 581 | 2029-07-12 |  | 0 | 3524000 | 1855000 | 1253000 | 0 | 0 | 0 | 0 | 0 | 6632000
DVRPC | 6 | Chester | 113312 | US 1: PA 41 - Schoolhouse Road | 1 | 210 | Highway Reconstruction | ROW | 581 | 2029-07-12 |  | 0 | 2289000 | 1000000 | 3485000 | 0 | 0 | 0 | 0 | 0 | 6774000
DVRPC | 6 | Chester | 113312 | US 1: PA 41 - Schoolhouse Road | 1 | 210 | Highway Reconstruction | UTL | 581 | 2029-07-12 |  | 0 | 0 | 0 | 0 | 299000 | 0 | 0 | 0 | 0 | 299000
DVRPC | 6 | Chester | 113312 | US 1: PA 41 - Schoolhouse Road | 1 | 210 | Highway Reconstruction | CON | BOF | 2029-07-12 |  | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 3000000
DVRPC | 6 | Chester | 113312 | US 1: PA 41 - Schoolhouse Road | 1 | 210 | Highway Reconstruction | CON | NHPP | 2029-07-12 |  | 0 | 0 | 0 | 2274000 | 7274000 | 6274000 | 0 | 10274000 | 46096000 | 72192000
DVRPC | 6 | Chester | 113312 | US 1: PA 41 - Schoolhouse Road | 1 | 210 | Highway Reconstruction | CON | STU | 2029-07-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3935000 | 0 | 6339000 | 10274000
DVRPC | 6 | Chester | 113312 | US 1: PA 41 - Schoolhouse Road | 1 | 210 | Highway Reconstruction | CON | 581 | 2029-07-12 |  | 0 | 0 | 0 | 2319000 | 2319000 | 1569000 | 984000 | 2319000 | 12610000 | 22120000
DVRPC | 6 | Chester | 114166 | PA 401 & Valley Hill Rd Improvement | 401 | VHR | Congestion Reduction | PE | CAQ | 2027-12-09 |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
DVRPC | 6 | Chester | 114166 | PA 401 & Valley Hill Rd Improvement | 401 | VHR | Congestion Reduction | CON | CAQ | 2027-12-09 |  | 0 | 757000 | 1365000 | 0 | 0 | 0 | 0 | 0 | 0 | 2122000
DVRPC | 6 | Chester | 115423 | PA 23 Corridor Safety Improvments(C) | 23 | SIP | Safety Improvement | CON | HVRU | 2025-06-26 | 2025-06-26 | 2812000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2812000
DVRPC | 6 | Chester | 115875 | Reese St RR WD |  | 289 | Rail Highway Grade Crossing | CON | RRX |  |  | 21122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21122
DVRPC | 6 | Chester | 115876 | Center St RR WD |  | 288 | Rail Highway Grade Crossing | CON | RRX |  |  | 23182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23182
DVRPC | 6 | Chester | 117969 | Toughkenamon Streetscape |  | TSI | Bicycle Pedestrian Highway | CON | TAU | 2026-04-09 |  | 965000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965000
DVRPC | 6 | Chester | 117970 | Moores Road Sidewalk |  | MRS | Bicycle Pedestrian Highway | CON | TAU | 2026-10-22 |  | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
DVRPC | 6 | Chester | 117999 | Thomas Road over Trout Creek (CB #300) | 7015 | 300 | Bridge Replacement | FD | 183 |  |  | 546000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546000
DVRPC | 6 | Chester | 117999 | Thomas Road over Trout Creek (CB #300) | 7015 | 300 | Bridge Replacement | ROW | 183 |  |  | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56000
DVRPC | 6 | Chester | 117999 | Thomas Road over Trout Creek (CB #300) | 7015 | 300 | Bridge Replacement | UTL | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69000 | 69000
DVRPC | 6 | Chester | 117999 | Thomas Road over Trout Creek (CB #300) | 7015 | 300 | Bridge Replacement | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3820000 | 3820000
DVRPC | 6 | Chester | 117999 | Thomas Road over Trout Creek (CB #300) | 7015 | 300 | Bridge Replacement | CON | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 955000 | 955000
DVRPC | 6 | Chester | 118024 | US 202: Oakbourne Rd - Matlack St | 202 | CWM | Congestion Reduction | PE | NHPP | 2030-06-27 |  | 1050000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050000
DVRPC | 6 | Chester | 118024 | US 202: Oakbourne Rd - Matlack St | 202 | CWM | Congestion Reduction | FD | 581 | 2030-06-27 |  | 1591000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1591000
DVRPC | 6 | Chester | 118024 | US 202: Oakbourne Rd - Matlack St | 202 | CWM | Congestion Reduction | ROW | STU | 2030-06-27 |  | 0 | 109000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109000
DVRPC | 6 | Chester | 118024 | US 202: Oakbourne Rd - Matlack St | 202 | CWM | Congestion Reduction | UTL | 581 | 2030-06-27 |  | 0 | 0 | 0 | 174000 | 0 | 0 | 0 | 0 | 0 | 174000
DVRPC | 6 | Chester | 118024 | US 202: Oakbourne Rd - Matlack St | 202 | CWM | Congestion Reduction | CON | 581 | 2030-06-27 |  | 0 | 0 | 0 | 1841000 | 3091000 | 3091000 | 1250000 | 0 | 0 | 9273000
DVRPC | 6 | Chester | 118025 | PA 100 NB @ Exton Station | 100 | CES | Additional Lanes | PE | NHPP | 2028-04-27 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Chester | 118025 | PA 100 NB @ Exton Station | 100 | CES | Additional Lanes | FD | STU | 2028-04-27 |  | 601000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 601000
DVRPC | 6 | Chester | 118025 | PA 100 NB @ Exton Station | 100 | CES | Additional Lanes | UTL | 581 | 2028-04-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 692000 | 692000
DVRPC | 6 | Chester | 118025 | PA 100 NB @ Exton Station | 100 | CES | Additional Lanes | CON | STP | 2028-04-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4516000 | 4516000
DVRPC | 6 | Chester | 118025 | PA 100 NB @ Exton Station | 100 | CES | Additional Lanes | CON | 581 | 2028-04-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1129000 | 1129000
DVRPC | 6 | Chester | 118183 | Lake Road West RR Xing |  | 290 | Rail Highway Grade Crossing | CON | RRX |  |  | 196510 | 137500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334010
DVRPC | 6 | Chester | 118184 | Lake Road East RR Xing |  | 291 | Rail Highway Grade Crossing | CON | RRX |  |  | 226032 | 137500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363532
DVRPC | 6 | Chester | 118185 | Woodland Ave. Xing |  | 293 | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 100000 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 400000
DVRPC | 6 | Chester | 118186 | Kimble Road Xing |  | 294 | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 0 | 0 | 0 | 0 | 305000 | 0 | 0 | 0 | 305000
DVRPC | 6 | Chester | 118188 | Mt. Pleasant Rd Xing |  | 295 | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 0 | 0 | 0 | 0 | 315000 | 0 | 0 | 0 | 315000
DVRPC | 6 | Chester | 118189 | Crowl Toot Rd RR Xing |  | 292 | Rail Highway Grade Crossing | CON | RRX |  |  | 315000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325000
DVRPC | 6 | Chester | 118355 | Jennersville Sidewalk | 796 | JSC | Bicycle Pedestrian Highway | CON | TAP | 2027-02-11 |  | 0 | 845000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 845000
DVRPC | 6 | Chester | 118552 | Harvey's Bridge Rd o/ W Br Brandywine Creek CB#92 | 7015 | 092 | Bridge Replacement | FD | BOF | 2027-08-26 |  | 820000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820000
DVRPC | 6 | Chester | 118552 | Harvey's Bridge Rd o/ W Br Brandywine Creek CB#92 | 7015 | 092 | Bridge Replacement | ROW | BOF | 2027-08-26 |  | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
DVRPC | 6 | Chester | 118552 | Harvey's Bridge Rd o/ W Br Brandywine Creek CB#92 | 7015 | 092 | Bridge Replacement | UTL | BOF | 2027-08-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208000 | 208000
DVRPC | 6 | Chester | 118552 | Harvey's Bridge Rd o/ W Br Brandywine Creek CB#92 | 7015 | 092 | Bridge Replacement | CON | BOF | 2027-08-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9344000 | 9344000
DVRPC | 6 | Chester | 118553 | Chstr Cnty Elect. Veh. Charging Stations(C) |  | CEV | Air Quality | CON | SXF | 2026-02-26 | 2026-02-12 | 645609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 645609
DVRPC | 6 | Chester | 119160 | SR 322 IDA Slope Failure(C) | 322 | IDA | Highway Restoration | CON | FFL | 2023-12-14 | 2023-12-14 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Chester | 119160 | SR 322 IDA Slope Failure(C) | 322 | IDA | Highway Restoration | CON | 581 | 2023-12-14 | 2023-12-14 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
DVRPC | 6 | Chester | 119786 | Unionville Rd Grade Xing | 842 | 280 | Rail Highway Grade Crossing | CON | RRX |  |  | 421099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421099
DVRPC | 6 | Chester | 120062 | Bondsville Road Retaining Wall | 4015 | CBC | Highway Restoration | PE | PRTCT | 2026-04-23 |  | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
DVRPC | 6 | Chester | 120062 | Bondsville Road Retaining Wall | 4015 | CBC | Highway Restoration | PE | 581 | 2026-04-23 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
DVRPC | 6 | Chester | 120062 | Bondsville Road Retaining Wall | 4015 | CBC | Highway Restoration | FD | PRTCT | 2026-04-23 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
DVRPC | 6 | Chester | 120062 | Bondsville Road Retaining Wall | 4015 | CBC | Highway Restoration | ROW | 581 | 2026-04-23 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Chester | 120062 | Bondsville Road Retaining Wall | 4015 | CBC | Highway Restoration | UTL | 581 | 2026-04-23 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
DVRPC | 6 | Chester | 120062 | Bondsville Road Retaining Wall | 4015 | CBC | Highway Restoration | CON | PRTCT | 2026-04-23 |  | 0 | 700000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 3700000
DVRPC | 6 | Chester | 120277 | US 30: Apple Lane to Church Road | 30 | MT2 | MultiModal | CON | 581 |  |  | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
DVRPC | 6 | Chester | 120278 | Marshallton-Thorndale & Poorhouse Rd Roundabout R9 | 3055 | MTF | Safety Improvement | CON | 411 |  |  | 975266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975266
DVRPC | 6 | Chester | 120278 | Marshallton-Thorndale & Poorhouse Rd Roundabout R9 | 3055 | MTF | Safety Improvement | CON | LOC |  |  | 292780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292780
DVRPC | 6 | Chester | 120938 | Chester & Delaware Counties ADA Ramps | 1 | A12 | Air Quality | PE | CRPU | 2026-12-03 |  | 0 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000
DVRPC | 6 | Chester | 120938 | Chester & Delaware Counties ADA Ramps | 1 | A12 | Air Quality | FD | CRPU | 2026-12-03 |  | 0 | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 130000
DVRPC | 6 | Chester | 120938 | Chester & Delaware Counties ADA Ramps | 1 | A12 | Air Quality | CON | CRPU | 2026-12-03 |  | 0 | 0 | 0 | 2050000 | 0 | 0 | 0 | 0 | 0 | 2050000
DVRPC | 6 | Chester | 120957 | N Caln Rd/Olive St & Lincoln Highway | 3074 | CCT | Congestion Reduction | PE | 581 |  |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
DVRPC | 6 | Chester | 120957 | N Caln Rd/Olive St & Lincoln Highway | 3074 | CCT | Congestion Reduction | FD | STP |  |  | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
DVRPC | 6 | Chester | 120957 | N Caln Rd/Olive St & Lincoln Highway | 3074 | CCT | Congestion Reduction | ROW | STP |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Chester | 120957 | N Caln Rd/Olive St & Lincoln Highway | 3074 | CCT | Congestion Reduction | UTL | STP |  |  | 0 | 0 | 470000 | 0 | 0 | 0 | 0 | 0 | 0 | 470000
DVRPC | 6 | Chester | 120957 | N Caln Rd/Olive St & Lincoln Highway | 3074 | CCT | Congestion Reduction | CON | STP |  |  | 0 | 0 | 0 | 747000 | 0 | 0 | 0 | 0 | 0 | 747000
DVRPC | 6 | Delaware | 15183 | Station Road over Chester Creek (DelCo #234) | 7023 | 234 | Bridge Replacement | ROW | BOF | 2028-03-02 |  | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68000
DVRPC | 6 | Delaware | 15183 | Station Road over Chester Creek (DelCo #234) | 7023 | 234 | Bridge Replacement | ROW | 179 | 2028-03-02 |  | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
DVRPC | 6 | Delaware | 15183 | Station Road over Chester Creek (DelCo #234) | 7023 | 234 | Bridge Replacement | UTL | BOF | 2028-03-02 |  | 0 | 74000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74000
DVRPC | 6 | Delaware | 15183 | Station Road over Chester Creek (DelCo #234) | 7023 | 234 | Bridge Replacement | UTL | 179 | 2028-03-02 |  | 0 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000
DVRPC | 6 | Delaware | 15183 | Station Road over Chester Creek (DelCo #234) | 7023 | 234 | Bridge Replacement | CON | BOF | 2028-03-02 |  | 0 | 1000000 | 1032000 | 1290000 | 0 | 0 | 0 | 0 | 0 | 3322000
DVRPC | 6 | Delaware | 15183 | Station Road over Chester Creek (DelCo #234) | 7023 | 234 | Bridge Replacement | CON | 179 | 2028-03-02 |  | 0 | 250000 | 258000 | 323000 | 0 | 0 | 0 | 0 | 0 | 831000
DVRPC | 6 | Delaware | 15225 | Ardmore Ave O/SEPTA (C) | 1018 | HAV | Bridge Replacement | FD | STU | 2018-12-06 | 2018-12-06 | 17900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17900
DVRPC | 6 | Delaware | 15251 | US 1/PA 352 Interchange | 352 | US1 | Safety Improvement | FD | STU | 2031-06-26 |  | 0 | 2092000 | 2092000 | 4167000 | 6925000 | 0 | 0 | 0 | 0 | 15276000
DVRPC | 6 | Delaware | 15251 | US 1/PA 352 Interchange | 352 | US1 | Safety Improvement | FD | 581 | 2031-06-26 |  | 0 | 523000 | 523000 | 1042000 | 1731000 | 0 | 0 | 0 | 0 | 3819000
DVRPC | 6 | Delaware | 15251 | US 1/PA 352 Interchange | 352 | US1 | Safety Improvement | ROW | STU | 2031-06-26 |  | 0 | 0 | 0 | 0 | 4866000 | 7084000 | 5552000 | 800000 | 12319000 | 30621000
DVRPC | 6 | Delaware | 15251 | US 1/PA 352 Interchange | 352 | US1 | Safety Improvement | ROW | 581 | 2031-06-26 |  | 0 | 0 | 0 | 0 | 1217000 | 1771000 | 1388000 | 4388000 | 18390000 | 27154000
DVRPC | 6 | Delaware | 15251 | US 1/PA 352 Interchange | 352 | US1 | Safety Improvement | UTL | 581 | 2031-06-26 |  | 0 | 0 | 0 | 0 | 9552000 | 0 | 0 | 0 | 0 | 9552000
DVRPC | 6 | Delaware | 15251 | US 1/PA 352 Interchange | 352 | US1 | Safety Improvement | CON | BRIP | 2031-06-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14850000 | 14850000
DVRPC | 6 | Delaware | 15251 | US 1/PA 352 Interchange | 352 | US1 | Safety Improvement | CON | STP | 2031-06-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16552000 | 16552000
DVRPC | 6 | Delaware | 15251 | US 1/PA 352 Interchange | 352 | US1 | Safety Improvement | CON | STU | 2031-06-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29341000 | 29341000
DVRPC | 6 | Delaware | 15251 | US 1/PA 352 Interchange | 352 | US1 | Safety Improvement | CON | 581 | 2031-06-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20338000 | 20338000
DVRPC | 6 | Delaware | 15278 | Chester Pike/9th St. Bridge (CB #146) | 7023 | 146 | Bridge Replacement | FD | 185 | 2029-09-13 |  | 844000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 844000
DVRPC | 6 | Delaware | 15278 | Chester Pike/9th St. Bridge (CB #146) | 7023 | 146 | Bridge Replacement | ROW | 185 | 2029-09-13 |  | 0 | 0 | 0 | 154000 | 0 | 0 | 0 | 0 | 0 | 154000
DVRPC | 6 | Delaware | 15278 | Chester Pike/9th St. Bridge (CB #146) | 7023 | 146 | Bridge Replacement | UTL | 185 | 2029-09-13 |  | 0 | 0 | 0 | 0 | 184000 | 0 | 0 | 0 | 0 | 184000
DVRPC | 6 | Delaware | 15278 | Chester Pike/9th St. Bridge (CB #146) | 7023 | 146 | Bridge Replacement | CON | BRIP | 2029-09-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12483000 | 12483000
DVRPC | 6 | Delaware | 15407 | Villanova Intermodal Sta | 30 |  | Air Quality | CON | SXF |  |  | 0 | 0 | 0 | 0 | 0 | 2400000 | 0 | 0 | 0 | 2400000
DVRPC | 6 | Delaware | 47147 | Third Street over Broomall Run |  | DBR | Bridge Replacement | FD | 183 | 2028-09-14 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
DVRPC | 6 | Delaware | 47147 | Third Street over Broomall Run |  | DBR | Bridge Replacement | CON | 183 | 2028-09-14 |  | 1140000 | 1440000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 2880000
DVRPC | 6 | Delaware | 47992 | New Rd O/Chester Cr (C) | 7023 | 007 | Bridge Replacement | CON | BOF | 2022-05-26 | 2022-05-26 | 625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000
DVRPC | 6 | Delaware | 48201 | DVRPC CMAQ Program |  |  | Reserve Line Item | CON | CAQ |  |  | 0 | 112839 | 360000 | 1295000 | 0 | 6734000 | 7342000 | 5000000 | 10000000 | 30843839
DVRPC | 6 | Delaware | 48201 | DVRPC CMAQ Program |  |  | Reserve Line Item | CON | LOC |  |  | 277000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277000
DVRPC | 6 | Delaware | 57773 | Lloyd Street over Amtrak | 7301 | LYD | Bridge Replacement | CON | BOF | 2027-04-08 |  | 0 | 949000 | 1757000 | 359000 | 0 | 78000 | 371000 | 0 | 0 | 3514000
DVRPC | 6 | Delaware | 57773 | Lloyd Street over Amtrak | 7301 | LYD | Bridge Replacement | CON | BRIP | 2027-04-08 |  | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 1007000 | 1757000
DVRPC | 6 | Delaware | 57773 | Lloyd Street over Amtrak | 7301 | LYD | Bridge Replacement | CON | 183 | 2027-04-08 |  | 0 | 177000 | 329000 | 67313 | 0 | 155625 | 69563 | 0 | 188000 | 986501
DVRPC | 6 | Delaware | 57773 | Lloyd Street over Amtrak | 7301 | LYD | Bridge Replacement | CON | LOC | 2027-04-08 |  | 0 | 60000 | 110000 | 22438 | 0 | 51875 | 23186 | 0 | 63000 | 330499
DVRPC | 6 | Delaware | 57780 | US 322/PA291 Intrchng (F) | 8018 | CAS | New Alignment | FD | STU | 2007-12-20 | 2007-12-20 | 27851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27851
DVRPC | 6 | Delaware | 57780 | US 322/PA291 Intrchng (F) | 8018 | CAS | New Alignment | FD | 581 | 2007-12-20 | 2007-12-20 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000
DVRPC | 6 | Delaware | 64790 | MacDade Blvd:South Ave (C) | 2006 | DMS | Congestion Reduction | UTL | CAQ | 2019-12-12 | 2019-12-12 | 49132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49132
DVRPC | 6 | Delaware | 69665 | S.Creek Rd O/Brandywine(C) | 3101 | DRB | Bridge Replacement | CON | BRIP | 2023-12-14 | 2023-12-14 | 8441000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8441000
DVRPC | 6 | Delaware | 69817 | US 322: Clayton Park - Chelsea Parkway | 322 | 102 | Additional Lanes | ROW | NHPP | 2028-09-14 |  | 400000 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000
DVRPC | 6 | Delaware | 69817 | US 322: Clayton Park - Chelsea Parkway | 322 | 102 | Additional Lanes | ROW | 581 | 2028-09-14 |  | 100000 | 213000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313000
DVRPC | 6 | Delaware | 69817 | US 322: Clayton Park - Chelsea Parkway | 322 | 102 | Additional Lanes | CON | NHPP | 2028-09-14 |  | 0 | 15954000 | 15954000 | 0 | 4863000 | 8863000 | 4863000 | 8863000 | 59406000 | 118766000
DVRPC | 6 | Delaware | 69817 | US 322: Clayton Park - Chelsea Parkway | 322 | 102 | Additional Lanes | CON | STU | 2028-09-14 |  | 0 | 0 | 0 | 8863000 | 0 | 0 | 0 | 0 | 0 | 8863000
DVRPC | 6 | Delaware | 69817 | US 322: Clayton Park - Chelsea Parkway | 322 | 102 | Additional Lanes | CON | 581 | 2028-09-14 |  | 0 | 3988000 | 3988000 | 2216000 | 1216000 | 2216000 | 1216000 | 2216000 | 14852000 | 31908000
DVRPC | 6 | Delaware | 70228 | I-476 @ MacDade Boulevard & US 1 (C) | 2006 | 476 | Highway Restoration | CON | NHPP | 2022-03-31 | 2022-03-31 | 3722000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3722000
DVRPC | 6 | Delaware | 70228 | I-476 @ MacDade Boulevard & US 1 (C) | 2006 | 476 | Highway Restoration | CON | 581 | 2022-03-31 | 2022-03-31 | 930000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930000
DVRPC | 6 | Delaware | 79329 | Concord Rd Industrial Prk Access | 3018 | STY | New Alignment | PE | STU |  |  | 1200000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000
DVRPC | 6 | Delaware | 79329 | Concord Rd Industrial Prk Access | 3018 | STY | New Alignment | PE | 581 |  |  | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
DVRPC | 6 | Delaware | 81734 | I-95 Chester City Noise Abatement Phs 1 | 95 | CN1 | Highway Restoration | CON | 581 | 2026-10-01 |  | 0 | 0 | 9000000 | 0 | 0 | 0 | 0 | 0 | 0 | 9000000
DVRPC | 6 | Delaware | 81882 | Springfield Rd Clifton Heights R10 | 2009 | MTF | Safety Improvement | CON | 411 |  |  | 0 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000
DVRPC | 6 | Delaware | 82011 | Norris Street Trail |  | NCS | Bicycle Pedestrian Highway | CON | TAU | 2026-10-22 |  | 0 | 1550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550000
DVRPC | 6 | Delaware | 82042 | Delaware County EV Charging Program |  | DEV | Electric Vehicle Charging Infrastructure | PE | CRPU |  |  | 0 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
DVRPC | 6 | Delaware | 82042 | Delaware County EV Charging Program |  | DEV | Electric Vehicle Charging Infrastructure | FD | CRPU |  |  | 0 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000
DVRPC | 6 | Delaware | 82042 | Delaware County EV Charging Program |  | DEV | Electric Vehicle Charging Infrastructure | CON | CRPU |  |  | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
DVRPC | 6 | Delaware | 82050 | W 6th Street o/ Chester Ck | 7301 | W6S | Bridge Replacement | PE | 185 |  |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Delaware | 82050 | W 6th Street o/ Chester Ck | 7301 | W6S | Bridge Replacement | FD | STP |  |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Delaware | 82050 | W 6th Street o/ Chester Ck | 7301 | W6S | Bridge Replacement | CON | STP |  |  | 0 | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 0 | 3500000
DVRPC | 6 | Delaware | 82069 | PA 291 Complete Streets: Irving St to Ridley Ck | 13 | DCS | Safety Improvement | STUDY | RCP | 2029-04-12 |  | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
DVRPC | 6 | Delaware | 82069 | PA 291 Complete Streets: Irving St to Ridley Ck | 13 | DCS | Safety Improvement | PE | 581 | 2029-04-12 |  | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
DVRPC | 6 | Delaware | 82069 | PA 291 Complete Streets: Irving St to Ridley Ck | 13 | DCS | Safety Improvement | FD | 581 | 2029-04-12 |  | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
DVRPC | 6 | Delaware | 82069 | PA 291 Complete Streets: Irving St to Ridley Ck | 13 | DCS | Safety Improvement | ROW | 581 | 2029-04-12 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Delaware | 82069 | PA 291 Complete Streets: Irving St to Ridley Ck | 13 | DCS | Safety Improvement | UTL | 581 | 2029-04-12 |  | 0 | 0 | 0 | 0 | 1900000 | 1900000 | 0 | 0 | 0 | 3800000
DVRPC | 6 | Delaware | 82069 | PA 291 Complete Streets: Irving St to Ridley Ck | 13 | DCS | Safety Improvement | CON | CRP | 2029-04-12 |  | 0 | 0 | 0 | 0 | 0 | 1300000 | 2668000 | 1032000 | 0 | 5000000
DVRPC | 6 | Delaware | 82069 | PA 291 Complete Streets: Irving St to Ridley Ck | 13 | DCS | Safety Improvement | CON | CRPU | 2029-04-12 |  | 0 | 0 | 0 | 0 | 0 | 2705000 | 5000000 | 5295000 | 0 | 13000000
DVRPC | 6 | Delaware | 82069 | PA 291 Complete Streets: Irving St to Ridley Ck | 13 | DCS | Safety Improvement | CON | STU | 2029-04-12 |  | 0 | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 10000000 | 11800000
DVRPC | 6 | Delaware | 82095 | Systemic Imp: High Friction Surface Treatments(C) | 1 | SIP | Safety Improvement | CON | HSIP | 2025-07-24 | 2025-07-24 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
DVRPC | 6 | Delaware | 82107 | Dutton Mill Road & Pancoast Ave Traffic Signal R11 | 3020 | MTF | MultiModal | PE | LOC |  |  | 0 | 31069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31069
DVRPC | 6 | Delaware | 82107 | Dutton Mill Road & Pancoast Ave Traffic Signal R11 | 3020 | MTF | MultiModal | CON | 411 |  |  | 0 | 399460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399460
DVRPC | 6 | Delaware | 82107 | Dutton Mill Road & Pancoast Ave Traffic Signal R11 | 3020 | MTF | MultiModal | CON | LOC |  |  | 0 | 88769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88769
DVRPC | 6 | Delaware | 84269 | Victory Ave over SEPTA | 2041 | DSB | Bridge Replacement | PE | BRIP | 2028-12-14 |  | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
DVRPC | 6 | Delaware | 84269 | Victory Ave over SEPTA | 2041 | DSB | Bridge Replacement | FD | BRIP | 2028-12-14 |  | 0 | 675000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675000
DVRPC | 6 | Delaware | 84269 | Victory Ave over SEPTA | 2041 | DSB | Bridge Replacement | ROW | STU | 2028-12-14 |  | 0 | 0 | 338000 | 0 | 0 | 0 | 0 | 0 | 0 | 338000
DVRPC | 6 | Delaware | 84269 | Victory Ave over SEPTA | 2041 | DSB | Bridge Replacement | UTL | 185 | 2028-12-14 |  | 0 | 0 | 0 | 580000 | 0 | 0 | 0 | 0 | 0 | 580000
DVRPC | 6 | Delaware | 84269 | Victory Ave over SEPTA | 2041 | DSB | Bridge Replacement | CON | BRIP | 2028-12-14 |  | 0 | 0 | 0 | 0 | 0 | 2952000 | 0 | 0 | 0 | 2952000
DVRPC | 6 | Delaware | 84269 | Victory Ave over SEPTA | 2041 | DSB | Bridge Replacement | CON | 185 | 2028-12-14 |  | 0 | 0 | 0 | 0 | 0 | 738000 | 0 | 0 | 0 | 738000
DVRPC | 6 | Delaware | 86370 | TribettAve/HermesprotaCk (C) | 7023 | 237 | Bridge Replacement | CON | BOF | 2022-03-31 | 2022-03-31 | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68000
DVRPC | 6 | Delaware | 86370 | TribettAve/HermesprotaCk (C) | 7023 | 237 | Bridge Replacement | CON | 179 | 2022-03-31 | 2022-03-31 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000
DVRPC | 6 | Delaware | 92323 | Wanamaker Ave o/ Darby Ck (C) | 420 | DWD | Bridge Replacement | CON | BRIP | 2023-03-23 | 2023-03-23 | 8079853 | 4697147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12777000
DVRPC | 6 | Delaware | 92323 | Wanamaker Ave o/ Darby Ck (C) | 420 | DWD | Bridge Replacement | CON | STU | 2023-03-23 | 2023-03-23 | 4243000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4243000
DVRPC | 6 | Delaware | 92324 | Gov Printz Blvd over Conrail(C) | 291 | DEC | Bridge Replacement | CON | BRIP | 2024-09-26 | 2024-09-26 | 2798000 | 4603000 | 1849000 | 1825000 | 0 | 0 | 0 | 0 | 0 | 11075000
DVRPC | 6 | Delaware | 92808 | Marshall Road over Cobbs Creek | 2024 | MCC | Bridge Replacement | FD | STU | 2027-06-24 |  | 765000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765000
DVRPC | 6 | Delaware | 92808 | Marshall Road over Cobbs Creek | 2024 | MCC | Bridge Replacement | FD | 185 | 2027-06-24 |  | 191000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191000
DVRPC | 6 | Delaware | 92808 | Marshall Road over Cobbs Creek | 2024 | MCC | Bridge Replacement | ROW | STU | 2027-06-24 |  | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
DVRPC | 6 | Delaware | 92808 | Marshall Road over Cobbs Creek | 2024 | MCC | Bridge Replacement | ROW | 185 | 2027-06-24 |  | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000
DVRPC | 6 | Delaware | 92808 | Marshall Road over Cobbs Creek | 2024 | MCC | Bridge Replacement | UTL | BRIP | 2027-06-24 |  | 0 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000
DVRPC | 6 | Delaware | 92808 | Marshall Road over Cobbs Creek | 2024 | MCC | Bridge Replacement | UTL | 185 | 2027-06-24 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
DVRPC | 6 | Delaware | 92808 | Marshall Road over Cobbs Creek | 2024 | MCC | Bridge Replacement | CON | BRIP | 2027-06-24 |  | 0 | 0 | 1249000 | 3200000 | 3249000 | 0 | 0 | 0 | 0 | 7698000
DVRPC | 6 | Delaware | 92808 | Marshall Road over Cobbs Creek | 2024 | MCC | Bridge Replacement | CON | STU | 2027-06-24 |  | 0 | 0 | 0 | 758000 | 757000 | 758000 | 757000 | 757000 | 757000 | 4544000
DVRPC | 6 | Delaware | 92808 | Marshall Road over Cobbs Creek | 2024 | MCC | Bridge Replacement | CON | 185 | 2027-06-24 |  | 0 | 0 | 312000 | 990000 | 1001000 | 190000 | 189000 | 189000 | 189000 | 3060000
DVRPC | 6 | Delaware | 93105 | State Rd over Darby Creek | 1 | DSB | Bridge Replacement | FD | 185 | 2026-08-13 |  | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
DVRPC | 6 | Delaware | 93105 | State Rd over Darby Creek | 1 | DSB | Bridge Replacement | CON | 185 | 2026-08-13 |  | 2065171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2065171
DVRPC | 6 | Delaware | 93105 | State Rd over Darby Creek | 1 | DSB | Bridge Replacement | CON | 581 | 2026-08-13 |  | 0 | 1503829 | 3271000 | 2280000 | 0 | 0 | 0 | 0 | 0 | 7054829
DVRPC | 6 | Delaware | 95429 | US202/US1 Intersection Area Improvements | 202 | LPR | Additional Lanes | CON | STP | 2026-07-16 |  | 833000 | 833000 | 0 | 833000 | 0 | 0 | 0 | 0 | 0 | 2499000
DVRPC | 6 | Delaware | 95429 | US202/US1 Intersection Area Improvements | 202 | LPR | Additional Lanes | CON | STU | 2026-07-16 |  | 0 | 0 | 833000 | 0 | 0 | 0 | 0 | 0 | 0 | 833000
DVRPC | 6 | Delaware | 95429 | US202/US1 Intersection Area Improvements | 202 | LPR | Additional Lanes | CON | 581 | 2026-07-16 |  | 208000 | 208000 | 208000 | 208000 | 0 | 0 | 0 | 0 | 0 | 832000
DVRPC | 6 | Delaware | 98216 | Michigan Avenue over Little Crum Creek(C) |  | 210 | Bridge Replacement | CON | 183 | 2025-12-11 | 2025-12-11 | 0 | 1754000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1754000
DVRPC | 6 | Delaware | 98216 | Michigan Avenue over Little Crum Creek(C) |  | 210 | Bridge Replacement | CON | LOC | 2025-12-11 | 2025-12-11 | 0 | 439000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439000
DVRPC | 6 | Delaware | 98218 | South Ave over Muckinipattis Creek | 7023 | 142 | Bridge Replacement | FD | 183 | 2026-10-01 |  | 0 | 104000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104000
DVRPC | 6 | Delaware | 98218 | South Ave over Muckinipattis Creek | 7023 | 142 | Bridge Replacement | FD | LOC | 2026-10-01 |  | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000
DVRPC | 6 | Delaware | 99668 | SR 291 Drainage Improvmnt | 291 | FLB | Highway Restoration | FD | 581 | 2027-12-09 |  | 844000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 844000
DVRPC | 6 | Delaware | 99668 | SR 291 Drainage Improvmnt | 291 | FLB | Highway Restoration | ROW | 581 | 2027-12-09 |  | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
DVRPC | 6 | Delaware | 99668 | SR 291 Drainage Improvmnt | 291 | FLB | Highway Restoration | UTL | 581 | 2027-12-09 |  | 0 | 61000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61000
DVRPC | 6 | Delaware | 99668 | SR 291 Drainage Improvmnt | 291 | FLB | Highway Restoration | CON | 581 | 2027-12-09 |  | 0 | 1200000 | 2450000 | 2450000 | 2475000 | 0 | 0 | 0 | 0 | 8575000
DVRPC | 6 | Delaware | 103217 | Main St, 6th St & CSX Crossing Improvement | 2005 | 383 | Rail Highway Grade Crossing | FD | 581 | 2026-08-13 |  | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000
DVRPC | 6 | Delaware | 103217 | Main St, 6th St & CSX Crossing Improvement | 2005 | 383 | Rail Highway Grade Crossing | CON | RRX | 2026-08-13 |  | 0 | 0 | 0 | 0 | 369000 | 0 | 0 | 0 | 0 | 369000
DVRPC | 6 | Delaware | 103217 | Main St, 6th St & CSX Crossing Improvement | 2005 | 383 | Rail Highway Grade Crossing | CON | STU | 2026-08-13 |  | 3572000 | 1000000 | 1000000 | 1000000 | 572000 | 0 | 0 | 0 | 0 | 7144000
DVRPC | 6 | Delaware | 103521 | Reed Road over Whetstone Run | 7023 | 036 | Bridge Replacement | PE | BOF | 2028-06-08 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Delaware | 103521 | Reed Road over Whetstone Run | 7023 | 036 | Bridge Replacement | FD | 185 | 2028-06-08 |  | 0 | 0 | 394000 | 0 | 0 | 0 | 0 | 0 | 0 | 394000
DVRPC | 6 | Delaware | 103521 | Reed Road over Whetstone Run | 7023 | 036 | Bridge Replacement | ROW | BRIP | 2028-06-08 |  | 0 | 0 | 0 | 87000 | 0 | 0 | 0 | 0 | 0 | 87000
DVRPC | 6 | Delaware | 103521 | Reed Road over Whetstone Run | 7023 | 036 | Bridge Replacement | UTL | BRIP | 2028-06-08 |  | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 60000
DVRPC | 6 | Delaware | 103521 | Reed Road over Whetstone Run | 7023 | 036 | Bridge Replacement | CON | 185 | 2028-06-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7566000 | 7566000
DVRPC | 6 | Delaware | 103525 | Paper Mill Rd/Darby (R)(C) | 7023 | BRG | Bridge Restoration | PE | 183 |  | 2023-06-07 | 0 | 341493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341493
DVRPC | 6 | Delaware | 103525 | Paper Mill Rd/Darby (R)(C) | 7023 | BRG | Bridge Restoration | PE | LOC |  | 2023-06-07 | 0 | 85373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85373
DVRPC | 6 | Delaware | 103525 | Paper Mill Rd/Darby (R)(C) | 7023 | BRG | Bridge Restoration | ROW | 183 |  | 2023-06-07 | 0 | 101120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101120
DVRPC | 6 | Delaware | 103525 | Paper Mill Rd/Darby (R)(C) | 7023 | BRG | Bridge Restoration | ROW | LOC |  | 2023-06-07 | 0 | 25280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25280
DVRPC | 6 | Delaware | 103525 | Paper Mill Rd/Darby (R)(C) | 7023 | BRG | Bridge Restoration | CON | 183 |  | 2023-06-07 | 0 | 250000 | 2000000 | 701863 | 0 | 0 | 0 | 0 | 0 | 2951863
DVRPC | 6 | Delaware | 103525 | Paper Mill Rd/Darby (R)(C) | 7023 | BRG | Bridge Restoration | CON | LOC |  | 2023-06-07 | 0 | 62500 | 500000 | 175466 | 0 | 0 | 0 | 0 | 0 | 737966
DVRPC | 6 | Delaware | 103528 | Mattson Road over W Br Chester Creek | 7023 | MAP | Bridge Restoration | PE | STU | 2028-12-07 |  | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000
DVRPC | 6 | Delaware | 103528 | Mattson Road over W Br Chester Creek | 7023 | MAP | Bridge Restoration | FD | STP | 2028-12-07 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
DVRPC | 6 | Delaware | 103528 | Mattson Road over W Br Chester Creek | 7023 | MAP | Bridge Restoration | ROW | STP | 2028-12-07 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
DVRPC | 6 | Delaware | 103528 | Mattson Road over W Br Chester Creek | 7023 | MAP | Bridge Restoration | UTL | STP | 2028-12-07 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
DVRPC | 6 | Delaware | 103528 | Mattson Road over W Br Chester Creek | 7023 | MAP | Bridge Restoration | CON | STP | 2028-12-07 |  | 0 | 1315000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1315000
DVRPC | 6 | Delaware | 103535 | Manchester Road over Ridley Creek (R) | 7023 | BRG | Bridge Replacement | PE | 183 |  | 2023-06-14 | 219879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219879
DVRPC | 6 | Delaware | 103535 | Manchester Road over Ridley Creek (R) | 7023 | BRG | Bridge Replacement | PE | LOC |  | 2023-06-14 | 54970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54970
DVRPC | 6 | Delaware | 103535 | Manchester Road over Ridley Creek (R) | 7023 | BRG | Bridge Replacement | ROW | 183 |  | 2023-06-14 | 40868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40868
DVRPC | 6 | Delaware | 103535 | Manchester Road over Ridley Creek (R) | 7023 | BRG | Bridge Replacement | ROW | LOC |  | 2023-06-14 | 10217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10217
DVRPC | 6 | Delaware | 103535 | Manchester Road over Ridley Creek (R) | 7023 | BRG | Bridge Replacement | CON | 183 |  | 2023-06-14 | 1956211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1956211
DVRPC | 6 | Delaware | 103535 | Manchester Road over Ridley Creek (R) | 7023 | BRG | Bridge Replacement | CON | LOC |  | 2023-06-14 | 489053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489053
DVRPC | 6 | Delaware | 103546 | Pine Street over Darby Creek | 7023 | 145 | Bridge Restoration | PE | BOF |  |  | 0 | 600000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
DVRPC | 6 | Delaware | 103546 | Pine Street over Darby Creek | 7023 | 145 | Bridge Restoration | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000
DVRPC | 6 | Delaware | 103546 | Pine Street over Darby Creek | 7023 | 145 | Bridge Restoration | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000 | 0 | 155000
DVRPC | 6 | Delaware | 103546 | Pine Street over Darby Creek | 7023 | 145 | Bridge Restoration | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 0 | 175000
DVRPC | 6 | Delaware | 103546 | Pine Street over Darby Creek | 7023 | 145 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6270000 | 6270000
DVRPC | 6 | Delaware | 104343 | US 322 over CSX & Bethel Rd(C) | 322 | CSX | Bridge Replacement | FD | STU | 2025-09-25 | 2025-09-25 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Delaware | 104343 | US 322 over CSX & Bethel Rd(C) | 322 | CSX | Bridge Replacement | CON | BRIP | 2025-09-25 | 2025-09-25 | 0 | 0 | 4772000 | 8144000 | 5268000 | 2035144 | 1380000 | 6898000 | 31157856 | 59655000
DVRPC | 6 | Delaware | 104343 | US 322 over CSX & Bethel Rd(C) | 322 | CSX | Bridge Replacement | CON | STU | 2025-09-25 | 2025-09-25 | 3969000 | 6798000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10767000
DVRPC | 6 | Delaware | 104879 | Cheyney Rd over Br Chester Creek(C) | 4015 | DB1 | Bridge Replacement | ROW | 185 | 2025-08-21 | 2025-08-21 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
DVRPC | 6 | Delaware | 104879 | Cheyney Rd over Br Chester Creek(C) | 4015 | DB1 | Bridge Replacement | UTL | 185 | 2025-08-21 | 2025-08-21 | 398000 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1048000
DVRPC | 6 | Delaware | 104879 | Cheyney Rd over Br Chester Creek(C) | 4015 | DB1 | Bridge Replacement | CON | STU | 2025-08-21 | 2025-08-21 | 960000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960000
DVRPC | 6 | Delaware | 104879 | Cheyney Rd over Br Chester Creek(C) | 4015 | DB1 | Bridge Replacement | CON | 185 | 2025-08-21 | 2025-08-21 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
DVRPC | 6 | Delaware | 107642 | Smithbridge Road Trail & Roundabout | 3046 | OFF | Safety Improvement | CON | CAQ | 2026-10-22 |  | 1843000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1843000
DVRPC | 6 | Delaware | 107642 | Smithbridge Road Trail & Roundabout | 3046 | OFF | Safety Improvement | CON | HSIP | 2026-10-22 |  | 0 | 1055000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1055000
DVRPC | 6 | Delaware | 108910 | I-95 Chester City Noise Abatement Phs 2 | 95 | CNA | Highway Restoration | ROW | 581 | 2028-12-14 |  | 0 | 869000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869000
DVRPC | 6 | Delaware | 108910 | I-95 Chester City Noise Abatement Phs 2 | 95 | CNA | Highway Restoration | UTL | STU | 2028-12-14 |  | 0 | 0 | 760000 | 0 | 0 | 0 | 0 | 0 | 0 | 760000
DVRPC | 6 | Delaware | 108910 | I-95 Chester City Noise Abatement Phs 2 | 95 | CNA | Highway Restoration | CON | 581 | 2028-12-14 |  | 0 | 0 | 3167000 | 15721000 | 172000 | 0 | 0 | 0 | 0 | 19060000
DVRPC | 6 | Delaware | 110951 | Macdade Blvd Corridor Safety | 2006 | SIP | Safety Improvement | PE | HSIP | 2029-04-26 |  | 0 | 494959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494959
DVRPC | 6 | Delaware | 110951 | Macdade Blvd Corridor Safety | 2006 | SIP | Safety Improvement | CON | HSIP | 2029-04-26 |  | 0 | 0 | 0 | 2300645 | 0 | 0 | 0 | 0 | 0 | 2300645
DVRPC | 6 | Delaware | 111022 | Chichester Ave & I-95 Ramp Roundabouts | 3009 | SP2 | Safety Improvement | PE | CRPU | 2029-02-15 |  | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
DVRPC | 6 | Delaware | 111022 | Chichester Ave & I-95 Ramp Roundabouts | 3009 | SP2 | Safety Improvement | FD | HSIP | 2029-02-15 |  | 0 | 36385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36385
DVRPC | 6 | Delaware | 111022 | Chichester Ave & I-95 Ramp Roundabouts | 3009 | SP2 | Safety Improvement | CON | HSIP | 2029-02-15 |  | 0 | 0 | 848981 | 0 | 0 | 0 | 0 | 0 | 0 | 848981
DVRPC | 6 | Delaware | 111486 | Octoraro Trail Phase 1/1a |  | OTC | Bicycle Pedestrian Highway | CON | TAP | 2026-12-10 |  | 0 | 1163000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163000
DVRPC | 6 | Delaware | 111487 | Walkable Chadds Ford(C) | 1 | WCF | Bicycle Pedestrian Highway | CON | TAU | 2025-04-17 | 2025-04-17 | 770472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770472
DVRPC | 6 | Delaware | 111488 | Ridge Road Stormwater |  | MSW | Stormwater Management | CON | TAP | 2026-06-18 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
DVRPC | 6 | Delaware | 113251 | Highland Ave. Railroad Preemption | 291 | 386 | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
DVRPC | 6 | Delaware | 113416 | Concrete Arch Bridge Repair | 1 | MPH | Bridge Restoration | FD | 185 | 2026-10-22 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Delaware | 113416 | Concrete Arch Bridge Repair | 1 | MPH | Bridge Restoration | ROW | STP | 2026-10-22 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Delaware | 113416 | Concrete Arch Bridge Repair | 1 | MPH | Bridge Restoration | UTL | STP | 2026-10-22 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Delaware | 113416 | Concrete Arch Bridge Repair | 1 | MPH | Bridge Restoration | CON | STP | 2026-10-22 |  | 0 | 0 | 1200000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 2400000
DVRPC | 6 | Delaware | 114034 | US 322: Chelsea Parkway - Market St Int(C) | 322 | 103 | Additional Lanes | CON | NHPP | 2024-08-22 | 2024-08-22 | 19956000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19956000
DVRPC | 6 | Delaware | 114034 | US 322: Chelsea Parkway - Market St Int(C) | 322 | 103 | Additional Lanes | CON | STP | 2024-08-22 | 2024-08-22 | 2332000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2332000
DVRPC | 6 | Delaware | 114034 | US 322: Chelsea Parkway - Market St Int(C) | 322 | 103 | Additional Lanes | CON | STU | 2024-08-22 | 2024-08-22 | 579000 | 495000 | 4087000 | 3731000 | 6399000 | 12649000 | 13757000 | 1625000 | 0 | 43322000
DVRPC | 6 | Delaware | 114102 | West Chester Pk & 476(C) | 3 | DLR | Congestion Reduction | CON | CAQ | 2024-12-12 | 2024-12-12 | 1557343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557343
DVRPC | 6 | Delaware | 114112 | Media Bypass ITS | 1 | ITS | Intelligent Transportation System | FD | CAQ | 2028-02-17 |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Delaware | 114167 | Naamans Cr Rd & SR 202(C) | 202 | DCT | Congestion Reduction | CON | CAQ | 2022-07-28 | 2022-07-28 | 0 | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111000
DVRPC | 6 | Delaware | 115426 | Haverford Rd Corridor Safety Improvements | 1001 | SIP | Safety Improvement | CON | HSIP | 2028-01-13 |  | 0 | 0 | 0 | 2039000 | 0 | 0 | 0 | 0 | 0 | 2039000
DVRPC | 6 | Delaware | 115427 | Lansdowne Ave. Corridor Safety Improvements(C) | 2005 | SP2 | Safety Improvement | CON | CRPU | 2024-08-22 | 2024-08-22 | 0 | 287000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287000
DVRPC | 6 | Delaware | 115427 | Lansdowne Ave. Corridor Safety Improvements(C) | 2005 | SP2 | Safety Improvement | CON | HSIP | 2024-08-22 | 2024-08-22 | 163286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163286
DVRPC | 6 | Delaware | 115872 | 4th Street RR WD | 2029 | 388 | Rail Highway Grade Crossing | CON | RRX |  |  | 17082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17082
DVRPC | 6 | Delaware | 115969 | Regional GIS Coordination |  |  | Planning/Research/Administration | PE | STU |  |  | 350000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
DVRPC | 6 | Delaware | 117957 | Highland Ave. Complete St.(C) |  | HCS | Bicycle Pedestrian Highway | CON | TAU | 2025-02-27 | 2025-02-27 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000
DVRPC | 6 | Delaware | 118006 | Ridley Creek Rd over Br Ridley Creek | 4003 | DRC | Bridge Replacement | FD | BRIP | 2028-12-14 |  | 0 | 563000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563000
DVRPC | 6 | Delaware | 118006 | Ridley Creek Rd over Br Ridley Creek | 4003 | DRC | Bridge Replacement | ROW | BRIP | 2028-12-14 |  | 0 | 0 | 0 | 278000 | 0 | 0 | 0 | 0 | 0 | 278000
DVRPC | 6 | Delaware | 118006 | Ridley Creek Rd over Br Ridley Creek | 4003 | DRC | Bridge Replacement | ROW | 183 | 2028-12-14 |  | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 70000
DVRPC | 6 | Delaware | 118006 | Ridley Creek Rd over Br Ridley Creek | 4003 | DRC | Bridge Replacement | UTL | BRIP | 2028-12-14 |  | 0 | 0 | 0 | 0 | 478000 | 0 | 0 | 0 | 0 | 478000
DVRPC | 6 | Delaware | 118006 | Ridley Creek Rd over Br Ridley Creek | 4003 | DRC | Bridge Replacement | UTL | 183 | 2028-12-14 |  | 0 | 0 | 0 | 0 | 119000 | 0 | 0 | 0 | 0 | 119000
DVRPC | 6 | Delaware | 118006 | Ridley Creek Rd over Br Ridley Creek | 4003 | DRC | Bridge Replacement | CON | BRIP | 2028-12-14 |  | 0 | 0 | 0 | 0 | 0 | 984000 | 0 | 0 | 0 | 984000
DVRPC | 6 | Delaware | 118006 | Ridley Creek Rd over Br Ridley Creek | 4003 | DRC | Bridge Replacement | CON | 183 | 2028-12-14 |  | 0 | 0 | 0 | 0 | 0 | 246000 | 0 | 0 | 0 | 246000
DVRPC | 6 | Delaware | 118029 | Concrd, Foulk, Chelsea & Valleybrook Intersection | 3007 | DBR | Congestion Reduction | FD | STP |  |  | 0 | 699000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 699000
DVRPC | 6 | Delaware | 118029 | Concrd, Foulk, Chelsea & Valleybrook Intersection | 3007 | DBR | Congestion Reduction | FD | 581 |  |  | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
DVRPC | 6 | Delaware | 118029 | Concrd, Foulk, Chelsea & Valleybrook Intersection | 3007 | DBR | Congestion Reduction | ROW | STP |  |  | 0 | 0 | 0 | 325000 | 0 | 0 | 0 | 0 | 0 | 325000
DVRPC | 6 | Delaware | 118029 | Concrd, Foulk, Chelsea & Valleybrook Intersection | 3007 | DBR | Congestion Reduction | ROW | 581 |  |  | 0 | 0 | 0 | 81000 | 0 | 0 | 0 | 0 | 0 | 81000
DVRPC | 6 | Delaware | 118029 | Concrd, Foulk, Chelsea & Valleybrook Intersection | 3007 | DBR | Congestion Reduction | UTL | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 101000 | 0 | 0 | 101000
DVRPC | 6 | Delaware | 118029 | Concrd, Foulk, Chelsea & Valleybrook Intersection | 3007 | DBR | Congestion Reduction | UTL | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
DVRPC | 6 | Delaware | 118029 | Concrd, Foulk, Chelsea & Valleybrook Intersection | 3007 | DBR | Congestion Reduction | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4054000 | 0 | 0 | 4054000
DVRPC | 6 | Delaware | 118029 | Concrd, Foulk, Chelsea & Valleybrook Intersection | 3007 | DBR | Congestion Reduction | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1013000 | 0 | 0 | 1013000
DVRPC | 6 | Delaware | 118030 | Newtown Trail |  | BME | Bicycle Pedestrian Highway | PE | STP |  |  | 154000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154000
DVRPC | 6 | Delaware | 118030 | Newtown Trail |  | BME | Bicycle Pedestrian Highway | PE | 581 |  |  | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000
DVRPC | 6 | Delaware | 118030 | Newtown Trail |  | BME | Bicycle Pedestrian Highway | FD | STU |  |  | 0 | 77000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77000
DVRPC | 6 | Delaware | 118030 | Newtown Trail |  | BME | Bicycle Pedestrian Highway | FD | 581 |  |  | 0 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000
DVRPC | 6 | Delaware | 118030 | Newtown Trail |  | BME | Bicycle Pedestrian Highway | CON | 581 |  |  | 0 | 0 | 1928000 | 0 | 0 | 0 | 0 | 0 | 0 | 1928000
DVRPC | 6 | Delaware | 118353 | West Cobbs Creek Pkwy Infrastr |  | WCC | Safety Improvement | CON | TAP | 2026-06-04 |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Delaware | 118358 | Garrett Rd Connectivity | 2019 | GRM | Bicycle Pedestrian Highway | CON | TAP | 2027-01-28 |  | 0 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000
DVRPC | 6 | Delaware | 118360 | Providence Road Sidewalk Improvements | 252 | PRS | Bicycle Pedestrian Highway | CON | TAP | 2026-12-10 |  | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Delaware | 118494 | EastDelCo BkwyImplemntatn Program(TOP) |  | TOP | Bicycle Pedestrian Highway | CON | CAQ |  |  | 0 | 0 | 552000 | 0 | 0 | 0 | 0 | 0 | 0 | 552000
DVRPC | 6 | Delaware | 118494 | EastDelCo BkwyImplemntatn Program(TOP) |  | TOP | Bicycle Pedestrian Highway | CON | LOC |  |  | 0 | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 130000
DVRPC | 6 | Delaware | 119435 | PA 452 @ I-95 Interchange | 452 | I95 | Highway Reconstruction | FD | NHPP | 2028-05-11 |  | 1036000 | 385791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1421791
DVRPC | 6 | Delaware | 119435 | PA 452 @ I-95 Interchange | 452 | I95 | Highway Reconstruction | FD | STU | 2028-05-11 |  | 78209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78209
DVRPC | 6 | Delaware | 119435 | PA 452 @ I-95 Interchange | 452 | I95 | Highway Reconstruction | ROW | NHPP | 2028-05-11 |  | 0 | 0 | 430000 | 0 | 0 | 0 | 0 | 0 | 0 | 430000
DVRPC | 6 | Delaware | 119435 | PA 452 @ I-95 Interchange | 452 | I95 | Highway Reconstruction | UTL | NHPP | 2028-05-11 |  | 0 | 0 | 0 | 0 | 0 | 101000 | 0 | 0 | 0 | 101000
DVRPC | 6 | Delaware | 119435 | PA 452 @ I-95 Interchange | 452 | I95 | Highway Reconstruction | UTL | 581 | 2028-05-11 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
DVRPC | 6 | Delaware | 119435 | PA 452 @ I-95 Interchange | 452 | I95 | Highway Reconstruction | CON | NHPP | 2028-05-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3851000 | 0 | 0 | 3851000
DVRPC | 6 | Delaware | 119435 | PA 452 @ I-95 Interchange | 452 | I95 | Highway Reconstruction | CON | 581 | 2028-05-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 963000 | 0 | 0 | 963000
DVRPC | 6 | Delaware | 119558 | ADA Ramps DelCo & ChesCo(C) | 3021 | A10 | Americans with Disabilities Act (ADA) | CON | CRPU | 2024-08-08 | 2024-08-22 | 1950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1950000
DVRPC | 6 | Delaware | 119917 | Concord Road: Bethel Rd & Engle St | 3007 | DBE | Highway Reconstruction | FD | STU |  |  | 628000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628000
DVRPC | 6 | Delaware | 119917 | Concord Road: Bethel Rd & Engle St | 3007 | DBE | Highway Reconstruction | FD | 581 |  |  | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000
DVRPC | 6 | Delaware | 119917 | Concord Road: Bethel Rd & Engle St | 3007 | DBE | Highway Reconstruction | ROW | STU |  |  | 0 | 0 | 0 | 0 | 478000 | 0 | 0 | 0 | 0 | 478000
DVRPC | 6 | Delaware | 119917 | Concord Road: Bethel Rd & Engle St | 3007 | DBE | Highway Reconstruction | ROW | 581 |  |  | 0 | 0 | 0 | 0 | 119000 | 0 | 0 | 0 | 0 | 119000
DVRPC | 6 | Delaware | 119917 | Concord Road: Bethel Rd & Engle St | 3007 | DBE | Highway Reconstruction | UTL | STU |  |  | 0 | 0 | 0 | 0 | 0 | 236000 | 0 | 0 | 0 | 236000
DVRPC | 6 | Delaware | 119917 | Concord Road: Bethel Rd & Engle St | 3007 | DBE | Highway Reconstruction | UTL | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 59000 | 0 | 0 | 0 | 59000
DVRPC | 6 | Delaware | 119917 | Concord Road: Bethel Rd & Engle St | 3007 | DBE | Highway Reconstruction | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3851000 | 0 | 0 | 3851000
DVRPC | 6 | Delaware | 119917 | Concord Road: Bethel Rd & Engle St | 3007 | DBE | Highway Reconstruction | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 963000 | 0 | 0 | 963000
DVRPC | 6 | Delaware | 120374 | Concord Rd & Bridgewater Rd | 3007 | BWI | Highway Reconstruction | FD | STU |  |  | 0 | 612000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612000
DVRPC | 6 | Delaware | 120374 | Concord Rd & Bridgewater Rd | 3007 | BWI | Highway Reconstruction | FD | 581 |  |  | 0 | 153000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153000
DVRPC | 6 | Delaware | 120374 | Concord Rd & Bridgewater Rd | 3007 | BWI | Highway Reconstruction | ROW | STU |  |  | 0 | 0 | 0 | 0 | 430000 | 0 | 0 | 0 | 0 | 430000
DVRPC | 6 | Delaware | 120374 | Concord Rd & Bridgewater Rd | 3007 | BWI | Highway Reconstruction | ROW | 581 |  |  | 0 | 0 | 0 | 0 | 107000 | 0 | 0 | 0 | 0 | 107000
DVRPC | 6 | Delaware | 120374 | Concord Rd & Bridgewater Rd | 3007 | BWI | Highway Reconstruction | UTL | STU |  |  | 0 | 0 | 0 | 0 | 0 | 359000 | 0 | 0 | 0 | 359000
DVRPC | 6 | Delaware | 120374 | Concord Rd & Bridgewater Rd | 3007 | BWI | Highway Reconstruction | UTL | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 90000
DVRPC | 6 | Delaware | 120374 | Concord Rd & Bridgewater Rd | 3007 | BWI | Highway Reconstruction | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3040000 | 0 | 0 | 3040000
DVRPC | 6 | Delaware | 120374 | Concord Rd & Bridgewater Rd | 3007 | BWI | Highway Reconstruction | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 760000 | 0 | 0 | 760000
DVRPC | 6 | Delaware | 120688 | Concord Rd & McDonald Blvd | 3007 | DMB | Highway Reconstruction | FD | STU | 2029-02-15 |  | 594000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594000
DVRPC | 6 | Delaware | 120688 | Concord Rd & McDonald Blvd | 3007 | DMB | Highway Reconstruction | FD | 581 | 2029-02-15 |  | 149000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149000
DVRPC | 6 | Delaware | 120688 | Concord Rd & McDonald Blvd | 3007 | DMB | Highway Reconstruction | ROW | STU | 2029-02-15 |  | 0 | 0 | 0 | 0 | 478000 | 0 | 0 | 0 | 0 | 478000
DVRPC | 6 | Delaware | 120688 | Concord Rd & McDonald Blvd | 3007 | DMB | Highway Reconstruction | ROW | 581 | 2029-02-15 |  | 0 | 0 | 0 | 0 | 119000 | 0 | 0 | 0 | 0 | 119000
DVRPC | 6 | Delaware | 120688 | Concord Rd & McDonald Blvd | 3007 | DMB | Highway Reconstruction | UTL | STU | 2029-02-15 |  | 0 | 0 | 0 | 0 | 0 | 394000 | 0 | 0 | 0 | 394000
DVRPC | 6 | Delaware | 120688 | Concord Rd & McDonald Blvd | 3007 | DMB | Highway Reconstruction | UTL | 581 | 2029-02-15 |  | 0 | 0 | 0 | 0 | 0 | 98000 | 0 | 0 | 0 | 98000
DVRPC | 6 | Delaware | 120688 | Concord Rd & McDonald Blvd | 3007 | DMB | Highway Reconstruction | CON | 581 | 2029-02-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3808000 | 2588000 | 571000 | 6967000
DVRPC | 6 | Delaware | 120910 | Kedron Avenue over Stony Creek | 420 | KAS | Bridge Replacement | PE | 185 |  |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Delaware | 120910 | Kedron Avenue over Stony Creek | 420 | KAS | Bridge Replacement | FD | STU |  |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Delaware | 120910 | Kedron Avenue over Stony Creek | 420 | KAS | Bridge Replacement | ROW | STU |  |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Delaware | 120910 | Kedron Avenue over Stony Creek | 420 | KAS | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Delaware | 120910 | Kedron Avenue over Stony Creek | 420 | KAS | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 1500000
DVRPC | 6 | Montgomery | 16150 | Tokany Creek Parkway over Jenkintwn Creek | 7102 | CHE | Bridge Replacement | FD | 183 |  |  | 382000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382000
DVRPC | 6 | Montgomery | 16150 | Tokany Creek Parkway over Jenkintwn Creek | 7102 | CHE | Bridge Replacement | FD | LOC |  |  | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96000
DVRPC | 6 | Montgomery | 16150 | Tokany Creek Parkway over Jenkintwn Creek | 7102 | CHE | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 54000 | 0 | 0 | 0 | 0 | 0 | 54000
DVRPC | 6 | Montgomery | 16150 | Tokany Creek Parkway over Jenkintwn Creek | 7102 | CHE | Bridge Replacement | ROW | 183 |  |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
DVRPC | 6 | Montgomery | 16150 | Tokany Creek Parkway over Jenkintwn Creek | 7102 | CHE | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 70000
DVRPC | 6 | Montgomery | 16150 | Tokany Creek Parkway over Jenkintwn Creek | 7102 | CHE | Bridge Replacement | UTL | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 13000
DVRPC | 6 | Montgomery | 16150 | Tokany Creek Parkway over Jenkintwn Creek | 7102 | CHE | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2419000 | 2419000
DVRPC | 6 | Montgomery | 16150 | Tokany Creek Parkway over Jenkintwn Creek | 7102 | CHE | Bridge Replacement | CON | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454000 | 454000
DVRPC | 6 | Montgomery | 16178 | Construction Management Tasks |  |  | Planning/Research/Administration | PRA | 581 |  |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
DVRPC | 6 | Montgomery | 16214 | Old York Road over SEPTA | 611 | MBR | Bridge Replacement | CON | BRIP | 2026-12-03 |  | 0 | 6946706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6946706
DVRPC | 6 | Montgomery | 16214 | Old York Road over SEPTA | 611 | MBR | Bridge Replacement | CON | NHPP | 2026-12-03 |  | 4502000 | 999000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5501000
DVRPC | 6 | Montgomery | 16214 | Old York Road over SEPTA | 611 | MBR | Bridge Replacement | CON | STU | 2026-12-03 |  | 1170000 | 2772294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3942294
DVRPC | 6 | Montgomery | 16239 | New Hanover Sqr Rd Bridge (C) | 4030 | NHS | Bridge Replacement | UTL | 185 | 2021-03-11 | 2021-03-11 | 129000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129000
DVRPC | 6 | Montgomery | 16292 | Washington St. over Norfolk Southern RR | 7416 | MWA | Bridge Replacement | PE | BOF |  |  | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
DVRPC | 6 | Montgomery | 16292 | Washington St. over Norfolk Southern RR | 7416 | MWA | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000
DVRPC | 6 | Montgomery | 16292 | Washington St. over Norfolk Southern RR | 7416 | MWA | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 250000
DVRPC | 6 | Montgomery | 16292 | Washington St. over Norfolk Southern RR | 7416 | MWA | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
DVRPC | 6 | Montgomery | 16292 | Washington St. over Norfolk Southern RR | 7416 | MWA | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8100000 | 0 | 8100000
DVRPC | 6 | Montgomery | 16334 | Church Rd:Greenwd-Rice's(C) | 73 | 04N | Congestion Reduction | FD | CAQ | 2024-02-29 | 2024-02-29 | 84762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84762
DVRPC | 6 | Montgomery | 16334 | Church Rd:Greenwd-Rice's(C) | 73 | 04N | Congestion Reduction | FD | 581 | 2024-02-29 | 2024-02-29 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000
DVRPC | 6 | Montgomery | 16334 | Church Rd:Greenwd-Rice's(C) | 73 | 04N | Congestion Reduction | CON | CAQ | 2024-02-29 | 2024-02-29 | 6500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500000
DVRPC | 6 | Montgomery | 16408 | Fruitville Road over Perkiomen Creek | 7046 | 232 | Bridge Replacement | PE | BRIP | 2028-06-15 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
DVRPC | 6 | Montgomery | 16408 | Fruitville Road over Perkiomen Creek | 7046 | 232 | Bridge Replacement | PE | 183 | 2028-06-15 |  | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
DVRPC | 6 | Montgomery | 16408 | Fruitville Road over Perkiomen Creek | 7046 | 232 | Bridge Replacement | PE | LOC | 2028-06-15 |  | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
DVRPC | 6 | Montgomery | 16408 | Fruitville Road over Perkiomen Creek | 7046 | 232 | Bridge Replacement | FD | BOF | 2028-06-15 |  | 628000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628000
DVRPC | 6 | Montgomery | 16408 | Fruitville Road over Perkiomen Creek | 7046 | 232 | Bridge Replacement | FD | 183 | 2028-06-15 |  | 118000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118000
DVRPC | 6 | Montgomery | 16408 | Fruitville Road over Perkiomen Creek | 7046 | 232 | Bridge Replacement | ROW | BOF | 2028-06-15 |  | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
DVRPC | 6 | Montgomery | 16408 | Fruitville Road over Perkiomen Creek | 7046 | 232 | Bridge Replacement | ROW | 183 | 2028-06-15 |  | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000
DVRPC | 6 | Montgomery | 16408 | Fruitville Road over Perkiomen Creek | 7046 | 232 | Bridge Replacement | CON | BOF | 2028-06-15 |  | 0 | 0 | 0 | 1146000 | 1146000 | 1146000 | 2292000 | 0 | 0 | 5730000
DVRPC | 6 | Montgomery | 16408 | Fruitville Road over Perkiomen Creek | 7046 | 232 | Bridge Replacement | CON | 183 | 2028-06-15 |  | 0 | 0 | 0 | 215000 | 215000 | 215000 | 430000 | 0 | 0 | 1075000
DVRPC | 6 | Montgomery | 16408 | Fruitville Road over Perkiomen Creek | 7046 | 232 | Bridge Replacement | CON | LOC | 2028-06-15 |  | 0 | 0 | 0 | 72000 | 72000 | 72000 | 144000 | 0 | 0 | 360000
DVRPC | 6 | Montgomery | 16438 | PA 63/PA 309 - Phase 1(C) | 1058 | HAT | New Alignment | FD | NHPP | 2009-07-02 | 2009-07-02 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
DVRPC | 6 | Montgomery | 16483 | Washington Lane over SEPTA & Tacony Creek | 73 | MWL | Bridge Restoration | PE | BRIP | 2029-06-07 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
DVRPC | 6 | Montgomery | 16483 | Washington Lane over SEPTA & Tacony Creek | 73 | MWL | Bridge Restoration | PE | 185 | 2029-06-07 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Montgomery | 16483 | Washington Lane over SEPTA & Tacony Creek | 73 | MWL | Bridge Restoration | FD | 185 | 2029-06-07 |  | 0 | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
DVRPC | 6 | Montgomery | 16483 | Washington Lane over SEPTA & Tacony Creek | 73 | MWL | Bridge Restoration | ROW | 185 | 2029-06-07 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Montgomery | 16483 | Washington Lane over SEPTA & Tacony Creek | 73 | MWL | Bridge Restoration | UTL | 185 | 2029-06-07 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Montgomery | 16483 | Washington Lane over SEPTA & Tacony Creek | 73 | MWL | Bridge Restoration | CON | 185 | 2029-06-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000
DVRPC | 6 | Montgomery | 16577 | Ridge Pk: Harmon Rd - Crescent Ave. | 0 | BCP | Highway Restoration | ROW | STU | 2027-12-16 |  | 2122000 | 2122000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4244000
DVRPC | 6 | Montgomery | 16577 | Ridge Pk: Harmon Rd - Crescent Ave. | 0 | BCP | Highway Restoration | UTL | STU | 2027-12-16 |  | 0 | 1748000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1748000
DVRPC | 6 | Montgomery | 16577 | Ridge Pk: Harmon Rd - Crescent Ave. | 0 | BCP | Highway Restoration | CON | STU | 2027-12-16 |  | 0 | 1121000 | 2121000 | 2116000 | 3127000 | 4121000 | 2121000 | 5121000 | 9000000 | 28848000
DVRPC | 6 | Montgomery | 16651 | East High Street over Sprogels Run | 4031 | MSR | Bridge Restoration | PE | PRTCT | 2029-03-01 |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
DVRPC | 6 | Montgomery | 16651 | East High Street over Sprogels Run | 4031 | MSR | Bridge Restoration | CON | PRTCT | 2029-03-01 |  | 0 | 0 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | 2600000
DVRPC | 6 | Montgomery | 16665 | US 202: Markley St (SB)(Parent) | 202 | 500 | Additional Lanes | FD | 581 |  |  | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
DVRPC | 6 | Montgomery | 16688 | River Rd@Balligomingo(F) | 23 | 99S | Safety Improvement | UTL | STU | 2011-08-18 | 2011-02-17 | 13078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13078
DVRPC | 6 | Montgomery | 16738 | US 422: Norfolk Southern - Evergreen Rd(C) | 422 | M1B | Highway Reconstruction | CON | NHPP | 2023-09-28 | 2023-09-28 | 35689349 | 3879000 | 0 | 0 | 846000 | 5290000 | 0 | 1896651 | 0 | 47601000
DVRPC | 6 | Montgomery | 16738 | US 422: Norfolk Southern - Evergreen Rd(C) | 422 | M1B | Highway Reconstruction | CON | STU | 2023-09-28 | 2023-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 4572000 | 0 | 0 | 4572000
DVRPC | 6 | Montgomery | 16738 | US 422: Norfolk Southern - Evergreen Rd(C) | 422 | M1B | Highway Reconstruction | CON | 581 | 2023-09-28 | 2023-09-28 | 6732000 | 970000 | 0 | 0 | 212000 | 1323000 | 1143000 | 2483000 | 182000 | 13045000
DVRPC | 6 | Montgomery | 48172 | PA 23: Moore to Geerdes | 23 | TCB | New Alignment | FD | STU | 2028-11-02 |  | 1013000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1013000
DVRPC | 6 | Montgomery | 48172 | PA 23: Moore to Geerdes | 23 | TCB | New Alignment | ROW | STU | 2028-11-02 |  | 405000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405000
DVRPC | 6 | Montgomery | 48172 | PA 23: Moore to Geerdes | 23 | TCB | New Alignment | ROW | 581 | 2028-11-02 |  | 101000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101000
DVRPC | 6 | Montgomery | 48172 | PA 23: Moore to Geerdes | 23 | TCB | New Alignment | UTL | STU | 2028-11-02 |  | 0 | 0 | 0 | 526000 | 0 | 0 | 0 | 0 | 0 | 526000
DVRPC | 6 | Montgomery | 48172 | PA 23: Moore to Geerdes | 23 | TCB | New Alignment | UTL | 581 | 2028-11-02 |  | 0 | 0 | 658000 | 658000 | 0 | 0 | 0 | 0 | 0 | 1316000
DVRPC | 6 | Montgomery | 48172 | PA 23: Moore to Geerdes | 23 | TCB | New Alignment | CON | 185 | 2028-11-02 |  | 0 | 0 | 0 | 0 | 0 | 4585000 | 4443000 | 7607000 | 3263000 | 19898000
DVRPC | 6 | Montgomery | 48174 | PA 63, PA 152 & Norristown Rd Improvements | 63 | C01 | Highway Restoration | ROW | STU | 2028-09-28 |  | 2971000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2971000
DVRPC | 6 | Montgomery | 48174 | PA 63, PA 152 & Norristown Rd Improvements | 63 | C01 | Highway Restoration | ROW | 581 | 2028-09-28 |  | 743000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 743000
DVRPC | 6 | Montgomery | 48174 | PA 63, PA 152 & Norristown Rd Improvements | 63 | C01 | Highway Restoration | CON | STP | 2028-09-28 |  | 0 | 0 | 463000 | 1805000 | 1805000 | 106000 | 4805000 | 0 | 0 | 8984000
DVRPC | 6 | Montgomery | 48174 | PA 63, PA 152 & Norristown Rd Improvements | 63 | C01 | Highway Restoration | CON | STU | 2028-09-28 |  | 0 | 2805000 | 1342000 | 0 | 0 | 2699000 | 0 | 1000000 | 0 | 7846000
DVRPC | 6 | Montgomery | 48174 | PA 63, PA 152 & Norristown Rd Improvements | 63 | C01 | Highway Restoration | CON | 581 | 2028-09-28 |  | 0 | 701000 | 451000 | 451000 | 451000 | 701000 | 1201000 | 250000 | 0 | 4206000
DVRPC | 6 | Montgomery | 48175 | RidgePk:Belvoir-Chemical(Parent) (C) |  | MG2 | Highway Reconstruction | CON | STU | 2023-04-27 | 2023-04-27 | 1450000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000
DVRPC | 6 | Montgomery | 48175 | RidgePk:Belvoir-Chemical(Parent) (C) |  | MG2 | Highway Reconstruction | CON | LOC | 2023-04-27 | 2023-04-27 | 363000 | 187000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
DVRPC | 6 | Montgomery | 48187 | S.Gulph & Henderson | 3039 | SGR | Additional Lanes | FD | 581 |  |  | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000
DVRPC | 6 | Montgomery | 48187 | S.Gulph & Henderson | 3039 | SGR | Additional Lanes | ROW | STP |  |  | 0 | 0 | 0 | 0 | 0 | 598000 | 0 | 0 | 0 | 598000
DVRPC | 6 | Montgomery | 48187 | S.Gulph & Henderson | 3039 | SGR | Additional Lanes | ROW | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 149000 | 0 | 0 | 0 | 149000
DVRPC | 6 | Montgomery | 48187 | S.Gulph & Henderson | 3039 | SGR | Additional Lanes | UTL | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 947000 | 0 | 0 | 947000
DVRPC | 6 | Montgomery | 48187 | S.Gulph & Henderson | 3039 | SGR | Additional Lanes | UTL | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 237000 | 0 | 0 | 237000
DVRPC | 6 | Montgomery | 48187 | S.Gulph & Henderson | 3039 | SGR | Additional Lanes | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 3972000 | 15512000 | 0 | 0 | 19484000
DVRPC | 6 | Montgomery | 57176 | Easton Rd & I-276 Interchange Improvements | 611 | MER | Additional Lanes | PE | 185 |  |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Montgomery | 57176 | Easton Rd & I-276 Interchange Improvements | 611 | MER | Additional Lanes | FD | STP |  |  | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
DVRPC | 6 | Montgomery | 57176 | Easton Rd & I-276 Interchange Improvements | 611 | MER | Additional Lanes | ROW | STP |  |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
DVRPC | 6 | Montgomery | 57176 | Easton Rd & I-276 Interchange Improvements | 611 | MER | Additional Lanes | UTL | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000
DVRPC | 6 | Montgomery | 57176 | Easton Rd & I-276 Interchange Improvements | 611 | MER | Additional Lanes | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4825000 | 10175000 | 15000000
DVRPC | 6 | Montgomery | 57630 | Districtwide SWM/MS4 Improvements Group 1 | 63 | SWM | Stormwater Management | PE | PRTCT | 2026-11-05 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
DVRPC | 6 | Montgomery | 57630 | Districtwide SWM/MS4 Improvements Group 1 | 63 | SWM | Stormwater Management | CON | PRTCT | 2026-11-05 |  | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
DVRPC | 6 | Montgomery | 63486 | US202:Johnson-Swede #4 (C) | 202 | 61S | Additional Lanes | CON | NHPP | 2021-01-14 | 2021-01-14 | 1168000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1168000
DVRPC | 6 | Montgomery | 63486 | US202:Johnson-Swede #4 (C) | 202 | 61S | Additional Lanes | CON | STU | 2021-01-14 | 2021-01-14 | 1132000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1132000
DVRPC | 6 | Montgomery | 63490 | US202:Swede-Morris #2 (C) | 202 | 61N | Additional Lanes | ROW | STU | 2018-07-26 | 2018-08-02 | 10583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10583
DVRPC | 6 | Montgomery | 63490 | US202:Swede-Morris #2 (C) | 202 | 61N | Additional Lanes | CON | NHPP | 2018-07-26 | 2018-08-02 | 4800000 | 1560000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6360000
DVRPC | 6 | Montgomery | 63490 | US202:Swede-Morris #2 (C) | 202 | 61N | Additional Lanes | CON | 581 | 2018-07-26 | 2018-08-02 | 1200000 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1590000
DVRPC | 6 | Montgomery | 64795 | Rock Hil Rd & Belmont Av Improvements | 3045 | MRH | Additional Lanes | ROW | STU | 2027-02-25 |  | 875000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875000
DVRPC | 6 | Montgomery | 64795 | Rock Hil Rd & Belmont Av Improvements | 3045 | MRH | Additional Lanes | CON | BRIP | 2027-02-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21214000 | 21214000
DVRPC | 6 | Montgomery | 64798 | N Narberth Ave over Amtrak(C) | 7412 | NNA | Bridge Replacement | CON | BOF | 2025-05-08 | 2025-05-08 | 7728000 | 2155000 | 2638000 | 1593000 | 2723000 | 0 | 0 | 0 | 0 | 16837000
DVRPC | 6 | Montgomery | 66952 | PA23/US422 Int & N Gulph | 23 | 2NG | Highway Reconstruction | FD | STU | 2027-01-14 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Montgomery | 66952 | PA23/US422 Int & N Gulph | 23 | 2NG | Highway Reconstruction | FD | 581 | 2027-01-14 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
DVRPC | 6 | Montgomery | 66952 | PA23/US422 Int & N Gulph | 23 | 2NG | Highway Reconstruction | ROW | STU | 2027-01-14 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
DVRPC | 6 | Montgomery | 66952 | PA23/US422 Int & N Gulph | 23 | 2NG | Highway Reconstruction | ROW | 581 | 2027-01-14 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
DVRPC | 6 | Montgomery | 66952 | PA23/US422 Int & N Gulph | 23 | 2NG | Highway Reconstruction | UTL | STU | 2027-01-14 |  | 0 | 0 | 1520000 | 0 | 0 | 0 | 0 | 0 | 0 | 1520000
DVRPC | 6 | Montgomery | 66952 | PA23/US422 Int & N Gulph | 23 | 2NG | Highway Reconstruction | UTL | 581 | 2027-01-14 |  | 0 | 0 | 380000 | 0 | 0 | 0 | 0 | 0 | 0 | 380000
DVRPC | 6 | Montgomery | 66952 | PA23/US422 Int & N Gulph | 23 | 2NG | Highway Reconstruction | CON | STU | 2027-01-14 |  | 1433000 | 2000000 | 1000000 | 1200000 | 1000000 | 0 | 0 | 0 | 0 | 6633000
DVRPC | 6 | Montgomery | 66952 | PA23/US422 Int & N Gulph | 23 | 2NG | Highway Reconstruction | CON | SXF | 2027-01-14 |  | 6081000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6081000
DVRPC | 6 | Montgomery | 72355 | W Valley Green Rd over Wissahickon Creek | 7046 | 059 | Bridge Replacement | FD | STU | 2028-06-08 |  | 538000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538000
DVRPC | 6 | Montgomery | 72355 | W Valley Green Rd over Wissahickon Creek | 7046 | 059 | Bridge Replacement | FD | 183 | 2028-06-08 |  | 101000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101000
DVRPC | 6 | Montgomery | 72355 | W Valley Green Rd over Wissahickon Creek | 7046 | 059 | Bridge Replacement | ROW | STU | 2028-06-08 |  | 116000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116000
DVRPC | 6 | Montgomery | 72355 | W Valley Green Rd over Wissahickon Creek | 7046 | 059 | Bridge Replacement | ROW | 183 | 2028-06-08 |  | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000
DVRPC | 6 | Montgomery | 72355 | W Valley Green Rd over Wissahickon Creek | 7046 | 059 | Bridge Replacement | CON | STP | 2028-06-08 |  | 0 | 1113000 | 1113000 | 557000 | 557000 | 0 | 0 | 0 | 0 | 3340000
DVRPC | 6 | Montgomery | 72355 | W Valley Green Rd over Wissahickon Creek | 7046 | 059 | Bridge Replacement | CON | 183 | 2028-06-08 |  | 0 | 209000 | 209000 | 104000 | 104000 | 0 | 0 | 0 | 0 | 626000
DVRPC | 6 | Montgomery | 74813 | Ambler Borough Street Imp(L)(C) |  | AS2 | Bicycle Pedestrian Highway | CON | STP | 2024-05-23 | 2024-05-23 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000
DVRPC | 6 | Montgomery | 77211 | 309 Cnntr: Allntwn Rd-Souderton Pk (C) | 1058 | HT2 | New Alignment | UTL | STU | 2021-10-21 | 2021-10-21 | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000
DVRPC | 6 | Montgomery | 77211 | 309 Cnntr: Allntwn Rd-Souderton Pk (C) | 1058 | HT2 | New Alignment | UTL | 581 | 2021-10-21 | 2021-10-21 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000
DVRPC | 6 | Montgomery | 77211 | 309 Cnntr: Allntwn Rd-Souderton Pk (C) | 1058 | HT2 | New Alignment | CON | STU | 2021-10-21 | 2021-10-21 | 1500000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
DVRPC | 6 | Montgomery | 77211 | 309 Cnntr: Allntwn Rd-Souderton Pk (C) | 1058 | HT2 | New Alignment | CON | 581 | 2021-10-21 | 2021-10-21 | 375000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000
DVRPC | 6 | Montgomery | 80052 | Fetters Mill Road over Pennypack Creek(C) | 7046 | 027 | Bridge Preservation - Federal | CON | BOF | 2024-09-12 | 2024-09-12 | 1991000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1991000
DVRPC | 6 | Montgomery | 81168 | Arch Street Greenway |  | ASG | Bicycle Pedestrian Highway | CON | SRTSF | 2027-01-14 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Montgomery | 81168 | Arch Street Greenway |  | ASG | Bicycle Pedestrian Highway | CON | TAP | 2027-01-14 |  | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Montgomery | 81226 | Montgomery County 3R Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 246000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246000
DVRPC | 6 | Montgomery | 81677 | Upper Dublin Sidewalk to School | 152 | SSP | Bicycle Pedestrian Highway | CON | SRTSF | 2026-11-05 |  | 0 | 0 | 1139179 | 0 | 0 | 0 | 0 | 0 | 0 | 1139179
DVRPC | 6 | Montgomery | 81725 | My School in Motion 2025-2027 |  | MSM | Bicycle Pedestrian Highway | CON | TAP |  | 2025-01-24 | 399700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399700
DVRPC | 6 | Montgomery | 81785 | Cross County Trail East - Section A |  | ESA | Bicycle and Pedestrian Facilities Transit | PE | CRP | 2029-08-23 |  | 208000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208000
DVRPC | 6 | Montgomery | 81785 | Cross County Trail East - Section A |  | ESA | Bicycle and Pedestrian Facilities Transit | PE | CRPU | 2029-08-23 |  | 0 | 552000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552000
DVRPC | 6 | Montgomery | 81785 | Cross County Trail East - Section A |  | ESA | Bicycle and Pedestrian Facilities Transit | PE | LOC | 2029-08-23 |  | 52000 | 138000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000
DVRPC | 6 | Montgomery | 81785 | Cross County Trail East - Section A |  | ESA | Bicycle and Pedestrian Facilities Transit | FD | CRP | 2029-08-23 |  | 0 | 156000 | 156000 | 0 | 0 | 0 | 0 | 0 | 0 | 312000
DVRPC | 6 | Montgomery | 81785 | Cross County Trail East - Section A |  | ESA | Bicycle and Pedestrian Facilities Transit | ROW | CRP | 2029-08-23 |  | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 480000
DVRPC | 6 | Montgomery | 81785 | Cross County Trail East - Section A |  | ESA | Bicycle and Pedestrian Facilities Transit | CON | CRP | 2029-08-23 |  | 0 | 0 | 0 | 1348000 | 358000 | 0 | 0 | 0 | 0 | 1706000
DVRPC | 6 | Montgomery | 81785 | Cross County Trail East - Section A |  | ESA | Bicycle and Pedestrian Facilities Transit | CON | CRPU | 2029-08-23 |  | 0 | 0 | 0 | 82000 | 1072000 | 0 | 0 | 0 | 0 | 1154000
DVRPC | 6 | Montgomery | 81892 | SR 73 and SR 2016 Improvements R10 | 73 | MT2 | Congestion Reduction | CON | 411 | 2026-02-10 | 2026-02-10 | 1463300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1463300
DVRPC | 6 | Montgomery | 81892 | SR 73 and SR 2016 Improvements R10 | 73 | MT2 | Congestion Reduction | CON | LOC | 2026-02-10 | 2026-02-10 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
DVRPC | 6 | Montgomery | 81893 | Marshall and Forest Intersection R10 | 3019 | MTF | MultiModal | PE | LOC |  |  | 0 | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000
DVRPC | 6 | Montgomery | 81893 | Marshall and Forest Intersection R10 | 3019 | MTF | MultiModal | CON | 411 |  |  | 0 | 547166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 547166
DVRPC | 6 | Montgomery | 81893 | Marshall and Forest Intersection R10 | 3019 | MTF | MultiModal | CON | LOC |  |  | 0 | 113151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113151
DVRPC | 6 | Montgomery | 81895 | St. Paul's Church Rd over Macoby Creek R10 | 7219 | MTF | Bridge Replacement | PE | LOC |  |  | 222193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222193
DVRPC | 6 | Montgomery | 81895 | St. Paul's Church Rd over Macoby Creek R10 | 7219 | MTF | Bridge Replacement | CON | 411 |  |  | 1977846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977846
DVRPC | 6 | Montgomery | 81895 | St. Paul's Church Rd over Macoby Creek R10 | 7219 | MTF | Bridge Replacement | CON | LOC |  |  | 371161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371161
DVRPC | 6 | Montgomery | 81915 | Districtwide MS4-SWM Improvements Group 2 | 76 | SWM | Stormwater Management | PE | PRTCT | 2026-11-05 |  | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000
DVRPC | 6 | Montgomery | 81915 | Districtwide MS4-SWM Improvements Group 2 | 76 | SWM | Stormwater Management | CON | PRTCT | 2026-11-05 |  | 0 | 0 | 1060000 | 0 | 0 | 0 | 0 | 0 | 0 | 1060000
DVRPC | 6 | Montgomery | 82024 | HSIP Project Development |  | SIP | Safety Improvement | STUDY | HSIP |  |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Montgomery | 82029 | Montgomery County EV Charging Program |  | MEV | Electric Vehicle Charging Infrastructure | PE | CRPU |  |  | 0 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
DVRPC | 6 | Montgomery | 82029 | Montgomery County EV Charging Program |  | MEV | Electric Vehicle Charging Infrastructure | FD | CRPU |  |  | 0 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000
DVRPC | 6 | Montgomery | 82029 | Montgomery County EV Charging Program |  | MEV | Electric Vehicle Charging Infrastructure | CON | CRPU |  |  | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
DVRPC | 6 | Montgomery | 82083 | Cross County Trl: WisshcknTrl - SEPTA's FrtWshtStn |  | LFW | Bicycle and Pedestrian Facilities Transit | CON | CRPU |  |  | 0 | 0 | 1904000 | 1809000 | 3904000 | 0 | 0 | 0 | 0 | 7617000
DVRPC | 6 | Montgomery | 82084 | Cross County Trail East - Section B |  | ESB | Bicycle Pedestrian Highway | PE | CRP | 2029-08-23 |  | 336000 | 252000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588000
DVRPC | 6 | Montgomery | 82084 | Cross County Trail East - Section B |  | ESB | Bicycle Pedestrian Highway | PE | CRPU | 2029-08-23 |  | 0 | 496000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496000
DVRPC | 6 | Montgomery | 82084 | Cross County Trail East - Section B |  | ESB | Bicycle Pedestrian Highway | PE | LOC | 2029-08-23 |  | 84000 | 187000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271000
DVRPC | 6 | Montgomery | 82084 | Cross County Trail East - Section B |  | ESB | Bicycle Pedestrian Highway | FD | CRP | 2029-08-23 |  | 0 | 0 | 512000 | 0 | 0 | 0 | 0 | 0 | 0 | 512000
DVRPC | 6 | Montgomery | 82084 | Cross County Trail East - Section B |  | ESB | Bicycle Pedestrian Highway | FD | LOC | 2029-08-23 |  | 0 | 0 | 128000 | 0 | 0 | 0 | 0 | 0 | 0 | 128000
DVRPC | 6 | Montgomery | 82084 | Cross County Trail East - Section B |  | ESB | Bicycle Pedestrian Highway | ROW | CRP | 2029-08-23 |  | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 220000
DVRPC | 6 | Montgomery | 82084 | Cross County Trail East - Section B |  | ESB | Bicycle Pedestrian Highway | ROW | CRPU | 2029-08-23 |  | 0 | 0 | 0 | 260000 | 0 | 0 | 0 | 0 | 0 | 260000
DVRPC | 6 | Montgomery | 82084 | Cross County Trail East - Section B |  | ESB | Bicycle Pedestrian Highway | ROW | LOC | 2029-08-23 |  | 0 | 0 | 55000 | 65000 | 0 | 0 | 0 | 0 | 0 | 120000
DVRPC | 6 | Montgomery | 82084 | Cross County Trail East - Section B |  | ESB | Bicycle Pedestrian Highway | CON | CRP | 2029-08-23 |  | 0 | 0 | 0 | 0 | 2310000 | 0 | 0 | 0 | 0 | 2310000
DVRPC | 6 | Montgomery | 82084 | Cross County Trail East - Section B |  | ESB | Bicycle Pedestrian Highway | CON | CRPU | 2029-08-23 |  | 0 | 0 | 0 | 659000 | 0 | 1391000 | 0 | 0 | 260000 | 2310000
DVRPC | 6 | Montgomery | 82084 | Cross County Trail East - Section B |  | ESB | Bicycle Pedestrian Highway | CON | LOC | 2029-08-23 |  | 0 | 0 | 0 | 166000 | 578000 | 347000 | 0 | 0 | 65000 | 1156000
DVRPC | 6 | Montgomery | 82087 | Syst. Improvements: Intersection Safety(Parent)(C) |  | SIP | Safety Improvement | PE | HVRU | 2025-10-23 | 2025-10-23 | 300000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Montgomery | 82087 | Syst. Improvements: Intersection Safety(Parent)(C) |  | SIP | Safety Improvement | CON | HVRU | 2025-10-23 | 2025-10-23 | 2504000 | 510800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3014800
DVRPC | 6 | Montgomery | 82088 | Systemic Improvements: Vulnerable Users |  | SIP | Safety Improvement | PE | HVRU |  |  | 300000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Montgomery | 82089 | Systemic Imp: Wrong Way Countermeasures(Child)(C) |  | SIP | Safety Improvement | PE | HSIP | 2025-10-23 | 2025-10-23 | 300000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Montgomery | 82089 | Systemic Imp: Wrong Way Countermeasures(Child)(C) |  | SIP | Safety Improvement | CON | HSIP | 2025-10-23 | 2025-10-23 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
DVRPC | 6 | Montgomery | 82091 | D6 ITS Network Arch Tech Refresh Ph1 - PA 309 Hubs |  | L31 | Intelligent Transportation System | CON | CRP |  |  | 324816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324816
DVRPC | 6 | Montgomery | 82124 | PA 100 & Hanover Street ITS Deployment | 100 | ITS | Intelligent Transportation System | PE | CRPU | 2029-10-25 |  | 0 | 530000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530000
DVRPC | 6 | Montgomery | 82124 | PA 100 & Hanover Street ITS Deployment | 100 | ITS | Intelligent Transportation System | CON | CRP | 2029-10-25 |  | 0 | 0 | 0 | 2900000 | 0 | 0 | 0 | 0 | 0 | 2900000
DVRPC | 6 | Montgomery | 83742 | Keim St o/ Schuylkll River(C) | 7046 | 190 | Bridge Replacement | UTL | STU | 2024-09-12 | 2024-09-12 | 1062000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062000
DVRPC | 6 | Montgomery | 83742 | Keim St o/ Schuylkll River(C) | 7046 | 190 | Bridge Replacement | UTL | 183 | 2024-09-12 | 2024-09-12 | 199000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199000
DVRPC | 6 | Montgomery | 83742 | Keim St o/ Schuylkll River(C) | 7046 | 190 | Bridge Replacement | UTL | LOC | 2024-09-12 | 2024-09-12 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66000
DVRPC | 6 | Montgomery | 83742 | Keim St o/ Schuylkll River(C) | 7046 | 190 | Bridge Replacement | CON | STP | 2024-09-12 | 2024-09-12 | 3279000 | 3005000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6284000
DVRPC | 6 | Montgomery | 92182 | Expressway Service Patrol - Suburban Corridors |  | TOW | Safety Improvement | CON | NHPP |  |  | 3800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800000
DVRPC | 6 | Montgomery | 92807 | Skippack Pk o/Skippack Cr(C) | 73 | MS2 | Bridge Replacement | FD | STU | 2024-09-12 | 2024-09-12 | 109302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109302
DVRPC | 6 | Montgomery | 92807 | Skippack Pk o/Skippack Cr(C) | 73 | MS2 | Bridge Replacement | FD | 581 | 2024-09-12 | 2024-09-12 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000
DVRPC | 6 | Montgomery | 92807 | Skippack Pk o/Skippack Cr(C) | 73 | MS2 | Bridge Replacement | CON | BRIP | 2024-09-12 | 2024-09-12 | 2302147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302147
DVRPC | 6 | Montgomery | 92839 | Ridge Pike ov Norfolk Southern(C ) |  | MG3 | Bridge Replacement | CON | STU | 2023-04-27 | 2023-04-27 | 1650000 | 953765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2603765
DVRPC | 6 | Montgomery | 92839 | Ridge Pike ov Norfolk Southern(C ) |  | MG3 | Bridge Replacement | CON | 183 | 2023-04-27 | 2023-04-27 | 234000 | 179000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413000
DVRPC | 6 | Montgomery | 92839 | Ridge Pike ov Norfolk Southern(C ) |  | MG3 | Bridge Replacement | CON | LOC | 2023-04-27 | 2023-04-27 | 78000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138000
DVRPC | 6 | Montgomery | 96069 | Bucks & MontCo Bridge Group(C) | 1042 | HBV | Bridge Replacement | FD | 185 | 2025-05-08 | 2025-05-08 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
DVRPC | 6 | Montgomery | 96069 | Bucks & MontCo Bridge Group(C) | 1042 | HBV | Bridge Replacement | CON | 185 | 2025-05-08 | 2025-05-08 | 0 | 1750000 | 1000000 | 606000 | 0 | 0 | 0 | 0 | 0 | 3356000
DVRPC | 6 | Montgomery | 98037 | Niantic Road over W Br Perkiomen Creek | 1035 | MB1 | Bridge Replacement | FD | 185 | 2026-08-27 |  | 179000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179000
DVRPC | 6 | Montgomery | 98037 | Niantic Road over W Br Perkiomen Creek | 1035 | MB1 | Bridge Replacement | ROW | 185 | 2026-08-27 |  | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111000
DVRPC | 6 | Montgomery | 98037 | Niantic Road over W Br Perkiomen Creek | 1035 | MB1 | Bridge Replacement | CON | 185 | 2026-08-27 |  | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
DVRPC | 6 | Montgomery | 102105 | Municipal Brdg Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1336000 | 1336000
DVRPC | 6 | Montgomery | 102105 | Municipal Brdg Line Item |  |  | Reserve Line Item | CON | 183 |  |  | 0 | 0 | 869800 | 3745687 | 4813000 | 0 | 0 | 0 | 4000000 | 13428487
DVRPC | 6 | Montgomery | 102105 | Municipal Brdg Line Item |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
DVRPC | 6 | Montgomery | 102105 | Municipal Brdg Line Item |  |  | Reserve Line Item | CON | LOC |  |  | 0 | 685347 | 217700 | 727562 | 3000000 | 0 | 0 | 0 | 0 | 4630609
DVRPC | 6 | Montgomery | 102273 | Ridge/Germantwn Intrs Re-Alignmnt(C) | 4031 | PH1 | Highway Reconstruction | UTL | CAQ | 2024-12-12 | 2024-12-12 | 615000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615000
DVRPC | 6 | Montgomery | 102273 | Ridge/Germantwn Intrs Re-Alignmnt(C) | 4031 | PH1 | Highway Reconstruction | CON | CAQ | 2024-12-12 | 2024-12-12 | 18503000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18503000
DVRPC | 6 | Montgomery | 102275 | Study Line Item |  |  | Reserve Line Item | PE | 581 |  |  | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Montgomery | 102665 | Signal Upgrade Line Item |  |  | Reserve Line Item | CON | CAQ |  |  | 0 | 889000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 889000
DVRPC | 6 | Montgomery | 103371 | Woodmont Road over Arrowmink Creek | 7046 | 010 | Bridge Replacement | FD | BRIP |  |  | 0 | 437000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437000
DVRPC | 6 | Montgomery | 103371 | Woodmont Road over Arrowmink Creek | 7046 | 010 | Bridge Replacement | ROW | BRIP |  |  | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
DVRPC | 6 | Montgomery | 103371 | Woodmont Road over Arrowmink Creek | 7046 | 010 | Bridge Replacement | UTL | BRIP |  |  | 0 | 124000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124000
DVRPC | 6 | Montgomery | 103371 | Woodmont Road over Arrowmink Creek | 7046 | 010 | Bridge Replacement | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 3107000 | 2427000 | 0 | 0 | 0 | 5534000
DVRPC | 6 | Montgomery | 103372 | Waverly Rd O/Tacony Cr(C) | 7046 | 275 | Bridge Replacement | CON | STP | 2025-09-25 | 2025-09-11 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000
DVRPC | 6 | Montgomery | 103372 | Waverly Rd O/Tacony Cr(C) | 7046 | 275 | Bridge Replacement | CON | BOF | 2025-09-25 | 2025-09-11 | 296956 | 1903044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000
DVRPC | 6 | Montgomery | 103440 | Penllyn Pike over Wissahickon Creek | 7046 | 289 | Bridge Replacement | PE | STU | 2027-12-30 |  | 103000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128000
DVRPC | 6 | Montgomery | 103440 | Penllyn Pike over Wissahickon Creek | 7046 | 289 | Bridge Replacement | FD | 185 | 2027-12-30 |  | 328000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328000
DVRPC | 6 | Montgomery | 103440 | Penllyn Pike over Wissahickon Creek | 7046 | 289 | Bridge Replacement | ROW | 185 | 2027-12-30 |  | 82000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82000
DVRPC | 6 | Montgomery | 103440 | Penllyn Pike over Wissahickon Creek | 7046 | 289 | Bridge Replacement | UTL | 185 | 2027-12-30 |  | 0 | 0 | 0 | 0 | 61000 | 0 | 0 | 0 | 0 | 61000
DVRPC | 6 | Montgomery | 103440 | Penllyn Pike over Wissahickon Creek | 7046 | 289 | Bridge Replacement | CON | 185 | 2027-12-30 |  | 0 | 0 | 0 | 0 | 5411000 | 0 | 0 | 0 | 0 | 5411000
DVRPC | 6 | Montgomery | 105291 | Circuit Line Item |  |  | Reserve Line Item | CON | CAQ |  |  | 0 | 4159000 | 0 | 841000 | 0 | 0 | 720000 | 0 | 11006000 | 16726000
DVRPC | 6 | Montgomery | 105291 | Circuit Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8988000 | 8988000
DVRPC | 6 | Montgomery | 105291 | Circuit Line Item |  |  | Reserve Line Item | CON | CRPU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1006000 | 5711000 | 37614000 | 44331000
DVRPC | 6 | Montgomery | 105803 | PA 63/PA 309 Connector Phase 3 | 1058 | HT3 | Highway Reconstruction | FD | STU | 2026-12-10 |  | 3016000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3016000
DVRPC | 6 | Montgomery | 105803 | PA 63/PA 309 Connector Phase 3 | 1058 | HT3 | Highway Reconstruction | FD | 581 | 2026-12-10 |  | 754000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 754000
DVRPC | 6 | Montgomery | 105803 | PA 63/PA 309 Connector Phase 3 | 1058 | HT3 | Highway Reconstruction | ROW | STU | 2026-12-10 |  | 3000000 | 2500000 | 4500000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 12000000
DVRPC | 6 | Montgomery | 105803 | PA 63/PA 309 Connector Phase 3 | 1058 | HT3 | Highway Reconstruction | ROW | 581 | 2026-12-10 |  | 750000 | 625000 | 1125000 | 500000 | 0 | 0 | 0 | 0 | 0 | 3000000
DVRPC | 6 | Montgomery | 105803 | PA 63/PA 309 Connector Phase 3 | 1058 | HT3 | Highway Reconstruction | UTL | STU | 2026-12-10 |  | 0 | 1390000 | 1730000 | 2730000 | 0 | 0 | 0 | 0 | 0 | 5850000
DVRPC | 6 | Montgomery | 105803 | PA 63/PA 309 Connector Phase 3 | 1058 | HT3 | Highway Reconstruction | UTL | 581 | 2026-12-10 |  | 0 | 348000 | 433000 | 683000 | 0 | 0 | 0 | 0 | 0 | 1464000
DVRPC | 6 | Montgomery | 105803 | PA 63/PA 309 Connector Phase 3 | 1058 | HT3 | Highway Reconstruction | CON | STP | 2026-12-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000
DVRPC | 6 | Montgomery | 105803 | PA 63/PA 309 Connector Phase 3 | 1058 | HT3 | Highway Reconstruction | CON | STU | 2026-12-10 |  | 0 | 0 | 1652000 | 2626000 | 4626000 | 4626000 | 3626000 | 6626000 | 21054000 | 44836000
DVRPC | 6 | Montgomery | 105803 | PA 63/PA 309 Connector Phase 3 | 1058 | HT3 | Highway Reconstruction | CON | 581 | 2026-12-10 |  | 0 | 0 | 413000 | 657000 | 1174000 | 1174000 | 907000 | 1657000 | 5412000 | 11394000
DVRPC | 6 | Montgomery | 106648 | Sink Holes Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Montgomery | 106649 | StrmwatrPrmits/EnvrnMit Design |  |  | Reserve Line Item | CON | 581 |  |  | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
DVRPC | 6 | Montgomery | 107175 | US 202 & PA 29 Sinkhole Remediation(C) | 202 | SNK | Highway Restoration | CON | PRTCT | 2024-07-25 | 2024-07-25 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
DVRPC | 6 | Montgomery | 109847 | ROW Divestment 6-0 |  |  | Study Phase of Project | PE | 581 |  |  | 1000000 | 640000 | 960000 | 0 | 0 | 0 | 0 | 0 | 0 | 2600000
DVRPC | 6 | Montgomery | 110127 | D6 Modeling Assistance |  | MOD | Planning/Research/Administration | PRA | STU |  |  | 18080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18080
DVRPC | 6 | Montgomery | 110127 | D6 Modeling Assistance |  | MOD | Planning/Research/Administration | PRA | 581 |  |  | 4520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4520
DVRPC | 6 | Montgomery | 110315 | Philmont/Tomlinson/Pine Rd Intersection | 2013 | PTP | Congestion Reduction | FD | 581 | 2027-09-16 |  | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
DVRPC | 6 | Montgomery | 110315 | Philmont/Tomlinson/Pine Rd Intersection | 2013 | PTP | Congestion Reduction | ROW | STU | 2027-09-16 |  | 0 | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800000
DVRPC | 6 | Montgomery | 110315 | Philmont/Tomlinson/Pine Rd Intersection | 2013 | PTP | Congestion Reduction | ROW | 581 | 2027-09-16 |  | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
DVRPC | 6 | Montgomery | 110315 | Philmont/Tomlinson/Pine Rd Intersection | 2013 | PTP | Congestion Reduction | UTL | 581 | 2027-09-16 |  | 0 | 1311000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1311000
DVRPC | 6 | Montgomery | 110315 | Philmont/Tomlinson/Pine Rd Intersection | 2013 | PTP | Congestion Reduction | CON | 581 | 2027-09-16 |  | 0 | 1755000 | 1755000 | 1752000 | 2755000 | 3758000 | 3755000 | 3755000 | 0 | 19285000
DVRPC | 6 | Montgomery | 110444 | Ridge Pike: School - Belvoir | 7046 | MG4 | Bridge Replacement | FD | STU | 2026-11-05 |  | 337000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337000
DVRPC | 6 | Montgomery | 110444 | Ridge Pike: School - Belvoir | 7046 | MG4 | Bridge Replacement | FD | 183 | 2026-11-05 |  | 659000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 659000
DVRPC | 6 | Montgomery | 110444 | Ridge Pike: School - Belvoir | 7046 | MG4 | Bridge Replacement | FD | LOC | 2026-11-05 |  | 174000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174000
DVRPC | 6 | Montgomery | 110444 | Ridge Pike: School - Belvoir | 7046 | MG4 | Bridge Replacement | ROW | STU | 2026-11-05 |  | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
DVRPC | 6 | Montgomery | 110444 | Ridge Pike: School - Belvoir | 7046 | MG4 | Bridge Replacement | ROW | 183 | 2026-11-05 |  | 820000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820000
DVRPC | 6 | Montgomery | 110444 | Ridge Pike: School - Belvoir | 7046 | MG4 | Bridge Replacement | ROW | LOC | 2026-11-05 |  | 205000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205000
DVRPC | 6 | Montgomery | 110444 | Ridge Pike: School - Belvoir | 7046 | MG4 | Bridge Replacement | UTL | 183 | 2026-11-05 |  | 637000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637000
DVRPC | 6 | Montgomery | 110444 | Ridge Pike: School - Belvoir | 7046 | MG4 | Bridge Replacement | CON | BRIP | 2026-11-05 |  | 0 | 3900147 | 9324853 | 0 | 0 | 0 | 0 | 0 | 0 | 13225000
DVRPC | 6 | Montgomery | 110444 | Ridge Pike: School - Belvoir | 7046 | MG4 | Bridge Replacement | CON | STU | 2026-11-05 |  | 0 | 4739000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4739000
DVRPC | 6 | Montgomery | 110444 | Ridge Pike: School - Belvoir | 7046 | MG4 | Bridge Replacement | CON | 183 | 2026-11-05 |  | 0 | 1620000 | 1748000 | 0 | 0 | 0 | 0 | 0 | 0 | 3368000
DVRPC | 6 | Montgomery | 110444 | Ridge Pike: School - Belvoir | 7046 | MG4 | Bridge Replacement | CON | LOC | 2026-11-05 |  | 0 | 540000 | 583000 | 0 | 0 | 0 | 0 | 0 | 0 | 1123000
DVRPC | 6 | Montgomery | 110444 | Ridge Pike: School - Belvoir | 7046 | MG4 | Bridge Replacement | CON | TPK | 2026-11-05 |  | 33677000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33677000
DVRPC | 6 | Montgomery | 110494 | RTMC General Contract |  | GRT | Intelligent Transportation System | CON | CAQ | 2019-09-12 | 2019-09-12 | 175370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175370
DVRPC | 6 | Montgomery | 110494 | RTMC General Contract |  | GRT | Intelligent Transportation System | CON | STU | 2019-09-12 | 2019-09-12 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
DVRPC | 6 | Montgomery | 110761 | Gilbertsville Rd over Br Ministers Creek | 4040 | MB3 | Bridge Replacement | FD | 185 | 2026-11-05 |  | 137000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137000
DVRPC | 6 | Montgomery | 110761 | Gilbertsville Rd over Br Ministers Creek | 4040 | MB3 | Bridge Replacement | ROW | 185 | 2026-11-05 |  | 82000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82000
DVRPC | 6 | Montgomery | 110761 | Gilbertsville Rd over Br Ministers Creek | 4040 | MB3 | Bridge Replacement | UTL | 185 | 2026-11-05 |  | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
DVRPC | 6 | Montgomery | 110761 | Gilbertsville Rd over Br Ministers Creek | 4040 | MB3 | Bridge Replacement | CON | 185 | 2026-11-05 |  | 0 | 146000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146000
DVRPC | 6 | Montgomery | 110761 | Gilbertsville Rd over Br Ministers Creek | 4040 | MB3 | Bridge Replacement | CON | 581 | 2026-11-05 |  | 0 | 585000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585000
DVRPC | 6 | Montgomery | 110762 | Perkiomenville Road over Scioto Creek | 1028 | MB2 | Bridge Replacement | FD | 185 | 2026-11-05 |  | 179000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179000
DVRPC | 6 | Montgomery | 110762 | Perkiomenville Road over Scioto Creek | 1028 | MB2 | Bridge Replacement | ROW | 185 | 2026-11-05 |  | 119000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119000
DVRPC | 6 | Montgomery | 110762 | Perkiomenville Road over Scioto Creek | 1028 | MB2 | Bridge Replacement | UTL | 185 | 2026-11-05 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
DVRPC | 6 | Montgomery | 110762 | Perkiomenville Road over Scioto Creek | 1028 | MB2 | Bridge Replacement | CON | STU | 2026-11-05 |  | 0 | 960000 | 960000 | 0 | 0 | 0 | 0 | 0 | 0 | 1920000
DVRPC | 6 | Montgomery | 110762 | Perkiomenville Road over Scioto Creek | 1028 | MB2 | Bridge Replacement | CON | 185 | 2026-11-05 |  | 0 | 240000 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 480000
DVRPC | 6 | Montgomery | 110779 | Parkside Cynwyd Trail Extension(C) |  | CTE | Bicycle Pedestrian Highway | CON | TAU | 2024-03-14 | 2024-03-14 | 411000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 411000
DVRPC | 6 | Montgomery | 110961 | Old Skippack Rd Roundabout (C) | 1017 | SIP | Safety Improvement | FD | HSIP | 2022-04-28 | 2022-04-28 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
DVRPC | 6 | Montgomery | 110961 | Old Skippack Rd Roundabout (C) | 1017 | SIP | Safety Improvement | CON | HSIP | 2022-04-28 | 2022-04-28 | 61000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61000
DVRPC | 6 | Montgomery | 110971 | Main Street Safety: Egypt to Forrest/Airy | 3009 | SIP | Safety Improvement | PE | CRPU | 2027-12-09 |  | 0 | 648000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 648000
DVRPC | 6 | Montgomery | 110971 | Main Street Safety: Egypt to Forrest/Airy | 3009 | SIP | Safety Improvement | PE | HSIP | 2027-12-09 |  | 102000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102000
DVRPC | 6 | Montgomery | 110971 | Main Street Safety: Egypt to Forrest/Airy | 3009 | SIP | Safety Improvement | ROW | HSIP | 2027-12-09 |  | 0 | 68198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68198
DVRPC | 6 | Montgomery | 110971 | Main Street Safety: Egypt to Forrest/Airy | 3009 | SIP | Safety Improvement | UTL | HSIP | 2027-12-09 |  | 0 | 34099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34099
DVRPC | 6 | Montgomery | 110971 | Main Street Safety: Egypt to Forrest/Airy | 3009 | SIP | Safety Improvement | CON | HSIP | 2027-12-09 |  | 0 | 0 | 0 | 4773832 | 0 | 0 | 0 | 0 | 0 | 4773832
DVRPC | 6 | Montgomery | 111495 | Main Street Ped Improvements | 29 | MSP | Bicycle Pedestrian Highway | CON | TAP | 2027-01-14 |  | 682000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682000
DVRPC | 6 | Montgomery | 112524 | Low Cost Safety Improvments 6-0 (C) |  | SIP | Safety Improvement | CON | HSIP | 2020-01-30 | 2020-01-30 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
DVRPC | 6 | Montgomery | 113257 | Outdoor Advertising Control |  | OAC | Outdoor Advertising Management | PRA | STU |  |  | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
DVRPC | 6 | Montgomery | 114116 | Skippack Pk Signal System(L)(C) | 73 | MWT | Congestion Reduction | CON | CAQ | 2022-12-08 | 2022-12-08 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145000
DVRPC | 6 | Montgomery | 114944 | Bethlehem Pike Safety Improvements(C) | 2018 | SIP | Safety Improvement | CON | HVRU | 2023-08-10 | 2023-08-10 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000
DVRPC | 6 | Montgomery | 114948 | Lancaster Ave & Remington Rd Int. Improvements | 30 | SIP | Safety Improvement | FD | HVRU | 2027-06-24 |  | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
DVRPC | 6 | Montgomery | 114948 | Lancaster Ave & Remington Rd Int. Improvements | 30 | SIP | Safety Improvement | FD | HVRU | 2027-06-24 |  | 0 | 460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460000
DVRPC | 6 | Montgomery | 114948 | Lancaster Ave & Remington Rd Int. Improvements | 30 | SIP | Safety Improvement | ROW | HVRU | 2027-06-24 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Montgomery | 114948 | Lancaster Ave & Remington Rd Int. Improvements | 30 | SIP | Safety Improvement | UTL | HVRU | 2027-06-24 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
DVRPC | 6 | Montgomery | 114948 | Lancaster Ave & Remington Rd Int. Improvements | 30 | SIP | Safety Improvement | UTL | HVRU | 2027-06-24 |  | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000
DVRPC | 6 | Montgomery | 114948 | Lancaster Ave & Remington Rd Int. Improvements | 30 | SIP | Safety Improvement | CON | HSIP | 2027-06-24 |  | 0 | 0 | 1202219 | 0 | 0 | 0 | 0 | 0 | 0 | 1202219
DVRPC | 6 | Montgomery | 115428 | Sumneytown Pike Intersection Safety Imp. | 63 | SIP | Safety Improvement | FD | HSIP | 2028-02-03 |  | 288328 | 361672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
DVRPC | 6 | Montgomery | 115428 | Sumneytown Pike Intersection Safety Imp. | 63 | SIP | Safety Improvement | ROW | HSIP | 2028-02-03 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Montgomery | 115428 | Sumneytown Pike Intersection Safety Imp. | 63 | SIP | Safety Improvement | UTL | HSIP | 2028-02-03 |  | 0 | 0 | 300000 | 419000 | 0 | 0 | 0 | 0 | 0 | 719000
DVRPC | 6 | Montgomery | 115428 | Sumneytown Pike Intersection Safety Imp. | 63 | SIP | Safety Improvement | CON | HSIP | 2028-02-03 |  | 0 | 0 | 4750000 | 0 | 0 | 0 | 0 | 0 | 0 | 4750000
DVRPC | 6 | Montgomery | 115429 | Belmont Ave & St. Asaphs Rd Intersection | 3045 | SIP | Safety Improvement | FD | HSIP | 2028-01-13 |  | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000
DVRPC | 6 | Montgomery | 115429 | Belmont Ave & St. Asaphs Rd Intersection | 3045 | SIP | Safety Improvement | ROW | HSIP | 2028-01-13 |  | 0 | 0 | 200000 | 227000 | 0 | 0 | 0 | 0 | 0 | 427000
DVRPC | 6 | Montgomery | 115429 | Belmont Ave & St. Asaphs Rd Intersection | 3045 | SIP | Safety Improvement | UTL | HSIP | 2028-01-13 |  | 0 | 0 | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 41000
DVRPC | 6 | Montgomery | 115429 | Belmont Ave & St. Asaphs Rd Intersection | 3045 | SIP | Safety Improvement | CON | HSIP | 2028-01-13 |  | 0 | 0 | 0 | 2119000 | 0 | 0 | 0 | 0 | 0 | 2119000
DVRPC | 6 | Montgomery | 115968 | Travel Monitoring |  |  | Planning/Research/Administration | PRA | STU |  |  | 225000 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370000
DVRPC | 6 | Montgomery | 115974 | D6 Modeling Assistance |  |  | Planning/Research/Administration | PRA | NHPP |  |  | 496000 | 368000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 864000
DVRPC | 6 | Montgomery | 115974 | D6 Modeling Assistance |  |  | Planning/Research/Administration | PRA | 581 |  |  | 124000 | 92000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000
DVRPC | 6 | Montgomery | 116843 | I-76 Overhead Bridges | 3110 | OHB | Bridge Replacement | FD | 185 | 2028-11-09 |  | 62000 | 2938000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
DVRPC | 6 | Montgomery | 116843 | I-76 Overhead Bridges | 3110 | OHB | Bridge Replacement | ROW | BOF | 2028-11-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000
DVRPC | 6 | Montgomery | 116843 | I-76 Overhead Bridges | 3110 | OHB | Bridge Replacement | UTL | BOF | 2028-11-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
DVRPC | 6 | Montgomery | 116843 | I-76 Overhead Bridges | 3110 | OHB | Bridge Replacement | CON | BOF | 2028-11-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000000 | 28000000
DVRPC | 6 | Montgomery | 117912 | PA SRHPP 2022-23 |  |  | Planning/Research/Administration | PRA | STU |  |  | 828000 | 798000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1626000
DVRPC | 6 | Montgomery | 117928 | Travel Options Program(TOP) 2022-23 |  |  | Planning/Research/Administration | PRA | CAQ |  |  | 0 | 1835000 | 0 | 1835000 | 0 | 0 | 0 | 0 | 0 | 3670000
DVRPC | 6 | Montgomery | 117929 | PA TDM 2022-23 |  |  | Planning/Research/Administration | PRA | CAQ |  |  | 0 | 800000 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
DVRPC | 6 | Montgomery | 117931 | Regional TOP Competitive Admin |  |  | Planning/Research/Administration | PRA | CAQ |  |  | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Montgomery | 117936 | Reg. Electric Vehicle Plan 2022-23 |  |  | Planning/Research/Administration | PRA | STU |  |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
DVRPC | 6 | Montgomery | 117961 | Main St. East-Ruth Rd. Sidewalk(C) | 63 | MRS | Bicycle Pedestrian Highway | CON | TAU | 2025-04-17 | 2025-04-17 | 985000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985000
DVRPC | 6 | Montgomery | 117963 | Old Allentown Rd o/ Br Towamencin Crk(C) | 1001 | DEM | Bridge Removal | FD | BRIP | 2025-12-11 | 2025-12-11 | 318000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318000
DVRPC | 6 | Montgomery | 117963 | Old Allentown Rd o/ Br Towamencin Crk(C) | 1001 | DEM | Bridge Removal | ROW | 185 | 2025-12-11 | 2025-12-11 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
DVRPC | 6 | Montgomery | 117963 | Old Allentown Rd o/ Br Towamencin Crk(C) | 1001 | DEM | Bridge Removal | UTL | 185 | 2025-12-11 | 2025-12-11 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Montgomery | 117963 | Old Allentown Rd o/ Br Towamencin Crk(C) | 1001 | DEM | Bridge Removal | CON | BRIP | 2025-12-11 | 2025-12-11 | 0 | 0 | 0 | 0 | 395000 | 0 | 0 | 0 | 0 | 395000
DVRPC | 6 | Montgomery | 117963 | Old Allentown Rd o/ Br Towamencin Crk(C) | 1001 | DEM | Bridge Removal | CON | STP | 2025-12-11 | 2025-12-11 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
DVRPC | 6 | Montgomery | 117965 | Liberty Bell Trail P3 |  | LBT | Bicycle Pedestrian Highway | CON | TAP | 2026-04-09 |  | 373000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373000
DVRPC | 6 | Montgomery | 117965 | Liberty Bell Trail P3 |  | LBT | Bicycle Pedestrian Highway | CON | TAU | 2026-04-09 |  | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
DVRPC | 6 | Montgomery | 117997 | BRIP Reserve Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 2004003 | 1477000 | 0 | 0 | 0 | 0 | 0 | 3481003
DVRPC | 6 | Montgomery | 118005 | Black Rock Rd o/ Trib Schuylkill Rvr | 113 | MTS | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 1160000
DVRPC | 6 | Montgomery | 118015 | CMAQ FLEX f/SEPTA Proj of Significance |  |  | Reserve Line Item | PE | CAQ |  |  | 20613000 | 23049000 | 30221000 | 30630000 | 33884000 | 31651000 | 30630000 | 30630000 | 94156000 | 325464000
DVRPC | 6 | Montgomery | 118031 | PA 29 & PA 113 | 29 | RHN | Congestion Reduction | FD | STP | 2028-10-05 |  | 764000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 764000
DVRPC | 6 | Montgomery | 118031 | PA 29 & PA 113 | 29 | RHN | Congestion Reduction | FD | 581 | 2028-10-05 |  | 191000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191000
DVRPC | 6 | Montgomery | 118031 | PA 29 & PA 113 | 29 | RHN | Congestion Reduction | ROW | STP | 2028-10-05 |  | 0 | 1311000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1311000
DVRPC | 6 | Montgomery | 118031 | PA 29 & PA 113 | 29 | RHN | Congestion Reduction | ROW | 581 | 2028-10-05 |  | 0 | 328000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328000
DVRPC | 6 | Montgomery | 118031 | PA 29 & PA 113 | 29 | RHN | Congestion Reduction | UTL | 581 | 2028-10-05 |  | 0 | 0 | 0 | 0 | 239000 | 0 | 0 | 0 | 0 | 239000
DVRPC | 6 | Montgomery | 118031 | PA 29 & PA 113 | 29 | RHN | Congestion Reduction | CON | 581 | 2028-10-05 |  | 0 | 0 | 0 | 0 | 1791000 | 1791000 | 0 | 0 | 0 | 3582000
DVRPC | 6 | Montgomery | 118032 | DeKalb St: Main St - Johnson Hwy | 202 | M2W | Highway Restoration | FD | STP | 2029-01-15 |  | 1273000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273000
DVRPC | 6 | Montgomery | 118032 | DeKalb St: Main St - Johnson Hwy | 202 | M2W | Highway Restoration | FD | 581 | 2029-01-15 |  | 318000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318000
DVRPC | 6 | Montgomery | 118032 | DeKalb St: Main St - Johnson Hwy | 202 | M2W | Highway Restoration | ROW | STP | 2029-01-15 |  | 0 | 219000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000
DVRPC | 6 | Montgomery | 118032 | DeKalb St: Main St - Johnson Hwy | 202 | M2W | Highway Restoration | ROW | 581 | 2029-01-15 |  | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
DVRPC | 6 | Montgomery | 118032 | DeKalb St: Main St - Johnson Hwy | 202 | M2W | Highway Restoration | UTL | STP | 2029-01-15 |  | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
DVRPC | 6 | Montgomery | 118032 | DeKalb St: Main St - Johnson Hwy | 202 | M2W | Highway Restoration | UTL | 581 | 2029-01-15 |  | 0 | 0 | 113000 | 0 | 0 | 0 | 0 | 0 | 0 | 113000
DVRPC | 6 | Montgomery | 118032 | DeKalb St: Main St - Johnson Hwy | 202 | M2W | Highway Restoration | CON | STP | 2029-01-15 |  | 0 | 0 | 0 | 1080000 | 1080000 | 1080000 | 1080000 | 0 | 0 | 4320000
DVRPC | 6 | Montgomery | 118032 | DeKalb St: Main St - Johnson Hwy | 202 | M2W | Highway Restoration | CON | STU | 2029-01-15 |  | 0 | 0 | 1080000 | 0 | 0 | 0 | 0 | 0 | 0 | 1080000
DVRPC | 6 | Montgomery | 118032 | DeKalb St: Main St - Johnson Hwy | 202 | M2W | Highway Restoration | CON | 581 | 2029-01-15 |  | 0 | 0 | 270000 | 270000 | 270000 | 270000 | 270000 | 0 | 0 | 1350000
DVRPC | 6 | Montgomery | 118033 | PA 309 Connector HT4 | 63 | HT4 | Congestion Reduction | FD | STP |  |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
DVRPC | 6 | Montgomery | 118033 | PA 309 Connector HT4 | 63 | HT4 | Congestion Reduction | FD | 581 |  |  | 87000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87000
DVRPC | 6 | Montgomery | 118033 | PA 309 Connector HT4 | 63 | HT4 | Congestion Reduction | ROW | STP |  |  | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000
DVRPC | 6 | Montgomery | 118033 | PA 309 Connector HT4 | 63 | HT4 | Congestion Reduction | ROW | 581 |  |  | 0 | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68000
DVRPC | 6 | Montgomery | 118033 | PA 309 Connector HT4 | 63 | HT4 | Congestion Reduction | UTL | STP |  |  | 0 | 0 | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 93000
DVRPC | 6 | Montgomery | 118033 | PA 309 Connector HT4 | 63 | HT4 | Congestion Reduction | UTL | 581 |  |  | 0 | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 23000
DVRPC | 6 | Montgomery | 118033 | PA 309 Connector HT4 | 63 | HT4 | Congestion Reduction | CON | STP |  |  | 0 | 0 | 0 | 860000 | 860000 | 860000 | 860000 | 0 | 0 | 3440000
DVRPC | 6 | Montgomery | 118033 | PA 309 Connector HT4 | 63 | HT4 | Congestion Reduction | CON | 581 |  |  | 0 | 0 | 0 | 215000 | 215000 | 215000 | 215000 | 0 | 0 | 860000
DVRPC | 6 | Montgomery | 118036 | HSIP Supportive Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
DVRPC | 6 | Montgomery | 118187 | Central Ave. Xing |  | 290 | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425000
DVRPC | 6 | Montgomery | 118350 | Center & West Street Pedestrian Improvements |  | CSP | Bicycle Pedestrian Highway | CON | TAP | 2026-04-23 |  | 770000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770000
DVRPC | 6 | Montgomery | 118356 | Liberty Bell Trail | 1004 | LBT | Bicycle Pedestrian Highway | CON | TAP | 2026-10-01 |  | 0 | 910000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910000
DVRPC | 6 | Montgomery | 119299 | Carbon Reduction Program Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1636000 | 1684000 | 3320000
DVRPC | 6 | Montgomery | 119299 | Carbon Reduction Program Line Item |  |  | Reserve Line Item | CON | CRPU |  |  | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 4246000 | 4288000
DVRPC | 6 | Montgomery | 119476 | I-76 Parallel Arterial P2(C) | 23 | 002 | Intelligent Transportation System | CON | CRP | 2024-06-13 | 2024-06-13 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
DVRPC | 6 | Montgomery | 119476 | I-76 Parallel Arterial P2(C) | 23 | 002 | Intelligent Transportation System | CON | 073 | 2024-06-13 | 2024-06-13 | 3500000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500000
DVRPC | 6 | Montgomery | 119481 | Cross County Trail: Germantown Pk - Joshua Rd |  | XCT | Bicycle and Pedestrian Facilities Transit | PE | SXF | 2027-11-18 |  | 1650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650000
DVRPC | 6 | Montgomery | 119481 | Cross County Trail: Germantown Pk - Joshua Rd |  | XCT | Bicycle and Pedestrian Facilities Transit | FD | SXF | 2027-11-18 |  | 0 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000
DVRPC | 6 | Montgomery | 119481 | Cross County Trail: Germantown Pk - Joshua Rd |  | XCT | Bicycle and Pedestrian Facilities Transit | CON | CAQ | 2027-11-18 |  | 0 | 0 | 1917000 | 5436000 | 8345000 | 4652000 | 0 | 0 | 0 | 20350000
DVRPC | 6 | Montgomery | 120911 | Dreshertown Road o/ Br. Sandy Run Ck | 2024 | DSR | Bridge Replacement | PE | 185 |  |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
DVRPC | 6 | Montgomery | 120911 | Dreshertown Road o/ Br. Sandy Run Ck | 2024 | DSR | Bridge Replacement | FD | STP |  |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
DVRPC | 6 | Montgomery | 120911 | Dreshertown Road o/ Br. Sandy Run Ck | 2024 | DSR | Bridge Replacement | ROW | STP |  |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
DVRPC | 6 | Montgomery | 120911 | Dreshertown Road o/ Br. Sandy Run Ck | 2024 | DSR | Bridge Replacement | UTL | STP |  |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Montgomery | 120911 | Dreshertown Road o/ Br. Sandy Run Ck | 2024 | DSR | Bridge Replacement | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 1400000 | 0 | 0 | 0 | 0 | 1400000
DVRPC | 6 | Montgomery | 120934 | Bucks and Montgomery Counties ADA Ramps | 73 | A11 | Americans with Disabilities Act (ADA) | PE | CRPU | 2026-12-03 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
DVRPC | 6 | Montgomery | 120934 | Bucks and Montgomery Counties ADA Ramps | 73 | A11 | Americans with Disabilities Act (ADA) | FD | CRPU | 2026-12-03 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
DVRPC | 6 | Montgomery | 120934 | Bucks and Montgomery Counties ADA Ramps | 73 | A11 | Americans with Disabilities Act (ADA) | CON | CRPU | 2026-12-03 |  | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 0 | 0 | 1800000
DVRPC | 6 | Montgomery | 120942 | Districtwide MS4 and Wetland Mit Repairs |  | MP1 | Stormwater Management | PE | 581 | 2026-11-05 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
DVRPC | 6 | Montgomery | 120942 | Districtwide MS4 and Wetland Mit Repairs |  | MP1 | Stormwater Management | FD | STP | 2026-11-05 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
DVRPC | 6 | Montgomery | 120942 | Districtwide MS4 and Wetland Mit Repairs |  | MP1 | Stormwater Management | CON | STP | 2026-11-05 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
DVRPC | 6 | Philadelphia | 12886 | ADA Ramps 2020 Phila Cnty (C) | 1 | AD8 | Americans with Disabilities Act (ADA) | CON | STU | 2020-08-06 | 2020-08-20 | 234800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234800
DVRPC | 6 | Philadelphia | 16827 | Eakins Oval Transformation RAISE(BUILD) 25 | 3007 | EAK | Highway Reconstruction | PE | RAISE | 2028-12-14 |  | 0 | 829082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829082
DVRPC | 6 | Philadelphia | 17215 | 70th, 71st, & 72nd Streets over Amtrak | 7301 | AMT | Bridge Restoration | PE | 183 | 2032-01-15 |  | 500000 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000
DVRPC | 6 | Philadelphia | 17215 | 70th, 71st, & 72nd Streets over Amtrak | 7301 | AMT | Bridge Restoration | FD | 183 | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 7379000 | 0 | 0 | 0 | 7379000
DVRPC | 6 | Philadelphia | 17215 | 70th, 71st, & 72nd Streets over Amtrak | 7301 | AMT | Bridge Restoration | UTL | 183 | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 3262000 | 3262000 | 3262000 | 3262000 | 13048000
DVRPC | 6 | Philadelphia | 17215 | 70th, 71st, & 72nd Streets over Amtrak | 7301 | AMT | Bridge Restoration | CON | BRIP | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 1655000 | 33401000 | 37056000
DVRPC | 6 | Philadelphia | 17511 | City Ave o/ SEPTA(C) | 1 | PCS | Bridge Restoration | CON | NHPP | 2024-11-07 | 2024-11-07 | 5876844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5876844
DVRPC | 6 | Philadelphia | 17511 | City Ave o/ SEPTA(C) | 1 | PCS | Bridge Restoration | CON | 185 | 2024-11-07 | 2024-11-07 | 1469211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1469211
DVRPC | 6 | Philadelphia | 17595 | Margie Street over Amtrak | 7301 | 178 | Bridge Replacement | PE | BOF |  |  | 0 | 954000 | 546000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
DVRPC | 6 | Philadelphia | 17595 | Margie Street over Amtrak | 7301 | 178 | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 0 | 0 | 1250000
DVRPC | 6 | Philadelphia | 17595 | Margie Street over Amtrak | 7301 | 178 | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 274000 | 2726000 | 0 | 3000000
DVRPC | 6 | Philadelphia | 17595 | Margie Street over Amtrak | 7301 | 178 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3403000 | 13847000 | 17250000
DVRPC | 6 | Philadelphia | 17678 | Spring Garden Street over Amtrak | 3014 | AMT | Bridge Restoration | FD | BRIP | 2033-01-27 |  | 0 | 0 | 0 | 0 | 5015000 | 0 | 0 | 0 | 0 | 5015000
DVRPC | 6 | Philadelphia | 17678 | Spring Garden Street over Amtrak | 3014 | AMT | Bridge Restoration | FD | 185 | 2033-01-27 |  | 0 | 0 | 0 | 0 | 1254000 | 0 | 0 | 0 | 0 | 1254000
DVRPC | 6 | Philadelphia | 17678 | Spring Garden Street over Amtrak | 3014 | AMT | Bridge Restoration | ROW | BRIP | 2033-01-27 |  | 0 | 0 | 0 | 0 | 19000 | 0 | 0 | 0 | 0 | 19000
DVRPC | 6 | Philadelphia | 17678 | Spring Garden Street over Amtrak | 3014 | AMT | Bridge Restoration | ROW | 185 | 2033-01-27 |  | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000
DVRPC | 6 | Philadelphia | 17678 | Spring Garden Street over Amtrak | 3014 | AMT | Bridge Restoration | UTL | BRIP | 2033-01-27 |  | 0 | 0 | 0 | 0 | 0 | 6979000 | 4705000 | 0 | 0 | 11684000
DVRPC | 6 | Philadelphia | 17678 | Spring Garden Street over Amtrak | 3014 | AMT | Bridge Restoration | CON | BRIP | 2033-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10472000 | 10472000 | 10472000 | 31416000
DVRPC | 6 | Philadelphia | 17678 | Spring Garden Street over Amtrak | 3014 | AMT | Bridge Restoration | CON | 185 | 2033-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2618000 | 2618000 | 2618000 | 7854000
DVRPC | 6 | Philadelphia | 17697 | Island Ave: Woodland Ave - Bartram Ave(C) | 3013 | TF2 | Highway Restoration | CON | CAQ | 2022-11-03 | 2022-11-03 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000
DVRPC | 6 | Philadelphia | 17829 | LncstrAv@Prksde&Girard(C) | 3017 | 000 | Congestion Reduction | CON | SXF | 2010-11-04 | 2010-12-09 | 401324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401324
DVRPC | 6 | Philadelphia | 17829 | LncstrAv@Prksde&Girard(C) | 3017 | 000 | Congestion Reduction | CON | LOC | 2010-11-04 | 2010-12-09 | 100331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100331
DVRPC | 6 | Philadelphia | 17918 | I-95: Cornwell Hgts Shuttle | 95 | SHU | Congestion Reduction | CON | STP |  |  | 529000 | 529000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058000
DVRPC | 6 | Philadelphia | 51095 | ITS Program Integrator |  | ITC | Intelligent Transportation System | PRA | STP |  |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
DVRPC | 6 | Philadelphia | 51095 | ITS Program Integrator |  | ITC | Intelligent Transportation System | PRA | 581 |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Philadelphia | 57927 | Regional Hwy Safety Initiativ |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 109981 | 897000 | 19058000 | 23862000 | 23862000 | 23862000 | 23862000 | 95448000 | 210960981
DVRPC | 6 | Philadelphia | 63406 | On Road Bike Retrofits |  | RET | Bicycle Pedestrian Highway | PE | CAQ |  |  | 40927 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540927
DVRPC | 6 | Philadelphia | 63406 | On Road Bike Retrofits |  | RET | Bicycle Pedestrian Highway | CON | 581 |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Philadelphia | 64984 | TAP/HTS/SR2S Line Item |  | LNE | Reserve Line Item | CON | TAU |  |  | 0 | 3369117 | 8762000 | 8762000 | 8762000 | 8762000 | 8762000 | 8762000 | 35048000 | 90989117
DVRPC | 6 | Philadelphia | 65109 | Transit Flex - SEPTA |  |  | Public Transit | PE | CAQ |  |  | 17083000 | 17083000 | 17083000 | 17083000 | 17083000 | 17083000 | 17083000 | 17083000 | 68332000 | 204996000
DVRPC | 6 | Philadelphia | 66460 | TAP Project Engr/Mgment |  | TEM | Reserve Line Item | PE | STU |  |  | 11093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11093
DVRPC | 6 | Philadelphia | 66460 | TAP Project Engr/Mgment |  | TEM | Reserve Line Item | PE | 581 |  |  | 2772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2772
DVRPC | 6 | Philadelphia | 66461 | CMAQ Proj Engr/Mgmt |  | CEM | Congestion Reduction | PE | CAQ |  |  | 12160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12160
DVRPC | 6 | Philadelphia | 66461 | CMAQ Proj Engr/Mgmt |  | CEM | Congestion Reduction | PE | 581 |  |  | 3040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3040
DVRPC | 6 | Philadelphia | 69828 | Market St over Schuylkill River, SEPTA & CSX(C) | 3010 | MSB | Bridge Restoration | UTL | 185 | 2024-12-05 | 2024-12-05 | 2814000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2814000
DVRPC | 6 | Philadelphia | 69828 | Market St over Schuylkill River, SEPTA & CSX(C) | 3010 | MSB | Bridge Restoration | CON | BRIP | 2024-12-05 | 2024-12-05 | 10749000 | 1940000 | 7967000 | 12409000 | 1600000 | 8635000 | 16170000 | 14170000 | 31653944 | 105293944
DVRPC | 6 | Philadelphia | 69828 | Market St over Schuylkill River, SEPTA & CSX(C) | 3010 | MSB | Bridge Restoration | CON | STU | 2024-12-05 | 2024-12-05 | 0 | 3153000 | 4263000 | 2344000 | 0 | 0 | 0 | 0 | 0 | 9760000
DVRPC | 6 | Philadelphia | 69828 | Market St over Schuylkill River, SEPTA & CSX(C) | 3010 | MSB | Bridge Restoration | CON | 185 | 2024-12-05 | 2024-12-05 | 1041000 | 1273000 | 3058000 | 3688000 | 400000 | 2159000 | 4043000 | 3543000 | 7913486 | 27118486
DVRPC | 6 | Philadelphia | 69909 | Willits Road over Wooden Bridge Run | 1011 | PWB | Bridge Restoration | PE | 185 | 2028-01-27 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
DVRPC | 6 | Philadelphia | 69909 | Willits Road over Wooden Bridge Run | 1011 | PWB | Bridge Restoration | FD | 185 | 2028-01-27 |  | 1061000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1061000
DVRPC | 6 | Philadelphia | 69909 | Willits Road over Wooden Bridge Run | 1011 | PWB | Bridge Restoration | ROW | 185 | 2028-01-27 |  | 338000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338000
DVRPC | 6 | Philadelphia | 69909 | Willits Road over Wooden Bridge Run | 1011 | PWB | Bridge Restoration | UTL | 185 | 2028-01-27 |  | 0 | 580000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580000
DVRPC | 6 | Philadelphia | 69909 | Willits Road over Wooden Bridge Run | 1011 | PWB | Bridge Restoration | CON | 185 | 2028-01-27 |  | 0 | 1631000 | 1000000 | 2517000 | 1716000 | 1716000 | 0 | 0 | 0 | 8580000
DVRPC | 6 | Philadelphia | 70230 | Bells Mill & Valley Green Roads o/ Wissahickon Ck. | 7301 | WIS | Bridge Restoration | PE | PRTDG | 2026-10-01 |  | 704761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704761
DVRPC | 6 | Philadelphia | 70230 | Bells Mill & Valley Green Roads o/ Wissahickon Ck. | 7301 | WIS | Bridge Restoration | PE | LOC | 2026-10-01 |  | 1495239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495239
DVRPC | 6 | Philadelphia | 70230 | Bells Mill & Valley Green Roads o/ Wissahickon Ck. | 7301 | WIS | Bridge Restoration | FD | PRTDG | 2026-10-01 |  | 560606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560606
DVRPC | 6 | Philadelphia | 70230 | Bells Mill & Valley Green Roads o/ Wissahickon Ck. | 7301 | WIS | Bridge Restoration | FD | LOC | 2026-10-01 |  | 1289394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1289394
DVRPC | 6 | Philadelphia | 70230 | Bells Mill & Valley Green Roads o/ Wissahickon Ck. | 7301 | WIS | Bridge Restoration | ROW | PRTDG | 2026-10-01 |  | 160173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160173
DVRPC | 6 | Philadelphia | 70230 | Bells Mill & Valley Green Roads o/ Wissahickon Ck. | 7301 | WIS | Bridge Restoration | ROW | LOC | 2026-10-01 |  | 339827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339827
DVRPC | 6 | Philadelphia | 70230 | Bells Mill & Valley Green Roads o/ Wissahickon Ck. | 7301 | WIS | Bridge Restoration | CON | PRTDG | 2026-10-01 |  | 0 | 12819460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12819460
DVRPC | 6 | Philadelphia | 70230 | Bells Mill & Valley Green Roads o/ Wissahickon Ck. | 7301 | WIS | Bridge Restoration | CON | LOC | 2026-10-01 |  | 0 | 536540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536540
DVRPC | 6 | Philadelphia | 70231 | Swanson St: Columbus Blvd to Oregon Ave |  |  | Highway Reconstruction | CON | STP | 2027-07-15 |  | 0 | 2353000 | 4481000 | 56000 | 1945000 | 0 | 0 | 0 | 0 | 8835000
DVRPC | 6 | Philadelphia | 70231 | Swanson St: Columbus Blvd to Oregon Ave |  |  | Highway Reconstruction | CON | STU | 2027-07-15 |  | 0 | 0 | 0 | 1945000 | 0 | 5000000 | 0 | 0 | 0 | 6945000
DVRPC | 6 | Philadelphia | 70231 | Swanson St: Columbus Blvd to Oregon Ave |  |  | Highway Reconstruction | CON | LOC | 2027-07-15 |  | 0 | 588000 | 1120000 | 500000 | 486000 | 1250000 | 0 | 0 | 0 | 3944000
DVRPC | 6 | Philadelphia | 72597 | Ben Franklin Bridge Preservation | 7301 | BFW | Bridge Preservation - Federal | FD | STU | 2026-07-16 |  | 530000 | 530000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1060000
DVRPC | 6 | Philadelphia | 72597 | Ben Franklin Bridge Preservation | 7301 | BFW | Bridge Preservation - Federal | CON | NHPP | 2026-07-16 |  | 0 | 15227000 | 2233000 | 2232000 | 0 | 0 | 0 | 0 | 0 | 19692000
DVRPC | 6 | Philadelphia | 72597 | Ben Franklin Bridge Preservation | 7301 | BFW | Bridge Preservation - Federal | CON | STU | 2026-07-16 |  | 0 | 1093000 | 1000000 | 1093000 | 0 | 0 | 0 | 0 | 0 | 3186000
DVRPC | 6 | Philadelphia | 72597 | Ben Franklin Bridge Preservation | 7301 | BFW | Bridge Preservation - Federal | CON | LOC | 2026-07-16 |  | 0 | 42122000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42122000
DVRPC | 6 | Philadelphia | 72738 | Transportation Systems Mgmt & Operations(TSMO) |  | LEG | Intelligent Transportation System | PRA | STU |  |  | 23519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23519
DVRPC | 6 | Philadelphia | 72738 | Transportation Systems Mgmt & Operations(TSMO) |  | LEG | Intelligent Transportation System | PRA | 581 |  |  | 5880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5880
DVRPC | 6 | Philadelphia | 75804 | 34th St o/ Schuylkill Rvr Park Ext(C) | 3003 | UAR | Bridge Replacement | CON | 185 | 2021-05-06 | 2021-05-13 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000
DVRPC | 6 | Philadelphia | 77466 | Mid-East Girard Ave (C) | 2008 | HTS | Home Town Streets | CON | TAU | 2010-06-10 | 2010-06-10 | 399341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399341
DVRPC | 6 | Philadelphia | 78757 | JFK Blvd @ 32nd St. over SEPTA | 3028 | SWB | Bridge Restoration | FD | NHPP | 2027-10-21 |  | 747000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747000
DVRPC | 6 | Philadelphia | 78757 | JFK Blvd @ 32nd St. over SEPTA | 3028 | SWB | Bridge Restoration | UTL | 185 | 2027-10-21 |  | 1250000 | 1250000 | 1250000 | 1250000 | 0 | 0 | 0 | 0 | 0 | 5000000
DVRPC | 6 | Philadelphia | 78757 | JFK Blvd @ 32nd St. over SEPTA | 3028 | SWB | Bridge Restoration | CON | BRIP | 2027-10-21 |  | 0 | 0 | 2188000 | 2942000 | 6000000 | 0 | 0 | 0 | 0 | 11130000
DVRPC | 6 | Philadelphia | 78757 | JFK Blvd @ 32nd St. over SEPTA | 3028 | SWB | Bridge Restoration | CON | NHPP | 2027-10-21 |  | 0 | 5565000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5565000
DVRPC | 6 | Philadelphia | 78757 | JFK Blvd @ 32nd St. over SEPTA | 3028 | SWB | Bridge Restoration | CON | 185 | 2027-10-21 |  | 0 | 1391000 | 547000 | 736000 | 1500000 | 0 | 0 | 0 | 0 | 4174000
DVRPC | 6 | Philadelphia | 79832 | N Delaware River Greenway Trail Sec3 |  | SC3 | Bicycle Pedestrian Highway | CON | STU | 2027-11-04 |  | 0 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000
DVRPC | 6 | Philadelphia | 79832 | N Delaware River Greenway Trail Sec3 |  | SC3 | Bicycle Pedestrian Highway | CON | SXF | 2027-11-04 |  | 0 | 2669000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2669000
DVRPC | 6 | Philadelphia | 80104 | Henry Ave Congested Corr1 (C) | 4001 | SIP | Safety Improvement | CON | HVRU | 2020-11-05 | 2020-11-05 | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49000
DVRPC | 6 | Philadelphia | 81219 | 25th St: Washington Ave to Passyunk Ave |  | PWP | Highway Restoration | PE | 581 |  |  | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
DVRPC | 6 | Philadelphia | 81219 | 25th St: Washington Ave to Passyunk Ave |  | PWP | Highway Restoration | FD | STP |  |  | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
DVRPC | 6 | Philadelphia | 81219 | 25th St: Washington Ave to Passyunk Ave |  | PWP | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500000 | 16500000
DVRPC | 6 | Philadelphia | 81223 | W Chestnut St Pedestrian Islands - Phase 2(C) | 3 | CP2 | Bicycle and Pedestrian Facilities Transit | CON | TAU | 2026-02-26 | 2026-02-26 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
DVRPC | 6 | Philadelphia | 81227 | PA Air Quality Action Supp Services 2024-25 |  |  | Air Quality | PRA | CAQ |  |  | 200000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
DVRPC | 6 | Philadelphia | 81227 | PA Air Quality Action Supp Services 2024-25 |  |  | Air Quality | PRA | LOC |  |  | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
DVRPC | 6 | Philadelphia | 81230 | Better Bus Stops - S 7th & 8th Streets |  | BBS | Transportation Enhancement | CON | TAP | 2027-01-14 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Philadelphia | 81230 | Better Bus Stops - S 7th & 8th Streets |  | BBS | Transportation Enhancement | CON | TAU | 2027-01-14 |  | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Philadelphia | 81232 | Transportation Operations 2024-25 |  |  | Air Quality | PRA | CAQ |  |  | 208000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208000
DVRPC | 6 | Philadelphia | 81232 | Transportation Operations 2024-25 |  |  | Air Quality | PRA | STU |  |  | 208000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208000
DVRPC | 6 | Philadelphia | 81232 | Transportation Operations 2024-25 |  |  | Air Quality | PRA | 581 |  |  | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000
DVRPC | 6 | Philadelphia | 81237 | 2025 On-Board & Household Travel Surveys |  |  | Planning/Research/Administration | PRA | STU |  |  | 1095000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1095000
DVRPC | 6 | Philadelphia | 81292 | Frankford Aveue over Frankford Creek(C) | 2007 | FAR | Bridge Restoration | FD | 185 | 2025-05-08 | 2025-05-08 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
DVRPC | 6 | Philadelphia | 81292 | Frankford Aveue over Frankford Creek(C) | 2007 | FAR | Bridge Restoration | CON | BRIP | 2025-05-08 | 2025-05-08 | 2158000 | 2915000 | 750000 | 1500000 | 750000 | 0 | 0 | 0 | 0 | 8073000
DVRPC | 6 | Philadelphia | 81305 | Belmont Ave Trail Reconstruction | 3005 | BTR | Bicycle Pedestrian Highway | CON | TAP | 2027-01-14 |  | 0 | 0 | 1255500 | 0 | 0 | 0 | 0 | 0 | 0 | 1255500
DVRPC | 6 | Philadelphia | 81307 | Cobbs Creek Trail Segment B2 |  | CB2 | Bicycle Pedestrian Highway | CON | TAP | 2028-01-27 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
DVRPC | 6 | Philadelphia | 81308 | Logan Elementary School Zone |  | LES | Safety Improvement | CON | SRTSF | 2027-01-14 |  | 0 | 0 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000
DVRPC | 6 | Philadelphia | 81309 | Frankford Creek Greenway - Phase 3 | 1004 | FC3 | Bicycle Pedestrian Highway | CON | TAP | 2027-01-14 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
DVRPC | 6 | Philadelphia | 81726 | Safe Routes Philly-Special Education Modules |  |  | Bicycle Pedestrian Highway | CON | SRTSF |  |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
DVRPC | 6 | Philadelphia | 81729 | Navy Yard Lift Bridge Rehabilitation | 7301 | NYL | Bridge Restoration | PE | SXF | 2028-08-10 |  | 1666279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1666279
DVRPC | 6 | Philadelphia | 81729 | Navy Yard Lift Bridge Rehabilitation | 7301 | NYL | Bridge Restoration | PE | LOC | 2028-08-10 |  | 334000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334000
DVRPC | 6 | Philadelphia | 81729 | Navy Yard Lift Bridge Rehabilitation | 7301 | NYL | Bridge Restoration | CON | LOC | 2028-08-10 |  | 0 | 0 | 17735000 | 0 | 0 | 0 | 0 | 0 | 0 | 17735000
DVRPC | 6 | Philadelphia | 81884 | Historic Philadelphia Streets R10 |  | MT1 | Highway Restoration | CON | 411 |  | 2025-07-29 | 1436320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1436320
DVRPC | 6 | Philadelphia | 81884 | Historic Philadelphia Streets R10 |  | MT1 | Highway Restoration | CON | LOC |  | 2025-07-29 | 451680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451680
DVRPC | 6 | Philadelphia | 81930 | Phila Vision Zero Capital Plan Implement SS4A FY22 | 611 | S4A | Safety Improvement | PRA | SS4A | 2027-03-11 |  | 560000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560000
DVRPC | 6 | Philadelphia | 81930 | Phila Vision Zero Capital Plan Implement SS4A FY22 | 611 | S4A | Safety Improvement | PRA | LOC | 2027-03-11 |  | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
DVRPC | 6 | Philadelphia | 81930 | Phila Vision Zero Capital Plan Implement SS4A FY22 | 611 | S4A | Safety Improvement | PE | SS4A | 2027-03-11 |  | 1931200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1931200
DVRPC | 6 | Philadelphia | 81930 | Phila Vision Zero Capital Plan Implement SS4A FY22 | 611 | S4A | Safety Improvement | PE | LOC | 2027-03-11 |  | 482800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482800
DVRPC | 6 | Philadelphia | 81930 | Phila Vision Zero Capital Plan Implement SS4A FY22 | 611 | S4A | Safety Improvement | FD | SS4A | 2027-03-11 |  | 4117600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4117600
DVRPC | 6 | Philadelphia | 81930 | Phila Vision Zero Capital Plan Implement SS4A FY22 | 611 | S4A | Safety Improvement | FD | LOC | 2027-03-11 |  | 1029400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1029400
DVRPC | 6 | Philadelphia | 81930 | Phila Vision Zero Capital Plan Implement SS4A FY22 | 611 | S4A | Safety Improvement | CON | SS4A | 2027-03-11 |  | 0 | 23391200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23391200
DVRPC | 6 | Philadelphia | 81930 | Phila Vision Zero Capital Plan Implement SS4A FY22 | 611 | S4A | Safety Improvement | CON | LOC | 2027-03-11 |  | 0 | 5847800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5847800
DVRPC | 6 | Philadelphia | 81936 | Complete and Safe Streets Philadelphian SS4A FY 23 | 611 | S4A | Safety Improvement | PRA | SS4A |  |  | 294504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294504
DVRPC | 6 | Philadelphia | 81936 | Complete and Safe Streets Philadelphian SS4A FY 23 | 611 | S4A | Safety Improvement | PRA | LOC |  |  | 73626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73626
DVRPC | 6 | Philadelphia | 81936 | Complete and Safe Streets Philadelphian SS4A FY 23 | 611 | S4A | Safety Improvement | PE | SS4A |  |  | 256000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256000
DVRPC | 6 | Philadelphia | 81936 | Complete and Safe Streets Philadelphian SS4A FY 23 | 611 | S4A | Safety Improvement | PE | LOC |  |  | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64000
DVRPC | 6 | Philadelphia | 81936 | Complete and Safe Streets Philadelphian SS4A FY 23 | 611 | S4A | Safety Improvement | FD | SS4A |  |  | 384000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384000
DVRPC | 6 | Philadelphia | 81936 | Complete and Safe Streets Philadelphian SS4A FY 23 | 611 | S4A | Safety Improvement | FD | LOC |  |  | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96000
DVRPC | 6 | Philadelphia | 81936 | Complete and Safe Streets Philadelphian SS4A FY 23 | 611 | S4A | Safety Improvement | CON | SS4A |  |  | 0 | 15486400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15486400
DVRPC | 6 | Philadelphia | 81936 | Complete and Safe Streets Philadelphian SS4A FY 23 | 611 | S4A | Safety Improvement | CON | LOC |  |  | 0 | 3871600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3871600
DVRPC | 6 | Philadelphia | 81939 | Philadelphia CFI Community Project | 9153 | CFI | Electric Vehicle Charging Infrastructure | PE | CFI |  |  | 3160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3160000
DVRPC | 6 | Philadelphia | 81939 | Philadelphia CFI Community Project | 9153 | CFI | Electric Vehicle Charging Infrastructure | PE | LOC |  |  | 790000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 790000
DVRPC | 6 | Philadelphia | 81939 | Philadelphia CFI Community Project | 9153 | CFI | Electric Vehicle Charging Infrastructure | CON | CFI |  |  | 0 | 3600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600000
DVRPC | 6 | Philadelphia | 81939 | Philadelphia CFI Community Project | 9153 | CFI | Electric Vehicle Charging Infrastructure | CON | LOC |  |  | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
DVRPC | 6 | Philadelphia | 81942 | Philadelphia CFI Corridor Project | 95 | CFI | Electric Vehicle Charging Infrastructure | PE | CFI |  |  | 278252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278252
DVRPC | 6 | Philadelphia | 81942 | Philadelphia CFI Corridor Project | 95 | CFI | Electric Vehicle Charging Infrastructure | PE | LOC |  |  | 69563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69563
DVRPC | 6 | Philadelphia | 81942 | Philadelphia CFI Corridor Project | 95 | CFI | Electric Vehicle Charging Infrastructure | CON | CFI |  |  | 0 | 1946548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1946548
DVRPC | 6 | Philadelphia | 81942 | Philadelphia CFI Corridor Project | 95 | CFI | Electric Vehicle Charging Infrastructure | CON | LOC |  |  | 0 | 486637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486637
DVRPC | 6 | Philadelphia | 82005 | Honor Sq. @ 5 Points Streetscape & Traffic Impr. | 73 | HSS | Safety Improvement | PE | LOC | 2026-12-10 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Philadelphia | 82005 | Honor Sq. @ 5 Points Streetscape & Traffic Impr. | 73 | HSS | Safety Improvement | CON | SXF | 2026-12-10 |  | 1616279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1616279
DVRPC | 6 | Philadelphia | 82005 | Honor Sq. @ 5 Points Streetscape & Traffic Impr. | 73 | HSS | Safety Improvement | CON | LOC | 2026-12-10 |  | 1023721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1023721
DVRPC | 6 | Philadelphia | 82007 | Westpark Redevelopment RAISE FY24 |  | WPR | Bicycle Pedestrian Highway | FD | RAISE |  |  | 1824158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1824158
DVRPC | 6 | Philadelphia | 82007 | Westpark Redevelopment RAISE FY24 |  | WPR | Bicycle Pedestrian Highway | FD | LOC |  |  | 911000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911000
DVRPC | 6 | Philadelphia | 82007 | Westpark Redevelopment RAISE FY24 |  | WPR | Bicycle Pedestrian Highway | CON | RAISE |  |  | 19571397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19571397
DVRPC | 6 | Philadelphia | 82007 | Westpark Redevelopment RAISE FY24 |  | WPR | Bicycle Pedestrian Highway | CON | OTH-S |  |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
DVRPC | 6 | Philadelphia | 82007 | Westpark Redevelopment RAISE FY24 |  | WPR | Bicycle Pedestrian Highway | CON | LOC |  |  | 4221000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4221000
DVRPC | 6 | Philadelphia | 82012 | Philadelphia Community EV Charging Stations |  |  | Electric Vehicle Charging Infrastructure | CON | CRP |  |  | 2029000 | 1971000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
DVRPC | 6 | Philadelphia | 82013 | Transportation Improvement Program FY26/27 UPWP |  | TIP | Planning/Research/Administration | PRA | STU |  |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
DVRPC | 6 | Philadelphia | 82065 | Transportation Resilience Improvement Program |  | RSL | Study Phase of Project | STUDY | PRTCT |  |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Philadelphia | 82199 | Cottman Ave: Castor Ave to US 1 | 73 | 000 | Highway Restoration | CON | NHPP | 2026-07-16 |  | 0 | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000
DVRPC | 6 | Philadelphia | 82199 | Cottman Ave: Castor Ave to US 1 | 73 | 000 | Highway Restoration | CON | TAU | 2026-07-16 |  | 4119559 | 80441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200000
DVRPC | 6 | Philadelphia | 82199 | Cottman Ave: Castor Ave to US 1 | 73 | 000 | Highway Restoration | CON | LOC | 2026-07-16 |  | 3950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3950000
DVRPC | 6 | Philadelphia | 82216 | N H P P Reserve Item |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 10011850 | 3050000 | 2194000 | 1344000 | 0 | 1456000 | 0 | 2838149 | 20893999
DVRPC | 6 | Philadelphia | 82216 | N H P P Reserve Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 2755000 | 0 | 0 | 86000 | 0 | 0 | 0 | 766200 | 3607200
DVRPC | 6 | Philadelphia | 83736 | Rsvlt Blvd o/Wayne Junc (C) | 1 | WAV | Bridge Restoration | CON | STP | 2018-10-18 | 2018-10-18 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
DVRPC | 6 | Philadelphia | 83736 | Rsvlt Blvd o/Wayne Junc (C) | 1 | WAV | Bridge Restoration | CON | 581 | 2018-10-18 | 2018-10-18 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Philadelphia | 83743 | ADA Ramps Line Item |  | ADA | Reserve Line Item | CON | STP |  |  | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
DVRPC | 6 | Philadelphia | 83743 | ADA Ramps Line Item |  | ADA | Reserve Line Item | CON | 581 |  |  | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Philadelphia | 84457 | Signal re-timing Program |  |  | Safety Improvement | PRA | CAQ |  |  | 350000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
DVRPC | 6 | Philadelphia | 87784 | Aramingo Ave: Church St to Bridge St | 2009 | BS3 | Highway Reconstruction | ROW | NHPP | 2029-01-25 |  | 1273000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273000
DVRPC | 6 | Philadelphia | 87784 | Aramingo Ave: Church St to Bridge St | 2009 | BS3 | Highway Reconstruction | UTL | NHPP | 2029-01-25 |  | 0 | 0 | 0 | 6260000 | 0 | 0 | 0 | 0 | 0 | 6260000
DVRPC | 6 | Philadelphia | 87784 | Aramingo Ave: Church St to Bridge St | 2009 | BS3 | Highway Reconstruction | UTL | 581 | 2029-01-25 |  | 0 | 0 | 0 | 696000 | 0 | 0 | 0 | 0 | 0 | 696000
DVRPC | 6 | Philadelphia | 87784 | Aramingo Ave: Church St to Bridge St | 2009 | BS3 | Highway Reconstruction | CON | NHPP | 2029-01-25 |  | 0 | 0 | 3000000 | 3605000 | 2477000 | 5477000 | 3477000 | 5477000 | 26908000 | 50421000
DVRPC | 6 | Philadelphia | 87784 | Aramingo Ave: Church St to Bridge St | 2009 | BS3 | Highway Reconstruction | CON | 185 | 2029-01-25 |  | 0 | 0 | 750000 | 0 | 0 | 0 | 869000 | 0 | 0 | 1619000
DVRPC | 6 | Philadelphia | 87784 | Aramingo Ave: Church St to Bridge St | 2009 | BS3 | Highway Reconstruction | CON | 581 | 2029-01-25 |  | 0 | 0 | 0 | 901000 | 619000 | 1369000 | 0 | 1369000 | 6726000 | 10984000
DVRPC | 6 | Philadelphia | 88085 | Byberry Road over CSX(C) | 7301 | GAV | Bridge Replacement | FD | STU | 2025-12-11 | 2025-12-11 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
DVRPC | 6 | Philadelphia | 88085 | Byberry Road over CSX(C) | 7301 | GAV | Bridge Replacement | FD | 185 | 2025-12-11 | 2025-12-11 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
DVRPC | 6 | Philadelphia | 88085 | Byberry Road over CSX(C) | 7301 | GAV | Bridge Replacement | CON | BRIP | 2025-12-11 | 2025-12-11 | 0 | 11087000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11087000
DVRPC | 6 | Philadelphia | 91490 | Expressway Service Patrol - Philadelphia |  | TOW | Safety Improvement | CON | NHPP |  |  | 1350000 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700000
DVRPC | 6 | Philadelphia | 92554 | Ridge Avenue over Amtrak | 3009 | PAR | Bridge Replacement | FD | STP | 2028-10-05 |  | 1358000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1358000
DVRPC | 6 | Philadelphia | 92554 | Ridge Avenue over Amtrak | 3009 | PAR | Bridge Replacement | FD | 185 | 2028-10-05 |  | 339000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339000
DVRPC | 6 | Philadelphia | 92554 | Ridge Avenue over Amtrak | 3009 | PAR | Bridge Replacement | ROW | STP | 2028-10-05 |  | 694000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 694000
DVRPC | 6 | Philadelphia | 92554 | Ridge Avenue over Amtrak | 3009 | PAR | Bridge Replacement | ROW | 185 | 2028-10-05 |  | 174000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174000
DVRPC | 6 | Philadelphia | 92554 | Ridge Avenue over Amtrak | 3009 | PAR | Bridge Replacement | UTL | BRIP | 2028-10-05 |  | 0 | 0 | 1291000 | 0 | 0 | 0 | 0 | 0 | 0 | 1291000
DVRPC | 6 | Philadelphia | 92554 | Ridge Avenue over Amtrak | 3009 | PAR | Bridge Replacement | UTL | 185 | 2028-10-05 |  | 0 | 0 | 323000 | 0 | 0 | 0 | 0 | 0 | 0 | 323000
DVRPC | 6 | Philadelphia | 92554 | Ridge Avenue over Amtrak | 3009 | PAR | Bridge Replacement | CON | BRIP | 2028-10-05 |  | 0 | 0 | 1278000 | 2278000 | 2427000 | 2278000 | 3129000 | 0 | 0 | 11390000
DVRPC | 6 | Philadelphia | 92554 | Ridge Avenue over Amtrak | 3009 | PAR | Bridge Replacement | CON | 185 | 2028-10-05 |  | 0 | 0 | 320000 | 570000 | 607000 | 570000 | 782000 | 0 | 0 | 2849000
DVRPC | 6 | Philadelphia | 92809 | Roosevelt Blvd Exit(C) | 13 | RBR | Bridge Restoration | CON | STU | 2021-12-16 | 2021-12-16 | 128189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128189
DVRPC | 6 | Philadelphia | 98229 | 59th Street O/ AMTRAK | 7301 | 631 | Bridge Replacement | UTL | BOF | 2027-01-28 |  | 1906000 | 4578000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6484000
DVRPC | 6 | Philadelphia | 98229 | 59th Street O/ AMTRAK | 7301 | 631 | Bridge Replacement | CON | BOF | 2027-01-28 |  | 0 | 1055000 | 5192000 | 7954000 | 8850000 | 6624000 | 0 | 0 | 1918000 | 31593000
DVRPC | 6 | Philadelphia | 98229 | 59th Street O/ AMTRAK | 7301 | 631 | Bridge Replacement | CON | BRIP | 2027-01-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918000 | 1918000
DVRPC | 6 | Philadelphia | 98229 | 59th Street O/ AMTRAK | 7301 | 631 | Bridge Replacement | CON | 183 | 2027-01-28 |  | 0 | 197000 | 973000 | 1491000 | 1659000 | 1242000 | 0 | 0 | 720000 | 6282000
DVRPC | 6 | Philadelphia | 98229 | 59th Street O/ AMTRAK | 7301 | 631 | Bridge Replacement | CON | LOC | 2027-01-28 |  | 0 | 66000 | 324000 | 497000 | 553000 | 414000 | 0 | 0 | 240000 | 2094000
DVRPC | 6 | Philadelphia | 98230 | Tabor Road over Tacony Creek | 7301 | 255 | Bridge Restoration | CON | BRIP | 2026-10-01 |  | 0 | 0 | 1634000 | 0 | 0 | 0 | 0 | 0 | 0 | 1634000
DVRPC | 6 | Philadelphia | 98230 | Tabor Road over Tacony Creek | 7301 | 255 | Bridge Restoration | CON | STP | 2026-10-01 |  | 2215000 | 1634000 | 0 | 1234000 | 2000000 | 0 | 0 | 0 | 0 | 7083000
DVRPC | 6 | Philadelphia | 98230 | Tabor Road over Tacony Creek | 7301 | 255 | Bridge Restoration | CON | STU | 2026-10-01 |  | 0 | 0 | 0 | 0 | 0 | 1934000 | 1234000 | 0 | 0 | 3168000
DVRPC | 6 | Philadelphia | 98230 | Tabor Road over Tacony Creek | 7301 | 255 | Bridge Restoration | CON | 183 | 2026-10-01 |  | 554000 | 409000 | 409000 | 308000 | 375000 | 484000 | 309000 | 0 | 0 | 2848000
DVRPC | 6 | Philadelphia | 103563 | Delaware Avenue Ext.: Orthodox St - Munroe Rd | 1021 | BS5 | New Alignment | ROW | NHPP | 2027-07-15 |  | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
DVRPC | 6 | Philadelphia | 103563 | Delaware Avenue Ext.: Orthodox St - Munroe Rd | 1021 | BS5 | New Alignment | UTL | STU | 2027-07-15 |  | 0 | 2150000 | 4390000 | 5760000 | 0 | 0 | 0 | 0 | 0 | 12300000
DVRPC | 6 | Philadelphia | 103563 | Delaware Avenue Ext.: Orthodox St - Munroe Rd | 1021 | BS5 | New Alignment | CON | NHPP | 2027-07-15 |  | 0 | 2000000 | 4000000 | 6000000 | 8000000 | 6000000 | 6000000 | 14000000 | 5952000 | 51952000
DVRPC | 6 | Philadelphia | 103563 | Delaware Avenue Ext.: Orthodox St - Munroe Rd | 1021 | BS5 | New Alignment | CON | STP | 2027-07-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1787000 | 1787000
DVRPC | 6 | Philadelphia | 103563 | Delaware Avenue Ext.: Orthodox St - Munroe Rd | 1021 | BS5 | New Alignment | CON | STU | 2027-07-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33261000 | 33261000
DVRPC | 6 | Philadelphia | 103563 | Delaware Avenue Ext.: Orthodox St - Munroe Rd | 1021 | BS5 | New Alignment | CON | 581 | 2027-07-15 |  | 0 | 500000 | 1000000 | 1500000 | 2000000 | 1500000 | 1500000 | 3500000 | 10499000 | 21999000
DVRPC | 6 | Philadelphia | 106264 | Penn's Landing Project Development(C) | 95 | CAP | Bicycle and Pedestrian Facilities Transit | FD | NHPP | 2022-12-15 | 2022-12-16 | 1650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650000
DVRPC | 6 | Philadelphia | 106264 | Penn's Landing Project Development(C) | 95 | CAP | Bicycle and Pedestrian Facilities Transit | FD | STP | 2022-12-15 | 2022-12-16 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
DVRPC | 6 | Philadelphia | 106264 | Penn's Landing Project Development(C) | 95 | CAP | Bicycle and Pedestrian Facilities Transit | CON | STP | 2022-12-15 | 2022-12-16 | 20093593 | 2908745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23002338
DVRPC | 6 | Philadelphia | 106264 | Penn's Landing Project Development(C) | 95 | CAP | Bicycle and Pedestrian Facilities Transit | CON | NHPP | 2022-12-15 | 2022-12-16 | 8850000 | 3568000 | 18299000 | 10084000 | 16924000 | 10000000 | 5000000 | 0 | 0 | 72725000
DVRPC | 6 | Philadelphia | 106264 | Penn's Landing Project Development(C) | 95 | CAP | Bicycle and Pedestrian Facilities Transit | CON | STU | 2022-12-15 | 2022-12-16 | 2625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2625000
DVRPC | 6 | Philadelphia | 106654 | I-95 Transp Demand Mgmt TMA |  | TMA | Planning/Research/Administration | PRA | NHPP |  |  | 0 | 465000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465000
DVRPC | 6 | Philadelphia | 106993 | Frankford Avenue Signal Improvements(C) | 13 | SP2 | Safety Improvement | PE | HVRU | 2022-09-15 | 2022-09-15 | 37000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37000
DVRPC | 6 | Philadelphia | 107648 | 5th St Streetscape: RisingSunAve - US 1(Parent) |  | 648 | Congestion Reduction | CON | CAQ | 2026-07-30 |  | 2020000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020000
DVRPC | 6 | Philadelphia | 107648 | 5th St Streetscape: RisingSunAve - US 1(Parent) |  | 648 | Congestion Reduction | CON | STU | 2026-07-30 |  | 1400000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000
DVRPC | 6 | Philadelphia | 108090 | Citywide Resurf/Ramps 106(C) |  | 106 | Highway Reconstruction | PE | STU | 2019-06-06 | 2019-06-06 | 142926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142926
DVRPC | 6 | Philadelphia | 108090 | Citywide Resurf/Ramps 106(C) |  | 106 | Highway Reconstruction | PE | LOC | 2019-06-06 | 2019-06-06 | 35732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35732
DVRPC | 6 | Philadelphia | 108099 | Falls Bridge over Schuylkill River | 7301 | FAL | Bridge Restoration | UTL | 183 | 2027-01-28 |  | 67000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67000
DVRPC | 6 | Philadelphia | 108099 | Falls Bridge over Schuylkill River | 7301 | FAL | Bridge Restoration | CON | BRIP | 2027-01-28 |  | 0 | 0 | 0 | 0 | 0 | 2784000 | 1184000 | 8184000 | 0 | 12152000
DVRPC | 6 | Philadelphia | 108099 | Falls Bridge over Schuylkill River | 7301 | FAL | Bridge Restoration | CON | STP | 2027-01-28 |  | 0 | 0 | 589000 | 589000 | 2184000 | 0 | 0 | 0 | 0 | 3362000
DVRPC | 6 | Philadelphia | 108099 | Falls Bridge over Schuylkill River | 7301 | FAL | Bridge Restoration | CON | STU | 2027-01-28 |  | 0 | 2184000 | 3824000 | 3004000 | 820000 | 1400000 | 0 | 0 | 0 | 11232000
DVRPC | 6 | Philadelphia | 108099 | Falls Bridge over Schuylkill River | 7301 | FAL | Bridge Restoration | CON | 183 | 2027-01-28 |  | 0 | 410000 | 828000 | 675000 | 564000 | 785000 | 222000 | 1535000 | 0 | 5019000
DVRPC | 6 | Philadelphia | 108099 | Falls Bridge over Schuylkill River | 7301 | FAL | Bridge Restoration | CON | LOC | 2027-01-28 |  | 0 | 137000 | 276000 | 225000 | 188000 | 262000 | 74000 | 512000 | 0 | 1674000
DVRPC | 6 | Philadelphia | 108129 | MLK Drive Bridge(C ) | 7301 | MLK | Bridge Restoration | CON | BRIP | 2022-09-29 | 2022-09-29 | 2708000 | 4229000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6937000
DVRPC | 6 | Philadelphia | 110313 | Green Ln/Belmont Ave over Schuylkill River | 7301 | GLB | Bridge Restoration | PE | STP | 2029-04-12 |  | 0 | 594000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594000
DVRPC | 6 | Philadelphia | 110313 | Green Ln/Belmont Ave over Schuylkill River | 7301 | GLB | Bridge Restoration | PE | STU | 2029-04-12 |  | 0 | 985000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985000
DVRPC | 6 | Philadelphia | 110313 | Green Ln/Belmont Ave over Schuylkill River | 7301 | GLB | Bridge Restoration | PE | 183 | 2029-04-12 |  | 0 | 296000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296000
DVRPC | 6 | Philadelphia | 110313 | Green Ln/Belmont Ave over Schuylkill River | 7301 | GLB | Bridge Restoration | PE | LOC | 2029-04-12 |  | 0 | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99000
DVRPC | 6 | Philadelphia | 110313 | Green Ln/Belmont Ave over Schuylkill River | 7301 | GLB | Bridge Restoration | FD | BOF | 2029-04-12 |  | 1910000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1910000
DVRPC | 6 | Philadelphia | 110313 | Green Ln/Belmont Ave over Schuylkill River | 7301 | GLB | Bridge Restoration | FD | 183 | 2029-04-12 |  | 358000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358000
DVRPC | 6 | Philadelphia | 110313 | Green Ln/Belmont Ave over Schuylkill River | 7301 | GLB | Bridge Restoration | UTL | STU | 2029-04-12 |  | 0 | 0 | 0 | 594000 | 0 | 0 | 0 | 0 | 0 | 594000
DVRPC | 6 | Philadelphia | 110313 | Green Ln/Belmont Ave over Schuylkill River | 7301 | GLB | Bridge Restoration | UTL | 183 | 2029-04-12 |  | 0 | 0 | 0 | 111000 | 0 | 0 | 0 | 0 | 0 | 111000
DVRPC | 6 | Philadelphia | 110313 | Green Ln/Belmont Ave over Schuylkill River | 7301 | GLB | Bridge Restoration | UTL | LOC | 2029-04-12 |  | 0 | 0 | 0 | 37000 | 0 | 0 | 0 | 0 | 0 | 37000
DVRPC | 6 | Philadelphia | 110313 | Green Ln/Belmont Ave over Schuylkill River | 7301 | GLB | Bridge Restoration | CON | BRIP | 2029-04-12 |  | 0 | 0 | 1915000 | 2915000 | 3915000 | 2915000 | 2915000 | 2915000 | 0 | 17490000
DVRPC | 6 | Philadelphia | 110313 | Green Ln/Belmont Ave over Schuylkill River | 7301 | GLB | Bridge Restoration | CON | STU | 2029-04-12 |  | 0 | 0 | 0 | 0 | 972000 | 972000 | 971000 | 0 | 0 | 2915000
DVRPC | 6 | Philadelphia | 110313 | Green Ln/Belmont Ave over Schuylkill River | 7301 | GLB | Bridge Restoration | CON | 183 | 2029-04-12 |  | 0 | 0 | 0 | 0 | 243000 | 243000 | 243000 | 0 | 0 | 729000
DVRPC | 6 | Philadelphia | 110313 | Green Ln/Belmont Ave over Schuylkill River | 7301 | GLB | Bridge Restoration | CON | 581 | 2029-04-12 |  | 0 | 0 | 479000 | 729000 | 979000 | 729000 | 729000 | 729000 | 0 | 4374000
DVRPC | 6 | Philadelphia | 110314 | 30th Street (viaduct) over 30th Street (ground) | 7301 | 267 | Bridge Restoration | FD | BOF | 2027-08-12 |  | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
DVRPC | 6 | Philadelphia | 110314 | 30th Street (viaduct) over 30th Street (ground) | 7301 | 267 | Bridge Restoration | FD | 183 | 2027-08-12 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
DVRPC | 6 | Philadelphia | 110314 | 30th Street (viaduct) over 30th Street (ground) | 7301 | 267 | Bridge Restoration | UTL | BOF | 2027-08-12 |  | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68000
DVRPC | 6 | Philadelphia | 110314 | 30th Street (viaduct) over 30th Street (ground) | 7301 | 267 | Bridge Restoration | UTL | 183 | 2027-08-12 |  | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
DVRPC | 6 | Philadelphia | 110314 | 30th Street (viaduct) over 30th Street (ground) | 7301 | 267 | Bridge Restoration | CON | BOF | 2027-08-12 |  | 0 | 0 | 3210000 | 4116000 | 1000000 | 7403000 | 12332000 | 0 | 0 | 28061000
DVRPC | 6 | Philadelphia | 110314 | 30th Street (viaduct) over 30th Street (ground) | 7301 | 267 | Bridge Restoration | CON | 183 | 2027-08-12 |  | 0 | 0 | 602000 | 772000 | 187000 | 1388000 | 2312000 | 0 | 0 | 5261000
DVRPC | 6 | Philadelphia | 110314 | 30th Street (viaduct) over 30th Street (ground) | 7301 | 267 | Bridge Restoration | CON | LOC | 2027-08-12 |  | 0 | 0 | 201000 | 62000 | 655000 | 462000 | 771000 | 0 | 0 | 2151000
DVRPC | 6 | Philadelphia | 110415 | SchuylBnksTrail-Chrstn-CrsntTIGER (C) |  | SBT | Bicycle Pedestrian Highway | CON | CAQ | 2021-05-06 | 2021-05-13 | 785000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 785000
DVRPC | 6 | Philadelphia | 110958 | Castor & Wyoming Ave. Roundabout(C) | 1005 | SP3 | Safety Improvement | FD | HSIP | 2025-02-27 | 2025-02-27 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
DVRPC | 6 | Philadelphia | 110958 | Castor & Wyoming Ave. Roundabout(C) | 1005 | SP3 | Safety Improvement | CON | HSIP | 2025-02-27 | 2025-02-27 | 5072000 | 557039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5629039
DVRPC | 6 | Philadelphia | 111194 | Castor Ave: Oxford Circle to Cottman Ave | 1005 | SP2 | Safety Improvement | CON | HSIP | 2028-04-06 |  | 0 | 0 | 6969000 | 0 | 0 | 0 | 0 | 0 | 0 | 6969000
DVRPC | 6 | Philadelphia | 111500 | Manayunk Canal Masonry Wall Restor |  | MCL | Transportation Enhancement | CON | TAP | 2026-10-01 |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Philadelphia | 111515 | Cherokee Street over Valley Green Road | 7301 | CSB | Bridge Restoration | CON | STP | 2026-07-02 |  | 1660000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1660000
DVRPC | 6 | Philadelphia | 111515 | Cherokee Street over Valley Green Road | 7301 | CSB | Bridge Restoration | CON | STP | 2026-07-02 |  | 3890000 | 1450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5340000
DVRPC | 6 | Philadelphia | 112463 | ADA Ramps in Center City Phila(C) | 3010 | ADM | Americans with Disabilities Act (ADA) | CON | CRPU | 2024-04-18 | 2024-04-18 | 1950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1950000
DVRPC | 6 | Philadelphia | 112500 | Citywide 3R 110(C) |  | 110 | Highway Restoration | CON | CRPU | 2023-08-24 | 2023-08-24 | 790000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 790000
DVRPC | 6 | Philadelphia | 112500 | Citywide 3R 110(C) |  | 110 | Highway Restoration | CON | STP | 2023-08-24 | 2023-08-24 | 1562000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1562000
DVRPC | 6 | Philadelphia | 112500 | Citywide 3R 110(C) |  | 110 | Highway Restoration | CON | STU | 2023-08-24 | 2023-08-24 | 5378610 | 2000000 | 438000 | 3940000 | 3036000 | 176000 | 0 | 0 | 0 | 14968610
DVRPC | 6 | Philadelphia | 112525 | Citywide 3R 111(C) |  | 111 | Highway Restoration | CON | STU | 2025-05-08 | 2025-05-08 | 5460000 | 3446000 | 2069000 | 678000 | 5069000 | 4917000 | 4069000 | 16221000 | 0 | 41929000
DVRPC | 6 | Philadelphia | 112525 | Citywide 3R 111(C) |  | 111 | Highway Restoration | CON | LOC | 2025-05-08 | 2025-05-08 | 1365000 | 861000 | 517000 | 169000 | 1267000 | 1229000 | 1017000 | 4055000 | 0 | 10480000
DVRPC | 6 | Philadelphia | 112527 | Citywide ADA Ramps 3 |  | AD3 | Americans with Disabilities Act (ADA) | FD | STP | 2027-03-25 |  | 1384000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1384000
DVRPC | 6 | Philadelphia | 112527 | Citywide ADA Ramps 3 |  | AD3 | Americans with Disabilities Act (ADA) | CON | STP | 2027-03-25 |  | 0 | 1880000 | 0 | 880000 | 2880000 | 1880000 | 0 | 0 | 0 | 7520000
DVRPC | 6 | Philadelphia | 112527 | Citywide ADA Ramps 3 |  | AD3 | Americans with Disabilities Act (ADA) | CON | STU | 2027-03-25 |  | 0 | 0 | 1880000 | 0 | 0 | 0 | 0 | 0 | 0 | 1880000
DVRPC | 6 | Philadelphia | 113813 | 2026 Bridge Rehabilitation Group | 63 | HB1 | Bridge Restoration | UTL | 185 | 2026-04-09 |  | 478000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 478000
DVRPC | 6 | Philadelphia | 113813 | 2026 Bridge Rehabilitation Group | 63 | HB1 | Bridge Restoration | CON | 185 | 2026-04-09 |  | 1950000 | 2125000 | 1775000 | 1950000 | 1950000 | 1950000 | 0 | 0 | 0 | 11700000
DVRPC | 6 | Philadelphia | 114173 | Roosevelt Blvd Crossovr Lanes(C) | 1 | XBA | Congestion Reduction | FD | CAQ | 2025-07-24 | 2025-07-24 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
DVRPC | 6 | Philadelphia | 114173 | Roosevelt Blvd Crossovr Lanes(C) | 1 | XBA | Congestion Reduction | CON | CAQ | 2025-07-24 | 2025-07-24 | 5664510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5664510
DVRPC | 6 | Philadelphia | 115430 | Broad St Safety Imp: Allegheny-Hunting Prk Ave(C) | 611 | SIP | Safety Improvement | CON | HVRU | 2024-06-13 | 2024-06-13 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
DVRPC | 6 | Philadelphia | 115434 | Frankford Ave Corridor Safety Improvements | 2007 | SIP | Safety Improvement | FD | HVRU | 2026-09-17 |  | 855000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855000
DVRPC | 6 | Philadelphia | 115434 | Frankford Ave Corridor Safety Improvements | 2007 | SIP | Safety Improvement | CON | HSIP | 2026-09-17 |  | 0 | 3751000 | 3375000 | 0 | 0 | 0 | 0 | 0 | 0 | 7126000
DVRPC | 6 | Philadelphia | 115435 | 63rd St. Safety Improvements | 3015 | SIP | Safety Improvement | FD | HSIP |  |  | 0 | 1500000 | 715000 | 0 | 0 | 0 | 0 | 0 | 0 | 2215000
DVRPC | 6 | Philadelphia | 115435 | 63rd St. Safety Improvements | 3015 | SIP | Safety Improvement | UTL | HSIP |  |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
DVRPC | 6 | Philadelphia | 115435 | 63rd St. Safety Improvements | 3015 | SIP | Safety Improvement | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 3571000 | 0 | 0 | 0 | 3571000
DVRPC | 6 | Philadelphia | 115435 | 63rd St. Safety Improvements | 3015 | SIP | Safety Improvement | CON | 581 |  |  | 0 | 0 | 0 | 0 | 488000 | 738000 | 1421000 | 6127000 | 11777000 | 20551000
DVRPC | 6 | Philadelphia | 115440 | Washington Lane Corridor Safety Improvements | 4019 | SIP | Safety Improvement | FD | HSIP | 2026-09-17 |  | 0 | 695000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695000
DVRPC | 6 | Philadelphia | 115440 | Washington Lane Corridor Safety Improvements | 4019 | SIP | Safety Improvement | UTL | HSIP | 2026-09-17 |  | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
DVRPC | 6 | Philadelphia | 115440 | Washington Lane Corridor Safety Improvements | 4019 | SIP | Safety Improvement | CON | HSIP | 2026-09-17 |  | 0 | 3450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3450000
DVRPC | 6 | Philadelphia | 115442 | Vine St Corridor Safety Improvements(C) | 2676 | SIP | Safety Improvement | FD | HSIP | 2025-04-17 | 2025-04-17 | 352000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352000
DVRPC | 6 | Philadelphia | 115442 | Vine St Corridor Safety Improvements(C) | 2676 | SIP | Safety Improvement | FD | HVRU | 2025-04-17 | 2025-04-17 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
DVRPC | 6 | Philadelphia | 115442 | Vine St Corridor Safety Improvements(C) | 2676 | SIP | Safety Improvement | UTL | HSIP | 2025-04-17 | 2025-04-17 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
DVRPC | 6 | Philadelphia | 115442 | Vine St Corridor Safety Improvements(C) | 2676 | SIP | Safety Improvement | CON | HVRU | 2025-04-17 | 2025-04-17 | 5000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000000
DVRPC | 6 | Philadelphia | 115442 | Vine St Corridor Safety Improvements(C) | 2676 | SIP | Safety Improvement | CON | HSIP | 2025-04-17 | 2025-04-17 | 0 | 0 | 3893000 | 0 | 0 | 0 | 0 | 0 | 0 | 3893000
DVRPC | 6 | Philadelphia | 115444 | Wyoming Ave Corridor Safety Improvements |  | SIP | Safety Improvement | UTL | HSIP | 2026-11-05 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
DVRPC | 6 | Philadelphia | 115444 | Wyoming Ave Corridor Safety Improvements |  | SIP | Safety Improvement | CON | HSIP | 2026-11-05 |  | 0 | 3600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600000
DVRPC | 6 | Philadelphia | 115445 | 5th St Safety: Spring Garden St to Erie Ave |  | SIP | Safety Improvement | FD | HSIP | 2026-07-30 |  | 530000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530000
DVRPC | 6 | Philadelphia | 115445 | 5th St Safety: Spring Garden St to Erie Ave |  | SIP | Safety Improvement | UTL | HSIP | 2026-07-30 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
DVRPC | 6 | Philadelphia | 115445 | 5th St Safety: Spring Garden St to Erie Ave |  | SIP | Safety Improvement | CON | HSIP | 2026-07-30 |  | 0 | 7500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500000
DVRPC | 6 | Philadelphia | 115905 | 2022-23 ADA Ramps Phila County(C) | 3 | AD9 | Americans with Disabilities Act (ADA) | CON | CRPU | 2023-10-19 | 2023-10-19 | 1950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1950000
DVRPC | 6 | Philadelphia | 115965 | TAP Project Engineering/Management |  |  | Transportation Enhancement | PRA | STU |  |  | 712000 | 712000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1424000
DVRPC | 6 | Philadelphia | 115965 | TAP Project Engineering/Management |  |  | Transportation Enhancement | PRA | 581 |  |  | 178000 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356000
DVRPC | 6 | Philadelphia | 115966 | CMAQ Project Engineering/Management |  |  | Reserve Line Item | PRA | STU |  |  | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
DVRPC | 6 | Philadelphia | 115966 | CMAQ Project Engineering/Management |  |  | Reserve Line Item | PRA | 581 |  |  | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
DVRPC | 6 | Philadelphia | 115971 | Transp. Systems Mgmt. and Operations(TSMO)2022-23 |  |  | Planning/Research/Administration | PRA | CRP |  |  | 63885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63885
DVRPC | 6 | Philadelphia | 115971 | Transp. Systems Mgmt. and Operations(TSMO)2022-23 |  |  | Planning/Research/Administration | PRA | STU |  |  | 310000 | 310000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620000
DVRPC | 6 | Philadelphia | 115971 | Transp. Systems Mgmt. and Operations(TSMO)2022-23 |  |  | Planning/Research/Administration | PRA | 581 |  |  | 78000 | 78000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156000
DVRPC | 6 | Philadelphia | 115972 | I-95 Planning Assistance |  |  | Planning/Research/Administration | PRA | NHPP |  |  | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
DVRPC | 6 | Philadelphia | 115972 | I-95 Planning Assistance |  |  | Planning/Research/Administration | PRA | 581 |  |  | 40000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
DVRPC | 6 | Philadelphia | 115973 | Enhance & Maintain Travel Forecasting Tools |  |  | Planning/Research/Administration | PRA | STU |  |  | 578000 | 454000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032000
DVRPC | 6 | Philadelphia | 116807 | Citywide ADA Ramps 4 |  | AD4 | Americans with Disabilities Act (ADA) | FD | STP | 2028-02-17 |  | 720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720000
DVRPC | 6 | Philadelphia | 116807 | Citywide ADA Ramps 4 |  | AD4 | Americans with Disabilities Act (ADA) | CON | STP | 2028-02-17 |  | 0 | 1855000 | 1000000 | 2005000 | 3722000 | 693000 | 0 | 0 | 0 | 9275000
DVRPC | 6 | Philadelphia | 117796 | Systemic Improvements-Vulnerable Users (C) |  | SIP | Safety Improvement | CON | HVRU | 2024-03-28 | 2024-03-28 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
DVRPC | 6 | Philadelphia | 117904 | PA TCDI |  |  | Planning/Research/Administration | PE | STU |  |  | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
DVRPC | 6 | Philadelphia | 117930 | TripSmart PA Admin & DVRPC Commuter Services |  |  | Planning/Research/Administration | PRA | CAQ |  |  | 325000 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
DVRPC | 6 | Philadelphia | 117966 | Overbrook Edu Center Slow Zone(C) | 3018 | OEC | Bicycle Pedestrian Highway | CON | TAU | 2025-04-10 | 2025-04-10 | 1352060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1352060
DVRPC | 6 | Philadelphia | 118010 | Bellwether District Master Study |  | BWS | Study Phase of Project | STUDY | 581 |  |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Philadelphia | 118010 | Bellwether District Master Study |  | BWS | Study Phase of Project | STUDY | LOC |  |  | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
DVRPC | 6 | Philadelphia | 118014 | Bridge Painting Package | 7301 | PNT | Bridge Restoration | FD | 185 | 2029-01-11 |  | 0 | 437000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437000
DVRPC | 6 | Philadelphia | 118014 | Bridge Painting Package | 7301 | PNT | Bridge Restoration | UTL | BRIP | 2029-01-11 |  | 0 | 874000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 874000
DVRPC | 6 | Philadelphia | 118014 | Bridge Painting Package | 7301 | PNT | Bridge Restoration | CON | BOF | 2029-01-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3900000
DVRPC | 6 | Philadelphia | 118014 | Bridge Painting Package | 7301 | PNT | Bridge Restoration | CON | BRIP | 2029-01-11 |  | 0 | 0 | 0 | 0 | 0 | 3502000 | 3339000 | 0 | 0 | 6841000
DVRPC | 6 | Philadelphia | 118034 | Spring Garden St: Pennsylvania Ave -- Delaware Ave | 2006 | SGC | Bicycle Pedestrian Highway | CON | CRP | 2027-09-16 |  | 0 | 0 | 1300000 | 1320000 | 0 | 1368000 | 0 | 0 | 0 | 3988000
DVRPC | 6 | Philadelphia | 118034 | Spring Garden St: Pennsylvania Ave -- Delaware Ave | 2006 | SGC | Bicycle Pedestrian Highway | CON | CRPU | 2027-09-16 |  | 0 | 0 | 8822000 | 0 | 280000 | 6006000 | 5000000 | 0 | 1904000 | 22012000
DVRPC | 6 | Philadelphia | 118034 | Spring Garden St: Pennsylvania Ave -- Delaware Ave | 2006 | SGC | Bicycle Pedestrian Highway | CON | STU | 2027-09-16 |  | 0 | 2660000 | 2660000 | 2660000 | 5320000 | 5320000 | 5320000 | 1000000 | 1110000 | 26050000
DVRPC | 6 | Philadelphia | 118035 | North 5th St: US 1 to Godfrey Ave |  | GA1 | Safety Improvement | FD | 581 | 2027-09-16 |  | 0 | 705000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705000
DVRPC | 6 | Philadelphia | 118035 | North 5th St: US 1 to Godfrey Ave |  | GA1 | Safety Improvement | CON | STP | 2027-09-16 |  | 0 | 0 | 1000000 | 0 | 1566000 | 556000 | 2132000 | 1566000 | 0 | 6820000
DVRPC | 6 | Philadelphia | 118035 | North 5th St: US 1 to Godfrey Ave |  | GA1 | Safety Improvement | CON | STU | 2027-09-16 |  | 0 | 0 | 0 | 2576000 | 0 | 0 | 0 | 0 | 0 | 2576000
DVRPC | 6 | Philadelphia | 118035 | North 5th St: US 1 to Godfrey Ave |  | GA1 | Safety Improvement | CON | 581 | 2027-09-16 |  | 0 | 0 | 250000 | 644000 | 391000 | 139000 | 533000 | 391000 | 0 | 2348000
DVRPC | 6 | Philadelphia | 118074 | US 1 BAT Lanes: Hellerman/Bustleton - Bucks | 6001 | BAT | Congestion Reduction | FD | 244 | 2026-12-03 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
DVRPC | 6 | Philadelphia | 118074 | US 1 BAT Lanes: Hellerman/Bustleton - Bucks | 6001 | BAT | Congestion Reduction | CON | 244 | 2026-12-03 |  | 0 | 515000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515000
DVRPC | 6 | Philadelphia | 118074 | US 1 BAT Lanes: Hellerman/Bustleton - Bucks | 6001 | BAT | Congestion Reduction | CON | LOC | 2026-12-03 |  | 0 | 2585000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2585000
DVRPC | 6 | Philadelphia | 118359 | Logan Square Sidewalk(C) | 3007 | LSS | Bicycle Pedestrian Highway | CON | TAP | 2025-09-25 | 2025-09-25 | 1686000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1686000
DVRPC | 6 | Philadelphia | 118496 | Woodlnd Av Trolley Portal Comp St(TOP)R9 |  | TOP | Bicycle Pedestrian Highway | PE | LOC | 2028-01-13 |  | 0 | 0 | 129000 | 0 | 0 | 0 | 0 | 0 | 0 | 129000
DVRPC | 6 | Philadelphia | 118496 | Woodlnd Av Trolley Portal Comp St(TOP)R9 |  | TOP | Bicycle Pedestrian Highway | CON | CAQ | 2028-01-13 |  | 0 | 0 | 627000 | 0 | 0 | 0 | 0 | 0 | 0 | 627000
DVRPC | 6 | Philadelphia | 118496 | Woodlnd Av Trolley Portal Comp St(TOP)R9 |  | TOP | Bicycle Pedestrian Highway | CON | TAP | 2028-01-13 |  | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Philadelphia | 118496 | Woodlnd Av Trolley Portal Comp St(TOP)R9 |  | TOP | Bicycle Pedestrian Highway | CON | 411 | 2028-01-13 |  | 0 | 0 | 608000 | 0 | 0 | 0 | 0 | 0 | 0 | 608000
DVRPC | 6 | Philadelphia | 118496 | Woodlnd Av Trolley Portal Comp St(TOP)R9 |  | TOP | Bicycle Pedestrian Highway | CON | LOC | 2028-01-13 |  | 0 | 0 | 360400 | 0 | 0 | 0 | 0 | 0 | 0 | 360400
DVRPC | 6 | Philadelphia | 119437 | Great Streets PHL - RAISE 22 |  | GSP | Safety Improvement | PE | LOC | 2026-11-05 |  | 2073767 | 233600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2307367
DVRPC | 6 | Philadelphia | 119437 | Great Streets PHL - RAISE 22 |  | GSP | Safety Improvement | FD | LOC | 2026-11-05 |  | 1360633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360633
DVRPC | 6 | Philadelphia | 119437 | Great Streets PHL - RAISE 22 |  | GSP | Safety Improvement | CON | RAISE | 2026-11-05 |  | 0 | 25000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000000
DVRPC | 6 | Philadelphia | 119437 | Great Streets PHL - RAISE 22 |  | GSP | Safety Improvement | CON | LOC | 2026-11-05 |  | 0 | 652000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 652000
DVRPC | 6 | Philadelphia | 119480 | Roosevelt Blvd Study | 1 | RFC | Study Phase of Project | STUDY | 581 |  |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
DVRPC | 6 | Philadelphia | 119793 | Technical Assistance - TASA 2023-2026 |  |  | Planning/Research/Administration | PRA | TAP |  |  | 450000 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
DVRPC | 6 | Philadelphia | 119822 | US 1: Broad St - Pratt St | 1 | RB1 | Safety Improvement | CON | MEGA | 2028-05-11 |  | 0 | 11100000 | 11100000 | 11100000 | 0 | 0 | 0 | 0 | 0 | 33300000
DVRPC | 6 | Philadelphia | 119822 | US 1: Broad St - Pratt St | 1 | RB1 | Safety Improvement | CON | STU | 2028-05-11 |  | 0 | 3833000 | 3833000 | 3833000 | 0 | 0 | 0 | 0 | 0 | 11499000
DVRPC | 6 | Philadelphia | 119836 | US 1: Pratt St - Old Lincoln Hwy | 1 | RB2 | Safety Improvement | CON | MEGA | 2027-12-16 |  | 0 | 14900000 | 14900000 | 14900000 | 0 | 0 | 0 | 0 | 0 | 44700000
DVRPC | 6 | Philadelphia | 119836 | US 1: Pratt St - Old Lincoln Hwy | 1 | RB2 | Safety Improvement | CON | STU | 2027-12-16 |  | 0 | 5140000 | 5140000 | 5140000 | 0 | 0 | 0 | 0 | 0 | 15420000
DVRPC | 6 | Philadelphia | 119896 | Reconnecting Our Chinatown | 676 | RCP | Bicycle Pedestrian Highway | PE | RCP |  |  | 8397608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8397608
DVRPC | 6 | Philadelphia | 119896 | Reconnecting Our Chinatown | 676 | RCP | Bicycle Pedestrian Highway | FD | RCP |  |  | 12476780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12476780
DVRPC | 6 | Philadelphia | 119896 | Reconnecting Our Chinatown | 676 | RCP | Bicycle Pedestrian Highway | CON | RCP |  |  | 0 | 138037276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138037276
DVRPC | 6 | Philadelphia | 120282 | Fairhill Neighborhood Slow Zone Phase 2 R9 |  | MTF | MultiModal | CON | 411 |  |  | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
DVRPC | 6 | Philadelphia | 120282 | Fairhill Neighborhood Slow Zone Phase 2 R9 |  | MTF | MultiModal | CON | LOC |  |  | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
DVRPC | 6 | Philadelphia | 120702 | ADA Ramps Philadelphia 2024(C) | 1004 | A11 | Americans with Disabilities Act (ADA) | CON | CRPU | 2024-10-24 | 2024-10-24 | 1950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1950000
DVRPC | 6 | Philadelphia | 120762 | Cobbs Creek Parkway: Market - Woodland | 3015 | SP1 | Safety Improvement | FD | 581 | 2026-08-27 |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
DVRPC | 6 | Philadelphia | 120762 | Cobbs Creek Parkway: Market - Woodland | 3015 | SP1 | Safety Improvement | UTL | 581 | 2026-08-27 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
DVRPC | 6 | Philadelphia | 120762 | Cobbs Creek Parkway: Market - Woodland | 3015 | SP1 | Safety Improvement | CON | HSIP | 2026-08-27 |  | 2485000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2485000
DVRPC | 6 | Philadelphia | 120762 | Cobbs Creek Parkway: Market - Woodland | 3015 | SP1 | Safety Improvement | CON | NHPP | 2026-08-27 |  | 0 | 12500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500000
DVRPC | 6 | Philadelphia | 120940 | Philadelphia County ADA Ramps | 3 | A13 | Air Quality | PE | CRPU | 2026-11-05 |  | 400000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
DVRPC | 6 | Philadelphia | 120940 | Philadelphia County ADA Ramps | 3 | A13 | Air Quality | CON | CRPU | 2026-11-05 |  | 0 | 0 | 0 | 2346000 | 2654000 | 0 | 0 | 0 | 0 | 5000000
DVRPC | 6 | Philadelphia | 120993 | North Phila School Zones RAISE 23 |  | SZS | Safety Improvement | PE | RAISE | 2027-11-04 |  | 559500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 559500
DVRPC | 6 | Philadelphia | 120993 | North Phila School Zones RAISE 23 |  | SZS | Safety Improvement | PE | LOC | 2027-11-04 |  | 559500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 559500
DVRPC | 6 | Philadelphia | 120993 | North Phila School Zones RAISE 23 |  | SZS | Safety Improvement | CON | RAISE | 2027-11-04 |  | 0 | 24440500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24440500
DVRPC | 6 | Philadelphia | 120993 | North Phila School Zones RAISE 23 |  | SZS | Safety Improvement | CON | LOC | 2027-11-04 |  | 0 | 2321500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2321500
DVRPC | 6 | Philadelphia | 121096 | Citywide Resurfacing 112 |  | 112 | Highway Restoration | PE | STU | 2026-11-05 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
DVRPC | 6 | Philadelphia | 121096 | Citywide Resurfacing 112 |  | 112 | Highway Restoration | PE | LOC | 2026-11-05 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
DVRPC | 6 | Philadelphia | 121096 | Citywide Resurfacing 112 |  | 112 | Highway Restoration | CON | STU | 2026-11-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19609000 | 19609000
DVRPC | 6 | Philadelphia | 121096 | Citywide Resurfacing 112 |  | 112 | Highway Restoration | CON | LOC | 2026-11-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4902000 | 4902000
Erie | 1 | Erie | 613 | Twenty Mile Creek Br | 20 | B15 | Bridge Replacement | CON | 185 | 2024-07-11 | 2024-07-25 | 1140000 | 732248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1872248
Erie | 1 | Erie | 622 | SR 97: French Ck Brdg | 97 | B00 | Bridge Restoration | CON | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 339548 | 410452 | 0 | 750000
Erie | 1 | Erie | 995 | US 6: Hare Creek Br | 6 | B09 | Bridge Replacement | FD | 185 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 600000
Erie | 1 | Erie | 995 | US 6: Hare Creek Br | 6 | B09 | Bridge Replacement | CON | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280000 | 1280000
Erie | 1 | Erie | 995 | US 6: Hare Creek Br | 6 | B09 | Bridge Replacement | CON | 185 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000
Erie | 1 | Erie | 1003 | Grubb Rd Brdg over Elk Creek | 4011 | B03 | Bridge Preservation - State Funded | CON | 185 | 2025-10-23 | 2025-12-11 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
Erie | 1 | Erie | 1036 | Union LeBoeuf Rd (T-672) Br ov S Br of French Cr | 7217 | L01 | Bridge Replacement | PE | BRIP | 2027-01-01 |  | 166700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166700
Erie | 1 | Erie | 1036 | Union LeBoeuf Rd (T-672) Br ov S Br of French Cr | 7217 | L01 | Bridge Replacement | FD | BOF | 2027-01-01 |  | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Erie | 1 | Erie | 1036 | Union LeBoeuf Rd (T-672) Br ov S Br of French Cr | 7217 | L01 | Bridge Replacement | FD | 183 | 2027-01-01 |  | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
Erie | 1 | Erie | 1036 | Union LeBoeuf Rd (T-672) Br ov S Br of French Cr | 7217 | L01 | Bridge Replacement | FD | LOC | 2027-01-01 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Erie | 1 | Erie | 1036 | Union LeBoeuf Rd (T-672) Br ov S Br of French Cr | 7217 | L01 | Bridge Replacement | ROW | BOF | 2027-01-01 |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Erie | 1 | Erie | 1036 | Union LeBoeuf Rd (T-672) Br ov S Br of French Cr | 7217 | L01 | Bridge Replacement | ROW | 183 | 2027-01-01 |  | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250
Erie | 1 | Erie | 1036 | Union LeBoeuf Rd (T-672) Br ov S Br of French Cr | 7217 | L01 | Bridge Replacement | ROW | LOC | 2027-01-01 |  | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
Erie | 1 | Erie | 1036 | Union LeBoeuf Rd (T-672) Br ov S Br of French Cr | 7217 | L01 | Bridge Replacement | UTL | BOF | 2027-01-01 |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Erie | 1 | Erie | 1036 | Union LeBoeuf Rd (T-672) Br ov S Br of French Cr | 7217 | L01 | Bridge Replacement | UTL | 183 | 2027-01-01 |  | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250
Erie | 1 | Erie | 1036 | Union LeBoeuf Rd (T-672) Br ov S Br of French Cr | 7217 | L01 | Bridge Replacement | UTL | LOC | 2027-01-01 |  | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
Erie | 1 | Erie | 1036 | Union LeBoeuf Rd (T-672) Br ov S Br of French Cr | 7217 | L01 | Bridge Replacement | CON | BOF | 2027-01-01 |  | 0 | 0 | 725000 | 475000 | 0 | 0 | 0 | 0 | 0 | 1200000
Erie | 1 | Erie | 1036 | Union LeBoeuf Rd (T-672) Br ov S Br of French Cr | 7217 | L01 | Bridge Replacement | CON | 183 | 2027-01-01 |  | 0 | 0 | 138604 | 86396 | 0 | 0 | 0 | 0 | 0 | 225000
Erie | 1 | Erie | 1036 | Union LeBoeuf Rd (T-672) Br ov S Br of French Cr | 7217 | L01 | Bridge Replacement | CON | LOC | 2027-01-01 |  | 0 | 0 | 45313 | 29687 | 0 | 0 | 0 | 0 | 0 | 75000
Erie | 1 | Erie | 1119 | SR 699: Meadville St Brdg | 699 | B02 | Bridge Replacement | FD | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Erie | 1 | Erie | 1119 | SR 699: Meadville St Brdg | 699 | B02 | Bridge Replacement | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
Erie | 1 | Erie | 1125 | SR 3015: Brdg/I-90 | 3015 | B01 | Bridge Restoration | PE | BOF |  |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Erie | 1 | Erie | 1125 | SR 3015: Brdg/I-90 | 3015 | B01 | Bridge Restoration | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
Erie | 1 | Erie | 1125 | SR 3015: Brdg/I-90 | 3015 | B01 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Erie | 1 | Erie | 1127 | SR 3022: Brdg/Little Conneauttee Cr. | 3022 | B01 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 457600 | 0 | 0 | 0 | 0 | 0 | 0 | 457600
Erie | 1 | Erie | 1133 | SR 2003: Main Street over French Creek | 2003 | B01 | Bridge Restoration | PE | BOF | 2029-01-01 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Erie | 1 | Erie | 1133 | SR 2003: Main Street over French Creek | 2003 | B01 | Bridge Restoration | PE | 185 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 180000
Erie | 1 | Erie | 1133 | SR 2003: Main Street over French Creek | 2003 | B01 | Bridge Restoration | CON | BRIP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 900000 | 1350000
Erie | 1 | Erie | 1172 | US 20: Bridge over B. & L.E. R.R. | 20 | B07 | Bridge Restoration | CON | 185 | 2030-01-01 |  | 0 | 0 | 0 | 510000 | 898550 | 791450 | 0 | 0 | 0 | 2200000
Erie | 1 | Erie | 1180 | Niemeyer Road (T-463) Br | 7220 | L00 | Bridge Restoration | CON | 183 | 2023-07-13 | 2023-07-13 | 96500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96500
Erie | 1 | Erie | 1211 | SR 299: Brdg/CSX & NS RR | 299 | B00 | Bridge Restoration | PE | BRIP | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000
Erie | 1 | Erie | 1211 | SR 299: Brdg/CSX & NS RR | 299 | B00 | Bridge Restoration | CON | BRIP | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 250000
Erie | 1 | Erie | 1246 | Weigh Station Sensors | 9202 | WIM | Highway Restoration | CON | 581 | 2026-05-21 |  | 522961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522961
Erie | 1 | Erie | 1268 | SR 5 over Eight Mile Ck - Scour Group | 5 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Erie | 1 | Erie | 1268 | SR 5 over Eight Mile Ck - Scour Group | 5 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Erie | 1 | Erie | 1268 | SR 5 over Eight Mile Ck - Scour Group | 5 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Erie | 1 | Erie | 1279 | SR 1101: Brdg/I-90 | 1101 | B00 | Bridge Restoration | PE | BOF |  |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Erie | 1 | Erie | 1279 | SR 1101: Brdg/I-90 | 1101 | B00 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 1508800 | 1508800 | 982400 | 0 | 0 | 0 | 4000000
Erie | 1 | Erie | 1280 | SR 1103: Brdg/I-90 | 1103 | B00 | Bridge Restoration | PE | BOF | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 140000
Erie | 1 | Erie | 1280 | SR 1103: Brdg/I-90 | 1103 | B00 | Bridge Restoration | CON | BOF | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234200 | 3033400 | 3267600
Erie | 1 | Erie | 1288 | Gay Road over I-90 | 1019 | B00 | Bridge Replacement | PE | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Erie | 1 | Erie | 1288 | Gay Road over I-90 | 1019 | B00 | Bridge Replacement | CON | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1080337 | 1635015 | 2284648 | 5000000
Erie | 1 | Erie | 1292 | SR 3003: Bridge over Conneaut Creek West Branch | 3003 | B00 | Bridge Restoration | PE | 185 | 2033-01-01 |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Erie | 1 | Erie | 1292 | SR 3003: Bridge over Conneaut Creek West Branch | 3003 | B00 | Bridge Restoration | CON | BRIP | 2033-01-01 |  | 0 | 0 | 0 | 718600 | 481400 | 0 | 0 | 0 | 0 | 1200000
Erie | 1 | Erie | 32244 | US 20: School St - Franklin Rd | 20 | 26M | Preventive Maintenance | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Erie | 1 | Erie | 32244 | US 20: School St - Franklin Rd | 20 | 26M | Preventive Maintenance | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6088852 | 6088852
Erie | 1 | Erie | 47274 | US 19: Kuntz Rd. to W. 38th St. | 19 | 17M | Highway Restoration | FD | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 300000
Erie | 1 | Erie | 47274 | US 19: Kuntz Rd. to W. 38th St. | 19 | 17M | Highway Restoration | CON | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 108729 | 0 | 0 | 1678271 | 0 | 1787000
Erie | 1 | Erie | 47274 | US 19: Kuntz Rd. to W. 38th St. | 19 | 17M | Highway Restoration | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 152182 | 0 | 0 | 550000 | 0 | 702182
Erie | 1 | Erie | 47501 | SR 4108: Jordan Rd/I-90 | 4108 | B00 | Bridge Replacement | CON | BRIP | 2024-08-08 | 2024-08-08 | 2211840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2211840
Erie | 1 | Erie | 47502 | SR 1102: Brdg/I-90 | 1102 | B01 | Bridge Replacement | PE | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 140000
Erie | 1 | Erie | 47502 | SR 1102: Brdg/I-90 | 1102 | B01 | Bridge Replacement | ROW | BOF | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 0 | 32000
Erie | 1 | Erie | 47502 | SR 1102: Brdg/I-90 | 1102 | B01 | Bridge Replacement | CON | BOF | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334200 | 3000000 | 3334200
Erie | 1 | Erie | 47505 | PA 699: Edinboro Rd/I-90 Br | 699 | B01 | Bridge Replacement | UTL | 185 | 2022-09-29 | 2022-09-29 | 36286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36286
Erie | 1 | Erie | 47508 | Moorheadville Rd Br/I-90 | 1006 | B00 | Bridge Preservation - Federal | CON | BOF | 2028-01-01 |  | 0 | 0 | 0 | 0 | 0 | 259600 | 1040400 | 0 | 0 | 1300000
Erie | 1 | Erie | 57838 | West 38th & Liberty | 4016 | 02S | Safety Improvement | PE | HVRU | 2026-08-13 |  | 0 | 67000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67000
Erie | 1 | Erie | 57838 | West 38th & Liberty | 4016 | 02S | Safety Improvement | CON | HVRU | 2026-08-13 |  | 0 | 777000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 777000
Erie | 1 | Erie | 67101 | On-Call Bridge Repair Line Item |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 96467 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 2000000 | 5096467
Erie | 1 | Erie | 72136 | Erie BIL/IIJA Line Item Reserve |  | RES | Reserve Line Item | CON | BRIP |  |  | 0 | 57732 | 138800 | 762300 | 322200 | 300000 | 322200 | 322200 | 1288900 | 3514332
Erie | 1 | Erie | 72136 | Erie BIL/IIJA Line Item Reserve |  | RES | Reserve Line Item | CON | CRP |  |  | 0 | 202192 | 0 | 795000 | 795000 | 795000 | 795000 | 795000 | 3181000 | 7358192
Erie | 1 | Erie | 72136 | Erie BIL/IIJA Line Item Reserve |  | RES | Reserve Line Item | CON | CRPU |  |  | 0 | 0 | 0 | 517000 | 517000 | 517000 | 517000 | 517000 | 2069000 | 4654000
Erie | 1 | Erie | 72374 | SR 4103 bridge over I-90 | 4103 | B00 | Bridge Preservation - Federal | CON | BOF | 2024-03-14 | 2024-03-14 | 378043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378043
Erie | 1 | Erie | 72440 | SR 8 Bridge over East Branch French Creek | 8 | B12 | Bridge Restoration | FD | BRIP | 2027-10-07 |  | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325000
Erie | 1 | Erie | 72440 | SR 8 Bridge over East Branch French Creek | 8 | B12 | Bridge Restoration | ROW | BRIP | 2027-10-07 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Erie | 1 | Erie | 72440 | SR 8 Bridge over East Branch French Creek | 8 | B12 | Bridge Restoration | CON | BRIP | 2027-10-07 |  | 0 | 860500 | 678200 | 61300 | 0 | 0 | 0 | 0 | 0 | 1600000
Erie | 1 | Erie | 72440 | SR 8 Bridge over East Branch French Creek | 8 | B12 | Bridge Restoration | CON | 185 | 2027-10-07 |  | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Erie | 1 | Erie | 72447 | SR 20 Brdg over Six Mile Creek - Scour Group | 20 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Erie | 1 | Erie | 72447 | SR 20 Brdg over Six Mile Creek - Scour Group | 20 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Erie | 1 | Erie | 72447 | SR 20 Brdg over Six Mile Creek - Scour Group | 20 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Erie | 1 | Erie | 72449 | US 20: Brdg/ Eightmile Creek #1 | 20 | B18 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 175000
Erie | 1 | Erie | 72449 | US 20: Brdg/ Eightmile Creek #1 | 20 | B18 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016000 | 1016000
Erie | 1 | Erie | 72455 | SR 430 Bridge over Four Mile Creek - Scour Lead | 430 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 200000 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305000
Erie | 1 | Erie | 72455 | SR 430 Bridge over Four Mile Creek - Scour Lead | 430 | BSC | Bridge Preservation - Federal | ROW | PRTCT | 2026-06-18 |  | 0 | 82500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500
Erie | 1 | Erie | 72455 | SR 430 Bridge over Four Mile Creek - Scour Lead | 430 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Erie | 1 | Erie | 72455 | SR 430 Bridge over Four Mile Creek - Scour Lead | 430 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Erie | 1 | Erie | 72638 | SR 2018 Brdg ov Frch Ck S Br | 2018 | B05 | Bridge Restoration | PE | BOF | 2025-10-23 | 2025-12-11 | 0 | 2662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2662
Erie | 1 | Erie | 72638 | SR 2018 Brdg ov Frch Ck S Br | 2018 | B05 | Bridge Restoration | ROW | BOF | 2025-10-23 | 2025-12-11 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Erie | 1 | Erie | 72638 | SR 2018 Brdg ov Frch Ck S Br | 2018 | B05 | Bridge Restoration | CON | 185 | 2025-10-23 | 2025-12-11 | 125000 | 76065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201065
Erie | 1 | Erie | 72649 | SR 5: Bridge/Cascade Creek | 5 | B06 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 700000
Erie | 1 | Erie | 72649 | SR 5: Bridge/Cascade Creek | 5 | B06 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650100 | 1650100
Erie | 1 | Erie | 73242 | SR 430: SR 290-Shannon Rd | 430 | 04M | Highway Restoration | PE | NHPP | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000
Erie | 1 | Erie | 73242 | SR 430: SR 290-Shannon Rd | 430 | 04M | Highway Restoration | CON | NHPP | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700000 | 0 | 1700000
Erie | 1 | Erie | 78443 | Old Rte 99/Lamson Run #1 | 7212 | 452 | Bridge Replacement | UTL | 185 | 2024-08-08 | 2024-08-08 | 21500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21500
Erie | 1 | Erie | 78443 | Old Rte 99/Lamson Run #1 | 7212 | 452 | Bridge Replacement | CON | BOF | 2024-08-08 | 2024-08-08 | 579164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579164
Erie | 1 | Erie | 78444 | Old Rte 99/Lamson Run #2 | 7212 | 453 | Bridge Replacement | UTL | 185 | 2024-08-08 | 2024-08-08 | 28500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28500
Erie | 1 | Erie | 78444 | Old Rte 99/Lamson Run #2 | 7212 | 453 | Bridge Replacement | CON | BOF | 2024-08-08 | 2024-08-08 | 654530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654530
Erie | 1 | Erie | 78451 | Old Rte 99/Lamson Run #3 | 7212 | 454 | Bridge Replacement | CON | BOF | 2024-08-08 | 2024-08-08 | 607728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607728
Erie | 1 | Erie | 82879 | US 19: I-90 to Zimmerly Rd | 19 | 09M | Highway Restoration | PE | NHPP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 300000
Erie | 1 | Erie | 82879 | US 19: I-90 to Zimmerly Rd | 19 | 09M | Highway Restoration | CON | NHPP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 3158271 | 0 | 0 | 521729 | 0 | 3680000
Erie | 1 | Erie | 82879 | US 19: I-90 to Zimmerly Rd | 19 | 09M | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 664568 | 0 | 0 | 0 | 0 | 664568
Erie | 1 | Erie | 84305 | Dept. Force Br Line Item | 8 | 0 | Bridge Preservation - State Funded | CON | 185 |  |  | 0 | 0 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 0 | 720000
Erie | 1 | Erie | 84905 | SR 20 over Walnut Creek - Scour Group | 20 | BSC | Bridge Preservation - State Funded | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Erie | 1 | Erie | 84905 | SR 20 over Walnut Creek - Scour Group | 20 | BSC | Bridge Preservation - State Funded | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Erie | 1 | Erie | 84905 | SR 20 over Walnut Creek - Scour Group | 20 | BSC | Bridge Preservation - State Funded | CON | PRTCT | 2026-06-18 |  | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
Erie | 1 | Erie | 84907 | SR 2006 over Leboeuf Ck | 2006 | B00 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Erie | 1 | Erie | 84907 | SR 2006 over Leboeuf Ck | 2006 | B00 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770000 | 662448 | 1432448
Erie | 1 | Erie | 84910 | SR 4013 over Elk Creek | 4013 | B01 | Bridge Replacement | PE | 185 | 2026-06-04 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Erie | 1 | Erie | 84910 | SR 4013 over Elk Creek | 4013 | B01 | Bridge Replacement | ROW | BOF | 2026-06-04 |  | 0 | 14120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14120
Erie | 1 | Erie | 84910 | SR 4013 over Elk Creek | 4013 | B01 | Bridge Replacement | CON | BOF | 2026-06-04 |  | 146224 | 1234076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380300
Erie | 1 | Erie | 85362 | Erie Local Bridge Waterproofing 2024 | 7213 | L00 | Bridge Preservation - Federal | CON | BRIP | 2024-09-12 | 2024-09-12 | 175000 | 98562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273562
Erie | 1 | Erie | 85443 | Erie County Systemic HFST | 18 | S01 | Safety Improvement | PE | HSIP | 2026-02-26 | 2026-02-26 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Erie | 1 | Erie | 85443 | Erie County Systemic HFST | 18 | S01 | Safety Improvement | CON | HRRR | 2026-02-26 | 2026-02-26 | 0 | 423516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423516
Erie | 1 | Erie | 85443 | Erie County Systemic HFST | 18 | S01 | Safety Improvement | CON | HSIP | 2026-02-26 | 2026-02-26 | 0 | 414525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414525
Erie | 1 | Erie | 86499 | SR 5: Melhorn Rd - Gorman Dr | 5 | 261 | 409 Expanded Maintenance | CON | STP | 2026-04-09 |  | 0 | 0 | 0 | 0 | 0 | 3161000 | 1425000 | 0 | 0 | 4586000
Erie | 1 | Erie | 86499 | SR 5: Melhorn Rd - Gorman Dr | 5 | 261 | 409 Expanded Maintenance | CON | 581 | 2026-04-09 |  | 0 | 0 | 0 | 0 | 0 | 425500 | 356250 | 0 | 0 | 781750
Erie | 1 | Erie | 86951 | SR 18: Albion | 18 | 263 | General Maintenance | PE | 581 | 2026-02-26 | 2026-02-26 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
Erie | 1 | Erie | 86951 | SR 18: Albion | 18 | 263 | General Maintenance | CON | HSIP | 2026-02-26 | 2026-02-26 | 0 | 15130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15130
Erie | 1 | Erie | 86951 | SR 18: Albion | 18 | 263 | General Maintenance | CON | 581 | 2026-02-26 | 2026-02-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 800000 | 1200000
Erie | 1 | Erie | 87030 | US 20: SR 4004 - SR 4016 | 20 | 36M | Highway Restoration | PE | 581 | 2029-01-01 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Erie | 1 | Erie | 87030 | US 20: SR 4004 - SR 4016 | 20 | 36M | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 1150709 | 3626141 | 0 | 0 | 0 | 0 | 4776850
Erie | 1 | Erie | 87031 | US 20: Chestnut St to Imperial Parkway | 20 | 30M | Highway Restoration | CON | STP | 2023-03-30 | 2023-03-30 | 564815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564815
Erie | 1 | Erie | 88473 | Erie County T-Beam Rehab Group | 19 | B07 | Bridge Restoration | PE | BRIP | 2027-01-01 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Erie | 1 | Erie | 88473 | Erie County T-Beam Rehab Group | 19 | B07 | Bridge Restoration | CON | BRIP | 2027-01-01 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Erie | 1 | Erie | 89210 | SR 8: Lowville to Firethorn Road | 8 | 271 | 409 Expanded Maintenance | PE | 581 | 2027-02-11 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Erie | 1 | Erie | 89210 | SR 8: Lowville to Firethorn Road | 8 | 271 | 409 Expanded Maintenance | CON | 581 | 2027-02-11 |  | 0 | 0 | 0 | 0 | 624571 | 3786750 | 5316679 | 0 | 0 | 9728000
Erie | 1 | Erie | 90282 | US 6: SR 3006/Crossingville Rd | 3006 | 09M | Highway Restoration | PE | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Erie | 1 | Erie | 90282 | US 6: SR 3006/Crossingville Rd | 3006 | 09M | Highway Restoration | CON | STP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1827000 | 3152000 | 521000 | 5500000
Erie | 1 | Erie | 90282 | US 6: SR 3006/Crossingville Rd | 3006 | 09M | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 456750 | 788000 | 130250 | 1375000
Erie | 1 | Erie | 90285 | US 20: North East - I-90 Interchange | 20 | 31M | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Erie | 1 | Erie | 90285 | US 20: North East - I-90 Interchange | 20 | 31M | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
Erie | 1 | Erie | 90384 | Erie Safety Line Item |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 656000 | 0 | 0 | 0 | 0 | 0 | 0 | 656000
Erie | 1 | Erie | 90384 | Erie Safety Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 0 | 1000000 | 2500000
Erie | 1 | Erie | 93165 | SR 699 over Stancliff Rd | 699 | B00 | Bridge Restoration | PE | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Erie | 1 | Erie | 93165 | SR 699 over Stancliff Rd | 699 | B00 | Bridge Restoration | CON | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
Erie | 1 | Erie | 97132 | SR 4030: Brdg/CSX RR | 4030 | B00 | Bridge Restoration | PE | 185 | 2032-01-01 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Erie | 1 | Erie | 97132 | SR 4030: Brdg/CSX RR | 4030 | B00 | Bridge Restoration | ROW | 185 | 2032-01-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Erie | 1 | Erie | 97132 | SR 4030: Brdg/CSX RR | 4030 | B00 | Bridge Restoration | CON | BRIP | 2032-01-01 |  | 0 | 0 | 0 | 1429800 | 0 | 0 | 0 | 0 | 0 | 1429800
Erie | 1 | Erie | 97139 | US 20: Brdg/Lake Erie Trib | 20 | B10 | Bridge Restoration | FD | 185 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 109800 | 190200 | 0 | 0 | 300000
Erie | 1 | Erie | 97139 | US 20: Brdg/Lake Erie Trib | 20 | B10 | Bridge Restoration | CON | 185 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800000 | 2800000
Erie | 1 | Erie | 97149 | SR 5 Bridges/Turkey Creek & Turkey Creek Trib#1 | 5 | B14 | Bridge Restoration | PE | 185 | 2028-01-01 |  | 0 | 240200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240200
Erie | 1 | Erie | 97149 | SR 5 Bridges/Turkey Creek & Turkey Creek Trib#1 | 5 | B14 | Bridge Restoration | CON | 185 | 2028-01-01 |  | 0 | 0 | 0 | 1616000 | 384000 | 0 | 0 | 0 | 0 | 2000000
Erie | 1 | Erie | 97150 | SR 1001 Bridge over French Creek North Branch | 1001 | B06 | Bridge Restoration | CON | BOF | 2028-06-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 468400 | 931600 | 0 | 1400000
Erie | 1 | Erie | 97170 | SR 5 Bridge over Wensel Run | 5 | B18 | Bridge Restoration | PE | 185 | 2028-01-01 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Erie | 1 | Erie | 97170 | SR 5 Bridge over Wensel Run | 5 | B18 | Bridge Restoration | ROW | 185 | 2028-01-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Erie | 1 | Erie | 97170 | SR 5 Bridge over Wensel Run | 5 | B18 | Bridge Restoration | CON | 185 | 2028-01-01 |  | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000
Erie | 1 | Erie | 97171 | SR 4105 Bridge over I-90 | 4105 | B00 | Bridge Restoration | CON | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 258102 | 591898 | 0 | 0 | 850000
Erie | 1 | Erie | 97205 | US 20 Bridge/16 Mile Creek - Scour Group | 20 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Erie | 1 | Erie | 97205 | US 20 Bridge/16 Mile Creek - Scour Group | 20 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Erie | 1 | Erie | 97205 | US 20 Bridge/16 Mile Creek - Scour Group | 20 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Erie | 1 | Erie | 97208 | US 20 Bridge over Unknown Stream | 20 | B13 | Bridge Restoration | PE | 185 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000
Erie | 1 | Erie | 97208 | US 20 Bridge over Unknown Stream | 20 | B13 | Bridge Restoration | ROW | 185 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 14648 | 10352 | 0 | 0 | 25000
Erie | 1 | Erie | 97208 | US 20 Bridge over Unknown Stream | 20 | B13 | Bridge Restoration | CON | 185 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 400000
Erie | 1 | Erie | 97213 | PA 505 Bridge/Mill Ck #2 - Scour Group | 505 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Erie | 1 | Erie | 97213 | PA 505 Bridge/Mill Ck #2 - Scour Group | 505 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Erie | 1 | Erie | 97213 | PA 505 Bridge/Mill Ck #2 - Scour Group | 505 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Erie | 1 | Erie | 97214 | PA 505 Bridge/Mill Creek #1 -Scour Group | 505 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Erie | 1 | Erie | 97214 | PA 505 Bridge/Mill Creek #1 -Scour Group | 505 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Erie | 1 | Erie | 97214 | PA 505 Bridge/Mill Creek #1 -Scour Group | 505 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Erie | 1 | Erie | 97215 | PA 8 Bridge over West Branch of French Creek | 8 | B11 | Bridge Restoration | ROW | 185 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Erie | 1 | Erie | 97215 | PA 8 Bridge over West Branch of French Creek | 8 | B11 | Bridge Restoration | CON | 185 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 550000 | 200000 | 0 | 0 | 0 | 750000
Erie | 1 | Erie | 97218 | SR 4101 Bridge/I-90 | 4101 | B00 | Bridge Restoration | CON | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 848000 | 0 | 0 | 0 | 848000
Erie | 1 | Erie | 97221 | SR 1013: Brdg/I-90 | 1013 | B01 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Erie | 1 | Erie | 97240 | US 6 Bridge/French Ck. Trib | 6 | B11 | Bridge Restoration | PE | BRIP | 2029-01-01 |  | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Erie | 1 | Erie | 97240 | US 6 Bridge/French Ck. Trib | 6 | B11 | Bridge Restoration | ROW | BRIP | 2029-01-01 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Erie | 1 | Erie | 97240 | US 6 Bridge/French Ck. Trib | 6 | B11 | Bridge Restoration | CON | BRIP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 720000 | 0 | 0 | 0 | 0 | 720000
Erie | 1 | Erie | 97240 | US 6 Bridge/French Ck. Trib | 6 | B11 | Bridge Restoration | CON | 185 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 180000
Erie | 1 | Erie | 98256 | Erie Local Brdg Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 575000 | 950000 | 950000 | 950000 | 3800000 | 7225000
Erie | 1 | Erie | 98256 | Erie Local Brdg Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 250000 | 250000 | 250000 | 250000 | 1000000 | 2000000
Erie | 1 | Erie | 98308 | US 19: Dorn Rd - Robison Rd | 19 | A09 | Congestion Reduction | FD | STP | 2031-01-01 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Erie | 1 | Erie | 98308 | US 19: Dorn Rd - Robison Rd | 19 | A09 | Congestion Reduction | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 3000000
Erie | 1 | Erie | 98338 | US 6N (SR 3006) & SR 3023 (Angling Rd) | 3006 | A03 | Highway Reconstruction | PE | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Erie | 1 | Erie | 98338 | US 6N (SR 3006) & SR 3023 (Angling Rd) | 3006 | A03 | Highway Reconstruction | FD | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Erie | 1 | Erie | 98338 | US 6N (SR 3006) & SR 3023 (Angling Rd) | 3006 | A03 | Highway Reconstruction | ROW | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Erie | 1 | Erie | 98338 | US 6N (SR 3006) & SR 3023 (Angling Rd) | 3006 | A03 | Highway Reconstruction | UTL | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Erie | 1 | Erie | 98338 | US 6N (SR 3006) & SR 3023 (Angling Rd) | 3006 | A03 | Highway Reconstruction | CON | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510071 | 3510071
Erie | 1 | Erie | 99000 | SR 290: SR 5 - McClelland Ave. | 290 | 02M | Highway Restoration | CON | NHPP | 2034-01-01 |  | 0 | 0 | 0 | 1824000 | 0 | 1536000 | 0 | 0 | 0 | 3360000
Erie | 1 | Erie | 99000 | SR 290: SR 5 - McClelland Ave. | 290 | 02M | Highway Restoration | CON | 581 | 2034-01-01 |  | 0 | 0 | 0 | 331000 | 0 | 509000 | 0 | 0 | 0 | 840000
Erie | 1 | Erie | 99023 | SR 77: W Church St - SR 426 | 77 | 05M | Highway Reconstruction | FD | STP | 2025-12-04 | 2025-12-04 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000
Erie | 1 | Erie | 99023 | SR 77: W Church St - SR 426 | 77 | 05M | Highway Reconstruction | CON | NHPP | 2025-12-04 | 2025-12-04 | 2000000 | 1728872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3728872
Erie | 1 | Erie | 99049 | SR 8: Arbuckle Rd to Phillips Rd | 8 | 16M | Highway Restoration | PE | STP | 2035-01-01 |  | 25156 | 74844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Erie | 1 | Erie | 99049 | SR 8: Arbuckle Rd to Phillips Rd | 8 | 16M | Highway Restoration | CON | STP | 2035-01-01 |  | 0 | 0 | 0 | 641234 | 243000 | 0 | 0 | 0 | 0 | 884234
Erie | 1 | Erie | 99056 | SR 290 Signal Upgrade | 290 | 01S | Safety Improvement | PE | STP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Erie | 1 | Erie | 99056 | SR 290 Signal Upgrade | 290 | 01S | Safety Improvement | FD | STP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Erie | 1 | Erie | 99056 | SR 290 Signal Upgrade | 290 | 01S | Safety Improvement | ROW | STP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000
Erie | 1 | Erie | 99056 | SR 290 Signal Upgrade | 290 | 01S | Safety Improvement | UTL | STP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Erie | 1 | Erie | 99056 | SR 290 Signal Upgrade | 290 | 01S | Safety Improvement | CON | STP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 1400000
Erie | 1 | Erie | 99057 | SR 5: Gorman-Brewster - Signals | 5 | 08S | Safety Improvement | PE | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Erie | 1 | Erie | 99057 | SR 5: Gorman-Brewster - Signals | 5 | 08S | Safety Improvement | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
Erie | 1 | Erie | 99057 | SR 5: Gorman-Brewster - Signals | 5 | 08S | Safety Improvement | ROW | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
Erie | 1 | Erie | 99057 | SR 5: Gorman-Brewster - Signals | 5 | 08S | Safety Improvement | UTL | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
Erie | 1 | Erie | 99057 | SR 5: Gorman-Brewster - Signals | 5 | 08S | Safety Improvement | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Erie | 1 | Erie | 99701 | SR 18: Crawford Co- US 6N | 18 | 08M | Highway Restoration | PE | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
Erie | 1 | Erie | 99701 | SR 18: Crawford Co- US 6N | 18 | 08M | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2920000 | 2920000
Erie | 1 | Erie | 99703 | SR 5: Lake Road | 5 | 18M | Highway Restoration | PE | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
Erie | 1 | Erie | 99703 | SR 5: Lake Road | 5 | 18M | Highway Restoration | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1028512 | 3035488 | 4064000
Erie | 1 | Erie | 99711 | US 20: Depot Rd to Elliotts Run | 20 | 20M | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Erie | 1 | Erie | 99711 | US 20: Depot Rd to Elliotts Run | 20 | 20M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1870000 | 1870000
Erie | 1 | Erie | 99718 | SR 699: Mckean Boro Line to Interchange Rd. | 699 | 253 | General Maintenance | PE | 581 | 2025-03-27 | 2025-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
Erie | 1 | Erie | 99735 | SR 77: Crawford Co Ln - Pleasant St | 77 | 04M | 409 Expanded Maintenance | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Erie | 1 | Erie | 99735 | SR 77: Crawford Co Ln - Pleasant St | 77 | 04M | 409 Expanded Maintenance | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000
Erie | 1 | Erie | 99744 | US 20: W. Hirtzel Rd to NY | 20 | 23M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 1600000
Erie | 1 | Erie | 99750 | SR 832: US 20 to Presque Isle State Park | 832 | 06M | Highway Restoration | CON | CRP | 2025-05-08 | 2025-05-08 | 0 | 0 | 793000 | 0 | 0 | 0 | 0 | 0 | 0 | 793000
Erie | 1 | Erie | 99750 | SR 832: US 20 to Presque Isle State Park | 832 | 06M | Highway Restoration | CON | CRPU | 2025-05-08 | 2025-05-08 | 0 | 0 | 443402 | 0 | 0 | 0 | 0 | 0 | 0 | 443402
Erie | 1 | Erie | 99750 | SR 832: US 20 to Presque Isle State Park | 832 | 06M | Highway Restoration | CON | HVRU | 2025-05-08 | 2025-05-08 | 454816 | 682379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1137195
Erie | 1 | Erie | 99750 | SR 832: US 20 to Presque Isle State Park | 832 | 06M | Highway Restoration | CON | STP | 2025-05-08 | 2025-05-08 | 4736693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4736693
Erie | 1 | Erie | 99750 | SR 832: US 20 to Presque Isle State Park | 832 | 06M | Highway Restoration | CON | 581 | 2025-05-08 | 2025-05-08 | 179804 | 420250 | 552483 | 0 | 0 | 0 | 0 | 0 | 0 | 1152537
Erie | 1 | Erie | 99753 | SR 3006: SR 90 to SR 18 | 3006 | M01 | Highway Restoration | CON | NHPP | 2023-03-23 | 2023-03-23 | 70678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70678
Erie | 1 | Erie | 99757 | SR 8: Crawford to Union City | 8 | 272 | 409 Expanded Maintenance | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
Erie | 1 | Erie | 99757 | SR 8: Crawford to Union City | 8 | 272 | 409 Expanded Maintenance | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7800000 | 7800000
Erie | 1 | Erie | 101502 | SR 197 & I-90 Interchange | 197 | A00 | Highway Reconstruction | PE | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Erie | 1 | Erie | 101502 | SR 197 & I-90 Interchange | 197 | A00 | Highway Reconstruction | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Erie | 1 | Erie | 101502 | SR 197 & I-90 Interchange | 197 | A00 | Highway Reconstruction | ROW | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Erie | 1 | Erie | 101502 | SR 197 & I-90 Interchange | 197 | A00 | Highway Reconstruction | UTL | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Erie | 1 | Erie | 102069 | Hamot Rd/Oliver Rd Intersection | 4008 | S01 | Safety Improvement | UTL | STP | 2021-05-06 | 2021-05-06 | 41547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41547
Erie | 1 | Erie | 102468 | SR 531: Depot Road, Section 2 | 531 | A08 | Highway Reconstruction | CON | 581 | 2024-04-18 | 2024-04-18 | 3581140 | 3324025 | 5770921 | 0 | 0 | 0 | 0 | 0 | 0 | 12676086
Erie | 1 | Erie | 106421 | Erie Highway/Bridge Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 412915 | 273200 | 273200 | 273200 | 250000 | 273200 | 250000 | 1092600 | 3098315
Erie | 1 | Erie | 106421 | Erie Highway/Bridge Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 282621 | 2090000 | 2090000 | 2090000 | 2090000 | 2090000 | 2090000 | 8362000 | 21184621
Erie | 1 | Erie | 106421 | Erie Highway/Bridge Line Item |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 221128 | 0 | 0 | 250000 | 1025271 | 250000 | 3335000 | 1000000 | 6081399
Erie | 1 | Erie | 106421 | Erie Highway/Bridge Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 1033611 | 1566000 | 506068 | 250000 | 250000 | 250000 | 250000 | 1000000 | 5105679
Erie | 1 | Erie | 106421 | Erie Highway/Bridge Line Item |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 343488 | 613769 | 538604 | 300000 | 300000 | 300000 | 300000 | 1005900 | 3701761
Erie | 1 | Erie | 106421 | Erie Highway/Bridge Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 97292 | 1470444 | 300000 | 118818 | 300000 | 0 | 3301300 | 5587854
Erie | 1 | Erie | 106586 | SR 531: Depot Road, Section 4 | 531 | A09 | Highway Reconstruction | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1086000 | 1086000
Erie | 1 | Erie | 106586 | SR 531: Depot Road, Section 4 | 531 | A09 | Highway Reconstruction | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150064 | 150064
Erie | 1 | Erie | 106874 | Erie Local Fed Aid Rt Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 110903 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 2000000 | 5110903
Erie | 1 | Erie | 108952 | Central Bayfront Parkway Multimodal | 4034 | A01 | Congestion Reduction | UTL | 581 | 2023-07-27 | 2023-07-27 | 327625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327625
Erie | 1 | Erie | 108952 | Central Bayfront Parkway Multimodal | 4034 | A01 | Congestion Reduction | CON | CRP | 2023-07-27 | 2023-07-27 | 9290636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9290636
Erie | 1 | Erie | 108952 | Central Bayfront Parkway Multimodal | 4034 | A01 | Congestion Reduction | CON | BRIP | 2023-07-27 | 2023-07-27 | 243460 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10243460
Erie | 1 | Erie | 108952 | Central Bayfront Parkway Multimodal | 4034 | A01 | Congestion Reduction | CON | CRP | 2023-07-27 | 2023-07-27 | 776000 | 445000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 1223000
Erie | 1 | Erie | 108952 | Central Bayfront Parkway Multimodal | 4034 | A01 | Congestion Reduction | CON | CRPU | 2023-07-27 | 2023-07-27 | 507000 | 517000 | 73598 | 0 | 0 | 0 | 0 | 0 | 0 | 1097598
Erie | 1 | Erie | 108952 | Central Bayfront Parkway Multimodal | 4034 | A01 | Congestion Reduction | CON | NHPP | 2023-07-27 | 2023-07-27 | 2282509 | 1714000 | 880000 | 0 | 0 | 0 | 0 | 0 | 0 | 4876509
Erie | 1 | Erie | 108952 | Central Bayfront Parkway Multimodal | 4034 | A01 | Congestion Reduction | CON | STP | 2023-07-27 | 2023-07-27 | 124844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124844
Erie | 1 | Erie | 108952 | Central Bayfront Parkway Multimodal | 4034 | A01 | Congestion Reduction | CON | 185 | 2023-07-27 | 2023-07-27 | 1430896 | 1514621 | 1543627 | 0 | 0 | 0 | 0 | 0 | 0 | 4489144
Erie | 1 | Erie | 108952 | Central Bayfront Parkway Multimodal | 4034 | A01 | Congestion Reduction | CON | 581 | 2023-07-27 | 2023-07-27 | 1286985 | 2000000 | 509000 | 2595222 | 0 | 0 | 0 | 0 | 0 | 6391207
Erie | 1 | Erie | 109141 | City of Corry resurfacing | 426 | 01M | Highway Restoration | FD | STP | 2025-12-04 | 2025-12-04 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Erie | 1 | Erie | 109141 | City of Corry resurfacing | 426 | 01M | Highway Restoration | CON | STP | 2025-12-04 | 2025-12-04 | 2082009 | 1355490 | 1592000 | 2009698 | 0 | 0 | 0 | 0 | 0 | 7039197
Erie | 1 | Erie | 109893 | Erie 2022 Bridge Shotcrete Group | 430 | BSG | Bridge Restoration | CON | 185 | 2024-09-12 | 2024-09-12 | 43250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43250
Erie | 1 | Erie | 110343 | US 6N Underpass - Springfield Twp | 3006 | B11 | Bridge Replacement | FD | STP | 2028-01-01 |  | 0 | 250000 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 750000
Erie | 1 | Erie | 110343 | US 6N Underpass - Springfield Twp | 3006 | B11 | Bridge Replacement | CON | 581 | 2028-01-01 |  | 0 | 0 | 127080 | 2456625 | 2536538 | 0 | 0 | 0 | 0 | 5120243
Erie | 1 | Erie | 110379 | Erie Loop Bikeway French St |  | BW2 | Bicycle Pedestrian Highway | CON | CRP | 2026-02-26 | 2026-02-26 | 0 | 147808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147808
Erie | 1 | Erie | 110836 | Bayfront Parkway at 6th Street Intersection Impr. | 4034 | S00 | General Maintenance | CON | HSIP | 2023-09-14 | 2023-09-14 | 484184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484184
Erie | 1 | Erie | 111147 | Huntley Road RR Crossing |  | R00 | Safety Improvement | CON | RRX | 2021-08-26 |  | 133743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133743
Erie | 1 | Erie | 113215 | Bayfront Parkway RRX | 4034 | RRX | Rail Highway Grade Crossing | CON | RRX | 2020-07-23 | 2020-07-23 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000
Erie | 1 | Erie | 113880 | US 19: 4016 to US 20 | 19 | 16M | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Erie | 1 | Erie | 113880 | US 19: 4016 to US 20 | 19 | 16M | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 1900000
Erie | 1 | Erie | 113882 | US 20: Chestnut St. - Cumberland Rd. | 20 | 29M | Highway Restoration | PE | HVRU | 2026-05-21 |  | 86000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86000
Erie | 1 | Erie | 113882 | US 20: Chestnut St. - Cumberland Rd. | 20 | 29M | Highway Restoration | CON | HVRU | 2026-05-21 |  | 1004000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1004000
Erie | 1 | Erie | 113882 | US 20: Chestnut St. - Cumberland Rd. | 20 | 29M | Highway Restoration | CON | NHPP | 2026-05-21 |  | 0 | 733000 | 1006000 | 921271 | 0 | 0 | 0 | 0 | 0 | 2660271
Erie | 1 | Erie | 114480 | Norfolk Southern Erie County Circuitry Upgrade | 1017 | 0 | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 790713 | 672920 | 1779507 | 756860 | 0 | 0 | 0 | 0 | 4000000
Erie | 1 | Erie | 116144 | Sassafras St Ext Ped Bridge | 4034 | P02 | Bicycle Pedestrian Highway | PE | 581 | 2027-01-01 |  | 378012 | 17988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396000
Erie | 1 | Erie | 116161 | Erie 2025 RPM |  |  | Safety Improvement | CON | STP | 2025-03-13 | 2025-03-13 | 131889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131889
Erie | 1 | Erie | 116162 | Erie 2026 RPM |  |  | Safety Improvement | CON | STP | 2026-03-12 | 2026-03-12 | 0 | 100337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100337
Erie | 1 | Erie | 116638 | I-79 Erie County ITS Addition - Interchange - TSMO | 4012 | TS1 | Intelligent Transportation System | CON | STP | 2023-11-02 | 2023-11-02 | 79625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79625
Erie | 1 | Erie | 116639 | I-90 Erie County ITS Addition - SR 19 - TSMO | 19 | TS2 | Intelligent Transportation System | CON | STP | 2023-09-14 | 2023-11-02 | 79625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79625
Erie | 1 | Erie | 116737 | SR 3004: Bridge over Conneaut Creek | 3004 | B01 | Bridge Replacement | PE | 185 |  |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Erie | 1 | Erie | 116737 | SR 3004: Bridge over Conneaut Creek | 3004 | B01 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 66200 | 0 | 0 | 0 | 0 | 0 | 0 | 66200
Erie | 1 | Erie | 116740 | SR 832: Brdg/I-90 | 832 | B05 | Bridge Replacement | PE | BRIP | 2030-01-01 |  | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
Erie | 1 | Erie | 116740 | SR 832: Brdg/I-90 | 832 | B05 | Bridge Replacement | ROW | 185 | 2030-01-01 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Erie | 1 | Erie | 116740 | SR 832: Brdg/I-90 | 832 | B05 | Bridge Replacement | CON | BRIP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 429800 | 690600 | 2010252 | 869348 | 0 | 4000000
Erie | 1 | Erie | 116740 | SR 832: Brdg/I-90 | 832 | B05 | Bridge Replacement | CON | 185 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 107450 | 293000 | 382213 | 217337 | 0 | 1000000
Erie | 1 | Erie | 116741 | SR 5 over Sixmile Creek | 5 | B21 | Bridge Replacement | FD | 185 | 2026-05-21 |  | 91568 | 208432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Erie | 1 | Erie | 116741 | SR 5 over Sixmile Creek | 5 | B21 | Bridge Replacement | ROW | 185 | 2026-05-21 |  | 25000 | 10090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35090
Erie | 1 | Erie | 116741 | SR 5 over Sixmile Creek | 5 | B21 | Bridge Replacement | CON | BRIP | 2026-05-21 |  | 0 | 1405206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1405206
Erie | 1 | Erie | 116813 | SR 4010: Hershey Road | 4010 | 01M | Highway Restoration | PE | 185 | 2029-01-01 |  | 0 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325000
Erie | 1 | Erie | 116813 | SR 4010: Hershey Road | 4010 | 01M | Highway Restoration | PE | 581 | 2029-01-01 |  | 0 | 180776 | 144224 | 0 | 0 | 0 | 0 | 0 | 0 | 325000
Erie | 1 | Erie | 116813 | SR 4010: Hershey Road | 4010 | 01M | Highway Restoration | CON | BRIP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 1018600 | 1981400 | 0 | 0 | 0 | 3000000
Erie | 1 | Erie | 116813 | SR 4010: Hershey Road | 4010 | 01M | Highway Restoration | CON | STP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 3009000 | 91000 | 0 | 0 | 0 | 3100000
Erie | 1 | Erie | 116814 | SR 832: SR 98 to Segment 110 | 832 | 07M | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 833707 | 3078534 | 0 | 3912241
Erie | 1 | Erie | 116815 | SR 4016: US 19 to SR 197 | 4016 | 05M | Highway Restoration | CON | NHPP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 304546 | 1695454 | 0 | 2000000
Erie | 1 | Erie | 116816 | SR 4028: Gore Road | 4028 | 02M | Highway Restoration | PE | STP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
Erie | 1 | Erie | 116816 | SR 4028: Gore Road | 4028 | 02M | Highway Restoration | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308954 | 467046 | 1776000
Erie | 1 | Erie | 117438 | US 6: Crawford County Line to SR 3006 | 6 | 12M | Highway Restoration | PE | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Erie | 1 | Erie | 117438 | US 6: Crawford County Line to SR 3006 | 6 | 12M | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 1900000
Erie | 1 | Erie | 117481 | SR 5: Pittsburgh Ave to Parade St | 5 | 27M | Highway Restoration | PE | NHPP | 2027-01-01 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Erie | 1 | Erie | 117481 | SR 5: Pittsburgh Ave to Parade St | 5 | 27M | Highway Restoration | CON | NHPP | 2027-01-01 |  | 0 | 0 | 1350000 | 771729 | 0 | 700000 | 0 | 0 | 0 | 2821729
Erie | 1 | Erie | 117486 | SR 290 Structure - Waterproofing | 290 | B05 | Bridge Restoration | FD | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
Erie | 1 | Erie | 117486 | SR 290 Structure - Waterproofing | 290 | B05 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2507652 | 2507652
Erie | 1 | Erie | 117538 | US 6: Mill Village to Old Meadville Rd | 6 | 295 | 409 Expanded Maintenance | PE | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 135000
Erie | 1 | Erie | 117538 | US 6: Mill Village to Old Meadville Rd | 6 | 295 | 409 Expanded Maintenance | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2844475 | 2844475
Erie | 1 | Erie | 117639 | US 6 (SR 3006): I-79 to Edinboro | 3006 | 254 | General Maintenance | CON | NHPP | 2025-04-10 | 2025-04-10 | 0 | 0 | 0 | 0 | 0 | 255729 | 2962454 | 0 | 0 | 3218183
Erie | 1 | Erie | 117639 | US 6 (SR 3006): I-79 to Edinboro | 3006 | 254 | General Maintenance | CON | 581 | 2025-04-10 | 2025-04-10 | 0 | 0 | 0 | 0 | 0 | 63932 | 740614 | 0 | 0 | 804546
Erie | 1 | Erie | 117697 | SR 5 Brdg over Crooked Creek - Scour Group | 5 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Erie | 1 | Erie | 117697 | SR 5 Brdg over Crooked Creek - Scour Group | 5 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Erie | 1 | Erie | 117697 | SR 5 Brdg over Crooked Creek - Scour Group | 5 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
Erie | 1 | Erie | 118365 | Edinboro TASA Project 2022 | 3006 | T01 | General Maintenance | CON | TAP | 2024-12-12 | 2024-12-12 | 756748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 756748
Erie | 1 | Erie | 118747 | SR 4034 (Bayfront Parkway) and Cranberry St. Int. | 4034 | S01 | Congestion Reduction | CON | HVRU | 2023-12-07 | 2023-12-07 | 151813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151813
Erie | 1 | Erie | 118747 | SR 4034 (Bayfront Parkway) and Cranberry St. Int. | 4034 | S01 | Congestion Reduction | CON | NHPP | 2023-12-07 | 2023-12-07 | 151813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151813
Erie | 1 | Erie | 119713 | Erie 2027 RPM |  |  | Safety Improvement | CON | STP | 2027-02-25 |  | 0 | 0 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 95000
Erie | 1 | Erie | 119714 | Erie 2028 RPM |  |  | Safety Improvement | CON | STP | 2028-01-01 |  | 0 | 0 | 0 | 95000 | 0 | 0 | 0 | 0 | 0 | 95000
Erie | 1 | Erie | 120126 | Erie On Demand Bridge Project - 2025 |  |  | Bridge Preservation - State Funded | CON | 185 | 2024-10-24 | 2024-10-24 | 200000 | 109389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309389
Erie | 1 | Erie | 120516 | Edinboro Sidewalk Improvements | 699 | MTF | MultiModal | CON | 407 |  |  | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
Erie | 1 | Erie | 120516 | Edinboro Sidewalk Improvements | 699 | MTF | MultiModal | CON | LOC |  |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Erie | 1 | Erie | 120537 | City of Erie State Street Multimodal Improvements |  | MTF | MultiModal | CON | 411 | 2026-09-17 |  | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455000
Erie | 1 | Erie | 120537 | City of Erie State Street Multimodal Improvements |  | MTF | MultiModal | CON | LOC | 2026-09-17 |  | 195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000
Erie | 1 | Erie | 120693 | SR 1001: Brdg/Lake Pleasant Outlet | 1001 | B00 | Bridge Preservation - Federal | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Erie | 1 | Erie | 120693 | SR 1001: Brdg/Lake Pleasant Outlet | 1001 | B00 | Bridge Preservation - Federal | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Erie | 1 | Erie | 120694 | US 6: Brdg/Darrows Creek | 3006 | B00 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Erie | 1 | Erie | 120694 | US 6: Brdg/Darrows Creek | 3006 | B00 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792648 | 607352 | 1400000
Erie | 1 | Erie | 120696 | SR 5 over Cascade Creek | 5 | B22 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Erie | 1 | Erie | 120696 | SR 5 over Cascade Creek | 5 | B22 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
Erie | 1 | Erie | 121182 | SR 5 and Hardscrabble Blvd - VRU | 5 | VU1 | Safety Improvement | CON | HVRU | 2025-06-26 | 2025-06-26 | 143717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143717
Erie | 1 | Erie | 121312 | I-90 WB Erie Co ITS Addition at SR 98 - TSMO | 90 | TS3 | Intelligent Transportation System | CON | CRP | 2025-03-27 | 2025-03-27 | 316867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316867
Erie | 1 | Erie | 121312 | I-90 WB Erie Co ITS Addition at SR 98 - TSMO | 90 | TS3 | Intelligent Transportation System | CON | 581 | 2025-03-27 | 2025-03-27 | 79217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79217
Erie | 1 | Erie | 121313 | I-90 EB Erie Co ITS Addition at SR 89 - TSMO | 90 | TS4 | Intelligent Transportation System | CON | CRP | 2025-03-27 | 2025-03-27 | 316867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316867
Erie | 1 | Erie | 121313 | I-90 EB Erie Co ITS Addition at SR 89 - TSMO | 90 | TS4 | Intelligent Transportation System | CON | 581 | 2025-03-27 | 2025-03-27 | 79217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79217
Erie | 1 | Erie | 121506 | City of Erie Safe Routes to Parks and Schools |  | T01 | Federal Safe Routes to Schools | CON | SRTSF | 2026-08-13 |  | 0 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
Erie | 1 | Erie | 121655 | Port Access Road - LFAR 2023-2024 |  | F10 | General Maintenance | CON | STP | 2026-06-04 |  | 0 | 128459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128459
Erie | 1 | Erie | 121699 | City of Erie LFAR - 2025-2026 |  | F11 | Highway Restoration | CON | STP | 2025-06-26 | 2025-06-26 | 312931 | 202029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514960
Erie | 1 | Erie | 121701 | Millcreek Township LFAR - 2025-2026 |  | F12 | Highway Restoration | CON | STP | 2025-06-05 | 2025-06-05 | 94029 | 94029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188058
Erie | 1 | Erie | 122158 | SR 7214: Brickyard Rd Br (Act-13) | 7214 | ACT | Bridge Replacement | PE | ACT13 |  |  | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000
Erie | 1 | Erie | 122158 | SR 7214: Brickyard Rd Br (Act-13) | 7214 | ACT | Bridge Replacement | PE | LOC |  |  | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000
Erie | 1 | Erie | 122158 | SR 7214: Brickyard Rd Br (Act-13) | 7214 | ACT | Bridge Replacement | CON | ACT13 |  |  | 224000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224000
Erie | 1 | Erie | 122158 | SR 7214: Brickyard Rd Br (Act-13) | 7214 | ACT | Bridge Replacement | CON | LOC |  |  | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96000
Erie | 1 | Erie | 122345 | Dept. Force Br. Erie |  |  | Bridge Preservation - State Funded | CON | 185 |  |  | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Erie | 1 | Erie | 122543 | Euclid Boulevard - LFAR 2025 |  | F13 | Highway Restoration | CON | STP |  |  | 0 | 619734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 619734
Erie | 1 | Erie | 122668 | Donlin Rd Culvert (Act13) |  |  | Bridge Preservation - State Funded | CON | ACT13 |  |  | 59500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59500
Erie | 1 | Erie | 122668 | Donlin Rd Culvert (Act13) |  |  | Bridge Preservation - State Funded | CON | LOC |  |  | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25500
Erie | 1 | Erie | 122999 | Erie Co. Interstate Ramps Systemic | 8170 | S01 | Safety Improvement | PE | HSIP | 2026-08-13 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Erie | 1 | Erie | 122999 | Erie Co. Interstate Ramps Systemic | 8170 | S01 | Safety Improvement | CON | HSIP | 2026-08-13 |  | 0 | 261000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261000
Erie | 1 | Erie | 123183 | SR 426 over Sixteen Mile CK BR - Sediment Removal | 426 | BSR | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Erie | 1 | Erie | 123183 | SR 426 over Sixteen Mile CK BR - Sediment Removal | 426 | BSR | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Erie | 1 | Erie | 123183 | SR 426 over Sixteen Mile CK BR - Sediment Removal | 426 | BSR | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Erie | 1 | Erie | 123230 | US 20 Bridge over Eight Mile Creek - Scour Group | 20 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Erie | 1 | Erie | 123230 | US 20 Bridge over Eight Mile Creek - Scour Group | 20 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Erie | 1 | Erie | 123231 | US 20 Bridge over Trout Run - Scour Group | 20 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Erie | 1 | Erie | 123231 | US 20 Bridge over Trout Run - Scour Group | 20 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Erie | 1 | Erie | 123232 | SR 699 Bridge over Elk Creek - Scour Group | 699 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Erie | 1 | Erie | 123232 | SR 699 Bridge over Elk Creek - Scour Group | 699 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
Erie | 1 | Erie | 123573 | Erie Local Bridge Bundle Preservation - 2028 | 7206 | BBP | Bridge Preservation - Federal | PE | BOF | 2028-01-01 |  | 0 | 235000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235000
Erie | 1 | Erie | 123573 | Erie Local Bridge Bundle Preservation - 2028 | 7206 | BBP | Bridge Preservation - Federal | FD | BOF | 2028-01-01 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Erie | 1 | Erie | 123573 | Erie Local Bridge Bundle Preservation - 2028 | 7206 | BBP | Bridge Preservation - Federal | FD | BRIP | 2028-01-01 |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Erie | 1 | Erie | 123573 | Erie Local Bridge Bundle Preservation - 2028 | 7206 | BBP | Bridge Preservation - Federal | CON | BOF | 2028-01-01 |  | 0 | 0 | 1170000 | 475000 | 375000 | 0 | 0 | 0 | 0 | 2020000
Erie | 1 | Erie | 123573 | Erie Local Bridge Bundle Preservation - 2028 | 7206 | BBP | Bridge Preservation - Federal | CON | BRIP | 2028-01-01 |  | 0 | 0 | 175000 | 250000 | 0 | 0 | 0 | 0 | 0 | 425000
Erie | 1 | Erie | 123706 | State Route 4007 over Walnut Creek | 4007 | B03 | Bridge Replacement | PE | BRIP |  |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Erie | 1 | Erie | 123837 | West Fourth Street Bridge Replacement (Act-13) | 7414 | ACT | Bridge Replacement | PE | ACT13 |  |  | 0 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24500
Erie | 1 | Erie | 123837 | West Fourth Street Bridge Replacement (Act-13) | 7414 | ACT | Bridge Replacement | PE | LOC |  |  | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500
Erie | 1 | Erie | 123837 | West Fourth Street Bridge Replacement (Act-13) | 7414 | ACT | Bridge Replacement | CON | ACT13 |  |  | 0 | 225500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225500
Erie | 1 | Erie | 123837 | West Fourth Street Bridge Replacement (Act-13) | 7414 | ACT | Bridge Replacement | CON | LOC |  |  | 0 | 144500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144500
Erie | 1 | Erie | 123958 | SR 2022 over Baskin Run | 2022 | B01 | Bridge Replacement | PE | BOF |  |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Franklin | 8 | Franklin | 19304 | West King Street Bridge | 11 | 095 | Bridge Replacement | CON | BRIP | 2024-10-24 | 2024-10-24 | 891219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 891219
Franklin | 8 | Franklin | 19304 | West King Street Bridge | 11 | 095 | Bridge Replacement | CON | NHPP | 2024-10-24 | 2024-10-24 | 891220 | 891220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1782440
Franklin | 8 | Franklin | 19304 | West King Street Bridge | 11 | 095 | Bridge Replacement | CON | STP | 2024-10-24 | 2024-10-24 | 604000 | 435350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1039350
Franklin | 8 | Franklin | 19304 | West King Street Bridge | 11 | 095 | Bridge Replacement | CON | 185 | 2024-10-24 | 2024-10-24 | 445610 | 387658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833268
Franklin | 8 | Franklin | 19304 | West King Street Bridge | 11 | 095 | Bridge Replacement | CON | 581 | 2024-10-24 | 2024-10-24 | 0 | 57952 | 445609 | 0 | 0 | 0 | 0 | 0 | 0 | 503561
Franklin | 8 | Franklin | 63174 | Stone Bridge Road Bridge | 4006 | 007 | Bridge Replacement | PE | STP | 2030-06-06 |  | 0 | 328000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328000
Franklin | 8 | Franklin | 63174 | Stone Bridge Road Bridge | 4006 | 007 | Bridge Replacement | FD | STP | 2030-06-06 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Franklin | 8 | Franklin | 63174 | Stone Bridge Road Bridge | 4006 | 007 | Bridge Replacement | ROW | STP | 2030-06-06 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Franklin | 8 | Franklin | 63174 | Stone Bridge Road Bridge | 4006 | 007 | Bridge Replacement | UTL | STP | 2030-06-06 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Franklin | 8 | Franklin | 63174 | Stone Bridge Road Bridge | 4006 | 007 | Bridge Replacement | CON | BOF | 2030-06-06 |  | 0 | 0 | 0 | 0 | 0 | 121293 | 914239 | 1754000 | 3150468 | 5940000
Franklin | 8 | Franklin | 78690 | Fort Loudon Rd ov Buck Run | 75 | 013 | Bridge Restoration | PE | BRIP | 2027-09-16 |  | 26046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26046
Franklin | 8 | Franklin | 78690 | Fort Loudon Rd ov Buck Run | 75 | 013 | Bridge Restoration | FD | 185 | 2027-09-16 |  | 230000 | 87238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317238
Franklin | 8 | Franklin | 78690 | Fort Loudon Rd ov Buck Run | 75 | 013 | Bridge Restoration | ROW | BRIP | 2027-09-16 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Franklin | 8 | Franklin | 78690 | Fort Loudon Rd ov Buck Run | 75 | 013 | Bridge Restoration | UTL | BRIP | 2027-09-16 |  | 21685 | 58315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Franklin | 8 | Franklin | 78690 | Fort Loudon Rd ov Buck Run | 75 | 013 | Bridge Restoration | CON | 185 | 2027-09-16 |  | 0 | 0 | 0 | 380987 | 0 | 0 | 0 | 0 | 0 | 380987
Franklin | 8 | Franklin | 78690 | Fort Loudon Rd ov Buck Run | 75 | 013 | Bridge Restoration | CON | 581 | 2027-09-16 |  | 0 | 0 | 1237013 | 0 | 0 | 0 | 0 | 0 | 0 | 1237013
Franklin | 8 | Franklin | 78692 | SR 641 O/Trout Run | 641 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Franklin | 8 | Franklin | 78692 | SR 641 O/Trout Run | 641 | 0 | Bridge Preservation - Federal | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 195364 | 0 | 0 | 0 | 195364
Franklin | 8 | Franklin | 78692 | SR 641 O/Trout Run | 641 | 0 | Bridge Preservation - Federal | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 162852 | 0 | 0 | 162852
Franklin | 8 | Franklin | 78699 | Lemar Road Bridge | 3007 | 017 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123000 | 123000
Franklin | 8 | Franklin | 87804 | Franklin Bridge Reserve |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 0 | 2002532 | 3192532
Franklin | 8 | Franklin | 87804 | Franklin Bridge Reserve |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 0 | 370084 | 23282 | 0 | 102147 | 1562000 | 6248000 | 8305513
Franklin | 8 | Franklin | 87804 | Franklin Bridge Reserve |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1482000 | 871000 | 4451000 | 6804000
Franklin | 8 | Franklin | 87805 | Highway Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 843439 | 0 | 0 | 0 | 0 | 8000 | 8512000 | 9363439
Franklin | 8 | Franklin | 87805 | Highway Reserve |  |  | Reserve Line Item | CON | STP |  |  | 0 | 20564 | 868900 | 1364278 | 1680564 | 2858000 | 1528000 | 2858000 | 7970000 | 19148306
Franklin | 8 | Franklin | 87805 | Highway Reserve |  |  | Reserve Line Item | CON | 581 |  |  | 14645 | 0 | 2182029 | 3561218 | 2799926 | 1000000 | 1267774 | 681543 | 1045000 | 12552135
Franklin | 8 | Franklin | 87810 | Delivery/Consult Assist |  |  | Reserve Line Item | PE | 185 |  |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Franklin | 8 | Franklin | 87810 | Delivery/Consult Assist |  |  | Reserve Line Item | PE | 581 |  |  | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Franklin | 8 | Franklin | 87810 | Delivery/Consult Assist |  |  | Reserve Line Item | CON | 581 |  |  | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Franklin | 8 | Franklin | 87816 | HSIP Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 595889 | 1301000 | 5205000 | 7101889
Franklin | 8 | Franklin | 88666 | SRTP Rideshare Program |  |  | Reserve Line Item | PE | STP |  |  | 0 | 107365 | 97767 | 98745 | 0 | 0 | 0 | 0 | 0 | 303877
Franklin | 8 | Franklin | 90839 | Rocky Mountain Creek Br | 30 | 103 | Bridge Replacement | CON | NHPP | 2026-05-07 |  | 2000000 | 3585977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5585977
Franklin | 8 | Franklin | 90845 | Little Antietam Creek | 233 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Franklin | 8 | Franklin | 90847 | Rocky Mtn Rd ov W Branch Antietam Creek | 233 | 023 | Bridge Replacement | PE | 185 |  |  | 20416 | 41397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61813
Franklin | 8 | Franklin | 90847 | Rocky Mtn Rd ov W Branch Antietam Creek | 233 | 023 | Bridge Replacement | FD | 185 |  |  | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000
Franklin | 8 | Franklin | 90969 | Social Island Road Bridge-C | 3012 | 027 | Bridge Replacement | PE | BOF | 2028-04-06 |  | 0 | 340000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340000
Franklin | 8 | Franklin | 90969 | Social Island Road Bridge-C | 3012 | 027 | Bridge Replacement | PE | STP | 2028-04-06 |  | 0 | 13039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13039
Franklin | 8 | Franklin | 90969 | Social Island Road Bridge-C | 3012 | 027 | Bridge Replacement | FD | PRTCT | 2028-04-06 |  | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
Franklin | 8 | Franklin | 90969 | Social Island Road Bridge-C | 3012 | 027 | Bridge Replacement | ROW | PRTCT | 2028-04-06 |  | 0 | 109000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109000
Franklin | 8 | Franklin | 90969 | Social Island Road Bridge-C | 3012 | 027 | Bridge Replacement | UTL | PRTCT | 2028-04-06 |  | 0 | 109000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109000
Franklin | 8 | Franklin | 90969 | Social Island Road Bridge-C | 3012 | 027 | Bridge Replacement | CON | BOF | 2028-04-06 |  | 0 | 0 | 295550 | 565530 | 0 | 0 | 0 | 0 | 0 | 861080
Franklin | 8 | Franklin | 90969 | Social Island Road Bridge-C | 3012 | 027 | Bridge Replacement | CON | STP | 2028-04-06 |  | 0 | 0 | 572218 | 302237 | 0 | 0 | 0 | 0 | 0 | 874455
Franklin | 8 | Franklin | 90995 | Fort Loudon Rd Resurf 2 | 75 | 014 | 409 Expanded Maintenance | PE | 581 | 2025-06-26 | 2025-06-26 | 39155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39155
Franklin | 8 | Franklin | 90995 | Fort Loudon Rd Resurf 2 | 75 | 014 | 409 Expanded Maintenance | FD | 581 | 2025-06-26 | 2025-06-26 | 187971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187971
Franklin | 8 | Franklin | 90995 | Fort Loudon Rd Resurf 2 | 75 | 014 | 409 Expanded Maintenance | ROW | 581 | 2025-06-26 | 2025-06-26 | 33700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33700
Franklin | 8 | Franklin | 90995 | Fort Loudon Rd Resurf 2 | 75 | 014 | 409 Expanded Maintenance | UTL | 581 | 2025-06-26 | 2025-06-26 | 94535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94535
Franklin | 8 | Franklin | 91340 | Williamsport Pike Bridge | 3001 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 91343 | Social Island Road Bridge 2-C | 3012 | 034 | Bridge Replacement | CON | 185 | 2028-04-06 |  | 0 | 0 | 340812 | 478013 | 0 | 0 | 0 | 0 | 0 | 818825
Franklin | 8 | Franklin | 91343 | Social Island Road Bridge 2-C | 3012 | 034 | Bridge Replacement | CON | 581 | 2028-04-06 |  | 0 | 0 | 0 | 129970 | 0 | 0 | 0 | 0 | 0 | 129970
Franklin | 8 | Franklin | 93055 | I-81 New Interchange (Exit 12) | 81 | 075 | Highway Reconstruction | FD | STP | 2026-05-21 |  | 261465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261465
Franklin | 8 | Franklin | 93055 | I-81 New Interchange (Exit 12) | 81 | 075 | Highway Reconstruction | UTL | BRIP | 2026-05-21 |  | 323050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 323050
Franklin | 8 | Franklin | 93055 | I-81 New Interchange (Exit 12) | 81 | 075 | Highway Reconstruction | UTL | NHPP | 2026-05-21 |  | 878780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 878780
Franklin | 8 | Franklin | 93055 | I-81 New Interchange (Exit 12) | 81 | 075 | Highway Reconstruction | UTL | STP | 2026-05-21 |  | 1323362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1323362
Franklin | 8 | Franklin | 93055 | I-81 New Interchange (Exit 12) | 81 | 075 | Highway Reconstruction | UTL | 185 | 2026-05-21 |  | 738974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738974
Franklin | 8 | Franklin | 93055 | I-81 New Interchange (Exit 12) | 81 | 075 | Highway Reconstruction | UTL | 581 | 2026-05-21 |  | 297235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297235
Franklin | 8 | Franklin | 93055 | I-81 New Interchange (Exit 12) | 81 | 075 | Highway Reconstruction | CON | NHPP | 2026-05-21 |  | 0 | 0 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 20000000
Franklin | 8 | Franklin | 93055 | I-81 New Interchange (Exit 12) | 81 | 075 | Highway Reconstruction | CON | BRIP | 2026-05-21 |  | 0 | 0 | 0 | 0 | 0 | 1562000 | 1459853 | 0 | 0 | 3021853
Franklin | 8 | Franklin | 93055 | I-81 New Interchange (Exit 12) | 81 | 075 | Highway Reconstruction | CON | NHPP | 2026-05-21 |  | 0 | 780780 | 636561 | 1338000 | 1338000 | 1338000 | 1338000 | 0 | 0 | 6769341
Franklin | 8 | Franklin | 93055 | I-81 New Interchange (Exit 12) | 81 | 075 | Highway Reconstruction | CON | STP | 2026-05-21 |  | 0 | 6397 | 0 | 0 | 444150 | 0 | 0 | 0 | 0 | 450547
Franklin | 8 | Franklin | 93055 | I-81 New Interchange (Exit 12) | 81 | 075 | Highway Reconstruction | CON | 185 | 2026-05-21 |  | 0 | 168292 | 0 | 0 | 513872 | 776663 | 170000 | 0 | 0 | 1628827
Franklin | 8 | Franklin | 93055 | I-81 New Interchange (Exit 12) | 81 | 075 | Highway Reconstruction | CON | 581 | 2026-05-21 |  | 1932021 | 3744048 | 0 | 0 | 2639074 | 1935000 | 1160374 | 0 | 0 | 11410517
Franklin | 8 | Franklin | 95662 | I-81/Buchanan Trail Impr | 16 | 041 | Safety Improvement | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
Franklin | 8 | Franklin | 97964 | Path Valley Rd Resurf #3 | 75 | 010 | 409 Expanded Maintenance | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1083000 | 747000 | 0 | 0 | 1830000
Franklin | 8 | Franklin | 99929 | Amberson Road Bridge2 | 4005 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 99938 | Amberson Road Bridge 3 | 4005 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 99964 | Bear Valley Rd/ Broad Run | 4001 | 0 | Bridge Preservation - Federal | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 99967 | Bino Road Bridge PM | 3004 | 0 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 100012 | PA16 Bridge PM 1 | 16 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 100023 | PA16 over Red Run 1 | 16 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 100027 | PA16 over Red Run 2 | 16 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 100042 | Leitersburg RD/ Marsh Run | 2002 | 0 | Bridge Replacement | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 100138 | Paxton Run Rd Bridge 1 | 4018 | 0 | Bridge Preservation - Federal | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 100143 | Paxton Run Road Bridge 2 | 4018 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 100169 | PA316/trib to W Antietam | 316 | 0 | Bridge Replacement | PE | 581 |  |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
Franklin | 8 | Franklin | 100169 | PA316/trib to W Antietam | 316 | 0 | Bridge Replacement | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1324272 | 0 | 1324272
Franklin | 8 | Franklin | 100245 | Mill Road over Carters Cr | 3026 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 100249 | Mount Pleasant Rd Bridge | 1001 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 100256 | Newburg Road/Laughlin Run | 641 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 100261 | Oregon St ov Steigers Run | 3009 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 101401 | South Fayette Road Bridge | 696 | 015 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Franklin | 8 | Franklin | 101402 | Spring Run Road Bridge PM | 641 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Franklin | 8 | Franklin | 101404 | Welsh Run Rd over Welsh Run | 995 | 009 | Bridge Restoration | FD | BOF | 2026-09-17 |  | 230000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Franklin | 8 | Franklin | 101404 | Welsh Run Rd over Welsh Run | 995 | 009 | Bridge Restoration | ROW | BOF | 2026-09-17 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Franklin | 8 | Franklin | 101404 | Welsh Run Rd over Welsh Run | 995 | 009 | Bridge Restoration | UTL | BOF | 2026-09-17 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Franklin | 8 | Franklin | 101404 | Welsh Run Rd over Welsh Run | 995 | 009 | Bridge Restoration | CON | BOF | 2026-09-17 |  | 0 | 287889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287889
Franklin | 8 | Franklin | 101404 | Welsh Run Rd over Welsh Run | 995 | 009 | Bridge Restoration | CON | STP | 2026-09-17 |  | 0 | 994111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994111
Franklin | 8 | Franklin | 102974 | South Third St Crossing |  | RRX | Rail Highway Grade Crossing | CON | 581 |  |  | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
Franklin | 8 | Franklin | 106709 | PA997 & SR2015 Intersection | 997 | 037 | Safety Improvement | CON | HSIP | 2025-01-16 | 2025-01-16 | 1271000 | 1301000 | 1301000 | 449383 | 0 | 0 | 0 | 0 | 0 | 4322383
Franklin | 8 | Franklin | 106709 | PA997 & SR2015 Intersection | 997 | 037 | Safety Improvement | CON | STP | 2025-01-16 | 2025-01-16 | 2939373 | 101350 | 145800 | 0 | 0 | 0 | 0 | 0 | 0 | 3186523
Franklin | 8 | Franklin | 111394 | Waynesboro Ped Safety Project | 16 | TAP | Transportation Enhancement | CON | TAP | 2022-02-17 | 2022-02-17 | 29121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29121
Franklin | 8 | Franklin | 113339 | Rocky Mtn Road Resurface | 233 | 0 | 409 Expanded Maintenance | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1421000 | 1500000 | 0 | 0 | 2921000
Franklin | 8 | Franklin | 114555 | Lincoln Way Intersection Safety Imp | 30 | 150 | Safety Improvement | PE | STP | 2028-02-17 |  | 538401 | 270036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808437
Franklin | 8 | Franklin | 114555 | Lincoln Way Intersection Safety Imp | 30 | 150 | Safety Improvement | FD | STP | 2028-02-17 |  | 0 | 292000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292000
Franklin | 8 | Franklin | 114555 | Lincoln Way Intersection Safety Imp | 30 | 150 | Safety Improvement | ROW | STP | 2028-02-17 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Franklin | 8 | Franklin | 114555 | Lincoln Way Intersection Safety Imp | 30 | 150 | Safety Improvement | UTL | STP | 2028-02-17 |  | 0 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000
Franklin | 8 | Franklin | 114555 | Lincoln Way Intersection Safety Imp | 30 | 150 | Safety Improvement | CON | HSIP | 2028-02-17 |  | 0 | 0 | 0 | 851617 | 1301000 | 1301000 | 705111 | 0 | 0 | 4158728
Franklin | 8 | Franklin | 116075 | Lincoln Way Resurface | 30 | 0 | Highway Restoration | CON | NHPP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1330000 | 0 | 1330000
Franklin | 8 | Franklin | 116075 | Lincoln Way Resurface | 30 | 0 | Highway Restoration | CON | STP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1330000 | 0 | 0 | 1330000
Franklin | 8 | Franklin | 116077 | Lincoln Way Resurface 3 | 30 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700000 | 3700000
Franklin | 8 | Franklin | 116146 | Chambersburg Signals Imp Phase 2 | 11 | 125 | Air Quality | FD | CRP | 2025-07-10 | 2025-07-10 | 169940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169940
Franklin | 8 | Franklin | 116146 | Chambersburg Signals Imp Phase 2 | 11 | 125 | Air Quality | CON | CRP | 2025-07-10 | 2025-07-10 | 322839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322839
Franklin | 8 | Franklin | 116146 | Chambersburg Signals Imp Phase 2 | 11 | 125 | Air Quality | CON | CRPU | 2025-07-10 | 2025-07-10 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000
Franklin | 8 | Franklin | 116962 | Rockdale Rd ov Trib to Back Cr | 3017 | 035 | Bridge Replacement | FD | 185 | 2027-04-08 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Franklin | 8 | Franklin | 116962 | Rockdale Rd ov Trib to Back Cr | 3017 | 035 | Bridge Replacement | ROW | 581 | 2027-04-08 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Franklin | 8 | Franklin | 116962 | Rockdale Rd ov Trib to Back Cr | 3017 | 035 | Bridge Replacement | UTL | 581 | 2027-04-08 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Franklin | 8 | Franklin | 116962 | Rockdale Rd ov Trib to Back Cr | 3017 | 035 | Bridge Replacement | CON | 185 | 2027-04-08 |  | 0 | 0 | 777162 | 0 | 0 | 0 | 0 | 0 | 0 | 777162
Franklin | 8 | Franklin | 116963 | Corner Road over Licking Cr | 3009 | 022 | Bridge Restoration | FD | BOF | 2026-11-05 |  | 304000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304000
Franklin | 8 | Franklin | 116963 | Corner Road over Licking Cr | 3009 | 022 | Bridge Restoration | ROW | BOF | 2026-11-05 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Franklin | 8 | Franklin | 116963 | Corner Road over Licking Cr | 3009 | 022 | Bridge Restoration | CON | BRIP | 2026-11-05 |  | 0 | 659685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 659685
Franklin | 8 | Franklin | 116963 | Corner Road over Licking Cr | 3009 | 022 | Bridge Restoration | CON | STP | 2026-11-05 |  | 0 | 0 | 734315 | 0 | 0 | 0 | 0 | 0 | 0 | 734315
Franklin | 8 | Franklin | 117071 | West King St over Falling Spring Ck | 7401 | BRG | Bridge Replacement | FD | BOF | 2027-10-07 |  | 0 | 118927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118927
Franklin | 8 | Franklin | 117071 | West King St over Falling Spring Ck | 7401 | BRG | Bridge Replacement | FD | BRIP | 2027-10-07 |  | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275000
Franklin | 8 | Franklin | 117071 | West King St over Falling Spring Ck | 7401 | BRG | Bridge Replacement | ROW | BOF | 2027-10-07 |  | 0 | 45020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45020
Franklin | 8 | Franklin | 117071 | West King St over Falling Spring Ck | 7401 | BRG | Bridge Replacement | UTL | BOF | 2027-10-07 |  | 0 | 33765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33765
Franklin | 8 | Franklin | 117071 | West King St over Falling Spring Ck | 7401 | BRG | Bridge Replacement | CON | BOF | 2027-10-07 |  | 0 | 0 | 857000 | 279974 | 438843 | 410836 | 0 | 0 | 0 | 1986653
Franklin | 8 | Franklin | 117071 | West King St over Falling Spring Ck | 7401 | BRG | Bridge Replacement | CON | STP | 2027-10-07 |  | 0 | 0 | 0 | 250000 | 576026 | 0 | 0 | 0 | 0 | 826026
Franklin | 8 | Franklin | 117072 | West King St over Conococheague Ck | 7401 | BR | Bridge Replacement | FD | BOF | 2027-10-07 |  | 0 | 193927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193927
Franklin | 8 | Franklin | 117072 | West King St over Conococheague Ck | 7401 | BR | Bridge Replacement | FD | BRIP | 2027-10-07 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Franklin | 8 | Franklin | 117072 | West King St over Conococheague Ck | 7401 | BR | Bridge Replacement | ROW | BOF | 2027-10-07 |  | 0 | 45020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45020
Franklin | 8 | Franklin | 117072 | West King St over Conococheague Ck | 7401 | BR | Bridge Replacement | UTL | BOF | 2027-10-07 |  | 0 | 39452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39452
Franklin | 8 | Franklin | 117072 | West King St over Conococheague Ck | 7401 | BR | Bridge Replacement | CON | BOF | 2027-10-07 |  | 0 | 0 | 0 | 112496 | 794426 | 0 | 0 | 0 | 0 | 906922
Franklin | 8 | Franklin | 117072 | West King St over Conococheague Ck | 7401 | BR | Bridge Replacement | CON | STP | 2027-10-07 |  | 0 | 0 | 588866 | 842740 | 157260 | 0 | 0 | 0 | 0 | 1588866
Franklin | 8 | Franklin | 117141 | Rolling Rd ov Tributary to Back Ck | 3028 | 007 | Bridge Replacement | FD | 185 | 2027-04-08 |  | 0 | 164543 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 289543
Franklin | 8 | Franklin | 117141 | Rolling Rd ov Tributary to Back Ck | 3028 | 007 | Bridge Replacement | ROW | 581 | 2027-04-08 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Franklin | 8 | Franklin | 117141 | Rolling Rd ov Tributary to Back Ck | 3028 | 007 | Bridge Replacement | UTL | 581 | 2027-04-08 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Franklin | 8 | Franklin | 117141 | Rolling Rd ov Tributary to Back Ck | 3028 | 007 | Bridge Replacement | CON | 185 | 2027-04-08 |  | 0 | 0 | 300000 | 315000 | 209491 | 0 | 0 | 0 | 0 | 824491
Franklin | 8 | Franklin | 117142 | Black Gap Rd ov Mountain Run | 997 | 043 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Franklin | 8 | Franklin | 117142 | Black Gap Rd ov Mountain Run | 997 | 043 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000
Franklin | 8 | Franklin | 117142 | Black Gap Rd ov Mountain Run | 997 | 043 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781000 | 0 | 781000
Franklin | 8 | Franklin | 117143 | Hykes Rd over I-81 | 3014 | 013 | Bridge Restoration | PE | BOF | 2027-03-25 |  | 90167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90167
Franklin | 8 | Franklin | 117143 | Hykes Rd over I-81 | 3014 | 013 | Bridge Restoration | FD | BOF | 2027-03-25 |  | 275000 | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
Franklin | 8 | Franklin | 117143 | Hykes Rd over I-81 | 3014 | 013 | Bridge Restoration | FD | STP | 2027-03-25 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Franklin | 8 | Franklin | 117143 | Hykes Rd over I-81 | 3014 | 013 | Bridge Restoration | ROW | BOF | 2027-03-25 |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Franklin | 8 | Franklin | 117143 | Hykes Rd over I-81 | 3014 | 013 | Bridge Restoration | UTL | BOF | 2027-03-25 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Franklin | 8 | Franklin | 117143 | Hykes Rd over I-81 | 3014 | 013 | Bridge Restoration | CON | BOF | 2027-03-25 |  | 0 | 0 | 12584 | 796000 | 1126368 | 0 | 0 | 0 | 0 | 1934952
Franklin | 8 | Franklin | 117143 | Hykes Rd over I-81 | 3014 | 013 | Bridge Restoration | CON | BRIP | 2027-03-25 |  | 0 | 0 | 1159720 | 1000000 | 1538718 | 0 | 0 | 0 | 0 | 3698438
Franklin | 8 | Franklin | 117144 | US 30 Bridge over W Br Conococheague Creek | 30 | 158 | Bridge Preservation - Federal | FD | 185 | 2026-09-17 |  | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000
Franklin | 8 | Franklin | 117144 | US 30 Bridge over W Br Conococheague Creek | 30 | 158 | Bridge Preservation - Federal | ROW | BRIP | 2026-09-17 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Franklin | 8 | Franklin | 117144 | US 30 Bridge over W Br Conococheague Creek | 30 | 158 | Bridge Preservation - Federal | CON | 185 | 2026-09-17 |  | 0 | 434872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434872
Franklin | 8 | Franklin | 117144 | US 30 Bridge over W Br Conococheague Creek | 30 | 158 | Bridge Preservation - Federal | CON | 581 | 2026-09-17 |  | 0 | 0 | 165128 | 0 | 0 | 0 | 0 | 0 | 0 | 165128
Franklin | 8 | Franklin | 117156 | Swamp Fox Rd over I-81 | 914 | 003 | Bridge Preservation - Federal | PE | BRIP | 2027-03-25 |  | 159000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159000
Franklin | 8 | Franklin | 117156 | Swamp Fox Rd over I-81 | 914 | 003 | Bridge Preservation - Federal | FD | BRIP | 2027-03-25 |  | 141000 | 259000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Franklin | 8 | Franklin | 117156 | Swamp Fox Rd over I-81 | 914 | 003 | Bridge Preservation - Federal | ROW | BRIP | 2027-03-25 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Franklin | 8 | Franklin | 117156 | Swamp Fox Rd over I-81 | 914 | 003 | Bridge Preservation - Federal | UTL | BRIP | 2027-03-25 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Franklin | 8 | Franklin | 117156 | Swamp Fox Rd over I-81 | 914 | 003 | Bridge Preservation - Federal | CON | BRIP | 2027-03-25 |  | 0 | 0 | 402280 | 191916 | 0 | 0 | 0 | 0 | 0 | 594196
Franklin | 8 | Franklin | 117157 | Newburg Road over Paxtons Run | 641 | 037 | Bridge Replacement | FD | BOF | 2027-01-28 |  | 300000 | 28032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328032
Franklin | 8 | Franklin | 117157 | Newburg Road over Paxtons Run | 641 | 037 | Bridge Replacement | FD | STP | 2027-01-28 |  | 0 | 12435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12435
Franklin | 8 | Franklin | 117157 | Newburg Road over Paxtons Run | 641 | 037 | Bridge Replacement | ROW | BOF | 2027-01-28 |  | 38833 | 1167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Franklin | 8 | Franklin | 117157 | Newburg Road over Paxtons Run | 641 | 037 | Bridge Replacement | UTL | BOF | 2027-01-28 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Franklin | 8 | Franklin | 117157 | Newburg Road over Paxtons Run | 641 | 037 | Bridge Replacement | CON | 185 | 2027-01-28 |  | 0 | 0 | 105026 | 300000 | 0 | 0 | 0 | 0 | 0 | 405026
Franklin | 8 | Franklin | 117157 | Newburg Road over Paxtons Run | 641 | 037 | Bridge Replacement | CON | 581 | 2027-01-28 |  | 0 | 0 | 541221 | 698812 | 0 | 0 | 0 | 0 | 0 | 1240033
Franklin | 8 | Franklin | 118004 | Cornertown Rd over Conococheague Creek | 7203 | BRG | Bridge Replacement | PE | BOF |  |  | 361000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361000
Franklin | 8 | Franklin | 118004 | Cornertown Rd over Conococheague Creek | 7203 | BRG | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000
Franklin | 8 | Franklin | 118004 | Cornertown Rd over Conococheague Creek | 7203 | BRG | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 62000 | 0 | 0 | 0 | 0 | 62000
Franklin | 8 | Franklin | 118004 | Cornertown Rd over Conococheague Creek | 7203 | BRG | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 13000
Franklin | 8 | Franklin | 118004 | Cornertown Rd over Conococheague Creek | 7203 | BRG | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 1171871 | 839761 | 0 | 0 | 2011632
Franklin | 8 | Franklin | 118495 | CVRT Ext to West Shippensburg |  |  | Conversion of Abandoned Railway Corridors to Trail | CON | TAP | 2027-04-29 |  | 0 | 0 | 1264094 | 0 | 0 | 0 | 0 | 0 | 0 | 1264094
Franklin | 8 | Franklin | 119286 | Carbon Reduction Program (CRP) Chambersburg RSL |  |  | Reserve Line Item | CON | CRP |  |  | 33221 | 540000 | 540000 | 540000 | 540000 | 540000 | 540000 | 540000 | 2159000 | 5972221
Franklin | 8 | Franklin | 119287 | Carbon Reduction Program (CRP) Hagerstown RSL |  |  | Reserve Line Item | CON | CRPU |  |  | 0 | 138000 | 138000 | 138000 | 138000 | 0 | 138000 | 138000 | 552000 | 1380000
Franklin | 8 | Franklin | 121390 | SR 16 Retaining Wall | 16 | 056 | Safety Improvement | PE | PRTCT | 2026-09-03 |  | 38233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38233
Franklin | 8 | Franklin | 121390 | SR 16 Retaining Wall | 16 | 056 | Safety Improvement | FD | PRTCT | 2026-09-03 |  | 106980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106980
Franklin | 8 | Franklin | 121390 | SR 16 Retaining Wall | 16 | 056 | Safety Improvement | ROW | PRTCT | 2026-09-03 |  | 15217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15217
Franklin | 8 | Franklin | 121390 | SR 16 Retaining Wall | 16 | 056 | Safety Improvement | UTL | PRTCT | 2026-09-03 |  | 13889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13889
Franklin | 8 | Franklin | 121390 | SR 16 Retaining Wall | 16 | 056 | Safety Improvement | CON | PRTCT | 2026-09-03 |  | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
Franklin | 8 | Franklin | 121522 | Southgate Pedestrian Improvements |  | TAP | Bicycle and Pedestrian Facilities Transit | CON | TAP | 2027-07-15 |  | 0 | 0 | 734871 | 0 | 0 | 0 | 0 | 0 | 0 | 734871
Franklin | 8 | Franklin | 122218 | Franklin -District 8-0 Asset Management- Paving | 11 | 0 | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 900000 | 0 | 1146047 | 600000 | 2967111 | 17150000 | 22763158
Franklin | 8 | Franklin | 122545 | Shimpstown Rd over Licking Creek Act 13 | 7209 | ACT | Bridge Restoration | PE | ACT13 |  |  | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
Franklin | 8 | Franklin | 122545 | Shimpstown Rd over Licking Creek Act 13 | 7209 | ACT | Bridge Restoration | FD | ACT13 |  |  | 0 | 196260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196260
Franklin | 8 | Franklin | 122545 | Shimpstown Rd over Licking Creek Act 13 | 7209 | ACT | Bridge Restoration | ROW | ACT13 |  |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Franklin | 8 | Franklin | 122545 | Shimpstown Rd over Licking Creek Act 13 | 7209 | ACT | Bridge Restoration | UTL | ACT13 |  |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Franklin | 8 | Franklin | 122545 | Shimpstown Rd over Licking Creek Act 13 | 7209 | ACT | Bridge Restoration | CON | ACT13 |  |  | 0 | 0 | 1551305 | 0 | 0 | 0 | 0 | 0 | 0 | 1551305
Harrisburg | 8 | Cumberland | 87419 | Enola Road over Bloser Creek | 944 | 022 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 87421 | Pine Road ov Irishtown Gap Hol Crk | 3006 | 023 | Bridge Replacement | PE | 185 | 2028-11-02 |  | 3922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3922
Harrisburg | 8 | Cumberland | 87421 | Pine Road ov Irishtown Gap Hol Crk | 3006 | 023 | Bridge Replacement | FD | 185 | 2028-11-02 |  | 300000 | 50410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350410
Harrisburg | 8 | Cumberland | 87421 | Pine Road ov Irishtown Gap Hol Crk | 3006 | 023 | Bridge Replacement | ROW | 185 | 2028-11-02 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Harrisburg | 8 | Cumberland | 87421 | Pine Road ov Irishtown Gap Hol Crk | 3006 | 023 | Bridge Replacement | UTL | 185 | 2028-11-02 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Cumberland | 87421 | Pine Road ov Irishtown Gap Hol Crk | 3006 | 023 | Bridge Replacement | CON | 185 | 2028-11-02 |  | 0 | 0 | 128434 | 224751 | 0 | 0 | 0 | 0 | 0 | 353185
Harrisburg | 8 | Cumberland | 87421 | Pine Road ov Irishtown Gap Hol Crk | 3006 | 023 | Bridge Replacement | CON | 581 | 2028-11-02 |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Harrisburg | 8 | Cumberland | 88314 | American Ex-POW Mem Hwy | 581 | 009 | Preventive Maintenance | CON | STP | 2024-11-07 | 2024-11-07 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000
Harrisburg | 8 | Cumberland | 88314 | American Ex-POW Mem Hwy | 581 | 009 | Preventive Maintenance | CON | 581 | 2024-11-07 | 2024-11-07 | 10896522 | 4482019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15378541
Harrisburg | 8 | Cumberland | 90346 | Roxbury Road ov Whiskey Run | 997 | 044 | Bridge Replacement | FD | 185 | 2027-01-14 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Harrisburg | 8 | Cumberland | 90346 | Roxbury Road ov Whiskey Run | 997 | 044 | Bridge Replacement | ROW | 185 | 2027-01-14 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Harrisburg | 8 | Cumberland | 90346 | Roxbury Road ov Whiskey Run | 997 | 044 | Bridge Replacement | UTL | 185 | 2027-01-14 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Cumberland | 90346 | Roxbury Road ov Whiskey Run | 997 | 044 | Bridge Replacement | CON | 185 | 2027-01-14 |  | 0 | 0 | 603185 | 0 | 0 | 0 | 0 | 0 | 0 | 603185
Harrisburg | 8 | Cumberland | 90734 | Roxbury Road Bridge 2 | 997 | 040 | Bridge Preservation - Federal | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 90741 | Big Spring Rd ov Big Spring Ck | 3007 | 019 | Bridge Replacement | PE | 185 | 2028-09-14 |  | 31893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31893
Harrisburg | 8 | Cumberland | 90741 | Big Spring Rd ov Big Spring Ck | 3007 | 019 | Bridge Replacement | FD | BOF | 2028-09-14 |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Harrisburg | 8 | Cumberland | 90741 | Big Spring Rd ov Big Spring Ck | 3007 | 019 | Bridge Replacement | ROW | BOF | 2028-09-14 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Harrisburg | 8 | Cumberland | 90741 | Big Spring Rd ov Big Spring Ck | 3007 | 019 | Bridge Replacement | CON | BOF | 2028-09-14 |  | 0 | 0 | 0 | 1187521 | 0 | 0 | 0 | 0 | 0 | 1187521
Harrisburg | 8 | Cumberland | 90749 | Hays Grove Rd over Yellow Breeches Ck | 3011 | 010 | Bridge Replacement | FD | 185 | 2028-11-02 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Harrisburg | 8 | Cumberland | 90749 | Hays Grove Rd over Yellow Breeches Ck | 3011 | 010 | Bridge Replacement | ROW | 185 | 2028-11-02 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Harrisburg | 8 | Cumberland | 90749 | Hays Grove Rd over Yellow Breeches Ck | 3011 | 010 | Bridge Replacement | UTL | 185 | 2028-11-02 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Cumberland | 90749 | Hays Grove Rd over Yellow Breeches Ck | 3011 | 010 | Bridge Replacement | CON | 185 | 2028-11-02 |  | 0 | 0 | 527787 | 0 | 0 | 0 | 0 | 0 | 0 | 527787
Harrisburg | 8 | Cumberland | 94913 | Trindle/St Johns Church | 641 | 032 | Congestion Reduction | PE | CAQ |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340500 | 340500
Harrisburg | 8 | Cumberland | 94913 | Trindle/St Johns Church | 641 | 032 | Congestion Reduction | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85122 | 85122
Harrisburg | 8 | Cumberland | 94913 | Trindle/St Johns Church | 641 | 032 | Congestion Reduction | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1634336 | 1634336
Harrisburg | 8 | Cumberland | 94913 | Trindle/St Johns Church | 641 | 032 | Congestion Reduction | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408584 | 408584
Harrisburg | 8 | Cumberland | 96229 | Shippensburg Rd Resurface | 533 | 007 | 409 Expanded Maintenance | PE | 581 | 2026-06-04 |  | 0 | 47884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47884
Harrisburg | 8 | Cumberland | 99669 | Lambs Gap Rd over Creek | 1011 | 0 | Bridge Preservation - Federal | PE | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 99669 | Lambs Gap Rd over Creek | 1011 | 0 | Bridge Preservation - Federal | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1524500 | 1524500
Harrisburg | 8 | Cumberland | 99678 | US-11 NB over Conodoguinet Creek | 11 | 115 | Bridge Preservation - Federal | CON | STU | 2024-10-24 | 2024-10-24 | 0 | 7483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7483
Harrisburg | 8 | Cumberland | 99684 | York Rd over Yellow Breec | 74 | 071 | Bridge Replacement | CON | STP | 2024-09-26 | 2024-09-26 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Harrisburg | 8 | Cumberland | 99685 | PA 114 / Conodoguinet Cr Br | 114 | 029 | Bridge Preservation - Federal | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415270 | 415270
Harrisburg | 8 | Cumberland | 99685 | PA 114 / Conodoguinet Cr Br | 114 | 029 | Bridge Preservation - Federal | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3176500 | 3176500
Harrisburg | 8 | Cumberland | 99688 | Good Hope Rd over Conodoguinet | 1013 | 017 | Bridge Preservation - Federal | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 99688 | Good Hope Rd over Conodoguinet | 1013 | 017 | Bridge Preservation - Federal | FD | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134500 | 134500
Harrisburg | 8 | Cumberland | 99688 | Good Hope Rd over Conodoguinet | 1013 | 017 | Bridge Preservation - Federal | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1815108 | 1815108
Harrisburg | 8 | Cumberland | 99692 | South Queen St over NS | 3001 | 0 | Bridge Preservation - Federal | PE | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 99692 | South Queen St over NS | 3001 | 0 | Bridge Preservation - Federal | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401250 | 401250
Harrisburg | 8 | Cumberland | 99695 | Brandy Run Rd over Conodo | 4006 | 0 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 99695 | Brandy Run Rd over Conodo | 4006 | 0 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1248300 | 1248300
Harrisburg | 8 | Cumberland | 99699 | Bloserville Rd over Condo | 4021 | 0 | Bridge Preservation - Federal | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 99699 | Bloserville Rd over Condo | 4021 | 0 | Bridge Preservation - Federal | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203530 | 1203530
Harrisburg | 8 | Cumberland | 99702 | Old Mill Rd over Conodoguinet | 4025 | 0 | Bridge Preservation - Federal | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 99702 | Old Mill Rd over Conodoguinet | 4025 | 0 | Bridge Preservation - Federal | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Harrisburg | 8 | Cumberland | 99702 | Old Mill Rd over Conodoguinet | 4025 | 0 | Bridge Preservation - Federal | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1436960 | 1436960
Harrisburg | 8 | Cumberland | 99787 | Newville Rd over Peebles | 641 | 0 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 99787 | Newville Rd over Peebles | 641 | 0 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000
Harrisburg | 8 | Cumberland | 99791 | Shippensburg Rd ov Condo | 696 | 0 | Bridge Replacement | PE | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 99799 | N Middlesex Rd over Condo | 1005 | 0 | Bridge Preservation - Federal | PE | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 99799 | N Middlesex Rd over Condo | 1005 | 0 | Bridge Preservation - Federal | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 995000 | 995000
Harrisburg | 8 | Cumberland | 99800 | Good Hope Rd ov Sears Run | 1013 | 0 | Bridge Preservation - Federal | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 99800 | Good Hope Rd ov Sears Run | 1013 | 0 | Bridge Preservation - Federal | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 225000
Harrisburg | 8 | Cumberland | 99801 | Camp Hill Bypass ov Trib | 1014 | 0 | Bridge Preservation - Federal | PE | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 99801 | Camp Hill Bypass ov Trib | 1014 | 0 | Bridge Preservation - Federal | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112500 | 112500
Harrisburg | 8 | Cumberland | 99813 | Old Forge Rd over Yellow Breeches Ck | 2019 | 021 | Bridge Preservation - Federal | FD | 185 | 2027-08-26 |  | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260000
Harrisburg | 8 | Cumberland | 99813 | Old Forge Rd over Yellow Breeches Ck | 2019 | 021 | Bridge Preservation - Federal | ROW | 185 | 2027-08-26 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Harrisburg | 8 | Cumberland | 99813 | Old Forge Rd over Yellow Breeches Ck | 2019 | 021 | Bridge Preservation - Federal | CON | BRIP | 2027-08-26 |  | 0 | 0 | 500000 | 2618505 | 0 | 0 | 0 | 0 | 0 | 3118505
Harrisburg | 8 | Cumberland | 99841 | Pine Road over Spruce Run | 3006 | 0 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 99841 | Pine Road over Spruce Run | 3006 | 0 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200750 | 200750
Harrisburg | 8 | Cumberland | 100025 | Cedar Run Bridge | 2021 | 0 | Bridge Preservation - Federal | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 100034 | Green Spring Road Bridge | 641 | 0 | Bridge Replacement | PE | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 100035 | Wertzville Rd Bridge 2 | 944 | 0 | Bridge Preservation - Federal | PE | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 100037 | Lisburn Road Bridge | 2004 | 0 | Bridge Replacement | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 100044 | Wertzville Road Bridge 1 | 944 | 0 | Bridge Preservation - Federal | PE | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Cumberland | 100080 | Spring Run Road Bridge | 34 | 054 | Bridge Replacement | CON | 185 | 2024-08-08 | 2024-08-08 | 166182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166182
Harrisburg | 8 | Cumberland | 110474 | Simpson Ferry Rd/ Sheely Ln Imp | 2014 | 022 | Congestion Reduction | PE | STP | 2029-09-27 |  | 52839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52839
Harrisburg | 8 | Cumberland | 110474 | Simpson Ferry Rd/ Sheely Ln Imp | 2014 | 022 | Congestion Reduction | FD | STP | 2029-09-27 |  | 0 | 245000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245000
Harrisburg | 8 | Cumberland | 110474 | Simpson Ferry Rd/ Sheely Ln Imp | 2014 | 022 | Congestion Reduction | ROW | 581 | 2029-09-27 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Harrisburg | 8 | Cumberland | 110474 | Simpson Ferry Rd/ Sheely Ln Imp | 2014 | 022 | Congestion Reduction | UTL | 581 | 2029-09-27 |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Cumberland | 110474 | Simpson Ferry Rd/ Sheely Ln Imp | 2014 | 022 | Congestion Reduction | CON | STU | 2029-09-27 |  | 0 | 0 | 0 | 0 | 0 | 1118455 | 1681545 | 0 | 0 | 2800000
Harrisburg | 8 | Cumberland | 113265 | High St Resurf | 74 | 083 | 409 Expanded Maintenance | PE | 581 | 2026-05-07 |  | 0 | 32829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32829
Harrisburg | 8 | Cumberland | 113461 | Enola Road Pavement Preservation | 11 | 126 | Highway Restoration | CON | NHPP | 2025-12-04 | 2025-12-04 | 7735493 | 1897474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9632967
Harrisburg | 8 | Cumberland | 114202 | Lemoyne Bottleneck Improvements | 1010 | 029 | Safety Improvement | FD | CAQ | 2027-08-26 |  | 632856 | 20408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 653264
Harrisburg | 8 | Cumberland | 114202 | Lemoyne Bottleneck Improvements | 1010 | 029 | Safety Improvement | FD | STP | 2027-08-26 |  | 450000 | 23268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 473268
Harrisburg | 8 | Cumberland | 114202 | Lemoyne Bottleneck Improvements | 1010 | 029 | Safety Improvement | FD | STU | 2027-08-26 |  | 104468 | 108889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213357
Harrisburg | 8 | Cumberland | 114202 | Lemoyne Bottleneck Improvements | 1010 | 029 | Safety Improvement | ROW | CAQ | 2027-08-26 |  | 20300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20300
Harrisburg | 8 | Cumberland | 114202 | Lemoyne Bottleneck Improvements | 1010 | 029 | Safety Improvement | ROW | STP | 2027-08-26 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Cumberland | 114202 | Lemoyne Bottleneck Improvements | 1010 | 029 | Safety Improvement | UTL | STP | 2027-08-26 |  | 50000 | 62500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112500
Harrisburg | 8 | Cumberland | 114202 | Lemoyne Bottleneck Improvements | 1010 | 029 | Safety Improvement | CON | CAQ | 2027-08-26 |  | 0 | 0 | 1804593 | 1383185 | 0 | 0 | 0 | 0 | 0 | 3187778
Harrisburg | 8 | Cumberland | 114202 | Lemoyne Bottleneck Improvements | 1010 | 029 | Safety Improvement | CON | NHPP | 2027-08-26 |  | 0 | 0 | 686813 | 773799 | 0 | 0 | 0 | 0 | 0 | 1460612
Harrisburg | 8 | Cumberland | 114315 | Sporting Hill Turn Lane | 1013 | 018 | Congestion Reduction | PE | CAQ | 2029-01-11 |  | 663715 | 394733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058448
Harrisburg | 8 | Cumberland | 114315 | Sporting Hill Turn Lane | 1013 | 018 | Congestion Reduction | FD | CAQ | 2029-01-11 |  | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
Harrisburg | 8 | Cumberland | 114315 | Sporting Hill Turn Lane | 1013 | 018 | Congestion Reduction | ROW | 581 | 2029-01-11 |  | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
Harrisburg | 8 | Cumberland | 114315 | Sporting Hill Turn Lane | 1013 | 018 | Congestion Reduction | UTL | STP | 2029-01-11 |  | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
Harrisburg | 8 | Cumberland | 114315 | Sporting Hill Turn Lane | 1013 | 018 | Congestion Reduction | CON | CAQ | 2029-01-11 |  | 0 | 0 | 673327 | 2473884 | 2455599 | 1645348 | 0 | 0 | 0 | 7248158
Harrisburg | 8 | Cumberland | 114315 | Sporting Hill Turn Lane | 1013 | 018 | Congestion Reduction | CON | STP | 2029-01-11 |  | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000
Harrisburg | 8 | Cumberland | 114315 | Sporting Hill Turn Lane | 1013 | 018 | Congestion Reduction | CON | 581 | 2029-01-11 |  | 0 | 0 | 168331 | 633471 | 613900 | 411337 | 0 | 0 | 0 | 1827039
Harrisburg | 8 | Cumberland | 114319 | Center/21st Intersection | 1006 | 009 | Congestion Reduction | PE | CAQ | 2028-09-28 |  | 184340 | 686874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 871214
Harrisburg | 8 | Cumberland | 114319 | Center/21st Intersection | 1006 | 009 | Congestion Reduction | FD | CRP | 2028-09-28 |  | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Harrisburg | 8 | Cumberland | 114319 | Center/21st Intersection | 1006 | 009 | Congestion Reduction | ROW | CRPU | 2028-09-28 |  | 0 | 0 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 950000
Harrisburg | 8 | Cumberland | 114319 | Center/21st Intersection | 1006 | 009 | Congestion Reduction | UTL | CRPU | 2028-09-28 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Harrisburg | 8 | Cumberland | 114319 | Center/21st Intersection | 1006 | 009 | Congestion Reduction | CON | CRP | 2028-09-28 |  | 0 | 0 | 0 | 640000 | 0 | 0 | 0 | 0 | 0 | 640000
Harrisburg | 8 | Cumberland | 114319 | Center/21st Intersection | 1006 | 009 | Congestion Reduction | CON | CRPU | 2028-09-28 |  | 0 | 0 | 0 | 1352000 | 0 | 0 | 0 | 0 | 0 | 1352000
Harrisburg | 8 | Cumberland | 114319 | Center/21st Intersection | 1006 | 009 | Congestion Reduction | CON | STP | 2028-09-28 |  | 0 | 0 | 0 | 584000 | 0 | 0 | 0 | 0 | 0 | 584000
Harrisburg | 8 | Cumberland | 114559 | Systemic Low-Cost Improvements for Stop Controlled | 944 | 023 | Safety Improvement | CON | HSIP | 2022-09-29 | 2022-10-06 | 3194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3194
Harrisburg | 8 | Cumberland | 114853 | HATS TSMO | 15 | 055 | Intelligent Transportation System | CON | NHPP | 2022-09-29 | 2022-09-29 | 864711 | 83803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948514
Harrisburg | 8 | Cumberland | 114853 | HATS TSMO | 15 | 055 | Intelligent Transportation System | CON | STU | 2022-09-29 | 2022-09-29 | 40094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40094
Harrisburg | 8 | Cumberland | 115788 | Ped Safety Impr | 2014 | 024 | Bicycle Pedestrian Highway | CON | STU | 2026-05-21 |  | 0 | 424377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424377
Harrisburg | 8 | Cumberland | 115795 | Multi-Use Trail |  |  | Bicycle Pedestrian Highway | CON | STU | 2026-07-02 |  | 720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720000
Harrisburg | 8 | Cumberland | 115796 | Boiling Springs Ped | 2037 | 003 | Bicycle Pedestrian Highway | CON | STU | 2028-01-01 |  | 0 | 0 | 432330 | 0 | 0 | 0 | 0 | 0 | 0 | 432330
Harrisburg | 8 | Cumberland | 115948 | Hempt Farms | 11 | 140 | Transportation Enhancement | CON | 581 |  |  | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
Harrisburg | 8 | Cumberland | 116119 | Blue-Gray Resurf | 15 | 060 | Highway Restoration | CON | NHPP | 2026-08-13 |  | 6428383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6428383
Harrisburg | 8 | Cumberland | 116119 | Blue-Gray Resurf | 15 | 060 | Highway Restoration | CON | STU | 2026-08-13 |  | 3300153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300153
Harrisburg | 8 | Cumberland | 116119 | Blue-Gray Resurf | 15 | 060 | Highway Restoration | CON | 581 | 2026-08-13 |  | 6963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6963
Harrisburg | 8 | Cumberland | 116120 | Walnut Bottom Resurf | 174 | 017 | Highway Restoration | UTL | 581 | 2025-01-30 | 2025-01-30 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Harrisburg | 8 | Cumberland | 116120 | Walnut Bottom Resurf | 174 | 017 | Highway Restoration | CON | STP | 2025-01-30 | 2025-01-30 | 1236104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1236104
Harrisburg | 8 | Cumberland | 116120 | Walnut Bottom Resurf | 174 | 017 | Highway Restoration | CON | STU | 2025-01-30 | 2025-01-30 | 2216892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2216892
Harrisburg | 8 | Cumberland | 117464 | US 11 over Burd Run | 11 | 128 | Bridge Restoration | PE | BRIP | 2026-09-03 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Harrisburg | 8 | Cumberland | 117464 | US 11 over Burd Run | 11 | 128 | Bridge Restoration | FD | BRIP | 2026-09-03 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Harrisburg | 8 | Cumberland | 117464 | US 11 over Burd Run | 11 | 128 | Bridge Restoration | ROW | BRIP | 2026-09-03 |  | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500
Harrisburg | 8 | Cumberland | 117464 | US 11 over Burd Run | 11 | 128 | Bridge Restoration | UTL | BRIP | 2026-09-03 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Cumberland | 117464 | US 11 over Burd Run | 11 | 128 | Bridge Restoration | CON | BRIP | 2026-09-03 |  | 0 | 1604081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1604081
Harrisburg | 8 | Cumberland | 117479 | US 11 ov Letort Spring | 11 | 129 | Bridge Replacement | PE | BRIP | 2028-03-23 |  | 0 | 113786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113786
Harrisburg | 8 | Cumberland | 117479 | US 11 ov Letort Spring | 11 | 129 | Bridge Replacement | FD | STP | 2028-03-23 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Harrisburg | 8 | Cumberland | 117479 | US 11 ov Letort Spring | 11 | 129 | Bridge Replacement | ROW | 185 | 2028-03-23 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Cumberland | 117479 | US 11 ov Letort Spring | 11 | 129 | Bridge Replacement | UTL | 185 | 2028-03-23 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Cumberland | 117479 | US 11 ov Letort Spring | 11 | 129 | Bridge Replacement | CON | 185 | 2028-03-23 |  | 0 | 0 | 196438 | 2411984 | 2091674 | 1309903 | 0 | 0 | 0 | 6009999
Harrisburg | 8 | Cumberland | 117594 | SR 641 and Locust Point Rd Intersection HSM | 641 | 038 | Safety Improvement | PE | LOC | 2027-11-04 |  | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Harrisburg | 8 | Cumberland | 117594 | SR 641 and Locust Point Rd Intersection HSM | 641 | 038 | Safety Improvement | FD | LOC | 2027-11-04 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Cumberland | 117594 | SR 641 and Locust Point Rd Intersection HSM | 641 | 038 | Safety Improvement | ROW | HSIP | 2027-11-04 |  | 303200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303200
Harrisburg | 8 | Cumberland | 117594 | SR 641 and Locust Point Rd Intersection HSM | 641 | 038 | Safety Improvement | UTL | HSIP | 2027-11-04 |  | 77074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77074
Harrisburg | 8 | Cumberland | 117594 | SR 641 and Locust Point Rd Intersection HSM | 641 | 038 | Safety Improvement | CON | HSIP | 2027-11-04 |  | 0 | 0 | 0 | 1148441 | 2480388 | 0 | 0 | 0 | 0 | 3628829
Harrisburg | 8 | Cumberland | 117594 | SR 641 and Locust Point Rd Intersection HSM | 641 | 038 | Safety Improvement | CON | STU | 2027-11-04 |  | 0 | 0 | 0 | 516179 | 0 | 0 | 0 | 0 | 0 | 516179
Harrisburg | 8 | Cumberland | 117596 | SR 641 and Middlesex Rd Intersection HSM | 641 | 039 | Safety Improvement | PE | HSIP | 2027-11-04 |  | 579029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579029
Harrisburg | 8 | Cumberland | 117596 | SR 641 and Middlesex Rd Intersection HSM | 641 | 039 | Safety Improvement | FD | HSIP | 2027-11-04 |  | 0 | 342000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342000
Harrisburg | 8 | Cumberland | 117596 | SR 641 and Middlesex Rd Intersection HSM | 641 | 039 | Safety Improvement | ROW | HSIP | 2027-11-04 |  | 0 | 470100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470100
Harrisburg | 8 | Cumberland | 117596 | SR 641 and Middlesex Rd Intersection HSM | 641 | 039 | Safety Improvement | UTL | HSIP | 2027-11-04 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Cumberland | 117596 | SR 641 and Middlesex Rd Intersection HSM | 641 | 039 | Safety Improvement | CON | HSIP | 2027-11-04 |  | 0 | 0 | 1137870 | 1562278 | 0 | 0 | 0 | 0 | 0 | 2700148
Harrisburg | 8 | Cumberland | 117646 | Lisburn Rd over Cedar Run | 2031 | 016 | Bridge Restoration | FD | 185 | 2027-02-11 |  | 100000 | 162155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262155
Harrisburg | 8 | Cumberland | 117646 | Lisburn Rd over Cedar Run | 2031 | 016 | Bridge Restoration | ROW | 185 | 2027-02-11 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Cumberland | 117646 | Lisburn Rd over Cedar Run | 2031 | 016 | Bridge Restoration | UTL | 185 | 2027-02-11 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Harrisburg | 8 | Cumberland | 117646 | Lisburn Rd over Cedar Run | 2031 | 016 | Bridge Restoration | CON | STP | 2027-02-11 |  | 0 | 0 | 1141930 | 0 | 0 | 0 | 0 | 0 | 0 | 1141930
Harrisburg | 8 | Cumberland | 117675 | Walnut Bottom Road/West Street/Willow Street | 3023 | 014 | Highway Reconstruction | FD | STP | 2029-01-11 |  | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
Harrisburg | 8 | Cumberland | 117675 | Walnut Bottom Road/West Street/Willow Street | 3023 | 014 | Highway Reconstruction | CON | STP | 2029-01-11 |  | 0 | 0 | 0 | 0 | 1074647 | 0 | 0 | 0 | 0 | 1074647
Harrisburg | 8 | Cumberland | 117702 | Lisburn Rd ov Mill Race | 114 | 037 | Bridge Preservation - Federal | PE | 185 | 2027-08-26 |  | 18032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18032
Harrisburg | 8 | Cumberland | 117702 | Lisburn Rd ov Mill Race | 114 | 037 | Bridge Preservation - Federal | FD | 185 | 2027-08-26 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Harrisburg | 8 | Cumberland | 117702 | Lisburn Rd ov Mill Race | 114 | 037 | Bridge Preservation - Federal | ROW | 185 | 2027-08-26 |  | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Harrisburg | 8 | Cumberland | 117702 | Lisburn Rd ov Mill Race | 114 | 037 | Bridge Preservation - Federal | UTL | 185 | 2027-08-26 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Cumberland | 117702 | Lisburn Rd ov Mill Race | 114 | 037 | Bridge Preservation - Federal | CON | STP | 2027-08-26 |  | 0 | 0 | 424318 | 0 | 0 | 0 | 0 | 0 | 0 | 424318
Harrisburg | 8 | Cumberland | 118504 | East Penn Dr Ped Bridge | 1015 | TAP | Bicycle Pedestrian Highway | CON | TAP | 2023-09-28 | 2023-09-28 | 24217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24217
Harrisburg | 8 | Cumberland | 119233 | D-8 Ped Countdown Signals Safe Project for VRU | 11 | VRU | Safety Improvement | CON | HVRU | 2023-10-19 | 2023-10-19 | 250000 | 163437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413437
Harrisburg | 8 | Cumberland | 119303 | CVRT Downtown Ship | 696 | 018 | Transportation Enhancement | CON | TAU | 2025-09-25 | 2025-09-25 | 281615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281615
Harrisburg | 8 | Cumberland | 119304 | Phase II Streetscape Improvements - 3rd St | 2035 | 0 | Transportation Enhancement | CON | TAU | 2027-10-07 |  | 0 | 0 | 716600 | 985500 | 0 | 0 | 0 | 0 | 0 | 1702100
Harrisburg | 8 | Cumberland | 119708 | I-81 & US 11/15 Lighting | 11 | 139 | Transportation Enhancement | FD | CRP | 2025-12-04 | 2025-12-04 | 71640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71640
Harrisburg | 8 | Cumberland | 119708 | I-81 & US 11/15 Lighting | 11 | 139 | Transportation Enhancement | FD | CRPU | 2025-12-04 | 2025-12-04 | 55325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55325
Harrisburg | 8 | Cumberland | 119708 | I-81 & US 11/15 Lighting | 11 | 139 | Transportation Enhancement | CON | CRP | 2025-12-04 | 2025-12-04 | 545360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545360
Harrisburg | 8 | Cumberland | 119708 | I-81 & US 11/15 Lighting | 11 | 139 | Transportation Enhancement | CON | CRPU | 2025-12-04 | 2025-12-04 | 1235715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1235715
Harrisburg | 8 | Cumberland | 119708 | I-81 & US 11/15 Lighting | 11 | 139 | Transportation Enhancement | CON | NHPP | 2025-12-04 | 2025-12-04 | 866619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 866619
Harrisburg | 8 | Cumberland | 120270 | Cumberland County Bridge Bundle | 7213 | BR3 | Bridge Replacement | PE | BOF | 2028-04-06 |  | 121760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121760
Harrisburg | 8 | Cumberland | 120270 | Cumberland County Bridge Bundle | 7213 | BR3 | Bridge Replacement | PE | STU | 2028-04-06 |  | 454000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454000
Harrisburg | 8 | Cumberland | 120270 | Cumberland County Bridge Bundle | 7213 | BR3 | Bridge Replacement | PE | 183 | 2028-04-06 |  | 107955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107955
Harrisburg | 8 | Cumberland | 120270 | Cumberland County Bridge Bundle | 7213 | BR3 | Bridge Replacement | PE | LOC | 2028-04-06 |  | 35985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35985
Harrisburg | 8 | Cumberland | 120270 | Cumberland County Bridge Bundle | 7213 | BR3 | Bridge Replacement | FD | BOF | 2028-04-06 |  | 0 | 0 | 454000 | 0 | 0 | 0 | 0 | 0 | 0 | 454000
Harrisburg | 8 | Cumberland | 120270 | Cumberland County Bridge Bundle | 7213 | BR3 | Bridge Replacement | FD | 183 | 2028-04-06 |  | 0 | 0 | 85125 | 0 | 0 | 0 | 0 | 0 | 0 | 85125
Harrisburg | 8 | Cumberland | 120270 | Cumberland County Bridge Bundle | 7213 | BR3 | Bridge Replacement | ROW | BOF | 2028-04-06 |  | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
Harrisburg | 8 | Cumberland | 120270 | Cumberland County Bridge Bundle | 7213 | BR3 | Bridge Replacement | ROW | 183 | 2028-04-06 |  | 0 | 0 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 5250
Harrisburg | 8 | Cumberland | 120270 | Cumberland County Bridge Bundle | 7213 | BR3 | Bridge Replacement | UTL | BOF | 2028-04-06 |  | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 56000
Harrisburg | 8 | Cumberland | 120270 | Cumberland County Bridge Bundle | 7213 | BR3 | Bridge Replacement | UTL | 183 | 2028-04-06 |  | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 10500
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | PE | BOF | 2029-01-11 |  | 237600 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | PE | 183 | 2029-01-11 |  | 44550 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | PE | LOC | 2029-01-11 |  | 14850 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | FD | BOF | 2029-01-11 |  | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 180000
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | FD | 183 | 2029-01-11 |  | 0 | 0 | 33750 | 0 | 0 | 0 | 0 | 0 | 0 | 33750
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | FD | LOC | 2029-01-11 |  | 0 | 0 | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 11250
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | ROW | BOF | 2029-01-11 |  | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | ROW | 183 | 2029-01-11 |  | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 2250
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | ROW | LOC | 2029-01-11 |  | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 750
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | UTL | BOF | 2029-01-11 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | UTL | 183 | 2029-01-11 |  | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | UTL | LOC | 2029-01-11 |  | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 1250
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | CON | BOF | 2029-01-11 |  | 0 | 0 | 0 | 369579 | 229525 | 0 | 0 | 0 | 0 | 599104
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | CON | 183 | 2029-01-11 |  | 0 | 0 | 0 | 95219 | 17113 | 0 | 0 | 0 | 0 | 112332
Harrisburg | 8 | Cumberland | 120308 | Quarry Road over Mountain Creek | 7201 | BRG | Bridge Replacement | CON | LOC | 2029-01-11 |  | 0 | 0 | 0 | 23099 | 14345 | 0 | 0 | 0 | 0 | 37444
Harrisburg | 8 | Cumberland | 121438 | Enola Road (SR 11) Retaining Wall Improvement | 11 | 144 | Safety Improvement | PE | PRTCT | 2026-09-17 |  | 42800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42800
Harrisburg | 8 | Cumberland | 121438 | Enola Road (SR 11) Retaining Wall Improvement | 11 | 144 | Safety Improvement | FD | PRTCT | 2026-09-17 |  | 0 | 191997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191997
Harrisburg | 8 | Cumberland | 121438 | Enola Road (SR 11) Retaining Wall Improvement | 11 | 144 | Safety Improvement | ROW | PRTCT | 2026-09-17 |  | 0 | 38900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38900
Harrisburg | 8 | Cumberland | 121438 | Enola Road (SR 11) Retaining Wall Improvement | 11 | 144 | Safety Improvement | UTL | PRTCT | 2026-09-17 |  | 0 | 13889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13889
Harrisburg | 8 | Cumberland | 121438 | Enola Road (SR 11) Retaining Wall Improvement | 11 | 144 | Safety Improvement | CON | PRTCT | 2026-09-17 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Harrisburg | 8 | Cumberland | 121521 | Carlisle Route 74 School Zone Shared-Use Path | 74 | TAP | Bicycle Pedestrian Highway | CON | TAP | 2027-06-24 |  | 0 | 0 | 633000 | 0 | 0 | 0 | 0 | 0 | 0 | 633000
Harrisburg | 8 | Cumberland | 121635 | Cumberland Valley Culvert | 11 | 149 | New Bridge | CON | SRTSF | 2026-09-17 |  | 0 | 3600000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000
Harrisburg | 8 | Cumberland | 122136 | West Shore Gateway Trail Feasibility Study |  |  | Study Phase of Project | STUDY | STU |  |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Cumberland | 122136 | West Shore Gateway Trail Feasibility Study |  |  | Study Phase of Project | STUDY | LOC |  |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Harrisburg | 8 | Cumberland | 122219 | HATS MPO -District 8-0 Asset Management- Paving | 11 | 0 | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26056725 | 26056725
Harrisburg | 8 | Cumberland | 122515 | Army Heritage Dr over I-81 | 2009 | 019 | Bridge Preservation - State Funded | CON | 185 | 2025-08-21 | 2025-08-21 | 0 | 128552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128552
Harrisburg | 8 | Cumberland | 122531 | Good Hope Road Grant Submission | 1013 | 0 | Safety Improvement | PE | 581 |  |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
Harrisburg | 8 | Cumberland | 122853 | Cumberland County Department Force Box Culvert |  |  | Bridge Replacement | PE | 185 |  |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Harrisburg | 8 | Cumberland | 123762 | HATS SS4A Supplemental Safety Planning Study |  |  | Planning/Research/Administration | STUDY | SS4A |  |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Harrisburg | 8 | Cumberland | 123762 | HATS SS4A Supplemental Safety Planning Study |  |  | Planning/Research/Administration | STUDY | 581 |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Dauphin | 18977 | Market St ov Juniata River | 849 | 020 | Bridge Restoration | PE | 185 | 2028-10-19 |  | 131000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131000
Harrisburg | 8 | Dauphin | 18977 | Market St ov Juniata River | 849 | 020 | Bridge Restoration | FD | 185 | 2028-10-19 |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Harrisburg | 8 | Dauphin | 18977 | Market St ov Juniata River | 849 | 020 | Bridge Restoration | ROW | 185 | 2028-10-19 |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Dauphin | 18977 | Market St ov Juniata River | 849 | 020 | Bridge Restoration | UTL | 185 | 2028-10-19 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Harrisburg | 8 | Dauphin | 18977 | Market St ov Juniata River | 849 | 020 | Bridge Restoration | CON | BRIP | 2028-10-19 |  | 0 | 0 | 0 | 0 | 3057459 | 1000000 | 0 | 0 | 0 | 4057459
Harrisburg | 8 | Dauphin | 18977 | Market St ov Juniata River | 849 | 020 | Bridge Restoration | CON | STP | 2028-10-19 |  | 0 | 0 | 0 | 0 | 1078358 | 0 | 0 | 0 | 0 | 1078358
Harrisburg | 8 | Dauphin | 19110 | Luxemburg Road Bridge 2 | 4002 | 0 | Bridge Preservation - Federal | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441500 | 441500
Harrisburg | 8 | Dauphin | 19110 | Luxemburg Road Bridge 2 | 4002 | 0 | Bridge Preservation - Federal | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925750 | 1925750
Harrisburg | 8 | Dauphin | 47519 | Laudermilch Road Bridge | 2012 | 007 | Bridge Replacement | CON | BOF | 2023-03-02 | 2023-03-02 | 1005521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1005521
Harrisburg | 8 | Dauphin | 47519 | Laudermilch Road Bridge | 2012 | 007 | Bridge Replacement | CON | BRIP | 2023-03-02 | 2023-03-02 | 986797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 986797
Harrisburg | 8 | Dauphin | 74521 | Maclay Street Bridge | 3022 | 005 | Bridge Replacement | FD | 185 | 2026-05-07 |  | 661956 | 146545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808501
Harrisburg | 8 | Dauphin | 74521 | Maclay Street Bridge | 3022 | 005 | Bridge Replacement | CON | BRIP | 2026-05-07 |  | 0 | 9673291 | 4287159 | 0 | 0 | 0 | 0 | 0 | 0 | 13960450
Harrisburg | 8 | Dauphin | 74521 | Maclay Street Bridge | 3022 | 005 | Bridge Replacement | CON | NHPP | 2026-05-07 |  | 0 | 13676437 | 2428651 | 0 | 0 | 0 | 0 | 0 | 0 | 16105088
Harrisburg | 8 | Dauphin | 74521 | Maclay Street Bridge | 3022 | 005 | Bridge Replacement | CON | STP | 2026-05-07 |  | 0 | 4060000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4060000
Harrisburg | 8 | Dauphin | 74521 | Maclay Street Bridge | 3022 | 005 | Bridge Replacement | CON | STU | 2026-05-07 |  | 0 | 7000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000000
Harrisburg | 8 | Dauphin | 74522 | Powells Valley Rd Bridge | 4013 | 010 | Bridge Replacement | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610000 | 610000
Harrisburg | 8 | Dauphin | 74522 | Powells Valley Rd Bridge | 4013 | 010 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1986750 | 1986750
Harrisburg | 8 | Dauphin | 78706 | Rutter Rd ov Armstrong Creek | 4001 | 023 | Bridge Restoration | FD | BOF | 2027-08-26 |  | 217604 | 143428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361032
Harrisburg | 8 | Dauphin | 78706 | Rutter Rd ov Armstrong Creek | 4001 | 023 | Bridge Restoration | ROW | BOF | 2027-08-26 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Harrisburg | 8 | Dauphin | 78706 | Rutter Rd ov Armstrong Creek | 4001 | 023 | Bridge Restoration | CON | BOF | 2027-08-26 |  | 0 | 0 | 914853 | 309171 | 0 | 0 | 0 | 0 | 0 | 1224024
Harrisburg | 8 | Dauphin | 80971 | Sand Beach Rd over Swatar | 2015 | 0 | Bridge Preservation - Federal | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 80973 | Vine St Bridge #2 PM | 2003 | 028 | Bridge Preservation - State Funded | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416000 | 416000
Harrisburg | 8 | Dauphin | 80973 | Vine St Bridge #2 PM | 2003 | 028 | Bridge Preservation - State Funded | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3932734 | 3932734
Harrisburg | 8 | Dauphin | 84324 | HATS Bridge Reserve Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 1373573 | 17222 | 0 | 0 | 180282 | 0 | 4536915 | 8451224 | 14559216
Harrisburg | 8 | Dauphin | 84324 | HATS Bridge Reserve Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 497280 | 16134 | 2408545 | 0 | 3501652 | 0 | 0 | 53153429 | 59577040
Harrisburg | 8 | Dauphin | 84324 | HATS Bridge Reserve Line Item |  |  | Reserve Line Item | CON | 185 |  |  | 357400 | 797660 | 0 | 0 | 8834 | 656560 | 0 | 0 | 33525508 | 35345962
Harrisburg | 8 | Dauphin | 85337 | Milroy Road Underpass | 2019 | 016 | Additional Lanes | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33316897 | 33316897
Harrisburg | 8 | Dauphin | 87454 | Cameron St ovr Asylum Run | 230 | 042 | Bridge Replacement | PE | STP | 2027-11-04 |  | 0 | 749903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749903
Harrisburg | 8 | Dauphin | 87454 | Cameron St ovr Asylum Run | 230 | 042 | Bridge Replacement | FD | 185 | 2027-11-04 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Harrisburg | 8 | Dauphin | 87454 | Cameron St ovr Asylum Run | 230 | 042 | Bridge Replacement | ROW | 185 | 2027-11-04 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Dauphin | 87454 | Cameron St ovr Asylum Run | 230 | 042 | Bridge Replacement | UTL | 185 | 2027-11-04 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Dauphin | 87454 | Cameron St ovr Asylum Run | 230 | 042 | Bridge Replacement | CON | 185 | 2027-11-04 |  | 0 | 0 | 0 | 2339581 | 1060419 | 0 | 0 | 0 | 0 | 3400000
Harrisburg | 8 | Dauphin | 87459 | Honeymoon Trail ov Trib to Pine Ck | 1017 | 007 | Bridge Replacement | PE | BOF | 2028-07-13 |  | 0 | 625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000
Harrisburg | 8 | Dauphin | 87459 | Honeymoon Trail ov Trib to Pine Ck | 1017 | 007 | Bridge Replacement | FD | BOF | 2028-07-13 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Dauphin | 87459 | Honeymoon Trail ov Trib to Pine Ck | 1017 | 007 | Bridge Replacement | ROW | BOF | 2028-07-13 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Dauphin | 87459 | Honeymoon Trail ov Trib to Pine Ck | 1017 | 007 | Bridge Replacement | UTL | BOF | 2028-07-13 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Harrisburg | 8 | Dauphin | 87459 | Honeymoon Trail ov Trib to Pine Ck | 1017 | 007 | Bridge Replacement | CON | BOF | 2028-07-13 |  | 0 | 0 | 0 | 2278252 | 0 | 0 | 0 | 0 | 0 | 2278252
Harrisburg | 8 | Dauphin | 87653 | Mountain House Rd over Armstrong Ck | 1003 | 027 | Bridge Preservation - Federal | PE | 185 | 2028-09-14 |  | 119391 | 4090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123481
Harrisburg | 8 | Dauphin | 87653 | Mountain House Rd over Armstrong Ck | 1003 | 027 | Bridge Preservation - Federal | FD | 185 | 2028-09-14 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Harrisburg | 8 | Dauphin | 87653 | Mountain House Rd over Armstrong Ck | 1003 | 027 | Bridge Preservation - Federal | ROW | 185 | 2028-09-14 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Harrisburg | 8 | Dauphin | 87653 | Mountain House Rd over Armstrong Ck | 1003 | 027 | Bridge Preservation - Federal | UTL | 185 | 2028-09-14 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Dauphin | 87653 | Mountain House Rd over Armstrong Ck | 1003 | 027 | Bridge Preservation - Federal | CON | 185 | 2028-09-14 |  | 0 | 0 | 315334 | 0 | 0 | 0 | 0 | 0 | 0 | 315334
Harrisburg | 8 | Dauphin | 88058 | TAP Line Item |  |  | Reserve Line Item | CON | TAU |  |  | 907385 | 0 | 0 | 90500 | 1076000 | 1076000 | 1076000 | 1076000 | 4304000 | 9605885
Harrisburg | 8 | Dauphin | 88060 | HSIP Reserve Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 536491 | 1550393 | 0 | 1344612 | 0 | 0 | 775763 | 15300000 | 19507259
Harrisburg | 8 | Dauphin | 88061 | Highway Reserve Line Item |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 357168 | 0 | 0 | 0 | 0 | 0 | 12594536 | 38393000 | 51344704
Harrisburg | 8 | Dauphin | 88061 | Highway Reserve Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 691529 | 330091 | 676815 | 223843 | 0 | 0 | 188009 | 23303628 | 25413915
Harrisburg | 8 | Dauphin | 88061 | Highway Reserve Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 2189316 | 1604978 | 462160 | 430240 | 150671 | 888429 | 14696799 | 10000000 | 30422593
Harrisburg | 8 | Dauphin | 88068 | STU Reserve Line Item |  |  | Reserve Line Item | CON | STU |  |  | 0 | 21231 | 950205 | 0 | 0 | 0 | 6019643 | 0 | 31874386 | 38865465
Harrisburg | 8 | Dauphin | 88069 | Delivery/ Consult Assist |  |  | Reserve Line Item | PE | 185 |  |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Harrisburg | 8 | Dauphin | 88069 | Delivery/ Consult Assist |  |  | Reserve Line Item | PE | 581 |  |  | 1500000 | 1500000 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 6000000
Harrisburg | 8 | Dauphin | 88069 | Delivery/ Consult Assist |  |  | Reserve Line Item | CON | 581 |  |  | 480000 | 480000 | 480000 | 480000 | 0 | 0 | 0 | 0 | 0 | 1920000
Harrisburg | 8 | Dauphin | 90328 | Elizabethtown Rd over Trib to Conewago Ck | 743 | 038 | Bridge Preservation - Federal | PE | 185 | 2027-09-16 |  | 58000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58000
Harrisburg | 8 | Dauphin | 90328 | Elizabethtown Rd over Trib to Conewago Ck | 743 | 038 | Bridge Preservation - Federal | FD | 185 | 2027-09-16 |  | 100000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
Harrisburg | 8 | Dauphin | 90328 | Elizabethtown Rd over Trib to Conewago Ck | 743 | 038 | Bridge Preservation - Federal | ROW | 185 | 2027-09-16 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Dauphin | 90328 | Elizabethtown Rd over Trib to Conewago Ck | 743 | 038 | Bridge Preservation - Federal | UTL | 185 | 2027-09-16 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Dauphin | 90328 | Elizabethtown Rd over Trib to Conewago Ck | 743 | 038 | Bridge Preservation - Federal | CON | 185 | 2027-09-16 |  | 0 | 0 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 230000
Harrisburg | 8 | Dauphin | 90341 | SR 209 over Tributary to Wiconisco Ck | 209 | 017 | Bridge Replacement | FD | 185 | 2027-01-14 |  | 242698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242698
Harrisburg | 8 | Dauphin | 90341 | SR 209 over Tributary to Wiconisco Ck | 209 | 017 | Bridge Replacement | ROW | 185 | 2027-01-14 |  | 23800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23800
Harrisburg | 8 | Dauphin | 90341 | SR 209 over Tributary to Wiconisco Ck | 209 | 017 | Bridge Replacement | UTL | 185 | 2027-01-14 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Dauphin | 90341 | SR 209 over Tributary to Wiconisco Ck | 209 | 017 | Bridge Replacement | CON | 185 | 2027-01-14 |  | 0 | 0 | 508306 | 1440494 | 0 | 0 | 0 | 0 | 0 | 1948800
Harrisburg | 8 | Dauphin | 90771 | South River Rd ov Powells Ck | 147 | 022 | Bridge Restoration | FD | 185 | 2027-07-15 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Harrisburg | 8 | Dauphin | 90771 | South River Rd ov Powells Ck | 147 | 022 | Bridge Restoration | ROW | 185 | 2027-07-15 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Harrisburg | 8 | Dauphin | 90771 | South River Rd ov Powells Ck | 147 | 022 | Bridge Restoration | UTL | 185 | 2027-07-15 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Dauphin | 90771 | South River Rd ov Powells Ck | 147 | 022 | Bridge Restoration | CON | BRIP | 2027-07-15 |  | 0 | 0 | 0 | 1352046 | 0 | 0 | 0 | 0 | 0 | 1352046
Harrisburg | 8 | Dauphin | 90771 | South River Rd ov Powells Ck | 147 | 022 | Bridge Restoration | CON | STP | 2027-07-15 |  | 0 | 0 | 1000000 | 1365377 | 2340331 | 0 | 0 | 0 | 0 | 4705708
Harrisburg | 8 | Dauphin | 90772 | Market Street Bridge-A | 147 | 017 | Bridge Replacement | CON | STP | 2023-08-10 | 2023-08-10 | 390550 | 26847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417397
Harrisburg | 8 | Dauphin | 90772 | Market Street Bridge-A | 147 | 017 | Bridge Replacement | CON | STU | 2023-08-10 | 2023-08-10 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Harrisburg | 8 | Dauphin | 90781 | Roundtop Road Bridge | 2005 | 0 | Bridge Replacement | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 90783 | Manada Gap Road Bridge | 2015 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 90837 | 19th Street Bridge | 3007 | 0 | Bridge Preservation - State Funded | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 225000
Harrisburg | 8 | Dauphin | 90837 | 19th Street Bridge | 3007 | 0 | Bridge Preservation - State Funded | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Harrisburg | 8 | Dauphin | 90844 | Shippen Dam Road Bridge | 4002 | 0 | Bridge Preservation - Federal | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 90849 | Powells Valley Rd ov Rattling Creek | 4013 | 016 | Bridge Restoration | FD | BOF | 2027-08-26 |  | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
Harrisburg | 8 | Dauphin | 90849 | Powells Valley Rd ov Rattling Creek | 4013 | 016 | Bridge Restoration | ROW | 185 | 2027-08-26 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Dauphin | 90849 | Powells Valley Rd ov Rattling Creek | 4013 | 016 | Bridge Restoration | UTL | 185 | 2027-08-26 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Dauphin | 90849 | Powells Valley Rd ov Rattling Creek | 4013 | 016 | Bridge Restoration | CON | BOF | 2027-08-26 |  | 0 | 0 | 1260570 | 0 | 0 | 0 | 0 | 0 | 0 | 1260570
Harrisburg | 8 | Dauphin | 92945 | US 322 & Chambers Hill Rd | 322 | 050 | Congestion Reduction | CON | STU | 2023-04-13 | 2023-04-13 | 248920 | 44299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 293219
Harrisburg | 8 | Dauphin | 93176 | Market St Bridge West | 3012 | 026 | Bridge Restoration | PE | BRIP | 2027-01-28 |  | 0 | 22453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22453
Harrisburg | 8 | Dauphin | 93176 | Market St Bridge West | 3012 | 026 | Bridge Restoration | FD | BRIP | 2027-01-28 |  | 855678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855678
Harrisburg | 8 | Dauphin | 93176 | Market St Bridge West | 3012 | 026 | Bridge Restoration | FD | NHPP | 2027-01-28 |  | 706699 | 1437695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2144394
Harrisburg | 8 | Dauphin | 93176 | Market St Bridge West | 3012 | 026 | Bridge Restoration | FD | STU | 2027-01-28 |  | 217743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217743
Harrisburg | 8 | Dauphin | 93176 | Market St Bridge West | 3012 | 026 | Bridge Restoration | ROW | 185 | 2027-01-28 |  | 67600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67600
Harrisburg | 8 | Dauphin | 93176 | Market St Bridge West | 3012 | 026 | Bridge Restoration | UTL | NHPP | 2027-01-28 |  | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000
Harrisburg | 8 | Dauphin | 93176 | Market St Bridge West | 3012 | 026 | Bridge Restoration | CON | BRIP | 2027-01-28 |  | 0 | 0 | 0 | 880426 | 3854940 | 0 | 0 | 0 | 0 | 4735366
Harrisburg | 8 | Dauphin | 93176 | Market St Bridge West | 3012 | 026 | Bridge Restoration | CON | NHPP | 2027-01-28 |  | 0 | 0 | 7836948 | 9237312 | 12016675 | 411103 | 5911756 | 3115464 | 0 | 38529258
Harrisburg | 8 | Dauphin | 93176 | Market St Bridge West | 3012 | 026 | Bridge Restoration | CON | STP | 2027-01-28 |  | 0 | 0 | 0 | 0 | 0 | 3611750 | 0 | 0 | 0 | 3611750
Harrisburg | 8 | Dauphin | 93176 | Market St Bridge West | 3012 | 026 | Bridge Restoration | CON | STU | 2027-01-28 |  | 0 | 0 | 2764959 | 980264 | 2554016 | 4545814 | 0 | 0 | 0 | 10845053
Harrisburg | 8 | Dauphin | 93177 | Market St Bridge East | 3012 | 029 | Bridge Restoration | FD | BRIP | 2027-01-28 |  | 855679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855679
Harrisburg | 8 | Dauphin | 93177 | Market St Bridge East | 3012 | 029 | Bridge Restoration | FD | NHPP | 2027-01-28 |  | 740548 | 2376315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116863
Harrisburg | 8 | Dauphin | 93177 | Market St Bridge East | 3012 | 029 | Bridge Restoration | FD | 185 | 2027-01-28 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Harrisburg | 8 | Dauphin | 93177 | Market St Bridge East | 3012 | 029 | Bridge Restoration | ROW | NHPP | 2027-01-28 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Dauphin | 93177 | Market St Bridge East | 3012 | 029 | Bridge Restoration | UTL | NHPP | 2027-01-28 |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Harrisburg | 8 | Dauphin | 93177 | Market St Bridge East | 3012 | 029 | Bridge Restoration | CON | BRIP | 2027-01-28 |  | 0 | 0 | 0 | 1343185 | 1860892 | 1221756 | 11480244 | 0 | 0 | 15906077
Harrisburg | 8 | Dauphin | 93177 | Market St Bridge East | 3012 | 029 | Bridge Restoration | CON | NHPP | 2027-01-28 |  | 0 | 0 | 6433588 | 4412688 | 18581119 | 411103 | 9798244 | 0 | 0 | 39636742
Harrisburg | 8 | Dauphin | 93177 | Market St Bridge East | 3012 | 029 | Bridge Restoration | CON | STP | 2027-01-28 |  | 0 | 0 | 0 | 0 | 0 | 3611750 | 0 | 0 | 0 | 3611750
Harrisburg | 8 | Dauphin | 93177 | Market St Bridge East | 3012 | 029 | Bridge Restoration | CON | STU | 2027-01-28 |  | 0 | 0 | 2496406 | 1142837 | 2554017 | 4545814 | 2706357 | 0 | 0 | 13445431
Harrisburg | 8 | Dauphin | 93178 | Clarks Ferry Bridge PM | 22 | 059 | Bridge Preservation - Federal | PE | 185 | 2028-10-19 |  | 78256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78256
Harrisburg | 8 | Dauphin | 93178 | Clarks Ferry Bridge PM | 22 | 059 | Bridge Preservation - Federal | FD | BRIP | 2028-10-19 |  | 0 | 0 | 0 | 725555 | 0 | 0 | 0 | 0 | 0 | 725555
Harrisburg | 8 | Dauphin | 93178 | Clarks Ferry Bridge PM | 22 | 059 | Bridge Preservation - Federal | FD | STP | 2028-10-19 |  | 0 | 0 | 774445 | 0 | 0 | 0 | 0 | 0 | 0 | 774445
Harrisburg | 8 | Dauphin | 93178 | Clarks Ferry Bridge PM | 22 | 059 | Bridge Preservation - Federal | CON | BRIP | 2028-10-19 |  | 0 | 0 | 0 | 0 | 3928709 | 5036388 | 1221756 | 12702000 | 0 | 22888853
Harrisburg | 8 | Dauphin | 93178 | Clarks Ferry Bridge PM | 22 | 059 | Bridge Preservation - Federal | CON | STP | 2028-10-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8186870 | 2208858 | 0 | 10395728
Harrisburg | 8 | Dauphin | 93178 | Clarks Ferry Bridge PM | 22 | 059 | Bridge Preservation - Federal | CON | STU | 2028-10-19 |  | 0 | 0 | 0 | 0 | 1154300 | 0 | 1118455 | 0 | 0 | 2272755
Harrisburg | 8 | Dauphin | 93583 | Armstrong Valley Rd Brg | 225 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 94636 | Rolling Stock Replacement |  |  | Reserve Line Item | CON | CAQ |  |  | 2527500 | 2527500 | 2527500 | 2527500 | 2527500 | 0 | 0 | 0 | 0 | 12637500
Harrisburg | 8 | Dauphin | 96302 | Elmerton Avenue Resurface | 3026 | 009 | 409 Expanded Maintenance | PE | 581 | 2027-10-07 |  | 58505 | 214362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272867
Harrisburg | 8 | Dauphin | 96302 | Elmerton Avenue Resurface | 3026 | 009 | 409 Expanded Maintenance | ROW | 581 | 2027-10-07 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Harrisburg | 8 | Dauphin | 96302 | Elmerton Avenue Resurface | 3026 | 009 | 409 Expanded Maintenance | UTL | 581 | 2027-10-07 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Dauphin | 99844 | Schoolhouse Rd ov PA-283 | 2043 | 0 | Bridge Preservation - Federal | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 99848 | US-11 over Juniata River | 11 | 092 | Bridge Preservation - Federal | PE | 185 | 2026-09-17 |  | 452673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452673
Harrisburg | 8 | Dauphin | 99848 | US-11 over Juniata River | 11 | 092 | Bridge Preservation - Federal | FD | 185 | 2026-09-17 |  | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Harrisburg | 8 | Dauphin | 99848 | US-11 over Juniata River | 11 | 092 | Bridge Preservation - Federal | CON | BRIP | 2026-09-17 |  | 6000000 | 28997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6028997
Harrisburg | 8 | Dauphin | 99848 | US-11 over Juniata River | 11 | 092 | Bridge Preservation - Federal | CON | NHPP | 2026-09-17 |  | 0 | 135127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135127
Harrisburg | 8 | Dauphin | 99848 | US-11 over Juniata River | 11 | 092 | Bridge Preservation - Federal | CON | 185 | 2026-09-17 |  | 1114761 | 3221115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4335876
Harrisburg | 8 | Dauphin | 99870 | US-209 over Wiconisco Creek | 209 | 018 | Bridge Preservation - Federal | FD | 185 | 2027-08-26 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Harrisburg | 8 | Dauphin | 99870 | US-209 over Wiconisco Creek | 209 | 018 | Bridge Preservation - Federal | ROW | 185 | 2027-08-26 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Dauphin | 99870 | US-209 over Wiconisco Creek | 209 | 018 | Bridge Preservation - Federal | UTL | 185 | 2027-08-26 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Dauphin | 99870 | US-209 over Wiconisco Creek | 209 | 018 | Bridge Preservation - Federal | CON | BRIP | 2027-08-26 |  | 0 | 0 | 1000000 | 1185454 | 0 | 0 | 0 | 0 | 0 | 2185454
Harrisburg | 8 | Dauphin | 99876 | Valley Road Bridge | 1020 | 0 | Bridge Replacement | PE | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 99876 | Valley Road Bridge | 1020 | 0 | Bridge Replacement | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 722250 | 722250
Harrisburg | 8 | Dauphin | 99879 | North Front Street Bridge | 3009 | 0 | Bridge Preservation - Federal | PE | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 99879 | North Front Street Bridge | 3009 | 0 | Bridge Preservation - Federal | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 722118 | 722118
Harrisburg | 8 | Dauphin | 99885 | Enders Road ov Armstrong Ck | 4006 | 011 | Bridge Replacement | FD | BOF | 2026-12-03 |  | 330000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330000
Harrisburg | 8 | Dauphin | 99885 | Enders Road ov Armstrong Ck | 4006 | 011 | Bridge Replacement | ROW | BOF | 2026-12-03 |  | 0 | 30500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30500
Harrisburg | 8 | Dauphin | 99885 | Enders Road ov Armstrong Ck | 4006 | 011 | Bridge Replacement | CON | 185 | 2026-12-03 |  | 0 | 400409 | 2151309 | 0 | 0 | 0 | 0 | 0 | 0 | 2551718
Harrisburg | 8 | Dauphin | 99895 | US-422 Bridge over US-322 | 422 | 0 | Bridge Preservation - Federal | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 99912 | Wilhour Rd over Wiconisco | 1007 | 024 | Bridge Preservation - Federal | FD | BOF | 2027-01-14 |  | 271342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271342
Harrisburg | 8 | Dauphin | 99912 | Wilhour Rd over Wiconisco | 1007 | 024 | Bridge Preservation - Federal | ROW | BOF | 2027-01-14 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Dauphin | 99912 | Wilhour Rd over Wiconisco | 1007 | 024 | Bridge Preservation - Federal | UTL | BOF | 2027-01-14 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Dauphin | 99912 | Wilhour Rd over Wiconisco | 1007 | 024 | Bridge Preservation - Federal | CON | BOF | 2027-01-14 |  | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
Harrisburg | 8 | Dauphin | 99913 | Erdman Rd over Pine Creek | 1013 | 0 | Bridge Restoration | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 99913 | Erdman Rd over Pine Creek | 1013 | 0 | Bridge Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786500 | 786500
Harrisburg | 8 | Dauphin | 99917 | Fairville Ave overI-81 | 2033 | 011 | Bridge Preservation - Federal | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 225000
Harrisburg | 8 | Dauphin | 99917 | Fairville Ave overI-81 | 2033 | 011 | Bridge Preservation - Federal | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1248254 | 1248254
Harrisburg | 8 | Dauphin | 99920 | Rosedale Ave over Airport | 2040 | 0 | Bridge Preservation - Federal | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 99925 | Deodate Rd Over PA-283 | 2007 | 0 | Bridge Preservation - Federal | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 99934 | Nyes Rd over Beaver Creek | 2019 | 018 | Bridge Preservation - Federal | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 99934 | Nyes Rd over Beaver Creek | 2019 | 018 | Bridge Preservation - Federal | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 907750 | 907750
Harrisburg | 8 | Dauphin | 99939 | Toll House Rd over PA-283 | 2023 | 0 | Bridge Preservation - Federal | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 99945 | Spring Garden Rd over Con | 2042 | 0 | Bridge Preservation - Federal | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 99980 | Market St ov Rattling Cr | 4013 | 017 | Bridge Preservation - Federal | FD | BOF | 2027-08-26 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Dauphin | 99980 | Market St ov Rattling Cr | 4013 | 017 | Bridge Preservation - Federal | ROW | 185 | 2027-08-26 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Dauphin | 99980 | Market St ov Rattling Cr | 4013 | 017 | Bridge Preservation - Federal | UTL | 185 | 2027-08-26 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Dauphin | 99980 | Market St ov Rattling Cr | 4013 | 017 | Bridge Preservation - Federal | CON | BOF | 2027-08-26 |  | 0 | 0 | 149151 | 589923 | 0 | 0 | 0 | 0 | 0 | 739074
Harrisburg | 8 | Dauphin | 99980 | Market St ov Rattling Cr | 4013 | 017 | Bridge Preservation - Federal | CON | STP | 2027-08-26 |  | 0 | 0 | 215858 | 1186813 | 0 | 0 | 0 | 0 | 0 | 1402671
Harrisburg | 8 | Dauphin | 99984 | Wm Penn Hwy EB ov US 11 | 8037 | 0 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 99984 | Wm Penn Hwy EB ov US 11 | 8037 | 0 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449500 | 449500
Harrisburg | 8 | Dauphin | 100036 | Armstrong Street over Arm | 225 | 0 | Bridge Preservation - Federal | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318374 | 318374
Harrisburg | 8 | Dauphin | 100068 | Railroad Street over Wico | 1005 | 0 | Bridge Preservation - Federal | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 100068 | Railroad Street over Wico | 1005 | 0 | Bridge Preservation - Federal | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369250 | 369250
Harrisburg | 8 | Dauphin | 100083 | Roundtop Road ov Iron Mine Run | 2005 | 019 | Bridge Replacement | FD | 185 | 2027-07-29 |  | 200000 | 193000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393000
Harrisburg | 8 | Dauphin | 100083 | Roundtop Road ov Iron Mine Run | 2005 | 019 | Bridge Replacement | ROW | 185 | 2027-07-29 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Harrisburg | 8 | Dauphin | 100083 | Roundtop Road ov Iron Mine Run | 2005 | 019 | Bridge Replacement | UTL | 185 | 2027-07-29 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Dauphin | 100083 | Roundtop Road ov Iron Mine Run | 2005 | 019 | Bridge Replacement | CON | BRIP | 2027-07-29 |  | 0 | 0 | 920000 | 865900 | 0 | 0 | 0 | 0 | 0 | 1785900
Harrisburg | 8 | Dauphin | 100090 | Union Deposit Road over K | 2010 | 0 | Bridge Preservation - Federal | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Harrisburg | 8 | Dauphin | 100090 | Union Deposit Road over K | 2010 | 0 | Bridge Preservation - Federal | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1512590 | 1512590
Harrisburg | 8 | Dauphin | 100095 | Hockersville Road over Sp | 2011 | 0 | Bridge Restoration | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 100098 | Schoolhouse Road over Hof | 2013 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214000 | 214000
Harrisburg | 8 | Dauphin | 100105 | Nyes Road over Tributary | 2019 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 100108 | North Front Street over F | 3009 | 0 | Bridge Replacement | PE | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 100108 | North Front Street over F | 3009 | 0 | Bridge Replacement | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925750 | 1925750
Harrisburg | 8 | Dauphin | 100109 | Paxton Street over Spring | 3010 | 0 | Bridge Preservation - Federal | PE | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 100110 | Airport Conn North Bound | 3032 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Harrisburg | 8 | Dauphin | 100110 | Airport Conn North Bound | 3032 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3781475 | 3781475
Harrisburg | 8 | Dauphin | 100117 | Locust Lane over Tributar | 3024 | 0 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 100117 | Locust Lane over Tributar | 3024 | 0 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000
Harrisburg | 8 | Dauphin | 100119 | Luxemburg Road over Tribu | 4002 | 0 | Bridge Preservation - Federal | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 100184 | Airport Conn South Bound | 3032 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Harrisburg | 8 | Dauphin | 100184 | Airport Conn South Bound | 3032 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3781475 | 3781475
Harrisburg | 8 | Dauphin | 100202 | US 209 Resurfacing | 209 | 019 | Highway Restoration | ROW | STP | 2027-01-28 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Dauphin | 100202 | US 209 Resurfacing | 209 | 019 | Highway Restoration | UTL | STP | 2027-01-28 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Dauphin | 100202 | US 209 Resurfacing | 209 | 019 | Highway Restoration | CON | 581 | 2027-01-28 |  | 0 | 0 | 1500000 | 1459596 | 0 | 0 | 0 | 0 | 0 | 2959596
Harrisburg | 8 | Dauphin | 100208 | Bachmanville Road Bridge | 2011 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 100233 | Phillips Road Bridge | 4010 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 100241 | East Middle Road Bridge | 1016 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 100253 | North Church Street Brdg | 1021 | 0 | Bridge Preservation - Federal | PE | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 100253 | North Church Street Brdg | 1021 | 0 | Bridge Preservation - Federal | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 963000 | 963000
Harrisburg | 8 | Dauphin | 100258 | Small Valley Road Bridge | 1023 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 100268 | Armstrong Valley Rd Brdg | 225 | 0 | Bridge Replacement | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 100268 | Armstrong Valley Rd Brdg | 225 | 0 | Bridge Replacement | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 722250 | 722250
Harrisburg | 8 | Dauphin | 100272 | Colebrook Road Bridge | 341 | 006 | Bridge Replacement | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 100272 | Colebrook Road Bridge | 341 | 006 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680665 | 680665
Harrisburg | 8 | Dauphin | 102173 | CMP implementation |  |  | Reserve Line Item | CON | CAQ |  |  | 0 | 1075377 | 0 | 0 | 174209 | 3923652 | 569000 | 0 | 21637500 | 27379738
Harrisburg | 8 | Dauphin | 102733 | CAT Intermodal Bridge |  | BRG | Bridge Restoration | FD | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000
Harrisburg | 8 | Dauphin | 102733 | CAT Intermodal Bridge |  | BRG | Bridge Restoration | CON | CAQ |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5569000 | 0 | 10569000
Harrisburg | 8 | Dauphin | 102733 | CAT Intermodal Bridge |  | BRG | Bridge Restoration | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11526000 | 0 | 11526000
Harrisburg | 8 | Dauphin | 106548 | Upper Daupin Park-n- Ride | 147 | 020 | Air Quality | CON | CAQ |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
Harrisburg | 8 | Dauphin | 106554 | Riverlands Safety Implementation | 22 | 075 | Safety Improvement | FD | 581 | 2028-10-19 |  | 0 | 0 | 2500000 | 2500000 | 0 | 0 | 0 | 0 | 0 | 5000000
Harrisburg | 8 | Dauphin | 106554 | Riverlands Safety Implementation | 22 | 075 | Safety Improvement | ROW | 581 | 2028-10-19 |  | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 2000000
Harrisburg | 8 | Dauphin | 106554 | Riverlands Safety Implementation | 22 | 075 | Safety Improvement | UTL | 581 | 2028-10-19 |  | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Harrisburg | 8 | Dauphin | 106554 | Riverlands Safety Implementation | 22 | 075 | Safety Improvement | CON | 581 | 2028-10-19 |  | 0 | 0 | 0 | 0 | 5782202 | 6000000 | 17752688 | 4782201 | 0 | 34317091
Harrisburg | 8 | Dauphin | 106563 | West Cross Rd Bridge | 7206 | BRG | Bridge Replacement | ROW | BOF | 2026-07-16 |  | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000
Harrisburg | 8 | Dauphin | 106563 | West Cross Rd Bridge | 7206 | BRG | Bridge Replacement | ROW | 183 | 2026-07-16 |  | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000
Harrisburg | 8 | Dauphin | 106563 | West Cross Rd Bridge | 7206 | BRG | Bridge Replacement | ROW | LOC | 2026-07-16 |  | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
Harrisburg | 8 | Dauphin | 106563 | West Cross Rd Bridge | 7206 | BRG | Bridge Replacement | UTL | BOF | 2026-07-16 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Harrisburg | 8 | Dauphin | 106563 | West Cross Rd Bridge | 7206 | BRG | Bridge Replacement | UTL | 183 | 2026-07-16 |  | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
Harrisburg | 8 | Dauphin | 106563 | West Cross Rd Bridge | 7206 | BRG | Bridge Replacement | UTL | LOC | 2026-07-16 |  | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
Harrisburg | 8 | Dauphin | 106563 | West Cross Rd Bridge | 7206 | BRG | Bridge Replacement | CON | BOF | 2026-07-16 |  | 418633 | 752049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1170682
Harrisburg | 8 | Dauphin | 106563 | West Cross Rd Bridge | 7206 | BRG | Bridge Replacement | CON | 183 | 2026-07-16 |  | 0 | 219503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219503
Harrisburg | 8 | Dauphin | 106563 | West Cross Rd Bridge | 7206 | BRG | Bridge Replacement | CON | LOC | 2026-07-16 |  | 0 | 73167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73167
Harrisburg | 8 | Dauphin | 108527 | SR 3024 Resurface | 3024 | 004 | 409 Expanded Maintenance | UTL | 581 | 2027-01-14 |  | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000
Harrisburg | 8 | Dauphin | 109713 | I-81 River Relief Bridge 2 | 22 | 078 | Bridge Restoration | CON | NHPP | 2021-08-12 | 2021-08-12 | 405539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405539
Harrisburg | 8 | Dauphin | 109713 | I-81 River Relief Bridge 2 | 22 | 078 | Bridge Restoration | CON | STP | 2021-08-12 | 2021-08-12 | 244227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244227
Harrisburg | 8 | Dauphin | 109713 | I-81 River Relief Bridge 2 | 22 | 078 | Bridge Restoration | CON | STU | 2021-08-12 | 2021-08-12 | 153251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153251
Harrisburg | 8 | Dauphin | 111064 | HATS Bikeshare |  |  | Bicycle and Pedestrian Facilities Transit | CON | CAQ | 2023-01-01 |  | 120000 | 120000 | 160000 | 160000 | 0 | 0 | 0 | 0 | 0 | 560000
Harrisburg | 8 | Dauphin | 111655 | Paxtang Parkway Restoration |  | TAP | Transportation Enhancement | CON | TAP | 2025-07-24 | 2025-07-24 | 927173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 927173
Harrisburg | 8 | Dauphin | 112974 | SRTA Employment Access |  |  | Public Transit | CON | CAQ | 2019-04-05 |  | 0 | 336960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336960
Harrisburg | 8 | Dauphin | 113283 | Elizabethtown Rd Resurfacing | 743 | 039 | Highway Restoration | PE | 581 | 2027-09-16 |  | 541478 | 381000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 922478
Harrisburg | 8 | Dauphin | 113283 | Elizabethtown Rd Resurfacing | 743 | 039 | Highway Restoration | ROW | STP | 2027-09-16 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Harrisburg | 8 | Dauphin | 113283 | Elizabethtown Rd Resurfacing | 743 | 039 | Highway Restoration | UTL | STP | 2027-09-16 |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Harrisburg | 8 | Dauphin | 113283 | Elizabethtown Rd Resurfacing | 743 | 039 | Highway Restoration | CON | STP | 2027-09-16 |  | 0 | 0 | 1215236 | 1417664 | 1494637 | 0 | 0 | 0 | 0 | 4127537
Harrisburg | 8 | Dauphin | 113283 | Elizabethtown Rd Resurfacing | 743 | 039 | Highway Restoration | CON | STU | 2027-09-16 |  | 0 | 0 | 157596 | 895539 | 0 | 0 | 0 | 0 | 0 | 1053135
Harrisburg | 8 | Dauphin | 113384 | Sycamore/Paxton Intersection Imp | 3010 | 014 | Safety Improvement | UTL | NHPP | 2026-02-12 | 2026-02-12 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000
Harrisburg | 8 | Dauphin | 113384 | Sycamore/Paxton Intersection Imp | 3010 | 014 | Safety Improvement | CON | HVRU | 2026-02-12 | 2026-02-12 | 1085177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085177
Harrisburg | 8 | Dauphin | 113384 | Sycamore/Paxton Intersection Imp | 3010 | 014 | Safety Improvement | CON | NHPP | 2026-02-12 | 2026-02-12 | 630485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630485
Harrisburg | 8 | Dauphin | 113384 | Sycamore/Paxton Intersection Imp | 3010 | 014 | Safety Improvement | CON | STU | 2026-02-12 | 2026-02-12 | 0 | 368813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368813
Harrisburg | 8 | Dauphin | 114107 | SRTP Rideshare Program |  |  | Reserve Line Item | PRA | CAQ |  |  | 1472700 | 407148 | 403580 | 407616 | 411692 | 0 | 0 | 0 | 0 | 3102736
Harrisburg | 8 | Dauphin | 114107 | SRTP Rideshare Program |  |  | Reserve Line Item | PRA | STP |  |  | 176090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176090
Harrisburg | 8 | Dauphin | 114200 | HATS RTP Implementation Program |  |  | Reserve Line Item | CON | STU |  |  | 0 | 802492 | 2073045 | 1324765 | 0 | 0 | 0 | 0 | 0 | 4200302
Harrisburg | 8 | Dauphin | 114316 | Cameron/Maclay Intersec | 22 | 320 | Congestion Reduction | CON | NHPP | 2023-04-27 | 2023-04-27 | 235000 | 137827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372827
Harrisburg | 8 | Dauphin | 114316 | Cameron/Maclay Intersec | 22 | 320 | Congestion Reduction | CON | STP | 2023-04-27 | 2023-04-27 | 315000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315000
Harrisburg | 8 | Dauphin | 115784 | Capital Gateway | 3016 | 013 | Bicycle and Pedestrian Facilities Transit | CON | HSIP | 2024-04-18 | 2024-04-18 | 0 | 62199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62199
Harrisburg | 8 | Dauphin | 115784 | Capital Gateway | 3016 | 013 | Bicycle and Pedestrian Facilities Transit | CON | HVRU | 2024-04-18 | 2024-04-18 | 67023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67023
Harrisburg | 8 | Dauphin | 115785 | Derry Township Ped X-ing | 422 | 047 | Highway Restoration | CON | STP | 2024-04-11 | 2024-04-11 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
Harrisburg | 8 | Dauphin | 115790 | Union Deposit Impr | 3020 | 014 | Bicycle Pedestrian Highway | ROW | STU | 2026-04-09 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Harrisburg | 8 | Dauphin | 115790 | Union Deposit Impr | 3020 | 014 | Bicycle Pedestrian Highway | CON | STU | 2026-04-09 |  | 389063 | 833615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1222678
Harrisburg | 8 | Dauphin | 115797 | Highland St Connectivity | 3004 | 009 | Bicycle Pedestrian Highway | CON | STU | 2027-01-28 |  | 0 | 0 | 453675 | 0 | 0 | 0 | 0 | 0 | 0 | 453675
Harrisburg | 8 | Dauphin | 116786 | Middletown Rd Safety and Congestion Impr | 2003 | 033 | Highway Reconstruction | PE | STU | 2027-12-16 |  | 100576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100576
Harrisburg | 8 | Dauphin | 116786 | Middletown Rd Safety and Congestion Impr | 2003 | 033 | Highway Reconstruction | FD | STU | 2027-12-16 |  | 1325189 | 424811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000
Harrisburg | 8 | Dauphin | 116786 | Middletown Rd Safety and Congestion Impr | 2003 | 033 | Highway Reconstruction | ROW | STU | 2027-12-16 |  | 0 | 132597 | 742403 | 0 | 0 | 0 | 0 | 0 | 0 | 875000
Harrisburg | 8 | Dauphin | 116786 | Middletown Rd Safety and Congestion Impr | 2003 | 033 | Highway Reconstruction | UTL | STU | 2027-12-16 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Harrisburg | 8 | Dauphin | 116786 | Middletown Rd Safety and Congestion Impr | 2003 | 033 | Highway Reconstruction | CON | STP | 2027-12-16 |  | 0 | 0 | 0 | 1057362 | 0 | 0 | 0 | 0 | 0 | 1057362
Harrisburg | 8 | Dauphin | 116786 | Middletown Rd Safety and Congestion Impr | 2003 | 033 | Highway Reconstruction | CON | STU | 2027-12-16 |  | 0 | 0 | 0 | 3746373 | 5263667 | 1315917 | 0 | 0 | 0 | 10325957
Harrisburg | 8 | Dauphin | 116786 | Middletown Rd Safety and Congestion Impr | 2003 | 033 | Highway Reconstruction | CON | 581 | 2027-12-16 |  | 0 | 0 | 0 | 1200933 | 1315917 | 5263667 | 0 | 0 | 0 | 7780517
Harrisburg | 8 | Dauphin | 117160 | HATS Local Bridge Bundle |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000 | 2400000
Harrisburg | 8 | Dauphin | 117160 | HATS Local Bridge Bundle |  |  | Reserve Line Item | CON | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000
Harrisburg | 8 | Dauphin | 117189 | Nyes Rd ovr Beaver Creek | 2019 | 022 | Bridge Restoration | UTL | BRIP | 2026-01-15 | 2026-01-15 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Harrisburg | 8 | Dauphin | 117189 | Nyes Rd ovr Beaver Creek | 2019 | 022 | Bridge Restoration | CON | BRIP | 2026-01-15 | 2026-01-15 | 39673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39673
Harrisburg | 8 | Dauphin | 117189 | Nyes Rd ovr Beaver Creek | 2019 | 022 | Bridge Restoration | CON | 185 | 2026-01-15 | 2026-01-15 | 0 | 2499166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2499166
Harrisburg | 8 | Dauphin | 117196 | Walnut St ov Susq | 3034 | 004 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000
Harrisburg | 8 | Dauphin | 117196 | Walnut St ov Susq | 3034 | 004 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
Harrisburg | 8 | Dauphin | 117196 | Walnut St ov Susq | 3034 | 004 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4031749 | 0 | 4031749
Harrisburg | 8 | Dauphin | 117216 | Hillsdale Rd ov Trib Conewago Cr | 2001 | 018 | Bridge Replacement | FD | 185 | 2027-07-15 |  | 175000 | 109000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284000
Harrisburg | 8 | Dauphin | 117216 | Hillsdale Rd ov Trib Conewago Cr | 2001 | 018 | Bridge Replacement | ROW | 185 | 2027-07-15 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Harrisburg | 8 | Dauphin | 117216 | Hillsdale Rd ov Trib Conewago Cr | 2001 | 018 | Bridge Replacement | UTL | 185 | 2027-07-15 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Dauphin | 117216 | Hillsdale Rd ov Trib Conewago Cr | 2001 | 018 | Bridge Replacement | CON | 185 | 2027-07-15 |  | 0 | 0 | 530450 | 665240 | 0 | 0 | 0 | 0 | 0 | 1195690
Harrisburg | 8 | Dauphin | 117469 | Straws Church over Conley's Creek | 4004 | 017 | Bridge Restoration | PE | 185 | 2027-08-26 |  | 0 | 4024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4024
Harrisburg | 8 | Dauphin | 117469 | Straws Church over Conley's Creek | 4004 | 017 | Bridge Restoration | FD | 185 | 2027-08-26 |  | 215000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215000
Harrisburg | 8 | Dauphin | 117469 | Straws Church over Conley's Creek | 4004 | 017 | Bridge Restoration | ROW | 185 | 2027-08-26 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Harrisburg | 8 | Dauphin | 117469 | Straws Church over Conley's Creek | 4004 | 017 | Bridge Restoration | CON | 185 | 2027-08-26 |  | 0 | 0 | 630249 | 151309 | 0 | 0 | 0 | 0 | 0 | 781558
Harrisburg | 8 | Dauphin | 117578 | HATS Pipeline Priority Studies |  |  | Study Phase of Project | STUDY | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Harrisburg | 8 | Dauphin | 117612 | PA 743 and PA 341 Intersection HSM | 743 | 040 | Safety Improvement | PE | HSIP | 2027-11-04 |  | 633071 | 74990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 708061
Harrisburg | 8 | Dauphin | 117612 | PA 743 and PA 341 Intersection HSM | 743 | 040 | Safety Improvement | FD | HSIP | 2027-11-04 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Harrisburg | 8 | Dauphin | 117612 | PA 743 and PA 341 Intersection HSM | 743 | 040 | Safety Improvement | ROW | HSIP | 2027-11-04 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Dauphin | 117612 | PA 743 and PA 341 Intersection HSM | 743 | 040 | Safety Improvement | UTL | HSIP | 2027-11-04 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Harrisburg | 8 | Dauphin | 117612 | PA 743 and PA 341 Intersection HSM | 743 | 040 | Safety Improvement | CON | HSIP | 2027-11-04 |  | 0 | 0 | 1136737 | 1114281 | 0 | 0 | 0 | 0 | 0 | 2251018
Harrisburg | 8 | Dauphin | 117612 | PA 743 and PA 341 Intersection HSM | 743 | 040 | Safety Improvement | CON | STP | 2027-11-04 |  | 0 | 0 | 449130 | 0 | 0 | 0 | 0 | 0 | 0 | 449130
Harrisburg | 8 | Dauphin | 117663 | Derry Street over Spring Creek | 3012 | 037 | Bridge Restoration | PE | STU | 2027-09-16 |  | 246260 | 75565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321825
Harrisburg | 8 | Dauphin | 117663 | Derry Street over Spring Creek | 3012 | 037 | Bridge Restoration | FD | BRIP | 2027-09-16 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Harrisburg | 8 | Dauphin | 117663 | Derry Street over Spring Creek | 3012 | 037 | Bridge Restoration | ROW | 185 | 2027-09-16 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Harrisburg | 8 | Dauphin | 117663 | Derry Street over Spring Creek | 3012 | 037 | Bridge Restoration | UTL | 185 | 2027-09-16 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Harrisburg | 8 | Dauphin | 117663 | Derry Street over Spring Creek | 3012 | 037 | Bridge Restoration | CON | BRIP | 2027-09-16 |  | 0 | 0 | 800000 | 987661 | 0 | 0 | 0 | 0 | 0 | 1787661
Harrisburg | 8 | Dauphin | 117663 | Derry Street over Spring Creek | 3012 | 037 | Bridge Restoration | CON | STP | 2027-09-16 |  | 0 | 0 | 62670 | 0 | 0 | 0 | 0 | 0 | 0 | 62670
Harrisburg | 8 | Dauphin | 117663 | Derry Street over Spring Creek | 3012 | 037 | Bridge Restoration | CON | STU | 2027-09-16 |  | 0 | 0 | 169623 | 0 | 0 | 0 | 0 | 0 | 0 | 169623
Harrisburg | 8 | Dauphin | 117665 | Thirteenth Street over NS | 7301 | BRG | Bridge Replacement | PE | BOF | 2030-01-01 |  | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640000
Harrisburg | 8 | Dauphin | 117665 | Thirteenth Street over NS | 7301 | BRG | Bridge Replacement | PE | 183 | 2030-01-01 |  | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Harrisburg | 8 | Dauphin | 117665 | Thirteenth Street over NS | 7301 | BRG | Bridge Replacement | PE | LOC | 2030-01-01 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Harrisburg | 8 | Dauphin | 117665 | Thirteenth Street over NS | 7301 | BRG | Bridge Replacement | FD | BRIP | 2030-01-01 |  | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Harrisburg | 8 | Dauphin | 117665 | Thirteenth Street over NS | 7301 | BRG | Bridge Replacement | FD | 183 | 2030-01-01 |  | 0 | 0 | 112500 | 0 | 0 | 0 | 0 | 0 | 0 | 112500
Harrisburg | 8 | Dauphin | 117665 | Thirteenth Street over NS | 7301 | BRG | Bridge Replacement | FD | LOC | 2030-01-01 |  | 0 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 37500
Harrisburg | 8 | Dauphin | 117665 | Thirteenth Street over NS | 7301 | BRG | Bridge Replacement | CON | BOF | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 4527750 | 1681323 | 0 | 0 | 6209073
Harrisburg | 8 | Dauphin | 117665 | Thirteenth Street over NS | 7301 | BRG | Bridge Replacement | CON | 183 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 848953 | 315248 | 0 | 0 | 1164201
Harrisburg | 8 | Dauphin | 117667 | Market Street over Paxton Creek | 7301 | BRG | Bridge Replacement | PE | BRIP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
Harrisburg | 8 | Dauphin | 117667 | Market Street over Paxton Creek | 7301 | BRG | Bridge Replacement | PE | 183 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Dauphin | 117667 | Market Street over Paxton Creek | 7301 | BRG | Bridge Replacement | FD | BRIP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000
Harrisburg | 8 | Dauphin | 117667 | Market Street over Paxton Creek | 7301 | BRG | Bridge Replacement | FD | 183 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000
Harrisburg | 8 | Dauphin | 117667 | Market Street over Paxton Creek | 7301 | BRG | Bridge Replacement | CON | BRIP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3901652 | 3901652
Harrisburg | 8 | Dauphin | 117667 | Market Street over Paxton Creek | 7301 | BRG | Bridge Replacement | CON | 183 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 731560 | 731560
Harrisburg | 8 | Dauphin | 117672 | US 322/422 and Hershey Park Drive Interchange | 322 | 064 | Highway Reconstruction | PE | NHPP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2190000 | 2190000
Harrisburg | 8 | Dauphin | 117672 | US 322/422 and Hershey Park Drive Interchange | 322 | 064 | Highway Reconstruction | FD | NHPP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 3500000
Harrisburg | 8 | Dauphin | 117672 | US 322/422 and Hershey Park Drive Interchange | 322 | 064 | Highway Reconstruction | CON | NHPP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17306000 | 17306000
Harrisburg | 8 | Dauphin | 117708 | Harvey Taylor | 3016 | 014 | Bridge Preservation - Federal | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Dauphin | 117708 | Harvey Taylor | 3016 | 014 | Bridge Preservation - Federal | FD | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
Harrisburg | 8 | Dauphin | 117825 | I-283 ITS Fiber Inter | 283 | 017 | Intelligent Transportation System | CON | STP | 2024-05-23 | 2024-05-23 | 176900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176900
Harrisburg | 8 | Dauphin | 118276 | Eisenhower Bl Safety Improv | 441 | 037 | Safety Improvement | CON | HVRU | 2025-04-10 | 2025-04-10 | 133950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133950
Harrisburg | 8 | Dauphin | 118276 | Eisenhower Bl Safety Improv | 441 | 037 | Safety Improvement | CON | STP | 2025-04-10 | 2025-04-10 | 526343 | 327308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 853651
Harrisburg | 8 | Dauphin | 118276 | Eisenhower Bl Safety Improv | 441 | 037 | Safety Improvement | CON | STU | 2025-04-10 | 2025-04-10 | 1165074 | 128560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1293634
Harrisburg | 8 | Dauphin | 118502 | Herr St Ped Improv | 3018 | 005 | Bicycle Pedestrian Highway | CON | TAP | 2027-03-11 |  | 0 | 0 | 925000 | 0 | 0 | 0 | 0 | 0 | 0 | 925000
Harrisburg | 8 | Dauphin | 119216 | HATS MPO TIP Funded Bridge Repair Contract |  |  | Bridge Preservation - State Funded | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Dauphin | 119216 | HATS MPO TIP Funded Bridge Repair Contract |  |  | Bridge Preservation - State Funded | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 3000000
Harrisburg | 8 | Dauphin | 119283 | Carbon Reduction Program (CRP) HATS MPO RLI |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 602335 | 40000 | 0 | 640000 | 640000 | 640000 | 640000 | 2560000 | 5762335
Harrisburg | 8 | Dauphin | 119283 | Carbon Reduction Program (CRP) HATS MPO RLI |  |  | Reserve Line Item | CON | CRPU |  |  | 0 | 1278346 | 252000 | 0 | 1352000 | 1352000 | 1352000 | 1352000 | 5407000 | 12345346
Harrisburg | 8 | Dauphin | 119305 | Hummelstown Ped Impr | 2018 | 018 | Transportation Enhancement | PE | STU | 2027-09-30 |  | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000
Harrisburg | 8 | Dauphin | 119305 | Hummelstown Ped Impr | 2018 | 018 | Transportation Enhancement | FD | STU | 2027-09-30 |  | 0 | 63819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63819
Harrisburg | 8 | Dauphin | 119305 | Hummelstown Ped Impr | 2018 | 018 | Transportation Enhancement | UTL | STU | 2027-09-30 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Harrisburg | 8 | Dauphin | 119305 | Hummelstown Ped Impr | 2018 | 018 | Transportation Enhancement | CON | STU | 2027-09-30 |  | 0 | 0 | 0 | 732504 | 0 | 0 | 0 | 0 | 0 | 732504
Harrisburg | 8 | Dauphin | 119310 | Emaus Streetscape Project |  | LOC | Transportation Enhancement | PE | STU | 2027-11-04 |  | 169310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169310
Harrisburg | 8 | Dauphin | 119310 | Emaus Streetscape Project |  | LOC | Transportation Enhancement | FD | STU | 2027-11-04 |  | 0 | 0 | 38150 | 0 | 0 | 0 | 0 | 0 | 0 | 38150
Harrisburg | 8 | Dauphin | 119310 | Emaus Streetscape Project |  | LOC | Transportation Enhancement | UTL | STU | 2027-11-04 |  | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 2800
Harrisburg | 8 | Dauphin | 119310 | Emaus Streetscape Project |  | LOC | Transportation Enhancement | CON | STU | 2027-11-04 |  | 0 | 0 | 0 | 942731 | 0 | 0 | 0 | 0 | 0 | 942731
Harrisburg | 8 | Dauphin | 119484 | Clarks Ferry Interim Repairs | 22 | 104 | Bridge Restoration | CON | 185 | 2023-09-14 | 2023-09-14 | 707961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 707961
Harrisburg | 8 | Dauphin | 119783 | 22 Concrete Patching & Diamond Grinding | 22 | 105 | Highway Restoration | CON | 581 | 2028-01-13 |  | 0 | 0 | 2300065 | 2300065 | 2300066 | 0 | 0 | 0 | 0 | 6900196
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | PE | BOF | 2029-01-11 |  | 560000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560000
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | PE | 183 | 2029-01-11 |  | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | PE | LOC | 2029-01-11 |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | FD | BRIP | 2029-01-11 |  | 0 | 0 | 560000 | 0 | 0 | 0 | 0 | 0 | 0 | 560000
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | FD | 183 | 2029-01-11 |  | 0 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 105000
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | FD | LOC | 2029-01-11 |  | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | ROW | BRIP | 2029-01-11 |  | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | ROW | 183 | 2029-01-11 |  | 0 | 0 | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 11250
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | ROW | LOC | 2029-01-11 |  | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | UTL | BRIP | 2029-01-11 |  | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | UTL | 183 | 2029-01-11 |  | 0 | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 22500
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | UTL | LOC | 2029-01-11 |  | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | CON | BOF | 2029-01-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3103100 | 225540 | 0 | 3328640
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | CON | 183 | 2029-01-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 581832 | 42289 | 0 | 624121
Harrisburg | 8 | Dauphin | 120271 | Dauphin County Bridge Bundle | 7208 | BDL | Bridge Replacement | CON | LOC | 2029-01-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 193943 | 14096 | 0 | 208039
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | PE | BOF | 2029-01-11 |  | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | PE | 183 | 2029-01-11 |  | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52500
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | PE | LOC | 2029-01-11 |  | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17500
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | FD | BOF | 2029-01-11 |  | 0 | 114000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114000
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | FD | 183 | 2029-01-11 |  | 0 | 21375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21375
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | FD | LOC | 2029-01-11 |  | 0 | 7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7125
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | ROW | BOF | 2029-01-11 |  | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | ROW | 183 | 2029-01-11 |  | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | ROW | LOC | 2029-01-11 |  | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | UTL | BOF | 2029-01-11 |  | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | UTL | 183 | 2029-01-11 |  | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | UTL | LOC | 2029-01-11 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | CON | BOF | 2029-01-11 |  | 0 | 0 | 0 | 0 | 1128200 | 214008 | 0 | 0 | 0 | 1342208
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | CON | 183 | 2029-01-11 |  | 0 | 0 | 0 | 0 | 251664 | 0 | 0 | 0 | 0 | 251664
Harrisburg | 8 | Dauphin | 120307 | Kohn Road over Paxton Creek | 7101 | BRG | Bridge Replacement | CON | LOC | 2029-01-11 |  | 0 | 0 | 0 | 0 | 83888 | 0 | 0 | 0 | 0 | 83888
Harrisburg | 8 | Dauphin | 121186 | UPS for Existing Sites - HATS TSMO 2025-2026 | 81 | ITS | Intelligent Transportation System | PE | CRP | 2026-07-30 |  | 12320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12320
Harrisburg | 8 | Dauphin | 121186 | UPS for Existing Sites - HATS TSMO 2025-2026 | 81 | ITS | Intelligent Transportation System | PE | CRPU | 2026-07-30 |  | 33960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33960
Harrisburg | 8 | Dauphin | 121186 | UPS for Existing Sites - HATS TSMO 2025-2026 | 81 | ITS | Intelligent Transportation System | FD | CRP | 2026-07-30 |  | 0 | 37665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37665
Harrisburg | 8 | Dauphin | 121186 | UPS for Existing Sites - HATS TSMO 2025-2026 | 81 | ITS | Intelligent Transportation System | CON | CRP | 2026-07-30 |  | 0 | 70096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70096
Harrisburg | 8 | Dauphin | 121186 | UPS for Existing Sites - HATS TSMO 2025-2026 | 81 | ITS | Intelligent Transportation System | CON | CRPU | 2026-07-30 |  | 0 | 73654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73654
Harrisburg | 8 | Dauphin | 121399 | SR 3010 (Paxton Street) Resurfacing | 3010 | 018 | Highway Restoration | CON | NHPP | 2026-02-12 | 2026-02-12 | 787523 | 670076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1457599
Harrisburg | 8 | Dauphin | 121487 | Paxtang Parkway Trail Restoration Phase 3 TASA |  |  | Transportation Enhancement | CON | TAU | 2027-01-14 |  | 0 | 1076000 | 359400 | 0 | 0 | 0 | 0 | 0 | 0 | 1435400
Harrisburg | 8 | Dauphin | 121524 | Harrisburg City East-West Connection-Walnut Street |  |  | Bicycle and Pedestrian Facilities Transit | CON | TAP | 2027-06-24 |  | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Harrisburg | 8 | Dauphin | 121540 | Prince St. Pedestrian Mobility Improvements |  | TAP | Bicycle Pedestrian Highway | CON | TAP | 2027-06-10 |  | 0 | 0 | 1184767 | 0 | 0 | 0 | 0 | 0 | 0 | 1184767
Harrisburg | 8 | Dauphin | 122544 | Market St ov Juniata River Early Action | 849 | 021 | Bridge Preservation - Federal | ROW | PRTCT | 2026-09-03 |  | 0 | 16600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16600
Harrisburg | 8 | Dauphin | 122544 | Market St ov Juniata River Early Action | 849 | 021 | Bridge Preservation - Federal | CON | PRTCT | 2026-09-03 |  | 0 | 510000 | 510000 | 0 | 0 | 0 | 0 | 0 | 0 | 1020000
Harrisburg | 8 | Dauphin | 122854 | Dauphin County Department Force Box Culvert |  |  | Bridge Replacement | PE | 185 |  |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Harrisburg | 8 | Dauphin | 122926 | Operational and Maintenance Transit Facility |  |  | Public Transit | CON | STP |  |  | 1744800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1744800
Harrisburg | 8 | Dauphin | 122926 | Operational and Maintenance Transit Facility |  |  | Public Transit | CON | OTH-S |  |  | 422133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422133
Harrisburg | 8 | Dauphin | 122926 | Operational and Maintenance Transit Facility |  |  | Public Transit | CON | LOC |  |  | 14067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14067
Harrisburg | 8 | Dauphin | 123438 | City of Hbg Traffic Signal Retiming SS4A |  |  | Planning/Research/Administration | FD | SS4A |  |  | 0 | 300784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300784
Harrisburg | 8 | Dauphin | 123438 | City of Hbg Traffic Signal Retiming SS4A |  |  | Planning/Research/Administration | CON | SS4A |  |  | 0 | 654400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654400
Harrisburg | 8 | Dauphin | 123444 | Mountain Rd and I-81 SB Ramp Int Signal | 3019 | 013 | Safety Improvement | PE | HSIP | 2026-09-17 |  | 0 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000
Harrisburg | 8 | Dauphin | 123444 | Mountain Rd and I-81 SB Ramp Int Signal | 3019 | 013 | Safety Improvement | CON | HSIP | 2026-09-17 |  | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
Harrisburg | 8 | Perry | 20576 | Juniata Parkway ov Cocolamus Ck | 1015 | 009 | Bridge Replacement | PE | BOF | 2027-09-30 |  | 149189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149189
Harrisburg | 8 | Perry | 20576 | Juniata Parkway ov Cocolamus Ck | 1015 | 009 | Bridge Replacement | FD | BOF | 2027-09-30 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Harrisburg | 8 | Perry | 20576 | Juniata Parkway ov Cocolamus Ck | 1015 | 009 | Bridge Replacement | ROW | BOF | 2027-09-30 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Perry | 20576 | Juniata Parkway ov Cocolamus Ck | 1015 | 009 | Bridge Replacement | UTL | BOF | 2027-09-30 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Perry | 20576 | Juniata Parkway ov Cocolamus Ck | 1015 | 009 | Bridge Replacement | CON | BOF | 2027-09-30 |  | 0 | 0 | 986832 | 886984 | 320000 | 0 | 0 | 0 | 0 | 2193816
Harrisburg | 8 | Perry | 20576 | Juniata Parkway ov Cocolamus Ck | 1015 | 009 | Bridge Replacement | CON | STP | 2027-09-30 |  | 0 | 0 | 0 | 0 | 1726184 | 0 | 0 | 0 | 0 | 1726184
Harrisburg | 8 | Perry | 20578 | Center Road Bridge | 3001 | 055 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214000 | 214000
Harrisburg | 8 | Perry | 20578 | Center Road Bridge | 3001 | 055 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492735 | 492735
Harrisburg | 8 | Perry | 20579 | PA 34 over Little Buffalo | 34 | 067 | Bridge Replacement | FD | BRIP | 2027-05-20 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Perry | 20579 | PA 34 over Little Buffalo | 34 | 067 | Bridge Replacement | ROW | BRIP | 2027-05-20 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Harrisburg | 8 | Perry | 20579 | PA 34 over Little Buffalo | 34 | 067 | Bridge Replacement | UTL | BRIP | 2027-05-20 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Perry | 20579 | PA 34 over Little Buffalo | 34 | 067 | Bridge Replacement | CON | STP | 2027-05-20 |  | 0 | 0 | 2440551 | 1124073 | 0 | 0 | 0 | 0 | 0 | 3564624
Harrisburg | 8 | Perry | 63084 | Middle Ridge Road ov Big Buffalo Ck | 4008 | 023 | Bridge Restoration | FD | 185 | 2027-11-04 |  | 0 | 0 | 0 | 165000 | 0 | 0 | 0 | 0 | 0 | 165000
Harrisburg | 8 | Perry | 63084 | Middle Ridge Road ov Big Buffalo Ck | 4008 | 023 | Bridge Restoration | CON | BOF | 2027-11-04 |  | 0 | 0 | 1009431 | 1155529 | 2953539 | 0 | 0 | 0 | 0 | 5118499
Harrisburg | 8 | Perry | 79072 | Paradise Road Bridge | 2005 | 012 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
Harrisburg | 8 | Perry | 79072 | Paradise Road Bridge | 2005 | 012 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1762240 | 1762240
Harrisburg | 8 | Perry | 81012 | Weavers Mill Road Bridge | 3011 | 0 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378250 | 378250
Harrisburg | 8 | Perry | 81012 | Weavers Mill Road Bridge | 3011 | 0 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043000 | 2043000
Harrisburg | 8 | Perry | 87462 | State Road ov Fishing Ck | 11 | 131 | Bridge Preservation - Federal | PE | 185 | 2027-07-15 |  | 138871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138871
Harrisburg | 8 | Perry | 87462 | State Road ov Fishing Ck | 11 | 131 | Bridge Preservation - Federal | FD | 185 | 2027-07-15 |  | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275000
Harrisburg | 8 | Perry | 87462 | State Road ov Fishing Ck | 11 | 131 | Bridge Preservation - Federal | CON | 185 | 2027-07-15 |  | 0 | 0 | 232550 | 500000 | 0 | 0 | 0 | 0 | 0 | 732550
Harrisburg | 8 | Perry | 87479 | Juniata Parkway over Tributary to Juniata Rvr | 1015 | 020 | Bridge Replacement | FD | 185 | 2027-02-25 |  | 220159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220159
Harrisburg | 8 | Perry | 87479 | Juniata Parkway over Tributary to Juniata Rvr | 1015 | 020 | Bridge Replacement | ROW | 185 | 2027-02-25 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Harrisburg | 8 | Perry | 87479 | Juniata Parkway over Tributary to Juniata Rvr | 1015 | 020 | Bridge Replacement | UTL | 185 | 2027-02-25 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Harrisburg | 8 | Perry | 87479 | Juniata Parkway over Tributary to Juniata Rvr | 1015 | 020 | Bridge Replacement | CON | 185 | 2027-02-25 |  | 0 | 0 | 800190 | 24744 | 0 | 0 | 0 | 0 | 0 | 824934
Harrisburg | 8 | Perry | 87485 | PA 17 BR over Raccoon Crk | 17 | 020 | Bridge Replacement | FD | 185 | 2027-08-26 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Perry | 87485 | PA 17 BR over Raccoon Crk | 17 | 020 | Bridge Replacement | ROW | 185 | 2027-08-26 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Perry | 87485 | PA 17 BR over Raccoon Crk | 17 | 020 | Bridge Replacement | UTL | 185 | 2027-08-26 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Perry | 87485 | PA 17 BR over Raccoon Crk | 17 | 020 | Bridge Replacement | CON | 185 | 2027-08-26 |  | 0 | 0 | 0 | 0 | 0 | 841770 | 0 | 0 | 0 | 841770
Harrisburg | 8 | Perry | 87490 | Pisgah State Rd ov Trib to Shermans Ck | 3016 | 011 | Bridge Replacement | FD | 185 | 2027-02-25 |  | 265631 | 22499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288130
Harrisburg | 8 | Perry | 87490 | Pisgah State Rd ov Trib to Shermans Ck | 3016 | 011 | Bridge Replacement | ROW | BOF | 2027-02-25 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Harrisburg | 8 | Perry | 87490 | Pisgah State Rd ov Trib to Shermans Ck | 3016 | 011 | Bridge Replacement | UTL | BOF | 2027-02-25 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Perry | 87490 | Pisgah State Rd ov Trib to Shermans Ck | 3016 | 011 | Bridge Replacement | CON | BOF | 2027-02-25 |  | 0 | 0 | 1253168 | 0 | 0 | 0 | 0 | 0 | 0 | 1253168
Harrisburg | 8 | Perry | 90332 | Juniata Py ov Trib to Juniata Rvr | 1015 | 021 | Bridge Replacement | FD | 185 | 2029-06-07 |  | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Harrisburg | 8 | Perry | 90332 | Juniata Py ov Trib to Juniata Rvr | 1015 | 021 | Bridge Replacement | ROW | 185 | 2029-06-07 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Harrisburg | 8 | Perry | 90332 | Juniata Py ov Trib to Juniata Rvr | 1015 | 021 | Bridge Replacement | UTL | 185 | 2029-06-07 |  | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
Harrisburg | 8 | Perry | 90332 | Juniata Py ov Trib to Juniata Rvr | 1015 | 021 | Bridge Replacement | CON | 185 | 2029-06-07 |  | 0 | 0 | 0 | 0 | 1558064 | 0 | 0 | 0 | 0 | 1558064
Harrisburg | 8 | Perry | 90703 | Tuscarora Road Bridge | 17 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Harrisburg | 8 | Perry | 90704 | Raccoon Valley Rd Bridge1 | 17 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214000 | 214000
Harrisburg | 8 | Perry | 90706 | Raccoon Valley Rd ov Trib to Raccoon Ck | 17 | 019 | Bridge Preservation - Federal | FD | 185 | 2027-08-26 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Perry | 90706 | Raccoon Valley Rd ov Trib to Raccoon Ck | 17 | 019 | Bridge Preservation - Federal | ROW | 185 | 2027-08-26 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Perry | 90706 | Raccoon Valley Rd ov Trib to Raccoon Ck | 17 | 019 | Bridge Preservation - Federal | UTL | 185 | 2027-08-26 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Perry | 90706 | Raccoon Valley Rd ov Trib to Raccoon Ck | 17 | 019 | Bridge Preservation - Federal | CON | 185 | 2027-08-26 |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Harrisburg | 8 | Perry | 90708 | Spring Road Bridge 1 | 34 | 059 | Bridge Restoration | FD | 185 | 2029-09-06 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Harrisburg | 8 | Perry | 90708 | Spring Road Bridge 1 | 34 | 059 | Bridge Restoration | ROW | 185 | 2029-09-06 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Perry | 90708 | Spring Road Bridge 1 | 34 | 059 | Bridge Restoration | UTL | 185 | 2029-09-06 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Harrisburg | 8 | Perry | 90708 | Spring Road Bridge 1 | 34 | 059 | Bridge Restoration | CON | 185 | 2029-09-06 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 663491 | 0 | 0 | 1663491
Harrisburg | 8 | Perry | 90709 | Spring Road Bridge 2 | 34 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142750 | 142750
Harrisburg | 8 | Perry | 90710 | Carlisle Street Bridge | 34 | 049 | Bridge Replacement | CON | 185 | 2024-12-12 | 2024-12-12 | 1023483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1023483
Harrisburg | 8 | Perry | 90712 | Big Spring Rd Bridge 1 | 274 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178250 | 178250
Harrisburg | 8 | Perry | 90718 | Old Ferry Road Bridge | 1012 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214000 | 214000
Harrisburg | 8 | Perry | 90907 | Juniata Pkwy ov Trb Juniata River | 1015 | 022 | Bridge Preservation - State Funded | FD | 185 | 2027-02-25 |  | 176070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176070
Harrisburg | 8 | Perry | 90907 | Juniata Pkwy ov Trb Juniata River | 1015 | 022 | Bridge Preservation - State Funded | ROW | 185 | 2027-02-25 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Harrisburg | 8 | Perry | 90907 | Juniata Pkwy ov Trb Juniata River | 1015 | 022 | Bridge Preservation - State Funded | UTL | 185 | 2027-02-25 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Harrisburg | 8 | Perry | 90907 | Juniata Pkwy ov Trb Juniata River | 1015 | 022 | Bridge Preservation - State Funded | CON | 185 | 2027-02-25 |  | 0 | 0 | 235000 | 202318 | 0 | 0 | 0 | 0 | 0 | 437318
Harrisburg | 8 | Perry | 91396 | Pisgah State Road Bridge | 3016 | 0 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491592 | 491592
Harrisburg | 8 | Perry | 91397 | Cold Storage Rd ov Little Buffalo Ck | 4005 | 014 | Bridge Restoration | FD | BOF | 2027-10-07 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Perry | 91397 | Cold Storage Rd ov Little Buffalo Ck | 4005 | 014 | Bridge Restoration | CON | BOF | 2027-10-07 |  | 0 | 0 | 0 | 0 | 1113528 | 0 | 0 | 0 | 0 | 1113528
Harrisburg | 8 | Perry | 99893 | Sunbury Path Bridge | 17 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Perry | 99896 | Green Valley Run 1 Bridge | 74 | 0 | Bridge Preservation - State Funded | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Perry | 99947 | Fort Robinson Road Bridge | 850 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Perry | 99950 | Cove Creek Bridge | 11 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Perry | 99983 | Montour Creek Bridge | 274 | 028 | Bridge Replacement | CON | 185 | 2024-11-07 | 2024-11-07 | 317596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317596
Harrisburg | 8 | Perry | 100011 | Shermansdale Park-n-Ride | 34 | 044 | Air Quality | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 954810 | 954810
Harrisburg | 8 | Perry | 100266 | Susq Trail over PA-274 | 11 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Perry | 100271 | Susq Trail over Li Juni C | 11 | 132 | Bridge Preservation - Federal | PE | BRIP | 2028-01-27 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Harrisburg | 8 | Perry | 100271 | Susq Trail over Li Juni C | 11 | 132 | Bridge Preservation - Federal | FD | 185 | 2028-01-27 |  | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Harrisburg | 8 | Perry | 100271 | Susq Trail over Li Juni C | 11 | 132 | Bridge Preservation - Federal | ROW | 185 | 2028-01-27 |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Perry | 100271 | Susq Trail over Li Juni C | 11 | 132 | Bridge Preservation - Federal | UTL | 185 | 2028-01-27 |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Perry | 100271 | Susq Trail over Li Juni C | 11 | 132 | Bridge Preservation - Federal | CON | 185 | 2028-01-27 |  | 0 | 0 | 0 | 4422228 | 1459484 | 2457745 | 0 | 0 | 0 | 8339457
Harrisburg | 8 | Perry | 100271 | Susq Trail over Li Juni C | 11 | 132 | Bridge Preservation - Federal | CON | 581 | 2028-01-27 |  | 0 | 0 | 0 | 4470071 | 253546 | 0 | 0 | 0 | 0 | 4723617
Harrisburg | 8 | Perry | 100281 | Tuscarora Path over Pnthr | 17 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Perry | 100285 | Sunbury St over Susq Trib | 17 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Perry | 100300 | Waggoners Gap Rd over McC | 74 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Perry | 100304 | Waggoners Gap Rd over Bak | 74 | 070 | Bridge Replacement | CON | 185 | 2023-10-05 | 2023-10-05 | 16047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16047
Harrisburg | 8 | Perry | 100360 | Newport Road over Susqueh | 849 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Perry | 100360 | Newport Road over Susqueh | 849 | 0 | Bridge Preservation - Federal | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1076000 | 1076000
Harrisburg | 8 | Perry | 100368 | Pfoutz Valley Rd ov Cocolamus Ck | 1008 | 004 | Bridge Restoration | FD | BOF | 2028-06-08 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Harrisburg | 8 | Perry | 100368 | Pfoutz Valley Rd ov Cocolamus Ck | 1008 | 004 | Bridge Restoration | ROW | BOF | 2028-06-08 |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Perry | 100368 | Pfoutz Valley Rd ov Cocolamus Ck | 1008 | 004 | Bridge Restoration | UTL | BOF | 2028-06-08 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Perry | 100368 | Pfoutz Valley Rd ov Cocolamus Ck | 1008 | 004 | Bridge Restoration | CON | 185 | 2028-06-08 |  | 0 | 0 | 753641 | 0 | 0 | 0 | 0 | 0 | 0 | 753641
Harrisburg | 8 | Perry | 100377 | Chicken Hollow Rd over Tr | 1019 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Perry | 100441 | Hidden Valley Rd over Shm | 3010 | 012 | Bridge Replacement | CON | BOF | 2023-10-05 | 2023-10-05 | 506551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506551
Harrisburg | 8 | Perry | 100456 | Stone Arch Rd over Trib to Buffalo Crk | 4007 | 018 | Bridge Restoration | FD | BOF | 2027-02-11 |  | 100000 | 183672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283672
Harrisburg | 8 | Perry | 100456 | Stone Arch Rd over Trib to Buffalo Crk | 4007 | 018 | Bridge Restoration | ROW | BOF | 2027-02-11 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Perry | 100456 | Stone Arch Rd over Trib to Buffalo Crk | 4007 | 018 | Bridge Restoration | UTL | BOF | 2027-02-11 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Harrisburg | 8 | Perry | 100456 | Stone Arch Rd over Trib to Buffalo Crk | 4007 | 018 | Bridge Restoration | CON | STP | 2027-02-11 |  | 0 | 0 | 700000 | 766912 | 0 | 0 | 0 | 0 | 0 | 1466912
Harrisburg | 8 | Perry | 101093 | Spring Road over Little J | 34 | 047 | Bridge Replacement | CON | BRIP | 2024-12-12 | 2024-12-12 | 2323353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2323353
Harrisburg | 8 | Perry | 101104 | Landisburg Rd ov BakeTrib | 850 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Perry | 101108 | PA 850 over Trib Shermans | 850 | 015 | Bridge Replacement | CON | 185 | 2024-11-07 | 2024-11-07 | 594117 | 395753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 989870
Harrisburg | 8 | Perry | 101121 | Bucks Valley Road over Ho | 1018 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Harrisburg | 8 | Perry | 105347 | Creek Road Resurface | 849 | 0 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2058888 | 2058888
Harrisburg | 8 | Perry | 105347 | Creek Road Resurface | 849 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514722 | 514722
Harrisburg | 8 | Perry | 106558 | Center Rd Bridge T-403 | 7210 | BRG | Bridge Replacement | ROW | BOF | 2026-10-22 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Harrisburg | 8 | Perry | 106558 | Center Rd Bridge T-403 | 7210 | BRG | Bridge Replacement | ROW | 183 | 2026-10-22 |  | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
Harrisburg | 8 | Perry | 106558 | Center Rd Bridge T-403 | 7210 | BRG | Bridge Replacement | ROW | LOC | 2026-10-22 |  | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
Harrisburg | 8 | Perry | 106558 | Center Rd Bridge T-403 | 7210 | BRG | Bridge Replacement | UTL | BOF | 2026-10-22 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Harrisburg | 8 | Perry | 106558 | Center Rd Bridge T-403 | 7210 | BRG | Bridge Replacement | UTL | 183 | 2026-10-22 |  | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
Harrisburg | 8 | Perry | 106558 | Center Rd Bridge T-403 | 7210 | BRG | Bridge Replacement | UTL | LOC | 2026-10-22 |  | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
Harrisburg | 8 | Perry | 106558 | Center Rd Bridge T-403 | 7210 | BRG | Bridge Replacement | CON | BRIP | 2026-10-22 |  | 0 | 0 | 1017521 | 334723 | 0 | 0 | 0 | 0 | 0 | 1352244
Harrisburg | 8 | Perry | 106558 | Center Rd Bridge T-403 | 7210 | BRG | Bridge Replacement | CON | 183 | 2026-10-22 |  | 0 | 0 | 190785 | 62761 | 0 | 0 | 0 | 0 | 0 | 253546
Harrisburg | 8 | Perry | 108605 | Scheaffers Valley Rd Resf | 233 | 022 | Highway Restoration | ROW | 581 | 2025-10-09 | 2025-10-09 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500
Harrisburg | 8 | Perry | 108605 | Scheaffers Valley Rd Resf | 233 | 022 | Highway Restoration | UTL | 581 | 2025-10-09 | 2025-10-09 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
Harrisburg | 8 | Perry | 108605 | Scheaffers Valley Rd Resf | 233 | 022 | Highway Restoration | CON | STP | 2025-10-09 | 2025-10-09 | 5419282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5419282
Harrisburg | 8 | Perry | 108605 | Scheaffers Valley Rd Resf | 233 | 022 | Highway Restoration | CON | STU | 2025-10-09 | 2025-10-09 | 663168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 663168
Harrisburg | 8 | Perry | 113299 | Big Spring Road Resurface 2 | 274 | 030 | Highway Restoration | CON | STU | 2024-09-26 | 2024-09-26 | 0 | 28270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28270
Harrisburg | 8 | Perry | 114321 | PA 34 Safety Improvements and Resurfacing | 34 | 060 | Safety Improvement | PE | HSIP | 2029-09-06 |  | 815282 | 809220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1624502
Harrisburg | 8 | Perry | 114321 | PA 34 Safety Improvements and Resurfacing | 34 | 060 | Safety Improvement | PE | STP | 2029-09-06 |  | 439 | 678906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679345
Harrisburg | 8 | Perry | 114321 | PA 34 Safety Improvements and Resurfacing | 34 | 060 | Safety Improvement | FD | 581 | 2029-09-06 |  | 0 | 0 | 2700000 | 0 | 0 | 0 | 0 | 0 | 0 | 2700000
Harrisburg | 8 | Perry | 114321 | PA 34 Safety Improvements and Resurfacing | 34 | 060 | Safety Improvement | ROW | STP | 2029-09-06 |  | 0 | 0 | 0 | 600000 | 600000 | 0 | 0 | 0 | 0 | 1200000
Harrisburg | 8 | Perry | 114321 | PA 34 Safety Improvements and Resurfacing | 34 | 060 | Safety Improvement | UTL | STP | 2029-09-06 |  | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
Harrisburg | 8 | Perry | 114321 | PA 34 Safety Improvements and Resurfacing | 34 | 060 | Safety Improvement | CON | HSIP | 2029-09-06 |  | 0 | 0 | 0 | 0 | 0 | 3825000 | 3825000 | 3049237 | 0 | 10699237
Harrisburg | 8 | Perry | 114321 | PA 34 Safety Improvements and Resurfacing | 34 | 060 | Safety Improvement | CON | STP | 2029-09-06 |  | 0 | 0 | 0 | 0 | 0 | 1912500 | 449130 | 6739133 | 0 | 9100763
Harrisburg | 8 | Perry | 115791 | S Main St Bridge Imp |  |  | Bridge Replacement | CON | BRIP | 2027-03-25 |  | 0 | 0 | 1395631 | 0 | 0 | 0 | 0 | 0 | 0 | 1395631
Harrisburg | 8 | Perry | 115794 | Market Street Improvements (Newport) | 4008 | 032 | Bicycle Pedestrian Highway | CON | STP | 2028-03-23 |  | 0 | 0 | 384771 | 0 | 0 | 0 | 0 | 0 | 0 | 384771
Harrisburg | 8 | Perry | 117225 | US 22 ov Cocolamus Cr | 22 | 101 | Bridge Preservation - State Funded | FD | 185 | 2027-06-10 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Harrisburg | 8 | Perry | 117225 | US 22 ov Cocolamus Cr | 22 | 101 | Bridge Preservation - State Funded | ROW | 185 | 2027-06-10 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Harrisburg | 8 | Perry | 117225 | US 22 ov Cocolamus Cr | 22 | 101 | Bridge Preservation - State Funded | UTL | 185 | 2027-06-10 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Perry | 117225 | US 22 ov Cocolamus Cr | 22 | 101 | Bridge Preservation - State Funded | CON | 185 | 2027-06-10 |  | 0 | 0 | 693571 | 1449935 | 1440494 | 0 | 0 | 0 | 0 | 3584000
Harrisburg | 8 | Perry | 117251 | Juniata over Howe Run | 1015 | 023 | Bridge Restoration | FD | 185 | 2027-02-25 |  | 196725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196725
Harrisburg | 8 | Perry | 117251 | Juniata over Howe Run | 1015 | 023 | Bridge Restoration | ROW | 185 | 2027-02-25 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Harrisburg | 8 | Perry | 117251 | Juniata over Howe Run | 1015 | 023 | Bridge Restoration | UTL | 185 | 2027-02-25 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Harrisburg | 8 | Perry | 117251 | Juniata over Howe Run | 1015 | 023 | Bridge Restoration | CON | 185 | 2027-02-25 |  | 0 | 0 | 210896 | 0 | 0 | 0 | 0 | 0 | 0 | 210896
Harrisburg | 8 | Perry | 117545 | PA 34 over Juniata River | 34 | 069 | Bridge Replacement | PE | BRIP | 2029-06-07 |  | 0 | 1095631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1095631
Harrisburg | 8 | Perry | 117545 | PA 34 over Juniata River | 34 | 069 | Bridge Replacement | PE | STP | 2029-06-07 |  | 0 | 124582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124582
Harrisburg | 8 | Perry | 117545 | PA 34 over Juniata River | 34 | 069 | Bridge Replacement | FD | 581 | 2029-06-07 |  | 0 | 0 | 0 | 550000 | 1450000 | 0 | 0 | 0 | 0 | 2000000
Harrisburg | 8 | Perry | 117545 | PA 34 over Juniata River | 34 | 069 | Bridge Replacement | CON | 185 | 2029-06-07 |  | 0 | 0 | 0 | 0 | 2833241 | 4387004 | 6531731 | 7364109 | 8043032 | 29159117
Harrisburg | 8 | Perry | 117545 | PA 34 over Juniata River | 34 | 069 | Bridge Replacement | CON | 581 | 2029-06-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 840883 | 0 | 0 | 840883
Harrisburg | 8 | Perry | 117824 | US 22/322 Devices | 22 | 103 | Intelligent Transportation System | CON | STP | 2024-05-23 | 2024-05-23 | 0 | 222030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222030
Harrisburg | 8 | Perry | 118787 | Market and 6th St | 4008 | 031 | Highway Reconstruction | PE | 581 | 2028-03-23 |  | 71529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71529
Harrisburg | 8 | Perry | 118787 | Market and 6th St | 4008 | 031 | Highway Reconstruction | UTL | 581 | 2028-03-23 |  | 39145 | 720855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760000
Harrisburg | 8 | Perry | 118787 | Market and 6th St | 4008 | 031 | Highway Reconstruction | UTL | LOC | 2028-03-23 |  | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060
Harrisburg | 8 | Perry | 118787 | Market and 6th St | 4008 | 031 | Highway Reconstruction | CON | 581 | 2028-03-23 |  | 0 | 0 | 1296514 | 460449 | 0 | 0 | 0 | 0 | 0 | 1756963
Harrisburg | 8 | Perry | 119311 | Perry County Covered Bridges | 7211 | COV | Bridge Restoration | PE | BOF | 2029-10-18 |  | 0 | 1120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120000
Harrisburg | 8 | Perry | 119311 | Perry County Covered Bridges | 7211 | COV | Bridge Restoration | PE | BRIP | 2029-10-18 |  | 237600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237600
Harrisburg | 8 | Perry | 119311 | Perry County Covered Bridges | 7211 | COV | Bridge Restoration | FD | BRIP | 2029-10-18 |  | 126720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126720
Harrisburg | 8 | Perry | 119311 | Perry County Covered Bridges | 7211 | COV | Bridge Restoration | CON | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 1542204 | 0 | 0 | 0 | 1542204
Harrisburg | 8 | Perry | 119313 | Sidewalks and Curbs Reconstruction Phase 2 | 849 | 022 | Transportation Enhancement | CON | STP | 2026-11-05 |  | 0 | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520000
Harrisburg | 8 | Perry | 119784 | Susquehanna Trail Restoration | 11 | 141 | Highway Restoration | PE | 581 | 2028-11-09 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Harrisburg | 8 | Perry | 119784 | Susquehanna Trail Restoration | 11 | 141 | Highway Restoration | CON | 581 | 2028-11-09 |  | 0 | 0 | 0 | 2471255 | 5064789 | 7658325 | 0 | 0 | 0 | 15194369
Harrisburg | 8 | Perry | 120273 | Perry County Bridge Bundle | 7219 | BND | Bridge Replacement | PE | BOF | 2029-09-27 |  | 876800 | 960000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836800
Harrisburg | 8 | Perry | 120273 | Perry County Bridge Bundle | 7219 | BND | Bridge Replacement | PE | 183 | 2029-09-27 |  | 164400 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344400
Harrisburg | 8 | Perry | 120273 | Perry County Bridge Bundle | 7219 | BND | Bridge Replacement | PE | LOC | 2029-09-27 |  | 54800 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114800
Harrisburg | 8 | Perry | 120273 | Perry County Bridge Bundle | 7219 | BND | Bridge Replacement | FD | BOF | 2029-09-27 |  | 0 | 182586 | 65773 | 310041 | 0 | 0 | 0 | 0 | 0 | 558400
Harrisburg | 8 | Perry | 120273 | Perry County Bridge Bundle | 7219 | BND | Bridge Replacement | FD | 183 | 2029-09-27 |  | 0 | 104700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104700
Harrisburg | 8 | Perry | 120273 | Perry County Bridge Bundle | 7219 | BND | Bridge Replacement | CON | BOF | 2029-09-27 |  | 0 | 0 | 0 | 0 | 0 | 2164960 | 0 | 2324545 | 0 | 4489505
Harrisburg | 8 | Perry | 120273 | Perry County Bridge Bundle | 7219 | BND | Bridge Replacement | CON | 183 | 2029-09-27 |  | 0 | 0 | 0 | 0 | 0 | 202065 | 202965 | 435853 | 0 | 840883
Harrisburg | 8 | Perry | 121179 | SR 34 Bridge over Juniata River Repairs | 34 | 073 | Bridge Preservation - State Funded | CON | 185 | 2024-11-07 | 2024-11-07 | 178233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178233
Harrisburg | 8 | Perry | 121672 | SR 34 over Little Buffalo Creek Emergency Repairs | 34 | 074 | Bridge Preservation - State Funded | CON | 185 |  | 2024-01-25 | 17888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17888
Harrisburg | 8 | Perry | 122258 | PA 34 Spring Rd Resurface | 34 | 075 | Highway Restoration | PE | 581 | 2026-05-21 |  | 274863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274863
Harrisburg | 8 | Perry | 122258 | PA 34 Spring Rd Resurface | 34 | 075 | Highway Restoration | CON | 581 | 2026-05-21 |  | 0 | 5490888 | 559112 | 0 | 0 | 0 | 0 | 0 | 0 | 6050000
Harrisburg | 8 | Perry | 122522 | PA 34 Resurfacing Perry Co | 34 | 076 | 409 Expanded Maintenance | PE | 581 | 2026-06-04 |  | 0 | 36342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36342
Harrisburg | 8 | Perry | 122623 | Bloomfield Ave over Little Buffalo Creek | 7211 | BRG | Bridge Replacement | PE | BRIP | 2029-01-01 |  | 260000 | 92036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352036
Harrisburg | 8 | Perry | 122623 | Bloomfield Ave over Little Buffalo Creek | 7211 | BRG | Bridge Replacement | PE | 183 | 2029-01-01 |  | 48750 | 17257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66007
Harrisburg | 8 | Perry | 122623 | Bloomfield Ave over Little Buffalo Creek | 7211 | BRG | Bridge Replacement | PE | LOC | 2029-01-01 |  | 16250 | 5752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22002
Harrisburg | 8 | Perry | 122623 | Bloomfield Ave over Little Buffalo Creek | 7211 | BRG | Bridge Replacement | FD | BOF | 2029-01-01 |  | 0 | 172000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172000
Harrisburg | 8 | Perry | 122623 | Bloomfield Ave over Little Buffalo Creek | 7211 | BRG | Bridge Replacement | FD | 183 | 2029-01-01 |  | 0 | 32250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32250
Harrisburg | 8 | Perry | 122623 | Bloomfield Ave over Little Buffalo Creek | 7211 | BRG | Bridge Replacement | CON | STP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 598000 | 0 | 0 | 0 | 0 | 598000
Harrisburg | 8 | Perry | 122623 | Bloomfield Ave over Little Buffalo Creek | 7211 | BRG | Bridge Replacement | CON | 183 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 112125 | 0 | 0 | 0 | 0 | 112125
Harrisburg | 8 | Perry | 122855 | Perry County Department Force Box Culvert |  |  | Bridge Replacement | PE | 185 |  |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Johnstown | 9 | Cambria | 22338 | SR 4007 over California Run | 4007 | 01B | Bridge Restoration | PE | 185 | 2030-01-17 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 22338 | SR 4007 over California Run | 4007 | 01B | Bridge Restoration | ROW | 185 | 2030-01-17 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 22338 | SR 4007 over California Run | 4007 | 01B | Bridge Restoration | UTL | 185 | 2030-01-17 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 22338 | SR 4007 over California Run | 4007 | 01B | Bridge Restoration | CON | BOF | 2030-01-17 |  | 0 | 0 | 0 | 0 | 0 | 720000 | 0 | 0 | 0 | 720000
Johnstown | 9 | Cambria | 22380 | Sonman Avenue over Trout Run | 7423 | SON | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 128000 | 0 | 0 | 0 | 0 | 0 | 128000
Johnstown | 9 | Cambria | 22380 | Sonman Avenue over Trout Run | 7423 | SON | Bridge Restoration | PE | 183 |  |  | 0 | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 24000
Johnstown | 9 | Cambria | 22380 | Sonman Avenue over Trout Run | 7423 | SON | Bridge Restoration | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 72000
Johnstown | 9 | Cambria | 22380 | Sonman Avenue over Trout Run | 7423 | SON | Bridge Restoration | FD | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 13500 | 0 | 0 | 0 | 13500
Johnstown | 9 | Cambria | 22380 | Sonman Avenue over Trout Run | 7423 | SON | Bridge Restoration | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Johnstown | 9 | Cambria | 22380 | Sonman Avenue over Trout Run | 7423 | SON | Bridge Restoration | ROW | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 3750
Johnstown | 9 | Cambria | 22380 | Sonman Avenue over Trout Run | 7423 | SON | Bridge Restoration | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Johnstown | 9 | Cambria | 22380 | Sonman Avenue over Trout Run | 7423 | SON | Bridge Restoration | UTL | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 3750
Johnstown | 9 | Cambria | 22380 | Sonman Avenue over Trout Run | 7423 | SON | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 592000 | 0 | 0 | 592000
Johnstown | 9 | Cambria | 22380 | Sonman Avenue over Trout Run | 7423 | SON | Bridge Restoration | CON | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 148000 | 0 | 0 | 148000
Johnstown | 9 | Cambria | 22391 | T-406 Jamestown Rd over NSRR | 7220 | 406 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 405183 | 0 | 0 | 0 | 0 | 0 | 405183
Johnstown | 9 | Cambria | 22391 | T-406 Jamestown Rd over NSRR | 7220 | 406 | Bridge Restoration | PE | 183 |  |  | 0 | 0 | 0 | 75972 | 0 | 0 | 0 | 0 | 0 | 75972
Johnstown | 9 | Cambria | 22391 | T-406 Jamestown Rd over NSRR | 7220 | 406 | Bridge Restoration | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 160000
Johnstown | 9 | Cambria | 22391 | T-406 Jamestown Rd over NSRR | 7220 | 406 | Bridge Restoration | FD | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000
Johnstown | 9 | Cambria | 22391 | T-406 Jamestown Rd over NSRR | 7220 | 406 | Bridge Restoration | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 160000
Johnstown | 9 | Cambria | 22391 | T-406 Jamestown Rd over NSRR | 7220 | 406 | Bridge Restoration | ROW | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000
Johnstown | 9 | Cambria | 22391 | T-406 Jamestown Rd over NSRR | 7220 | 406 | Bridge Restoration | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 160000
Johnstown | 9 | Cambria | 22391 | T-406 Jamestown Rd over NSRR | 7220 | 406 | Bridge Restoration | UTL | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000
Johnstown | 9 | Cambria | 22391 | T-406 Jamestown Rd over NSRR | 7220 | 406 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2491898 | 299364 | 0 | 2791262
Johnstown | 9 | Cambria | 22391 | T-406 Jamestown Rd over NSRR | 7220 | 406 | Bridge Restoration | CON | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 523361 | 0 | 0 | 523361
Johnstown | 9 | Cambria | 22391 | T-406 Jamestown Rd over NSRR | 7220 | 406 | Bridge Restoration | CON | LOC |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 174454 | 0 | 0 | 174454
Johnstown | 9 | Cambria | 22437 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | BOF |  |  | 0 | 146118 | 1887994 | 0 | 0 | 1531207 | 582157 | 0 | 1000000 | 5147476
Johnstown | 9 | Cambria | 22437 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424901 | 1000000 | 1424901
Johnstown | 9 | Cambria | 22437 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | CAQ |  |  | 0 | 0 | 0 | 978854 | 1362000 | 1362000 | 1362000 | 1362000 | 5447000 | 11873854
Johnstown | 9 | Cambria | 22437 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | HSIP |  |  | 0 | 0 | 0 | 23000 | 1108000 | 1108000 | 1108000 | 1108000 | 4431000 | 8886000
Johnstown | 9 | Cambria | 22437 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | HVRU |  |  | 0 | 0 | 0 | 124940 | 0 | 0 | 0 | 0 | 0 | 124940
Johnstown | 9 | Cambria | 22437 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Johnstown | 9 | Cambria | 22437 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | STP |  |  | 0 | 0 | 167351 | 118378 | 0 | 0 | 0 | 0 | 1000000 | 1285729
Johnstown | 9 | Cambria | 22437 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 84514 | 135800 | 0 | 220314
Johnstown | 9 | Cambria | 22437 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 672351 | 1224932 | 584235 | 576000 | 0 | 0 | 0 | 3057518
Johnstown | 9 | Cambria | 22437 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | 581 |  |  | 0 | 1151725 | 0 | 65000 | 16621 | 473793 | 2201843 | 0 | 1000000 | 4908982
Johnstown | 9 | Cambria | 22437 | Bridge & Highway Reserve |  | BHR | Reserve Line Item | CON | LOC |  |  | 0 | 0 | 32000 | 0 | 28000 | 144000 | 16251 | 45266 | 0 | 265517
Johnstown | 9 | Cambria | 22445 | Dutch Rd Bridge Replace | 1009 | 01B | Bridge Restoration | CON | BOF | 2023-07-27 | 2023-07-27 | 14591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14591
Johnstown | 9 | Cambria | 22478 | SR 1021 over Beaverdam Run | 1021 | 0 | Bridge Restoration | PE | BRIP | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 700000
Johnstown | 9 | Cambria | 22478 | SR 1021 over Beaverdam Run | 1021 | 0 | Bridge Restoration | FD | BRIP | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000
Johnstown | 9 | Cambria | 22478 | SR 1021 over Beaverdam Run | 1021 | 0 | Bridge Restoration | CON | BRIP | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4167000 | 4167000
Johnstown | 9 | Cambria | 22491 | Franklin Borough Clapboard | 3026 | 02B | Bridge Restoration | ROW | 185 | 2028-10-05 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 22491 | Franklin Borough Clapboard | 3026 | 02B | Bridge Restoration | UTL | 185 | 2028-10-05 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 22491 | Franklin Borough Clapboard | 3026 | 02B | Bridge Restoration | CON | BRIP | 2028-10-05 |  | 0 | 0 | 0 | 0 | 594898 | 750102 | 0 | 0 | 0 | 1345000
Johnstown | 9 | Cambria | 22532 | SR 3035 over Little Conemaugh River | 3035 | 02B | Bridge Restoration | PE | BOF | 2033-01-06 |  | 0 | 0 | 0 | 405817 | 100000 | 0 | 0 | 0 | 0 | 505817
Johnstown | 9 | Cambria | 22532 | SR 3035 over Little Conemaugh River | 3035 | 02B | Bridge Restoration | FD | BOF | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 58000 | 322000 | 0 | 0 | 380000
Johnstown | 9 | Cambria | 22532 | SR 3035 over Little Conemaugh River | 3035 | 02B | Bridge Restoration | ROW | BOF | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 22532 | SR 3035 over Little Conemaugh River | 3035 | 02B | Bridge Restoration | UTL | BOF | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 22532 | SR 3035 over Little Conemaugh River | 3035 | 02B | Bridge Restoration | CON | BOF | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1400000 | 2000000 | 3900000
Johnstown | 9 | Cambria | 22570 | N Br Conemaugh Rn Br | 2014 | 07B | Bridge Restoration | PE | 185 | 2029-09-13 |  | 0 | 246155 | 153845 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Johnstown | 9 | Cambria | 22570 | N Br Conemaugh Rn Br | 2014 | 07B | Bridge Restoration | ROW | 185 | 2029-09-13 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 22570 | N Br Conemaugh Rn Br | 2014 | 07B | Bridge Restoration | UTL | 185 | 2029-09-13 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 22570 | N Br Conemaugh Rn Br | 2014 | 07B | Bridge Restoration | CON | 185 | 2029-09-13 |  | 0 | 0 | 0 | 0 | 1395000 | 0 | 0 | 0 | 0 | 1395000
Johnstown | 9 | Cambria | 22595 | SR 2015 over Little Conemaugh River | 2015 | 03B | Bridge Restoration | PE | 185 | 2030-02-14 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 22595 | SR 2015 over Little Conemaugh River | 2015 | 03B | Bridge Restoration | ROW | 185 | 2030-02-14 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 22595 | SR 2015 over Little Conemaugh River | 2015 | 03B | Bridge Restoration | UTL | 185 | 2030-02-14 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 22595 | SR 2015 over Little Conemaugh River | 2015 | 03B | Bridge Restoration | CON | BRIP | 2030-02-14 |  | 0 | 0 | 0 | 0 | 0 | 720000 | 0 | 0 | 0 | 720000
Johnstown | 9 | Cambria | 22622 | PA 53 Pattys Run Bridge | 53 | 29B | Bridge Restoration | PE | 185 | 2028-01-13 |  | 262266 | 237734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Johnstown | 9 | Cambria | 22622 | PA 53 Pattys Run Bridge | 53 | 29B | Bridge Restoration | FD | 185 | 2028-01-13 |  | 0 | 0 | 0 | 178176 | 0 | 0 | 0 | 0 | 0 | 178176
Johnstown | 9 | Cambria | 22622 | PA 53 Pattys Run Bridge | 53 | 29B | Bridge Restoration | ROW | 185 | 2028-01-13 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 22622 | PA 53 Pattys Run Bridge | 53 | 29B | Bridge Restoration | UTL | 185 | 2028-01-13 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 22622 | PA 53 Pattys Run Bridge | 53 | 29B | Bridge Restoration | CON | BRIP | 2028-01-13 |  | 0 | 0 | 0 | 570000 | 755000 | 0 | 0 | 0 | 0 | 1325000
Johnstown | 9 | Cambria | 22633 | SR 1027 over Burgoon Run | 1027 | 01B | Bridge Restoration | PE | 185 | 2028-10-19 |  | 350000 | 67168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417168
Johnstown | 9 | Cambria | 22633 | SR 1027 over Burgoon Run | 1027 | 01B | Bridge Restoration | FD | BOF | 2028-10-19 |  | 0 | 0 | 202006 | 0 | 0 | 0 | 0 | 0 | 0 | 202006
Johnstown | 9 | Cambria | 22633 | SR 1027 over Burgoon Run | 1027 | 01B | Bridge Restoration | ROW | BOF | 2028-10-19 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 22633 | SR 1027 over Burgoon Run | 1027 | 01B | Bridge Restoration | UTL | BOF | 2028-10-19 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 22633 | SR 1027 over Burgoon Run | 1027 | 01B | Bridge Restoration | CON | BOF | 2028-10-19 |  | 0 | 0 | 0 | 185000 | 1480000 | 0 | 0 | 0 | 0 | 1665000
Johnstown | 9 | Cambria | 67240 | Reed Street Bridge Replacement | 7227 | 513 | Bridge Restoration | CON | 411 | 2025-09-25 |  | 348275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348275
Johnstown | 9 | Cambria | 67240 | Reed Street Bridge Replacement | 7227 | 513 | Bridge Restoration | CON | LOC | 2025-09-25 |  | 104485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104485
Johnstown | 9 | Cambria | 74509 | T-405 Hinckston Run Bridge | 7213 | 405 | Bridge Replacement | CON | LOC |  |  | 0 | 626010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626010
Johnstown | 9 | Cambria | 88597 | Brubaker Run Bridge | 53 | 25B | Bridge Replacement | FD | 185 | 2027-12-09 |  | 0 | 193433 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 245933
Johnstown | 9 | Cambria | 88597 | Brubaker Run Bridge | 53 | 25B | Bridge Replacement | ROW | 185 | 2027-12-09 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Johnstown | 9 | Cambria | 88597 | Brubaker Run Bridge | 53 | 25B | Bridge Replacement | UTL | 185 | 2027-12-09 |  | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000
Johnstown | 9 | Cambria | 88597 | Brubaker Run Bridge | 53 | 25B | Bridge Replacement | CON | 185 | 2027-12-09 |  | 0 | 0 | 0 | 1064000 | 709765 | 0 | 0 | 0 | 0 | 1773765
Johnstown | 9 | Cambria | 88696 | PA160 Conemaugh Rvr Culv | 160 | 18B | Bridge Replacement | FD | 185 | 2026-01-15 | 2026-01-15 | 285000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285000
Johnstown | 9 | Cambria | 88696 | PA160 Conemaugh Rvr Culv | 160 | 18B | Bridge Replacement | ROW | 185 | 2026-01-15 | 2026-01-15 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 88696 | PA160 Conemaugh Rvr Culv | 160 | 18B | Bridge Replacement | UTL | 185 | 2026-01-15 | 2026-01-15 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 88696 | PA160 Conemaugh Rvr Culv | 160 | 18B | Bridge Replacement | CON | 185 | 2026-01-15 | 2026-01-15 | 0 | 1017500 | 503875 | 0 | 0 | 0 | 0 | 0 | 0 | 1521375
Johnstown | 9 | Cambria | 91675 | PA271 Susquehanna Rvr Br | 271 | 23B | Bridge Restoration | ROW | 185 | 2027-02-11 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Johnstown | 9 | Cambria | 91675 | PA271 Susquehanna Rvr Br | 271 | 23B | Bridge Restoration | UTL | 185 | 2027-02-11 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 91675 | PA271 Susquehanna Rvr Br | 271 | 23B | Bridge Restoration | CON | BRIP | 2027-02-11 |  | 0 | 0 | 500000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 1500000
Johnstown | 9 | Cambria | 91689 | SR 2101 over US 22 | 2101 | 02B | Bridge Restoration | CON | BOF | 2025-01-30 | 2025-01-30 | 3235344.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3235344.21
Johnstown | 9 | Cambria | 91700 | SR 2019 over US 22 Bridge - D/B | 2019 | 03B | Bridge Restoration | PE | 185 | 2023-09-28 | 2023-09-28 | 0 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
Johnstown | 9 | Cambria | 91700 | SR 2019 over US 22 Bridge - D/B | 2019 | 03B | Bridge Restoration | CON | BRIP | 2023-09-28 | 2023-09-28 | 3242000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3242000
Johnstown | 9 | Cambria | 91700 | SR 2019 over US 22 Bridge - D/B | 2019 | 03B | Bridge Restoration | CON | STP | 2023-09-28 | 2023-09-28 | 541501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541501
Johnstown | 9 | Cambria | 92692 | PA160 Laurel Run Brdg #3 | 160 | 11B | Bridge Restoration | ROW | 185 | 2028-01-13 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Johnstown | 9 | Cambria | 92692 | PA160 Laurel Run Brdg #3 | 160 | 11B | Bridge Restoration | UTL | 185 | 2028-01-13 |  | 0 | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 65000
Johnstown | 9 | Cambria | 92692 | PA160 Laurel Run Brdg #3 | 160 | 11B | Bridge Restoration | CON | 185 | 2028-01-13 |  | 0 | 0 | 467000 | 0 | 0 | 0 | 0 | 0 | 0 | 467000
Johnstown | 9 | Cambria | 94468 | PA 271 Elk Creek Bridge | 271 | 24B | Bridge Restoration | ROW | 185 | 2027-02-11 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Johnstown | 9 | Cambria | 94468 | PA 271 Elk Creek Bridge | 271 | 24B | Bridge Restoration | UTL | 185 | 2027-02-11 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 94468 | PA 271 Elk Creek Bridge | 271 | 24B | Bridge Restoration | CON | BRIP | 2027-02-11 |  | 0 | 0 | 493000 | 0 | 0 | 0 | 0 | 0 | 0 | 493000
Johnstown | 9 | Cambria | 94469 | PA 271 Browns Run Bridge | 271 | 25B | Bridge Restoration | ROW | 185 | 2027-02-11 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Johnstown | 9 | Cambria | 94469 | PA 271 Browns Run Bridge | 271 | 25B | Bridge Restoration | UTL | 185 | 2027-02-11 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 94469 | PA 271 Browns Run Bridge | 271 | 25B | Bridge Restoration | CON | BRIP | 2027-02-11 |  | 0 | 0 | 254000 | 0 | 0 | 0 | 0 | 0 | 0 | 254000
Johnstown | 9 | Cambria | 94491 | N Patton Chest Creek Brdg | 4017 | 03B | Bridge Restoration | PE | BOF | 2025-04-10 | 2025-04-10 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000
Johnstown | 9 | Cambria | 94491 | N Patton Chest Creek Brdg | 4017 | 03B | Bridge Restoration | UTL | 185 | 2025-04-10 | 2025-04-10 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 94491 | N Patton Chest Creek Brdg | 4017 | 03B | Bridge Restoration | CON | BOF | 2025-04-10 | 2025-04-10 | 1438620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1438620
Johnstown | 9 | Cambria | 94756 | Local Br Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 726000 | 740000 | 1000000 | 2466000
Johnstown | 9 | Cambria | 94756 | Local Br Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Johnstown | 9 | Cambria | 94756 | Local Br Line Item |  |  | Reserve Line Item | CON | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 599000 | 0 | 1000000 | 1599000
Johnstown | 9 | Cambria | 96482 | Widman St to Walters Ave | 56 | 035 | Highway Restoration | CON | NHPP | 2024-01-11 | 2024-01-11 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Johnstown | 9 | Cambria | 96489 | Moss Crk Rd-Indiana Co Line | 219 | 049 | Highway Restoration | UTL | 581 | 2027-07-15 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 96489 | Moss Crk Rd-Indiana Co Line | 219 | 049 | Highway Restoration | CON | 581 | 2027-07-15 |  | 0 | 0 | 1518245 | 691355 | 0 | 0 | 0 | 0 | 0 | 2209600
Johnstown | 9 | Cambria | 98750 | Bradley Run Bridge | 53 | 30B | Bridge Restoration | PE | 185 | 2028-01-13 |  | 400000 | 88628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488628
Johnstown | 9 | Cambria | 98750 | Bradley Run Bridge | 53 | 30B | Bridge Restoration | FD | 185 | 2028-01-13 |  | 0 | 0 | 0 | 179392 | 0 | 0 | 0 | 0 | 0 | 179392
Johnstown | 9 | Cambria | 98750 | Bradley Run Bridge | 53 | 30B | Bridge Restoration | ROW | 185 | 2028-01-13 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 98750 | Bradley Run Bridge | 53 | 30B | Bridge Restoration | UTL | 185 | 2028-01-13 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 98750 | Bradley Run Bridge | 53 | 30B | Bridge Restoration | CON | 185 | 2028-01-13 |  | 0 | 0 | 0 | 704528 | 625000 | 0 | 0 | 0 | 0 | 1329528
Johnstown | 9 | Cambria | 98753 | PA 53 Lost Creek Bridge | 53 | 31B | Bridge Restoration | PE | 185 | 2028-01-13 |  | 400000 | 204304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604304
Johnstown | 9 | Cambria | 98753 | PA 53 Lost Creek Bridge | 53 | 31B | Bridge Restoration | FD | 185 | 2028-01-13 |  | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
Johnstown | 9 | Cambria | 98753 | PA 53 Lost Creek Bridge | 53 | 31B | Bridge Restoration | ROW | 185 | 2028-01-13 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 98753 | PA 53 Lost Creek Bridge | 53 | 31B | Bridge Restoration | UTL | 185 | 2028-01-13 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 98753 | PA 53 Lost Creek Bridge | 53 | 31B | Bridge Restoration | CON | BRIP | 2028-01-13 |  | 0 | 0 | 0 | 1000000 | 750102 | 0 | 0 | 0 | 0 | 1750102
Johnstown | 9 | Cambria | 98762 | Lloydsville Run Bridge | 865 | 04B | Bridge Restoration | ROW | 185 | 2028-03-23 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 98762 | Lloydsville Run Bridge | 865 | 04B | Bridge Restoration | UTL | 185 | 2028-03-23 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Johnstown | 9 | Cambria | 98762 | Lloydsville Run Bridge | 865 | 04B | Bridge Restoration | CON | 185 | 2028-03-23 |  | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000
Johnstown | 9 | Cambria | 98764 | PA865 Powell Run Bridge | 865 | 05B | Bridge Restoration | ROW | 185 | 2028-03-23 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Johnstown | 9 | Cambria | 98764 | PA865 Powell Run Bridge | 865 | 05B | Bridge Restoration | UTL | 185 | 2028-03-23 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Johnstown | 9 | Cambria | 98764 | PA865 Powell Run Bridge | 865 | 05B | Bridge Restoration | CON | 185 | 2028-03-23 |  | 0 | 0 | 0 | 312500 | 0 | 0 | 0 | 0 | 0 | 312500
Johnstown | 9 | Cambria | 106064 | Sunset Road to Nixon Ave | 219 | 028 | Highway Restoration | CON | NHPP | 2024-07-11 | 2024-07-11 | 0 | 700000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Johnstown | 9 | Cambria | 107229 | PA 53 - SR 3024 to PA 164 | 53 | 037 | Highway Restoration | CON | STP | 2026-06-04 |  | 2098496 | 3697755 | 2528649 | 0 | 0 | 0 | 0 | 0 | 0 | 8324900
Johnstown | 9 | Cambria | 108162 | PA 756 - PA 403 to SR 3016 | 756 | 009 | Highway Restoration | CON | STP | 2026-01-08 | 2026-01-08 | 0 | 1525392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1525392
Johnstown | 9 | Cambria | 110118 | PA 756 - PA 160 to Industrial Park Rd | 756 | 011 | Highway Restoration | PE | 581 | 2027-12-16 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 110118 | PA 756 - PA 160 to Industrial Park Rd | 756 | 011 | Highway Restoration | FD | 581 | 2027-12-16 |  | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000
Johnstown | 9 | Cambria | 110118 | PA 756 - PA 160 to Industrial Park Rd | 756 | 011 | Highway Restoration | UTL | 581 | 2027-12-16 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 110118 | PA 756 - PA 160 to Industrial Park Rd | 756 | 011 | Highway Restoration | CON | 581 | 2027-12-16 |  | 0 | 0 | 0 | 0 | 428400 | 871600 | 0 | 0 | 0 | 1300000
Johnstown | 9 | Cambria | 110119 | PA 756 - Lamberd Ave to Alvin St | 756 | 010 | Highway Restoration | CON | 581 | 2025-12-04 | 2025-12-04 | 0 | 1374341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1374341
Johnstown | 9 | Cambria | 110424 | US 22 - US 219 to PA 164 | 22 | 035 | Highway Restoration | PE | 581 | 2028-01-13 |  | 1039892 | 205108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1245000
Johnstown | 9 | Cambria | 110424 | US 22 - US 219 to PA 164 | 22 | 035 | Highway Restoration | FD | 581 | 2028-01-13 |  | 0 | 0 | 357976 | 327024 | 0 | 0 | 0 | 0 | 0 | 685000
Johnstown | 9 | Cambria | 110424 | US 22 - US 219 to PA 164 | 22 | 035 | Highway Restoration | CON | 581 | 2028-01-13 |  | 0 | 0 | 0 | 4251621 | 4489979 | 3458400 | 0 | 0 | 0 | 12200000
Johnstown | 9 | Cambria | 110437 | US 219 - PA 869 to New Germany | 219 | 055 | Highway Restoration | PE | 581 | 2031-01-16 |  | 0 | 453995 | 2038176 | 0 | 0 | 0 | 0 | 0 | 0 | 2492171
Johnstown | 9 | Cambria | 110437 | US 219 - PA 869 to New Germany | 219 | 055 | Highway Restoration | FD | 581 | 2031-01-16 |  | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 1000000
Johnstown | 9 | Cambria | 110437 | US 219 - PA 869 to New Germany | 219 | 055 | Highway Restoration | CON | NHPP | 2031-01-16 |  | 0 | 0 | 0 | 0 | 2660150 | 4485000 | 4485000 | 0 | 0 | 11630150
Johnstown | 9 | Cambria | 110437 | US 219 - PA 869 to New Germany | 219 | 055 | Highway Restoration | CON | STP | 2031-01-16 |  | 0 | 0 | 0 | 0 | 2635400 | 2695000 | 2695000 | 0 | 0 | 8025400
Johnstown | 9 | Cambria | 113250 | Jackson Twp Business Park Access |  | JBP | New Alignment | CON | APL | 2025-02-27 | 2025-02-27 | 847700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 847700
Johnstown | 9 | Cambria | 113250 | Jackson Twp Business Park Access |  | JBP | New Alignment | CON | LOC | 2025-02-27 | 2025-02-27 | 895978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895978
Johnstown | 9 | Cambria | 113997 | US 22 - PA 164 to Blair Cnty Line | 22 | 030 | Highway Restoration | CON | BRIP | 2025-08-07 | 2025-08-07 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Johnstown | 9 | Cambria | 113997 | US 22 - PA 164 to Blair Cnty Line | 22 | 030 | Highway Restoration | CON | NHPP | 2025-08-07 | 2025-08-07 | 4906605 | 1357033 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 7263638
Johnstown | 9 | Cambria | 113997 | US 22 - PA 164 to Blair Cnty Line | 22 | 030 | Highway Restoration | CON | 581 | 2025-08-07 | 2025-08-07 | 3444108 | 322314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3766422
Johnstown | 9 | Cambria | 114001 | PA 756 - Alvin St to Industrial Park Rd | 756 | 013 | Safety Improvement | CON | CAQ | 2025-12-04 | 2025-12-04 | 1751653 | 1362000 | 1362000 | 383146 | 0 | 0 | 0 | 0 | 0 | 4858799
Johnstown | 9 | Cambria | 114001 | PA 756 - Alvin St to Industrial Park Rd | 756 | 013 | Safety Improvement | CON | CRP | 2025-12-04 | 2025-12-04 | 0 | 3721 | 440000 | 76123 | 0 | 0 | 0 | 0 | 0 | 519844
Johnstown | 9 | Cambria | 114001 | PA 756 - Alvin St to Industrial Park Rd | 756 | 013 | Safety Improvement | CON | CRPU | 2025-12-04 | 2025-12-04 | 0 | 169000 | 169000 | 0 | 0 | 0 | 0 | 0 | 0 | 338000
Johnstown | 9 | Cambria | 114001 | PA 756 - Alvin St to Industrial Park Rd | 756 | 013 | Safety Improvement | CON | HVRU | 2025-12-04 | 2025-12-04 | 0 | 1261386 | 1108000 | 960060 | 0 | 0 | 0 | 0 | 0 | 3329446
Johnstown | 9 | Cambria | 114040 | Sidman PA160 Super Repl 1 | 160 | 15B | Bridge Restoration | CON | BRIP | 2025-10-09 | 2025-10-09 | 0 | 1204000 | 335000 | 0 | 0 | 0 | 0 | 0 | 0 | 1539000
Johnstown | 9 | Cambria | 114040 | Sidman PA160 Super Repl 1 | 160 | 15B | Bridge Restoration | CON | NHPP | 2025-10-09 | 2025-10-09 | 0 | 174046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174046
Johnstown | 9 | Cambria | 114040 | Sidman PA160 Super Repl 1 | 160 | 15B | Bridge Restoration | CON | 185 | 2025-10-09 | 2025-10-09 | 0 | 38539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38539
Johnstown | 9 | Cambria | 114041 | Sidman PA160 Super Repl 2 | 160 | 16B | Bridge Restoration | CON | BRIP | 2025-10-09 | 2025-10-09 | 0 | 1688000 | 258000 | 0 | 0 | 0 | 0 | 0 | 0 | 1946000
Johnstown | 9 | Cambria | 114041 | Sidman PA160 Super Repl 2 | 160 | 16B | Bridge Restoration | CON | NHPP | 2025-10-09 | 2025-10-09 | 0 | 169046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169046
Johnstown | 9 | Cambria | 114043 | Mount Airy Drive over US 219 Rehab | 3104 | 02B | Bridge Restoration | CON | BOF | 2025-12-11 | 2025-12-11 | 585234.79 | 1945036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2530270.79
Johnstown | 9 | Cambria | 115615 | Johnstown Urban Ind. Park Cnnctr St |  | PCS | New Alignment | FD | APL | 2026-12-10 |  | 0 | 67111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67111
Johnstown | 9 | Cambria | 115615 | Johnstown Urban Ind. Park Cnnctr St |  | PCS | New Alignment | CON | APL | 2026-12-10 |  | 0 | 1229386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1229386
Johnstown | 9 | Cambria | 116926 | US 219 - PA 56 to PA 869 | 219 | 050 | Highway Restoration | CON | BRIP | 2027-01-14 |  | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Johnstown | 9 | Cambria | 116926 | US 219 - PA 56 to PA 869 | 219 | 050 | Highway Restoration | CON | NHPP | 2027-01-14 |  | 0 | 0 | 3664000 | 4485000 | 1824850 | 0 | 0 | 0 | 0 | 9973850
Johnstown | 9 | Cambria | 116926 | US 219 - PA 56 to PA 869 | 219 | 050 | Highway Restoration | CON | STP | 2027-01-14 |  | 0 | 0 | 0 | 1767457 | 0 | 0 | 0 | 0 | 0 | 1767457
Johnstown | 9 | Cambria | 116931 | US 22 - PA 271 to US 219 | 22 | 036 | Highway Restoration | PE | 581 | 2028-12-07 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 116931 | US 22 - PA 271 to US 219 | 22 | 036 | Highway Restoration | FD | 581 | 2028-12-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 700000
Johnstown | 9 | Cambria | 116931 | US 22 - PA 271 to US 219 | 22 | 036 | Highway Restoration | CON | NHPP | 2028-12-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4485000 | 4474300 | 8959300
Johnstown | 9 | Cambria | 116931 | US 22 - PA 271 to US 219 | 22 | 036 | Highway Restoration | CON | STP | 2028-12-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2695000 | 0 | 2695000
Johnstown | 9 | Cambria | 117007 | US 22 Segment 351 Over Norfolk Southern Railroad | 22 | 32B | Bridge Restoration | CON | 185 | 2025-08-07 | 2025-08-07 | 876232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 876232
Johnstown | 9 | Cambria | 117008 | US 22 Segment 350 Over Norfolk Southern Railroad | 22 | 33B | Bridge Restoration | CON | 185 | 2025-08-07 | 2025-08-07 | 125002 | 339539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464541
Johnstown | 9 | Cambria | 117010 | SR 8016 Over SR 3016 and Horner Street | 8016 | 02B | Bridge Restoration | CON | NHPP | 2024-03-14 | 2024-03-14 | 0 | 250728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250728
Johnstown | 9 | Cambria | 117010 | SR 8016 Over SR 3016 and Horner Street | 8016 | 02B | Bridge Restoration | CON | STP | 2024-03-14 | 2024-03-14 | 701572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 701572
Johnstown | 9 | Cambria | 117012 | PA 271 Over North Branch Blacklick Creek | 271 | 26B | Bridge Restoration | ROW | 185 | 2027-02-11 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 117012 | PA 271 Over North Branch Blacklick Creek | 271 | 26B | Bridge Restoration | UTL | 185 | 2027-02-11 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 117012 | PA 271 Over North Branch Blacklick Creek | 271 | 26B | Bridge Restoration | CON | BRIP | 2027-02-11 |  | 0 | 0 | 402000 | 0 | 0 | 0 | 0 | 0 | 0 | 402000
Johnstown | 9 | Cambria | 117016 | US 219 Abandoned Railroad Tunnel Removal | 219 | 053 | Preventive Maintenance | PE | 581 | 2028-07-13 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 117016 | US 219 Abandoned Railroad Tunnel Removal | 219 | 053 | Preventive Maintenance | ROW | 581 | 2028-07-13 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 117016 | US 219 Abandoned Railroad Tunnel Removal | 219 | 053 | Preventive Maintenance | UTL | 581 | 2028-07-13 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 117016 | US 219 Abandoned Railroad Tunnel Removal | 219 | 053 | Preventive Maintenance | CON | STP | 2028-07-13 |  | 0 | 0 | 0 | 809165 | 59600 | 0 | 0 | 0 | 0 | 868765
Johnstown | 9 | Cambria | 117025 | Bridge PM Reserve Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Johnstown | 9 | Cambria | 117025 | Bridge PM Reserve Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 272000 | 0 | 902735 | 1000000 | 2174735
Johnstown | 9 | Cambria | 117025 | Bridge PM Reserve Line Item |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 455000 | 514125 | 732200 | 1000000 | 2701325
Johnstown | 9 | Cambria | 117089 | Iron Street over Hinckston Run | 7301 | ISB | Bridge Restoration | PE | BOF | 2028-08-10 |  | 568000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568000
Johnstown | 9 | Cambria | 117089 | Iron Street over Hinckston Run | 7301 | ISB | Bridge Restoration | PE | 183 | 2028-08-10 |  | 106500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106500
Johnstown | 9 | Cambria | 117089 | Iron Street over Hinckston Run | 7301 | ISB | Bridge Restoration | PE | LOC | 2028-08-10 |  | 35500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35500
Johnstown | 9 | Cambria | 117089 | Iron Street over Hinckston Run | 7301 | ISB | Bridge Restoration | FD | BOF | 2028-08-10 |  | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Johnstown | 9 | Cambria | 117089 | Iron Street over Hinckston Run | 7301 | ISB | Bridge Restoration | FD | 183 | 2028-08-10 |  | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500
Johnstown | 9 | Cambria | 117089 | Iron Street over Hinckston Run | 7301 | ISB | Bridge Restoration | FD | LOC | 2028-08-10 |  | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
Johnstown | 9 | Cambria | 117089 | Iron Street over Hinckston Run | 7301 | ISB | Bridge Restoration | ROW | BOF | 2028-08-10 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Johnstown | 9 | Cambria | 117089 | Iron Street over Hinckston Run | 7301 | ISB | Bridge Restoration | ROW | 183 | 2028-08-10 |  | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
Johnstown | 9 | Cambria | 117089 | Iron Street over Hinckston Run | 7301 | ISB | Bridge Restoration | ROW | LOC | 2028-08-10 |  | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250
Johnstown | 9 | Cambria | 117089 | Iron Street over Hinckston Run | 7301 | ISB | Bridge Restoration | UTL | BOF | 2028-08-10 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Johnstown | 9 | Cambria | 117089 | Iron Street over Hinckston Run | 7301 | ISB | Bridge Restoration | UTL | 183 | 2028-08-10 |  | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
Johnstown | 9 | Cambria | 117089 | Iron Street over Hinckston Run | 7301 | ISB | Bridge Restoration | UTL | LOC | 2028-08-10 |  | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250
Johnstown | 9 | Cambria | 117089 | Iron Street over Hinckston Run | 7301 | ISB | Bridge Restoration | CON | BOF | 2028-08-10 |  | 0 | 0 | 0 | 904000 | 0 | 0 | 0 | 0 | 0 | 904000
Johnstown | 9 | Cambria | 117089 | Iron Street over Hinckston Run | 7301 | ISB | Bridge Restoration | CON | 183 | 2028-08-10 |  | 0 | 0 | 0 | 169500 | 0 | 0 | 0 | 0 | 0 | 169500
Johnstown | 9 | Cambria | 117119 | PA 56 - PA 403 to 2nd Avenue | 56 | 040 | Highway Restoration | CON | 581 | 2027-04-11 |  | 0 | 0 | 1827603 | 0 | 0 | 0 | 0 | 0 | 0 | 1827603
Johnstown | 9 | Cambria | 117121 | SR 3024 under 8' Pipe | 3024 | 009 | Stormwater Management | CON | STP | 2024-06-06 | 2024-06-13 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000
Johnstown | 9 | Cambria | 117232 | 2024 Cambria County Safety Improvements | 422 | 10S | Safety Improvement | ROW | 581 | 2024-05-09 | 2024-05-09 | 3833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3833
Johnstown | 9 | Cambria | 117232 | 2024 Cambria County Safety Improvements | 422 | 10S | Safety Improvement | CON | HSIP | 2024-05-09 | 2024-05-09 | 2232736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2232736
Johnstown | 9 | Cambria | 117761 | US 219 Bridge Preservations | 219 | 51B | Bridge Preservation - Federal | CON | NHPP | 2025-01-09 | 2025-01-09 | 1427883 | 107301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1535184
Johnstown | 9 | Cambria | 117761 | US 219 Bridge Preservations | 219 | 51B | Bridge Preservation - Federal | CON | STP | 2025-01-09 | 2025-01-09 | 0 | 22699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22699
Johnstown | 9 | Cambria | 118380 | Sidewalk Improvement Project - Phase 5 Lighting | 164 | SIP | Bicycle Pedestrian Highway | CON | 411 | 2025-07-24 |  | 701300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 701300
Johnstown | 9 | Cambria | 118380 | Sidewalk Improvement Project - Phase 5 Lighting | 164 | SIP | Bicycle Pedestrian Highway | CON | LOC | 2025-07-24 |  | 210678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210678
Johnstown | 9 | Cambria | 118410 | 2025 RPM Installation Cambria County |  |  | Safety Improvement | CON | 581 | 2025-02-13 | 2025-02-13 | 75901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75901
Johnstown | 9 | Cambria | 119242 | PA 160 Slide North of Wilmore | 160 | 019 | Preventive Maintenance | PE | PRTCT | 2029-02-15 |  | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
Johnstown | 9 | Cambria | 119242 | PA 160 Slide North of Wilmore | 160 | 019 | Preventive Maintenance | CON | PRTCT | 2029-02-15 |  | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 4000000
Johnstown | 9 | Cambria | 119278 | PA 271 Menoher Boulevard Rockfall Mesh | 271 | 027 | Preventive Maintenance | ROW | 581 | 2026-06-18 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 119278 | PA 271 Menoher Boulevard Rockfall Mesh | 271 | 027 | Preventive Maintenance | UTL | 581 | 2026-06-18 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Johnstown | 9 | Cambria | 119278 | PA 271 Menoher Boulevard Rockfall Mesh | 271 | 027 | Preventive Maintenance | CON | PRTCT | 2026-06-18 |  | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Johnstown | 9 | Cambria | 119315 | Johnstown CRP Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 0 | 0 | 388877 | 465000 | 465000 | 465000 | 465000 | 1858000 | 4106877
Johnstown | 9 | Cambria | 119315 | Johnstown CRP Line Item |  |  | Reserve Line Item | CON | CRPU |  |  | 0 | 0 | 0 | 169000 | 169000 | 169000 | 169000 | 169000 | 678000 | 1523000
Johnstown | 9 | Cambria | 119505 | Cambria County Environmental Monitoring |  |  | Planning/Research/Administration | PE | 581 |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120073 | 2024 Cambria Interchange Lighting | 22 | 0 | Safety Improvement | CON | CRP | 2023-10-05 | 2023-10-05 | 400000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425000
Johnstown | 9 | Cambria | 120300 | US 22 - Indiana Co Line to Mundy's Corner Int. | 22 | 0 | Highway Restoration | PE | 581 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000
Johnstown | 9 | Cambria | 120300 | US 22 - Indiana Co Line to Mundy's Corner Int. | 22 | 0 | Highway Restoration | FD | 581 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 700000
Johnstown | 9 | Cambria | 120300 | US 22 - Indiana Co Line to Mundy's Corner Int. | 22 | 0 | Highway Restoration | CON | 581 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6334000 | 6284000 | 12618000
Johnstown | 9 | Cambria | 120334 | SR 219 - US 422 Int to Carrolltown Int | 219 | 0 | Highway Restoration | PE | 581 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 0 | 0 | 1250000
Johnstown | 9 | Cambria | 120334 | SR 219 - US 422 Int to Carrolltown Int | 219 | 0 | Highway Restoration | FD | 581 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Johnstown | 9 | Cambria | 120334 | SR 219 - US 422 Int to Carrolltown Int | 219 | 0 | Highway Restoration | CON | NHPP | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12466700 | 12466700
Johnstown | 9 | Cambria | 120336 | PA 53 - PA 164 to Cresson-Portage Int | 53 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 200000
Johnstown | 9 | Cambria | 120336 | PA 53 - PA 164 to Cresson-Portage Int | 53 | 0 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4782000 | 4782000
Johnstown | 9 | Cambria | 120337 | PA 53 - PA 36 to SR 1026 | 53 | 042 | Highway Restoration | PE | 581 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 200000
Johnstown | 9 | Cambria | 120337 | PA 53 - PA 36 to SR 1026 | 53 | 042 | Highway Restoration | CON | STP | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
Johnstown | 9 | Cambria | 120339 | PA 36 - Blair County to SR 1010 | 36 | 004 | Highway Restoration | PE | 581 | 2032-03-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
Johnstown | 9 | Cambria | 120339 | PA 36 - Blair County to SR 1010 | 36 | 004 | Highway Restoration | CON | 581 | 2032-03-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500000 | 5500000
Johnstown | 9 | Cambria | 120340 | PA 53 - SR 1026 to Clearfield Co Line | 53 | 043 | Highway Restoration | PE | 581 | 2032-05-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 200000
Johnstown | 9 | Cambria | 120340 | PA 53 - SR 1026 to Clearfield Co Line | 53 | 043 | Highway Restoration | CON | 581 | 2032-05-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 3500000
Johnstown | 9 | Cambria | 120342 | SR 2014 - SR 1036 to SR 1005 | 2014 | 0 | Highway Restoration | PE | 581 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
Johnstown | 9 | Cambria | 120342 | SR 2014 - SR 1036 to SR 1005 | 2014 | 0 | Highway Restoration | CON | 581 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
Johnstown | 9 | Cambria | 120343 | SR 271 - SR 3037 to Mundy's Corner Int | 271 | 0 | Highway Restoration | PE | 581 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Johnstown | 9 | Cambria | 120343 | SR 271 - SR 3037 to Mundy's Corner Int | 271 | 0 | Highway Restoration | CON | 581 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
Johnstown | 9 | Cambria | 120394 | 8th Street Bridge over Fox Run | 7434 | 01B | Bridge Restoration | PE | BOF | 2029-08-23 |  | 0 | 324363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324363
Johnstown | 9 | Cambria | 120394 | 8th Street Bridge over Fox Run | 7434 | 01B | Bridge Restoration | PE | 183 | 2029-08-23 |  | 0 | 60818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60818
Johnstown | 9 | Cambria | 120394 | 8th Street Bridge over Fox Run | 7434 | 01B | Bridge Restoration | PE | LOC | 2029-08-23 |  | 0 | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17500
Johnstown | 9 | Cambria | 120394 | 8th Street Bridge over Fox Run | 7434 | 01B | Bridge Restoration | FD | BOF | 2029-08-23 |  | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000
Johnstown | 9 | Cambria | 120394 | 8th Street Bridge over Fox Run | 7434 | 01B | Bridge Restoration | FD | 183 | 2029-08-23 |  | 0 | 0 | 0 | 13500 | 0 | 0 | 0 | 0 | 0 | 13500
Johnstown | 9 | Cambria | 120394 | 8th Street Bridge over Fox Run | 7434 | 01B | Bridge Restoration | ROW | BOF | 2029-08-23 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Johnstown | 9 | Cambria | 120394 | 8th Street Bridge over Fox Run | 7434 | 01B | Bridge Restoration | ROW | 183 | 2029-08-23 |  | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750
Johnstown | 9 | Cambria | 120394 | 8th Street Bridge over Fox Run | 7434 | 01B | Bridge Restoration | UTL | BOF | 2029-08-23 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Johnstown | 9 | Cambria | 120394 | 8th Street Bridge over Fox Run | 7434 | 01B | Bridge Restoration | UTL | 183 | 2029-08-23 |  | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750
Johnstown | 9 | Cambria | 120394 | 8th Street Bridge over Fox Run | 7434 | 01B | Bridge Restoration | CON | BOF | 2029-08-23 |  | 0 | 0 | 0 | 0 | 560000 | 0 | 0 | 0 | 0 | 560000
Johnstown | 9 | Cambria | 120394 | 8th Street Bridge over Fox Run | 7434 | 01B | Bridge Restoration | CON | 183 | 2029-08-23 |  | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 0 | 0 | 105000
Johnstown | 9 | Cambria | 120425 | SR 4019 over Little Chest Creek | 4019 | 01B | Bridge Restoration | PE | 185 | 2029-10-25 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120425 | SR 4019 over Little Chest Creek | 4019 | 01B | Bridge Restoration | ROW | 185 | 2029-10-25 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 120425 | SR 4019 over Little Chest Creek | 4019 | 01B | Bridge Restoration | UTL | 185 | 2029-10-25 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 120425 | SR 4019 over Little Chest Creek | 4019 | 01B | Bridge Restoration | CON | 185 | 2029-10-25 |  | 0 | 0 | 0 | 0 | 0 | 720000 | 0 | 0 | 0 | 720000
Johnstown | 9 | Cambria | 120428 | SR 4002 over Little Elk Creek | 4002 | 05B | Bridge Restoration | PE | 185 | 2030-01-31 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120428 | SR 4002 over Little Elk Creek | 4002 | 05B | Bridge Restoration | ROW | 185 | 2030-01-31 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 120428 | SR 4002 over Little Elk Creek | 4002 | 05B | Bridge Restoration | UTL | 185 | 2030-01-31 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 120428 | SR 4002 over Little Elk Creek | 4002 | 05B | Bridge Restoration | CON | BOF | 2030-01-31 |  | 0 | 0 | 0 | 0 | 0 | 720000 | 0 | 0 | 0 | 720000
Johnstown | 9 | Cambria | 120430 | SR 1025 over Burgoon Run | 1025 | 01B | Bridge Restoration | PE | 185 | 2029-01-04 |  | 0 | 366682 | 10429 | 0 | 0 | 0 | 0 | 0 | 0 | 377111
Johnstown | 9 | Cambria | 120430 | SR 1025 over Burgoon Run | 1025 | 01B | Bridge Restoration | FD | 185 | 2029-01-04 |  | 0 | 0 | 0 | 190000 | 0 | 0 | 0 | 0 | 0 | 190000
Johnstown | 9 | Cambria | 120430 | SR 1025 over Burgoon Run | 1025 | 01B | Bridge Restoration | ROW | 185 | 2029-01-04 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 120430 | SR 1025 over Burgoon Run | 1025 | 01B | Bridge Restoration | UTL | 185 | 2029-01-04 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 120430 | SR 1025 over Burgoon Run | 1025 | 01B | Bridge Restoration | CON | BRIP | 2029-01-04 |  | 0 | 0 | 0 | 0 | 142000 | 549898 | 750102 | 0 | 0 | 1442000
Johnstown | 9 | Cambria | 120431 | SR 3041 (BRKEY 8665) over Laurel Run | 3041 | 01B | Bridge Restoration | PE | 185 | 2030-10-24 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120431 | SR 3041 (BRKEY 8665) over Laurel Run | 3041 | 01B | Bridge Restoration | ROW | 185 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 120431 | SR 3041 (BRKEY 8665) over Laurel Run | 3041 | 01B | Bridge Restoration | UTL | 185 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 120431 | SR 3041 (BRKEY 8665) over Laurel Run | 3041 | 01B | Bridge Restoration | CON | BRIP | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 950000 | 0 | 0 | 0 | 950000
Johnstown | 9 | Cambria | 120432 | PA 271 Truss over Little Conemaugh River | 271 | 31B | Bridge Restoration | PE | 185 | 2031-01-09 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120432 | PA 271 Truss over Little Conemaugh River | 271 | 31B | Bridge Restoration | CON | 185 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 1207000 | 0 | 0 | 0 | 1207000
Johnstown | 9 | Cambria | 120433 | PA 56 over Paint Creek | 56 | 42B | Bridge Restoration | PE | 185 | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120433 | PA 56 over Paint Creek | 56 | 42B | Bridge Restoration | ROW | 185 | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120433 | PA 56 over Paint Creek | 56 | 42B | Bridge Restoration | UTL | 185 | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120433 | PA 56 over Paint Creek | 56 | 42B | Bridge Restoration | CON | BRIP | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000 | 0 | 850000
Johnstown | 9 | Cambria | 120434 | PA 403 over Laurel Run | 403 | 0 | Bridge Restoration | PE | 185 | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120434 | PA 403 over Laurel Run | 403 | 0 | Bridge Restoration | ROW | 185 | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120434 | PA 403 over Laurel Run | 403 | 0 | Bridge Restoration | UTL | 185 | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120434 | PA 403 over Laurel Run | 403 | 0 | Bridge Restoration | CON | BRIP | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765000 | 0 | 765000
Johnstown | 9 | Cambria | 120435 | SR 271 over Little Conemaugh River | 271 | 32B | Bridge Restoration | PE | 185 | 2031-08-21 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120435 | SR 271 over Little Conemaugh River | 271 | 32B | Bridge Restoration | ROW | 185 | 2031-08-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120435 | SR 271 over Little Conemaugh River | 271 | 32B | Bridge Restoration | UTL | 185 | 2031-08-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120435 | SR 271 over Little Conemaugh River | 271 | 32B | Bridge Restoration | CON | 185 | 2031-08-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 800000
Johnstown | 9 | Cambria | 120436 | US 22 over SR 8004 | 22 | 37B | Bridge Restoration | PE | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120436 | US 22 over SR 8004 | 22 | 37B | Bridge Restoration | ROW | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120436 | US 22 over SR 8004 | 22 | 37B | Bridge Restoration | UTL | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120436 | US 22 over SR 8004 | 22 | 37B | Bridge Restoration | CON | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1771000 | 2271000
Johnstown | 9 | Cambria | 120437 | US 22 over PA 160 | 22 | 38B | Bridge Restoration | PE | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120437 | US 22 over PA 160 | 22 | 38B | Bridge Restoration | ROW | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120437 | US 22 over PA 160 | 22 | 38B | Bridge Restoration | UTL | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120437 | US 22 over PA 160 | 22 | 38B | Bridge Restoration | CON | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 1900000 | 2500000
Johnstown | 9 | Cambria | 120438 | PA 865 over Abandoned Railroad | 865 | 06B | Bridge Restoration | PE | 185 | 2032-02-12 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120438 | PA 865 over Abandoned Railroad | 865 | 06B | Bridge Restoration | ROW | 185 | 2032-02-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120438 | PA 865 over Abandoned Railroad | 865 | 06B | Bridge Restoration | UTL | 185 | 2032-02-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120438 | PA 865 over Abandoned Railroad | 865 | 06B | Bridge Restoration | CON | 185 | 2032-02-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 800000
Johnstown | 9 | Cambria | 120440 | SR 1001 over Railroad | 1001 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 300000
Johnstown | 9 | Cambria | 120440 | SR 1001 over Railroad | 1001 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
Johnstown | 9 | Cambria | 120441 | SR 3041 (BRKEY 8664) over Laurel Run | 3041 | 02B | Bridge Restoration | PE | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 300000
Johnstown | 9 | Cambria | 120441 | SR 3041 (BRKEY 8664) over Laurel Run | 3041 | 02B | Bridge Restoration | CON | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
Johnstown | 9 | Cambria | 120442 | Cambria Epoxy Overlay Contract |  |  | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
Johnstown | 9 | Cambria | 120442 | Cambria Epoxy Overlay Contract |  |  | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000
Johnstown | 9 | Cambria | 120444 | SR 3016 over Solomon Run | 3016 | 0 | Bridge Restoration | PE | BRIP | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
Johnstown | 9 | Cambria | 120444 | SR 3016 over Solomon Run | 3016 | 0 | Bridge Restoration | FD | BRIP | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Johnstown | 9 | Cambria | 120444 | SR 3016 over Solomon Run | 3016 | 0 | Bridge Restoration | CON | BRIP | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
Johnstown | 9 | Cambria | 120448 | SR 2015 over Little Conemaugh Rvr, RR & RR Street | 2015 | 0 | Bridge Restoration | PE | BRIP | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Johnstown | 9 | Cambria | 120448 | SR 2015 over Little Conemaugh Rvr, RR & RR Street | 2015 | 0 | Bridge Restoration | FD | BRIP | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
Johnstown | 9 | Cambria | 120448 | SR 2015 over Little Conemaugh Rvr, RR & RR Street | 2015 | 0 | Bridge Restoration | CON | BRIP | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Johnstown | 9 | Cambria | 120552 | SR 3027 over PA 56 | 3027 | 01B | Bridge Restoration | PE | 185 | 2028-12-07 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 120552 | SR 3027 over PA 56 | 3027 | 01B | Bridge Restoration | ROW | 185 | 2028-12-07 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 120552 | SR 3027 over PA 56 | 3027 | 01B | Bridge Restoration | UTL | 185 | 2028-12-07 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Johnstown | 9 | Cambria | 120552 | SR 3027 over PA 56 | 3027 | 01B | Bridge Restoration | CON | BRIP | 2028-12-07 |  | 0 | 0 | 0 | 672000 | 1000000 | 0 | 0 | 0 | 0 | 1672000
Johnstown | 9 | Cambria | 120570 | SR 1002 over SR 219 | 1002 | 0 | Bridge Restoration | PE | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 650000
Johnstown | 9 | Cambria | 120570 | SR 1002 over SR 219 | 1002 | 0 | Bridge Restoration | FD | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Johnstown | 9 | Cambria | 120570 | SR 1002 over SR 219 | 1002 | 0 | Bridge Restoration | CON | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2409000 | 2409000
Johnstown | 9 | Cambria | 120734 | 2026 RPM Installation Cambria County |  |  | General Maintenance | CON | 581 | 2026-03-12 | 2026-03-12 | 0 | 130852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130852
Johnstown | 9 | Cambria | 121384 | SR 271 Clinton Street Crossing | 271 | 0 | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 0 | 200000 | 300000 | 0 | 0 | 0 | 0 | 0 | 500000
Johnstown | 9 | Cambria | 121469 | PA 271 Menoher Blvd Slide | 271 | 29E | Highway Restoration | ROW | PRTCT | 2024-07-11 | 2024-01-11 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000
Johnstown | 9 | Cambria | 121469 | PA 271 Menoher Blvd Slide | 271 | 29E | Highway Restoration | CON | PRTCT | 2024-07-11 | 2024-01-11 | 81241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81241
Johnstown | 9 | Cambria | 121561 | Station Street Walkway Rehab, Phase 2 |  | SW2 | Transportation Enhancement | CON | SRTSF | 2025-05-22 | 2025-05-22 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000
Johnstown | 9 | Cambria | 122134 | Waterfall Road Paving Project |  |  | MultiModal | CON | 411 | 2025-04-01 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Johnstown | 9 | Cambria | 122134 | Waterfall Road Paving Project |  |  | MultiModal | CON | LOC | 2025-04-01 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Johnstown | 9 | Cambria | 122193 | PA 36 - SR 1017 to Clearfield Twp | 36 | 002 | 409 Expanded Maintenance | CON | 409 |  |  | 218000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218000
Johnstown | 9 | Cambria | 122194 | PA 53 - PA 36 to T-472 | 53 | 002 | 409 Expanded Maintenance | CON | 409 |  |  | 672000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672000
Johnstown | 9 | Cambria | 122209 | County Wide Mill & Fill | 1004 | 001 | 409 Expanded Maintenance | CON | 409 | 2025-05-22 | 2025-05-22 | 2150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2150000
Johnstown | 9 | Cambria | 122234 | 2026 Cambria Interchange Lighting | 219 | L53 | Congestion Reduction | CON | CRP | 2025-10-09 | 2025-10-09 | 53000 | 436279 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 514279
Johnstown | 9 | Cambria | 122234 | 2026 Cambria Interchange Lighting | 219 | L53 | Congestion Reduction | CON | CRPU | 2025-10-09 | 2025-10-09 | 166000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166000
Johnstown | 9 | Cambria | 122301 | McNally Bridge Improvements | 219 | 02S | Bridge Restoration | STUDY | 185 |  |  | 350000 | 354000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704000
Johnstown | 9 | Cambria | 122481 | Munster Road Intersection ROW | 2014 | 01R | Safety Improvement | ROW | 581 |  |  | 16167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16167
Johnstown | 9 | Cambria | 123045 | Dellwood St Over NS Railroad | 7301 | 01B | Bridge Restoration | PE | BOF | 2029-04-12 |  | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000
Johnstown | 9 | Cambria | 123045 | Dellwood St Over NS Railroad | 7301 | 01B | Bridge Restoration | PE | 183 | 2029-04-12 |  | 0 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52500
Johnstown | 9 | Cambria | 123621 | PA 403 Rockfall Fence | 403 | 011 | Highway Restoration | CON | 581 | 2026-06-18 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Lancaster | 8 | Lancaster | 19763 | Strasburg Pk over Pequea Creek | 2029 | 017 | Bridge Restoration | PE | BOF | 2027-07-29 |  | 75500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75500
Lancaster | 8 | Lancaster | 19763 | Strasburg Pk over Pequea Creek | 2029 | 017 | Bridge Restoration | FD | BOF | 2027-07-29 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Lancaster | 8 | Lancaster | 19763 | Strasburg Pk over Pequea Creek | 2029 | 017 | Bridge Restoration | ROW | BOF | 2027-07-29 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Lancaster | 8 | Lancaster | 19763 | Strasburg Pk over Pequea Creek | 2029 | 017 | Bridge Restoration | UTL | BOF | 2027-07-29 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Lancaster | 8 | Lancaster | 19763 | Strasburg Pk over Pequea Creek | 2029 | 017 | Bridge Restoration | CON | BOF | 2027-07-29 |  | 0 | 0 | 800000 | 918620 | 1251900 | 0 | 0 | 0 | 0 | 2970520
Lancaster | 8 | Lancaster | 20119 | Brunnerville Rd and Newport Rd Int |  | LOC | Safety Improvement | CON | STU | 2028-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1037030 | 0 | 0 | 1037030
Lancaster | 8 | Lancaster | 63227 | Greenville Road Bridge-B | 1053 | 003 | Bridge Replacement | CON | BOF | 2025-01-30 | 2025-01-30 | 2991349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2991349
Lancaster | 8 | Lancaster | 64767 | Centerville Rd Interchange | 4057 | 002 | Highway Reconstruction | CON | STP | 2022-09-15 | 2022-09-15 | 360375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360375
Lancaster | 8 | Lancaster | 64827 | PA-441 Corridor-Columbia | 441 | 012 | Safety Improvement | CON | 581 | 2014-03-13 | 2014-03-13 | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000
Lancaster | 8 | Lancaster | 78833 | Twin County Road Bridge | 10 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Lancaster | 8 | Lancaster | 78833 | Twin County Road Bridge | 10 | 0 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000
Lancaster | 8 | Lancaster | 78890 | Br Rpl SR 1020-Middle Crk | 1020 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 78965 | Br Rpl SR 2009 over WB Octor.Ck | 2009 | 016 | Bridge Replacement | PE | BOF | 2020-10-22 | 2020-10-22 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000
Lancaster | 8 | Lancaster | 78978 | BrRpl SR2011-TBWBOctor.Cr | 2011 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 79020 | Veterans Mem Br -Susq Rv | 462 | 038 | Bridge Restoration | PE | 185 | 2027-12-09 |  | 39270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39270
Lancaster | 8 | Lancaster | 79020 | Veterans Mem Br -Susq Rv | 462 | 038 | Bridge Restoration | FD | BRIP | 2027-12-09 |  | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
Lancaster | 8 | Lancaster | 79020 | Veterans Mem Br -Susq Rv | 462 | 038 | Bridge Restoration | FD | STU | 2027-12-09 |  | 5284645 | 843405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6128050
Lancaster | 8 | Lancaster | 79020 | Veterans Mem Br -Susq Rv | 462 | 038 | Bridge Restoration | FD | 185 | 2027-12-09 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Lancaster | 8 | Lancaster | 79020 | Veterans Mem Br -Susq Rv | 462 | 038 | Bridge Restoration | ROW | 185 | 2027-12-09 |  | 0 | 833270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833270
Lancaster | 8 | Lancaster | 79020 | Veterans Mem Br -Susq Rv | 462 | 038 | Bridge Restoration | UTL | BRIP | 2027-12-09 |  | 1895000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1895000
Lancaster | 8 | Lancaster | 79020 | Veterans Mem Br -Susq Rv | 462 | 038 | Bridge Restoration | UTL | STP | 2027-12-09 |  | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
Lancaster | 8 | Lancaster | 79020 | Veterans Mem Br -Susq Rv | 462 | 038 | Bridge Restoration | UTL | 185 | 2027-12-09 |  | 1314933 | 190067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1505000
Lancaster | 8 | Lancaster | 79020 | Veterans Mem Br -Susq Rv | 462 | 038 | Bridge Restoration | CON | STP | 2027-12-09 |  | 0 | 0 | 22000000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 25000000
Lancaster | 8 | Lancaster | 79020 | Veterans Mem Br -Susq Rv | 462 | 038 | Bridge Restoration | CON | BRIP | 2027-12-09 |  | 0 | 0 | 8479000 | 4242525 | 6879000 | 8479000 | 8479000 | 624434 | 0 | 37182959
Lancaster | 8 | Lancaster | 79020 | Veterans Mem Br -Susq Rv | 462 | 038 | Bridge Restoration | CON | STP | 2027-12-09 |  | 0 | 0 | 6525556 | 6116000 | 453860 | 9116000 | 754849 | 0 | 2609640 | 25575905
Lancaster | 8 | Lancaster | 79020 | Veterans Mem Br -Susq Rv | 462 | 038 | Bridge Restoration | CON | 185 | 2027-12-09 |  | 0 | 0 | 454557 | 4750932 | 7039500 | 6823000 | 8771000 | 8167000 | 14923686 | 50929675
Lancaster | 8 | Lancaster | 79020 | Veterans Mem Br -Susq Rv | 462 | 038 | Bridge Restoration | CON | 581 | 2027-12-09 |  | 0 | 0 | 11837300 | 13577300 | 17118686 | 17955000 | 17952000 | 18337930 | 0 | 96778216
Lancaster | 8 | Lancaster | 79025 | California Rd Bridge #1 | 1019 | 013 | Bridge Replacement | CON | 185 | 2025-01-09 | 2025-01-09 | 657663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657663
Lancaster | 8 | Lancaster | 79102 | Mohler Church Rd over Cocalico Creek | 7218 | BRG | Bridge Restoration | PE | BOF | 2027-12-09 |  | 181928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181928
Lancaster | 8 | Lancaster | 79102 | Mohler Church Rd over Cocalico Creek | 7218 | BRG | Bridge Restoration | FD | BOF | 2027-12-09 |  | 0 | 125000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Lancaster | 8 | Lancaster | 79102 | Mohler Church Rd over Cocalico Creek | 7218 | BRG | Bridge Restoration | ROW | BOF | 2027-12-09 |  | 0 | 145000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 195000
Lancaster | 8 | Lancaster | 79102 | Mohler Church Rd over Cocalico Creek | 7218 | BRG | Bridge Restoration | UTL | BOF | 2027-12-09 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Lancaster | 8 | Lancaster | 79102 | Mohler Church Rd over Cocalico Creek | 7218 | BRG | Bridge Restoration | CON | BOF | 2027-12-09 |  | 0 | 0 | 0 | 993147 | 0 | 0 | 0 | 0 | 0 | 993147
Lancaster | 8 | Lancaster | 80931 | Hbg. Pike Corridor Improv | 4020 | 012 | Highway Restoration | PE | NHPP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 84016 | Pitney Rd over Amtrak Br | 3028 | 003 | Bridge Restoration | ROW | 185 | 2026-03-26 | 2026-03-26 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Lancaster | 8 | Lancaster | 84016 | Pitney Rd over Amtrak Br | 3028 | 003 | Bridge Restoration | UTL | 185 | 2026-03-26 | 2026-03-26 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Lancaster | 8 | Lancaster | 84016 | Pitney Rd over Amtrak Br | 3028 | 003 | Bridge Restoration | CON | 581 | 2026-03-26 | 2026-03-26 | 3115224 | 1037736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4152960
Lancaster | 8 | Lancaster | 87524 | Willow Street Bridge | 1061 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 87524 | Willow Street Bridge | 1061 | 0 | Bridge Replacement | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1805000 | 1805000
Lancaster | 8 | Lancaster | 87540 | River Road Bridge | 3017 | 033 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Lancaster | 8 | Lancaster | 87540 | River Road Bridge | 3017 | 033 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Lancaster | 8 | Lancaster | 87542 | Walnut Hill Bridge | 3027 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 87555 | Bunker Hill Bridge | 2029 | 014 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76000 | 76000
Lancaster | 8 | Lancaster | 87559 | Stackstown Road Bridge | 4004 | 014 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 87701 | Lincoln Road Bridge | 1024 | 009 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 87707 | Safe Harbor Rd Br | 3017 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Lancaster | 8 | Lancaster | 87823 | TAP Line Item |  |  | Reserve Line Item | CON | TAU |  |  | 0 | 599508 | 0 | 0 | 865000 | 865000 | 865000 | 865000 | 3460000 | 7519508
Lancaster | 8 | Lancaster | 87825 | HSIP Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 150000 | 62242 | 1338517 | 0 | 1899883 | 3685000 | 3685000 | 3685000 | 13227410 | 27733052
Lancaster | 8 | Lancaster | 87826 | Bridge Reserve |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 689512 | 1464186 | 453735 | 328787 | 6228728 | 6808000 | 6808000 | 26884000 | 49664948
Lancaster | 8 | Lancaster | 87826 | Bridge Reserve |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 341938 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 341939
Lancaster | 8 | Lancaster | 87826 | Bridge Reserve |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 510247 | 4297353 | 2472968 | 0 | 0 | 0 | 0 | 10306314 | 17586882
Lancaster | 8 | Lancaster | 87827 | Highway Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 41406 | 2609641 | 2135099 | 0 | 0 | 2084172 | 10182000 | 40578000 | 57630318
Lancaster | 8 | Lancaster | 87827 | Highway Reserve |  |  | Reserve Line Item | CON | STP |  |  | 0 | 10975 | 1588209 | 0 | 0 | 0 | 361151 | 0 | 0 | 1960335
Lancaster | 8 | Lancaster | 87827 | Highway Reserve |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 1714481 | 0 | 0 | 0 | 0 | 0 | 0 | 31829622 | 33544103
Lancaster | 8 | Lancaster | 87832 | CMAQ Line Item |  |  | Reserve Line Item | CON | CAQ |  |  | 1183712 | 0 | 5273880 | 5270199 | 3382154 | 1642000 | 1642000 | 5642000 | 22568000 | 46603945
Lancaster | 8 | Lancaster | 87848 | Delivery/ Consult Assist |  |  | Reserve Line Item | PE | 185 |  |  | 0 | 552000 | 729506 | 0 | 0 | 0 | 0 | 0 | 0 | 1281506
Lancaster | 8 | Lancaster | 87848 | Delivery/ Consult Assist |  |  | Reserve Line Item | PE | 581 |  |  | 800000 | 800000 | 800000 | 800000 | 0 | 0 | 0 | 0 | 0 | 3200000
Lancaster | 8 | Lancaster | 87848 | Delivery/ Consult Assist |  |  | Reserve Line Item | CON | 581 |  |  | 400000 | 400000 | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 1600000
Lancaster | 8 | Lancaster | 88067 | STU Line Item |  |  | Reserve Line Item | CON | STU |  |  | 0 | 752030 | 0 | 0 | 0 | 530391 | 6091871 | 9264000 | 22804000 | 39442292
Lancaster | 8 | Lancaster | 89288 | Rohrerstown Rd Bridge | 7101 | BRG | Bridge Replacement | FD | BOF | 2022-05-12 | 2022-05-12 | 4700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4700
Lancaster | 8 | Lancaster | 89288 | Rohrerstown Rd Bridge | 7101 | BRG | Bridge Replacement | FD | 185 | 2022-05-12 | 2022-05-12 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882
Lancaster | 8 | Lancaster | 89288 | Rohrerstown Rd Bridge | 7101 | BRG | Bridge Replacement | FD | LOC | 2022-05-12 | 2022-05-12 | 293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 293
Lancaster | 8 | Lancaster | 89288 | Rohrerstown Rd Bridge | 7101 | BRG | Bridge Replacement | UTL | BOF | 2022-05-12 | 2022-05-12 | 37600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37600
Lancaster | 8 | Lancaster | 89288 | Rohrerstown Rd Bridge | 7101 | BRG | Bridge Replacement | UTL | 185 | 2022-05-12 | 2022-05-12 | 7050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7050
Lancaster | 8 | Lancaster | 89288 | Rohrerstown Rd Bridge | 7101 | BRG | Bridge Replacement | UTL | LOC | 2022-05-12 | 2022-05-12 | 2350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2350
Lancaster | 8 | Lancaster | 91107 | Chickies Creek Bridge | 4020 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 91107 | Chickies Creek Bridge | 4020 | 0 | Bridge Restoration | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6281000 | 6281000
Lancaster | 8 | Lancaster | 91269 | Speedwell Forge Road BR | 1037 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 91336 | Martic Heights Drive Bridge | 3018 | 003 | Bridge Replacement | CON | 185 | 2025-01-30 | 2025-01-30 | 1294664 | 874304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2168968
Lancaster | 8 | Lancaster | 91338 | Bridge Valley Road Bridge | 3038 | 003 | Bridge Replacement | CON | 185 | 2025-01-30 | 2025-01-30 | 1930533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1930533
Lancaster | 8 | Lancaster | 91395 | Pumping Station Rd ovr Bowery Run | 2015 | 012 | Bridge Restoration | FD | BOF | 2027-12-09 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Lancaster | 8 | Lancaster | 91395 | Pumping Station Rd ovr Bowery Run | 2015 | 012 | Bridge Restoration | ROW | BOF | 2027-12-09 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Lancaster | 8 | Lancaster | 91395 | Pumping Station Rd ovr Bowery Run | 2015 | 012 | Bridge Restoration | UTL | BOF | 2027-12-09 |  | 89770 | 10230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Lancaster | 8 | Lancaster | 91395 | Pumping Station Rd ovr Bowery Run | 2015 | 012 | Bridge Restoration | CON | BOF | 2027-12-09 |  | 0 | 0 | 700000 | 700000 | 619954 | 0 | 0 | 0 | 0 | 2019954
Lancaster | 8 | Lancaster | 93581 | PA 462 Little Conestoga | 462 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 94572 | SRTP Rideshare Program |  |  | Reserve Line Item | PE | CAQ |  |  | 0 | 380720 | 368120 | 371801 | 0 | 0 | 0 | 0 | 0 | 1120641
Lancaster | 8 | Lancaster | 97013 | US 222 /US 30 Interchange Improvements | 222 | 059 | Highway Reconstruction | CON | NHPP | 2023-07-13 | 2023-07-13 | 6497308 | 782318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7279626
Lancaster | 8 | Lancaster | 97263 | N Reading over Muddy Cr | 272 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 100383 | Nottingham Rd Rsf 2 | 272 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Lancaster | 8 | Lancaster | 100436 | Fairview Rd/Beaver Cr | 3016 | 012 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Lancaster | 8 | Lancaster | 100436 | Fairview Rd/Beaver Cr | 3016 | 012 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000
Lancaster | 8 | Lancaster | 100530 | Red Run Rd over Muddy Cr | 1044 | 003 | Bridge Preservation - Federal | FD | BOF | 2027-01-28 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Lancaster | 8 | Lancaster | 100530 | Red Run Rd over Muddy Cr | 1044 | 003 | Bridge Preservation - Federal | ROW | BOF | 2027-01-28 |  | 0 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000
Lancaster | 8 | Lancaster | 100530 | Red Run Rd over Muddy Cr | 1044 | 003 | Bridge Preservation - Federal | UTL | BOF | 2027-01-28 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Lancaster | 8 | Lancaster | 100530 | Red Run Rd over Muddy Cr | 1044 | 003 | Bridge Preservation - Federal | CON | BOF | 2027-01-28 |  | 0 | 0 | 922665 | 0 | 0 | 0 | 0 | 0 | 0 | 922665
Lancaster | 8 | Lancaster | 100530 | Red Run Rd over Muddy Cr | 1044 | 003 | Bridge Preservation - Federal | CON | STP | 2027-01-28 |  | 0 | 0 | 772335 | 0 | 0 | 0 | 0 | 0 | 0 | 772335
Lancaster | 8 | Lancaster | 100531 | Marietta Avenue over NS | 23 | 034 | Bridge Restoration | CON | 185 | 2023-02-02 | 2023-02-02 | 314105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314105
Lancaster | 8 | Lancaster | 100543 | Millersville Rd Bridge | 741 | 025 | Bridge Preservation - Federal | CON | BRIP | 2024-10-10 | 2024-10-10 | 95062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95062
Lancaster | 8 | Lancaster | 100567 | Mount Joy Road Bridge PM | 772 | 050 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 100570 | Newport Rd over SR 6023 Br PM | 772 | 042 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482000 | 482000
Lancaster | 8 | Lancaster | 100592 | Horseshoe Rd over Amtrak | 1003 | 024 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 1437500 | 1950000 | 0 | 0 | 0 | 3387500
Lancaster | 8 | Lancaster | 100595 | Quarry Road Bridge PM | 1003 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 100598 | US 222 S/Muddy CR | 222 | 076 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101018 | N Churchtown Rd ovr Little Conestoga Ck | 1044 | 002 | Bridge Replacement | FD | BOF | 2027-04-08 |  | 0 | 344214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344214
Lancaster | 8 | Lancaster | 101018 | N Churchtown Rd ovr Little Conestoga Ck | 1044 | 002 | Bridge Replacement | ROW | BOF | 2027-04-08 |  | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000
Lancaster | 8 | Lancaster | 101018 | N Churchtown Rd ovr Little Conestoga Ck | 1044 | 002 | Bridge Replacement | UTL | BOF | 2027-04-08 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Lancaster | 8 | Lancaster | 101018 | N Churchtown Rd ovr Little Conestoga Ck | 1044 | 002 | Bridge Replacement | CON | BOF | 2027-04-08 |  | 0 | 0 | 1080552 | 1000000 | 0 | 0 | 0 | 0 | 0 | 2080552
Lancaster | 8 | Lancaster | 101020 | US 222 N/Muddy Creek | 222 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101022 | Fivepointville Rd ovr Little Muddy Ck | 1046 | 001 | Bridge Preservation - Federal | PE | 185 | 2027-09-16 |  | 6100 | 102077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108177
Lancaster | 8 | Lancaster | 101022 | Fivepointville Rd ovr Little Muddy Ck | 1046 | 001 | Bridge Preservation - Federal | FD | 185 | 2027-09-16 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Lancaster | 8 | Lancaster | 101022 | Fivepointville Rd ovr Little Muddy Ck | 1046 | 001 | Bridge Preservation - Federal | ROW | 185 | 2027-09-16 |  | 0 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000
Lancaster | 8 | Lancaster | 101022 | Fivepointville Rd ovr Little Muddy Ck | 1046 | 001 | Bridge Preservation - Federal | UTL | 185 | 2027-09-16 |  | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
Lancaster | 8 | Lancaster | 101022 | Fivepointville Rd ovr Little Muddy Ck | 1046 | 001 | Bridge Preservation - Federal | CON | 185 | 2027-09-16 |  | 0 | 0 | 1590400 | 0 | 0 | 0 | 0 | 0 | 0 | 1590400
Lancaster | 8 | Lancaster | 101033 | Maple Grove Rd Bridge PM | 1046 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
Lancaster | 8 | Lancaster | 101034 | US 222 N/Little Muddy Cr | 222 | 078 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101038 | Lloyd Rd over McCreary Run | 2007 | 014 | Bridge Restoration | FD | BOF | 2027-12-09 |  | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
Lancaster | 8 | Lancaster | 101038 | Lloyd Rd over McCreary Run | 2007 | 014 | Bridge Restoration | ROW | BOF | 2027-12-09 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Lancaster | 8 | Lancaster | 101038 | Lloyd Rd over McCreary Run | 2007 | 014 | Bridge Restoration | UTL | BOF | 2027-12-09 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Lancaster | 8 | Lancaster | 101038 | Lloyd Rd over McCreary Run | 2007 | 014 | Bridge Restoration | CON | BOF | 2027-12-09 |  | 0 | 0 | 0 | 555242 | 831385 | 0 | 0 | 0 | 0 | 1386627
Lancaster | 8 | Lancaster | 101039 | Ridge Road over PA 283 | 4041 | 002 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101044 | Spruce Grove Rd ovr W Br Octoraro Ck | 2007 | 015 | Bridge Restoration | FD | BOF | 2027-12-09 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Lancaster | 8 | Lancaster | 101044 | Spruce Grove Rd ovr W Br Octoraro Ck | 2007 | 015 | Bridge Restoration | ROW | BOF | 2027-12-09 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Lancaster | 8 | Lancaster | 101044 | Spruce Grove Rd ovr W Br Octoraro Ck | 2007 | 015 | Bridge Restoration | UTL | BOF | 2027-12-09 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Lancaster | 8 | Lancaster | 101044 | Spruce Grove Rd ovr W Br Octoraro Ck | 2007 | 015 | Bridge Restoration | CON | BOF | 2027-12-09 |  | 0 | 0 | 700000 | 700000 | 976416 | 0 | 0 | 0 | 0 | 2376416
Lancaster | 8 | Lancaster | 101055 | North Church St Brdg PM | 2019 | 019 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101061 | Bunker Hill Rd over Beaver Creek | 2029 | 015 | Bridge Restoration | FD | BOF | 2026-08-27 |  | 200000 | 134150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334150
Lancaster | 8 | Lancaster | 101061 | Bunker Hill Rd over Beaver Creek | 2029 | 015 | Bridge Restoration | ROW | BOF | 2026-08-27 |  | 15000 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21500
Lancaster | 8 | Lancaster | 101061 | Bunker Hill Rd over Beaver Creek | 2029 | 015 | Bridge Restoration | UTL | BOF | 2026-08-27 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Lancaster | 8 | Lancaster | 101061 | Bunker Hill Rd over Beaver Creek | 2029 | 015 | Bridge Restoration | CON | BOF | 2026-08-27 |  | 0 | 920000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920000
Lancaster | 8 | Lancaster | 101063 | Gypsy Hill Road Bridge PM | 2039 | 006 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101069 | Cardinal Road Bridge PM | 3008 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101077 | River Rd over Trib to Conestoga River | 3017 | 034 | Bridge Preservation - Federal | FD | BOF | 2027-01-14 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Lancaster | 8 | Lancaster | 101077 | River Rd over Trib to Conestoga River | 3017 | 034 | Bridge Preservation - Federal | ROW | BOF | 2027-01-14 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Lancaster | 8 | Lancaster | 101077 | River Rd over Trib to Conestoga River | 3017 | 034 | Bridge Preservation - Federal | CON | BOF | 2027-01-14 |  | 0 | 0 | 504620 | 339512 | 0 | 0 | 0 | 0 | 0 | 844132
Lancaster | 8 | Lancaster | 101103 | US 322 over Cocalico Cr | 322 | 056 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Lancaster | 8 | Lancaster | 101105 | US 322/Trib to Conestoga | 322 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152000 | 152000
Lancaster | 8 | Lancaster | 101106 | Old Phila Pike/Mill Creek | 340 | 012 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208000 | 208000
Lancaster | 8 | Lancaster | 101120 | East State Street Bridge | 372 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101122 | Water Street/Stamens Run | 441 | 034 | Bridge Preservation - Federal | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Lancaster | 8 | Lancaster | 101125 | Bridge Street over AMTRAK | 741 | 024 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101127 | Walnut Hill Rd Bridge PM | 3027 | 005 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101128 | Maytown Road over AMTRAK | 743 | 035 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208000 | 208000
Lancaster | 8 | Lancaster | 101129 | Mt Joy Rd/Little Chiques | 772 | 051 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208000 | 208000
Lancaster | 8 | Lancaster | 101130 | Long Ln over Stehman Run | 3030 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101135 | Newport Road/Cocalico Cr | 772 | 054 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101136 | Smithville Road Bridge PM | 3040 | 002 | Bridge Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 839314 | 0 | 0 | 0 | 0 | 839314
Lancaster | 8 | Lancaster | 101141 | W Main St/Cocalico Cr | 897 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101144 | Spooky Nook Rd ovr Amtrak | 4001 | 015 | Bridge Restoration | CON | STU |  |  | 0 | 0 | 0 | 0 | 1468534 | 0 | 0 | 0 | 0 | 1468534
Lancaster | 8 | Lancaster | 101145 | Peters Road over Mill Cre | 1013 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101148 | Cider Mill Rd/Conestoga | 1013 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Lancaster | 8 | Lancaster | 101150 | Stackstown Road Bridge PM | 4004 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101151 | SR 1035 over Middle Cr | 1035 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101152 | Elizabethtown Rd over Brubaker Run | 4008 | 034 | Bridge Restoration | FD | BOF | 2026-09-17 |  | 311915 | 13085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325000
Lancaster | 8 | Lancaster | 101152 | Elizabethtown Rd over Brubaker Run | 4008 | 034 | Bridge Restoration | ROW | BOF | 2026-09-17 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Lancaster | 8 | Lancaster | 101152 | Elizabethtown Rd over Brubaker Run | 4008 | 034 | Bridge Restoration | UTL | BOF | 2026-09-17 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Lancaster | 8 | Lancaster | 101152 | Elizabethtown Rd over Brubaker Run | 4008 | 034 | Bridge Restoration | CON | BOF | 2026-09-17 |  | 0 | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1160000
Lancaster | 8 | Lancaster | 101153 | SR 1037 over Hammer Cr | 1037 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101155 | Church Street/Cocalico Cr | 1047 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101158 | Willow Road Bridge PM | 1090 | 001 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101158 | Willow Road Bridge PM | 1090 | 001 | Bridge Preservation - Federal | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730000 | 1730000
Lancaster | 8 | Lancaster | 101159 | Hartman Station Br. PM | 1092 | 001 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101159 | Hartman Station Br. PM | 1092 | 001 | Bridge Preservation - Federal | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2547000 | 2547000
Lancaster | 8 | Lancaster | 101161 | May Post Office Road Brdg | 2015 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101264 | Harrisburg Pike Bridge PM | 4020 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101264 | Harrisburg Pike Bridge PM | 4020 | 0 | Bridge Restoration | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1891000 | 1891000
Lancaster | 8 | Lancaster | 101267 | Walnut Run Road Bridge | 2031 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101271 | Queen Road over Pequea Cr | 2035 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101272 | Greenfield Rd over US 30 | 1001 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101273 | Cinder Road Bridge | 3015 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101275 | Safe Harbor Road Bridge | 3017 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101279 | Old Phila Pike over US30 | 340 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101282 | Marietta Avenue Bridge PM | 23 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101284 | Truce Road Bridge | 3018 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101287 | Lampeter Road/Mill Creek | 3028 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101290 | Franklin Rd over Strickler Run | 3036 | 005 | Bridge Preservation - Federal | FD | BOF | 2026-09-17 |  | 177380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177380
Lancaster | 8 | Lancaster | 101290 | Franklin Rd over Strickler Run | 3036 | 005 | Bridge Preservation - Federal | ROW | BOF | 2026-09-17 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Lancaster | 8 | Lancaster | 101290 | Franklin Rd over Strickler Run | 3036 | 005 | Bridge Preservation - Federal | CON | BOF | 2026-09-17 |  | 0 | 322000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322000
Lancaster | 8 | Lancaster | 101295 | New Holland Pk Bridge PM | 23 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Lancaster | 8 | Lancaster | 101296 | East High St over PA 283 | 4008 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101300 | PA 72 over Chiques Creek | 72 | 063 | Bridge Restoration | ROW | 185 | 2026-09-17 |  | 200000 | 215411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415411
Lancaster | 8 | Lancaster | 101300 | PA 72 over Chiques Creek | 72 | 063 | Bridge Restoration | UTL | 185 | 2026-09-17 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Lancaster | 8 | Lancaster | 101300 | PA 72 over Chiques Creek | 72 | 063 | Bridge Restoration | CON | NHPP | 2026-09-17 |  | 3347654 | 730316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4077970
Lancaster | 8 | Lancaster | 101301 | Old Line Rd over Rife Run | 4026 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101302 | Bellaire Rd over Conewago Cr | 4037 | 005 | Bridge Restoration | FD | 185 | 2026-12-10 |  | 200000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245000
Lancaster | 8 | Lancaster | 101302 | Bellaire Rd over Conewago Cr | 4037 | 005 | Bridge Restoration | CON | 185 | 2026-12-10 |  | 0 | 0 | 644000 | 0 | 0 | 0 | 0 | 0 | 0 | 644000
Lancaster | 8 | Lancaster | 101305 | State Street over Groffs | 772 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 101328 | US 222 SB Bridge PM | 222 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lancaster | 8 | Lancaster | 108514 | SR 897 Resurfacing | 897 | 035 | Highway Restoration | PE | 581 | 2028-04-27 |  | 238668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238668
Lancaster | 8 | Lancaster | 108514 | SR 897 Resurfacing | 897 | 035 | Highway Restoration | CON | 581 | 2028-04-27 |  | 0 | 23424 | 0 | 0 | 0 | 0 | 0 | 0 | 4077808 | 4101232
Lancaster | 8 | Lancaster | 109618 | US 222 Reconstruction | 222 | 071 | Highway Reconstruction | FD | NHPP | 2028-05-25 |  | 4000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000
Lancaster | 8 | Lancaster | 109618 | US 222 Reconstruction | 222 | 071 | Highway Reconstruction | ROW | NHPP | 2028-05-25 |  | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Lancaster | 8 | Lancaster | 109618 | US 222 Reconstruction | 222 | 071 | Highway Reconstruction | UTL | NHPP | 2028-05-25 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Lancaster | 8 | Lancaster | 109618 | US 222 Reconstruction | 222 | 071 | Highway Reconstruction | CON | NHPP | 2028-05-25 |  | 0 | 0 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 20000000
Lancaster | 8 | Lancaster | 109618 | US 222 Reconstruction | 222 | 071 | Highway Reconstruction | CON | NHPP | 2028-05-25 |  | 0 | 0 | 8659359 | 8046901 | 10182000 | 10182000 | 8097828 | 0 | 0 | 45168088
Lancaster | 8 | Lancaster | 109618 | US 222 Reconstruction | 222 | 071 | Highway Reconstruction | CON | STU | 2028-05-25 |  | 0 | 0 | 4021794 | 6417976 | 6972034 | 8281216 | 2135099 | 0 | 0 | 27828119
Lancaster | 8 | Lancaster | 110475 | Weaver Rd Bridge | 7405 | BRG | Bridge Restoration | FD | BOF | 2027-06-24 |  | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
Lancaster | 8 | Lancaster | 110475 | Weaver Rd Bridge | 7405 | BRG | Bridge Restoration | FD | 183 | 2027-06-24 |  | 0 | 67500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500
Lancaster | 8 | Lancaster | 110475 | Weaver Rd Bridge | 7405 | BRG | Bridge Restoration | FD | LOC | 2027-06-24 |  | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500
Lancaster | 8 | Lancaster | 110475 | Weaver Rd Bridge | 7405 | BRG | Bridge Restoration | ROW | BOF | 2027-06-24 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Lancaster | 8 | Lancaster | 110475 | Weaver Rd Bridge | 7405 | BRG | Bridge Restoration | ROW | 183 | 2027-06-24 |  | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500
Lancaster | 8 | Lancaster | 110475 | Weaver Rd Bridge | 7405 | BRG | Bridge Restoration | ROW | LOC | 2027-06-24 |  | 0 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500
Lancaster | 8 | Lancaster | 110475 | Weaver Rd Bridge | 7405 | BRG | Bridge Restoration | UTL | BOF | 2027-06-24 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Lancaster | 8 | Lancaster | 110475 | Weaver Rd Bridge | 7405 | BRG | Bridge Restoration | UTL | 183 | 2027-06-24 |  | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
Lancaster | 8 | Lancaster | 110475 | Weaver Rd Bridge | 7405 | BRG | Bridge Restoration | UTL | LOC | 2027-06-24 |  | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
Lancaster | 8 | Lancaster | 110475 | Weaver Rd Bridge | 7405 | BRG | Bridge Restoration | CON | BOF | 2027-06-24 |  | 0 | 0 | 560977 | 0 | 0 | 0 | 0 | 0 | 0 | 560977
Lancaster | 8 | Lancaster | 110475 | Weaver Rd Bridge | 7405 | BRG | Bridge Restoration | CON | BRIP | 2027-06-24 |  | 0 | 0 | 0 | 2955200 | 1600000 | 0 | 0 | 0 | 0 | 4555200
Lancaster | 8 | Lancaster | 110475 | Weaver Rd Bridge | 7405 | BRG | Bridge Restoration | CON | 183 | 2027-06-24 |  | 0 | 0 | 105184 | 554100 | 300000 | 0 | 0 | 0 | 0 | 959284
Lancaster | 8 | Lancaster | 110475 | Weaver Rd Bridge | 7405 | BRG | Bridge Restoration | CON | LOC | 2027-06-24 |  | 0 | 0 | 35061 | 184700 | 0 | 0 | 0 | 0 | 0 | 219761
Lancaster | 8 | Lancaster | 110483 | S. Oak St Bridge | 7410 | 0 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000
Lancaster | 8 | Lancaster | 110502 | US30/PA 462 Improvements | 30 | 146 | Safety Improvement | FD | NHPP | 2026-09-03 |  | 269128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269128
Lancaster | 8 | Lancaster | 110502 | US30/PA 462 Improvements | 30 | 146 | Safety Improvement | CON | CAQ | 2026-09-03 |  | 0 | 1261280 | 0 | 0 | 2259846 | 0 | 0 | 0 | 0 | 3521126
Lancaster | 8 | Lancaster | 110502 | US30/PA 462 Improvements | 30 | 146 | Safety Improvement | CON | NHPP | 2026-09-03 |  | 0 | 7893428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7893428
Lancaster | 8 | Lancaster | 110502 | US30/PA 462 Improvements | 30 | 146 | Safety Improvement | CON | STP | 2026-09-03 |  | 0 | 3625178 | 0 | 0 | 2662140 | 0 | 0 | 0 | 0 | 6287318
Lancaster | 8 | Lancaster | 110502 | US30/PA 462 Improvements | 30 | 146 | Safety Improvement | CON | STU | 2026-09-03 |  | 0 | 3465601 | 0 | 0 | 485797 | 0 | 0 | 0 | 0 | 3951398
Lancaster | 8 | Lancaster | 110552 | Water Street Bicycle Blvd |  | SGT | Bicycle Pedestrian Highway | CON | STU | 2026-09-03 |  | 1524920 | 687560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2212480
Lancaster | 8 | Lancaster | 110556 | Main Street Sidewalk Impr | 23 | 036 | Bicycle Pedestrian Highway | ROW | STU | 2026-07-16 |  | 0 | 239634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239634
Lancaster | 8 | Lancaster | 110556 | Main Street Sidewalk Impr | 23 | 036 | Bicycle Pedestrian Highway | CON | STU | 2026-07-16 |  | 0 | 1130404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1130404
Lancaster | 8 | Lancaster | 110557 | Intercourse Village Safety Imp | 772 | 053 | Safety Improvement | PE | STU | 2027-06-24 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Lancaster | 8 | Lancaster | 110557 | Intercourse Village Safety Imp | 772 | 053 | Safety Improvement | ROW | STU | 2027-06-24 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Lancaster | 8 | Lancaster | 110557 | Intercourse Village Safety Imp | 772 | 053 | Safety Improvement | CON | STU | 2027-06-24 |  | 0 | 0 | 1586211 | 0 | 0 | 0 | 0 | 0 | 0 | 1586211
Lancaster | 8 | Lancaster | 112615 | Enola Low Grade Trail East |  | TAP | Transportation Enhancement | CON | TAU | 2023-09-28 | 2023-09-28 | 69000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000
Lancaster | 8 | Lancaster | 112969 | Lincoln HWY Resurf | 30 | 148 | Highway Restoration | UTL | 581 | 2026-03-26 | 2026-03-26 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
Lancaster | 8 | Lancaster | 112969 | Lincoln HWY Resurf | 30 | 148 | Highway Restoration | UTL | LOC | 2026-03-26 | 2026-03-26 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
Lancaster | 8 | Lancaster | 112969 | Lincoln HWY Resurf | 30 | 148 | Highway Restoration | CON | 581 | 2026-03-26 | 2026-03-26 | 3891894 | 777683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4669577
Lancaster | 8 | Lancaster | 112972 | Weaverland Valley Rd Resurf | 897 | 033 | Highway Restoration | CON | 581 | 2025-10-23 | 2025-10-23 | 1673861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1673861
Lancaster | 8 | Lancaster | 114205 | Strasburg Pk Improvements | 2029 | 016 | Safety Improvement | PE | HSIP | 2029-01-11 |  | 0 | 21198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21198
Lancaster | 8 | Lancaster | 114205 | Strasburg Pk Improvements | 2029 | 016 | Safety Improvement | FD | HSIP | 2029-01-11 |  | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
Lancaster | 8 | Lancaster | 114205 | Strasburg Pk Improvements | 2029 | 016 | Safety Improvement | ROW | HSIP | 2029-01-11 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Lancaster | 8 | Lancaster | 114205 | Strasburg Pk Improvements | 2029 | 016 | Safety Improvement | UTL | HSIP | 2029-01-11 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Lancaster | 8 | Lancaster | 114205 | Strasburg Pk Improvements | 2029 | 016 | Safety Improvement | CON | HSIP | 2029-01-11 |  | 0 | 0 | 0 | 280647 | 2214590 | 0 | 0 | 0 | 0 | 2495237
Lancaster | 8 | Lancaster | 114206 | McGovernville Rd Improvements | 741 | 031 | Safety Improvement | FD | HSIP | 2026-09-03 |  | 693498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693498
Lancaster | 8 | Lancaster | 114206 | McGovernville Rd Improvements | 741 | 031 | Safety Improvement | ROW | HSIP | 2026-09-03 |  | 400000 | 15411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415411
Lancaster | 8 | Lancaster | 114206 | McGovernville Rd Improvements | 741 | 031 | Safety Improvement | UTL | HSIP | 2026-09-03 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Lancaster | 8 | Lancaster | 114206 | McGovernville Rd Improvements | 741 | 031 | Safety Improvement | CON | HSIP | 2026-09-03 |  | 0 | 2828330 | 846400 | 0 | 0 | 0 | 0 | 0 | 0 | 3674730
Lancaster | 8 | Lancaster | 114206 | McGovernville Rd Improvements | 741 | 031 | Safety Improvement | CON | STP | 2026-09-03 |  | 0 | 1315744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1315744
Lancaster | 8 | Lancaster | 114216 | Water Street Bike Ped Blvd 2 |  |  | Bicycle Pedestrian Highway | CON | STU | 2026-09-03 |  | 1618400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1618400
Lancaster | 8 | Lancaster | 114217 | Riverfront to Downtown Connections Streetscape |  |  | Transportation Enhancement | CON | STU | 2026-01-08 | 2026-01-08 | 1648035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1648035
Lancaster | 8 | Lancaster | 114218 | Strasburg Pk to S Oakview Rd Trail |  |  | Bicycle Pedestrian Highway | CON | TAP | 2025-06-26 | 2025-06-26 | 1154417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1154417
Lancaster | 8 | Lancaster | 114218 | Strasburg Pk to S Oakview Rd Trail |  |  | Bicycle Pedestrian Highway | CON | TAU | 2025-06-26 | 2025-06-26 | 46002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46002
Lancaster | 8 | Lancaster | 114324 | Main St Traffic Signal Upgrades | 72 | 064 | Congestion Reduction | CON | CAQ | 2024-12-12 | 2024-12-12 | 946518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 946518
Lancaster | 8 | Lancaster | 115004 | Norman Wood Bridge Study | 372 | SDY | Study Phase of Project | STUDY | 185 |  |  | 310000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310000
Lancaster | 8 | Lancaster | 116658 | Church Street Resurface | 222 | 083 | Highway Restoration | PE | STP | 2026-08-27 |  | 0 | 18647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18647
Lancaster | 8 | Lancaster | 116658 | Church Street Resurface | 222 | 083 | Highway Restoration | FD | STP | 2026-08-27 |  | 309496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309496
Lancaster | 8 | Lancaster | 116658 | Church Street Resurface | 222 | 083 | Highway Restoration | UTL | STP | 2026-08-27 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Lancaster | 8 | Lancaster | 116658 | Church Street Resurface | 222 | 083 | Highway Restoration | CON | 581 | 2026-08-27 |  | 0 | 3363360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363360
Lancaster | 8 | Lancaster | 116897 | Plaza Boulevard over Amtrak | 7101 | BRG | Bridge Preservation - Federal | PE | 185 | 2029-08-23 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Lancaster | 8 | Lancaster | 116897 | Plaza Boulevard over Amtrak | 7101 | BRG | Bridge Preservation - Federal | FD | BOF | 2029-08-23 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Lancaster | 8 | Lancaster | 116897 | Plaza Boulevard over Amtrak | 7101 | BRG | Bridge Preservation - Federal | ROW | BOF | 2029-08-23 |  | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000
Lancaster | 8 | Lancaster | 116897 | Plaza Boulevard over Amtrak | 7101 | BRG | Bridge Preservation - Federal | UTL | BOF | 2029-08-23 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Lancaster | 8 | Lancaster | 116897 | Plaza Boulevard over Amtrak | 7101 | BRG | Bridge Preservation - Federal | CON | BOF | 2029-08-23 |  | 0 | 0 | 0 | 852267 | 700000 | 0 | 0 | 0 | 0 | 1552267
Lancaster | 8 | Lancaster | 117238 | Peartown Rd Stream Relocation | 1053 | 004 | General Maintenance | PE | 581 | 2027-02-11 |  | 38359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38359
Lancaster | 8 | Lancaster | 117362 | Rothsville Road Resurface | 772 | 059 | Highway Restoration | CON | STU | 2024-08-08 | 2024-08-08 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Lancaster | 8 | Lancaster | 117414 | May Post Office Rd ov Trib to Calamus Run | 2015 | 013 | Bridge Restoration | FD | 185 | 2026-08-27 |  | 250000 | 37433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287433
Lancaster | 8 | Lancaster | 117414 | May Post Office Rd ov Trib to Calamus Run | 2015 | 013 | Bridge Restoration | ROW | 185 | 2026-08-27 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Lancaster | 8 | Lancaster | 117414 | May Post Office Rd ov Trib to Calamus Run | 2015 | 013 | Bridge Restoration | UTL | 185 | 2026-08-27 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Lancaster | 8 | Lancaster | 117414 | May Post Office Rd ov Trib to Calamus Run | 2015 | 013 | Bridge Restoration | CON | 185 | 2026-08-27 |  | 0 | 747500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747500
Lancaster | 8 | Lancaster | 117415 | Norman Wood Bridge Improvement | 372 | 024 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 1000000
Lancaster | 8 | Lancaster | 117415 | Norman Wood Bridge Improvement | 372 | 024 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7854566 | 33917999 | 41772565
Lancaster | 8 | Lancaster | 117415 | Norman Wood Bridge Improvement | 372 | 024 | Bridge Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9116000 | 36466000 | 45582000
Lancaster | 8 | Lancaster | 117456 | Milton Grove Rd over Back Run | 4033 | 008 | Bridge Restoration | FD | BOF | 2026-09-17 |  | 312728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312728
Lancaster | 8 | Lancaster | 117456 | Milton Grove Rd over Back Run | 4033 | 008 | Bridge Restoration | ROW | BOF | 2026-09-17 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Lancaster | 8 | Lancaster | 117456 | Milton Grove Rd over Back Run | 4033 | 008 | Bridge Restoration | UTL | BOF | 2026-09-17 |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Lancaster | 8 | Lancaster | 117456 | Milton Grove Rd over Back Run | 4033 | 008 | Bridge Restoration | CON | BOF | 2026-09-17 |  | 0 | 1005309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1005309
Lancaster | 8 | Lancaster | 117456 | Milton Grove Rd over Back Run | 4033 | 008 | Bridge Restoration | CON | 185 | 2026-09-17 |  | 0 | 594691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594691
Lancaster | 8 | Lancaster | 118260 | PA 72 and Lititz Road Intersection | 72 | 069 | Safety Improvement | FD | HSIP | 2027-11-04 |  | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Lancaster | 8 | Lancaster | 118260 | PA 72 and Lititz Road Intersection | 72 | 069 | Safety Improvement | ROW | HSIP | 2027-11-04 |  | 653000 | 297000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000
Lancaster | 8 | Lancaster | 118260 | PA 72 and Lititz Road Intersection | 72 | 069 | Safety Improvement | UTL | HSIP | 2027-11-04 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Lancaster | 8 | Lancaster | 118260 | PA 72 and Lititz Road Intersection | 72 | 069 | Safety Improvement | CON | HSIP | 2027-11-04 |  | 0 | 0 | 1314883 | 700000 | 785117 | 0 | 0 | 0 | 0 | 2800000
Lancaster | 8 | Lancaster | 118297 | T-470 Black Bear Rd over Conowingo Ck | 7212 | BRG | Bridge Restoration | FD | BRIP | 2027-03-11 |  | 150938 | 74062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
Lancaster | 8 | Lancaster | 118297 | T-470 Black Bear Rd over Conowingo Ck | 7212 | BRG | Bridge Restoration | ROW | BRIP | 2027-03-11 |  | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
Lancaster | 8 | Lancaster | 118297 | T-470 Black Bear Rd over Conowingo Ck | 7212 | BRG | Bridge Restoration | UTL | BRIP | 2027-03-11 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Lancaster | 8 | Lancaster | 118297 | T-470 Black Bear Rd over Conowingo Ck | 7212 | BRG | Bridge Restoration | CON | BOF | 2027-03-11 |  | 0 | 0 | 0 | 224749 | 500000 | 0 | 0 | 0 | 0 | 724749
Lancaster | 8 | Lancaster | 118297 | T-470 Black Bear Rd over Conowingo Ck | 7212 | BRG | Bridge Restoration | CON | BRIP | 2027-03-11 |  | 0 | 0 | 0 | 469304 | 0 | 0 | 0 | 0 | 0 | 469304
Lancaster | 8 | Lancaster | 118298 | T-713 Pinetown Rd over Lititz Run | 7101 | BRG | Bridge Restoration | FD | BRIP | 2028-04-06 |  | 0 | 0 | 410000 | 0 | 0 | 0 | 0 | 0 | 0 | 410000
Lancaster | 8 | Lancaster | 118298 | T-713 Pinetown Rd over Lititz Run | 7101 | BRG | Bridge Restoration | ROW | BRIP | 2028-04-06 |  | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000
Lancaster | 8 | Lancaster | 118298 | T-713 Pinetown Rd over Lititz Run | 7101 | BRG | Bridge Restoration | UTL | BRIP | 2028-04-06 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Lancaster | 8 | Lancaster | 118298 | T-713 Pinetown Rd over Lititz Run | 7101 | BRG | Bridge Restoration | CON | BOF | 2028-04-06 |  | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 800000
Lancaster | 8 | Lancaster | 118298 | T-713 Pinetown Rd over Lititz Run | 7101 | BRG | Bridge Restoration | CON | BRIP | 2028-04-06 |  | 0 | 0 | 0 | 811971 | 0 | 0 | 0 | 0 | 0 | 811971
Lancaster | 8 | Lancaster | 118511 | Conestoga Boardwalk | 23 | TAP | Bicycle Pedestrian Highway | CON | STU | 2027-03-11 |  | 0 | 0 | 421624 | 0 | 0 | 0 | 0 | 0 | 0 | 421624
Lancaster | 8 | Lancaster | 118511 | Conestoga Boardwalk | 23 | TAP | Bicycle Pedestrian Highway | CON | TAP | 2027-03-11 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Lancaster | 8 | Lancaster | 118511 | Conestoga Boardwalk | 23 | TAP | Bicycle Pedestrian Highway | CON | TAU | 2027-03-11 |  | 0 | 0 | 865000 | 865000 | 0 | 0 | 0 | 0 | 0 | 1730000
Lancaster | 8 | Lancaster | 118767 | SR 4022 Lititz Road Realignment | 4022 | 007 | New Alignment | CON | 581 |  |  | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
Lancaster | 8 | Lancaster | 119202 | Route 462 Eastern Corridor Transportation Enhance | 462 | 067 | Bicycle Pedestrian Highway | CON | STU |  |  | 0 | 0 | 0 | 2568995 | 60607 | 0 | 0 | 0 | 0 | 2629602
Lancaster | 8 | Lancaster | 119203 | Oak Grove to Conestoga Pines Study LHP |  |  | Study Phase of Project | STUDY | LOC |  |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Lancaster | 8 | Lancaster | 119206 | Market Square Improvement | 772 | 062 | Safety Improvement | CON | STU | 2026-08-13 |  | 0 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000
Lancaster | 8 | Lancaster | 119211 | Lancaster MPO TIP Funded Bridge Repair Contract | 222 | BRC | Bridge Preservation - State Funded | PE | 185 | 2026-08-13 |  | 0 | 1458504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1458504
Lancaster | 8 | Lancaster | 119211 | Lancaster MPO TIP Funded Bridge Repair Contract | 222 | BRC | Bridge Preservation - State Funded | CON | BRIP | 2026-08-13 |  | 3280000 | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11280000
Lancaster | 8 | Lancaster | 119211 | Lancaster MPO TIP Funded Bridge Repair Contract | 222 | BRC | Bridge Preservation - State Funded | CON | 185 | 2026-08-13 |  | 420000 | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2820000
Lancaster | 8 | Lancaster | 119284 | Carbon Reduction Program (CRP) Lancaster MPO RSL |  |  | Reserve Line Item | CON | CRP |  |  | 184637 | 0 | 332836 | 495000 | 495000 | 495000 | 495000 | 495000 | 1979000 | 4971473
Lancaster | 8 | Lancaster | 119284 | Carbon Reduction Program (CRP) Lancaster MPO RSL |  |  | Reserve Line Item | CON | CRPU |  |  | 0 | 0 | 186000 | 1086000 | 1086000 | 1086000 | 1086000 | 1086000 | 4346000 | 9962000
Lancaster | 8 | Lancaster | 119474 | Enola Low Grade Trail East 2 |  | TAP | Transportation Enhancement | CON | TAP | 2026-07-30 |  | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Lancaster | 8 | Lancaster | 119474 | Enola Low Grade Trail East 2 |  | TAP | Transportation Enhancement | CON | TAU | 2026-07-30 |  | 839998 | 115492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 955490
Lancaster | 8 | Lancaster | 119670 | Columbia Ave Safety Improvements | 462 | 065 | Safety Improvement | PE | HSIP | 2027-07-29 |  | 150000 | 86349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236349
Lancaster | 8 | Lancaster | 119670 | Columbia Ave Safety Improvements | 462 | 065 | Safety Improvement | PE | STP | 2027-07-29 |  | 0 | 135900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135900
Lancaster | 8 | Lancaster | 119670 | Columbia Ave Safety Improvements | 462 | 065 | Safety Improvement | FD | HSIP | 2027-07-29 |  | 0 | 35900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35900
Lancaster | 8 | Lancaster | 119670 | Columbia Ave Safety Improvements | 462 | 065 | Safety Improvement | CON | HSIP | 2027-07-29 |  | 0 | 0 | 0 | 797016 | 0 | 0 | 0 | 0 | 0 | 797016
Lancaster | 8 | Lancaster | 119671 | King Street Safety Improvements | 462 | 066 | Safety Improvement | PE | HSIP | 2028-01-01 |  | 0 | 0 | 185200 | 0 | 0 | 0 | 0 | 0 | 0 | 185200
Lancaster | 8 | Lancaster | 119671 | King Street Safety Improvements | 462 | 066 | Safety Improvement | PE | STP | 2028-01-01 |  | 0 | 0 | 47700 | 0 | 0 | 0 | 0 | 0 | 0 | 47700
Lancaster | 8 | Lancaster | 119671 | King Street Safety Improvements | 462 | 066 | Safety Improvement | FD | STP | 2028-01-01 |  | 0 | 0 | 135200 | 0 | 0 | 0 | 0 | 0 | 0 | 135200
Lancaster | 8 | Lancaster | 119671 | King Street Safety Improvements | 462 | 066 | Safety Improvement | UTL | STP | 2028-01-01 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Lancaster | 8 | Lancaster | 119671 | King Street Safety Improvements | 462 | 066 | Safety Improvement | CON | HSIP | 2028-01-01 |  | 0 | 0 | 0 | 753062 | 300000 | 0 | 0 | 0 | 0 | 1053062
Lancaster | 8 | Lancaster | 119672 | Lititz Pike Safety Improvements | 501 | 038 | Safety Improvement | PE | HSIP | 2027-07-29 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Lancaster | 8 | Lancaster | 119672 | Lititz Pike Safety Improvements | 501 | 038 | Safety Improvement | PE | STP | 2027-07-29 |  | 49900 | 18078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67978
Lancaster | 8 | Lancaster | 119672 | Lititz Pike Safety Improvements | 501 | 038 | Safety Improvement | FD | HSIP | 2027-07-29 |  | 0 | 90300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90300
Lancaster | 8 | Lancaster | 119672 | Lititz Pike Safety Improvements | 501 | 038 | Safety Improvement | ROW | HSIP | 2027-07-29 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Lancaster | 8 | Lancaster | 119672 | Lititz Pike Safety Improvements | 501 | 038 | Safety Improvement | UTL | HSIP | 2027-07-29 |  | 0 | 21299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21299
Lancaster | 8 | Lancaster | 119672 | Lititz Pike Safety Improvements | 501 | 038 | Safety Improvement | CON | HSIP | 2027-07-29 |  | 0 | 0 | 0 | 479440 | 0 | 0 | 0 | 0 | 0 | 479440
Lancaster | 8 | Lancaster | 119673 | Prospect Rd and Fairview Rd Int Safety Imp | 4001 | 026 | Safety Improvement | PE | HSIP |  |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Lancaster | 8 | Lancaster | 119673 | Prospect Rd and Fairview Rd Int Safety Imp | 4001 | 026 | Safety Improvement | FD | HSIP |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Lancaster | 8 | Lancaster | 119673 | Prospect Rd and Fairview Rd Int Safety Imp | 4001 | 026 | Safety Improvement | ROW | HSIP |  |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Lancaster | 8 | Lancaster | 119673 | Prospect Rd and Fairview Rd Int Safety Imp | 4001 | 026 | Safety Improvement | UTL | HSIP |  |  | 0 | 41971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41971
Lancaster | 8 | Lancaster | 119673 | Prospect Rd and Fairview Rd Int Safety Imp | 4001 | 026 | Safety Improvement | CON | HSIP |  |  | 0 | 0 | 0 | 674835 | 0 | 0 | 0 | 0 | 0 | 674835
Lancaster | 8 | Lancaster | 120050 | Veterans Memorial Bridge Interim Repairs | 462 | 062 | Bridge Restoration | CON | 185 | 2024-02-15 | 2024-02-15 | 35972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35972
Lancaster | 8 | Lancaster | 120649 | Quarry Rd Bridge Repairs | 1003 | 029 | Bridge Restoration | PE | 185 | 2027-06-24 |  | 454908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454908
Lancaster | 8 | Lancaster | 120649 | Quarry Rd Bridge Repairs | 1003 | 029 | Bridge Restoration | FD | 185 | 2027-06-24 |  | 101416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101416
Lancaster | 8 | Lancaster | 120649 | Quarry Rd Bridge Repairs | 1003 | 029 | Bridge Restoration | ROW | 185 | 2027-06-24 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Lancaster | 8 | Lancaster | 120649 | Quarry Rd Bridge Repairs | 1003 | 029 | Bridge Restoration | CON | 185 | 2027-06-24 |  | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
Lancaster | 8 | Lancaster | 120663 | US 222 Resurfacing 3 | 222 | 086 | 409 Expanded Maintenance | CON | NHPP | 2024-10-24 | 2024-10-24 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Lancaster | 8 | Lancaster | 120663 | US 222 Resurfacing 3 | 222 | 086 | 409 Expanded Maintenance | CON | STU | 2024-10-24 | 2024-10-24 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Lancaster | 8 | Lancaster | 120870 | Little Conestoga Blue/Green Corridor |  |  | Bicycle Pedestrian Highway | CON | STU | 2029-01-11 |  | 0 | 0 | 0 | 277029 | 277028 | 0 | 0 | 0 | 0 | 554057
Lancaster | 8 | Lancaster | 120871 | School Lane Active Transportation Project |  |  | Bicycle Pedestrian Highway | CON | STU | 2028-02-03 |  | 0 | 0 | 466284 | 0 | 0 | 0 | 0 | 0 | 0 | 466284
Lancaster | 8 | Lancaster | 120872 | Marshall Avenue Multimodal Corridor |  |  | Bicycle Pedestrian Highway | CON | STU | 2027-02-25 |  | 0 | 0 | 2768087 | 0 | 0 | 452393 | 0 | 0 | 0 | 3220480
Lancaster | 8 | Lancaster | 121042 | PA 272 NB Resurfacing | 272 | 052 | Highway Restoration | PE | 581 | 2026-09-03 |  | 169822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169822
Lancaster | 8 | Lancaster | 121042 | PA 272 NB Resurfacing | 272 | 052 | Highway Restoration | CON | 581 | 2026-09-03 |  | 0 | 3713150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3713150
Lancaster | 8 | Lancaster | 121044 | PA 741 Improvements | 741 | 032 | Safety Improvement | PE | 581 |  |  | 500000 | 396255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 896255
Lancaster | 8 | Lancaster | 121044 | PA 741 Improvements | 741 | 032 | Safety Improvement | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8000000 | 0 | 0 | 8000000
Lancaster | 8 | Lancaster | 121045 | PA 772 Resurfacing | 772 | 063 | Highway Restoration | FD | 581 | 2027-06-24 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Lancaster | 8 | Lancaster | 121045 | PA 772 Resurfacing | 772 | 063 | Highway Restoration | CON | 581 | 2027-06-24 |  | 0 | 0 | 3182700 | 3182700 | 0 | 0 | 0 | 0 | 0 | 6365400
Lancaster | 8 | Lancaster | 121046 | Rothsville Road Resurface | 1018 | 008 | 409 Expanded Maintenance | PE | 581 | 2027-02-25 |  | 825528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825528
Lancaster | 8 | Lancaster | 121046 | Rothsville Road Resurface | 1018 | 008 | 409 Expanded Maintenance | ROW | 581 | 2027-02-25 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Lancaster | 8 | Lancaster | 121046 | Rothsville Road Resurface | 1018 | 008 | 409 Expanded Maintenance | UTL | 581 | 2027-02-25 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Lancaster | 8 | Lancaster | 121047 | PA 272 SB Resurfacing | 272 | 053 | Highway Restoration | PE | 581 | 2026-09-03 |  | 168644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168644
Lancaster | 8 | Lancaster | 121047 | PA 272 SB Resurfacing | 272 | 053 | Highway Restoration | CON | 581 | 2026-09-03 |  | 0 | 2882594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2882594
Lancaster | 8 | Lancaster | 121048 | Pitney Rd and PA 340 Intersection with PA 462 | 462 | 068 | Safety Improvement | PE | CAQ |  |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Lancaster | 8 | Lancaster | 121048 | Pitney Rd and PA 340 Intersection with PA 462 | 462 | 068 | Safety Improvement | CON | CAQ |  |  | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 0 | 8000000
Lancaster | 8 | Lancaster | 121049 | Microtransit Implementation |  |  | Congestion Reduction | CON | CRPU |  |  | 0 | 900000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000
Lancaster | 8 | Lancaster | 121050 | SCTA Bus Replacement |  |  | Congestion Reduction | CON | CRPU |  |  | 882706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882706
Lancaster | 8 | Lancaster | 121060 | ITS - Lancaster TSMO 2025-2026 | 30 | ITS | Congestion Reduction | PE | CRP | 2026-09-03 |  | 70352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70352
Lancaster | 8 | Lancaster | 121060 | ITS - Lancaster TSMO 2025-2026 | 30 | ITS | Congestion Reduction | PE | CRP | 2026-09-03 |  | 240599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240599
Lancaster | 8 | Lancaster | 121060 | ITS - Lancaster TSMO 2025-2026 | 30 | ITS | Congestion Reduction | PE | CRPU | 2026-09-03 |  | 17588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17588
Lancaster | 8 | Lancaster | 121060 | ITS - Lancaster TSMO 2025-2026 | 30 | ITS | Congestion Reduction | CON | CRP | 2026-09-03 |  | 0 | 149648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149648
Lancaster | 8 | Lancaster | 121060 | ITS - Lancaster TSMO 2025-2026 | 30 | ITS | Congestion Reduction | CON | CRP | 2026-09-03 |  | 0 | 278188 | 162164 | 0 | 0 | 0 | 0 | 0 | 0 | 440352
Lancaster | 8 | Lancaster | 121061 | Lititz Pk and Oregon Pk - Lancaster TSMO 2025-2026 |  |  | Intelligent Transportation System | FD | CRPU |  |  | 24219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24219
Lancaster | 8 | Lancaster | 121062 | PA 741 Signals - Lancaster TSMO 2025-2026 | 741 | ITS | Transportation Enhancement | PE | CRP | 2026-07-30 |  | 18614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18614
Lancaster | 8 | Lancaster | 121062 | PA 741 Signals - Lancaster TSMO 2025-2026 | 741 | ITS | Transportation Enhancement | PE | CRPU | 2026-07-30 |  | 27666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27666
Lancaster | 8 | Lancaster | 121062 | PA 741 Signals - Lancaster TSMO 2025-2026 | 741 | ITS | Transportation Enhancement | FD | CRP | 2026-07-30 |  | 0 | 2665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2665
Lancaster | 8 | Lancaster | 121062 | PA 741 Signals - Lancaster TSMO 2025-2026 | 741 | ITS | Transportation Enhancement | FD | CRPU | 2026-07-30 |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Lancaster | 8 | Lancaster | 121062 | PA 741 Signals - Lancaster TSMO 2025-2026 | 741 | ITS | Transportation Enhancement | CON | CRP | 2026-07-30 |  | 0 | 105478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105478
Lancaster | 8 | Lancaster | 121062 | PA 741 Signals - Lancaster TSMO 2025-2026 | 741 | ITS | Transportation Enhancement | CON | CRP | 2026-07-30 |  | 0 | 48522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48522
Lancaster | 8 | Lancaster | 121062 | PA 741 Signals - Lancaster TSMO 2025-2026 | 741 | ITS | Transportation Enhancement | CON | CRPU | 2026-07-30 |  | 0 | 186000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000
Lancaster | 8 | Lancaster | 121063 | New Holland Pk Signals - Lancaster TSMO 2025-2026 | 1063 | ITS | Intelligent Transportation System | PE | CRP | 2026-07-30 |  | 17435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17435
Lancaster | 8 | Lancaster | 121063 | New Holland Pk Signals - Lancaster TSMO 2025-2026 | 1063 | ITS | Intelligent Transportation System | PE | CRPU | 2026-07-30 |  | 28845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28845
Lancaster | 8 | Lancaster | 121063 | New Holland Pk Signals - Lancaster TSMO 2025-2026 | 1063 | ITS | Intelligent Transportation System | FD | CRP | 2026-07-30 |  | 16764 | 2665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19429
Lancaster | 8 | Lancaster | 121063 | New Holland Pk Signals - Lancaster TSMO 2025-2026 | 1063 | ITS | Intelligent Transportation System | FD | CRPU | 2026-07-30 |  | 18236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18236
Lancaster | 8 | Lancaster | 121063 | New Holland Pk Signals - Lancaster TSMO 2025-2026 | 1063 | ITS | Intelligent Transportation System | CON | CRP | 2026-07-30 |  | 0 | 98797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98797
Lancaster | 8 | Lancaster | 121063 | New Holland Pk Signals - Lancaster TSMO 2025-2026 | 1063 | ITS | Intelligent Transportation System | CON | CRP | 2026-07-30 |  | 0 | 24715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24715
Lancaster | 8 | Lancaster | 121064 | UPS for Existing Sites - Lancaster TSMO 2025-2026 | 300 | ITS | Intelligent Transportation System | PE | CRP | 2026-07-30 |  | 15540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15540
Lancaster | 8 | Lancaster | 121064 | UPS for Existing Sites - Lancaster TSMO 2025-2026 | 300 | ITS | Intelligent Transportation System | PE | CRPU | 2026-07-30 |  | 30740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30740
Lancaster | 8 | Lancaster | 121064 | UPS for Existing Sites - Lancaster TSMO 2025-2026 | 300 | ITS | Intelligent Transportation System | FD | CRP | 2026-07-30 |  | 35000 | 2665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37665
Lancaster | 8 | Lancaster | 121064 | UPS for Existing Sites - Lancaster TSMO 2025-2026 | 300 | ITS | Intelligent Transportation System | CON | CRP | 2026-07-30 |  | 0 | 88420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88420
Lancaster | 8 | Lancaster | 121064 | UPS for Existing Sites - Lancaster TSMO 2025-2026 | 300 | ITS | Intelligent Transportation System | CON | CRP | 2026-07-30 |  | 0 | 135580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135580
Lancaster | 8 | Lancaster | 121478 | Bitzers Mill Covered Bridge | 1013 | 022 | Bridge Restoration | PE | BOF | 2027-01-01 |  | 170130 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190130
Lancaster | 8 | Lancaster | 121478 | Bitzers Mill Covered Bridge | 1013 | 022 | Bridge Restoration | FD | BOF | 2027-01-01 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Lancaster | 8 | Lancaster | 121478 | Bitzers Mill Covered Bridge | 1013 | 022 | Bridge Restoration | CON | BOF | 2027-01-01 |  | 0 | 0 | 0 | 70728 | 1000000 | 579272 | 0 | 0 | 0 | 1650000
Lancaster | 8 | Lancaster | 121533 | Lancaster City Paving |  |  | Highway Restoration | CON | STP | 2026-07-30 |  | 2466622 | 1533378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
Lancaster | 8 | Lancaster | 121544 | Water Street Bike Boulevard- TASA |  | TAP | Bicycle and Pedestrian Facilities Transit | CON | TAP | 2026-09-03 |  | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
Lancaster | 8 | Lancaster | 122220 | Lancaster -District 8-0 Asset Management- Paving | 10 | 0 | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32659000 | 32659000
Lancaster | 8 | Lancaster | 122290 | Norman Wood Deck Repairs | 372 | 025 | Bridge Restoration | PE | 185 |  |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Lancaster | 8 | Lancaster | 122392 | PA 23 Resurfacing | 23 | 045 | Highway Restoration | PE | STP |  |  | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Lancaster | 8 | Lancaster | 122392 | PA 23 Resurfacing | 23 | 045 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 3000000 | 6000000 | 0 | 0 | 0 | 0 | 9000000
Lancaster | 8 | Lancaster | 122402 | Train Station and Pikes Study | 4011 | SDY | Study Phase of Project | STUDY | 581 |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
Lancaster | 8 | Lancaster | 122634 | Lititz Pk/Oregon Pk Resurfacing | 222 | 087 | Highway Restoration | PE | STP | 2026-09-17 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Lancaster | 8 | Lancaster | 122634 | Lititz Pk/Oregon Pk Resurfacing | 222 | 087 | Highway Restoration | CON | NHPP | 2026-09-17 |  | 0 | 1762850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1762850
Lancaster | 8 | Lancaster | 122634 | Lititz Pk/Oregon Pk Resurfacing | 222 | 087 | Highway Restoration | CON | STP | 2026-09-17 |  | 2237150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2237150
Lancaster | 8 | Lancaster | 122780 | SCTA Bus Purchase |  |  | Public Transit | CON | CAQ |  |  | 2000000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000
Lancaster | 8 | Lancaster | 122989 | Lancaster County Department Force Box Culvert | 322 | BRG | Bridge Replacement | PE | 185 |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Lancaster | 8 | Lancaster | 123107 | Lancaster Co Systemic Intersection Imp | 72 | 074 | Safety Improvement | PE | STP | 2026-09-17 |  | 50000 | 156083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206083
Lancaster | 8 | Lancaster | 123107 | Lancaster Co Systemic Intersection Imp | 72 | 074 | Safety Improvement | CON | STP | 2026-09-17 |  | 1069654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1069654
Lancaster | 8 | Lancaster | 123108 | Lancaster Co Systemic Lane Departure Imp | 10 | 004 | Safety Improvement | PE | STP | 2026-09-17 |  | 50000 | 156083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206083
Lancaster | 8 | Lancaster | 123108 | Lancaster Co Systemic Lane Departure Imp | 10 | 004 | Safety Improvement | CON | STP | 2026-09-17 |  | 1171813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1171813
Lebanon | 8 | Lebanon | 20217 | N Lincoln Ave Leb-5 | 7301 | BRG | Bridge Replacement | CON | BOF | 2026-07-16 |  | 0 | 932234 | 379039 | 0 | 0 | 0 | 0 | 0 | 0 | 1311273
Lebanon | 8 | Lebanon | 20217 | N Lincoln Ave Leb-5 | 7301 | BRG | Bridge Replacement | CON | 183 | 2026-07-16 |  | 0 | 174794 | 71070 | 0 | 0 | 0 | 0 | 0 | 0 | 245864
Lebanon | 8 | Lebanon | 20217 | N Lincoln Ave Leb-5 | 7301 | BRG | Bridge Replacement | CON | LOC | 2026-07-16 |  | 0 | 58264 | 23690 | 0 | 0 | 0 | 0 | 0 | 0 | 81954
Lebanon | 8 | Lebanon | 20299 | Levan's Iron Bridge CO-5 | 7214 | BRG | Bridge Replacement | PE | BOF | 2028-11-09 |  | 0 | 384000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384000
Lebanon | 8 | Lebanon | 20299 | Levan's Iron Bridge CO-5 | 7214 | BRG | Bridge Replacement | PE | 183 | 2028-11-09 |  | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000
Lebanon | 8 | Lebanon | 20299 | Levan's Iron Bridge CO-5 | 7214 | BRG | Bridge Replacement | PE | LOC | 2028-11-09 |  | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000
Lebanon | 8 | Lebanon | 20299 | Levan's Iron Bridge CO-5 | 7214 | BRG | Bridge Replacement | FD | BRIP | 2028-11-09 |  | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 280000
Lebanon | 8 | Lebanon | 20299 | Levan's Iron Bridge CO-5 | 7214 | BRG | Bridge Replacement | FD | 183 | 2028-11-09 |  | 0 | 0 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 52500
Lebanon | 8 | Lebanon | 20299 | Levan's Iron Bridge CO-5 | 7214 | BRG | Bridge Replacement | FD | LOC | 2028-11-09 |  | 0 | 0 | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 17500
Lebanon | 8 | Lebanon | 20299 | Levan's Iron Bridge CO-5 | 7214 | BRG | Bridge Replacement | CON | BOF | 2028-11-09 |  | 0 | 0 | 436600 | 0 | 0 | 1088656 | 0 | 0 | 0 | 1525256
Lebanon | 8 | Lebanon | 20299 | Levan's Iron Bridge CO-5 | 7214 | BRG | Bridge Replacement | CON | BRIP | 2028-11-09 |  | 0 | 0 | 0 | 175509 | 222436 | 0 | 0 | 0 | 0 | 397945
Lebanon | 8 | Lebanon | 20299 | Levan's Iron Bridge CO-5 | 7214 | BRG | Bridge Replacement | CON | 183 | 2028-11-09 |  | 0 | 0 | 81863 | 32908 | 41707 | 204123 | 0 | 0 | 0 | 360601
Lebanon | 8 | Lebanon | 20364 | Yordys Bridge Road CO-22 | 7207 | BRG | Bridge Restoration | PE | BOF | 2028-12-14 |  | 576000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 576000
Lebanon | 8 | Lebanon | 20364 | Yordys Bridge Road CO-22 | 7207 | BRG | Bridge Restoration | PE | 183 | 2028-12-14 |  | 108000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108000
Lebanon | 8 | Lebanon | 20364 | Yordys Bridge Road CO-22 | 7207 | BRG | Bridge Restoration | PE | LOC | 2028-12-14 |  | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000
Lebanon | 8 | Lebanon | 20364 | Yordys Bridge Road CO-22 | 7207 | BRG | Bridge Restoration | FD | BOF | 2028-12-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 0 | 0 | 280000
Lebanon | 8 | Lebanon | 20364 | Yordys Bridge Road CO-22 | 7207 | BRG | Bridge Restoration | FD | 183 | 2028-12-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 52500 | 0 | 0 | 52500
Lebanon | 8 | Lebanon | 20364 | Yordys Bridge Road CO-22 | 7207 | BRG | Bridge Restoration | FD | LOC | 2028-12-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 17500 | 0 | 0 | 17500
Lebanon | 8 | Lebanon | 20364 | Yordys Bridge Road CO-22 | 7207 | BRG | Bridge Restoration | CON | BOF | 2028-12-14 |  | 0 | 0 | 0 | 0 | 709000 | 134137 | 0 | 0 | 0 | 843137
Lebanon | 8 | Lebanon | 20364 | Yordys Bridge Road CO-22 | 7207 | BRG | Bridge Restoration | CON | BRIP | 2028-12-14 |  | 0 | 0 | 0 | 0 | 237000 | 1315863 | 0 | 0 | 0 | 1552863
Lebanon | 8 | Lebanon | 20364 | Yordys Bridge Road CO-22 | 7207 | BRG | Bridge Restoration | CON | STP | 2028-12-14 |  | 0 | 0 | 0 | 340248 | 0 | 1036000 | 0 | 0 | 0 | 1376248
Lebanon | 8 | Lebanon | 20364 | Yordys Bridge Road CO-22 | 7207 | BRG | Bridge Restoration | CON | 183 | 2028-12-14 |  | 0 | 0 | 0 | 63796 | 177375 | 466125 | 0 | 0 | 0 | 707296
Lebanon | 8 | Lebanon | 78751 | SR 117 Over Conewago Crk | 117 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lebanon | 8 | Lebanon | 82375 | SRTP Rideshare Program |  | RSP | Reserve Line Item | PE | CAQ |  |  | 0 | 98655 | 98164 | 99145 | 0 | 0 | 0 | 0 | 0 | 295964
Lebanon | 8 | Lebanon | 87477 | East Main Street Bridge | 1020 | 009 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117000 | 0 | 117000
Lebanon | 8 | Lebanon | 87477 | East Main Street Bridge | 1020 | 009 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 832064 | 832064
Lebanon | 8 | Lebanon | 87835 | Bridge Reserve |  |  | Reserve Line Item | CON | BOF |  |  | 510000 | 61378 | 2000 | 1 | 0 | 173207 | 1116000 | 1396000 | 4998014 | 8256600
Lebanon | 8 | Lebanon | 87835 | Bridge Reserve |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 210000 | 47472 | 431963 | 0 | 1307000 | 2024000 | 936138 | 394586 | 5351159
Lebanon | 8 | Lebanon | 87835 | Bridge Reserve |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 113411 | 95000 | 0 | 1004062 | 400752 | 574926 | 804000 | 94921 | 3087072
Lebanon | 8 | Lebanon | 87838 | Highway Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 213447 | 0 | 0 | 0 | 103501 | 374000 | 1598000 | 5362517 | 7651465
Lebanon | 8 | Lebanon | 87838 | Highway Reserve |  |  | Reserve Line Item | CON | STP |  |  | 0 | 568781 | 139207 | 0 | 0 | 256698 | 386000 | 764128 | 4215709 | 6330523
Lebanon | 8 | Lebanon | 87838 | Highway Reserve |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 152265 | 1878064 | 917303 | 2309126 | 2958000 | 1665000 | 1619162 | 17456000 | 28954920
Lebanon | 8 | Lebanon | 87841 | CMAQ Line Item |  |  | Reserve Line Item | CON | CAQ |  |  | 1306415 | 1363345 | 1363836 | 1362855 | 1462000 | 1462000 | 1135000 | 1462000 | 3241588 | 14159039
Lebanon | 8 | Lebanon | 87842 | Delivery/Consult Assist |  |  | Reserve Line Item | PE | 185 |  |  | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
Lebanon | 8 | Lebanon | 87842 | Delivery/Consult Assist |  |  | Reserve Line Item | PE | 581 |  |  | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Lebanon | 8 | Lebanon | 87842 | Delivery/Consult Assist |  |  | Reserve Line Item | CON | 581 |  |  | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Lebanon | 8 | Lebanon | 87847 | HSIP Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 267000 | 0 | 0 | 0 | 0 | 1357000 | 1357000 | 5427000 | 8408000
Lebanon | 8 | Lebanon | 88057 | STU (HATS) |  |  | Reserve Line Item | CON | STU |  |  | 0 | 152144 | 0 | 59288 | 0 | 0 | 0 | 0 | 0 | 211432
Lebanon | 8 | Lebanon | 90340 | Ebenezer Road Bridge | 72 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lebanon | 8 | Lebanon | 90340 | Ebenezer Road Bridge | 72 | 0 | Bridge Preservation - Federal | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1173972 | 1173972
Lebanon | 8 | Lebanon | 91346 | PA 501 Bridge-B | 501 | 029 | Bridge Replacement | CON | BRIP | 2025-04-10 | 2025-04-10 | 930890 | 1251000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2181890
Lebanon | 8 | Lebanon | 91346 | PA 501 Bridge-B | 501 | 029 | Bridge Replacement | CON | STP | 2025-04-10 | 2025-04-10 | 0 | 159818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159818
Lebanon | 8 | Lebanon | 91346 | PA 501 Bridge-B | 501 | 029 | Bridge Replacement | CON | 185 | 2025-04-10 | 2025-04-10 | 208700 | 270477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479177
Lebanon | 8 | Lebanon | 91351 | Pleasant View Rd over Trib to Raccoon Ck | 4013 | 018 | Bridge Restoration | PE | BOF | 2027-01-14 |  | 0 | 18388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18388
Lebanon | 8 | Lebanon | 91351 | Pleasant View Rd over Trib to Raccoon Ck | 4013 | 018 | Bridge Restoration | FD | BOF | 2027-01-14 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Lebanon | 8 | Lebanon | 91351 | Pleasant View Rd over Trib to Raccoon Ck | 4013 | 018 | Bridge Restoration | ROW | BOF | 2027-01-14 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Lebanon | 8 | Lebanon | 91351 | Pleasant View Rd over Trib to Raccoon Ck | 4013 | 018 | Bridge Restoration | UTL | BOF | 2027-01-14 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Lebanon | 8 | Lebanon | 91351 | Pleasant View Rd over Trib to Raccoon Ck | 4013 | 018 | Bridge Restoration | CON | 185 | 2027-01-14 |  | 0 | 0 | 0 | 330488 | 0 | 0 | 0 | 0 | 0 | 330488
Lebanon | 8 | Lebanon | 91351 | Pleasant View Rd over Trib to Raccoon Ck | 4013 | 018 | Bridge Restoration | CON | 581 | 2027-01-14 |  | 0 | 0 | 463512 | 400000 | 0 | 0 | 0 | 0 | 0 | 863512
Lebanon | 8 | Lebanon | 97153 | Lingle Avenue Reconstruct | 3017 | 032 | Highway Reconstruction | FD | STP | 2027-07-29 |  | 0 | 645000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 645000
Lebanon | 8 | Lebanon | 97153 | Lingle Avenue Reconstruct | 3017 | 032 | Highway Reconstruction | FD | STU | 2027-07-29 |  | 0 | 355000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355000
Lebanon | 8 | Lebanon | 97153 | Lingle Avenue Reconstruct | 3017 | 032 | Highway Reconstruction | ROW | STU | 2027-07-29 |  | 0 | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
Lebanon | 8 | Lebanon | 97153 | Lingle Avenue Reconstruct | 3017 | 032 | Highway Reconstruction | UTL | STU | 2027-07-29 |  | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 180000
Lebanon | 8 | Lebanon | 97153 | Lingle Avenue Reconstruct | 3017 | 032 | Highway Reconstruction | CON | STP | 2027-07-29 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 1500000 | 1271872 | 0 | 3171872
Lebanon | 8 | Lebanon | 97153 | Lingle Avenue Reconstruct | 3017 | 032 | Highway Reconstruction | CON | 581 | 2027-07-29 |  | 0 | 0 | 0 | 1153396 | 1441704 | 0 | 0 | 0 | 0 | 2595100
Lebanon | 8 | Lebanon | 97161 | Cornwall Traffic Signals | 2001 | 0 | Safety Improvement | PE | CAQ |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 327000 | 0 | 0 | 327000
Lebanon | 8 | Lebanon | 97161 | Cornwall Traffic Signals | 2001 | 0 | Safety Improvement | CON | CAQ |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2604412 | 2604412
Lebanon | 8 | Lebanon | 100264 | Harrison Road over I-81 | 4017 | 006 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Lebanon | 8 | Lebanon | 100264 | Harrison Road over I-81 | 4017 | 006 | Bridge Preservation - Federal | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586986 | 586986
Lebanon | 8 | Lebanon | 100264 | Harrison Road over I-81 | 4017 | 006 | Bridge Preservation - Federal | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586986 | 586986
Lebanon | 8 | Lebanon | 100279 | Weavertown Road over NS | 2011 | 016 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 293574 | 0 | 0 | 293574
Lebanon | 8 | Lebanon | 100279 | Weavertown Road over NS | 2011 | 016 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 955014 | 955014
Lebanon | 8 | Lebanon | 100283 | Millbach Road ov Mill Cr | 2017 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
Lebanon | 8 | Lebanon | 100283 | Millbach Road ov Mill Cr | 2017 | 0 | Bridge Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812750 | 812750
Lebanon | 8 | Lebanon | 100291 | Horseshoe Pike ov Beck Cr | 322 | 0 | Bridge Preservation - Federal | PE | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lebanon | 8 | Lebanon | 100294 | SR 4005/Trib Swatara Cr | 4005 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Lebanon | 8 | Lebanon | 100302 | Harrison Rd ovr Spring Cr | 4008 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
Lebanon | 8 | Lebanon | 100302 | Harrison Rd ovr Spring Cr | 4008 | 0 | Bridge Preservation - Federal | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1083667 | 1083667
Lebanon | 8 | Lebanon | 100305 | Cumberland St Bridge 2 | 422 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lebanon | 8 | Lebanon | 100309 | Jonestown Rd/Raccoon Cr | 4013 | 0 | Bridge Preservation - Federal | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
Lebanon | 8 | Lebanon | 100309 | Jonestown Rd/Raccoon Cr | 4013 | 0 | Bridge Preservation - Federal | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1354583 | 1354583
Lebanon | 8 | Lebanon | 100311 | Lawn Rd over Conewago Crk | 3007 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Lebanon | 8 | Lebanon | 100312 | Sheridan Rd over Mill Cr | 2019 | 023 | Bridge Restoration | PE | BRIP | 2027-08-26 |  | 129000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129000
Lebanon | 8 | Lebanon | 100312 | Sheridan Rd over Mill Cr | 2019 | 023 | Bridge Restoration | PE | STP | 2027-08-26 |  | 309825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309825
Lebanon | 8 | Lebanon | 100312 | Sheridan Rd over Mill Cr | 2019 | 023 | Bridge Restoration | FD | BRIP | 2027-08-26 |  | 301110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301110
Lebanon | 8 | Lebanon | 100312 | Sheridan Rd over Mill Cr | 2019 | 023 | Bridge Restoration | FD | STP | 2027-08-26 |  | 0 | 8890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8890
Lebanon | 8 | Lebanon | 100312 | Sheridan Rd over Mill Cr | 2019 | 023 | Bridge Restoration | ROW | STP | 2027-08-26 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Lebanon | 8 | Lebanon | 100312 | Sheridan Rd over Mill Cr | 2019 | 023 | Bridge Restoration | UTL | STP | 2027-08-26 |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Lebanon | 8 | Lebanon | 100312 | Sheridan Rd over Mill Cr | 2019 | 023 | Bridge Restoration | CON | BRIP | 2027-08-26 |  | 0 | 0 | 753528 | 753528 | 0 | 0 | 0 | 0 | 0 | 1507056
Lebanon | 8 | Lebanon | 100317 | Lincoln Avenue Bridge | 422 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
Lebanon | 8 | Lebanon | 100327 | Fisher Ave over Forge Ck | 4020 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Lebanon | 8 | Lebanon | 100328 | Golf Rd over Little Swatara Ck | 7201 | BRG | Bridge Restoration | FD | BRIP | 2028-06-29 |  | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 280000
Lebanon | 8 | Lebanon | 100328 | Golf Rd over Little Swatara Ck | 7201 | BRG | Bridge Restoration | FD | 183 | 2028-06-29 |  | 0 | 0 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 52500
Lebanon | 8 | Lebanon | 100328 | Golf Rd over Little Swatara Ck | 7201 | BRG | Bridge Restoration | FD | LOC | 2028-06-29 |  | 0 | 0 | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 17500
Lebanon | 8 | Lebanon | 100328 | Golf Rd over Little Swatara Ck | 7201 | BRG | Bridge Restoration | CON | BOF | 2028-06-29 |  | 0 | 0 | 578361 | 1395999 | 687000 | 0 | 0 | 0 | 0 | 2661360
Lebanon | 8 | Lebanon | 100328 | Golf Rd over Little Swatara Ck | 7201 | BRG | Bridge Restoration | CON | BRIP | 2028-06-29 |  | 0 | 0 | 0 | 0 | 901564 | 0 | 0 | 0 | 0 | 901564
Lebanon | 8 | Lebanon | 100328 | Golf Rd over Little Swatara Ck | 7201 | BRG | Bridge Restoration | CON | STP | 2028-06-29 |  | 0 | 0 | 108639 | 0 | 0 | 0 | 0 | 0 | 0 | 108639
Lebanon | 8 | Lebanon | 100328 | Golf Rd over Little Swatara Ck | 7201 | BRG | Bridge Restoration | CON | 183 | 2028-06-29 |  | 0 | 0 | 128812 | 261750 | 297856 | 0 | 0 | 0 | 0 | 688418
Lebanon | 8 | Lebanon | 100331 | Ebenezer Rd/Swatara Cr | 72 | 060 | Bridge Replacement | CON | NHPP | 2023-08-24 | 2023-08-24 | 1439648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439648
Lebanon | 8 | Lebanon | 100331 | Ebenezer Rd/Swatara Cr | 72 | 060 | Bridge Replacement | CON | 185 | 2023-08-24 | 2023-08-24 | 359912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359912
Lebanon | 8 | Lebanon | 100333 | Allentown Blvd/Fisher Ave | 22 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
Lebanon | 8 | Lebanon | 100333 | Allentown Blvd/Fisher Ave | 22 | 0 | Bridge Preservation - Federal | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1029483 | 1029483
Lebanon | 8 | Lebanon | 100343 | Allentown Blvd/Trib Racc | 22 | 099 | Bridge Restoration | CON | 185 | 2024-05-09 | 2024-05-09 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Lebanon | 8 | Lebanon | 100347 | Cornwall Rd ovr Snitz Ck | 2001 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Lebanon | 8 | Lebanon | 100347 | Cornwall Rd ovr Snitz Ck | 2001 | 0 | Bridge Preservation - Federal | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1114278 | 1114278
Lebanon | 8 | Lebanon | 100349 | US 22 over Reeds Ck Brdg | 22 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
Lebanon | 8 | Lebanon | 100349 | US 22 over Reeds Ck Brdg | 22 | 0 | Bridge Preservation - Federal | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424862 | 3909805 | 4334667
Lebanon | 8 | Lebanon | 100350 | Pine Grove St over Elizabeth Run | 343 | 005 | Bridge Preservation - Federal | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1140609 | 1140609
Lebanon | 8 | Lebanon | 100351 | Ebenezer Rd over Forge Ck | 72 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
Lebanon | 8 | Lebanon | 100351 | Ebenezer Rd over Forge Ck | 72 | 0 | Bridge Preservation - Federal | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 903056 | 903056
Lebanon | 8 | Lebanon | 100352 | Beach Run Bridge | 1007 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
Lebanon | 8 | Lebanon | 100353 | Greble Road Bridge | 1014 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Lebanon | 8 | Lebanon | 105343 | US 422 Cumberland St Resurfacing | 422 | 044 | Highway Restoration | CON | NHPP | 2028-01-27 |  | 0 | 0 | 1519000 | 1598000 | 0 | 0 | 0 | 0 | 0 | 3117000
Lebanon | 8 | Lebanon | 105343 | US 422 Cumberland St Resurfacing | 422 | 044 | Highway Restoration | CON | 581 | 2028-01-27 |  | 0 | 0 | 624782 | 786913 | 0 | 0 | 0 | 0 | 0 | 1411695
Lebanon | 8 | Lebanon | 105802 | College St over Trib to Owl Cr | 501 | 035 | Bridge Replacement | PE | 185 | 2027-08-26 |  | 413476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413476
Lebanon | 8 | Lebanon | 105802 | College St over Trib to Owl Cr | 501 | 035 | Bridge Replacement | FD | 185 | 2027-08-26 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Lebanon | 8 | Lebanon | 105802 | College St over Trib to Owl Cr | 501 | 035 | Bridge Replacement | ROW | 581 | 2027-08-26 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Lebanon | 8 | Lebanon | 105802 | College St over Trib to Owl Cr | 501 | 035 | Bridge Replacement | UTL | 581 | 2027-08-26 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Lebanon | 8 | Lebanon | 105802 | College St over Trib to Owl Cr | 501 | 035 | Bridge Replacement | CON | 185 | 2027-08-26 |  | 0 | 0 | 990255 | 82058 | 0 | 0 | 0 | 0 | 0 | 1072313
Lebanon | 8 | Lebanon | 105802 | College St over Trib to Owl Cr | 501 | 035 | Bridge Replacement | CON | 581 | 2027-08-26 |  | 0 | 0 | 0 | 178859 | 0 | 0 | 0 | 0 | 0 | 178859
Lebanon | 8 | Lebanon | 106537 | PA72/Isabel Drive Improvements | 72 | 062 | Safety Improvement | CON | CAQ | 2023-11-02 | 2023-11-02 | 22471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22471
Lebanon | 8 | Lebanon | 111910 | Lebanon City Resurfacing Phase 4 - Cumberland St |  | RSF | Highway Restoration | CON | NHPP | 2024-04-11 | 2024-04-11 | 27950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27950
Lebanon | 8 | Lebanon | 113295 | Fisher Ave & I-81 SR 8008 Ramps Resurfacing | 4020 | 003 | Highway Restoration | CON | STP | 2023-11-02 | 2023-11-02 | 25550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25550
Lebanon | 8 | Lebanon | 113297 | PA 72 Quentin Rd Resurface | 72 | 066 | Highway Restoration | PE | 581 | 2025-10-09 | 2025-10-09 | 175981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175981
Lebanon | 8 | Lebanon | 113297 | PA 72 Quentin Rd Resurface | 72 | 066 | Highway Restoration | CON | NHPP | 2025-10-09 | 2025-10-09 | 292402 | 989626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1282028
Lebanon | 8 | Lebanon | 113297 | PA 72 Quentin Rd Resurface | 72 | 066 | Highway Restoration | CON | STP | 2025-10-09 | 2025-10-09 | 1568825 | 945972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2514797
Lebanon | 8 | Lebanon | 113297 | PA 72 Quentin Rd Resurface | 72 | 066 | Highway Restoration | CON | 581 | 2025-10-09 | 2025-10-09 | 2052829 | 1611997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3664826
Lebanon | 8 | Lebanon | 113297 | PA 72 Quentin Rd Resurface | 72 | 066 | Highway Restoration | CON | LOC | 2025-10-09 | 2025-10-09 | 64385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64385
Lebanon | 8 | Lebanon | 113316 | PA 443 Old State Rd Resurface | 443 | 014 | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1369000 | 2662000 | 2707838 | 0 | 6738838
Lebanon | 8 | Lebanon | 114554 | Hill Church Rd Safety Imp | 4004 | 015 | Safety Improvement | PE | HSIP | 2026-12-03 |  | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000
Lebanon | 8 | Lebanon | 114554 | Hill Church Rd Safety Imp | 4004 | 015 | Safety Improvement | FD | HSIP | 2026-12-03 |  | 27170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27170
Lebanon | 8 | Lebanon | 114554 | Hill Church Rd Safety Imp | 4004 | 015 | Safety Improvement | FD | STU | 2026-12-03 |  | 185173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185173
Lebanon | 8 | Lebanon | 114554 | Hill Church Rd Safety Imp | 4004 | 015 | Safety Improvement | ROW | STP | 2026-12-03 |  | 363800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363800
Lebanon | 8 | Lebanon | 114554 | Hill Church Rd Safety Imp | 4004 | 015 | Safety Improvement | ROW | STU | 2026-12-03 |  | 312027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312027
Lebanon | 8 | Lebanon | 114554 | Hill Church Rd Safety Imp | 4004 | 015 | Safety Improvement | UTL | HSIP | 2026-12-03 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Lebanon | 8 | Lebanon | 114554 | Hill Church Rd Safety Imp | 4004 | 015 | Safety Improvement | CON | STP | 2026-12-03 |  | 0 | 0 | 1189154 | 604305 | 0 | 0 | 0 | 0 | 0 | 1793459
Lebanon | 8 | Lebanon | 114554 | Hill Church Rd Safety Imp | 4004 | 015 | Safety Improvement | CON | 581 | 2026-12-03 |  | 0 | 0 | 0 | 576171 | 576170 | 0 | 0 | 0 | 0 | 1152341
Lebanon | 8 | Lebanon | 116163 | PA 343 Seventh Street Improvements | 343 | 006 | Safety Improvement | PE | HSIP | 2028-03-23 |  | 0 | 160714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160714
Lebanon | 8 | Lebanon | 116163 | PA 343 Seventh Street Improvements | 343 | 006 | Safety Improvement | FD | HSIP | 2028-03-23 |  | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
Lebanon | 8 | Lebanon | 116163 | PA 343 Seventh Street Improvements | 343 | 006 | Safety Improvement | ROW | HSIP | 2028-03-23 |  | 0 | 89286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89286
Lebanon | 8 | Lebanon | 116163 | PA 343 Seventh Street Improvements | 343 | 006 | Safety Improvement | ROW | STP | 2028-03-23 |  | 0 | 160714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160714
Lebanon | 8 | Lebanon | 116163 | PA 343 Seventh Street Improvements | 343 | 006 | Safety Improvement | UTL | HSIP | 2028-03-23 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Lebanon | 8 | Lebanon | 116163 | PA 343 Seventh Street Improvements | 343 | 006 | Safety Improvement | CON | HSIP | 2028-03-23 |  | 0 | 0 | 600000 | 0 | 710763 | 1357000 | 0 | 0 | 0 | 2667763
Lebanon | 8 | Lebanon | 116163 | PA 343 Seventh Street Improvements | 343 | 006 | Safety Improvement | CON | STP | 2028-03-23 |  | 0 | 0 | 0 | 627335 | 376465 | 0 | 0 | 0 | 0 | 1003800
Lebanon | 8 | Lebanon | 116164 | US 422 Cumberland St and Prescott Rd Int | 422 | 045 | Safety Improvement | PE | HSIP | 2028-01-27 |  | 0 | 57643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57643
Lebanon | 8 | Lebanon | 116164 | US 422 Cumberland St and Prescott Rd Int | 422 | 045 | Safety Improvement | FD | HSIP | 2028-01-27 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Lebanon | 8 | Lebanon | 116164 | US 422 Cumberland St and Prescott Rd Int | 422 | 045 | Safety Improvement | ROW | HSIP | 2028-01-27 |  | 260000 | 407537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 667537
Lebanon | 8 | Lebanon | 116164 | US 422 Cumberland St and Prescott Rd Int | 422 | 045 | Safety Improvement | ROW | STP | 2028-01-27 |  | 0 | 57463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57463
Lebanon | 8 | Lebanon | 116164 | US 422 Cumberland St and Prescott Rd Int | 422 | 045 | Safety Improvement | UTL | HSIP | 2028-01-27 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Lebanon | 8 | Lebanon | 116164 | US 422 Cumberland St and Prescott Rd Int | 422 | 045 | Safety Improvement | CON | HSIP | 2028-01-27 |  | 0 | 0 | 357000 | 557000 | 646237 | 0 | 0 | 0 | 0 | 1560237
Lebanon | 8 | Lebanon | 116164 | US 422 Cumberland St and Prescott Rd Int | 422 | 045 | Safety Improvement | CON | STP | 2028-01-27 |  | 0 | 0 | 0 | 464112 | 821454 | 0 | 0 | 0 | 0 | 1285566
Lebanon | 8 | Lebanon | 116164 | US 422 Cumberland St and Prescott Rd Int | 422 | 045 | Safety Improvement | CON | STU | 2028-01-27 |  | 0 | 0 | 152144 | 447856 | 0 | 0 | 0 | 0 | 0 | 600000
Lebanon | 8 | Lebanon | 117410 | Gravel Hill Rd ovr Trib to Swatara Ck | 4011 | 029 | Bridge Restoration | PE | 185 | 2027-01-14 |  | 0 | 118382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118382
Lebanon | 8 | Lebanon | 117410 | Gravel Hill Rd ovr Trib to Swatara Ck | 4011 | 029 | Bridge Restoration | FD | 185 | 2027-01-14 |  | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Lebanon | 8 | Lebanon | 117410 | Gravel Hill Rd ovr Trib to Swatara Ck | 4011 | 029 | Bridge Restoration | ROW | 185 | 2027-01-14 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Lebanon | 8 | Lebanon | 117410 | Gravel Hill Rd ovr Trib to Swatara Ck | 4011 | 029 | Bridge Restoration | UTL | 185 | 2027-01-14 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Lebanon | 8 | Lebanon | 117410 | Gravel Hill Rd ovr Trib to Swatara Ck | 4011 | 029 | Bridge Restoration | CON | 581 | 2027-01-14 |  | 0 | 0 | 991642 | 314358 | 0 | 0 | 0 | 0 | 0 | 1306000
Lebanon | 8 | Lebanon | 117411 | US322 Horseshoe Pk ovr Killinger Crk | 322 | 066 | Bridge Preservation - Federal | FD | NHPP | 2026-12-10 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Lebanon | 8 | Lebanon | 117411 | US322 Horseshoe Pk ovr Killinger Crk | 322 | 066 | Bridge Preservation - Federal | ROW | NHPP | 2026-12-10 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Lebanon | 8 | Lebanon | 117411 | US322 Horseshoe Pk ovr Killinger Crk | 322 | 066 | Bridge Preservation - Federal | UTL | NHPP | 2026-12-10 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Lebanon | 8 | Lebanon | 117411 | US322 Horseshoe Pk ovr Killinger Crk | 322 | 066 | Bridge Preservation - Federal | CON | NHPP | 2026-12-10 |  | 0 | 556764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556764
Lebanon | 8 | Lebanon | 117412 | PA72 Ebenezer Rd over Trib to Swatara Crk | 72 | 067 | Bridge Preservation - Federal | PE | 185 | 2026-08-27 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Lebanon | 8 | Lebanon | 117412 | PA72 Ebenezer Rd over Trib to Swatara Crk | 72 | 067 | Bridge Preservation - Federal | FD | NHPP | 2026-08-27 |  | 167753 | 16163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183916
Lebanon | 8 | Lebanon | 117412 | PA72 Ebenezer Rd over Trib to Swatara Crk | 72 | 067 | Bridge Preservation - Federal | FD | 185 | 2026-08-27 |  | 41043 | 4936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45979
Lebanon | 8 | Lebanon | 117412 | PA72 Ebenezer Rd over Trib to Swatara Crk | 72 | 067 | Bridge Preservation - Federal | ROW | NHPP | 2026-08-27 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Lebanon | 8 | Lebanon | 117412 | PA72 Ebenezer Rd over Trib to Swatara Crk | 72 | 067 | Bridge Preservation - Federal | UTL | NHPP | 2026-08-27 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Lebanon | 8 | Lebanon | 117412 | PA72 Ebenezer Rd over Trib to Swatara Crk | 72 | 067 | Bridge Preservation - Federal | CON | NHPP | 2026-08-27 |  | 0 | 202000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202000
Lebanon | 8 | Lebanon | 117488 | US 422 Main Street over Quittapahilla Creek | 422 | 046 | Bridge Replacement | PE | BRIP | 2028-01-01 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Lebanon | 8 | Lebanon | 117488 | US 422 Main Street over Quittapahilla Creek | 422 | 046 | Bridge Replacement | PE | NHPP | 2028-01-01 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Lebanon | 8 | Lebanon | 117488 | US 422 Main Street over Quittapahilla Creek | 422 | 046 | Bridge Replacement | FD | NHPP | 2028-01-01 |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Lebanon | 8 | Lebanon | 117488 | US 422 Main Street over Quittapahilla Creek | 422 | 046 | Bridge Replacement | CON | NHPP | 2028-01-01 |  | 0 | 0 | 0 | 0 | 1598000 | 1494499 | 1224000 | 0 | 0 | 4316499
Lebanon | 8 | Lebanon | 117496 | PA 501 Stiegel Pk and Reistville Rd | 2004 | 011 | Safety Improvement | FD | HSIP | 2027-12-16 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Lebanon | 8 | Lebanon | 117496 | PA 501 Stiegel Pk and Reistville Rd | 2004 | 011 | Safety Improvement | ROW | STP | 2027-12-16 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Lebanon | 8 | Lebanon | 117496 | PA 501 Stiegel Pk and Reistville Rd | 2004 | 011 | Safety Improvement | UTL | STP | 2027-12-16 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Lebanon | 8 | Lebanon | 117496 | PA 501 Stiegel Pk and Reistville Rd | 2004 | 011 | Safety Improvement | CON | HSIP | 2027-12-16 |  | 0 | 0 | 400000 | 800000 | 0 | 0 | 0 | 0 | 0 | 1200000
Lebanon | 8 | Lebanon | 117496 | PA 501 Stiegel Pk and Reistville Rd | 2004 | 011 | Safety Improvement | CON | STP | 2027-12-16 |  | 0 | 0 | 0 | 0 | 838081 | 343302 | 0 | 0 | 0 | 1181383
Lebanon | 8 | Lebanon | 118308 | HIGH TENSION CABLE MEDIAN BARRIER | 81 | CMB | General Maintenance | CON | HSIP | 2023-05-11 | 2023-05-11 | 303693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303693
Lebanon | 8 | Lebanon | 118513 | LVRT Phase 6C | 3025 | LVT | New Bridge | CON | PRTCT | 2026-10-01 |  | 1250000 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
Lebanon | 8 | Lebanon | 118513 | LVRT Phase 6C | 3025 | LVT | New Bridge | CON | TAP | 2026-10-01 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Lebanon | 8 | Lebanon | 119212 | Lebanon MPO TIP Funded Bridge Repair Contract | 22 | BRC | Bridge Preservation - State Funded | PE | 185 | 2026-11-05 |  | 195869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195869
Lebanon | 8 | Lebanon | 119212 | Lebanon MPO TIP Funded Bridge Repair Contract | 22 | BRC | Bridge Preservation - State Funded | PE | 581 | 2026-11-05 |  | 187837 | 277055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464892
Lebanon | 8 | Lebanon | 119212 | Lebanon MPO TIP Funded Bridge Repair Contract | 22 | BRC | Bridge Preservation - State Funded | CON | 185 | 2026-11-05 |  | 0 | 0 | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 800000
Lebanon | 8 | Lebanon | 119254 | Orange St and Cornwall Rd Intersection |  |  | Safety Improvement | CON | STP | 2026-06-18 |  | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000
Lebanon | 8 | Lebanon | 119254 | Orange St and Cornwall Rd Intersection |  |  | Safety Improvement | CON | STP | 2026-06-18 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Lebanon | 8 | Lebanon | 119290 | Carbon Reduction Program (CRP) Lebanon MPO |  |  | Reserve Line Item | CON | CRP |  |  | 197960 | 391000 | 0 | 260000 | 441000 | 441000 | 441000 | 441000 | 1764000 | 4376960
Lebanon | 8 | Lebanon | 119290 | Carbon Reduction Program (CRP) Lebanon MPO |  |  | Reserve Line Item | CON | CRPU |  |  | 0 | 208000 | 0 | 208000 | 208000 | 208000 | 208000 | 208000 | 831000 | 2079000
Lebanon | 8 | Lebanon | 121394 | Ebenezer Road Resurfacing | 72 | 071 | 409 Expanded Maintenance | PE | 581 | 2026-06-04 |  | 88574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88574
Lebanon | 8 | Lebanon | 121520 | LVRT Phase 10B |  | TAP | Bicycle Pedestrian Highway | CON | TAP | 2027-05-13 |  | 0 | 0 | 2650000 | 0 | 0 | 0 | 0 | 0 | 0 | 2650000
Lebanon | 8 | Lebanon | 121523 | S Lincoln Avenue Pedestrian Safety |  | TAP | Bicycle Pedestrian Highway | CON | TAP | 2027-04-08 |  | 0 | 0 | 788710 | 0 | 0 | 0 | 0 | 0 | 0 | 788710
Lebanon | 8 | Lebanon | 121782 | SR 72 Summit Street & York Street Int. Impvts | 72 | 072 | Safety Improvement | PE | CRP | 2027-06-24 |  | 232040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232040
Lebanon | 8 | Lebanon | 121782 | SR 72 Summit Street & York Street Int. Impvts | 72 | 072 | Safety Improvement | PE | CRPU | 2027-06-24 |  | 204000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204000
Lebanon | 8 | Lebanon | 121782 | SR 72 Summit Street & York Street Int. Impvts | 72 | 072 | Safety Improvement | UTL | CRP | 2027-06-24 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Lebanon | 8 | Lebanon | 121782 | SR 72 Summit Street & York Street Int. Impvts | 72 | 072 | Safety Improvement | CON | CRP | 2027-06-24 |  | 0 | 0 | 441000 | 181000 | 0 | 0 | 0 | 0 | 0 | 622000
Lebanon | 8 | Lebanon | 121782 | SR 72 Summit Street & York Street Int. Impvts | 72 | 072 | Safety Improvement | CON | CRPU | 2027-06-24 |  | 0 | 0 | 208000 | 0 | 0 | 0 | 0 | 0 | 0 | 208000
Lebanon | 8 | Lebanon | 122841 | Lebanon County Department Force Box Culverts | 72 | BRG | Bridge Replacement | PE | 185 |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Lehigh Valley | 5 | Lehigh | 11390 | Hollenbachs Bridge | 4009 | 02B | Bridge Replacement | CON | BOF | 2026-06-18 |  | 0 | 1620016 | 719984 | 0 | 0 | 0 | 0 | 0 | 0 | 2340000
Lehigh Valley | 5 | Lehigh | 11406 | Front Street Bridge | 1015 | 01B | Bridge Replacement | PE | 185 | 2036-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260960 | 260960
Lehigh Valley | 5 | Lehigh | 11413 | Cementon Bridge | 329 | 01B | Bridge Replacement | CON | NHPP | 2023-01-12 | 2023-01-12 | 1728664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1728664
Lehigh Valley | 5 | Lehigh | 11413 | Cementon Bridge | 329 | 01B | Bridge Replacement | CON | 581 | 2023-01-12 | 2023-01-12 | 432166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432166
Lehigh Valley | 5 | Lehigh | 11587 | Vera Cruz Road over Branch of Hosensack Creek | 2027 | BC2 | Bridge Replacement | ROW | 185 | 2030-04-01 |  | 41950 | 41950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83900
Lehigh Valley | 5 | Lehigh | 11587 | Vera Cruz Road over Branch of Hosensack Creek | 2027 | BC2 | Bridge Replacement | UTL | 185 | 2030-04-01 |  | 0 | 5305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5305
Lehigh Valley | 5 | Lehigh | 11588 | Donats Peak Road Bridge over Kistler Creek | 4037 | 02B | Bridge Replacement | ROW | 185 | 2025-12-04 | 2025-12-04 | 39517 | 1083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40600
Lehigh Valley | 5 | Lehigh | 11588 | Donats Peak Road Bridge over Kistler Creek | 4037 | 02B | Bridge Replacement | CON | 185 | 2025-12-04 | 2025-12-04 | 0 | 1178130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1178130
Lehigh Valley | 5 | Lehigh | 57433 | Lehigh Race Street Intersection | 1004 | 03S | Safety Improvement | CON | STP | 2023-01-26 | 2023-01-26 | 0 | 361540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361540
Lehigh Valley | 5 | Lehigh | 57433 | Lehigh Race Street Intersection | 1004 | 03S | Safety Improvement | CON | 581 | 2023-01-26 | 2023-01-26 | 0 | 90385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90385
Lehigh Valley | 5 | Lehigh | 64729 | LVTS CMAQ-LANTA Flex |  |  | Public Transit | CON | CAQ |  |  | 2920000 | 480000 | 480000 | 480000 | 480000 | 1480000 | 480000 | 480000 | 1920000 | 9200000
Lehigh Valley | 5 | Lehigh | 64729 | LVTS CMAQ-LANTA Flex |  |  | Public Transit | CON | CRP |  |  | 366000 | 319000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685000
Lehigh Valley | 5 | Lehigh | 68190 | Freeway Service Patrol | 78 | FSP | Intelligent Transportation System | CON | NHPP | 2004-05-07 | 2004-07-28 | 410562 | 384752 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 1600000 | 4795314
Lehigh Valley | 5 | Lehigh | 79127 | Indian Creek Road over Leibert Creek | 2018 | 01B | Bridge Replacement | CON | 185 | 2025-03-27 | 2025-03-27 | 800000 | 803447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1603447
Lehigh Valley | 5 | Lehigh | 79131 | Breinigsville Road over Breinig Run | 3007 | BC2 | Bridge Replacement | ROW | 185 | 2030-04-01 |  | 38700 | 38700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77400
Lehigh Valley | 5 | Lehigh | 79131 | Breinigsville Road over Breinig Run | 3007 | BC2 | Bridge Replacement | UTL | 185 | 2030-04-01 |  | 0 | 5305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5305
Lehigh Valley | 5 | Lehigh | 80073 | LVTS In House Bridge Design Assistance |  | SBC | Bridge Replacement | PE | 185 |  |  | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 200000 | 550000
Lehigh Valley | 5 | Lehigh | 82804 | Corridor Signal Impr LI |  |  | Reserve Line Item | CON | CAQ |  |  | 0 | 0 | 159000 | 142470 | 534000 | 3056100 | 6534000 | 6534000 | 25616080 | 42575650
Lehigh Valley | 5 | Lehigh | 82806 | TAP Line Item |  |  | Reserve Line Item | CON | TAU |  |  | 0 | 0 | 1129738 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 5179000 | 12783738
Lehigh Valley | 5 | Lehigh | 82807 | Safety Line Item_LVTS |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 289363 | 881331 | 3483688 | 4796000 | 5236000 | 4796000 | 5236000 | 19182000 | 43900382
Lehigh Valley | 5 | Lehigh | 82810 | Urban/Carbon Reduction Program Line Item Reserve |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 0 | 93000 | 93000 | 593000 | 593000 | 593000 | 593000 | 2372000 | 4930000
Lehigh Valley | 5 | Lehigh | 82810 | Urban/Carbon Reduction Program Line Item Reserve |  |  | Reserve Line Item | CON | CRPU |  |  | 0 | 0 | 1326000 | 1626000 | 1626000 | 1626000 | 1626000 | 1626000 | 6505000 | 15961000
Lehigh Valley | 5 | Lehigh | 82810 | Urban/Carbon Reduction Program Line Item Reserve |  |  | Reserve Line Item | CON | STU |  |  | 0 | 31388 | 159064 | 21745 | 102908 | 3005560 | 9868000 | 4799040 | 55471000 | 73458705
Lehigh Valley | 5 | Lehigh | 83086 | Delivery_Consult Assist |  | DCA | Preventive Maintenance | PE | 581 |  |  | 2000000 | 750000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 4000000 | 12750000
Lehigh Valley | 5 | Lehigh | 85677 | SR143 over Trib to Ontelaunee Creek | 143 | BC2 | Bridge Preservation - State Funded | ROW | 185 | 2026-07-02 |  | 17800 | 17800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35600
Lehigh Valley | 5 | Lehigh | 85677 | SR143 over Trib to Ontelaunee Creek | 143 | BC2 | Bridge Preservation - State Funded | UTL | 185 | 2026-07-02 |  | 0 | 5305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5305
Lehigh Valley | 5 | Lehigh | 85689 | Church Road Newside over Trib to Mill Creek | 4014 | 01B | Bridge Replacement | CON | 581 | 2025-12-04 | 2025-12-04 | 784746 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 802346
Lehigh Valley | 5 | Lehigh | 89055 | Transp Alternative/Multimodal Project Mngmt |  | TEM | Transportation Enhancement | PE | STP |  |  | 162000 | 260000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 300000 | 1172000
Lehigh Valley | 5 | Lehigh | 92049 | Schantz Rd /trib Cedar Creek | 2015 | 01B | Bridge Replacement | PE | 185 | 2031-04-01 |  | 0 | 0 | 200000 | 237080 | 0 | 0 | 0 | 0 | 0 | 437080
Lehigh Valley | 5 | Lehigh | 92049 | Schantz Rd /trib Cedar Creek | 2015 | 01B | Bridge Replacement | FD | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 370976 | 0 | 0 | 0 | 0 | 370976
Lehigh Valley | 5 | Lehigh | 92049 | Schantz Rd /trib Cedar Creek | 2015 | 01B | Bridge Replacement | FD | 185 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 92744 | 0 | 0 | 0 | 0 | 92744
Lehigh Valley | 5 | Lehigh | 92049 | Schantz Rd /trib Cedar Creek | 2015 | 01B | Bridge Replacement | ROW | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 66872 | 0 | 0 | 0 | 66872
Lehigh Valley | 5 | Lehigh | 92049 | Schantz Rd /trib Cedar Creek | 2015 | 01B | Bridge Replacement | ROW | 185 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 16718 | 0 | 0 | 0 | 16718
Lehigh Valley | 5 | Lehigh | 92049 | Schantz Rd /trib Cedar Creek | 2015 | 01B | Bridge Replacement | UTL | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 196784 | 0 | 0 | 196784
Lehigh Valley | 5 | Lehigh | 92049 | Schantz Rd /trib Cedar Creek | 2015 | 01B | Bridge Replacement | UTL | 185 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 49196 | 0 | 0 | 49196
Lehigh Valley | 5 | Lehigh | 92049 | Schantz Rd /trib Cedar Creek | 2015 | 01B | Bridge Replacement | CON | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 885528 | 0 | 0 | 885528
Lehigh Valley | 5 | Lehigh | 92049 | Schantz Rd /trib Cedar Creek | 2015 | 01B | Bridge Replacement | CON | 185 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 221382 | 0 | 0 | 221382
Lehigh Valley | 5 | Lehigh | 93630 | Hill to Hill Bridge Rehabilitation | 378 | 03B | Bridge Restoration | UTL | 581 | 2026-08-13 |  | 750000 | 1250000 | 1000000 | 786280 | 0 | 0 | 0 | 0 | 0 | 3786280
Lehigh Valley | 5 | Lehigh | 93630 | Hill to Hill Bridge Rehabilitation | 378 | 03B | Bridge Restoration | CON | BOF | 2026-08-13 |  | 0 | 0 | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 3000000
Lehigh Valley | 5 | Lehigh | 93630 | Hill to Hill Bridge Rehabilitation | 378 | 03B | Bridge Restoration | CON | BRIP | 2026-08-13 |  | 1832400 | 5500000 | 2917600 | 0 | 5000000 | 0 | 0 | 0 | 0 | 15250000
Lehigh Valley | 5 | Lehigh | 93630 | Hill to Hill Bridge Rehabilitation | 378 | 03B | Bridge Restoration | CON | NHPP | 2026-08-13 |  | 4250000 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 6750000
Lehigh Valley | 5 | Lehigh | 93630 | Hill to Hill Bridge Rehabilitation | 378 | 03B | Bridge Restoration | CON | STU | 2026-08-13 |  | 1000000 | 1500000 | 9250000 | 11500000 | 11606000 | 0 | 0 | 0 | 0 | 34856000
Lehigh Valley | 5 | Lehigh | 93630 | Hill to Hill Bridge Rehabilitation | 378 | 03B | Bridge Restoration | CON | 581 | 2026-08-13 |  | 1770600 | 1750000 | 3041900 | 3500000 | 4151500 | 0 | 0 | 0 | 0 | 14214000
Lehigh Valley | 5 | Lehigh | 94249 | Limeport Pike ovr Saucon Crk trib | 2029 | 02B | Bridge Replacement | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521920 | 521920
Lehigh Valley | 5 | Lehigh | 94249 | Limeport Pike ovr Saucon Crk trib | 2029 | 02B | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130480 | 130480
Lehigh Valley | 5 | Lehigh | 94329 | Werleys Corner Road over Switzer Creek | 4019 | 02B | Bridge Replacement | PE | BOF | 2029-04-01 |  | 0 | 236558 | 331924 | 0 | 0 | 0 | 0 | 0 | 0 | 568482
Lehigh Valley | 5 | Lehigh | 94329 | Werleys Corner Road over Switzer Creek | 4019 | 02B | Bridge Replacement | FD | BOF | 2029-04-01 |  | 0 | 0 | 0 | 315140 | 0 | 0 | 0 | 0 | 0 | 315140
Lehigh Valley | 5 | Lehigh | 94329 | Werleys Corner Road over Switzer Creek | 4019 | 02B | Bridge Replacement | FD | 185 | 2029-04-01 |  | 0 | 0 | 0 | 78785 | 0 | 0 | 0 | 0 | 0 | 78785
Lehigh Valley | 5 | Lehigh | 94329 | Werleys Corner Road over Switzer Creek | 4019 | 02B | Bridge Replacement | ROW | BOF | 2029-04-01 |  | 0 | 0 | 0 | 22512 | 0 | 0 | 0 | 0 | 0 | 22512
Lehigh Valley | 5 | Lehigh | 94329 | Werleys Corner Road over Switzer Creek | 4019 | 02B | Bridge Replacement | ROW | 185 | 2029-04-01 |  | 0 | 0 | 0 | 5628 | 0 | 0 | 0 | 0 | 0 | 5628
Lehigh Valley | 5 | Lehigh | 94329 | Werleys Corner Road over Switzer Creek | 4019 | 02B | Bridge Replacement | UTL | BOF | 2029-04-01 |  | 0 | 0 | 0 | 0 | 23188 | 0 | 0 | 0 | 0 | 23188
Lehigh Valley | 5 | Lehigh | 94329 | Werleys Corner Road over Switzer Creek | 4019 | 02B | Bridge Replacement | UTL | 185 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 5797 | 0 | 0 | 0 | 0 | 5797
Lehigh Valley | 5 | Lehigh | 94329 | Werleys Corner Road over Switzer Creek | 4019 | 02B | Bridge Replacement | CON | BOF | 2029-04-01 |  | 0 | 0 | 0 | 0 | 1391160 | 0 | 0 | 0 | 0 | 1391160
Lehigh Valley | 5 | Lehigh | 94329 | Werleys Corner Road over Switzer Creek | 4019 | 02B | Bridge Replacement | CON | 185 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 347790 | 0 | 0 | 0 | 0 | 347790
Lehigh Valley | 5 | Lehigh | 94680 | South Walnut Street Bridge | 7408 | WSB | Bridge Replacement | ROW | BOF | 2025-04-10 | 2025-04-10 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000
Lehigh Valley | 5 | Lehigh | 94680 | South Walnut Street Bridge | 7408 | WSB | Bridge Replacement | ROW | 183 | 2025-04-10 | 2025-04-10 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
Lehigh Valley | 5 | Lehigh | 94680 | South Walnut Street Bridge | 7408 | WSB | Bridge Replacement | ROW | LOC | 2025-04-10 | 2025-04-10 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Lehigh Valley | 5 | Lehigh | 94680 | South Walnut Street Bridge | 7408 | WSB | Bridge Replacement | UTL | BOF | 2025-04-10 | 2025-04-10 | 164800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164800
Lehigh Valley | 5 | Lehigh | 94680 | South Walnut Street Bridge | 7408 | WSB | Bridge Replacement | UTL | 183 | 2025-04-10 | 2025-04-10 | 30900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30900
Lehigh Valley | 5 | Lehigh | 94680 | South Walnut Street Bridge | 7408 | WSB | Bridge Replacement | CON | BOF | 2025-04-10 | 2025-04-10 | 2363472 | 2282288 | 1206000 | 0 | 0 | 0 | 0 | 0 | 0 | 5851760
Lehigh Valley | 5 | Lehigh | 94680 | South Walnut Street Bridge | 7408 | WSB | Bridge Replacement | CON | STU | 2025-04-10 | 2025-04-10 | 0 | 2202864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2202864
Lehigh Valley | 5 | Lehigh | 94680 | South Walnut Street Bridge | 7408 | WSB | Bridge Replacement | CON | 183 | 2025-04-10 | 2025-04-10 | 443151 | 840966 | 226125 | 0 | 0 | 0 | 0 | 0 | 0 | 1510242
Lehigh Valley | 5 | Lehigh | 94680 | South Walnut Street Bridge | 7408 | WSB | Bridge Replacement | CON | LOC | 2025-04-10 | 2025-04-10 | 147717 | 280322 | 75375 | 0 | 0 | 0 | 0 | 0 | 0 | 503414
Lehigh Valley | 5 | Lehigh | 94873 | Fifth Street Bridge | 1029 | 01B | Bridge Replacement | UTL | STP | 2030-04-01 |  | 0 | 0 | 437080 | 0 | 0 | 0 | 0 | 0 | 0 | 437080
Lehigh Valley | 5 | Lehigh | 94873 | Fifth Street Bridge | 1029 | 01B | Bridge Replacement | UTL | 581 | 2030-04-01 |  | 0 | 0 | 109270 | 0 | 0 | 0 | 0 | 0 | 0 | 109270
Lehigh Valley | 5 | Lehigh | 94873 | Fifth Street Bridge | 1029 | 01B | Bridge Replacement | CON | BRIP | 2030-04-01 |  | 0 | 0 | 2500000 | 4056200 | 0 | 0 | 0 | 0 | 0 | 6556200
Lehigh Valley | 5 | Lehigh | 95400 | Environmental Impacts Resolution LI |  | EIR | Planning/Research/Administration | PE | 581 |  |  | 182096 | 150100 | 150100 | 150100 | 150100 | 200000 | 200000 | 200000 | 800000 | 2182496
Lehigh Valley | 5 | Lehigh | 96386 | PA 309-4010 to 100 | 309 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 652400 | 652400
Lehigh Valley | 5 | Lehigh | 96413 | Lehigh Street Betterment | 2005 | 05M | Highway Restoration | PE | STP | 2026-12-03 |  | 370800 | 69612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440412
Lehigh Valley | 5 | Lehigh | 96413 | Lehigh Street Betterment | 2005 | 05M | Highway Restoration | PE | 581 | 2026-12-03 |  | 92700 | 17403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110103
Lehigh Valley | 5 | Lehigh | 96413 | Lehigh Street Betterment | 2005 | 05M | Highway Restoration | ROW | 581 | 2026-12-03 |  | 0 | 21218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21218
Lehigh Valley | 5 | Lehigh | 96413 | Lehigh Street Betterment | 2005 | 05M | Highway Restoration | UTL | STP | 2026-12-03 |  | 0 | 0 | 43708 | 0 | 0 | 0 | 0 | 0 | 0 | 43708
Lehigh Valley | 5 | Lehigh | 96413 | Lehigh Street Betterment | 2005 | 05M | Highway Restoration | UTL | 581 | 2026-12-03 |  | 0 | 0 | 10927 | 0 | 0 | 0 | 0 | 0 | 0 | 10927
Lehigh Valley | 5 | Lehigh | 96413 | Lehigh Street Betterment | 2005 | 05M | Highway Restoration | CON | 581 | 2026-12-03 |  | 0 | 0 | 1250000 | 2500000 | 1604230 | 0 | 0 | 0 | 0 | 5354230
Lehigh Valley | 5 | Lehigh | 96432 | 309 & Tilghman I/C Recon | 309 | 12M | Highway Reconstruction | CON | NHPP | 2024-07-25 | 2024-08-08 | 7424300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7424300
Lehigh Valley | 5 | Lehigh | 96432 | 309 & Tilghman I/C Recon | 309 | 12M | Highway Reconstruction | CON | STP | 2024-07-25 | 2024-08-08 | 4806000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4806000
Lehigh Valley | 5 | Lehigh | 96432 | 309 & Tilghman I/C Recon | 309 | 12M | Highway Reconstruction | CON | STU | 2024-07-25 | 2024-08-08 | 8500000 | 5296782 | 2834980 | 0 | 0 | 0 | 0 | 0 | 0 | 16631762
Lehigh Valley | 5 | Lehigh | 96432 | 309 & Tilghman I/C Recon | 309 | 12M | Highway Reconstruction | CON | 581 | 2024-07-25 | 2024-08-08 | 4750000 | 5375000 | 708745 | 0 | 0 | 0 | 0 | 0 | 0 | 10833745
Lehigh Valley | 5 | Lehigh | 97227 | 222 N. Widen-LVTS | 222 | 0 | Highway Reconstruction | STUDY | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 652400 | 652400
Lehigh Valley | 5 | Lehigh | 97325 | Construction Assistance |  | CAS | Reserve Line Item | CON | 581 |  |  | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 200000 | 550000
Lehigh Valley | 5 | Lehigh | 97953 | Construction Assistance |  | CAF | Reserve Line Item | CON | STP |  |  | 194978 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 300000 | 1019978
Lehigh Valley | 5 | Lehigh | 99697 | 7th St Multimodal Corridor | 145 | MLT | Congestion Reduction | FD | STU | 2029-04-01 |  | 0 | 250000 | 386540 | 0 | 0 | 0 | 0 | 0 | 0 | 636540
Lehigh Valley | 5 | Lehigh | 99697 | 7th St Multimodal Corridor | 145 | MLT | Congestion Reduction | FD | 581 | 2029-04-01 |  | 0 | 62500 | 96635 | 0 | 0 | 0 | 0 | 0 | 0 | 159135
Lehigh Valley | 5 | Lehigh | 99697 | 7th St Multimodal Corridor | 145 | MLT | Congestion Reduction | ROW | STU | 2029-04-01 |  | 0 | 0 | 87416 | 0 | 0 | 0 | 0 | 0 | 0 | 87416
Lehigh Valley | 5 | Lehigh | 99697 | 7th St Multimodal Corridor | 145 | MLT | Congestion Reduction | ROW | 581 | 2029-04-01 |  | 0 | 0 | 21854 | 0 | 0 | 0 | 0 | 0 | 0 | 21854
Lehigh Valley | 5 | Lehigh | 99697 | 7th St Multimodal Corridor | 145 | MLT | Congestion Reduction | UTL | 581 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 115930 | 0 | 0 | 0 | 0 | 115930
Lehigh Valley | 5 | Lehigh | 99697 | 7th St Multimodal Corridor | 145 | MLT | Congestion Reduction | CON | 581 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 750000 | 988950 | 0 | 0 | 0 | 1738950
Lehigh Valley | 5 | Lehigh | 102160 | 309 Center Valley IC | 309 | 19M | Congestion Reduction | PE | CAQ | 2028-07-27 |  | 1101600 | 26820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1128420
Lehigh Valley | 5 | Lehigh | 102160 | 309 Center Valley IC | 309 | 19M | Congestion Reduction | PE | STP | 2028-07-27 |  | 0 | 131404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131404
Lehigh Valley | 5 | Lehigh | 102160 | 309 Center Valley IC | 309 | 19M | Congestion Reduction | PE | 581 | 2028-07-27 |  | 275400 | 39556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314956
Lehigh Valley | 5 | Lehigh | 102160 | 309 Center Valley IC | 309 | 19M | Congestion Reduction | ROW | CAQ | 2028-07-27 |  | 1388400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1388400
Lehigh Valley | 5 | Lehigh | 102160 | 309 Center Valley IC | 309 | 19M | Congestion Reduction | ROW | NHPP | 2028-07-27 |  | 2290000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2290000
Lehigh Valley | 5 | Lehigh | 102160 | 309 Center Valley IC | 309 | 19M | Congestion Reduction | UTL | CAQ | 2028-07-27 |  | 0 | 212180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212180
Lehigh Valley | 5 | Lehigh | 102160 | 309 Center Valley IC | 309 | 19M | Congestion Reduction | UTL | 581 | 2028-07-27 |  | 0 | 53045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53045
Lehigh Valley | 5 | Lehigh | 102160 | 309 Center Valley IC | 309 | 19M | Congestion Reduction | CON | CAQ | 2028-07-27 |  | 0 | 5950000 | 6000000 | 6000000 | 5000000 | 0 | 0 | 0 | 0 | 22950000
Lehigh Valley | 5 | Lehigh | 102160 | 309 Center Valley IC | 309 | 19M | Congestion Reduction | CON | NHPP | 2028-07-27 |  | 0 | 0 | 8250000 | 5750000 | 1216800 | 0 | 0 | 0 | 0 | 15216800
Lehigh Valley | 5 | Lehigh | 102160 | 309 Center Valley IC | 309 | 19M | Congestion Reduction | CON | PRTCT | 2028-07-27 |  | 1480999 | 1519001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
Lehigh Valley | 5 | Lehigh | 102160 | 309 Center Valley IC | 309 | 19M | Congestion Reduction | CON | STP | 2028-07-27 |  | 0 | 0 | 5500000 | 6000000 | 5500000 | 0 | 0 | 0 | 0 | 17000000
Lehigh Valley | 5 | Lehigh | 102160 | 309 Center Valley IC | 309 | 19M | Congestion Reduction | CON | 581 | 2028-07-27 |  | 0 | 1487500 | 4937500 | 4437500 | 2929200 | 0 | 0 | 0 | 0 | 13791700
Lehigh Valley | 5 | Lehigh | 102201 | LVTS Highway & Bridge LI |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 308223 | 81280 | 755016 | 270857 | 1223490 | 1492758 | 2050450 | 22340000 | 28522074
Lehigh Valley | 5 | Lehigh | 102201 | LVTS Highway & Bridge LI |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 2896800 | 757472 | 431680 | 47960 | 2293612 | 3898332 | 8494000 | 33977000 | 52796856
Lehigh Valley | 5 | Lehigh | 102201 | LVTS Highway & Bridge LI |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 775622 | 1519940 | 319000 | 888480 | 1569000 | 3773000 | 8569000 | 50277000 | 67691042
Lehigh Valley | 5 | Lehigh | 102201 | LVTS Highway & Bridge LI |  |  | Reserve Line Item | CON | STP |  |  | 0 | 154118 | 468588 | 842768 | 395536 | 498540 | 1018688 | 4545280 | 24746208 | 32669726
Lehigh Valley | 5 | Lehigh | 102201 | LVTS Highway & Bridge LI |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 759928 | 779554 | 1942654 | 2013551 | 1890930 | 3271920 | 3204500 | 26999560 | 40862597
Lehigh Valley | 5 | Lehigh | 102201 | LVTS Highway & Bridge LI |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 1484240 | 77694 | 128685 | 453318 | 8764573 | 11268835 | 12042080 | 61225832 | 95445257
Lehigh Valley | 5 | Lehigh | 102312 | PA 309 Resurface | 309 | 14M | Highway Restoration | PE | 581 | 2026-06-04 |  | 50739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50739
Lehigh Valley | 5 | Lehigh | 102312 | PA 309 Resurface | 309 | 14M | Highway Restoration | FD | NHPP | 2026-06-04 |  | 152736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152736
Lehigh Valley | 5 | Lehigh | 102312 | PA 309 Resurface | 309 | 14M | Highway Restoration | FD | 581 | 2026-06-04 |  | 38184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38184
Lehigh Valley | 5 | Lehigh | 102312 | PA 309 Resurface | 309 | 14M | Highway Restoration | UTL | STU | 2026-06-04 |  | 0 | 155216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155216
Lehigh Valley | 5 | Lehigh | 102312 | PA 309 Resurface | 309 | 14M | Highway Restoration | UTL | 581 | 2026-06-04 |  | 0 | 38804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38804
Lehigh Valley | 5 | Lehigh | 102312 | PA 309 Resurface | 309 | 14M | Highway Restoration | CON | NHPP | 2026-06-04 |  | 4000000 | 11985000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15985000
Lehigh Valley | 5 | Lehigh | 102312 | PA 309 Resurface | 309 | 14M | Highway Restoration | CON | STP | 2026-06-04 |  | 0 | 2295000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295000
Lehigh Valley | 5 | Lehigh | 102761 | LVTS Traffic Review Assistance |  |  | Preventive Maintenance | PE | 581 |  |  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 200000 | 600000
Lehigh Valley | 5 | Lehigh | 102868 | Ruppsville Road |  | 06X | Rail Highway Grade Crossing | CON | RRX | 2028-04-01 |  | 0 | 0 | 0 | 270200 | 0 | 0 | 0 | 0 | 0 | 270200
Lehigh Valley | 5 | Lehigh | 102870 | Penn Ave Alburtis RRX |  |  | Rail Highway Grade Crossing | CON | RRX | 2028-04-01 |  | 0 | 0 | 0 | 282000 | 0 | 0 | 0 | 0 | 0 | 282000
Lehigh Valley | 5 | Lehigh | 102979 | Albert Street Allentown RRX |  |  | Rail Highway Grade Crossing | CON | RRX | 2028-04-01 |  | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Lehigh Valley | 5 | Lehigh | 107552 | Gap Bridge Repairs | 873 | 02B | Bridge Restoration | CON | BRIP | 2024-08-08 | 2024-08-08 | 2941040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941040
Lehigh Valley | 5 | Lehigh | 107552 | Gap Bridge Repairs | 873 | 02B | Bridge Restoration | CON | 581 | 2024-08-08 | 2024-08-08 | 735260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735260
Lehigh Valley | 5 | Lehigh | 109237 | Powder Valley Road over Indian Creek | 2025 | 01B | Bridge Replacement | PE | 185 | 2027-02-11 |  | 74137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74137
Lehigh Valley | 5 | Lehigh | 109237 | Powder Valley Road over Indian Creek | 2025 | 01B | Bridge Replacement | FD | BOF | 2027-02-11 |  | 362360 | 87640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
Lehigh Valley | 5 | Lehigh | 109237 | Powder Valley Road over Indian Creek | 2025 | 01B | Bridge Replacement | ROW | BOF | 2027-02-11 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Lehigh Valley | 5 | Lehigh | 109237 | Powder Valley Road over Indian Creek | 2025 | 01B | Bridge Replacement | UTL | BOF | 2027-02-11 |  | 0 | 0 | 12360 | 0 | 0 | 0 | 0 | 0 | 0 | 12360
Lehigh Valley | 5 | Lehigh | 109237 | Powder Valley Road over Indian Creek | 2025 | 01B | Bridge Replacement | UTL | 185 | 2027-02-11 |  | 0 | 0 | 3090 | 0 | 0 | 0 | 0 | 0 | 0 | 3090
Lehigh Valley | 5 | Lehigh | 109237 | Powder Valley Road over Indian Creek | 2025 | 01B | Bridge Replacement | CON | 185 | 2027-02-11 |  | 0 | 0 | 500000 | 530000 | 0 | 0 | 0 | 0 | 0 | 1030000
Lehigh Valley | 5 | Lehigh | 109971 | Route 145 Safety Improvements | 145 | 13S | Safety Improvement | CON | HSIP | 2023-09-14 | 2023-09-28 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
Lehigh Valley | 5 | Lehigh | 109971 | Route 145 Safety Improvements | 145 | 13S | Safety Improvement | CON | 581 | 2023-09-14 | 2023-09-28 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
Lehigh Valley | 5 | Lehigh | 110066 | Box Culvert Bundle-Round 2 | 143 | BC2 | Bridge Replacement | FD | 185 | 2026-07-02 |  | 768910 | 239090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1008000
Lehigh Valley | 5 | Lehigh | 110066 | Box Culvert Bundle-Round 2 | 143 | BC2 | Bridge Replacement | CON | 185 | 2026-07-02 |  | 0 | 750000 | 2786230 | 0 | 0 | 0 | 0 | 0 | 0 | 3536230
Lehigh Valley | 5 | Lehigh | 110067 | N. Dauphin St over Trib to Lehigh | 1007 | PM7 | Bridge Preservation - State Funded | ROW | 185 | 2024-12-12 | 2024-12-12 | 0 | 24850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24850
Lehigh Valley | 5 | Lehigh | 110067 | N. Dauphin St over Trib to Lehigh | 1007 | PM7 | Bridge Preservation - State Funded | UTL | 185 | 2024-12-12 | 2024-12-12 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Lehigh Valley | 5 | Lehigh | 110076 | Jordan Creek Brg Replacement | 145 | 09B | Bridge Replacement | FD | BRIP | 2029-11-01 |  | 0 | 0 | 763848 | 0 | 0 | 0 | 0 | 0 | 0 | 763848
Lehigh Valley | 5 | Lehigh | 110076 | Jordan Creek Brg Replacement | 145 | 09B | Bridge Replacement | FD | 185 | 2029-11-01 |  | 0 | 0 | 190962 | 0 | 0 | 0 | 0 | 0 | 0 | 190962
Lehigh Valley | 5 | Lehigh | 110076 | Jordan Creek Brg Replacement | 145 | 09B | Bridge Replacement | ROW | BRIP | 2029-11-01 |  | 0 | 0 | 636540 | 0 | 0 | 0 | 0 | 0 | 0 | 636540
Lehigh Valley | 5 | Lehigh | 110076 | Jordan Creek Brg Replacement | 145 | 09B | Bridge Replacement | ROW | 185 | 2029-11-01 |  | 0 | 0 | 159135 | 0 | 0 | 0 | 0 | 0 | 0 | 159135
Lehigh Valley | 5 | Lehigh | 110076 | Jordan Creek Brg Replacement | 145 | 09B | Bridge Replacement | UTL | BRIP | 2029-11-01 |  | 0 | 0 | 218540 | 0 | 0 | 0 | 0 | 0 | 0 | 218540
Lehigh Valley | 5 | Lehigh | 110076 | Jordan Creek Brg Replacement | 145 | 09B | Bridge Replacement | UTL | 185 | 2029-11-01 |  | 0 | 0 | 54635 | 0 | 0 | 0 | 0 | 0 | 0 | 54635
Lehigh Valley | 5 | Lehigh | 110076 | Jordan Creek Brg Replacement | 145 | 09B | Bridge Replacement | CON | BRIP | 2029-11-01 |  | 0 | 0 | 0 | 0 | 200000 | 6200388 | 2873808 | 0 | 0 | 9274196
Lehigh Valley | 5 | Lehigh | 110076 | Jordan Creek Brg Replacement | 145 | 09B | Bridge Replacement | CON | 185 | 2029-11-01 |  | 0 | 0 | 0 | 0 | 50000 | 1550097 | 718452 | 0 | 0 | 2318549
Lehigh Valley | 5 | Lehigh | 110086 | LVTS Urban ITS | 22 | LUI | Congestion Reduction | CON | CAQ | 2023-04-27 | 2023-04-27 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Lehigh Valley | 5 | Lehigh | 110086 | LVTS Urban ITS | 22 | LUI | Congestion Reduction | CON | STP | 2023-04-27 | 2023-04-27 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
Lehigh Valley | 5 | Lehigh | 110169 | SR 29/Cedar Crest Blvd Signal Upgrades | 29 | 04S | Congestion Reduction | CON | CAQ | 2022-09-15 | 2022-11-03 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Lehigh Valley | 5 | Lehigh | 110170 | MacArthur Rd Signal Upgrade | 145 | 14S | Congestion Reduction | CON | CAQ | 2022-10-20 | 2022-11-03 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Lehigh Valley | 5 | Lehigh | 110173 | SR 309 Coopersburg Adpt Signal Upgrade | 309 | 14S | Congestion Reduction | PE | CAQ | 2037-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521920 | 521920
Lehigh Valley | 5 | Lehigh | 110174 | Mauch Chunk Rd Signal Upgrade | 1017 | 02S | Congestion Reduction | UTL | CAQ | 2025-12-04 | 2025-12-11 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Lehigh Valley | 5 | Lehigh | 110174 | Mauch Chunk Rd Signal Upgrade | 1017 | 02S | Congestion Reduction | CON | CAQ | 2025-12-04 | 2025-12-11 | 1200000 | 797821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1997821
Lehigh Valley | 5 | Lehigh | 110174 | Mauch Chunk Rd Signal Upgrade | 1017 | 02S | Congestion Reduction | CON | OTH | 2025-12-04 | 2025-12-11 | 0 | 23750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23750
Lehigh Valley | 5 | Lehigh | 110183 | SR 29 - Shimersville Hill Safety Imprv | 29 | 05S | Safety Improvement | FD | NHPP | 2026-04-09 |  | 146421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146421
Lehigh Valley | 5 | Lehigh | 110183 | SR 29 - Shimersville Hill Safety Imprv | 29 | 05S | Safety Improvement | ROW | HSIP | 2026-04-09 |  | 1170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1170000
Lehigh Valley | 5 | Lehigh | 110183 | SR 29 - Shimersville Hill Safety Imprv | 29 | 05S | Safety Improvement | ROW | 581 | 2026-04-09 |  | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000
Lehigh Valley | 5 | Lehigh | 110183 | SR 29 - Shimersville Hill Safety Imprv | 29 | 05S | Safety Improvement | UTL | NHPP | 2026-04-09 |  | 81673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81673
Lehigh Valley | 5 | Lehigh | 110183 | SR 29 - Shimersville Hill Safety Imprv | 29 | 05S | Safety Improvement | CON | HSIP | 2026-04-09 |  | 3208806 | 3170344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6379150
Lehigh Valley | 5 | Lehigh | 110183 | SR 29 - Shimersville Hill Safety Imprv | 29 | 05S | Safety Improvement | CON | STP | 2026-04-09 |  | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
Lehigh Valley | 5 | Lehigh | 110183 | SR 29 - Shimersville Hill Safety Imprv | 29 | 05S | Safety Improvement | CON | STU | 2026-04-09 |  | 0 | 1214654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1214654
Lehigh Valley | 5 | Lehigh | 110388 | MacArthur Rd Multimodal Study | 145 | MMS | Highway Restoration | STUDY | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260960 | 260960
Lehigh Valley | 5 | Lehigh | 110396 | Summit Lawn to Amer Pkway Connectivity Study | 145 | MCS | Highway Restoration | STUDY | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391440 | 391440
Lehigh Valley | 5 | Lehigh | 110398 | SR 378 Lighting | 378 | 04M | Highway Restoration | ROW | 581 | 2027-04-01 |  | 0 | 21218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21218
Lehigh Valley | 5 | Lehigh | 110398 | SR 378 Lighting | 378 | 04M | Highway Restoration | UTL | 581 | 2027-04-01 |  | 0 | 0 | 81953 | 0 | 0 | 0 | 0 | 0 | 0 | 81953
Lehigh Valley | 5 | Lehigh | 110398 | SR 378 Lighting | 378 | 04M | Highway Restoration | CON | 581 | 2027-04-01 |  | 0 | 0 | 1000000 | 912225 | 0 | 0 | 0 | 0 | 0 | 1912225
Lehigh Valley | 5 | Lehigh | 113099 | Main St (SR 873) & Walnut St I/S Improvments | 873 | MWI | MultiModal | CON | 411 | 2025-04-10 | 2025-04-10 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440000
Lehigh Valley | 5 | Lehigh | 113099 | Main St (SR 873) & Walnut St I/S Improvments | 873 | MWI | MultiModal | CON | LOC | 2025-04-10 | 2025-04-10 | 132000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132000
Lehigh Valley | 5 | Lehigh | 114344 | LVTS TOC Operator | 22 | TOC | Intelligent Transportation System | CON | NHPP |  |  | 50000 | 129626 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 200000 | 679626
Lehigh Valley | 5 | Lehigh | 114345 | LVTS Bridge Preservation & Repair 8 | 2018 | BRM | Bridge Preservation - State Funded | CON | 185 | 2027-04-01 |  | 0 | 0 | 2500000 | 2963500 | 0 | 0 | 0 | 0 | 0 | 5463500
Lehigh Valley | 5 | Lehigh | 117517 | Municipal Bridge Line Item |  |  | Bridge Replacement | CON | 183 |  |  | 0 | 0 | 0 | 1000000 | 1000000 | 1000000 | 1500000 | 1500000 | 0 | 6000000
Lehigh Valley | 5 | Lehigh | 117522 | In House Geo Tech Assistance | 4009 | GTA | Bridge Restoration | PE | 581 |  |  | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 200000 | 550000
Lehigh Valley | 5 | Lehigh | 117610 | SR 22 / Fullerton Interchange | 22 | WD1 | Highway Reconstruction | FD | NHPP | 2030-04-01 |  | 0 | 0 | 1000000 | 2296000 | 0 | 0 | 0 | 0 | 0 | 3296000
Lehigh Valley | 5 | Lehigh | 117610 | SR 22 / Fullerton Interchange | 22 | WD1 | Highway Reconstruction | FD | 581 | 2030-04-01 |  | 0 | 0 | 250000 | 574000 | 0 | 0 | 0 | 0 | 0 | 824000
Lehigh Valley | 5 | Lehigh | 117610 | SR 22 / Fullerton Interchange | 22 | WD1 | Highway Reconstruction | ROW | NHPP | 2030-04-01 |  | 0 | 0 | 2970520 | 0 | 0 | 0 | 0 | 0 | 0 | 2970520
Lehigh Valley | 5 | Lehigh | 117610 | SR 22 / Fullerton Interchange | 22 | WD1 | Highway Reconstruction | ROW | 581 | 2030-04-01 |  | 0 | 0 | 742630 | 0 | 0 | 0 | 0 | 0 | 0 | 742630
Lehigh Valley | 5 | Lehigh | 117610 | SR 22 / Fullerton Interchange | 22 | WD1 | Highway Reconstruction | UTL | NHPP | 2030-04-01 |  | 0 | 0 | 218540 | 0 | 0 | 0 | 0 | 0 | 0 | 218540
Lehigh Valley | 5 | Lehigh | 117610 | SR 22 / Fullerton Interchange | 22 | WD1 | Highway Reconstruction | UTL | 581 | 2030-04-01 |  | 0 | 0 | 54635 | 0 | 0 | 0 | 0 | 0 | 0 | 54635
Lehigh Valley | 5 | Lehigh | 117610 | SR 22 / Fullerton Interchange | 22 | WD1 | Highway Reconstruction | CON | NHPP | 2030-04-01 |  | 0 | 0 | 0 | 1704000 | 10000000 | 10000000 | 4796000 | 0 | 0 | 26500000
Lehigh Valley | 5 | Lehigh | 117610 | SR 22 / Fullerton Interchange | 22 | WD1 | Highway Reconstruction | CON | STU | 2030-04-01 |  | 0 | 0 | 0 | 750000 | 950000 | 6766400 | 0 | 0 | 0 | 8466400
Lehigh Valley | 5 | Lehigh | 117610 | SR 22 / Fullerton Interchange | 22 | WD1 | Highway Reconstruction | CON | 581 | 2030-04-01 |  | 0 | 0 | 0 | 613500 | 2737500 | 4191600 | 1199000 | 0 | 0 | 8741600
Lehigh Valley | 5 | Lehigh | 118070 | Riverside Drive RAISE Grant |  | RSD | Additional Lanes | PE | RAISE | 2027-08-12 |  | 725000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 725000
Lehigh Valley | 5 | Lehigh | 118070 | Riverside Drive RAISE Grant |  | RSD | Additional Lanes | FD | RAISE | 2027-08-12 |  | 775000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775000
Lehigh Valley | 5 | Lehigh | 118070 | Riverside Drive RAISE Grant |  | RSD | Additional Lanes | ROW | RAISE | 2027-08-12 |  | 517900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517900
Lehigh Valley | 5 | Lehigh | 118070 | Riverside Drive RAISE Grant |  | RSD | Additional Lanes | UTL | RAISE | 2027-08-12 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Lehigh Valley | 5 | Lehigh | 118070 | Riverside Drive RAISE Grant |  | RSD | Additional Lanes | CON | RAISE | 2027-08-12 |  | 0 | 0 | 16840954 | 0 | 0 | 0 | 0 | 0 | 0 | 16840954
Lehigh Valley | 5 | Lehigh | 118404 | Bogert's Bridge Rehabilitation |  | BBR | Bridge Restoration | CON | TAP | 2025-05-08 | 2025-05-08 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Lehigh Valley | 5 | Lehigh | 118870 | South Albert Street over Lehigh Canal Replacement | 7301 | 0 | Bridge Replacement | PE | BOF | 2031-04-01 |  | 0 | 0 | 100000 | 227810 | 0 | 0 | 0 | 0 | 0 | 327810
Lehigh Valley | 5 | Lehigh | 118870 | South Albert Street over Lehigh Canal Replacement | 7301 | 0 | Bridge Replacement | FD | BOF | 2031-04-01 |  | 0 | 0 | 0 | 0 | 150000 | 81860 | 0 | 0 | 0 | 231860
Lehigh Valley | 5 | Lehigh | 118870 | South Albert Street over Lehigh Canal Replacement | 7301 | 0 | Bridge Replacement | ROW | BOF | 2031-04-01 |  | 0 | 0 | 0 | 0 | 57965 | 0 | 0 | 0 | 0 | 57965
Lehigh Valley | 5 | Lehigh | 118870 | South Albert Street over Lehigh Canal Replacement | 7301 | 0 | Bridge Replacement | UTL | BOF | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 30747 | 0 | 0 | 30747
Lehigh Valley | 5 | Lehigh | 118870 | South Albert Street over Lehigh Canal Replacement | 7301 | 0 | Bridge Replacement | CON | BOF | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 598870 | 0 | 1598870
Lehigh Valley | 5 | Lehigh | 119413 | LVTS Vulnerable Road User Project - Tier 1 | 145 | VRU | Safety Improvement | CON | HVRU | 2023-11-02 | 2023-11-02 | 0 | 8413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8413
Lehigh Valley | 5 | Lehigh | 119690 | SR 22 Widening - Lehigh River Bridge to Airport Rd | 22 | WD2 | Congestion Reduction | PE | NHPP | 2033-04-01 |  | 0 | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000
Lehigh Valley | 5 | Lehigh | 119933 | Fish Hatchery Road over Little Lehigh Creek | 2010 | 01B | Bridge Restoration | FD | BOF | 2027-07-29 |  | 0 | 250000 | 174360 | 0 | 0 | 0 | 0 | 0 | 0 | 424360
Lehigh Valley | 5 | Lehigh | 119933 | Fish Hatchery Road over Little Lehigh Creek | 2010 | 01B | Bridge Restoration | FD | 185 | 2027-07-29 |  | 0 | 62500 | 43590 | 0 | 0 | 0 | 0 | 0 | 0 | 106090
Lehigh Valley | 5 | Lehigh | 119933 | Fish Hatchery Road over Little Lehigh Creek | 2010 | 01B | Bridge Restoration | ROW | BOF | 2027-07-29 |  | 0 | 42436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42436
Lehigh Valley | 5 | Lehigh | 119933 | Fish Hatchery Road over Little Lehigh Creek | 2010 | 01B | Bridge Restoration | ROW | 185 | 2027-07-29 |  | 0 | 10609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10609
Lehigh Valley | 5 | Lehigh | 119933 | Fish Hatchery Road over Little Lehigh Creek | 2010 | 01B | Bridge Restoration | UTL | BOF | 2027-07-29 |  | 0 | 0 | 0 | 45020 | 0 | 0 | 0 | 0 | 0 | 45020
Lehigh Valley | 5 | Lehigh | 119933 | Fish Hatchery Road over Little Lehigh Creek | 2010 | 01B | Bridge Restoration | UTL | 185 | 2027-07-29 |  | 0 | 0 | 0 | 11255 | 0 | 0 | 0 | 0 | 0 | 11255
Lehigh Valley | 5 | Lehigh | 119933 | Fish Hatchery Road over Little Lehigh Creek | 2010 | 01B | Bridge Restoration | CON | BOF | 2027-07-29 |  | 0 | 0 | 0 | 1250000 | 775900 | 0 | 0 | 0 | 0 | 2025900
Lehigh Valley | 5 | Lehigh | 119933 | Fish Hatchery Road over Little Lehigh Creek | 2010 | 01B | Bridge Restoration | CON | 185 | 2027-07-29 |  | 0 | 0 | 0 | 312500 | 193975 | 0 | 0 | 0 | 0 | 506475
Lehigh Valley | 5 | Lehigh | 119936 | Limeport Pike over Hosensack Creek | 2029 | 04B | Bridge Replacement | FD | BOF | 2027-04-29 |  | 259970 | 45078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305048
Lehigh Valley | 5 | Lehigh | 119936 | Limeport Pike over Hosensack Creek | 2029 | 04B | Bridge Replacement | FD | 185 | 2027-04-29 |  | 64993 | 11269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76262
Lehigh Valley | 5 | Lehigh | 119936 | Limeport Pike over Hosensack Creek | 2029 | 04B | Bridge Replacement | ROW | BOF | 2027-04-29 |  | 0 | 81120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81120
Lehigh Valley | 5 | Lehigh | 119936 | Limeport Pike over Hosensack Creek | 2029 | 04B | Bridge Replacement | ROW | 185 | 2027-04-29 |  | 0 | 20280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20280
Lehigh Valley | 5 | Lehigh | 119936 | Limeport Pike over Hosensack Creek | 2029 | 04B | Bridge Replacement | UTL | BOF | 2027-04-29 |  | 0 | 0 | 43708 | 0 | 0 | 0 | 0 | 0 | 0 | 43708
Lehigh Valley | 5 | Lehigh | 119936 | Limeport Pike over Hosensack Creek | 2029 | 04B | Bridge Replacement | UTL | 185 | 2027-04-29 |  | 0 | 0 | 10927 | 0 | 0 | 0 | 0 | 0 | 0 | 10927
Lehigh Valley | 5 | Lehigh | 119936 | Limeport Pike over Hosensack Creek | 2029 | 04B | Bridge Replacement | CON | BOF | 2027-04-29 |  | 0 | 0 | 1048992 | 0 | 0 | 0 | 0 | 0 | 0 | 1048992
Lehigh Valley | 5 | Lehigh | 119936 | Limeport Pike over Hosensack Creek | 2029 | 04B | Bridge Replacement | CON | 185 | 2027-04-29 |  | 0 | 0 | 262248 | 0 | 0 | 0 | 0 | 0 | 0 | 262248
Lehigh Valley | 5 | Lehigh | 120950 | BPN-4 Guide Rail Upgrades 2025/2026 | 2047 | BPN | Highway Restoration | CON | 581 |  |  | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 200000
Lehigh Valley | 5 | Lehigh | 120953 | LVTS Bridge Preservation & Repair 10 | 100 | 0 | Bridge Preservation - State Funded | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Lehigh Valley | 5 | Lehigh | 120953 | LVTS Bridge Preservation & Repair 10 | 100 | 0 | Bridge Preservation - State Funded | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
Lehigh Valley | 5 | Lehigh | 120955 | LVTS Box Culvert Bundle 3 | 873 | BCB | Bridge Replacement | PE | 185 | 2029-04-01 |  | 1350000 | 555500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1905500
Lehigh Valley | 5 | Lehigh | 120955 | LVTS Box Culvert Bundle 3 | 873 | BCB | Bridge Replacement | FD | 185 | 2029-04-01 |  | 0 | 0 | 0 | 1000000 | 688250 | 0 | 0 | 0 | 0 | 1688250
Lehigh Valley | 5 | Lehigh | 120955 | LVTS Box Culvert Bundle 3 | 873 | BCB | Bridge Replacement | ROW | 185 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 318808 | 0 | 0 | 0 | 0 | 318808
Lehigh Valley | 5 | Lehigh | 120955 | LVTS Box Culvert Bundle 3 | 873 | BCB | Bridge Replacement | UTL | 185 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 307214 | 0 | 0 | 0 | 0 | 307214
Lehigh Valley | 5 | Lehigh | 120955 | LVTS Box Culvert Bundle 3 | 873 | BCB | Bridge Replacement | CON | 185 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 2000000 | 2347375 | 0 | 0 | 0 | 4347375
Lehigh Valley | 5 | Lehigh | 121443 | ABE Airport Northside Logistics & Cargo Complex |  | ABE | Highway Reconstruction | CON | INFRA |  |  | 40798046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40798046
Lehigh Valley | 5 | Lehigh | 121443 | ABE Airport Northside Logistics & Cargo Complex |  | ABE | Highway Reconstruction | CON | OTH-F |  |  | 4715887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4715887
Lehigh Valley | 5 | Lehigh | 121550 | City of Allentown - School Zone Traffic Safety Upg | 2002 | ASZ | Bicycle Pedestrian Highway | CON | SRTSF | 2026-12-10 |  | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Lehigh Valley | 5 | Lehigh | 121550 | City of Allentown - School Zone Traffic Safety Upg | 2002 | ASZ | Bicycle Pedestrian Highway | CON | TAU | 2026-12-10 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Lehigh Valley | 5 | Lehigh | 121552 | Borough of Coopersburg Streetscape - Phase 9 | 2026 | CS9 | Bicycle Pedestrian Highway | CON | SRTSF | 2026-11-05 |  | 0 | 0 | 1337316 | 0 | 0 | 0 | 0 | 0 | 0 | 1337316
Lehigh Valley | 5 | Lehigh | 122279 | King's Route 309 Business Park Roundabout | 309 | KBP | MultiModal | CON | 411 | 2026-06-18 |  | 2096367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2096367
Lehigh Valley | 5 | Lehigh | 122279 | King's Route 309 Business Park Roundabout | 309 | KBP | MultiModal | CON | LOC | 2026-06-18 |  | 898503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 898503
Lehigh Valley | 5 | Lehigh | 122781 | CAT Bike Education 2025 |  | C25 | Bicycle and Pedestrian Education (K-8 only) | CON | TAU | 2025-09-25 |  | 634122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634122
Lehigh Valley | 5 | Lehigh | 122785 | Albert Street D&L Trail |  | AST | Transportation Enhancement | CON | TAU | 2026-09-17 |  | 0 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000
Lehigh Valley | 5 | Lehigh | 123056 | Martin Luther King, Jr. Drive Ped Improvements |  | MLP | Transportation Enhancement | CON | CRPU | 2026-10-22 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Lehigh Valley | 5 | Lehigh | 123375 | Allentown LED Streetlight Conversion |  | LED | Transportation Enhancement | CON | CRP | 2026-12-03 |  | 0 | 274000 | 219000 | 0 | 0 | 0 | 0 | 0 | 0 | 493000
Lehigh Valley | 5 | Lehigh | 123375 | Allentown LED Streetlight Conversion |  | LED | Transportation Enhancement | CON | CRPU | 2026-12-03 |  | 0 | 226000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226000
Lehigh Valley | 5 | Lehigh | 123418 | Coplay Multimodal Street Improvements |  | CSI | MultiModal | CON | 411 |  |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Lehigh Valley | 5 | Lehigh | 123418 | Coplay Multimodal Street Improvements |  | CSI | MultiModal | CON | LOC |  |  | 301186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301186
Lehigh Valley | 5 | Northampton | 11974 | Frost Hollow Road over trib to Delaware River | 2038 | BC2 | Bridge Replacement | ROW | 185 | 2026-07-02 |  | 23000 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000
Lehigh Valley | 5 | Northampton | 11974 | Frost Hollow Road over trib to Delaware River | 2038 | BC2 | Bridge Replacement | UTL | 185 | 2026-07-02 |  | 0 | 5305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5305
Lehigh Valley | 5 | Northampton | 11981 | Linden Street | 3015 | 01M | Highway Restoration | CON | STU | 2023-08-10 | 2023-08-10 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Lehigh Valley | 5 | Northampton | 11981 | Linden Street | 3015 | 01M | Highway Restoration | CON | 581 | 2023-08-10 | 2023-08-10 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Lehigh Valley | 5 | Northampton | 12106 | Church Road over Trib to Little Bushkill Creek | 1016 | 02B | Bridge Replacement | FD | BOF | 2027-06-10 |  | 0 | 200000 | 139488 | 0 | 0 | 0 | 0 | 0 | 0 | 339488
Lehigh Valley | 5 | Northampton | 12106 | Church Road over Trib to Little Bushkill Creek | 1016 | 02B | Bridge Replacement | FD | 185 | 2027-06-10 |  | 0 | 50000 | 34872 | 0 | 0 | 0 | 0 | 0 | 0 | 84872
Lehigh Valley | 5 | Northampton | 12106 | Church Road over Trib to Little Bushkill Creek | 1016 | 02B | Bridge Replacement | ROW | BOF | 2027-06-10 |  | 38124 | 42436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80560
Lehigh Valley | 5 | Northampton | 12106 | Church Road over Trib to Little Bushkill Creek | 1016 | 02B | Bridge Replacement | ROW | 185 | 2027-06-10 |  | 9531 | 10609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20140
Lehigh Valley | 5 | Northampton | 12106 | Church Road over Trib to Little Bushkill Creek | 1016 | 02B | Bridge Replacement | UTL | BOF | 2027-06-10 |  | 0 | 0 | 43708 | 0 | 0 | 0 | 0 | 0 | 0 | 43708
Lehigh Valley | 5 | Northampton | 12106 | Church Road over Trib to Little Bushkill Creek | 1016 | 02B | Bridge Replacement | UTL | 185 | 2027-06-10 |  | 0 | 0 | 10927 | 0 | 0 | 0 | 0 | 0 | 0 | 10927
Lehigh Valley | 5 | Northampton | 12106 | Church Road over Trib to Little Bushkill Creek | 1016 | 02B | Bridge Replacement | CON | BOF | 2027-06-10 |  | 0 | 0 | 900000 | 148992 | 0 | 0 | 0 | 0 | 0 | 1048992
Lehigh Valley | 5 | Northampton | 12106 | Church Road over Trib to Little Bushkill Creek | 1016 | 02B | Bridge Replacement | CON | 185 | 2027-06-10 |  | 0 | 0 | 225000 | 37248 | 0 | 0 | 0 | 0 | 0 | 262248
Lehigh Valley | 5 | Northampton | 12149 | Million Dollar Highway (SR 1040) over Jacoby Creek | 1040 | BC2 | Bridge Replacement | UTL | 185 | 2032-04-01 |  | 0 | 5305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5305
Lehigh Valley | 5 | Northampton | 12286 | Meadows Road Bridge (Co Br 15) | 7210 | MRB | Bridge Replacement | CON | BOF | 2024-02-29 | 2024-02-29 | 25891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25891
Lehigh Valley | 5 | Northampton | 12286 | Meadows Road Bridge (Co Br 15) | 7210 | MRB | Bridge Replacement | CON | LOC | 2024-02-29 | 2024-02-29 | 6473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6473
Lehigh Valley | 5 | Northampton | 71707 | Farmersville Road Bridge over US 22 | 2029 | 01B | Bridge Replacement | CON | STP | 2024-08-22 | 2024-09-12 | 2418032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2418032
Lehigh Valley | 5 | Northampton | 71707 | Farmersville Road Bridge over US 22 | 2029 | 01B | Bridge Replacement | CON | 185 | 2024-08-22 | 2024-09-12 | 500000 | 104508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604508
Lehigh Valley | 5 | Northampton | 79468 | Williams Twp Canal Wall Replacements | 611 | WCW | Highway Restoration | CON | NHPP | 2024-10-10 | 2024-11-07 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Lehigh Valley | 5 | Northampton | 79468 | Williams Twp Canal Wall Replacements | 611 | WCW | Highway Restoration | CON | 581 | 2024-10-10 | 2024-11-07 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Lehigh Valley | 5 | Northampton | 85929 | Belvidere Rd o/Trib Delwr Riv | 1004 | BC2 | Bridge Restoration | ROW | 185 | 2030-04-01 |  | 19000 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000
Lehigh Valley | 5 | Northampton | 85929 | Belvidere Rd o/Trib Delwr Riv | 1004 | BC2 | Bridge Restoration | UTL | 185 | 2030-04-01 |  | 0 | 5305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5305
Lehigh Valley | 5 | Northampton | 85930 | Lower South Main Street o/Martins Creek | 1015 | 03B | Bridge Replacement | CON | STU | 2023-11-02 | 2023-11-02 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Lehigh Valley | 5 | Northampton | 85930 | Lower South Main Street o/Martins Creek | 1015 | 03B | Bridge Replacement | CON | 185 | 2023-11-02 | 2023-11-02 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Lehigh Valley | 5 | Northampton | 85931 | S. Main Street o/Martins Creek, Bangor | 1015 | 04B | Bridge Restoration | PE | STP | 2030-04-01 |  | 0 | 318628 | 125000 | 209232 | 0 | 0 | 0 | 0 | 0 | 652860
Lehigh Valley | 5 | Northampton | 85931 | S. Main Street o/Martins Creek, Bangor | 1015 | 04B | Bridge Restoration | PE | 581 | 2030-04-01 |  | 0 | 79657 | 31250 | 52308 | 0 | 0 | 0 | 0 | 0 | 163215
Lehigh Valley | 5 | Northampton | 85931 | S. Main Street o/Martins Creek, Bangor | 1015 | 04B | Bridge Restoration | FD | STP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 200000 | 263720 | 0 | 0 | 0 | 463720
Lehigh Valley | 5 | Northampton | 85931 | S. Main Street o/Martins Creek, Bangor | 1015 | 04B | Bridge Restoration | FD | 185 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 50000 | 65930 | 0 | 0 | 0 | 115930
Lehigh Valley | 5 | Northampton | 85931 | S. Main Street o/Martins Creek, Bangor | 1015 | 04B | Bridge Restoration | ROW | STP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 92744 | 0 | 0 | 0 | 0 | 92744
Lehigh Valley | 5 | Northampton | 85931 | S. Main Street o/Martins Creek, Bangor | 1015 | 04B | Bridge Restoration | ROW | 185 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 23186 | 0 | 0 | 0 | 0 | 23186
Lehigh Valley | 5 | Northampton | 85931 | S. Main Street o/Martins Creek, Bangor | 1015 | 04B | Bridge Restoration | UTL | STP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 33436 | 0 | 0 | 0 | 33436
Lehigh Valley | 5 | Northampton | 85931 | S. Main Street o/Martins Creek, Bangor | 1015 | 04B | Bridge Restoration | UTL | 581 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 8359 | 0 | 0 | 0 | 8359
Lehigh Valley | 5 | Northampton | 85931 | S. Main Street o/Martins Creek, Bangor | 1015 | 04B | Bridge Restoration | CON | STP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 2000000 | 388200 | 0 | 0 | 2388200
Lehigh Valley | 5 | Northampton | 85931 | S. Main Street o/Martins Creek, Bangor | 1015 | 04B | Bridge Restoration | CON | 185 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 97050 | 0 | 0 | 597050
Lehigh Valley | 5 | Northampton | 85945 | SR 512 o/ Brush Meadow Creek | 512 | 05B | Bridge Replacement | FD | STP | 2026-01-08 | 2026-01-08 | 23420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23420
Lehigh Valley | 5 | Northampton | 85945 | SR 512 o/ Brush Meadow Creek | 512 | 05B | Bridge Replacement | FD | 581 | 2026-01-08 | 2026-01-08 | 5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5855
Lehigh Valley | 5 | Northampton | 85945 | SR 512 o/ Brush Meadow Creek | 512 | 05B | Bridge Replacement | UTL | 185 | 2026-01-08 | 2026-01-08 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Lehigh Valley | 5 | Northampton | 85945 | SR 512 o/ Brush Meadow Creek | 512 | 05B | Bridge Replacement | CON | STP | 2026-01-08 | 2026-01-08 | 1381402 | 292198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1673600
Lehigh Valley | 5 | Northampton | 85945 | SR 512 o/ Brush Meadow Creek | 512 | 05B | Bridge Replacement | CON | STU | 2026-01-08 | 2026-01-08 | 400000 | 961183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1361183
Lehigh Valley | 5 | Northampton | 85946 | Beth-Bath Pike over Monocacy Creek | 512 | 04B | Bridge Replacement | UTL | STP | 2028-06-29 |  | 0 | 0 | 206000 | 0 | 0 | 0 | 0 | 0 | 0 | 206000
Lehigh Valley | 5 | Northampton | 85946 | Beth-Bath Pike over Monocacy Creek | 512 | 04B | Bridge Replacement | UTL | 185 | 2028-06-29 |  | 0 | 0 | 51500 | 0 | 0 | 0 | 0 | 0 | 0 | 51500
Lehigh Valley | 5 | Northampton | 85946 | Beth-Bath Pike over Monocacy Creek | 512 | 04B | Bridge Replacement | CON | BRIP | 2028-06-29 |  | 0 | 0 | 0 | 3394880 | 0 | 0 | 0 | 0 | 0 | 3394880
Lehigh Valley | 5 | Northampton | 85946 | Beth-Bath Pike over Monocacy Creek | 512 | 04B | Bridge Replacement | CON | 581 | 2028-06-29 |  | 0 | 0 | 0 | 848720 | 0 | 0 | 0 | 0 | 0 | 848720
Lehigh Valley | 5 | Northampton | 86853 | Route 248 Realignment | 248 | 05S | Congestion Reduction | CON | NHPP | 2024-07-11 | 2024-07-25 | 407816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407816
Lehigh Valley | 5 | Northampton | 86853 | Route 248 Realignment | 248 | 05S | Congestion Reduction | CON | STU | 2024-07-11 | 2024-07-25 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Lehigh Valley | 5 | Northampton | 86853 | Route 248 Realignment | 248 | 05S | Congestion Reduction | CON | 581 | 2024-07-11 | 2024-07-25 | 0 | 0 | 2583 | 0 | 0 | 0 | 0 | 0 | 0 | 2583
Lehigh Valley | 5 | Northampton | 89614 | Hecktown Road Bridge over US 22 | 2027 | 01B | Bridge Replacement | UTL | 185 | 2025-08-21 | 2025-08-21 | 292901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292901
Lehigh Valley | 5 | Northampton | 89614 | Hecktown Road Bridge over US 22 | 2027 | 01B | Bridge Replacement | CON | STU | 2025-08-21 | 2025-08-21 | 4649468 | 743321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5392789
Lehigh Valley | 5 | Northampton | 91931 | SR 2025 over Little Bushkill Creek | 2025 | 0 | Bridge Restoration | PE | 185 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 521685 | 0 | 0 | 0 | 0 | 521685
Lehigh Valley | 5 | Northampton | 91931 | SR 2025 over Little Bushkill Creek | 2025 | 0 | Bridge Restoration | FD | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 382112 | 0 | 0 | 0 | 382112
Lehigh Valley | 5 | Northampton | 91931 | SR 2025 over Little Bushkill Creek | 2025 | 0 | Bridge Restoration | FD | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 95528 | 0 | 0 | 0 | 95528
Lehigh Valley | 5 | Northampton | 91931 | SR 2025 over Little Bushkill Creek | 2025 | 0 | Bridge Restoration | ROW | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 23884 | 0 | 0 | 0 | 23884
Lehigh Valley | 5 | Northampton | 91931 | SR 2025 over Little Bushkill Creek | 2025 | 0 | Bridge Restoration | ROW | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 5971 | 0 | 0 | 0 | 5971
Lehigh Valley | 5 | Northampton | 91931 | SR 2025 over Little Bushkill Creek | 2025 | 0 | Bridge Restoration | UTL | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 24600 | 0 | 0 | 24600
Lehigh Valley | 5 | Northampton | 91931 | SR 2025 over Little Bushkill Creek | 2025 | 0 | Bridge Restoration | UTL | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6150 | 0 | 0 | 6150
Lehigh Valley | 5 | Northampton | 91931 | SR 2025 over Little Bushkill Creek | 2025 | 0 | Bridge Restoration | CON | BRIP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1721860 | 0 | 0 | 1721860
Lehigh Valley | 5 | Northampton | 91931 | SR 2025 over Little Bushkill Creek | 2025 | 0 | Bridge Restoration | CON | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 430465 | 0 | 0 | 430465
Lehigh Valley | 5 | Northampton | 92007 | SR 512 over Martins Creek | 512 | 06B | Bridge Restoration | PE | BRIP | 2030-04-01 |  | 131160 | 230093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361253
Lehigh Valley | 5 | Northampton | 92007 | SR 512 over Martins Creek | 512 | 06B | Bridge Restoration | PE | STP | 2030-04-01 |  | 174007 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349007
Lehigh Valley | 5 | Northampton | 92007 | SR 512 over Martins Creek | 512 | 06B | Bridge Restoration | PE | 581 | 2030-04-01 |  | 76292 | 101273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177565
Lehigh Valley | 5 | Northampton | 92007 | SR 512 over Martins Creek | 512 | 06B | Bridge Restoration | FD | 185 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 250000 | 329650 | 0 | 0 | 0 | 579650
Lehigh Valley | 5 | Northampton | 92007 | SR 512 over Martins Creek | 512 | 06B | Bridge Restoration | ROW | STP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 92744 | 0 | 0 | 0 | 0 | 92744
Lehigh Valley | 5 | Northampton | 92007 | SR 512 over Martins Creek | 512 | 06B | Bridge Restoration | ROW | 581 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 23186 | 0 | 0 | 0 | 0 | 23186
Lehigh Valley | 5 | Northampton | 92007 | SR 512 over Martins Creek | 512 | 06B | Bridge Restoration | UTL | STP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 33436 | 0 | 0 | 0 | 33436
Lehigh Valley | 5 | Northampton | 92007 | SR 512 over Martins Creek | 512 | 06B | Bridge Restoration | UTL | 581 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 8359 | 0 | 0 | 0 | 8359
Lehigh Valley | 5 | Northampton | 92007 | SR 512 over Martins Creek | 512 | 06B | Bridge Restoration | CON | STP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 2250000 | 138200 | 0 | 0 | 2388200
Lehigh Valley | 5 | Northampton | 92007 | SR 512 over Martins Creek | 512 | 06B | Bridge Restoration | CON | 581 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 562500 | 34550 | 0 | 0 | 597050
Lehigh Valley | 5 | Northampton | 93631 | Easton Rd over Saucon Crk E. Branch | 2006 | 02B | Bridge Replacement | PE | 185 | 2027-05-13 |  | 0 | 23693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23693
Lehigh Valley | 5 | Northampton | 93631 | Easton Rd over Saucon Crk E. Branch | 2006 | 02B | Bridge Replacement | FD | BRIP | 2027-05-13 |  | 211800 | 97200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309000
Lehigh Valley | 5 | Northampton | 93631 | Easton Rd over Saucon Crk E. Branch | 2006 | 02B | Bridge Replacement | ROW | STP | 2027-05-13 |  | 0 | 74500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74500
Lehigh Valley | 5 | Northampton | 93631 | Easton Rd over Saucon Crk E. Branch | 2006 | 02B | Bridge Replacement | UTL | STP | 2027-05-13 |  | 0 | 0 | 13112 | 0 | 0 | 0 | 0 | 0 | 0 | 13112
Lehigh Valley | 5 | Northampton | 93631 | Easton Rd over Saucon Crk E. Branch | 2006 | 02B | Bridge Replacement | UTL | 185 | 2027-05-13 |  | 0 | 0 | 3278 | 0 | 0 | 0 | 0 | 0 | 0 | 3278
Lehigh Valley | 5 | Northampton | 93631 | Easton Rd over Saucon Crk E. Branch | 2006 | 02B | Bridge Replacement | CON | BRIP | 2027-05-13 |  | 0 | 0 | 700000 | 611240 | 0 | 0 | 0 | 0 | 0 | 1311240
Lehigh Valley | 5 | Northampton | 93631 | Easton Rd over Saucon Crk E. Branch | 2006 | 02B | Bridge Replacement | CON | 185 | 2027-05-13 |  | 0 | 0 | 175000 | 152810 | 0 | 0 | 0 | 0 | 0 | 327810
Lehigh Valley | 5 | Northampton | 96423 | Pave PA 33_I-78 to US 22 | 33 | 08M | Highway Restoration | PE | 581 | 2027-04-01 |  | 25750 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Lehigh Valley | 5 | Northampton | 96423 | Pave PA 33_I-78 to US 22 | 33 | 08M | Highway Restoration | CON | 581 | 2027-04-01 |  | 0 | 0 | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | 8000000
Lehigh Valley | 5 | Northampton | 96431 | PA 33 Bushkill Creek Bridges | 33 | 05B | Bridge Replacement | CON | BRIP | 2023-01-12 | 2023-01-12 | 3377600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3377600
Lehigh Valley | 5 | Northampton | 96431 | PA 33 Bushkill Creek Bridges | 33 | 05B | Bridge Replacement | CON | 185 | 2023-01-12 | 2023-01-12 | 844400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 844400
Lehigh Valley | 5 | Northampton | 101564 | 25th Street Resurface | 2012 | 01M | Highway Restoration | CON | 581 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 950000 | 441160 | 0 | 0 | 0 | 1391160
Lehigh Valley | 5 | Northampton | 101570 | 25th Street to SR 611 in WilsonBoro/City of Easton | 248 | 11M | Highway Restoration | CON | NHPP | 2026-05-21 |  | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
Lehigh Valley | 5 | Northampton | 101570 | 25th Street to SR 611 in WilsonBoro/City of Easton | 248 | 11M | Highway Restoration | CON | STU | 2026-05-21 |  | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Lehigh Valley | 5 | Northampton | 102864 | Bethlehem Corr. Safety | 3015 | 01X | Rail Highway Grade Crossing | CON | RRX | 2034-04-01 |  | 0 | 0 | 0 | 500000 | 660000 | 0 | 0 | 0 | 0 | 1160000
Lehigh Valley | 5 | Northampton | 102869 | SR 512 (Beth Bath Pike) NS RRX | 512 | 05X | Rail Highway Grade Crossing | CON | RRX | 2028-06-29 |  | 0 | 0 | 284109 | 0 | 0 | 0 | 0 | 0 | 0 | 284109
Lehigh Valley | 5 | Northampton | 105371 | Howertown Road Bridge | 3017 | 01B | Bridge Replacement | CON | STU | 2023-03-23 | 2023-03-02 | 127600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127600
Lehigh Valley | 5 | Northampton | 105959 | 25th Street Hill Improvement | 2012 | 02S | Safety Improvement | PE | STP | 2035-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506720 | 0 | 506720
Lehigh Valley | 5 | Northampton | 105959 | 25th Street Hill Improvement | 2012 | 02S | Safety Improvement | PE | 581 | 2035-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126680 | 0 | 126680
Lehigh Valley | 5 | Northampton | 105959 | 25th Street Hill Improvement | 2012 | 02S | Safety Improvement | FD | STP | 2035-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365344 | 365344
Lehigh Valley | 5 | Northampton | 105959 | 25th Street Hill Improvement | 2012 | 02S | Safety Improvement | FD | 581 | 2035-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91336 | 91336
Lehigh Valley | 5 | Northampton | 105959 | 25th Street Hill Improvement | 2012 | 02S | Safety Improvement | ROW | STP | 2035-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156576 | 156576
Lehigh Valley | 5 | Northampton | 105959 | 25th Street Hill Improvement | 2012 | 02S | Safety Improvement | ROW | 581 | 2035-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39144 | 39144
Lehigh Valley | 5 | Northampton | 105959 | 25th Street Hill Improvement | 2012 | 02S | Safety Improvement | UTL | STP | 2035-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52192 | 52192
Lehigh Valley | 5 | Northampton | 105959 | 25th Street Hill Improvement | 2012 | 02S | Safety Improvement | UTL | 581 | 2035-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13048 | 13048
Lehigh Valley | 5 | Northampton | 105959 | 25th Street Hill Improvement | 2012 | 02S | Safety Improvement | CON | STP | 2035-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1565760 | 1565760
Lehigh Valley | 5 | Northampton | 105959 | 25th Street Hill Improvement | 2012 | 02S | Safety Improvement | CON | 581 | 2035-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391440 | 391440
Lehigh Valley | 5 | Northampton | 109914 | Raubsville Road over Frey's Run | 2006 | 01B | Bridge Replacement | CON | BOF | 2025-01-09 | 2025-02-13 | 2074868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2074868
Lehigh Valley | 5 | Northampton | 110062 | Box Culvert Bundle-Round 1 | 4007 | BC1 | Bridge Replacement | CON | 185 | 2024-08-22 | 2024-08-22 | 387782 | 204894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592676
Lehigh Valley | 5 | Northampton | 110179 | 611 Retaining Wall Rehab - Easton | 611 | RWR | Highway Restoration | CON | STU | 2029-04-01 |  | 0 | 0 | 0 | 473080 | 0 | 0 | 0 | 0 | 0 | 473080
Lehigh Valley | 5 | Northampton | 112231 | LVTS Bridge Preservation #7 | 2012 | BRM | Bridge Preservation - State Funded | CON | 185 | 2024-12-12 | 2024-12-12 | 2645878 | 2650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5295878
Lehigh Valley | 5 | Northampton | 113812 | Main St - 21st St to Cherryville Rd | 4003 | 02M | Highway Restoration | CON | STU | 2025-09-25 | 2025-09-25 | 350000 | 589451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939451
Lehigh Valley | 5 | Northampton | 114350 | SR 22 Resurface - Bethman Rd to 25th St | 22 | 14M | Highway Restoration | CON | NHPP | 2021-04-22 | 2021-04-22 | 89153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89153
Lehigh Valley | 5 | Northampton | 116936 | SR 191 Lower Nazareth Intersection Improvements | 191 | 04S | Safety Improvement | FD | HSIP | 2027-01-14 |  | 815751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815751
Lehigh Valley | 5 | Northampton | 116936 | SR 191 Lower Nazareth Intersection Improvements | 191 | 04S | Safety Improvement | FD | 581 | 2027-01-14 |  | 90639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90639
Lehigh Valley | 5 | Northampton | 116936 | SR 191 Lower Nazareth Intersection Improvements | 191 | 04S | Safety Improvement | ROW | HSIP | 2027-01-14 |  | 540450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540450
Lehigh Valley | 5 | Northampton | 116936 | SR 191 Lower Nazareth Intersection Improvements | 191 | 04S | Safety Improvement | ROW | 581 | 2027-01-14 |  | 60050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60050
Lehigh Valley | 5 | Northampton | 116936 | SR 191 Lower Nazareth Intersection Improvements | 191 | 04S | Safety Improvement | UTL | HSIP | 2027-01-14 |  | 0 | 190962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190962
Lehigh Valley | 5 | Northampton | 116936 | SR 191 Lower Nazareth Intersection Improvements | 191 | 04S | Safety Improvement | UTL | 581 | 2027-01-14 |  | 0 | 21218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21218
Lehigh Valley | 5 | Northampton | 116936 | SR 191 Lower Nazareth Intersection Improvements | 191 | 04S | Safety Improvement | CON | HSIP | 2027-01-14 |  | 0 | 235331 | 1914669 | 1032700 | 0 | 0 | 0 | 0 | 0 | 3182700
Lehigh Valley | 5 | Northampton | 117152 | LVTS Bridge Preservation & Repair 9 | 3005 | 0 | Bridge Preservation - State Funded | PE | 185 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 500000 | 659300 | 0 | 0 | 0 | 1159300
Lehigh Valley | 5 | Northampton | 117152 | LVTS Bridge Preservation & Repair 9 | 3005 | 0 | Bridge Preservation - State Funded | CON | 185 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 3649500 | 0 | 6149500
Lehigh Valley | 5 | Northampton | 117240 | Main Street over trib to Martins Creek | 1015 | BC2 | Bridge Replacement | ROW | 185 | 2026-07-02 |  | 27450 | 27450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54900
Lehigh Valley | 5 | Northampton | 117240 | Main Street over trib to Martins Creek | 1015 | BC2 | Bridge Replacement | UTL | 185 | 2026-07-02 |  | 0 | 5305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5305
Lehigh Valley | 5 | Northampton | 117400 | Northampton County Bridge 168 (High Street) | 7406 | HSE | Bridge Removal | PE | 183 | 2029-04-01 |  | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000
Lehigh Valley | 5 | Northampton | 117402 | Jacksonville Road Bridge | 7204 | 0 | Bridge Replacement | PE | BOF | 2031-04-01 |  | 0 | 0 | 100000 | 446350 | 0 | 0 | 0 | 0 | 0 | 546350
Lehigh Valley | 5 | Northampton | 117402 | Jacksonville Road Bridge | 7204 | 0 | Bridge Replacement | FD | BOF | 2031-04-01 |  | 0 | 0 | 0 | 0 | 300000 | 279650 | 0 | 0 | 0 | 579650
Lehigh Valley | 5 | Northampton | 117402 | Jacksonville Road Bridge | 7204 | 0 | Bridge Replacement | ROW | BOF | 2031-04-01 |  | 0 | 0 | 0 | 0 | 115930 | 0 | 0 | 0 | 0 | 115930
Lehigh Valley | 5 | Northampton | 117402 | Jacksonville Road Bridge | 7204 | 0 | Bridge Replacement | UTL | BOF | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 61495 | 0 | 0 | 61495
Lehigh Valley | 5 | Northampton | 117402 | Jacksonville Road Bridge | 7204 | 0 | Bridge Replacement | CON | BOF | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 1935680 | 0 | 3935680
Lehigh Valley | 5 | Northampton | 117509 | Freemansburg Ave (SR 2018) Safety Improvements | 2018 | 02S | Safety Improvement | FD | HSIP | 2026-07-16 |  | 839445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 839445
Lehigh Valley | 5 | Northampton | 117509 | Freemansburg Ave (SR 2018) Safety Improvements | 2018 | 02S | Safety Improvement | ROW | HSIP | 2026-07-16 |  | 683000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 683000
Lehigh Valley | 5 | Northampton | 117509 | Freemansburg Ave (SR 2018) Safety Improvements | 2018 | 02S | Safety Improvement | UTL | HSIP | 2026-07-16 |  | 238707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238707
Lehigh Valley | 5 | Northampton | 117509 | Freemansburg Ave (SR 2018) Safety Improvements | 2018 | 02S | Safety Improvement | UTL | 581 | 2026-07-16 |  | 26523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26523
Lehigh Valley | 5 | Northampton | 117509 | Freemansburg Ave (SR 2018) Safety Improvements | 2018 | 02S | Safety Improvement | CON | HSIP | 2026-07-16 |  | 0 | 1350000 | 2000000 | 719612 | 0 | 0 | 0 | 0 | 0 | 4069612
Lehigh Valley | 5 | Northampton | 117511 | SR 512 Bangor Borough Study | 512 | 05S | Safety Improvement | STUDY | 581 |  |  | 0 | 265922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265922
Lehigh Valley | 5 | Northampton | 117515 | County Bridge Reserve Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 500000 | 1000000 | 4000000 | 1000000 | 1000000 | 0 | 7500000
Lehigh Valley | 5 | Northampton | 117606 | SR 22/SR 191 Interchange Improvements | 22 | 15M | Highway Reconstruction | FD | STU | 2030-04-01 |  | 0 | 0 | 1000000 | 1000000 | 972144 | 0 | 0 | 0 | 0 | 2972144
Lehigh Valley | 5 | Northampton | 117606 | SR 22/SR 191 Interchange Improvements | 22 | 15M | Highway Reconstruction | FD | 581 | 2030-04-01 |  | 0 | 0 | 250000 | 250000 | 243036 | 0 | 0 | 0 | 0 | 743036
Lehigh Valley | 5 | Northampton | 117606 | SR 22/SR 191 Interchange Improvements | 22 | 15M | Highway Reconstruction | ROW | 581 | 2030-04-01 |  | 0 | 0 | 606318 | 1343682 | 1109560 | 0 | 0 | 0 | 0 | 3059560
Lehigh Valley | 5 | Northampton | 117606 | SR 22/SR 191 Interchange Improvements | 22 | 15M | Highway Reconstruction | UTL | NHPP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 463720 | 0 | 0 | 0 | 0 | 463720
Lehigh Valley | 5 | Northampton | 117606 | SR 22/SR 191 Interchange Improvements | 22 | 15M | Highway Reconstruction | UTL | 581 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 115930 | 0 | 0 | 0 | 0 | 115930
Lehigh Valley | 5 | Northampton | 117606 | SR 22/SR 191 Interchange Improvements | 22 | 15M | Highway Reconstruction | CON | NHPP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 4000000 | 4000000 | 0 | 9000000
Lehigh Valley | 5 | Northampton | 117606 | SR 22/SR 191 Interchange Improvements | 22 | 15M | Highway Reconstruction | CON | STP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 1500000 | 4000000 | 2000000 | 0 | 7500000
Lehigh Valley | 5 | Northampton | 117606 | SR 22/SR 191 Interchange Improvements | 22 | 15M | Highway Reconstruction | CON | STU | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 4000000 | 9068960 | 0 | 14068960
Lehigh Valley | 5 | Northampton | 117606 | SR 22/SR 191 Interchange Improvements | 22 | 15M | Highway Reconstruction | CON | 581 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 875000 | 3000000 | 3767240 | 0 | 7642240
Lehigh Valley | 5 | Northampton | 118069 | Hugh Moore Park Bridge Painting and Repairs | 7302 | HMP | Bridge Restoration | CON | BOF | 2026-03-26 | 2026-03-26 | 177991 | 602440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780431
Lehigh Valley | 5 | Northampton | 118069 | Hugh Moore Park Bridge Painting and Repairs | 7302 | HMP | Bridge Restoration | CON | SXF | 2026-03-26 | 2026-03-26 | 0 | 1616279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1616279
Lehigh Valley | 5 | Northampton | 118069 | Hugh Moore Park Bridge Painting and Repairs | 7302 | HMP | Bridge Restoration | CON | LOC | 2026-03-26 | 2026-03-26 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
Lehigh Valley | 5 | Northampton | 118435 | Easton/Lafayette College Ped Safety Project - Ph 3 | 2025 | LAF | Transportation Enhancement | CON | TAP | 2025-05-08 | 2025-05-08 | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93000
Lehigh Valley | 5 | Northampton | 119824 | Two Rivers Trail Gap 9A - South |  | TRS | Transportation Enhancement | CON | TAU | 2026-07-02 |  | 161756 | 165262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327018
Lehigh Valley | 5 | Northampton | 119940 | Lower Saucon Road over E. Branch of Saucon Creek | 2001 | 01B | Bridge Replacement | FD | BOF | 2027-01-14 |  | 682440 | 297047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 979487
Lehigh Valley | 5 | Northampton | 119940 | Lower Saucon Road over E. Branch of Saucon Creek | 2001 | 01B | Bridge Replacement | ROW | BOF | 2027-01-14 |  | 0 | 42436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42436
Lehigh Valley | 5 | Northampton | 119940 | Lower Saucon Road over E. Branch of Saucon Creek | 2001 | 01B | Bridge Replacement | ROW | 185 | 2027-01-14 |  | 0 | 10609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10609
Lehigh Valley | 5 | Northampton | 119940 | Lower Saucon Road over E. Branch of Saucon Creek | 2001 | 01B | Bridge Replacement | UTL | BOF | 2027-01-14 |  | 0 | 0 | 43708 | 0 | 0 | 0 | 0 | 0 | 0 | 43708
Lehigh Valley | 5 | Northampton | 119940 | Lower Saucon Road over E. Branch of Saucon Creek | 2001 | 01B | Bridge Replacement | UTL | 185 | 2027-01-14 |  | 0 | 0 | 10927 | 0 | 0 | 0 | 0 | 0 | 0 | 10927
Lehigh Valley | 5 | Northampton | 119940 | Lower Saucon Road over E. Branch of Saucon Creek | 2001 | 01B | Bridge Replacement | CON | BOF | 2027-01-14 |  | 0 | 0 | 500000 | 374160 | 0 | 0 | 0 | 0 | 0 | 874160
Lehigh Valley | 5 | Northampton | 119940 | Lower Saucon Road over E. Branch of Saucon Creek | 2001 | 01B | Bridge Replacement | CON | 185 | 2027-01-14 |  | 0 | 0 | 125000 | 93540 | 0 | 0 | 0 | 0 | 0 | 218540
Lehigh Valley | 5 | Northampton | 120949 | LVTS High Friction Surface - 2025 | 412 | HFS | Safety Improvement | CON | HSIP | 2025-07-10 | 2025-07-10 | 173840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173840
Lehigh Valley | 5 | Northampton | 120949 | LVTS High Friction Surface - 2025 | 412 | HFS | Safety Improvement | CON | HSIP | 2025-07-10 | 2025-07-10 | 0 | 0 | 440000 | 0 | 440000 | 0 | 440000 | 0 | 1760000 | 3080000
Lehigh Valley | 5 | Northampton | 120951 | LVTS All Weather Pavement Markers 2025 | 33 | AWT | Safety Improvement | CON | STP | 2025-03-13 | 2025-03-13 | 165688 | 0 | 400000 | 0 | 400000 | 0 | 400000 | 0 | 800000 | 2165688
Lehigh Valley | 5 | Northampton | 120952 | SR 248/Airport Road Intersection Improvements | 248 | 07S | Congestion Reduction | PE | CAQ | 2028-03-23 |  | 618000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618000
Lehigh Valley | 5 | Northampton | 120952 | SR 248/Airport Road Intersection Improvements | 248 | 07S | Congestion Reduction | PE | NHPP | 2028-03-23 |  | 27611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27611
Lehigh Valley | 5 | Northampton | 120952 | SR 248/Airport Road Intersection Improvements | 248 | 07S | Congestion Reduction | FD | CAQ | 2028-03-23 |  | 0 | 0 | 75000 | 88905 | 0 | 0 | 0 | 0 | 0 | 163905
Lehigh Valley | 5 | Northampton | 120952 | SR 248/Airport Road Intersection Improvements | 248 | 07S | Congestion Reduction | ROW | CAQ | 2028-03-23 |  | 0 | 0 | 300000 | 246350 | 0 | 0 | 0 | 0 | 0 | 546350
Lehigh Valley | 5 | Northampton | 120952 | SR 248/Airport Road Intersection Improvements | 248 | 07S | Congestion Reduction | UTL | CAQ | 2028-03-23 |  | 0 | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 56275
Lehigh Valley | 5 | Northampton | 120952 | SR 248/Airport Road Intersection Improvements | 248 | 07S | Congestion Reduction | CON | CAQ | 2028-03-23 |  | 0 | 0 | 0 | 0 | 1000000 | 2477900 | 0 | 0 | 0 | 3477900
Lehigh Valley | 5 | Northampton | 120954 | SR 191/Hecktown Rd/Hanover Rd Intersection Improve | 191 | 14M | Study Phase of Project | STUDY | 581 |  |  | 0 | 271111 | 13556 | 0 | 0 | 0 | 0 | 0 | 0 | 284667
Lehigh Valley | 5 | Northampton | 120966 | Bridge Overlay Bundle #3 | 33 | 0 | Bridge Preservation - Federal | PE | 581 | 2029-04-01 |  | 0 | 400000 | 130450 | 0 | 0 | 0 | 0 | 0 | 0 | 530450
Lehigh Valley | 5 | Northampton | 120966 | Bridge Overlay Bundle #3 | 33 | 0 | Bridge Preservation - Federal | CON | BRIP | 2029-04-01 |  | 0 | 0 | 0 | 0 | 3246040 | 0 | 0 | 0 | 0 | 3246040
Lehigh Valley | 5 | Northampton | 120966 | Bridge Overlay Bundle #3 | 33 | 0 | Bridge Preservation - Federal | CON | 581 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 811510 | 0 | 0 | 0 | 0 | 811510
Lehigh Valley | 5 | Northampton | 120973 | Carbon Reduction Monitoring and Evaluation Program |  |  | Congestion Reduction | STUDY | CRP |  |  | 0 | 0 | 281000 | 300000 | 0 | 0 | 0 | 0 | 0 | 581000
Lehigh Valley | 5 | Northampton | 120975 | St. John Street Improvements | 2005 | LSI | Safety Improvement | PE | STU | 2029-04-01 |  | 215412 | 227881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443293
Lehigh Valley | 5 | Northampton | 120975 | St. John Street Improvements | 2005 | LSI | Safety Improvement | FD | STU | 2029-04-01 |  | 0 | 0 | 150000 | 123175 | 0 | 0 | 0 | 0 | 0 | 273175
Lehigh Valley | 5 | Northampton | 120975 | St. John Street Improvements | 2005 | LSI | Safety Improvement | UTL | STU | 2029-04-01 |  | 0 | 0 | 0 | 0 | 86948 | 0 | 0 | 0 | 0 | 86948
Lehigh Valley | 5 | Northampton | 120975 | St. John Street Improvements | 2005 | LSI | Safety Improvement | CON | STU | 2029-04-01 |  | 0 | 0 | 0 | 0 | 150000 | 3096040 | 0 | 0 | 0 | 3246040
Lehigh Valley | 5 | Northampton | 120976 | Linden Street Two-Way Conversion |  | LSC | Congestion Reduction | PE | CAQ | 2026-06-04 |  | 206000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206000
Lehigh Valley | 5 | Northampton | 120976 | Linden Street Two-Way Conversion |  | LSC | Congestion Reduction | FD | CRP | 2026-06-04 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Lehigh Valley | 5 | Northampton | 120976 | Linden Street Two-Way Conversion |  | LSC | Congestion Reduction | CON | CRP | 2026-06-04 |  | 106000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106000
Lehigh Valley | 5 | Northampton | 120976 | Linden Street Two-Way Conversion |  | LSC | Congestion Reduction | CON | CRPU | 2026-06-04 |  | 1594000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1594000
Lehigh Valley | 5 | Northampton | 121551 | Youth Bike Education-Community Bike Works |  | YBE | Transportation Enhancement | CON | TAU | 2024-10-24 |  | 634122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634122
Lehigh Valley | 5 | Northampton | 121553 | Lehigh Canal Abbott Street Bridge |  |  | Bicycle Pedestrian Highway | CON | TAP | 2026-09-03 |  | 0 | 0 | 930118 | 0 | 0 | 0 | 0 | 0 | 0 | 930118
Lehigh Valley | 5 | Northampton | 122782 | South Bethlehem Greenway Trail Extension |  | SBE | Transportation Enhancement | CON | TAU | 2026-10-22 |  | 0 | 437000 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Lehigh Valley | 5 | Northampton | 122839 | Downtown Easton Intersection Improvements |  | EII | Transportation Enhancement | CON | TAU | 2026-11-05 |  | 0 | 197738 | 102262 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Lehigh Valley | 5 | Northampton | 122908 | Pearl Street Safety Improvements | 248 | PSI | MultiModal | CON | 411 |  |  | 83353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83353
Lehigh Valley | 5 | Northampton | 122908 | Pearl Street Safety Improvements | 248 | PSI | MultiModal | CON | LOC |  |  | 30008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30008
Lehigh Valley | 5 | Northampton | 123036 | Main Street and Polk Valley Road Improvements | 412 | MPI | Bicycle Pedestrian Highway | PE | CRPU | 2026-12-10 |  | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000
Lehigh Valley | 5 | Northampton | 123036 | Main Street and Polk Valley Road Improvements | 412 | MPI | Bicycle Pedestrian Highway | CON | CRPU | 2026-12-10 |  | 0 | 470000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470000
Lehigh Valley | 5 | Northampton | 123037 | Traffic Calming & Pedestrian Accommodation Improve | 248 | ETC | Transportation Enhancement | PE | CRPU | 2026-11-05 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Lehigh Valley | 5 | Northampton | 123037 | Traffic Calming & Pedestrian Accommodation Improve | 248 | ETC | Transportation Enhancement | CON | CRP | 2026-11-05 |  | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
Lehigh Valley | 5 | Northampton | 123037 | Traffic Calming & Pedestrian Accommodation Improve | 248 | ETC | Transportation Enhancement | CON | CRPU | 2026-11-05 |  | 0 | 350000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
NEPA | 4 | Pike | 9343 | SR 4003 over Masthope Creek | 4003 | 450 | Bridge Replacement | PE | BOF | 2027-08-26 |  | 560000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660000
NEPA | 4 | Pike | 9343 | SR 4003 over Masthope Creek | 4003 | 450 | Bridge Replacement | PE | 185 | 2027-08-26 |  | 140000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000
NEPA | 4 | Pike | 9343 | SR 4003 over Masthope Creek | 4003 | 450 | Bridge Replacement | FD | 185 | 2027-08-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
NEPA | 4 | Pike | 9343 | SR 4003 over Masthope Creek | 4003 | 450 | Bridge Replacement | CON | BOF | 2027-08-26 |  | 0 | 0 | 0 | 0 | 0 | 336000 | 0 | 0 | 0 | 336000
NEPA | 4 | Pike | 9343 | SR 4003 over Masthope Creek | 4003 | 450 | Bridge Replacement | CON | 581 | 2027-08-26 |  | 0 | 0 | 0 | 0 | 0 | 1344000 | 0 | 0 | 0 | 1344000
NEPA | 4 | Pike | 9354 | SR 4004 over Blooming Grove Creek | 4004 | 450 | Bridge Restoration | PE | BOF | 2027-10-14 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
NEPA | 4 | Pike | 9354 | SR 4004 over Blooming Grove Creek | 4004 | 450 | Bridge Restoration | PE | 185 | 2027-10-14 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
NEPA | 4 | Pike | 9354 | SR 4004 over Blooming Grove Creek | 4004 | 450 | Bridge Restoration | CON | BOF | 2027-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184000 | 184000
NEPA | 4 | Pike | 9354 | SR 4004 over Blooming Grove Creek | 4004 | 450 | Bridge Restoration | CON | 185 | 2027-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466000 | 466000
NEPA | 4 | Pike | 9354 | SR 4004 over Blooming Grove Creek | 4004 | 450 | Bridge Restoration | CON | 581 | 2027-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 1350000
NEPA | 4 | Pike | 9379 | SR 507 over Tributary to Lake Wallenpaupack 1 | 507 | 450 | Bridge Restoration | CON | STP | 2021-06-10 | 2021-06-10 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
NEPA | 4 | Pike | 9411 | SR 1006 over Shohola Creek | 1006 | D50 | Bridge Replacement | PE | BOF | 2027-06-24 |  | 200000 | 168000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368000
NEPA | 4 | Pike | 9411 | SR 1006 over Shohola Creek | 1006 | D50 | Bridge Replacement | PE | 185 | 2027-06-24 |  | 50000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000
NEPA | 4 | Pike | 9411 | SR 1006 over Shohola Creek | 1006 | D50 | Bridge Replacement | FD | BOF | 2027-06-24 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
NEPA | 4 | Pike | 9411 | SR 1006 over Shohola Creek | 1006 | D50 | Bridge Replacement | FD | 185 | 2027-06-24 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
NEPA | 4 | Pike | 9411 | SR 1006 over Shohola Creek | 1006 | D50 | Bridge Replacement | CON | BOF | 2027-06-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 1600000
NEPA | 4 | Pike | 9411 | SR 1006 over Shohola Creek | 1006 | D50 | Bridge Replacement | CON | 185 | 2027-06-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
NEPA | 4 | Pike | 9422 | SR 507 over Tributary to Lake Wallenpaupack 2 | 507 | 453 | Bridge Replacement | PE | BRIP | 2032-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
NEPA | 4 | Pike | 9422 | SR 507 over Tributary to Lake Wallenpaupack 2 | 507 | 453 | Bridge Replacement | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
NEPA | 4 | Pike | 9422 | SR 507 over Tributary to Lake Wallenpaupack 2 | 507 | 453 | Bridge Replacement | CON | STP | 2032-10-01 |  | 0 | 0 | 0 | 0 | 460000 | 0 | 0 | 0 | 0 | 460000
NEPA | 4 | Pike | 9422 | SR 507 over Tributary to Lake Wallenpaupack 2 | 507 | 453 | Bridge Replacement | CON | 581 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 115000 | 0 | 0 | 0 | 0 | 115000
NEPA | 4 | Pike | 67511 | SR 402 over Inlet to Pecks Pond | 402 | D50 | Bridge Replacement | PE | BRIP | 2032-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
NEPA | 4 | Pike | 67511 | SR 402 over Inlet to Pecks Pond | 402 | D50 | Bridge Replacement | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
NEPA | 4 | Pike | 67511 | SR 402 over Inlet to Pecks Pond | 402 | D50 | Bridge Replacement | CON | BRIP | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516120 | 0 | 516120
NEPA | 4 | Pike | 67511 | SR 402 over Inlet to Pecks Pond | 402 | D50 | Bridge Replacement | CON | 185 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129030 | 0 | 129030
NEPA | 4 | Pike | 68758 | SR 6 over Wallenpaupack Creek and PPand L Flume | 6 | 472 | Bridge Restoration | PE | STP | 2026-03-26 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
NEPA | 4 | Pike | 68758 | SR 6 over Wallenpaupack Creek and PPand L Flume | 6 | 472 | Bridge Restoration | FD | BRIP | 2026-03-26 |  | 130147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130147
NEPA | 4 | Pike | 68758 | SR 6 over Wallenpaupack Creek and PPand L Flume | 6 | 472 | Bridge Restoration | FD | STP | 2026-03-26 |  | 244853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244853
NEPA | 4 | Pike | 68758 | SR 6 over Wallenpaupack Creek and PPand L Flume | 6 | 472 | Bridge Restoration | ROW | 185 | 2026-03-26 |  | 125200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125200
NEPA | 4 | Pike | 68758 | SR 6 over Wallenpaupack Creek and PPand L Flume | 6 | 472 | Bridge Restoration | CON | BRIP | 2026-03-26 |  | 0 | 95000 | 775000 | 525000 | 0 | 0 | 0 | 0 | 0 | 1395000
NEPA | 4 | Pike | 68758 | SR 6 over Wallenpaupack Creek and PPand L Flume | 6 | 472 | Bridge Restoration | CON | NHPP | 2026-03-26 |  | 1600000 | 0 | 300000 | 200000 | 190000 | 0 | 0 | 0 | 0 | 2290000
NEPA | 4 | Pike | 68758 | SR 6 over Wallenpaupack Creek and PPand L Flume | 6 | 472 | Bridge Restoration | CON | STP | 2026-03-26 |  | 0 | 0 | 375630 | 649370 | 0 | 0 | 0 | 0 | 0 | 1025000
NEPA | 4 | Pike | 68758 | SR 6 over Wallenpaupack Creek and PPand L Flume | 6 | 472 | Bridge Restoration | CON | SXF | 2026-03-26 |  | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
NEPA | 4 | Pike | 68758 | SR 6 over Wallenpaupack Creek and PPand L Flume | 6 | 472 | Bridge Restoration | CON | 185 | 2026-03-26 |  | 0 | 0 | 75000 | 538750 | 0 | 200000 | 0 | 0 | 0 | 813750
NEPA | 4 | Pike | 68758 | SR 6 over Wallenpaupack Creek and PPand L Flume | 6 | 472 | Bridge Restoration | CON | 581 | 2026-03-26 |  | 775000 | 1155000 | 1350000 | 1700000 | 992000 | 0 | 0 | 0 | 0 | 5972000
NEPA | 4 | Pike | 68790 | SR 6 over Sawkill Creek | 6 | 474 | Bridge Replacement | PE | BRIP | 2027-03-11 |  | 49843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49843
NEPA | 4 | Pike | 68790 | SR 6 over Sawkill Creek | 6 | 474 | Bridge Replacement | PE | STP | 2027-03-11 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
NEPA | 4 | Pike | 68790 | SR 6 over Sawkill Creek | 6 | 474 | Bridge Replacement | PE | 185 | 2027-03-11 |  | 12461 | 6250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18711
NEPA | 4 | Pike | 68790 | SR 6 over Sawkill Creek | 6 | 474 | Bridge Replacement | FD | STP | 2027-03-11 |  | 0 | 24000 | 276000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
NEPA | 4 | Pike | 68790 | SR 6 over Sawkill Creek | 6 | 474 | Bridge Replacement | FD | 185 | 2027-03-11 |  | 0 | 6000 | 69000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
NEPA | 4 | Pike | 68790 | SR 6 over Sawkill Creek | 6 | 474 | Bridge Replacement | CON | STP | 2027-03-11 |  | 0 | 0 | 0 | 0 | 80000 | 1264000 | 0 | 0 | 0 | 1344000
NEPA | 4 | Pike | 68790 | SR 6 over Sawkill Creek | 6 | 474 | Bridge Replacement | CON | 185 | 2027-03-11 |  | 0 | 0 | 0 | 0 | 20000 | 316000 | 0 | 0 | 0 | 336000
NEPA | 4 | Pike | 68813 | SR 209 over Sawkill Creek | 209 | 450 | Bridge Restoration | CON | BRIP | 2024-02-15 | 2024-02-15 | 0 | 4674061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4674061
NEPA | 4 | Pike | 68813 | SR 209 over Sawkill Creek | 209 | 450 | Bridge Restoration | CON | NHPP | 2024-02-15 | 2024-02-15 | 0 | 1245700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1245700
NEPA | 4 | Pike | 68813 | SR 209 over Sawkill Creek | 209 | 450 | Bridge Restoration | CON | STP | 2024-02-15 | 2024-02-15 | 597371 | 855468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1452839
NEPA | 4 | Pike | 68813 | SR 209 over Sawkill Creek | 209 | 450 | Bridge Restoration | CON | 185 | 2024-02-15 | 2024-02-15 | 0 | 375000 | 1468150 | 0 | 0 | 0 | 0 | 0 | 0 | 1843150
NEPA | 4 | Pike | 68837 | SR 402 over Shohola Creek | 402 | 472 | Bridge Replacement | PE | BRIP | 2032-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
NEPA | 4 | Pike | 68837 | SR 402 over Shohola Creek | 402 | 472 | Bridge Replacement | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
NEPA | 4 | Pike | 68837 | SR 402 over Shohola Creek | 402 | 472 | Bridge Replacement | CON | BRIP | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 408000 | 0 | 0 | 408000
NEPA | 4 | Pike | 68837 | SR 402 over Shohola Creek | 402 | 472 | Bridge Replacement | CON | 185 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 102000 | 0 | 0 | 102000
NEPA | 4 | Pike | 68843 | SR 434 over Branch Ballard Creek | 434 | 473 | Bridge Replacement | PE | 185 | 2027-07-29 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
NEPA | 4 | Pike | 68843 | SR 434 over Branch Ballard Creek | 434 | 473 | Bridge Replacement | FD | STP | 2027-07-29 |  | 0 | 276000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276000
NEPA | 4 | Pike | 68843 | SR 434 over Branch Ballard Creek | 434 | 473 | Bridge Replacement | FD | 185 | 2027-07-29 |  | 0 | 69000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69000
NEPA | 4 | Pike | 68843 | SR 434 over Branch Ballard Creek | 434 | 473 | Bridge Replacement | CON | STP | 2027-07-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1264000 | 80000 | 0 | 1344000
NEPA | 4 | Pike | 68843 | SR 434 over Branch Ballard Creek | 434 | 473 | Bridge Replacement | CON | 185 | 2027-07-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 316000 | 20000 | 0 | 336000
NEPA | 4 | Pike | 68869 | SR 1014 over Westcolang Creek | 1014 | 470 | Bridge Replacement | FD | BOF | 2027-02-11 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
NEPA | 4 | Pike | 68869 | SR 1014 over Westcolang Creek | 1014 | 470 | Bridge Replacement | FD | 185 | 2027-02-11 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
NEPA | 4 | Pike | 68869 | SR 1014 over Westcolang Creek | 1014 | 470 | Bridge Replacement | CON | BOF | 2027-02-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 1350000
NEPA | 4 | Pike | 68869 | SR 1014 over Westcolang Creek | 1014 | 470 | Bridge Replacement | CON | 185 | 2027-02-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337500 | 337500
NEPA | 4 | Pike | 68878 | SR 3001 over East Branch of Wallenpaupack Creek | 3001 | 470 | Bridge Replacement | PE | BOF | 2032-10-10 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
NEPA | 4 | Pike | 68878 | SR 3001 over East Branch of Wallenpaupack Creek | 3001 | 470 | Bridge Replacement | PE | 185 | 2032-10-10 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
NEPA | 4 | Pike | 68878 | SR 3001 over East Branch of Wallenpaupack Creek | 3001 | 470 | Bridge Replacement | CON | BOF | 2032-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 784000 | 0 | 784000
NEPA | 4 | Pike | 68878 | SR 3001 over East Branch of Wallenpaupack Creek | 3001 | 470 | Bridge Replacement | CON | 185 | 2032-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 300000
NEPA | 4 | Pike | 68878 | SR 3001 over East Branch of Wallenpaupack Creek | 3001 | 470 | Bridge Replacement | CON | 581 | 2032-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416000 | 0 | 416000
NEPA | 4 | Pike | 68893 | SR 4004 over Outlet to Fairview Lake | 4004 | 470 | Bridge Replacement | PE | BOF | 2030-10-01 |  | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
NEPA | 4 | Pike | 68893 | SR 4004 over Outlet to Fairview Lake | 4004 | 470 | Bridge Replacement | PE | 185 | 2030-10-01 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
NEPA | 4 | Pike | 68893 | SR 4004 over Outlet to Fairview Lake | 4004 | 470 | Bridge Replacement | CON | BOF | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 200000
NEPA | 4 | Pike | 68893 | SR 4004 over Outlet to Fairview Lake | 4004 | 470 | Bridge Replacement | CON | 581 | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 0 | 0 | 800000
NEPA | 4 | Pike | 73295 | NEPA 4-0 Highway Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 16000 | 396000 | 484000 | 2000 | 784000 | 123500 | 8500 | 0 | 0 | 1814000
NEPA | 4 | Pike | 73295 | NEPA 4-0 Highway Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 18010 | 2000 | 3000 | 13000 | 98000 | 78000 | 270000 | 261880 | 2430000 | 3173890
NEPA | 4 | Pike | 73295 | NEPA 4-0 Highway Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 171166 | 184966 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 842000 | 2458132
NEPA | 4 | Pike | 73295 | NEPA 4-0 Highway Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 255011 | 655500 | 805500 | 805500 | 805500 | 805500 | 805500 | 805500 | 3222000 | 8965511
NEPA | 4 | Pike | 73295 | NEPA 4-0 Highway Line Item |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 115000 | 7000 | 27000 | 7000 | 197000 | 277000 | 277000 | 1109000 | 2016000
NEPA | 4 | Pike | 73295 | NEPA 4-0 Highway Line Item |  |  | Reserve Line Item | CON | STP |  |  | 13920 | 841 | 17000 | 507630 | 737000 | 13000 | 13000 | 397000 | 1770000 | 3469391
NEPA | 4 | Pike | 73295 | NEPA 4-0 Highway Line Item |  |  | Reserve Line Item | CON | 185 |  |  | 16339 | 32750 | 274000 | 13750 | 798000 | 126000 | 374000 | 167970 | 1084500 | 2887309
NEPA | 4 | Pike | 73295 | NEPA 4-0 Highway Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 6480 | 3000 | 18250 | 1000 | 380250 | 25875 | 989625 | 1430000 | 2032000 | 4886480
NEPA | 4 | Pike | 79543 | SR 447 over Wallenpaupack Creek | 447 | 450 | Bridge Restoration | CON | BOF | 2024-06-13 | 2024-07-11 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
NEPA | 4 | Pike | 79543 | SR 447 over Wallenpaupack Creek | 447 | 450 | Bridge Restoration | CON | 185 | 2024-06-13 | 2024-07-11 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
NEPA | 4 | Pike | 85737 | SR 2004 over Little Bushkill Creek | 2004 | D50 | Bridge Restoration | PE | BOF | 2029-01-04 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
NEPA | 4 | Pike | 85737 | SR 2004 over Little Bushkill Creek | 2004 | D50 | Bridge Restoration | PE | 185 | 2029-01-04 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
NEPA | 4 | Pike | 85737 | SR 2004 over Little Bushkill Creek | 2004 | D50 | Bridge Restoration | CON | BOF | 2029-01-04 |  | 0 | 0 | 100000 | 742000 | 0 | 0 | 0 | 0 | 0 | 842000
NEPA | 4 | Pike | 85737 | SR 2004 over Little Bushkill Creek | 2004 | D50 | Bridge Restoration | CON | 185 | 2029-01-04 |  | 0 | 0 | 25000 | 185500 | 0 | 0 | 0 | 0 | 0 | 210500
NEPA | 4 | Pike | 86916 | NEPA 4-0 Project Delivery |  |  | Highway Restoration | PE | 185 |  |  | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
NEPA | 4 | Pike | 89017 | SR 6 over Delaware River | 6 | 451 | Bridge Restoration | CON | BRIP | 2024-07-11 | 2024-07-11 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
NEPA | 4 | Pike | 89017 | SR 6 over Delaware River | 6 | 451 | Bridge Restoration | CON | 185 | 2024-07-11 | 2024-07-11 | 0 | 0 | 285000 | 0 | 0 | 0 | 0 | 0 | 0 | 285000
NEPA | 4 | Pike | 89017 | SR 6 over Delaware River | 6 | 451 | Bridge Restoration | CON | LOC | 2024-07-11 | 2024-07-11 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
NEPA | 4 | Pike | 94304 | SR 390 over Outlet Promised Land Lake | 390 | D50 | Bridge Replacement | CON | BRIP | 2024-12-12 | 2024-12-12 | 500000 | 680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1180000
NEPA | 4 | Pike | 94304 | SR 390 over Outlet Promised Land Lake | 390 | D50 | Bridge Replacement | CON | STP | 2024-12-12 | 2024-12-12 | 3607841 | 552159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4160000
NEPA | 4 | Pike | 94304 | SR 390 over Outlet Promised Land Lake | 390 | D50 | Bridge Replacement | CON | 185 | 2024-12-12 | 2024-12-12 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
NEPA | 4 | Pike | 94304 | SR 390 over Outlet Promised Land Lake | 390 | D50 | Bridge Replacement | CON | 581 | 2024-12-12 | 2024-12-12 | 412500 | 320000 | 208750 | 125000 | 168750 | 0 | 0 | 0 | 0 | 1235000
NEPA | 4 | Pike | 94686 | SR 739 Should / Widening | 739 | WID | Safety Improvement | UTL | HSIP | 2022-09-15 | 2022-09-15 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
NEPA | 4 | Pike | 94686 | SR 739 Should / Widening | 739 | WID | Safety Improvement | CON | HSIP | 2022-09-15 | 2022-09-15 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
NEPA | 4 | Pike | 94686 | SR 739 Should / Widening | 739 | WID | Safety Improvement | CON | STP | 2022-09-15 | 2022-09-15 | 0 | 312600 | 449370 | 0 | 0 | 0 | 0 | 0 | 0 | 761970
NEPA | 4 | Pike | 102029 | SR 447 Slide | 447 | D51 | Highway Restoration | PE | 581 | 2032-10-01 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
NEPA | 4 | Pike | 102029 | SR 447 Slide | 447 | D51 | Highway Restoration | CON | 581 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 287500 | 0 | 0 | 287500
NEPA | 4 | Pike | 107968 | MEC Phase 14 - Completing the Connection | 6 | TAP | Transportation Enhancement | CON | STP | 2023-03-02 | 2023-03-02 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000
NEPA | 4 | Pike | 114072 | Asset Management Phase 3 |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 80000
NEPA | 4 | Pike | 114072 | Asset Management Phase 3 |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
NEPA | 4 | Pike | 114074 | Asset Management Phase 4 |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 80000
NEPA | 4 | Pike | 114074 | Asset Management Phase 4 |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
NEPA | 4 | Pike | 114547 | SR 2001 Section (405) Reconstruct | 2001 | 405 | Highway Reconstruction | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
NEPA | 4 | Pike | 114547 | SR 2001 Section (405) Reconstruct | 2001 | 405 | Highway Reconstruction | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
NEPA | 4 | Pike | 115820 | SR 1002 over Greeley Lake | 1002 | 451 | Bridge Replacement | CON | 581 |  |  | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
NEPA | 4 | Pike | 116059 | Shohola Falls Road over Balliard Creek | 7210 | 457 | Bridge Replacement | FD | STP | 2026-10-01 |  | 209000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209000
NEPA | 4 | Pike | 116059 | Shohola Falls Road over Balliard Creek | 7210 | 457 | Bridge Replacement | ROW | STP | 2026-10-01 |  | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000
NEPA | 4 | Pike | 116059 | Shohola Falls Road over Balliard Creek | 7210 | 457 | Bridge Replacement | UTL | STP | 2026-10-01 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
NEPA | 4 | Pike | 116059 | Shohola Falls Road over Balliard Creek | 7210 | 457 | Bridge Replacement | CON | STP | 2026-10-01 |  | 0 | 728000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728000
NEPA | 4 | Pike | 116060 | Carlton Hill Road over Taylor Creek | 7204 | 456 | Bridge Replacement | PE | STP | 2027-06-10 |  | 0 | 23450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23450
NEPA | 4 | Pike | 116060 | Carlton Hill Road over Taylor Creek | 7204 | 456 | Bridge Replacement | FD | STP | 2027-06-10 |  | 166000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166000
NEPA | 4 | Pike | 116060 | Carlton Hill Road over Taylor Creek | 7204 | 456 | Bridge Replacement | ROW | STP | 2027-06-10 |  | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
NEPA | 4 | Pike | 116060 | Carlton Hill Road over Taylor Creek | 7204 | 456 | Bridge Replacement | UTL | STP | 2027-06-10 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
NEPA | 4 | Pike | 116060 | Carlton Hill Road over Taylor Creek | 7204 | 456 | Bridge Replacement | CON | STP | 2027-06-10 |  | 0 | 211000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211000
NEPA | 4 | Pike | 116060 | Carlton Hill Road over Taylor Creek | 7204 | 456 | Bridge Replacement | CON | 411 | 2027-06-10 |  | 0 | 517176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517176
NEPA | 4 | Pike | 116060 | Carlton Hill Road over Taylor Creek | 7204 | 456 | Bridge Replacement | CON | LOC | 2027-06-10 |  | 0 | 58406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58406
NEPA | 4 | Pike | 116691 | SR 6 over Decker Creek | 6 | 455 | Bridge Restoration | PE | NHPP | 2033-10-01 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
NEPA | 4 | Pike | 116691 | SR 6 over Decker Creek | 6 | 455 | Bridge Restoration | CON | BRIP | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 700000 | 100000 | 0 | 0 | 800000
NEPA | 4 | Pike | 116691 | SR 6 over Decker Creek | 6 | 455 | Bridge Restoration | CON | 185 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 175000 | 25000 | 0 | 0 | 200000
NEPA | 4 | Pike | 116692 | SR 6 over Spring Brook | 6 | 456 | Bridge Replacement | PE | NHPP | 2027-10-07 |  | 0 | 385000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385000
NEPA | 4 | Pike | 116692 | SR 6 over Spring Brook | 6 | 456 | Bridge Replacement | CON | BRIP | 2027-10-07 |  | 0 | 0 | 0 | 0 | 680000 | 0 | 0 | 0 | 0 | 680000
NEPA | 4 | Pike | 116692 | SR 6 over Spring Brook | 6 | 456 | Bridge Replacement | CON | 581 | 2027-10-07 |  | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 170000
NEPA | 4 | Pike | 116693 | SR 402 over Outlet to Porters Lake | 402 | 450 | Bridge Restoration | PE | BRIP | 2034-10-01 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
NEPA | 4 | Pike | 116693 | SR 402 over Outlet to Porters Lake | 402 | 450 | Bridge Restoration | PE | 185 | 2034-10-01 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
NEPA | 4 | Pike | 116693 | SR 402 over Outlet to Porters Lake | 402 | 450 | Bridge Restoration | CON | BRIP | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680000 | 680000
NEPA | 4 | Pike | 116693 | SR 402 over Outlet to Porters Lake | 402 | 450 | Bridge Restoration | CON | 185 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 170000
NEPA | 4 | Pike | 116694 | SR 402 over Indian Cabin Run | 402 | 451 | Bridge Restoration | PE | STP | 2034-10-01 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
NEPA | 4 | Pike | 116694 | SR 402 over Indian Cabin Run | 402 | 451 | Bridge Restoration | PE | 185 | 2034-10-01 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
NEPA | 4 | Pike | 116694 | SR 402 over Indian Cabin Run | 402 | 451 | Bridge Restoration | CON | STP | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
NEPA | 4 | Pike | 116694 | SR 402 over Indian Cabin Run | 402 | 451 | Bridge Restoration | CON | 185 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
NEPA | 4 | Pike | 116695 | SR 1003 over Taylortown Creek | 1003 | 451 | Bridge Restoration | PE | BOF | 2034-10-01 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
NEPA | 4 | Pike | 116695 | SR 1003 over Taylortown Creek | 1003 | 451 | Bridge Restoration | PE | 185 | 2034-10-01 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
NEPA | 4 | Pike | 116695 | SR 1003 over Taylortown Creek | 1003 | 451 | Bridge Restoration | CON | BOF | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 224500 | 675500 | 0 | 0 | 900000
NEPA | 4 | Pike | 116695 | SR 1003 over Taylortown Creek | 1003 | 451 | Bridge Restoration | CON | 581 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 56125 | 168875 | 0 | 0 | 225000
NEPA | 4 | Pike | 116701 | SR 1017 over Trib to Delaware River | 1017 | 450 | Bridge Restoration | PE | STP | 2034-10-01 |  | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
NEPA | 4 | Pike | 116701 | SR 1017 over Trib to Delaware River | 1017 | 450 | Bridge Restoration | PE | 185 | 2034-10-01 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
NEPA | 4 | Pike | 116701 | SR 1017 over Trib to Delaware River | 1017 | 450 | Bridge Restoration | CON | STP | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680000 | 680000
NEPA | 4 | Pike | 116701 | SR 1017 over Trib to Delaware River | 1017 | 450 | Bridge Restoration | CON | 185 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 170000
NEPA | 4 | Pike | 116734 | SR 2001 over Hornbeck Creek | 2001 | 452 | Bridge Restoration | PE | STP | 2034-10-01 |  | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
NEPA | 4 | Pike | 116734 | SR 2001 over Hornbeck Creek | 2001 | 452 | Bridge Restoration | PE | 185 | 2034-10-01 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
NEPA | 4 | Pike | 116734 | SR 2001 over Hornbeck Creek | 2001 | 452 | Bridge Restoration | CON | STP | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960000 | 960000
NEPA | 4 | Pike | 116734 | SR 2001 over Hornbeck Creek | 2001 | 452 | Bridge Restoration | CON | 185 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 240000
NEPA | 4 | Pike | 117287 | Asset Management Phase 1 | 1002 | AST | Reserve Line Item | CON | STP | 2030-10-01 |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80
NEPA | 4 | Pike | 117287 | Asset Management Phase 1 | 1002 | AST | Reserve Line Item | CON | 581 | 2030-10-01 |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
NEPA | 4 | Pike | 117288 | Asset Management Phase 2 | 1009 | CBR | Reserve Line Item | PE | 581 |  |  | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
NEPA | 4 | Pike | 117288 | Asset Management Phase 2 | 1009 | CBR | Reserve Line Item | CON | STP |  |  | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 800000 | 0 | 920000
NEPA | 4 | Pike | 117288 | Asset Management Phase 2 | 1009 | CBR | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 200000 | 0 | 210000
NEPA | 4 | Pike | 117288 | Asset Management Phase 2 | 1009 | CBR | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
NEPA | 4 | Pike | 121175 | SR 390 High Friction Surface Treatment | 390 | HFS | Safety Improvement | CON | HSIP | 2026-05-07 |  | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
NEPA | 4 | Pike | 121175 | SR 390 High Friction Surface Treatment | 390 | HFS | Safety Improvement | CON | HSIP | 2026-05-07 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
NEPA | 4 | Pike | 121294 | I-84 Cameras - Pike County | 84 | CAM | Intelligent Transportation System | PE | CRP | 2025-10-09 | 2025-10-09 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
NEPA | 4 | Pike | 121294 | I-84 Cameras - Pike County | 84 | CAM | Intelligent Transportation System | PE | CRP | 2025-10-09 | 2025-10-09 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
NEPA | 4 | Pike | 121294 | I-84 Cameras - Pike County | 84 | CAM | Intelligent Transportation System | FD | CRP | 2025-10-09 | 2025-10-09 | 23200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23200
NEPA | 4 | Pike | 121294 | I-84 Cameras - Pike County | 84 | CAM | Intelligent Transportation System | FD | CRP | 2025-10-09 | 2025-10-09 | 5800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5800
NEPA | 4 | Pike | 121294 | I-84 Cameras - Pike County | 84 | CAM | Intelligent Transportation System | CON | CRP | 2025-10-09 | 2025-10-09 | 80797 | 100135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180932
NEPA | 4 | Pike | 121294 | I-84 Cameras - Pike County | 84 | CAM | Intelligent Transportation System | CON | CRP | 2025-10-09 | 2025-10-09 | 25034 | 25034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50068
NEPA | 4 | Pike | 121416 | SR 6 & 434 Intersection Improvement | 6 | SAF | Safety Improvement | PE | HSIP | 2028-08-08 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
NEPA | 4 | Pike | 121500 | SR 6 over Delaware River Phase II | 6 | 457 | Bridge Restoration | CON | SXF | 2027-09-16 |  | 400000 | 580000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980000
NEPA | 4 | Pike | 121500 | SR 6 over Delaware River Phase II | 6 | 457 | Bridge Restoration | CON | 185 | 2027-09-16 |  | 100000 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245000
NEPA | 4 | Pike | 122495 | ROW Claims Assistance - NEPA |  |  | Reserve Line Item | ROW | 581 |  |  | 20000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
NEPA | 5 | Carbon | 11013 | Country Club Road over Mahoning Creek | 3005 | 01B | Bridge Replacement | CON | BOF | 2025-09-25 | 2025-09-25 | 0 | 1750485 | 168836 | 0 | 0 | 0 | 0 | 0 | 0 | 1919321
NEPA | 5 | Carbon | 66296 | 443 Roadway Improvements | 443 | 02S | Congestion Reduction | CON | CAQ | 2020-09-03 | 2020-09-03 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
NEPA | 5 | Carbon | 70239 | Urban Line Item Reserve |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 1180208 | 1329000 | 1329000 | 1329000 | 1329000 | 1329000 | 1329000 | 5314000 | 14468208
NEPA | 5 | Carbon | 75578 | Safety Line Item Reserve |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 0 | 29010 | 29305 | 131175 | 59487 | 1125994 | 2521000 | 9756652 | 13652623
NEPA | 5 | Carbon | 80074 | NEPA In-house Bridge Design Assistance |  |  | Bridge Replacement | PE | 185 |  |  | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
NEPA | 5 | Carbon | 82784 | CMAQ Line Item Reserve |  |  | Reserve Line Item | CON | CAQ |  |  | 0 | 0 | 526850 | 551000 | 551000 | 551000 | 551000 | 551000 | 2202000 | 5483850
NEPA | 5 | Carbon | 83087 | Delivery_Consult Assist |  | DCA | Preventive Maintenance | PE | 581 |  |  | 1500000 | 1500000 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 6000000
NEPA | 5 | Carbon | 89057 | Transp Enhance/Alternative Project Mngmt |  | TEM | Transportation Enhancement | PE | STP |  |  | 56000 | 105000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 211000
NEPA | 5 | Carbon | 91990 | US 209 over NRR | 209 | 13B | Bridge Restoration | CON | 581 | 2024-11-07 | 2024-11-07 | 1568378 | 95581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1663959
NEPA | 5 | Carbon | 94235 | Hudson Drive (SR 93) over Quakake Ck Br | 93 | HDB | Bridge Replacement | PE | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 393568 | 0 | 0 | 393568
NEPA | 5 | Carbon | 94235 | Hudson Drive (SR 93) over Quakake Ck Br | 93 | HDB | Bridge Replacement | PE | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 98392 | 0 | 0 | 98392
NEPA | 5 | Carbon | 94235 | Hudson Drive (SR 93) over Quakake Ck Br | 93 | HDB | Bridge Replacement | FD | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304032 | 0 | 304032
NEPA | 5 | Carbon | 94235 | Hudson Drive (SR 93) over Quakake Ck Br | 93 | HDB | Bridge Replacement | FD | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76008 | 0 | 76008
NEPA | 5 | Carbon | 94235 | Hudson Drive (SR 93) over Quakake Ck Br | 93 | HDB | Bridge Replacement | ROW | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25336 | 0 | 25336
NEPA | 5 | Carbon | 94235 | Hudson Drive (SR 93) over Quakake Ck Br | 93 | HDB | Bridge Replacement | ROW | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6334 | 0 | 6334
NEPA | 5 | Carbon | 94235 | Hudson Drive (SR 93) over Quakake Ck Br | 93 | HDB | Bridge Replacement | UTL | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26096 | 26096
NEPA | 5 | Carbon | 94235 | Hudson Drive (SR 93) over Quakake Ck Br | 93 | HDB | Bridge Replacement | UTL | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6524 | 6524
NEPA | 5 | Carbon | 94235 | Hudson Drive (SR 93) over Quakake Ck Br | 93 | HDB | Bridge Replacement | CON | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1957200 | 1957200
NEPA | 5 | Carbon | 96416 | Hunters Creek Bridge | 2002 | 03B | Bridge Replacement | FD | BRIP | 2027-03-25 |  | 0 | 640965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640965
NEPA | 5 | Carbon | 96416 | Hunters Creek Bridge | 2002 | 03B | Bridge Replacement | UTL | STP | 2027-03-25 |  | 0 | 0 | 106090 | 0 | 0 | 0 | 0 | 0 | 0 | 106090
NEPA | 5 | Carbon | 96416 | Hunters Creek Bridge | 2002 | 03B | Bridge Replacement | CON | BRIP | 2027-03-25 |  | 0 | 0 | 0 | 23464 | 0 | 0 | 0 | 0 | 0 | 23464
NEPA | 5 | Carbon | 96416 | Hunters Creek Bridge | 2002 | 03B | Bridge Replacement | CON | STP | 2027-03-25 |  | 0 | 0 | 0 | 995000 | 0 | 0 | 0 | 0 | 0 | 995000
NEPA | 5 | Carbon | 96416 | Hunters Creek Bridge | 2002 | 03B | Bridge Replacement | CON | 581 | 2027-03-25 |  | 0 | 0 | 0 | 254616 | 0 | 0 | 0 | 0 | 0 | 254616
NEPA | 5 | Carbon | 96418 | PA 248 PM Wall | 248 | PMW | Highway Reconstruction | PE | 581 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 895575 | 0 | 0 | 0 | 895575
NEPA | 5 | Carbon | 96418 | PA 248 PM Wall | 248 | PMW | Highway Reconstruction | FD | 581 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538390 | 0 | 538390
NEPA | 5 | Carbon | 96418 | PA 248 PM Wall | 248 | PMW | Highway Reconstruction | ROW | NHPP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126680 | 0 | 126680
NEPA | 5 | Carbon | 96418 | PA 248 PM Wall | 248 | PMW | Highway Reconstruction | ROW | 581 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31670 | 0 | 31670
NEPA | 5 | Carbon | 96418 | PA 248 PM Wall | 248 | PMW | Highway Reconstruction | UTL | NHPP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10440 | 10440
NEPA | 5 | Carbon | 96418 | PA 248 PM Wall | 248 | PMW | Highway Reconstruction | UTL | 581 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2610 | 2610
NEPA | 5 | Carbon | 96418 | PA 248 PM Wall | 248 | PMW | Highway Reconstruction | CON | NHPP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6461372 | 6461372
NEPA | 5 | Carbon | 96418 | PA 248 PM Wall | 248 | PMW | Highway Reconstruction | CON | 581 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1615343 | 1615343
NEPA | 5 | Carbon | 96419 | PA 309 Rehabilitation | 309 | 01M | Highway Restoration | PE | 581 | 2028-04-01 |  | 0 | 0 | 54635 | 0 | 0 | 0 | 0 | 0 | 0 | 54635
NEPA | 5 | Carbon | 96419 | PA 309 Rehabilitation | 309 | 01M | Highway Restoration | CON | 581 | 2028-04-01 |  | 0 | 0 | 0 | 562750 | 0 | 0 | 0 | 0 | 0 | 562750
NEPA | 5 | Carbon | 96436 | 903 Resurf. Old Stage Rd. to Lake Harmony Rd. | 903 | 06M | Highway Restoration | PE | 581 | 2029-04-01 |  | 0 | 0 | 200000 | 346350 | 0 | 0 | 0 | 0 | 0 | 546350
NEPA | 5 | Carbon | 96436 | 903 Resurf. Old Stage Rd. to Lake Harmony Rd. | 903 | 06M | Highway Restoration | CON | 581 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 1000000 | 2709760 | 0 | 0 | 0 | 3709760
NEPA | 5 | Carbon | 96437 | PA 940 Resurface | 940 | 04P | Highway Restoration | PE | 581 | 2029-04-01 |  | 0 | 0 | 300000 | 246350 | 0 | 0 | 0 | 0 | 0 | 546350
NEPA | 5 | Carbon | 96437 | PA 940 Resurface | 940 | 04P | Highway Restoration | CON | 581 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 1250000 | 1184530 | 0 | 0 | 0 | 2434530
NEPA | 5 | Carbon | 97326 | Environmental Impacts Resolution LI |  | EIR | Planning/Research/Administration | PE | 581 |  |  | 125000 | 125000 | 125000 | 127295 | 0 | 0 | 0 | 0 | 0 | 502295
NEPA | 5 | Carbon | 97421 | Construction Assistance |  | CAS | Reserve Line Item | CON | 581 | 2021-09-30 |  | 75000 | 75000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 250000
NEPA | 5 | Carbon | 97944 | Construction Assistance |  | CAF | Reserve Line Item | CON | STP |  |  | 75000 | 75000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 250000
NEPA | 5 | Carbon | 102240 | NEPA Hwy & Bridge Reserve |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 1497599 | 102060 | 0 | 305637 | 998933 | 4159240 | 4337668 | 18700000 | 30101137
NEPA | 5 | Carbon | 102240 | NEPA Hwy & Bridge Reserve |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 1419626 | 92584 | 61836 | 353256 | 1204950 | 4946000 | 4946000 | 19787000 | 32811252
NEPA | 5 | Carbon | 102240 | NEPA Hwy & Bridge Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 2997015 | 269828 | 2742509 | 4828176 | 4856000 | 4118060 | 4729320 | 10202716 | 34743624
NEPA | 5 | Carbon | 102240 | NEPA Hwy & Bridge Reserve |  |  | Reserve Line Item | CON | STP |  |  | 0 | 1370821 | 28569 | 516388 | 236600 | 2197140 | 70343 | 4029148 | 17696316 | 26145325
NEPA | 5 | Carbon | 102240 | NEPA Hwy & Bridge Reserve |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 337604 | 274689 | 215 | 324100 | 2269000 | 3269700 | 2009000 | 6979400 | 15463708
NEPA | 5 | Carbon | 102240 | NEPA Hwy & Bridge Reserve |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 228398 | 506890 | 896685 | 224772 | 541078 | 140960 | 9841824 | 47339308 | 59719915
NEPA | 5 | Carbon | 102762 | NEPA Traffic ReviewAssist |  |  | Preventive Maintenance | PE | 581 |  |  | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 200000
NEPA | 5 | Carbon | 109540 | Jim Thorpe Wall Rehabilitation | 209 | RWR | Highway Restoration | CON | NHPP | 2025-02-27 | 2025-02-27 | 6723384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6723384
NEPA | 5 | Carbon | 109540 | Jim Thorpe Wall Rehabilitation | 209 | RWR | Highway Restoration | CON | STP | 2025-02-27 | 2025-02-27 | 915580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 915580
NEPA | 5 | Carbon | 109540 | Jim Thorpe Wall Rehabilitation | 209 | RWR | Highway Restoration | CON | 581 | 2025-02-27 | 2025-02-27 | 899827 | 1009914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1909741
NEPA | 5 | Carbon | 109967 | 903 over Mud Run | 903 | 04B | Bridge Replacement | FD | 185 | 2026-06-04 |  | 0 | 25598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25598
NEPA | 5 | Carbon | 109967 | 903 over Mud Run | 903 | 04B | Bridge Replacement | UTL | STP | 2026-06-04 |  | 0 | 261444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261444
NEPA | 5 | Carbon | 109967 | 903 over Mud Run | 903 | 04B | Bridge Replacement | UTL | 581 | 2026-06-04 |  | 0 | 65361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65361
NEPA | 5 | Carbon | 109967 | 903 over Mud Run | 903 | 04B | Bridge Replacement | CON | BRIP | 2026-06-04 |  | 0 | 848720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 848720
NEPA | 5 | Carbon | 109967 | 903 over Mud Run | 903 | 04B | Bridge Replacement | CON | STP | 2026-06-04 |  | 0 | 0 | 950000 | 1444880 | 0 | 0 | 0 | 0 | 0 | 2394880
NEPA | 5 | Carbon | 109967 | 903 over Mud Run | 903 | 04B | Bridge Replacement | CON | SXF | 2026-06-04 |  | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
NEPA | 5 | Carbon | 113773 | 903 2nd to 13th Street | 903 | 05M | Highway Restoration | CON | STP |  |  | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 800
NEPA | 5 | Carbon | 113773 | 903 2nd to 13th Street | 903 | 05M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200
NEPA | 5 | Carbon | 113774 | SR 209 - Dept. Force Preservation | 209 | DFP | Preventive Maintenance | CON | STP |  | 2021-07-23 | 0 | 0 | 0 | 0 | 0 | 3000000 | 1750000 | 265220 | 0 | 5015220
NEPA | 5 | Carbon | 116965 | Delaware Ave Signal Improvements | 2002 | 04S | Congestion Reduction | FD | CAQ | 2026-07-16 |  | 160650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160650
NEPA | 5 | Carbon | 116965 | Delaware Ave Signal Improvements | 2002 | 04S | Congestion Reduction | UTL | CAQ | 2026-07-16 |  | 51500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51500
NEPA | 5 | Carbon | 116965 | Delaware Ave Signal Improvements | 2002 | 04S | Congestion Reduction | CON | CAQ | 2026-07-16 |  | 224850 | 551000 | 24150 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
NEPA | 5 | Carbon | 117253 | NEPA Br Preserv. & Repair #10 | 93 | 0 | Bridge Preservation - State Funded | PE | 581 | 2031-04-01 |  | 0 | 0 | 0 | 1125500 | 0 | 0 | 0 | 0 | 0 | 1125500
NEPA | 5 | Carbon | 117253 | NEPA Br Preserv. & Repair #10 | 93 | 0 | Bridge Preservation - State Funded | CON | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 2500000 | 2470500 | 0 | 5970500
NEPA | 5 | Carbon | 117254 | NEPA Bridge Overlay Bundle #2 | 248 | BOB | Bridge Preservation - Federal | CON | BRIP | 2023-02-16 | 2023-02-16 | 42834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42834
NEPA | 5 | Carbon | 117254 | NEPA Bridge Overlay Bundle #2 | 248 | BOB | Bridge Preservation - Federal | CON | STP | 2023-02-16 | 2023-02-16 | 18766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18766
NEPA | 5 | Carbon | 117254 | NEPA Bridge Overlay Bundle #2 | 248 | BOB | Bridge Preservation - Federal | CON | 185 | 2023-02-16 | 2023-02-16 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15400
NEPA | 5 | Carbon | 117255 | NEPA In-house Geotech Assistance | 2002 | GTA | Bridge Restoration | PE | 581 |  |  | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 200000
NEPA | 5 | Carbon | 120981 | Box Culvert Bundle 2 | 902 | BCB | Bridge Replacement | PE | 185 | 2032-04-01 |  | 0 | 0 | 0 | 0 | 500000 | 1750000 | 648250 | 0 | 0 | 2898250
NEPA | 5 | Carbon | 120981 | Box Culvert Bundle 2 | 902 | BCB | Bridge Replacement | CON | 185 | 2032-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 2183800 | 4433800
NEPA | 5 | Carbon | 121123 | Weatherly Retaining Wall Replacement | 4010 | WWR | Highway Reconstruction | UTL | PRTCT | 2025-02-27 | 2025-02-27 | 58371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58371
NEPA | 5 | Carbon | 121123 | Weatherly Retaining Wall Replacement | 4010 | WWR | Highway Reconstruction | CON | PRTCT | 2025-02-27 | 2025-02-27 | 237203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237203
NEPA | 5 | Monroe | 11756 | Mutton Hollow Rd over Kettle Creek | 3018 | 02B | Bridge Replacement | ROW | 185 | 2027-03-25 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
NEPA | 5 | Monroe | 11756 | Mutton Hollow Rd over Kettle Creek | 3018 | 02B | Bridge Replacement | UTL | 185 | 2027-03-25 |  | 0 | 10609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10609
NEPA | 5 | Monroe | 74979 | 611 /715 Improvements | 611 | 11M | Congestion Reduction | UTL | SXF | 2027-08-12 |  | 0 | 927424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 927424
NEPA | 5 | Monroe | 74979 | 611 /715 Improvements | 611 | 11M | Congestion Reduction | CON | NHPP | 2027-08-12 |  | 0 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000
NEPA | 5 | Monroe | 74979 | 611 /715 Improvements | 611 | 11M | Congestion Reduction | CON | SXF | 2027-08-12 |  | 0 | 3375181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3375181
NEPA | 5 | Monroe | 76370 | PA 191 Brodhead Cr. Br. | 191 | 05B | Bridge Replacement | PE | BRIP | 2029-12-13 |  | 716059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716059
NEPA | 5 | Monroe | 76370 | PA 191 Brodhead Cr. Br. | 191 | 05B | Bridge Replacement | FD | BRIP | 2029-12-13 |  | 0 | 125000 | 324360 | 0 | 0 | 0 | 0 | 0 | 0 | 449360
NEPA | 5 | Monroe | 76370 | PA 191 Brodhead Cr. Br. | 191 | 05B | Bridge Replacement | FD | STP | 2029-12-13 |  | 0 | 0 | 81090 | 0 | 0 | 0 | 0 | 0 | 0 | 81090
NEPA | 5 | Monroe | 76370 | PA 191 Brodhead Cr. Br. | 191 | 05B | Bridge Replacement | ROW | BRIP | 2029-12-13 |  | 0 | 50000 | 44872 | 0 | 0 | 0 | 0 | 0 | 0 | 94872
NEPA | 5 | Monroe | 76370 | PA 191 Brodhead Cr. Br. | 191 | 05B | Bridge Replacement | ROW | STP | 2029-12-13 |  | 0 | 0 | 11218 | 0 | 0 | 0 | 0 | 0 | 0 | 11218
NEPA | 5 | Monroe | 76370 | PA 191 Brodhead Cr. Br. | 191 | 05B | Bridge Replacement | CON | BRIP | 2029-12-13 |  | 0 | 0 | 0 | 4000000 | 2750000 | 1241050 | 0 | 0 | 0 | 7991050
NEPA | 5 | Monroe | 79160 | SR 447 over Brodhead Crk. | 447 | 05B | Bridge Replacement | UTL | 185 | 2017-09-14 | 2017-09-14 | 0 | 19920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19920
NEPA | 5 | Monroe | 79163 | SR 715 over Pocono Creek | 715 | 01B | Bridge Replacement | CON | 581 | 2024-08-22 | 2024-08-22 | 1100000 | 1504006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2604006
NEPA | 5 | Monroe | 79190 | Smith Hill Rd over Appenzell Ck | 3026 | 02B | Bridge Replacement | FD | BOF | 2027-04-08 |  | 0 | 485280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485280
NEPA | 5 | Monroe | 79190 | Smith Hill Rd over Appenzell Ck | 3026 | 02B | Bridge Replacement | ROW | BOF | 2027-04-08 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
NEPA | 5 | Monroe | 79190 | Smith Hill Rd over Appenzell Ck | 3026 | 02B | Bridge Replacement | UTL | BOF | 2027-04-08 |  | 0 | 0 | 13112 | 0 | 0 | 0 | 0 | 0 | 0 | 13112
NEPA | 5 | Monroe | 79190 | Smith Hill Rd over Appenzell Ck | 3026 | 02B | Bridge Replacement | UTL | 581 | 2027-04-08 |  | 0 | 0 | 3278 | 0 | 0 | 0 | 0 | 0 | 0 | 3278
NEPA | 5 | Monroe | 79190 | Smith Hill Rd over Appenzell Ck | 3026 | 02B | Bridge Replacement | CON | BOF | 2027-04-08 |  | 0 | 0 | 874160 | 0 | 0 | 0 | 0 | 0 | 0 | 874160
NEPA | 5 | Monroe | 79190 | Smith Hill Rd over Appenzell Ck | 3026 | 02B | Bridge Replacement | CON | 581 | 2027-04-08 |  | 0 | 0 | 218540 | 0 | 0 | 0 | 0 | 0 | 0 | 218540
NEPA | 5 | Monroe | 79203 | Red Rock Rd (SR 1006) over Paradise Ck | 1006 | 02B | Bridge Replacement | PE | BOF | 2027-10-07 |  | 27395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27395
NEPA | 5 | Monroe | 79203 | Red Rock Rd (SR 1006) over Paradise Ck | 1006 | 02B | Bridge Replacement | FD | BOF | 2027-10-07 |  | 196964 | 380636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577600
NEPA | 5 | Monroe | 79203 | Red Rock Rd (SR 1006) over Paradise Ck | 1006 | 02B | Bridge Replacement | FD | 185 | 2027-10-07 |  | 49241 | 95159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144400
NEPA | 5 | Monroe | 79203 | Red Rock Rd (SR 1006) over Paradise Ck | 1006 | 02B | Bridge Replacement | ROW | BOF | 2027-10-07 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
NEPA | 5 | Monroe | 79203 | Red Rock Rd (SR 1006) over Paradise Ck | 1006 | 02B | Bridge Replacement | ROW | 581 | 2027-10-07 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
NEPA | 5 | Monroe | 79203 | Red Rock Rd (SR 1006) over Paradise Ck | 1006 | 02B | Bridge Replacement | UTL | BOF | 2027-10-07 |  | 0 | 0 | 0 | 13508 | 0 | 0 | 0 | 0 | 0 | 13508
NEPA | 5 | Monroe | 79203 | Red Rock Rd (SR 1006) over Paradise Ck | 1006 | 02B | Bridge Replacement | UTL | 581 | 2027-10-07 |  | 0 | 0 | 0 | 3377 | 0 | 0 | 0 | 0 | 0 | 3377
NEPA | 5 | Monroe | 79203 | Red Rock Rd (SR 1006) over Paradise Ck | 1006 | 02B | Bridge Replacement | CON | BOF | 2027-10-07 |  | 0 | 0 | 0 | 936492 | 414108 | 0 | 0 | 0 | 0 | 1350600
NEPA | 5 | Monroe | 79203 | Red Rock Rd (SR 1006) over Paradise Ck | 1006 | 02B | Bridge Replacement | CON | 581 | 2027-10-07 |  | 0 | 0 | 0 | 234123 | 103527 | 0 | 0 | 0 | 0 | 337650
NEPA | 5 | Monroe | 79206 | Cherry Lane Rd (SR 1002) over Brodhead Crk | 1002 | 01B | Bridge Replacement | PE | BRIP | 2030-04-01 |  | 0 | 0 | 0 | 675300 | 0 | 0 | 0 | 0 | 0 | 675300
NEPA | 5 | Monroe | 79206 | Cherry Lane Rd (SR 1002) over Brodhead Crk | 1002 | 01B | Bridge Replacement | PE | 581 | 2030-04-01 |  | 0 | 0 | 0 | 168825 | 0 | 0 | 0 | 0 | 0 | 168825
NEPA | 5 | Monroe | 79206 | Cherry Lane Rd (SR 1002) over Brodhead Crk | 1002 | 01B | Bridge Replacement | FD | STP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 602836 | 0 | 0 | 0 | 0 | 602836
NEPA | 5 | Monroe | 79206 | Cherry Lane Rd (SR 1002) over Brodhead Crk | 1002 | 01B | Bridge Replacement | FD | 581 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 150709 | 0 | 0 | 0 | 0 | 150709
NEPA | 5 | Monroe | 79206 | Cherry Lane Rd (SR 1002) over Brodhead Crk | 1002 | 01B | Bridge Replacement | ROW | STP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 74196 | 0 | 0 | 0 | 0 | 74196
NEPA | 5 | Monroe | 79206 | Cherry Lane Rd (SR 1002) over Brodhead Crk | 1002 | 01B | Bridge Replacement | ROW | 581 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 18549 | 0 | 0 | 0 | 0 | 18549
NEPA | 5 | Monroe | 79206 | Cherry Lane Rd (SR 1002) over Brodhead Crk | 1002 | 01B | Bridge Replacement | UTL | STP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 28660 | 0 | 0 | 0 | 28660
NEPA | 5 | Monroe | 79206 | Cherry Lane Rd (SR 1002) over Brodhead Crk | 1002 | 01B | Bridge Replacement | UTL | 581 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 7165 | 0 | 0 | 0 | 7165
NEPA | 5 | Monroe | 79206 | Cherry Lane Rd (SR 1002) over Brodhead Crk | 1002 | 01B | Bridge Replacement | CON | STP | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 1388200 | 0 | 0 | 2388200
NEPA | 5 | Monroe | 79206 | Cherry Lane Rd (SR 1002) over Brodhead Crk | 1002 | 01B | Bridge Replacement | CON | 185 | 2030-04-01 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 347050 | 0 | 0 | 597050
NEPA | 5 | Monroe | 79473 | SR 715/ 611 Intersection | 715 | 03S | Safety Improvement | CON | 581 | 2024-08-22 | 2024-08-22 | 3102546 | 3621426 | 3109000 | 0 | 0 | 0 | 0 | 0 | 0 | 9832972
NEPA | 5 | Monroe | 85808 | Shiffer Rd (SR 2036) over PA 33 | 2036 | 01B | Bridge Replacement | FD | BOF | 2027-02-25 |  | 91624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91624
NEPA | 5 | Monroe | 85808 | Shiffer Rd (SR 2036) over PA 33 | 2036 | 01B | Bridge Replacement | FD | 185 | 2027-02-25 |  | 22906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22906
NEPA | 5 | Monroe | 85808 | Shiffer Rd (SR 2036) over PA 33 | 2036 | 01B | Bridge Replacement | UTL | BOF | 2027-02-25 |  | 61800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800
NEPA | 5 | Monroe | 85808 | Shiffer Rd (SR 2036) over PA 33 | 2036 | 01B | Bridge Replacement | UTL | 581 | 2027-02-25 |  | 15450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15450
NEPA | 5 | Monroe | 85808 | Shiffer Rd (SR 2036) over PA 33 | 2036 | 01B | Bridge Replacement | CON | BOF | 2027-02-25 |  | 0 | 0 | 2044532 | 96021 | 141903 | 0 | 0 | 0 | 0 | 2282456
NEPA | 5 | Monroe | 85808 | Shiffer Rd (SR 2036) over PA 33 | 2036 | 01B | Bridge Replacement | CON | NHPP | 2027-02-25 |  | 0 | 0 | 0 | 1748964 | 0 | 0 | 0 | 0 | 0 | 1748964
NEPA | 5 | Monroe | 85846 | Long Pond Road ov'rTunkhannock Crk | 4002 | 03B | Bridge Replacement | CON | BOF | 2022-05-26 | 2022-05-26 | 271779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271779
NEPA | 5 | Monroe | 85846 | Long Pond Road ov'rTunkhannock Crk | 4002 | 03B | Bridge Replacement | CON | STP | 2022-05-26 | 2022-05-26 | 428221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428221
NEPA | 5 | Monroe | 85882 | 209 Business over Kettle Creek | 2012 | 02B | Bridge Replacement | ROW | 581 | 2025-05-22 | 2025-05-22 | 205050 | 102501 | 435414 | 0 | 0 | 0 | 0 | 0 | 0 | 742965
NEPA | 5 | Monroe | 85882 | 209 Business over Kettle Creek | 2012 | 02B | Bridge Replacement | UTL | 185 | 2025-05-22 | 2025-05-22 | 68748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68748
NEPA | 5 | Monroe | 85882 | 209 Business over Kettle Creek | 2012 | 02B | Bridge Replacement | CON | BRIP | 2025-05-22 | 2025-05-22 | 2240244 | 240168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2480412
NEPA | 5 | Monroe | 85882 | 209 Business over Kettle Creek | 2012 | 02B | Bridge Replacement | CON | 185 | 2025-05-22 | 2025-05-22 | 560061 | 60042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620103
NEPA | 5 | Monroe | 88935 | 209/115 Int. Imp - Phase2 | 209 | 16S | Congestion Reduction | ROW | NHPP | 2021-02-19 | 2021-02-19 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
NEPA | 5 | Monroe | 88935 | 209/115 Int. Imp - Phase2 | 209 | 16S | Congestion Reduction | CON | NHPP | 2021-02-19 | 2021-02-19 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
NEPA | 5 | Monroe | 88935 | 209/115 Int. Imp - Phase2 | 209 | 16S | Congestion Reduction | CON | 581 | 2021-02-19 | 2021-02-19 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
NEPA | 5 | Monroe | 89620 | 191 Mountain Run Creek Arch | 191 | PM8 | Bridge Preservation - State Funded | ROW | 581 | 2026-10-22 |  | 0 | 33100 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 66100
NEPA | 5 | Monroe | 91624 | TOC Operator - NEPA | 380 | TOC | Intelligent Transportation System | CON | NHPP | 2011-03-10 | 2011-03-10 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 200000
NEPA | 5 | Monroe | 91914 | SR 209 over Marshalls Creek | 209 | MCB | Bridge Restoration | PE | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 192764 | 0 | 442764
NEPA | 5 | Monroe | 91914 | SR 209 over Marshalls Creek | 209 | MCB | Bridge Restoration | PE | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 62500 | 48191 | 0 | 110691
NEPA | 5 | Monroe | 91914 | SR 209 over Marshalls Creek | 209 | MCB | Bridge Restoration | FD | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365344 | 365344
NEPA | 5 | Monroe | 91914 | SR 209 over Marshalls Creek | 209 | MCB | Bridge Restoration | FD | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91336 | 91336
NEPA | 5 | Monroe | 91914 | SR 209 over Marshalls Creek | 209 | MCB | Bridge Restoration | ROW | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26096 | 26096
NEPA | 5 | Monroe | 91914 | SR 209 over Marshalls Creek | 209 | MCB | Bridge Restoration | ROW | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6524 | 6524
NEPA | 5 | Monroe | 91914 | SR 209 over Marshalls Creek | 209 | MCB | Bridge Restoration | UTL | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26096 | 26096
NEPA | 5 | Monroe | 91914 | SR 209 over Marshalls Creek | 209 | MCB | Bridge Restoration | UTL | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6524 | 6524
NEPA | 5 | Monroe | 91914 | SR 209 over Marshalls Creek | 209 | MCB | Bridge Restoration | CON | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1826720 | 1826720
NEPA | 5 | Monroe | 91914 | SR 209 over Marshalls Creek | 209 | MCB | Bridge Restoration | CON | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456680 | 456680
NEPA | 5 | Monroe | 93634 | Kellersville Historic Structures (SR 3023) | 3023 | 02B | Bridge Replacement | UTL | 185 | 2027-06-10 |  | 0 | 0 | 103000 | 0 | 0 | 0 | 0 | 0 | 0 | 103000
NEPA | 5 | Monroe | 93634 | Kellersville Historic Structures (SR 3023) | 3023 | 02B | Bridge Replacement | CON | BRIP | 2027-06-10 |  | 0 | 0 | 1697440 | 0 | 0 | 0 | 0 | 0 | 0 | 1697440
NEPA | 5 | Monroe | 93634 | Kellersville Historic Structures (SR 3023) | 3023 | 02B | Bridge Replacement | CON | 185 | 2027-06-10 |  | 0 | 0 | 127308 | 0 | 0 | 0 | 0 | 0 | 0 | 127308
NEPA | 5 | Monroe | 93634 | Kellersville Historic Structures (SR 3023) | 3023 | 02B | Bridge Replacement | CON | 581 | 2027-06-10 |  | 0 | 0 | 297052 | 0 | 0 | 0 | 0 | 0 | 0 | 297052
NEPA | 5 | Monroe | 94301 | Upper Smith Gap Rd over Aquashicola Crk Br | 3002 | 01B | Bridge Replacement | PE | BOF | 2028-06-08 |  | 0 | 0 | 0 | 0 | 324604 | 0 | 0 | 0 | 0 | 324604
NEPA | 5 | Monroe | 94301 | Upper Smith Gap Rd over Aquashicola Crk Br | 3002 | 01B | Bridge Replacement | PE | 581 | 2028-06-08 |  | 0 | 0 | 0 | 0 | 81151 | 0 | 0 | 0 | 0 | 81151
NEPA | 5 | Monroe | 94301 | Upper Smith Gap Rd over Aquashicola Crk Br | 3002 | 01B | Bridge Replacement | FD | BOF | 2028-06-08 |  | 0 | 0 | 0 | 0 | 0 | 286584 | 0 | 0 | 0 | 286584
NEPA | 5 | Monroe | 94301 | Upper Smith Gap Rd over Aquashicola Crk Br | 3002 | 01B | Bridge Replacement | FD | 581 | 2028-06-08 |  | 0 | 0 | 0 | 0 | 0 | 71646 | 0 | 0 | 0 | 71646
NEPA | 5 | Monroe | 94301 | Upper Smith Gap Rd over Aquashicola Crk Br | 3002 | 01B | Bridge Replacement | ROW | BOF | 2028-06-08 |  | 0 | 0 | 0 | 0 | 0 | 23884 | 0 | 0 | 0 | 23884
NEPA | 5 | Monroe | 94301 | Upper Smith Gap Rd over Aquashicola Crk Br | 3002 | 01B | Bridge Replacement | ROW | 581 | 2028-06-08 |  | 0 | 0 | 0 | 0 | 0 | 5971 | 0 | 0 | 0 | 5971
NEPA | 5 | Monroe | 94301 | Upper Smith Gap Rd over Aquashicola Crk Br | 3002 | 01B | Bridge Replacement | UTL | BOF | 2028-06-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 14760 | 0 | 0 | 14760
NEPA | 5 | Monroe | 94301 | Upper Smith Gap Rd over Aquashicola Crk Br | 3002 | 01B | Bridge Replacement | UTL | 581 | 2028-06-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3690 | 0 | 0 | 3690
NEPA | 5 | Monroe | 94301 | Upper Smith Gap Rd over Aquashicola Crk Br | 3002 | 01B | Bridge Replacement | CON | BOF | 2028-06-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 336332 | 0 | 836332
NEPA | 5 | Monroe | 94301 | Upper Smith Gap Rd over Aquashicola Crk Br | 3002 | 01B | Bridge Replacement | CON | 581 | 2028-06-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 84083 | 0 | 209083
NEPA | 5 | Monroe | 95398 | 209 Holy Cross Road to Hollow Road | 209 | 03S | Safety Improvement | FD | 581 | 2026-06-18 |  | 52831 | 51934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104765
NEPA | 5 | Monroe | 95398 | 209 Holy Cross Road to Hollow Road | 209 | 03S | Safety Improvement | CON | HSIP | 2026-06-18 |  | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
NEPA | 5 | Monroe | 95398 | 209 Holy Cross Road to Hollow Road | 209 | 03S | Safety Improvement | CON | CRP | 2026-06-18 |  | 1296000 | 148792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1444792
NEPA | 5 | Monroe | 95398 | 209 Holy Cross Road to Hollow Road | 209 | 03S | Safety Improvement | CON | HSIP | 2026-06-18 |  | 750000 | 486000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1236000
NEPA | 5 | Monroe | 95574 | Hamilton West Resurface-Sciota | 209 | 15M | Highway Restoration | CON | NHPP | 2024-05-23 | 2024-05-23 | 0 | 0 | 149472 | 0 | 0 | 0 | 0 | 0 | 0 | 149472
NEPA | 5 | Monroe | 95574 | Hamilton West Resurface-Sciota | 209 | 15M | Highway Restoration | CON | STP | 2024-05-23 | 2024-05-23 | 0 | 0 | 467400 | 0 | 0 | 0 | 0 | 0 | 0 | 467400
NEPA | 5 | Monroe | 95574 | Hamilton West Resurface-Sciota | 209 | 15M | Highway Restoration | CON | 581 | 2024-05-23 | 2024-05-23 | 0 | 0 | 154218 | 0 | 0 | 0 | 0 | 0 | 0 | 154218
NEPA | 5 | Monroe | 96434 | PA 715 Stone Arch Replace | 715 | 04B | Bridge Replacement | ROW | BRIP | 2026-07-16 |  | 96800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96800
NEPA | 5 | Monroe | 96434 | PA 715 Stone Arch Replace | 715 | 04B | Bridge Replacement | ROW | 581 | 2026-07-16 |  | 24200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24200
NEPA | 5 | Monroe | 96434 | PA 715 Stone Arch Replace | 715 | 04B | Bridge Replacement | UTL | BRIP | 2026-07-16 |  | 0 | 42436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42436
NEPA | 5 | Monroe | 96434 | PA 715 Stone Arch Replace | 715 | 04B | Bridge Replacement | UTL | 581 | 2026-07-16 |  | 0 | 10609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10609
NEPA | 5 | Monroe | 96434 | PA 715 Stone Arch Replace | 715 | 04B | Bridge Replacement | CON | STP | 2026-07-16 |  | 0 | 1000000 | 1227890 | 0 | 0 | 0 | 0 | 0 | 0 | 2227890
NEPA | 5 | Monroe | 96481 | PA 611 Corridor Improvements | 611 | 12M | Highway Reconstruction | STUDY | STP | 2031-04-01 |  | 426000 | 387600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813600
NEPA | 5 | Monroe | 96481 | PA 611 Corridor Improvements | 611 | 12M | Highway Reconstruction | STUDY | 581 | 2031-04-01 |  | 106500 | 96900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203400
NEPA | 5 | Monroe | 96481 | PA 611 Corridor Improvements | 611 | 12M | Highway Reconstruction | PE | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1043840 | 1043840
NEPA | 5 | Monroe | 96481 | PA 611 Corridor Improvements | 611 | 12M | Highway Reconstruction | PE | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260960 | 260960
NEPA | 5 | Monroe | 102167 | SR 115 Corridor Impr - Effort | 115 | 03S | Safety Improvement | CON | HSIP | 2023-10-19 | 2023-10-19 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
NEPA | 5 | Monroe | 102423 | 715 over McMichael's Creek II | 715 | 03B | Bridge Replacement | CON | STP | 2023-07-13 | 2023-07-13 | 75200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75200
NEPA | 5 | Monroe | 102423 | 715 over McMichael's Creek II | 715 | 03B | Bridge Replacement | CON | 185 | 2023-07-13 | 2023-07-13 | 18800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18800
NEPA | 5 | Monroe | 104432 | 209 -Schafer School House | 209 | 17S | Safety Improvement | ROW | HSIP | 2023-08-10 | 2023-08-10 | 0 | 90766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90766
NEPA | 5 | Monroe | 104432 | 209 -Schafer School House | 209 | 17S | Safety Improvement | CON | HSIP | 2023-08-10 | 2023-08-10 | 158235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158235
NEPA | 5 | Monroe | 104432 | 209 -Schafer School House | 209 | 17S | Safety Improvement | CON | STP | 2023-08-10 | 2023-08-10 | 0 | 93265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93265
NEPA | 5 | Monroe | 105966 | Sterling Road Safety Improvements Area 1 | 196 | 01S | Safety Improvement | FD | HSIP | 2027-07-29 |  | 600000 | 226005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826005
NEPA | 5 | Monroe | 105966 | Sterling Road Safety Improvements Area 1 | 196 | 01S | Safety Improvement | ROW | HSIP | 2027-07-29 |  | 311300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311300
NEPA | 5 | Monroe | 105966 | Sterling Road Safety Improvements Area 1 | 196 | 01S | Safety Improvement | UTL | HSIP | 2027-07-29 |  | 143060 | 216940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
NEPA | 5 | Monroe | 105966 | Sterling Road Safety Improvements Area 1 | 196 | 01S | Safety Improvement | UTL | 581 | 2027-07-29 |  | 15896 | 24104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
NEPA | 5 | Monroe | 105966 | Sterling Road Safety Improvements Area 1 | 196 | 01S | Safety Improvement | CON | STP | 2027-07-29 |  | 0 | 0 | 2055392 | 1500000 | 263848 | 0 | 0 | 0 | 0 | 3819240
NEPA | 5 | Monroe | 109334 | NEPA Brg Preserve & Repair 6 | 80 | BRM | Bridge Preservation - State Funded | CON | 185 | 2021-10-07 | 2021-10-07 | 258930 | 36400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295330
NEPA | 5 | Monroe | 109826 | NEPA Bridge Preservation & Repair 7 | 191 | BRM | Bridge Preservation - State Funded | CON | 185 | 2024-08-22 | 2024-08-22 | 1349514 | 3224250 | 45338 | 0 | 0 | 0 | 0 | 0 | 0 | 4619102
NEPA | 5 | Monroe | 109964 | 209 & 33 NB over Appenzell Creek | 209 | 20B | Bridge Replacement | CON | BRIP | 2024-02-29 | 2024-02-29 | 42000 | 1098044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1140044
NEPA | 5 | Monroe | 110457 | PA 33 Median Barrier SR 2002 to SR 2008 | 33 | 05S | Safety Improvement | PE | STP | 2026-09-17 |  | 0 | 0 | 0 | 180080 | 0 | 0 | 0 | 0 | 0 | 180080
NEPA | 5 | Monroe | 110457 | PA 33 Median Barrier SR 2002 to SR 2008 | 33 | 05S | Safety Improvement | PE | 581 | 2026-09-17 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
NEPA | 5 | Monroe | 110457 | PA 33 Median Barrier SR 2002 to SR 2008 | 33 | 05S | Safety Improvement | PE | 581 | 2026-09-17 |  | 0 | 0 | 0 | 45020 | 0 | 0 | 0 | 0 | 0 | 45020
NEPA | 5 | Monroe | 110457 | PA 33 Median Barrier SR 2002 to SR 2008 | 33 | 05S | Safety Improvement | FD | 581 | 2026-09-17 |  | 0 | 0 | 0 | 0 | 231860 | 0 | 0 | 0 | 0 | 231860
NEPA | 5 | Monroe | 110457 | PA 33 Median Barrier SR 2002 to SR 2008 | 33 | 05S | Safety Improvement | ROW | 581 | 2026-09-17 |  | 0 | 0 | 0 | 0 | 25505 | 0 | 0 | 0 | 0 | 25505
NEPA | 5 | Monroe | 110457 | PA 33 Median Barrier SR 2002 to SR 2008 | 33 | 05S | Safety Improvement | CON | STP | 2026-09-17 |  | 0 | 0 | 13200000 | 0 | 0 | 0 | 0 | 0 | 0 | 13200000
NEPA | 5 | Monroe | 111812 | Municipal Bridge Bundle | 7206 | MBB | Bridge Restoration | PE | BOF | 2029-04-01 |  | 0 | 0 | 800000 | 565875 | 0 | 0 | 0 | 0 | 0 | 1365875
NEPA | 5 | Monroe | 111812 | Municipal Bridge Bundle | 7206 | MBB | Bridge Restoration | FD | BOF | 2029-04-01 |  | 0 | 0 | 0 | 1519425 | 0 | 0 | 0 | 0 | 0 | 1519425
NEPA | 5 | Monroe | 111812 | Municipal Bridge Bundle | 7206 | MBB | Bridge Restoration | ROW | BOF | 2029-04-01 |  | 0 | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 56275
NEPA | 5 | Monroe | 111812 | Municipal Bridge Bundle | 7206 | MBB | Bridge Restoration | UTL | BOF | 2029-04-01 |  | 0 | 0 | 0 | 0 | 86948 | 0 | 0 | 0 | 0 | 86948
NEPA | 5 | Monroe | 111812 | Municipal Bridge Bundle | 7206 | MBB | Bridge Restoration | CON | BOF | 2029-04-01 |  | 0 | 0 | 0 | 0 | 2600000 | 3364599 | 0 | 0 | 0 | 5964599
NEPA | 5 | Monroe | 113494 | NEPA Br Preserv & Repair 8 | 2012 | BRM | Bridge Restoration | CON | 581 | 2026-10-22 |  | 0 | 0 | 2505000 | 2521420 | 0 | 0 | 0 | 0 | 0 | 5026420
NEPA | 5 | Monroe | 113745 | Mount Pocono Borough Pipe - Ida Perm Rpr | 4007 | IDA | Disaster Permanent Repair | CON | FFL | 2024-05-23 | 2024-06-13 | 57170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57170
NEPA | 5 | Monroe | 113745 | Mount Pocono Borough Pipe - Ida Perm Rpr | 4007 | IDA | Disaster Permanent Repair | CON | 581 | 2024-05-23 | 2024-06-13 | 14292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14292
NEPA | 5 | Monroe | 113878 | 209 Mt Nebo to Holy Cross Road | 209 | 23S | Safety Improvement | PE | HSIP | 2028-08-10 |  | 477405 | 769950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1247355
NEPA | 5 | Monroe | 113878 | 209 Mt Nebo to Holy Cross Road | 209 | 23S | Safety Improvement | FD | HSIP | 2028-08-10 |  | 0 | 345000 | 350000 | 100675 | 0 | 0 | 0 | 0 | 0 | 795675
NEPA | 5 | Monroe | 113878 | 209 Mt Nebo to Holy Cross Road | 209 | 23S | Safety Improvement | ROW | HSIP | 2028-08-10 |  | 0 | 315105 | 851885 | 0 | 0 | 0 | 0 | 0 | 0 | 1166990
NEPA | 5 | Monroe | 113878 | 209 Mt Nebo to Holy Cross Road | 209 | 23S | Safety Improvement | UTL | HSIP | 2028-08-10 |  | 0 | 0 | 100000 | 227810 | 0 | 0 | 0 | 0 | 0 | 327810
NEPA | 5 | Monroe | 113878 | 209 Mt Nebo to Holy Cross Road | 209 | 23S | Safety Improvement | CON | HSIP | 2028-08-10 |  | 0 | 0 | 0 | 950000 | 2100000 | 1761513 | 0 | 0 | 0 | 4811513
NEPA | 5 | Monroe | 113879 | 209 Middle Smithfield Elem. Dr. to Portuguese Lane | 209 | 24S | Safety Improvement | PE | HSIP | 2029-04-01 |  | 720838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720838
NEPA | 5 | Monroe | 113879 | 209 Middle Smithfield Elem. Dr. to Portuguese Lane | 209 | 24S | Safety Improvement | PE | HSIP | 2029-04-01 |  | 0 | 162000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162000
NEPA | 5 | Monroe | 113879 | 209 Middle Smithfield Elem. Dr. to Portuguese Lane | 209 | 24S | Safety Improvement | FD | HSIP | 2029-04-01 |  | 0 | 0 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
NEPA | 5 | Monroe | 113879 | 209 Middle Smithfield Elem. Dr. to Portuguese Lane | 209 | 24S | Safety Improvement | FD | HSIP | 2029-04-01 |  | 0 | 0 | 350000 | 360255 | 0 | 0 | 0 | 0 | 0 | 710255
NEPA | 5 | Monroe | 113879 | 209 Middle Smithfield Elem. Dr. to Portuguese Lane | 209 | 24S | Safety Improvement | ROW | HSIP | 2029-04-01 |  | 0 | 1000000 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 1650000
NEPA | 5 | Monroe | 113879 | 209 Middle Smithfield Elem. Dr. to Portuguese Lane | 209 | 24S | Safety Improvement | ROW | HSIP | 2029-04-01 |  | 0 | 0 | 440105 | 852955 | 0 | 0 | 0 | 0 | 0 | 1293060
NEPA | 5 | Monroe | 113879 | 209 Middle Smithfield Elem. Dr. to Portuguese Lane | 209 | 24S | Safety Improvement | UTL | HSIP | 2029-04-01 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
NEPA | 5 | Monroe | 113879 | 209 Middle Smithfield Elem. Dr. to Portuguese Lane | 209 | 24S | Safety Improvement | UTL | HSIP | 2029-04-01 |  | 0 | 0 | 0 | 0 | 289825 | 0 | 0 | 0 | 0 | 289825
NEPA | 5 | Monroe | 113879 | 209 Middle Smithfield Elem. Dr. to Portuguese Lane | 209 | 24S | Safety Improvement | CON | HSIP | 2029-04-01 |  | 0 | 0 | 0 | 2360041 | 0 | 0 | 0 | 0 | 0 | 2360041
NEPA | 5 | Monroe | 113879 | 209 Middle Smithfield Elem. Dr. to Portuguese Lane | 209 | 24S | Safety Improvement | CON | HSIP | 2029-04-01 |  | 0 | 0 | 0 | 0 | 0 | 700000 | 1395006 | 0 | 0 | 2095006
NEPA | 5 | Monroe | 113879 | 209 Middle Smithfield Elem. Dr. to Portuguese Lane | 209 | 24S | Safety Improvement | CON | STP | 2029-04-01 |  | 0 | 0 | 0 | 0 | 500000 | 0 | 1752369 | 0 | 0 | 2252369
NEPA | 5 | Monroe | 114078 | PA 611 Retaining Wall Repairs | 611 | SWR | Highway Restoration | FD | STP | 2035-04-01 |  | 0 | 0 | 0 | 169750 | 0 | 0 | 0 | 0 | 0 | 169750
NEPA | 5 | Monroe | 114078 | PA 611 Retaining Wall Repairs | 611 | SWR | Highway Restoration | FD | 581 | 2035-04-01 |  | 0 | 0 | 0 | 42440 | 0 | 0 | 0 | 0 | 0 | 42440
NEPA | 5 | Monroe | 114078 | PA 611 Retaining Wall Repairs | 611 | SWR | Highway Restoration | ROW | STP | 2035-04-01 |  | 0 | 0 | 0 | 84880 | 0 | 0 | 0 | 0 | 0 | 84880
NEPA | 5 | Monroe | 114078 | PA 611 Retaining Wall Repairs | 611 | SWR | Highway Restoration | ROW | 581 | 2035-04-01 |  | 0 | 0 | 0 | 21220 | 0 | 0 | 0 | 0 | 0 | 21220
NEPA | 5 | Monroe | 114078 | PA 611 Retaining Wall Repairs | 611 | SWR | Highway Restoration | UTL | 581 | 2035-04-01 |  | 0 | 0 | 54635 | 0 | 0 | 0 | 0 | 0 | 0 | 54635
NEPA | 5 | Monroe | 114078 | PA 611 Retaining Wall Repairs | 611 | SWR | Highway Restoration | CON | 581 | 2035-04-01 |  | 0 | 0 | 1000000 | 2000000 | 2463500 | 0 | 0 | 0 | 0 | 5463500
NEPA | 5 | Monroe | 116800 | Sterling Rd Safety Improvements Area 2 | 196 | 02S | Safety Improvement | PE | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1008520 | 0 | 0 | 1008520
NEPA | 5 | Monroe | 116800 | Sterling Rd Safety Improvements Area 2 | 196 | 02S | Safety Improvement | PE | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 252130 | 0 | 0 | 252130
NEPA | 5 | Monroe | 116800 | Sterling Rd Safety Improvements Area 2 | 196 | 02S | Safety Improvement | ROW | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342380 | 342380
NEPA | 5 | Monroe | 116800 | Sterling Rd Safety Improvements Area 2 | 196 | 02S | Safety Improvement | ROW | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85595 | 85595
NEPA | 5 | Monroe | 116800 | Sterling Rd Safety Improvements Area 2 | 196 | 02S | Safety Improvement | UTL | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1826720 | 1826720
NEPA | 5 | Monroe | 116800 | Sterling Rd Safety Improvements Area 2 | 196 | 02S | Safety Improvement | UTL | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456680 | 456680
NEPA | 5 | Monroe | 116800 | Sterling Rd Safety Improvements Area 2 | 196 | 02S | Safety Improvement | CON | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3314192 | 3314192
NEPA | 5 | Monroe | 116800 | Sterling Rd Safety Improvements Area 2 | 196 | 02S | Safety Improvement | CON | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 828548 | 828548
NEPA | 5 | Monroe | 117250 | 209 Betterment SR 33 split to SR 2010 Underpass | 209 | 31M | Highway Restoration | CON | NHPP | 2025-04-10 | 2025-04-10 | 3671135 | 966001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4637136
NEPA | 5 | Monroe | 117645 | AMTRAK Passenger Rail Service Line Item |  |  | Study Phase of Project | PE | STP |  |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
NEPA | 5 | Monroe | 118403 | SR 611 Learn Road (T-537) Safety Enhance. Project | 611 | LRS | Transportation Enhancement | CON | TAP | 2026-08-27 |  | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
NEPA | 5 | Monroe | 119479 | Tobyhanna Pocono Summit West | 940 | TPS | MultiModal | CON | 581 | 2026-07-16 |  | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
NEPA | 5 | Monroe | 119707 | SR 611 Rock-Slope Mitigation Phase 2 | 611 | 14S | Safety Improvement | PE | STP |  |  | 0 | 0 | 206000 | 0 | 0 | 0 | 0 | 0 | 0 | 206000
NEPA | 5 | Monroe | 119707 | SR 611 Rock-Slope Mitigation Phase 2 | 611 | 14S | Safety Improvement | PE | 581 |  |  | 0 | 0 | 51500 | 0 | 0 | 0 | 0 | 0 | 0 | 51500
NEPA | 5 | Monroe | 119707 | SR 611 Rock-Slope Mitigation Phase 2 | 611 | 14S | Safety Improvement | ROW | STP |  |  | 0 | 0 | 87416 | 0 | 0 | 0 | 0 | 0 | 0 | 87416
NEPA | 5 | Monroe | 119707 | SR 611 Rock-Slope Mitigation Phase 2 | 611 | 14S | Safety Improvement | ROW | 581 |  |  | 0 | 0 | 21854 | 0 | 0 | 0 | 0 | 0 | 0 | 21854
NEPA | 5 | Monroe | 119707 | SR 611 Rock-Slope Mitigation Phase 2 | 611 | 14S | Safety Improvement | CON | 581 |  |  | 0 | 0 | 0 | 1750000 | 1063750 | 0 | 0 | 0 | 0 | 2813750
NEPA | 5 | Monroe | 120977 | NEPA High Friction Surface - 2025 | 209 | HFS | Safety Improvement | CON | HSIP | 2025-07-10 | 2025-07-10 | 164945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164945
NEPA | 5 | Monroe | 120977 | NEPA High Friction Surface - 2025 | 209 | HFS | Safety Improvement | CON | HSIP | 2025-07-10 | 2025-07-10 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
NEPA | 5 | Monroe | 120985 | NEPA Bridge Preserv & Repair 11 | 611 | BPR | Bridge Preservation - State Funded | PE | 185 | 2036-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1304800 | 1304800
NEPA | 5 | Monroe | 120985 | NEPA Bridge Preserv & Repair 11 | 611 | BPR | Bridge Preservation - State Funded | CON | 185 | 2036-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6524000 | 6524000
NEPA | 5 | Monroe | 123770 | Fork Street Improvements |  | FSI | MultiModal | CON | 411 |  |  | 0 | 646027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646027
NEPA | 5 | Monroe | 123770 | Fork Street Improvements |  | FSI | MultiModal | CON | LOC |  |  | 0 | 222265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222265
NEPA | 5 | Schuylkill | 12611 | Minersville Arch Bridge | 4042 | MAB | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 10300 | 0 | 0 | 0 | 0 | 0 | 0 | 10300
NEPA | 5 | Schuylkill | 12611 | Minersville Arch Bridge | 4042 | MAB | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 5305 | 0 | 0 | 0 | 0 | 0 | 0 | 5305
NEPA | 5 | Schuylkill | 12704 | Brockton Mountain Drive over Locust Creek | 1011 | 01B | Bridge Replacement | CON | BOF | 2025-04-17 | 2025-04-17 | 1035600 | 150000 | 81100 | 0 | 0 | 0 | 0 | 0 | 0 | 1266700
NEPA | 5 | Schuylkill | 12704 | Brockton Mountain Drive over Locust Creek | 1011 | 01B | Bridge Replacement | CON | 185 | 2025-04-17 | 2025-04-17 | 258900 | 37500 | 28482 | 0 | 0 | 0 | 0 | 0 | 0 | 324882
NEPA | 5 | Schuylkill | 12709 | SR 209 over Panther Creek | 209 | PM8 | Bridge Preservation - State Funded | ROW | 581 | 2026-10-22 |  | 0 | 40200 | 40200 | 0 | 0 | 0 | 0 | 0 | 0 | 80400
NEPA | 5 | Schuylkill | 12720 | Little Catawissa Bridge | 4033 | PM8 | Bridge Preservation - State Funded | ROW | 581 | 2026-10-22 |  | 0 | 35800 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 65800
NEPA | 5 | Schuylkill | 85721 | Honeymoon Trail Rd over Pine Creek | 4017 | 01B | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 10300 | 0 | 0 | 0 | 0 | 0 | 0 | 10300
NEPA | 5 | Schuylkill | 85721 | Honeymoon Trail Rd over Pine Creek | 4017 | 01B | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 5150 | 0 | 0 | 0 | 0 | 0 | 0 | 5150
NEPA | 5 | Schuylkill | 85750 | SR 1021 (Lincoln Drive) over RBM&N Railroad | 1021 | 01B | Bridge Replacement | CON | BOF | 2025-10-23 | 2025-10-23 | 2920132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2920132
NEPA | 5 | Schuylkill | 85750 | SR 1021 (Lincoln Drive) over RBM&N Railroad | 1021 | 01B | Bridge Replacement | CON | STP | 2025-10-23 | 2025-10-23 | 382516 | 133543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516059
NEPA | 5 | Schuylkill | 85817 | Main Blvd over Trib of Catawissa Crk (3) | 924 | 06B | Bridge Replacement | FD | STP | 2027-05-27 |  | 0 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000
NEPA | 5 | Schuylkill | 85817 | Main Blvd over Trib of Catawissa Crk (3) | 924 | 06B | Bridge Replacement | UTL | STP | 2027-05-27 |  | 0 | 12732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12732
NEPA | 5 | Schuylkill | 85817 | Main Blvd over Trib of Catawissa Crk (3) | 924 | 06B | Bridge Replacement | UTL | 185 | 2027-05-27 |  | 0 | 3183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3183
NEPA | 5 | Schuylkill | 85817 | Main Blvd over Trib of Catawissa Crk (3) | 924 | 06B | Bridge Replacement | CON | STP | 2027-05-27 |  | 0 | 0 | 950000 | 1426416 | 0 | 0 | 0 | 0 | 0 | 2376416
NEPA | 5 | Schuylkill | 85817 | Main Blvd over Trib of Catawissa Crk (3) | 924 | 06B | Bridge Replacement | CON | 185 | 2027-05-27 |  | 0 | 0 | 332069 | 262035 | 0 | 0 | 0 | 0 | 0 | 594104
NEPA | 5 | Schuylkill | 85820 | Main Blvd over Trib of Catawissa Crk - 2 | 924 | 07B | Bridge Replacement | ROW | 185 | 2027-05-27 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
NEPA | 5 | Schuylkill | 85820 | Main Blvd over Trib of Catawissa Crk - 2 | 924 | 07B | Bridge Replacement | UTL | 185 | 2027-05-27 |  | 0 | 10609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10609
NEPA | 5 | Schuylkill | 85821 | PA 924 over Trib to Catawissa Crk - 1 | 924 | 08B | Bridge Replacement | ROW | 185 | 2027-05-27 |  | 0 | 25750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25750
NEPA | 5 | Schuylkill | 85821 | PA 924 over Trib to Catawissa Crk - 1 | 924 | 08B | Bridge Replacement | UTL | 185 | 2027-05-27 |  | 0 | 10609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10609
NEPA | 5 | Schuylkill | 85835 | PA 443 over Swatara Creek | 443 | 03B | Bridge Restoration | PE | BRIP | 2029-04-12 |  | 350000 | 299196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649196
NEPA | 5 | Schuylkill | 85835 | PA 443 over Swatara Creek | 443 | 03B | Bridge Restoration | PE | 185 | 2029-04-12 |  | 87500 | 74799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162299
NEPA | 5 | Schuylkill | 85835 | PA 443 over Swatara Creek | 443 | 03B | Bridge Restoration | FD | BRIP | 2029-04-12 |  | 0 | 0 | 699328 | 0 | 0 | 0 | 0 | 0 | 0 | 699328
NEPA | 5 | Schuylkill | 85835 | PA 443 over Swatara Creek | 443 | 03B | Bridge Restoration | FD | 581 | 2029-04-12 |  | 0 | 0 | 174832 | 0 | 0 | 0 | 0 | 0 | 0 | 174832
NEPA | 5 | Schuylkill | 85835 | PA 443 over Swatara Creek | 443 | 03B | Bridge Restoration | ROW | BRIP | 2029-04-12 |  | 0 | 0 | 87416 | 0 | 0 | 0 | 0 | 0 | 0 | 87416
NEPA | 5 | Schuylkill | 85835 | PA 443 over Swatara Creek | 443 | 03B | Bridge Restoration | ROW | 581 | 2029-04-12 |  | 0 | 0 | 21854 | 0 | 0 | 0 | 0 | 0 | 0 | 21854
NEPA | 5 | Schuylkill | 85835 | PA 443 over Swatara Creek | 443 | 03B | Bridge Restoration | UTL | BRIP | 2029-04-12 |  | 0 | 0 | 0 | 0 | 92744 | 0 | 0 | 0 | 0 | 92744
NEPA | 5 | Schuylkill | 85835 | PA 443 over Swatara Creek | 443 | 03B | Bridge Restoration | UTL | 581 | 2029-04-12 |  | 0 | 0 | 0 | 0 | 23186 | 0 | 0 | 0 | 0 | 23186
NEPA | 5 | Schuylkill | 85835 | PA 443 over Swatara Creek | 443 | 03B | Bridge Restoration | CON | BRIP | 2029-04-12 |  | 0 | 0 | 0 | 0 | 1750000 | 2500000 | 0 | 0 | 0 | 4250000
NEPA | 5 | Schuylkill | 85835 | PA 443 over Swatara Creek | 443 | 03B | Bridge Restoration | CON | STP | 2029-04-12 |  | 0 | 0 | 0 | 0 | 0 | 387200 | 0 | 0 | 0 | 387200
NEPA | 5 | Schuylkill | 85835 | PA 443 over Swatara Creek | 443 | 03B | Bridge Restoration | CON | 581 | 2029-04-12 |  | 0 | 0 | 0 | 0 | 437500 | 721800 | 0 | 0 | 0 | 1159300
NEPA | 5 | Schuylkill | 91674 | SR 309 over RBMNRR | 309 | 06B | Bridge Restoration | PE | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 500000 | 369475 | 0 | 0 | 0 | 869475
NEPA | 5 | Schuylkill | 91674 | SR 309 over RBMNRR | 309 | 06B | Bridge Restoration | FD | NHPP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 491960 | 0 | 0 | 491960
NEPA | 5 | Schuylkill | 91674 | SR 309 over RBMNRR | 309 | 06B | Bridge Restoration | FD | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 122990 | 0 | 0 | 122990
NEPA | 5 | Schuylkill | 91674 | SR 309 over RBMNRR | 309 | 06B | Bridge Restoration | ROW | NHPP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 245980 | 0 | 0 | 245980
NEPA | 5 | Schuylkill | 91674 | SR 309 over RBMNRR | 309 | 06B | Bridge Restoration | ROW | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 61495 | 0 | 0 | 61495
NEPA | 5 | Schuylkill | 91674 | SR 309 over RBMNRR | 309 | 06B | Bridge Restoration | UTL | NHPP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52192 | 52192
NEPA | 5 | Schuylkill | 91674 | SR 309 over RBMNRR | 309 | 06B | Bridge Restoration | UTL | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13048 | 13048
NEPA | 5 | Schuylkill | 91674 | SR 309 over RBMNRR | 309 | 06B | Bridge Restoration | CON | NHPP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4697280 | 4697280
NEPA | 5 | Schuylkill | 91674 | SR 309 over RBMNRR | 309 | 06B | Bridge Restoration | CON | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174320 | 1174320
NEPA | 5 | Schuylkill | 92053 | SR 209 over Mine Hollow Run | 209 | 11B | Bridge Restoration | ROW | 185 | 2027-03-25 |  | 0 | 25750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25750
NEPA | 5 | Schuylkill | 92053 | SR 209 over Mine Hollow Run | 209 | 11B | Bridge Restoration | UTL | 185 | 2027-03-25 |  | 0 | 10609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10609
NEPA | 5 | Schuylkill | 92104 | US 209 over Eagle Hill Run | 209 | 09B | Bridge Restoration | ROW | 185 | 2027-03-25 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
NEPA | 5 | Schuylkill | 92104 | US 209 over Eagle Hill Run | 209 | 09B | Bridge Restoration | UTL | 185 | 2027-03-25 |  | 0 | 10609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10609
NEPA | 5 | Schuylkill | 96441 | 309 Betterment_895 to 443 | 309 | 0 | Highway Restoration | ROW | NHPP | 2029-04-01 |  | 0 | 0 | 0 | 18008 | 0 | 0 | 0 | 0 | 0 | 18008
NEPA | 5 | Schuylkill | 96441 | 309 Betterment_895 to 443 | 309 | 0 | Highway Restoration | ROW | 581 | 2029-04-01 |  | 0 | 0 | 0 | 4502 | 0 | 0 | 0 | 0 | 0 | 4502
NEPA | 5 | Schuylkill | 96441 | 309 Betterment_895 to 443 | 309 | 0 | Highway Restoration | UTL | NHPP | 2029-04-01 |  | 0 | 0 | 0 | 0 | 18548 | 0 | 0 | 0 | 0 | 18548
NEPA | 5 | Schuylkill | 96441 | 309 Betterment_895 to 443 | 309 | 0 | Highway Restoration | UTL | 581 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 4637 | 0 | 0 | 0 | 0 | 4637
NEPA | 5 | Schuylkill | 96441 | 309 Betterment_895 to 443 | 309 | 0 | Highway Restoration | CON | 581 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 4000000 | 4500000 | 3093000 | 0 | 0 | 11593000
NEPA | 5 | Schuylkill | 96470 | St.Clair to Frackville Reconstruction | 61 | 14M | Highway Reconstruction | CON | HSIP | 2023-10-19 | 2023-11-09 | 4500000 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000000
NEPA | 5 | Schuylkill | 96470 | St.Clair to Frackville Reconstruction | 61 | 14M | Highway Reconstruction | CON | NHPP | 2023-10-19 | 2023-11-09 | 10868096 | 1157000 | 4957700 | 318499 | 0 | 0 | 0 | 0 | 0 | 17301295
NEPA | 5 | Schuylkill | 96470 | St.Clair to Frackville Reconstruction | 61 | 14M | Highway Reconstruction | CON | STP | 2023-10-19 | 2023-11-09 | 6915326 | 1500000 | 93910 | 720606 | 4935520 | 0 | 0 | 0 | 0 | 14165362
NEPA | 5 | Schuylkill | 96470 | St.Clair to Frackville Reconstruction | 61 | 14M | Highway Reconstruction | CON | 581 | 2023-10-19 | 2023-11-09 | 8500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500000
NEPA | 5 | Schuylkill | 96470 | St.Clair to Frackville Reconstruction | 61 | 14M | Highway Reconstruction | CON | 581 | 2023-10-19 | 2023-11-09 | 0 | 1050000 | 513848 | 572422 | 1330835 | 1100000 | 6641843 | 0 | 0 | 11208948
NEPA | 5 | Schuylkill | 96565 | 61 Resurf. Walmart Plaza to 1004 | 61 | 15M | Highway Restoration | ROW | NHPP | 2029-04-01 |  | 0 | 0 | 0 | 9004 | 0 | 0 | 0 | 0 | 0 | 9004
NEPA | 5 | Schuylkill | 96565 | 61 Resurf. Walmart Plaza to 1004 | 61 | 15M | Highway Restoration | ROW | 581 | 2029-04-01 |  | 0 | 0 | 0 | 2251 | 0 | 0 | 0 | 0 | 0 | 2251
NEPA | 5 | Schuylkill | 96565 | 61 Resurf. Walmart Plaza to 1004 | 61 | 15M | Highway Restoration | UTL | NHPP | 2029-04-01 |  | 0 | 0 | 0 | 0 | 9276 | 0 | 0 | 0 | 0 | 9276
NEPA | 5 | Schuylkill | 96565 | 61 Resurf. Walmart Plaza to 1004 | 61 | 15M | Highway Restoration | UTL | 581 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 2319 | 0 | 0 | 0 | 0 | 2319
NEPA | 5 | Schuylkill | 96565 | 61 Resurf. Walmart Plaza to 1004 | 61 | 15M | Highway Restoration | CON | NHPP | 2029-04-01 |  | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 500000 | 0 | 2000000
NEPA | 5 | Schuylkill | 96565 | 61 Resurf. Walmart Plaza to 1004 | 61 | 15M | Highway Restoration | CON | STP | 2029-04-01 |  | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 2296500 | 0 | 3796500
NEPA | 5 | Schuylkill | 109993 | 309 Resurface-Ben Titus Road North | 309 | 07M | Highway Restoration | CON | NHPP | 2026-03-12 | 2026-03-12 | 572884 | 1525984 | 500000 | 469016 | 0 | 0 | 0 | 0 | 0 | 3067884
NEPA | 5 | Schuylkill | 109993 | 309 Resurface-Ben Titus Road North | 309 | 07M | Highway Restoration | CON | STP | 2026-03-12 | 2026-03-12 | 797838 | 684278 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 1732116
NEPA | 5 | Schuylkill | 109993 | 309 Resurface-Ben Titus Road North | 309 | 07M | Highway Restoration | CON | 581 | 2026-03-12 | 2026-03-12 | 342680 | 552566 | 187500 | 117253 | 0 | 0 | 0 | 0 | 0 | 1199999
NEPA | 5 | Schuylkill | 109995 | 443 over Mill Creek | 443 | 02B | Bridge Replacement | CON | BRIP | 2025-09-25 | 2025-09-25 | 1538885 | 341845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1880730
NEPA | 5 | Schuylkill | 109995 | 443 over Mill Creek | 443 | 02B | Bridge Replacement | CON | STP | 2025-09-25 | 2025-09-25 | 669925 | 480075 | 234000 | 0 | 0 | 0 | 0 | 0 | 0 | 1384000
NEPA | 5 | Schuylkill | 114329 | NEPA Br Pres. & Repair #9 | 54 | BRM | Bridge Preservation - State Funded | PE | 185 | 2029-04-01 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
NEPA | 5 | Schuylkill | 114329 | NEPA Br Pres. & Repair #9 | 54 | BRM | Bridge Preservation - State Funded | CON | 185 | 2029-04-01 |  | 0 | 0 | 0 | 2813750 | 0 | 0 | 0 | 0 | 0 | 2813750
NEPA | 5 | Schuylkill | 115460 | Coaldale Hospital Ped Facilities & Klines Hill Rd |  | CAR | Highway Restoration | CON | APL | 2025-11-06 | 2025-11-06 | 644718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 644718
NEPA | 5 | Schuylkill | 116252 | Orwigsburg Industrial Park Access Road |  | OIP | Highway Reconstruction | CON | APL | 2027-01-28 |  | 1563666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1563666
NEPA | 5 | Schuylkill | 116252 | Orwigsburg Industrial Park Access Road |  | OIP | Highway Reconstruction | CON | LOC | 2027-01-28 |  | 267240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267240
NEPA | 5 | Schuylkill | 116811 | Box Culvert Bundle - Round 1 | 209 | BCB | Bridge Replacement | PE | 185 | 2027-03-25 |  | 38850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38850
NEPA | 5 | Schuylkill | 116811 | Box Culvert Bundle - Round 1 | 209 | BCB | Bridge Replacement | FD | 185 | 2027-03-25 |  | 1287500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1287500
NEPA | 5 | Schuylkill | 116811 | Box Culvert Bundle - Round 1 | 209 | BCB | Bridge Replacement | CON | 185 | 2027-03-25 |  | 0 | 0 | 1800000 | 1200000 | 3448900 | 0 | 0 | 0 | 0 | 6448900
NEPA | 5 | Schuylkill | 117330 | Paradise Rd over Upper Little Swatara Crk | 3002 | 01B | Bridge Replacement | FD | BOF | 2027-04-08 |  | 0 | 300000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
NEPA | 5 | Schuylkill | 117330 | Paradise Rd over Upper Little Swatara Crk | 3002 | 01B | Bridge Replacement | ROW | BOF | 2027-04-08 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
NEPA | 5 | Schuylkill | 117330 | Paradise Rd over Upper Little Swatara Crk | 3002 | 01B | Bridge Replacement | ROW | 581 | 2027-04-08 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
NEPA | 5 | Schuylkill | 117330 | Paradise Rd over Upper Little Swatara Crk | 3002 | 01B | Bridge Replacement | CON | BOF | 2027-04-08 |  | 0 | 0 | 0 | 1000000 | 800800 | 0 | 0 | 0 | 0 | 1800800
NEPA | 5 | Schuylkill | 117330 | Paradise Rd over Upper Little Swatara Crk | 3002 | 01B | Bridge Replacement | CON | 581 | 2027-04-08 |  | 0 | 0 | 0 | 250000 | 200200 | 0 | 0 | 0 | 0 | 450200
NEPA | 5 | Schuylkill | 117478 | Raven Run Road (SR 4031) over Shenandoah Creek | 4031 | 01B | Bridge Restoration | FD | BOF | 2027-10-21 |  | 347780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347780
NEPA | 5 | Schuylkill | 117478 | Raven Run Road (SR 4031) over Shenandoah Creek | 4031 | 01B | Bridge Restoration | ROW | BOF | 2027-10-21 |  | 20100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20100
NEPA | 5 | Schuylkill | 117478 | Raven Run Road (SR 4031) over Shenandoah Creek | 4031 | 01B | Bridge Restoration | UTL | BOF | 2027-10-21 |  | 0 | 0 | 15200 | 0 | 0 | 0 | 0 | 0 | 0 | 15200
NEPA | 5 | Schuylkill | 117478 | Raven Run Road (SR 4031) over Shenandoah Creek | 4031 | 01B | Bridge Restoration | UTL | 581 | 2027-10-21 |  | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 3800
NEPA | 5 | Schuylkill | 117478 | Raven Run Road (SR 4031) over Shenandoah Creek | 4031 | 01B | Bridge Restoration | CON | BOF | 2027-10-21 |  | 0 | 0 | 375000 | 486404 | 0 | 0 | 0 | 0 | 0 | 861404
NEPA | 5 | Schuylkill | 117478 | Raven Run Road (SR 4031) over Shenandoah Creek | 4031 | 01B | Bridge Restoration | CON | 581 | 2027-10-21 |  | 0 | 0 | 93750 | 121601 | 0 | 0 | 0 | 0 | 0 | 215351
NEPA | 5 | Schuylkill | 117599 | Centre St over trib Shenandoah Crk | 54 | 07B | Bridge Replacement | ROW | 185 | 2027-11-04 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
NEPA | 5 | Schuylkill | 117599 | Centre St over trib Shenandoah Crk | 54 | 07B | Bridge Replacement | UTL | 185 | 2027-11-04 |  | 0 | 0 | 10300 | 0 | 0 | 0 | 0 | 0 | 0 | 10300
NEPA | 5 | Schuylkill | 117607 | Suedberg Road over trib. to Swatara Creek | 443 | 04B | Bridge Restoration | ROW | 185 | 2027-03-25 |  | 0 | 139000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139000
NEPA | 5 | Schuylkill | 117607 | Suedberg Road over trib. to Swatara Creek | 443 | 04B | Bridge Restoration | UTL | 185 | 2027-03-25 |  | 0 | 0 | 10609 | 0 | 0 | 0 | 0 | 0 | 0 | 10609
NEPA | 5 | Schuylkill | 120802 | SR 183/SR 901 Cressona Intersection | 183 | 0XS | Study Phase of Project | STUDY | STP | 2030-03-01 |  | 0 | 175000 | 90225 | 0 | 0 | 0 | 0 | 0 | 0 | 265225
NEPA | 5 | Schuylkill | 120809 | Centre Street over Mahanoy Creek | 54 | PM8 | Bridge Preservation - State Funded | ROW | 581 | 2026-10-22 |  | 0 | 19400 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 34400
NEPA | 5 | Schuylkill | 120810 | SR 209 over Railroad | 209 | BRM | Bridge Preservation - State Funded | ROW | 581 | 2026-10-22 |  | 0 | 66200 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 116200
NEPA | 5 | Schuylkill | 120979 | NEPA Camera Gaps | 81 | ITC | Intelligent Transportation System | PE | CRP | 2026-01-15 | 2026-01-15 | 24713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24713
NEPA | 5 | Schuylkill | 120979 | NEPA Camera Gaps | 81 | ITC | Intelligent Transportation System | PE | STP | 2026-01-15 | 2026-01-15 | 6178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6178
NEPA | 5 | Schuylkill | 120979 | NEPA Camera Gaps | 81 | ITC | Intelligent Transportation System | FD | CRP | 2026-01-15 | 2026-01-15 | 1953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1953
NEPA | 5 | Schuylkill | 120979 | NEPA Camera Gaps | 81 | ITC | Intelligent Transportation System | FD | STP | 2026-01-15 | 2026-01-15 | 0 | 589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 589
NEPA | 5 | Schuylkill | 120979 | NEPA Camera Gaps | 81 | ITC | Intelligent Transportation System | CON | CRP | 2026-01-15 | 2026-01-15 | 0 | 281412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281412
NEPA | 5 | Schuylkill | 120979 | NEPA Camera Gaps | 81 | ITC | Intelligent Transportation System | CON | STP | 2026-01-15 | 2026-01-15 | 0 | 70353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70353
NEPA | 5 | Schuylkill | 120980 | NEPA All Weather Pavement Markings 2025 | 81 | AWT | Safety Improvement | CON | NHPP | 2025-03-13 | 2025-03-13 | 0 | 697000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697000
NEPA | 5 | Schuylkill | 120980 | NEPA All Weather Pavement Markings 2025 | 81 | AWT | Safety Improvement | CON | STP | 2025-03-13 | 2025-03-13 | 140664 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 340664
NEPA | 5 | Schuylkill | 120984 | Bridge Overlay Bundle 3 | 443 | BOB | Bridge Preservation - Federal | PE | 185 | 2027-04-01 |  | 105000 | 101000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206000
NEPA | 5 | Schuylkill | 120984 | Bridge Overlay Bundle 3 | 443 | BOB | Bridge Preservation - Federal | CON | BRIP | 2027-04-01 |  | 0 | 0 | 2000000 | 185400 | 0 | 0 | 0 | 0 | 0 | 2185400
NEPA | 5 | Schuylkill | 120986 | NEPA BPN4 Guiderail Upgrades 2025/2026 | 895 | BPN | Safety Improvement | CON | 581 |  |  | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 200000
NEPA | 5 | Schuylkill | 121534 | Schuylkill River Trail Mill Creek | 1027 | SRT | Bicycle Pedestrian Highway | CON | TAP | 2026-07-02 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
NEPA | 5 | Schuylkill | 121538 | Tri-Valley School District School Zone Signals | 25 | TVS | Transportation Enhancement | CON | TAP | 2026-08-13 |  | 0 | 91648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91648
NEPA | 5 | Schuylkill | 121545 | Tamaqua Riverwalk |  |  | Transportation Enhancement | CON | TAP | 2026-10-22 |  | 0 | 0 | 424000 | 0 | 0 | 0 | 0 | 0 | 0 | 424000
NEPA | 5 | Schuylkill | 122242 | Kline Twp 3 Repair Critical Deteriorated Section |  | KRC | MultiModal | PE | 411 |  |  | 4305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4305
NEPA | 5 | Schuylkill | 122242 | Kline Twp 3 Repair Critical Deteriorated Section |  | KRC | MultiModal | PE | LOC |  |  | 1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1845
NEPA | 5 | Schuylkill | 122242 | Kline Twp 3 Repair Critical Deteriorated Section |  | KRC | MultiModal | CON | 411 |  |  | 211717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211717
NEPA | 5 | Schuylkill | 122242 | Kline Twp 3 Repair Critical Deteriorated Section |  | KRC | MultiModal | CON | LOC |  |  | 90736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90736
NEPA | 5 | Schuylkill | 123337 | 309/895 Intersection Safety Improvements | 309 | 04S | Safety Improvement | STUDY | HSIP |  |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
North Central | 2 | Cameron | 68864 | Bridge over Cooks Run | 4004 | A05 | Bridge Replacement | PE | BOF | 2028-03-23 |  | 124639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124639
North Central | 2 | Cameron | 68864 | Bridge over Cooks Run | 4004 | A05 | Bridge Replacement | PE | 581 | 2028-03-23 |  | 19400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19400
North Central | 2 | Cameron | 68864 | Bridge over Cooks Run | 4004 | A05 | Bridge Replacement | FD | BOF | 2028-03-23 |  | 0 | 200000 | 138152 | 0 | 0 | 0 | 0 | 0 | 0 | 338152
North Central | 2 | Cameron | 68864 | Bridge over Cooks Run | 4004 | A05 | Bridge Replacement | ROW | BOF | 2028-03-23 |  | 0 | 0 | 55775 | 0 | 0 | 0 | 0 | 0 | 0 | 55775
North Central | 2 | Cameron | 68864 | Bridge over Cooks Run | 4004 | A05 | Bridge Replacement | UTL | BOF | 2028-03-23 |  | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 0 | 56275
North Central | 2 | Cameron | 68864 | Bridge over Cooks Run | 4004 | A05 | Bridge Replacement | CON | BOF | 2028-03-23 |  | 0 | 0 | 0 | 926420 | 0 | 0 | 0 | 0 | 0 | 926420
North Central | 2 | Cameron | 68864 | Bridge over Cooks Run | 4004 | A05 | Bridge Replacement | CON | 185 | 2028-03-23 |  | 0 | 0 | 0 | 231855 | 0 | 0 | 0 | 0 | 0 | 231855
North Central | 2 | Cameron | 68897 | Bridge over Eddies Run | 46 | A03 | Bridge Replacement | PE | 185 | 2028-04-27 |  | 0 | 258945 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 458945
North Central | 2 | Cameron | 68897 | Bridge over Eddies Run | 46 | A03 | Bridge Replacement | FD | 185 | 2028-04-27 |  | 0 | 0 | 338438 | 0 | 0 | 0 | 0 | 0 | 0 | 338438
North Central | 2 | Cameron | 68897 | Bridge over Eddies Run | 46 | A03 | Bridge Replacement | ROW | 185 | 2028-04-27 |  | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 0 | 56275
North Central | 2 | Cameron | 68897 | Bridge over Eddies Run | 46 | A03 | Bridge Replacement | UTL | 185 | 2028-04-27 |  | 0 | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 56275
North Central | 2 | Cameron | 68897 | Bridge over Eddies Run | 46 | A03 | Bridge Replacement | CON | 581 | 2028-04-27 |  | 0 | 0 | 0 | 868456 | 0 | 0 | 0 | 0 | 0 | 868456
North Central | 2 | Cameron | 74082 | SR 120 ov W Creek Bridge | 120 | A20 | Bridge Restoration | PE | 581 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581378 | 581378
North Central | 2 | Cameron | 74082 | SR 120 ov W Creek Bridge | 120 | A20 | Bridge Restoration | FD | 581 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415270 | 415270
North Central | 2 | Cameron | 74082 | SR 120 ov W Creek Bridge | 120 | A20 | Bridge Restoration | ROW | 581 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103818 | 103818
North Central | 2 | Cameron | 74082 | SR 120 ov W Creek Bridge | 120 | A20 | Bridge Restoration | UTL | 581 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103818 | 103818
North Central | 2 | Cameron | 74082 | SR 120 ov W Creek Bridge | 120 | A20 | Bridge Restoration | CON | BRIP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021000 | 2021000
North Central | 2 | Cameron | 74082 | SR 120 ov W Creek Bridge | 120 | A20 | Bridge Restoration | CON | STP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1577008 | 1577008
North Central | 2 | Cameron | 74082 | SR 120 ov W Creek Bridge | 120 | A20 | Bridge Restoration | CON | 581 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 899752 | 899752
North Central | 2 | Cameron | 82190 | Portage Creek | 155 | A04 | Bridge Restoration | PE | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581378 | 581378
North Central | 2 | Cameron | 82190 | Portage Creek | 155 | A04 | Bridge Restoration | FD | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415270 | 415270
North Central | 2 | Cameron | 82190 | Portage Creek | 155 | A04 | Bridge Restoration | ROW | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103818 | 103818
North Central | 2 | Cameron | 82190 | Portage Creek | 155 | A04 | Bridge Restoration | UTL | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103818 | 103818
North Central | 2 | Cameron | 82190 | Portage Creek | 155 | A04 | Bridge Restoration | CON | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599009 | 3599009
North Central | 2 | Cameron | 85085 | SR 46 over Dodge Hollow | 46 | A02 | Bridge Restoration | PE | 185 | 2026-03-26 | 2026-03-26 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Cameron | 85085 | SR 46 over Dodge Hollow | 46 | A02 | Bridge Restoration | FD | 185 | 2026-03-26 | 2026-03-26 | 273182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273182
North Central | 2 | Cameron | 85085 | SR 46 over Dodge Hollow | 46 | A02 | Bridge Restoration | ROW | 185 | 2026-03-26 | 2026-03-26 | 52450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52450
North Central | 2 | Cameron | 85085 | SR 46 over Dodge Hollow | 46 | A02 | Bridge Restoration | UTL | 185 | 2026-03-26 | 2026-03-26 | 86946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86946
North Central | 2 | Cameron | 85085 | SR 46 over Dodge Hollow | 46 | A02 | Bridge Restoration | CON | 581 | 2026-03-26 | 2026-03-26 | 0 | 764909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 764909
North Central | 2 | Cameron | 85102 | SR 4004 ov Little Elk Crk | 4004 | A04 | Bridge Restoration | PE | BOF | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501502 | 501502
North Central | 2 | Cameron | 85102 | SR 4004 ov Little Elk Crk | 4004 | A04 | Bridge Restoration | FD | BOF | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368962 | 368962
North Central | 2 | Cameron | 85102 | SR 4004 ov Little Elk Crk | 4004 | A04 | Bridge Restoration | ROW | BOF | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92420 | 92420
North Central | 2 | Cameron | 85102 | SR 4004 ov Little Elk Crk | 4004 | A04 | Bridge Restoration | UTL | BOF | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92420 | 92420
North Central | 2 | Cameron | 85102 | SR 4004 ov Little Elk Crk | 4004 | A04 | Bridge Restoration | CON | BOF | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950718 | 950718
North Central | 2 | Cameron | 85102 | SR 4004 ov Little Elk Crk | 4004 | A04 | Bridge Restoration | CON | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237520 | 237520
North Central | 2 | Cameron | 88295 | SR 0046 Betterment Proj | 46 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5359629 | 5359629
North Central | 2 | Cameron | 93363 | Elk Co Lin/Empor Resurfac | 120 | 408 | Highway Restoration | PE | 581 | 2026-04-09 |  | 0 | 100000 | 0 | 0 | 553694 | 0 | 0 | 0 | 0 | 653694
North Central | 2 | Cameron | 93363 | Elk Co Lin/Empor Resurfac | 120 | 408 | Highway Restoration | FD | 581 | 2026-04-09 |  | 0 | 0 | 0 | 0 | 0 | 415271 | 0 | 0 | 0 | 415271
North Central | 2 | Cameron | 93363 | Elk Co Lin/Empor Resurfac | 120 | 408 | Highway Restoration | ROW | 581 | 2026-04-09 |  | 0 | 0 | 0 | 0 | 0 | 138424 | 0 | 0 | 0 | 138424
North Central | 2 | Cameron | 93363 | Elk Co Lin/Empor Resurfac | 120 | 408 | Highway Restoration | UTL | 581 | 2026-04-09 |  | 0 | 0 | 0 | 0 | 0 | 138424 | 0 | 0 | 0 | 138424
North Central | 2 | Cameron | 93363 | Elk Co Lin/Empor Resurfac | 120 | 408 | Highway Restoration | CON | BRIP | 2026-04-09 |  | 0 | 520000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 570000
North Central | 2 | Cameron | 93363 | Elk Co Lin/Empor Resurfac | 120 | 408 | Highway Restoration | CON | STP | 2026-04-09 |  | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
North Central | 2 | Cameron | 93363 | Elk Co Lin/Empor Resurfac | 120 | 408 | Highway Restoration | CON | 581 | 2026-04-09 |  | 0 | 2000000 | 0 | 0 | 0 | 6513465 | 4634112 | 0 | 0 | 13147577
North Central | 2 | Cameron | 95989 | T-330, Salt Run | 7205 | REM | Bridge Removal | ROW | 581 | 2025-05-22 | 2025-05-22 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
North Central | 2 | Cameron | 95989 | T-330, Salt Run | 7205 | REM | Bridge Removal | ROW | 581 | 2025-05-22 | 2025-05-22 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Cameron | 95989 | T-330, Salt Run | 7205 | REM | Bridge Removal | CON | 581 | 2025-05-22 | 2025-05-22 | 225000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
North Central | 2 | Cameron | 112748 | Branch Wykoff Run | 2001 | A07 | Bridge Restoration | PE | 185 | 2028-01-01 |  | 0 | 0 | 213714 | 273689 | 0 | 0 | 0 | 0 | 0 | 487403
North Central | 2 | Cameron | 112748 | Branch Wykoff Run | 2001 | A07 | Bridge Restoration | FD | 581 | 2028-01-01 |  | 0 | 0 | 0 | 289818 | 0 | 0 | 0 | 0 | 0 | 289818
North Central | 2 | Cameron | 112748 | Branch Wykoff Run | 2001 | A07 | Bridge Restoration | ROW | 581 | 2028-01-01 |  | 0 | 0 | 0 | 57963 | 0 | 0 | 0 | 0 | 0 | 57963
North Central | 2 | Cameron | 112748 | Branch Wykoff Run | 2001 | A07 | Bridge Restoration | UTL | 185 | 2028-01-01 |  | 0 | 0 | 0 | 63439 | 0 | 0 | 0 | 0 | 0 | 63439
North Central | 2 | Cameron | 112748 | Branch Wykoff Run | 2001 | A07 | Bridge Restoration | CON | 185 | 2028-01-01 |  | 0 | 0 | 0 | 0 | 1007490 | 0 | 0 | 0 | 0 | 1007490
North Central | 2 | Cameron | 113118 | SR 872 over Joe's Run | 872 | A01 | Bridge Replacement | PE | 581 | 2027-10-21 |  | 430578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430578
North Central | 2 | Cameron | 113118 | SR 872 over Joe's Run | 872 | A01 | Bridge Replacement | FD | 581 | 2027-10-21 |  | 0 | 273182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273182
North Central | 2 | Cameron | 113118 | SR 872 over Joe's Run | 872 | A01 | Bridge Replacement | ROW | 581 | 2027-10-21 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
North Central | 2 | Cameron | 113118 | SR 872 over Joe's Run | 872 | A01 | Bridge Replacement | UTL | 581 | 2027-10-21 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
North Central | 2 | Cameron | 113118 | SR 872 over Joe's Run | 872 | A01 | Bridge Replacement | CON | 185 | 2027-10-21 |  | 0 | 0 | 844132 | 0 | 0 | 0 | 0 | 0 | 0 | 844132
North Central | 2 | Cameron | 116620 | SR 120 East Allegany Avenue | 120 | 407 | Highway Restoration | FD | STP | 2025-12-04 | 2025-10-23 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
North Central | 2 | Cameron | 116620 | SR 120 East Allegany Avenue | 120 | 407 | Highway Restoration | ROW | STP | 2025-12-04 | 2025-10-23 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Cameron | 116620 | SR 120 East Allegany Avenue | 120 | 407 | Highway Restoration | UTL | STP | 2025-12-04 | 2025-10-23 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Cameron | 116620 | SR 120 East Allegany Avenue | 120 | 407 | Highway Restoration | CON | STP | 2025-12-04 | 2025-10-23 | 3574464 | 1127823 | 0 | 1368984 | 0 | 0 | 0 | 0 | 0 | 6071271
North Central | 2 | Cameron | 116620 | SR 120 East Allegany Avenue | 120 | 407 | Highway Restoration | CON | 581 | 2025-12-04 | 2025-10-23 | 2511102 | 472828 | 744496 | 0 | 0 | 0 | 0 | 0 | 0 | 3728426
North Central | 2 | Cameron | 116842 | SR 155 over Sycamore Run | 155 | A05 | Bridge Replacement | PE | 185 | 2029-01-25 |  | 0 | 0 | 450203 | 0 | 0 | 0 | 0 | 0 | 0 | 450203
North Central | 2 | Cameron | 116842 | SR 155 over Sycamore Run | 155 | A05 | Bridge Replacement | FD | 581 | 2029-01-25 |  | 0 | 0 | 0 | 347782 | 0 | 0 | 0 | 0 | 0 | 347782
North Central | 2 | Cameron | 116842 | SR 155 over Sycamore Run | 155 | A05 | Bridge Replacement | ROW | 581 | 2029-01-25 |  | 0 | 0 | 0 | 57963 | 0 | 0 | 0 | 0 | 0 | 57963
North Central | 2 | Cameron | 116842 | SR 155 over Sycamore Run | 155 | A05 | Bridge Replacement | UTL | 581 | 2029-01-25 |  | 0 | 0 | 0 | 57963 | 0 | 0 | 0 | 0 | 0 | 57963
North Central | 2 | Cameron | 116842 | SR 155 over Sycamore Run | 155 | A05 | Bridge Replacement | CON | STP | 2029-01-25 |  | 0 | 0 | 0 | 0 | 1194052 | 0 | 0 | 0 | 0 | 1194052
North Central | 2 | Cameron | 116862 | SR 555 over Beaver Dam Run | 555 | A03 | Bridge Replacement | PE | 185 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581378 | 581378
North Central | 2 | Cameron | 116862 | SR 555 over Beaver Dam Run | 555 | A03 | Bridge Replacement | ROW | 185 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69212 | 69212
North Central | 2 | Cameron | 116862 | SR 555 over Beaver Dam Run | 555 | A03 | Bridge Replacement | UTL | 185 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69212 | 69212
North Central | 2 | Cameron | 116862 | SR 555 over Beaver Dam Run | 555 | A03 | Bridge Replacement | CON | 185 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1838176 | 1838176
North Central | 2 | Cameron | 116863 | SR 4004 over Bobby Run | 4004 | A07 | Bridge Replacement | PE | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581378 | 581378
North Central | 2 | Cameron | 116863 | SR 4004 over Bobby Run | 4004 | A07 | Bridge Replacement | ROW | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69212 | 69212
North Central | 2 | Cameron | 116863 | SR 4004 over Bobby Run | 4004 | A07 | Bridge Replacement | UTL | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69212 | 69212
North Central | 2 | Cameron | 116863 | SR 4004 over Bobby Run | 4004 | A07 | Bridge Replacement | CON | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 830540 | 830540
North Central | 2 | Cameron | 116863 | SR 4004 over Bobby Run | 4004 | A07 | Bridge Replacement | CON | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1007635 | 1007635
North Central | 2 | Cameron | 116867 | SR 4004 over Driftwood Branch | 4004 | A06 | Bridge Replacement | PE | BOF | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 692117 | 692117
North Central | 2 | Cameron | 116867 | SR 4004 over Driftwood Branch | 4004 | A06 | Bridge Replacement | FD | BOF | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415271 | 415271
North Central | 2 | Cameron | 116867 | SR 4004 over Driftwood Branch | 4004 | A06 | Bridge Replacement | ROW | BOF | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69212 | 69212
North Central | 2 | Cameron | 116867 | SR 4004 over Driftwood Branch | 4004 | A06 | Bridge Replacement | UTL | BOF | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69212 | 69212
North Central | 2 | Cameron | 116867 | SR 4004 over Driftwood Branch | 4004 | A06 | Bridge Replacement | CON | BOF | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879207 | 2879207
North Central | 2 | Cameron | 116867 | SR 4004 over Driftwood Branch | 4004 | A06 | Bridge Replacement | CON | 185 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719802 | 719802
North Central | 2 | Cameron | 116868 | SR 46 over North Creek | 46 | A05 | Bridge Replacement | PE | 581 | 2029-04-30 |  | 0 | 0 | 0 | 579638 | 0 | 0 | 0 | 0 | 0 | 579638
North Central | 2 | Cameron | 116868 | SR 46 over North Creek | 46 | A05 | Bridge Replacement | FD | STP | 2029-04-30 |  | 0 | 0 | 0 | 0 | 281378 | 0 | 0 | 0 | 0 | 281378
North Central | 2 | Cameron | 116868 | SR 46 over North Creek | 46 | A05 | Bridge Replacement | ROW | STP | 2029-04-30 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
North Central | 2 | Cameron | 116868 | SR 46 over North Creek | 46 | A05 | Bridge Replacement | UTL | STP | 2029-04-30 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
North Central | 2 | Cameron | 116868 | SR 46 over North Creek | 46 | A05 | Bridge Replacement | CON | STP | 2029-04-30 |  | 0 | 0 | 0 | 0 | 0 | 1869408 | 0 | 0 | 0 | 1869408
North Central | 2 | Cameron | 116868 | SR 46 over North Creek | 46 | A05 | Bridge Replacement | CON | 185 | 2029-04-30 |  | 0 | 0 | 0 | 0 | 0 | 467352 | 0 | 0 | 0 | 467352
North Central | 2 | Cameron | 116888 | 2026 North Central Bridge Preservation | 120 | P51 | Bridge Restoration | PE | BRIP | 2027-04-29 |  | 0 | 307090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307090
North Central | 2 | Cameron | 116888 | 2026 North Central Bridge Preservation | 120 | P51 | Bridge Restoration | PE | STP | 2027-04-29 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
North Central | 2 | Cameron | 116888 | 2026 North Central Bridge Preservation | 120 | P51 | Bridge Restoration | ROW | BRIP | 2027-04-29 |  | 0 | 0 | 112551 | 0 | 0 | 0 | 0 | 0 | 0 | 112551
North Central | 2 | Cameron | 116888 | 2026 North Central Bridge Preservation | 120 | P51 | Bridge Restoration | UTL | BRIP | 2027-04-29 |  | 0 | 0 | 112551 | 0 | 0 | 0 | 0 | 0 | 0 | 112551
North Central | 2 | Cameron | 116888 | 2026 North Central Bridge Preservation | 120 | P51 | Bridge Restoration | CON | BOF | 2027-04-29 |  | 0 | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 480000
North Central | 2 | Cameron | 116888 | 2026 North Central Bridge Preservation | 120 | P51 | Bridge Restoration | CON | BRIP | 2027-04-29 |  | 0 | 0 | 0 | 2376710 | 0 | 0 | 0 | 0 | 0 | 2376710
North Central | 2 | Cameron | 117040 | NC Bridge Preservation 4 | 155 | P60 | Bridge Restoration | PE | STP | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455450 | 455450
North Central | 2 | Cameron | 117040 | NC Bridge Preservation 4 | 155 | P60 | Bridge Restoration | ROW | STP | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69212 | 69212
North Central | 2 | Cameron | 117040 | NC Bridge Preservation 4 | 155 | P60 | Bridge Restoration | UTL | STP | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69212 | 69212
North Central | 2 | Cameron | 117040 | NC Bridge Preservation 4 | 155 | P60 | Bridge Restoration | CON | STP | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2217775 | 2217775
North Central | 2 | Cameron | 117040 | NC Bridge Preservation 4 | 155 | P60 | Bridge Restoration | CON | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546694 | 546694
North Central | 2 | Cameron | 118629 | T-306 Steam Mill Road Bridge (II) | 7203 | LOC | Bridge Replacement | FD | BOF | 2026-03-26 | 2026-03-26 | 274482 | 15518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290000
North Central | 2 | Cameron | 118629 | T-306 Steam Mill Road Bridge (II) | 7203 | LOC | Bridge Replacement | ROW | BOF | 2026-03-26 | 2026-03-26 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
North Central | 2 | Cameron | 118629 | T-306 Steam Mill Road Bridge (II) | 7203 | LOC | Bridge Replacement | CON | BOF | 2026-03-26 | 2026-03-26 | 0 | 165140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165140
North Central | 2 | Cameron | 118629 | T-306 Steam Mill Road Bridge (II) | 7203 | LOC | Bridge Replacement | CON | RURAL | 2026-03-26 | 2026-03-26 | 0 | 879888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 879888
North Central | 2 | Cameron | 118629 | T-306 Steam Mill Road Bridge (II) | 7203 | LOC | Bridge Replacement | CON | 185 | 2026-03-26 | 2026-03-26 | 0 | 219972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219972
North Central | 2 | Cameron | 118670 | SR 555 Roadway and Slope Stability | 555 | 409 | Highway Restoration | PE | 581 | 2025-12-11 | 2025-12-11 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Cameron | 118670 | SR 555 Roadway and Slope Stability | 555 | 409 | Highway Restoration | FD | PRTCT | 2025-12-11 | 2025-12-11 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
North Central | 2 | Cameron | 118670 | SR 555 Roadway and Slope Stability | 555 | 409 | Highway Restoration | ROW | 581 | 2025-12-11 | 2025-12-11 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
North Central | 2 | Cameron | 118670 | SR 555 Roadway and Slope Stability | 555 | 409 | Highway Restoration | CON | PRTCT | 2025-12-11 | 2025-12-11 | 417905 | 862095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280000
North Central | 2 | Cameron | 118670 | SR 555 Roadway and Slope Stability | 555 | 409 | Highway Restoration | CON | 581 | 2025-12-11 | 2025-12-11 | 0 | 0 | 444509 | 0 | 0 | 0 | 0 | 0 | 0 | 444509
North Central | 2 | Cameron | 119319 | North Central VRU Project | 120 | 0 | Safety Improvement | PE | HVRU | 2027-03-11 |  | 384503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384503
North Central | 2 | Cameron | 119851 | SR 872 over Lick Island Run | 872 | A02 | Bridge Replacement | PE | BRIP | 2029-03-29 |  | 0 | 0 | 272714 | 200000 | 0 | 0 | 0 | 0 | 0 | 472714
North Central | 2 | Cameron | 119851 | SR 872 over Lick Island Run | 872 | A02 | Bridge Replacement | FD | STP | 2029-03-29 |  | 0 | 0 | 0 | 373702 | 0 | 0 | 0 | 0 | 0 | 373702
North Central | 2 | Cameron | 119851 | SR 872 over Lick Island Run | 872 | A02 | Bridge Replacement | ROW | 581 | 2029-03-29 |  | 0 | 0 | 0 | 57963 | 0 | 0 | 0 | 0 | 0 | 57963
North Central | 2 | Cameron | 119851 | SR 872 over Lick Island Run | 872 | A02 | Bridge Replacement | UTL | 581 | 2029-03-29 |  | 0 | 0 | 0 | 57963 | 0 | 0 | 0 | 0 | 0 | 57963
North Central | 2 | Cameron | 119851 | SR 872 over Lick Island Run | 872 | A02 | Bridge Replacement | CON | BRIP | 2029-03-29 |  | 0 | 0 | 0 | 0 | 505000 | 0 | 0 | 0 | 0 | 505000
North Central | 2 | Cameron | 119851 | SR 872 over Lick Island Run | 872 | A02 | Bridge Replacement | CON | STP | 2029-03-29 |  | 0 | 0 | 0 | 0 | 330837 | 0 | 0 | 0 | 0 | 330837
North Central | 2 | Cameron | 119852 | SR 3001 Broad Street Bridge | 3001 | A02 | Bridge Replacement | PE | 185 | 2029-09-13 |  | 0 | 0 | 0 | 0 | 0 | 491950 | 0 | 0 | 0 | 491950
North Central | 2 | Cameron | 119852 | SR 3001 Broad Street Bridge | 3001 | A02 | Bridge Replacement | CON | BOF | 2029-09-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1962591 | 0 | 1962591
North Central | 2 | Cameron | 121037 | SR 120 over Driftwood Branch Pres | 120 | P52 | Bridge Preservation - Federal | PE | STP |  |  | 0 | 0 | 0 | 0 | 501502 | 0 | 0 | 0 | 0 | 501502
North Central | 2 | Cameron | 121037 | SR 120 over Driftwood Branch Pres | 120 | P52 | Bridge Preservation - Federal | FD | STP |  |  | 0 | 0 | 0 | 0 | 0 | 368962 | 0 | 0 | 0 | 368962
North Central | 2 | Cameron | 121037 | SR 120 over Driftwood Branch Pres | 120 | P52 | Bridge Preservation - Federal | ROW | STP |  |  | 0 | 0 | 0 | 0 | 0 | 92241 | 0 | 0 | 0 | 92241
North Central | 2 | Cameron | 121037 | SR 120 over Driftwood Branch Pres | 120 | P52 | Bridge Preservation - Federal | UTL | STP |  |  | 0 | 0 | 0 | 0 | 0 | 92241 | 0 | 0 | 0 | 92241
North Central | 2 | Cameron | 121037 | SR 120 over Driftwood Branch Pres | 120 | P52 | Bridge Preservation - Federal | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1357978 | 0 | 0 | 1357978
North Central | 2 | Cameron | 121037 | SR 120 over Driftwood Branch Pres | 120 | P52 | Bridge Preservation - Federal | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 339494 | 0 | 0 | 339494
North Central | 2 | Clearfield | 3410 | Montgomery Run Bridge Box | 1004 | A02 | Bridge Restoration | PE | 581 | 2026-07-30 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Clearfield | 3410 | Montgomery Run Bridge Box | 1004 | A02 | Bridge Restoration | FD | 185 | 2026-07-30 |  | 265225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265225
North Central | 2 | Clearfield | 3410 | Montgomery Run Bridge Box | 1004 | A02 | Bridge Restoration | ROW | 185 | 2026-07-30 |  | 45776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45776
North Central | 2 | Clearfield | 3410 | Montgomery Run Bridge Box | 1004 | A02 | Bridge Restoration | UTL | 185 | 2026-07-30 |  | 65776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65776
North Central | 2 | Clearfield | 3410 | Montgomery Run Bridge Box | 1004 | A02 | Bridge Restoration | CON | 185 | 2026-07-30 |  | 0 | 373809 | 484490 | 0 | 0 | 0 | 0 | 0 | 0 | 858299
North Central | 2 | Clearfield | 3449 | SR 4009 Conrail Br. | 4009 | A01 | Bridge Restoration | PE | BOF | 2026-10-22 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Clearfield | 3449 | SR 4009 Conrail Br. | 4009 | A01 | Bridge Restoration | FD | BOF | 2026-10-22 |  | 0 | 227818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227818
North Central | 2 | Clearfield | 3449 | SR 4009 Conrail Br. | 4009 | A01 | Bridge Restoration | ROW | BOF | 2026-10-22 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
North Central | 2 | Clearfield | 3449 | SR 4009 Conrail Br. | 4009 | A01 | Bridge Restoration | UTL | BOF | 2026-10-22 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
North Central | 2 | Clearfield | 3449 | SR 4009 Conrail Br. | 4009 | A01 | Bridge Restoration | CON | BOF | 2026-10-22 |  | 0 | 1012164 | 665051 | 437558 | 418598 | 0 | 0 | 0 | 0 | 2533371
North Central | 2 | Clearfield | 3557 | PA 153 Beaver Run Br. | 153 | A04 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 272714 | 200000 | 0 | 0 | 0 | 0 | 0 | 472714
North Central | 2 | Clearfield | 3557 | PA 153 Beaver Run Br. | 153 | A04 | Bridge Restoration | FD | STP |  |  | 0 | 0 | 0 | 246449 | 0 | 0 | 0 | 0 | 0 | 246449
North Central | 2 | Clearfield | 3557 | PA 153 Beaver Run Br. | 153 | A04 | Bridge Restoration | ROW | STP |  |  | 0 | 0 | 0 | 86946 | 0 | 0 | 0 | 0 | 0 | 86946
North Central | 2 | Clearfield | 3557 | PA 153 Beaver Run Br. | 153 | A04 | Bridge Restoration | UTL | STP |  |  | 0 | 0 | 0 | 86946 | 0 | 0 | 0 | 0 | 0 | 86946
North Central | 2 | Clearfield | 3557 | PA 153 Beaver Run Br. | 153 | A04 | Bridge Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 1223904 | 0 | 0 | 0 | 0 | 1223904
North Central | 2 | Clearfield | 3570 | Spring Creek BOX | 2007 | A04 | Bridge Restoration | PE | 185 | 2028-10-25 |  | 0 | 0 | 126398 | 200000 | 0 | 0 | 0 | 0 | 0 | 326398
North Central | 2 | Clearfield | 3570 | Spring Creek BOX | 2007 | A04 | Bridge Restoration | ROW | 185 | 2028-10-25 |  | 0 | 0 | 0 | 86945 | 0 | 0 | 0 | 0 | 0 | 86945
North Central | 2 | Clearfield | 3570 | Spring Creek BOX | 2007 | A04 | Bridge Restoration | UTL | 185 | 2028-10-25 |  | 0 | 0 | 0 | 0 | 92742 | 0 | 0 | 0 | 0 | 92742
North Central | 2 | Clearfield | 3570 | Spring Creek BOX | 2007 | A04 | Bridge Restoration | CON | 185 | 2028-10-25 |  | 0 | 0 | 0 | 0 | 895539 | 0 | 0 | 0 | 0 | 895539
North Central | 2 | Clearfield | 3608 | T-206 Anderson Creek | 7226 | REM | Bridge Removal | PE | 581 | 2027-07-15 |  | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
North Central | 2 | Clearfield | 3608 | T-206 Anderson Creek | 7226 | REM | Bridge Removal | ROW | 581 | 2027-07-15 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
North Central | 2 | Clearfield | 3608 | T-206 Anderson Creek | 7226 | REM | Bridge Removal | CON | 581 | 2027-07-15 |  | 0 | 0 | 0 | 372000 | 0 | 0 | 0 | 0 | 0 | 372000
North Central | 2 | Clearfield | 69380 | 2025 NC Bridge Preservation | 1006 | P46 | Bridge Preservation - Federal | PE | BOF | 2025-05-08 | 2025-05-08 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Clearfield | 69380 | 2025 NC Bridge Preservation | 1006 | P46 | Bridge Preservation - Federal | ROW | BOF | 2025-05-08 | 2025-05-08 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
North Central | 2 | Clearfield | 69380 | 2025 NC Bridge Preservation | 1006 | P46 | Bridge Preservation - Federal | CON | BOF | 2025-05-08 | 2025-05-08 | 1616179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1616179
North Central | 2 | Clearfield | 69380 | 2025 NC Bridge Preservation | 1006 | P46 | Bridge Preservation - Federal | CON | 581 | 2025-05-08 | 2025-05-08 | 117206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117206
North Central | 2 | Clearfield | 69383 | SR 322 over Roaring Run | 322 | A05 | Bridge Restoration | PE | NHPP | 2030-08-29 |  | 0 | 0 | 0 | 486895 | 0 | 0 | 0 | 0 | 0 | 486895
North Central | 2 | Clearfield | 69383 | SR 322 over Roaring Run | 322 | A05 | Bridge Restoration | FD | NHPP | 2030-08-29 |  | 0 | 0 | 0 | 0 | 298513 | 0 | 0 | 0 | 0 | 298513
North Central | 2 | Clearfield | 69383 | SR 322 over Roaring Run | 322 | A05 | Bridge Restoration | FD | 185 | 2030-08-29 |  | 0 | 0 | 0 | 0 | 298513 | 0 | 0 | 0 | 0 | 298513
North Central | 2 | Clearfield | 69383 | SR 322 over Roaring Run | 322 | A05 | Bridge Restoration | ROW | 185 | 2030-08-29 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
North Central | 2 | Clearfield | 69383 | SR 322 over Roaring Run | 322 | A05 | Bridge Restoration | UTL | 185 | 2030-08-29 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
North Central | 2 | Clearfield | 69383 | SR 322 over Roaring Run | 322 | A05 | Bridge Restoration | CON | NHPP | 2030-08-29 |  | 0 | 0 | 0 | 0 | 0 | 983899 | 0 | 0 | 0 | 983899
North Central | 2 | Clearfield | 69383 | SR 322 over Roaring Run | 322 | A05 | Bridge Restoration | CON | 185 | 2030-08-29 |  | 0 | 0 | 0 | 0 | 0 | 245975 | 0 | 0 | 0 | 245975
North Central | 2 | Clearfield | 69478 | SR 2035 ov Trib Mosh Crk BOX | 2035 | A02 | Bridge Replacement | PE | 581 | 2027-10-07 |  | 0 | 458495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458495
North Central | 2 | Clearfield | 69478 | SR 2035 ov Trib Mosh Crk BOX | 2035 | A02 | Bridge Replacement | ROW | 581 | 2027-10-07 |  | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 0 | 56275
North Central | 2 | Clearfield | 69478 | SR 2035 ov Trib Mosh Crk BOX | 2035 | A02 | Bridge Replacement | UTL | 581 | 2027-10-07 |  | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 0 | 56275
North Central | 2 | Clearfield | 69478 | SR 2035 ov Trib Mosh Crk BOX | 2035 | A02 | Bridge Replacement | CON | 185 | 2027-10-07 |  | 0 | 0 | 0 | 923923 | 0 | 0 | 0 | 0 | 0 | 923923
North Central | 2 | Clearfield | 83531 | North Camp Run Bridge | 3014 | A04 | Bridge Restoration | PE | BOF | 2026-02-12 | 2026-02-12 | 53144 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133144
North Central | 2 | Clearfield | 83531 | North Camp Run Bridge | 3014 | A04 | Bridge Restoration | PE | BRIP | 2026-02-12 | 2026-02-12 | 0 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000
North Central | 2 | Clearfield | 83531 | North Camp Run Bridge | 3014 | A04 | Bridge Restoration | ROW | BOF | 2026-02-12 | 2026-02-12 | 26523 | 15477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000
North Central | 2 | Clearfield | 83531 | North Camp Run Bridge | 3014 | A04 | Bridge Restoration | UTL | BOF | 2026-02-12 | 2026-02-12 | 2436 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42436
North Central | 2 | Clearfield | 83531 | North Camp Run Bridge | 3014 | A04 | Bridge Restoration | CON | BOF | 2026-02-12 | 2026-02-12 | 0 | 950850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950850
North Central | 2 | Clearfield | 83531 | North Camp Run Bridge | 3014 | A04 | Bridge Restoration | CON | BRIP | 2026-02-12 | 2026-02-12 | 0 | 0 | 88026 | 0 | 0 | 0 | 0 | 0 | 0 | 88026
North Central | 2 | Clearfield | 84344 | Poor Bridge /Betterment Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 14965 | 108984 | 0 | 0 | 0 | 0 | 0 | 0 | 123949
North Central | 2 | Clearfield | 84344 | Poor Bridge /Betterment Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 882719 | 741878 | 0 | 0 | 0 | 0 | 0 | 0 | 1624597
North Central | 2 | Clearfield | 84344 | Poor Bridge /Betterment Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 146361 | 0 | 0 | 0 | 0 | 0 | 0 | 3324942 | 3471303
North Central | 2 | Clearfield | 84344 | Poor Bridge /Betterment Line Item |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 44268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44268
North Central | 2 | Clearfield | 84344 | Poor Bridge /Betterment Line Item |  |  | Reserve Line Item | CON | TAP |  |  | 0 | 751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 751
North Central | 2 | Clearfield | 85080 | SR 219 Pentz Run | 219 | A10 | Bridge Restoration | PE | NHPP | 2028-09-28 |  | 0 | 155963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155963
North Central | 2 | Clearfield | 85080 | SR 219 Pentz Run | 219 | A10 | Bridge Restoration | PE | STP | 2028-09-28 |  | 150000 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
North Central | 2 | Clearfield | 85080 | SR 219 Pentz Run | 219 | A10 | Bridge Restoration | FD | STP | 2028-09-28 |  | 0 | 0 | 337653 | 0 | 0 | 0 | 0 | 0 | 0 | 337653
North Central | 2 | Clearfield | 85080 | SR 219 Pentz Run | 219 | A10 | Bridge Restoration | ROW | STP | 2028-09-28 |  | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 0 | 56275
North Central | 2 | Clearfield | 85080 | SR 219 Pentz Run | 219 | A10 | Bridge Restoration | UTL | STP | 2028-09-28 |  | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 0 | 56275
North Central | 2 | Clearfield | 85080 | SR 219 Pentz Run | 219 | A10 | Bridge Restoration | CON | NHPP | 2028-09-28 |  | 0 | 0 | 0 | 804852 | 300000 | 0 | 0 | 0 | 0 | 1104852
North Central | 2 | Clearfield | 85092 | SR 1008 over Trout Run | 1008 | A01 | Bridge Replacement | PE | BOF | 2031-05-01 |  | 0 | 0 | 0 | 0 | 502002 | 0 | 0 | 0 | 0 | 502002
North Central | 2 | Clearfield | 85092 | SR 1008 over Trout Run | 1008 | A01 | Bridge Replacement | FD | BOF | 2031-05-01 |  | 0 | 0 | 0 | 0 | 0 | 369462 | 0 | 0 | 0 | 369462
North Central | 2 | Clearfield | 85092 | SR 1008 over Trout Run | 1008 | A01 | Bridge Replacement | ROW | BOF | 2031-05-01 |  | 0 | 0 | 0 | 0 | 0 | 61494 | 0 | 0 | 0 | 61494
North Central | 2 | Clearfield | 85092 | SR 1008 over Trout Run | 1008 | A01 | Bridge Replacement | UTL | BOF | 2031-05-01 |  | 0 | 0 | 0 | 0 | 0 | 61494 | 0 | 0 | 0 | 61494
North Central | 2 | Clearfield | 85092 | SR 1008 over Trout Run | 1008 | A01 | Bridge Replacement | CON | BOF | 2031-05-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1288401 | 0 | 0 | 1288401
North Central | 2 | Clearfield | 85110 | SR 969 over Bell Run | 969 | A01 | Bridge Replacement | PE | 185 | 2031-07-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 652386 | 0 | 652386
North Central | 2 | Clearfield | 85110 | SR 969 over Bell Run | 969 | A01 | Bridge Replacement | FD | STP | 2031-07-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403175 | 403175
North Central | 2 | Clearfield | 85110 | SR 969 over Bell Run | 969 | A01 | Bridge Replacement | ROW | STP | 2031-07-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | Clearfield | 85110 | SR 969 over Bell Run | 969 | A01 | Bridge Replacement | UTL | STP | 2031-07-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | Clearfield | 85110 | SR 969 over Bell Run | 969 | A01 | Bridge Replacement | CON | STP | 2031-07-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5375665 | 5375665
North Central | 2 | Clearfield | 85134 | SR 36 over Moss Run | 36 | A09 | Bridge Restoration | PE | 185 | 2029-01-25 |  | 0 | 0 | 0 | 0 | 501502 | 0 | 0 | 0 | 0 | 501502
North Central | 2 | Clearfield | 85134 | SR 36 over Moss Run | 36 | A09 | Bridge Restoration | FD | 185 | 2029-01-25 |  | 0 | 0 | 0 | 0 | 0 | 399709 | 0 | 0 | 0 | 399709
North Central | 2 | Clearfield | 85134 | SR 36 over Moss Run | 36 | A09 | Bridge Restoration | ROW | 185 | 2029-01-25 |  | 0 | 0 | 0 | 0 | 0 | 92240 | 0 | 0 | 0 | 92240
North Central | 2 | Clearfield | 85134 | SR 36 over Moss Run | 36 | A09 | Bridge Restoration | UTL | 185 | 2029-01-25 |  | 0 | 0 | 0 | 0 | 0 | 92240 | 0 | 0 | 0 | 92240
North Central | 2 | Clearfield | 85134 | SR 36 over Moss Run | 36 | A09 | Bridge Restoration | CON | 185 | 2029-01-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1266771 | 0 | 0 | 1266771
North Central | 2 | Clearfield | 88619 | Local Retro's |  |  | Reserve Line Item | CON | 183 |  |  | 0 | 319013 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 1119013
North Central | 2 | Clearfield | 88619 | Local Retro's |  |  | Reserve Line Item | CON | LOC |  |  | 0 | 39519 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 239519
North Central | 2 | Clearfield | 91505 | Little Anderson Crk BOX | 4010 | A01 | Bridge Restoration | CON | 581 | 2023-10-05 | 2023-10-05 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Clearfield | 91543 | SR 410 Stump Creek Bridge | 410 | A01 | Bridge Replacement | CON | 581 | 2022-12-08 | 2022-12-08 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000
North Central | 2 | Clearfield | 92420 | NC Bridge Plank/Channel Program |  |  | Highway Restoration | CON | 185 |  |  | 0 | 18468 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 518468
North Central | 2 | Clearfield | 93330 | Clfd. Congestion Imprv | 153 | N46 | Congestion Reduction | PE | STP | 2026-09-17 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Clearfield | 93330 | Clfd. Congestion Imprv | 153 | N46 | Congestion Reduction | FD | STP | 2026-09-17 |  | 530450 | 100150 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 660600
North Central | 2 | Clearfield | 93330 | Clfd. Congestion Imprv | 153 | N46 | Congestion Reduction | ROW | STP | 2026-09-17 |  | 212180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212180
North Central | 2 | Clearfield | 93330 | Clfd. Congestion Imprv | 153 | N46 | Congestion Reduction | UTL | STP | 2026-09-17 |  | 212180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212180
North Central | 2 | Clearfield | 93330 | Clfd. Congestion Imprv | 153 | N46 | Congestion Reduction | CON | HSIP | 2026-09-17 |  | 0 | 390790 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 890790
North Central | 2 | Clearfield | 93330 | Clfd. Congestion Imprv | 153 | N46 | Congestion Reduction | CON | HVRU | 2026-09-17 |  | 0 | 157490 | 528800 | 400000 | 0 | 0 | 0 | 0 | 0 | 1086290
North Central | 2 | Clearfield | 93330 | Clfd. Congestion Imprv | 153 | N46 | Congestion Reduction | CON | NHPP | 2026-09-17 |  | 0 | 0 | 0 | 895376 | 0 | 0 | 0 | 0 | 0 | 895376
North Central | 2 | Clearfield | 93330 | Clfd. Congestion Imprv | 153 | N46 | Congestion Reduction | CON | STP | 2026-09-17 |  | 0 | 0 | 874639 | 1727169 | 797247 | 0 | 3543204 | 0 | 0 | 6942259
North Central | 2 | Clearfield | 93330 | Clfd. Congestion Imprv | 153 | N46 | Congestion Reduction | CON | 581 | 2026-09-17 |  | 0 | 655636 | 622636 | 655636 | 0 | 0 | 0 | 0 | 0 | 1933908
North Central | 2 | Clearfield | 93939 | SR 1006 Lick Run Bridge | 1006 | A02 | Bridge Restoration | PE | 185 | 2030-02-28 |  | 0 | 0 | 0 | 486895 | 0 | 0 | 0 | 0 | 0 | 486895
North Central | 2 | Clearfield | 93939 | SR 1006 Lick Run Bridge | 1006 | A02 | Bridge Restoration | FD | 185 | 2030-02-28 |  | 0 | 0 | 0 | 0 | 358216 | 0 | 0 | 0 | 0 | 358216
North Central | 2 | Clearfield | 93939 | SR 1006 Lick Run Bridge | 1006 | A02 | Bridge Restoration | ROW | 185 | 2030-02-28 |  | 0 | 0 | 0 | 0 | 89554 | 0 | 0 | 0 | 0 | 89554
North Central | 2 | Clearfield | 93939 | SR 1006 Lick Run Bridge | 1006 | A02 | Bridge Restoration | UTL | 185 | 2030-02-28 |  | 0 | 0 | 0 | 0 | 89554 | 0 | 0 | 0 | 0 | 89554
North Central | 2 | Clearfield | 93939 | SR 1006 Lick Run Bridge | 1006 | A02 | Bridge Restoration | CON | 185 | 2030-02-28 |  | 0 | 0 | 0 | 0 | 0 | 1229874 | 0 | 0 | 0 | 1229874
North Central | 2 | Clearfield | 95990 | T-566 over Clearfield Crk | 7222 | REM | Bridge Removal | PE | 581 | 2028-02-17 |  | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000
North Central | 2 | Clearfield | 95990 | T-566 over Clearfield Crk | 7222 | REM | Bridge Removal | ROW | 581 | 2028-02-17 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
North Central | 2 | Clearfield | 95990 | T-566 over Clearfield Crk | 7222 | REM | Bridge Removal | CON | 581 | 2028-02-17 |  | 0 | 0 | 0 | 0 | 720000 | 0 | 0 | 0 | 0 | 720000
North Central | 2 | Clearfield | 96271 | Penfield North Resurface | 153 | 266 | Highway Restoration | CON | NHPP | 2024-03-28 | 2024-03-28 | 1463699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1463699
North Central | 2 | Clearfield | 100553 | PA 53 Philipsbrg-Kylertwn | 53 | 276 | Highway Restoration | PE | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 368962 | 0 | 0 | 0 | 368962
North Central | 2 | Clearfield | 100553 | PA 53 Philipsbrg-Kylertwn | 53 | 276 | Highway Restoration | CON | STP | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4270437 | 0 | 4270437
North Central | 2 | Clearfield | 100553 | PA 53 Philipsbrg-Kylertwn | 53 | 276 | Highway Restoration | CON | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 855070 | 1499000 | 0 | 2354070
North Central | 2 | Clearfield | 100573 | PA53 Irvona-Osceola Mills | 53 | 0 | Highway Restoration | CON | 581 | 2029-03-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3125000 | 3125000
North Central | 2 | Clearfield | 101001 | 219 Gramp.-Chestnut Grov | 219 | 0 | Highway Restoration | CON | 581 | 2029-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3695770 | 3695770
North Central | 2 | Clearfield | 101059 | SR 729 Janesville-PA 969 | 729 | 0 | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3125000 | 3125000
North Central | 2 | Clearfield | 101091 | Brisbin SR 2007-W SR 2024 | 153 | 0 | Highway Restoration | CON | 581 | 2028-03-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5194294 | 5194294
North Central | 2 | Clearfield | 101286 | Luthersburg to DuBois | 219 | 0 | Highway Restoration | CON | 581 | 2029-03-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4924284 | 4924284
North Central | 2 | Clearfield | 109524 | T-899 over Laborde Branch | 7229 | 0 | Bridge Replacement | CON | LOC |  |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
North Central | 2 | Clearfield | 109839 | Maintenance/Betterment Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 14797 | 418791 | 771830 | 0 | 0 | 0 | 0 | 0 | 1205418
North Central | 2 | Clearfield | 109945 | Beaver Drive Intersection Improvement |  | CRP | Air Quality | PE | CRP | 2027-10-28 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Clearfield | 109945 | Beaver Drive Intersection Improvement |  | CRP | Air Quality | FD | CRP | 2027-10-28 |  | 267370 | 156990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424360
North Central | 2 | Clearfield | 109945 | Beaver Drive Intersection Improvement |  | CRP | Air Quality | ROW | CRP | 2027-10-28 |  | 26545 | 26545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53090
North Central | 2 | Clearfield | 109945 | Beaver Drive Intersection Improvement |  | CRP | Air Quality | UTL | CRP | 2027-10-28 |  | 26545 | 26545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53090
North Central | 2 | Clearfield | 109945 | Beaver Drive Intersection Improvement |  | CRP | Air Quality | CON | CRP | 2027-10-28 |  | 0 | 0 | 58288 | 234000 | 934000 | 349424 | 0 | 0 | 0 | 1575712
North Central | 2 | Clearfield | 109945 | Beaver Drive Intersection Improvement |  | CRP | Air Quality | CON | 581 | 2027-10-28 |  | 0 | 0 | 393928 | 0 | 0 | 0 | 0 | 0 | 0 | 393928
North Central | 2 | Clearfield | 113127 | SR 255 over Muddy Run | 255 | A12 | Bridge Restoration | CON | 185 | 2024-10-10 | 2024-10-10 | 1309954 | 427225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1737179
North Central | 2 | Clearfield | 114049 | McGees Mills RR Device Upgrade | 219 | R22 | Rail Highway Grade Crossing | CON | RRX | 2023-08-02 | 2023-08-02 | 108000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108000
North Central | 2 | Clearfield | 115898 | Penfield to Elk Co. Line | 255 | 272 | Highway Restoration | PE | BRIP | 2027-09-30 |  | 180449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180449
North Central | 2 | Clearfield | 115898 | Penfield to Elk Co. Line | 255 | 272 | Highway Restoration | PE | STP | 2027-09-30 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
North Central | 2 | Clearfield | 115898 | Penfield to Elk Co. Line | 255 | 272 | Highway Restoration | FD | BRIP | 2027-09-30 |  | 0 | 217818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217818
North Central | 2 | Clearfield | 115898 | Penfield to Elk Co. Line | 255 | 272 | Highway Restoration | ROW | BRIP | 2027-09-30 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
North Central | 2 | Clearfield | 115898 | Penfield to Elk Co. Line | 255 | 272 | Highway Restoration | UTL | BRIP | 2027-09-30 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
North Central | 2 | Clearfield | 115898 | Penfield to Elk Co. Line | 255 | 272 | Highway Restoration | CON | BRIP | 2027-09-30 |  | 0 | 0 | 0 | 450408 | 0 | 0 | 0 | 0 | 0 | 450408
North Central | 2 | Clearfield | 115898 | Penfield to Elk Co. Line | 255 | 272 | Highway Restoration | CON | STP | 2027-09-30 |  | 0 | 0 | 617803 | 752392 | 0 | 0 | 0 | 0 | 0 | 1370195
North Central | 2 | Clearfield | 115898 | Penfield to Elk Co. Line | 255 | 272 | Highway Restoration | CON | 581 | 2027-09-30 |  | 0 | 0 | 0 | 1241878 | 2565063 | 0 | 0 | 0 | 0 | 3806941
North Central | 2 | Clearfield | 116812 | SR 1011 over Browns Run | 1011 | A04 | Bridge Restoration | PE | 185 | 2025-12-11 | 2025-12-11 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Clearfield | 116812 | SR 1011 over Browns Run | 1011 | A04 | Bridge Restoration | FD | 185 | 2025-12-11 | 2025-12-11 | 281500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281500
North Central | 2 | Clearfield | 116812 | SR 1011 over Browns Run | 1011 | A04 | Bridge Restoration | ROW | 185 | 2025-12-11 | 2025-12-11 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
North Central | 2 | Clearfield | 116812 | SR 1011 over Browns Run | 1011 | A04 | Bridge Restoration | UTL | 185 | 2025-12-11 | 2025-12-11 | 22510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22510
North Central | 2 | Clearfield | 116812 | SR 1011 over Browns Run | 1011 | A04 | Bridge Restoration | CON | 581 | 2025-12-11 | 2025-12-11 | 0 | 879170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 879170
North Central | 2 | Clearfield | 116845 | SR 153 over Litz Run | 153 | A06 | Bridge Restoration | PE | 185 | 2027-08-26 |  | 413578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413578
North Central | 2 | Clearfield | 116845 | SR 153 over Litz Run | 153 | A06 | Bridge Restoration | ROW | 185 | 2027-08-26 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
North Central | 2 | Clearfield | 116845 | SR 153 over Litz Run | 153 | A06 | Bridge Restoration | UTL | 185 | 2027-08-26 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
North Central | 2 | Clearfield | 116845 | SR 153 over Litz Run | 153 | A06 | Bridge Restoration | CON | 185 | 2027-08-26 |  | 0 | 0 | 462431 | 400000 | 0 | 0 | 0 | 0 | 0 | 862431
North Central | 2 | Clearfield | 116854 | SR 0322 over Abandoned Railroad | 322 | A11 | Bridge Restoration | PE | 581 | 2031-09-25 |  | 0 | 0 | 0 | 486895 | 0 | 0 | 0 | 0 | 0 | 486895
North Central | 2 | Clearfield | 116854 | SR 0322 over Abandoned Railroad | 322 | A11 | Bridge Restoration | ROW | 185 | 2031-09-25 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
North Central | 2 | Clearfield | 116854 | SR 0322 over Abandoned Railroad | 322 | A11 | Bridge Restoration | UTL | 185 | 2031-09-25 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
North Central | 2 | Clearfield | 116854 | SR 0322 over Abandoned Railroad | 322 | A11 | Bridge Restoration | CON | 185 | 2031-09-25 |  | 0 | 0 | 0 | 0 | 0 | 922405 | 0 | 0 | 0 | 922405
North Central | 2 | Clearfield | 117035 | NC Bridge Preservation 2 | 36 | P61 | Bridge Restoration | PE | 185 | 2031-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 417918 | 0 | 0 | 417918
North Central | 2 | Clearfield | 117035 | NC Bridge Preservation 2 | 36 | P61 | Bridge Restoration | ROW | 185 | 2031-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 130477 | 0 | 0 | 130477
North Central | 2 | Clearfield | 117035 | NC Bridge Preservation 2 | 36 | P61 | Bridge Restoration | UTL | 185 | 2031-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 130477 | 0 | 0 | 130477
North Central | 2 | Clearfield | 117035 | NC Bridge Preservation 2 | 36 | P61 | Bridge Restoration | CON | 185 | 2031-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 581079 | 3198125 | 0 | 3779204
North Central | 2 | Clearfield | 117066 | SR 219 - SR 830 to Jefferson County Line | 219 | 274 | Highway Restoration | CON | NHPP | 2024-10-24 | 2024-10-24 | 2157268 | 34623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2191891
North Central | 2 | Clearfield | 117237 | DuBois St toward Liberty Blvd | 219 | 275 | Highway Restoration | PE | NHPP | 2026-09-03 |  | 170240 | 77445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247685
North Central | 2 | Clearfield | 117237 | DuBois St toward Liberty Blvd | 219 | 275 | Highway Restoration | FD | 581 | 2026-09-03 |  | 280852 | 45148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326000
North Central | 2 | Clearfield | 117237 | DuBois St toward Liberty Blvd | 219 | 275 | Highway Restoration | ROW | NHPP | 2026-09-03 |  | 78357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78357
North Central | 2 | Clearfield | 117237 | DuBois St toward Liberty Blvd | 219 | 275 | Highway Restoration | UTL | NHPP | 2026-09-03 |  | 79568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79568
North Central | 2 | Clearfield | 117237 | DuBois St toward Liberty Blvd | 219 | 275 | Highway Restoration | CON | HVRU | 2026-09-03 |  | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
North Central | 2 | Clearfield | 117237 | DuBois St toward Liberty Blvd | 219 | 275 | Highway Restoration | CON | NHPP | 2026-09-03 |  | 0 | 1400000 | 2601783 | 0 | 0 | 0 | 0 | 0 | 0 | 4001783
North Central | 2 | Clearfield | 117460 | SR 322 ov Clearfield Creek | 322 | P50 | Bridge Restoration | CON | BRIP | 2022-09-15 | 2022-09-15 | 15220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15220
North Central | 2 | Clearfield | 117919 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 2518500 | 2518500 | 2518500 | 2518500 | 10076000 | 20150000
North Central | 2 | Clearfield | 117919 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 4953000 | 4953000 | 4953000 | 4953000 | 19812000 | 39624000
North Central | 2 | Clearfield | 117919 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 613920 | 0 | 0 | 0 | 584576 | 934000 | 934000 | 3736000 | 6802496
North Central | 2 | Clearfield | 117919 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 0 | 0 | 0 | 0 | 330000 | 330000 | 330000 | 1320000 | 2310000
North Central | 2 | Clearfield | 117919 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 3539000 | 3539000 | 3539000 | 3539000 | 14156000 | 28312000
North Central | 2 | Clearfield | 117919 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 0 | 0 | 0 | 720000 | 720000 | 720000 | 720000 | 2880000 | 5760000
North Central | 2 | Clearfield | 118542 | T-748 Mosquito Creek Bridge (I) | 7221 | LOC | Bridge Replacement | PE | BOF | 2026-02-12 | 2026-02-12 | 208000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208000
North Central | 2 | Clearfield | 118542 | T-748 Mosquito Creek Bridge (I) | 7221 | LOC | Bridge Replacement | FD | BOF | 2026-02-12 | 2026-02-12 | 288564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288564
North Central | 2 | Clearfield | 118542 | T-748 Mosquito Creek Bridge (I) | 7221 | LOC | Bridge Replacement | FD | 185 | 2026-02-12 | 2026-02-12 | 72141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72141
North Central | 2 | Clearfield | 118542 | T-748 Mosquito Creek Bridge (I) | 7221 | LOC | Bridge Replacement | ROW | BOF | 2026-02-12 | 2026-02-12 | 24400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24400
North Central | 2 | Clearfield | 118542 | T-748 Mosquito Creek Bridge (I) | 7221 | LOC | Bridge Replacement | ROW | 185 | 2026-02-12 | 2026-02-12 | 6100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6100
North Central | 2 | Clearfield | 118542 | T-748 Mosquito Creek Bridge (I) | 7221 | LOC | Bridge Replacement | UTL | 185 | 2026-02-12 | 2026-02-12 | 609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609
North Central | 2 | Clearfield | 118542 | T-748 Mosquito Creek Bridge (I) | 7221 | LOC | Bridge Replacement | CON | BOF | 2026-02-12 | 2026-02-12 | 705800 | 82513 | 98362 | 0 | 0 | 0 | 0 | 0 | 0 | 886675
North Central | 2 | Clearfield | 118542 | T-748 Mosquito Creek Bridge (I) | 7221 | LOC | Bridge Replacement | CON | RURAL | 2026-02-12 | 2026-02-12 | 0 | 1391240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1391240
North Central | 2 | Clearfield | 118542 | T-748 Mosquito Creek Bridge (I) | 7221 | LOC | Bridge Replacement | CON | 185 | 2026-02-12 | 2026-02-12 | 20000 | 327810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347810
North Central | 2 | Clearfield | 118770 | SR 2024 Metal Arch Pipe | 2024 | A05 | Bridge Replacement | CON | 581 | 2024-09-26 | 2024-09-26 | 416540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416540
North Central | 2 | Clearfield | 119245 | 322 Intersection toward S.B. Elliott | 153 | 277 | Highway Restoration | PE | NHPP | 2025-11-06 | 2025-11-06 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
North Central | 2 | Clearfield | 119245 | 322 Intersection toward S.B. Elliott | 153 | 277 | Highway Restoration | CON | NHPP | 2025-11-06 | 2025-11-06 | 3226806 | 2111434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5338240
North Central | 2 | Clearfield | 119245 | 322 Intersection toward S.B. Elliott | 153 | 277 | Highway Restoration | CON | STP | 2025-11-06 | 2025-11-06 | 7199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7199
North Central | 2 | Clearfield | 119866 | SR 219 over Trib to Wolf Run | 219 | P04 | Bridge Replacement | PE | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260955 | 0 | 260955
North Central | 2 | Clearfield | 119866 | SR 219 over Trib to Wolf Run | 219 | P04 | Bridge Replacement | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 978580 | 0 | 978580
North Central | 2 | Clearfield | 119869 | Clearfield Market St Bridge | 1004 | A04 | Bridge Restoration | PE | STP | 2027-06-30 |  | 304509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304509
North Central | 2 | Clearfield | 119869 | Clearfield Market St Bridge | 1004 | A04 | Bridge Restoration | FD | BRIP | 2027-06-30 |  | 0 | 218545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218545
North Central | 2 | Clearfield | 119869 | Clearfield Market St Bridge | 1004 | A04 | Bridge Restoration | ROW | BRIP | 2027-06-30 |  | 0 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43709
North Central | 2 | Clearfield | 119869 | Clearfield Market St Bridge | 1004 | A04 | Bridge Restoration | UTL | BRIP | 2027-06-30 |  | 0 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43709
North Central | 2 | Clearfield | 119869 | Clearfield Market St Bridge | 1004 | A04 | Bridge Restoration | CON | 581 | 2027-06-30 |  | 0 | 0 | 813807 | 2562719 | 0 | 0 | 0 | 0 | 0 | 3376526
North Central | 2 | Clearfield | 119876 | Butterbaugh Road Bridge | 3004 | A01 | Bridge Replacement | PE | BOF | 2028-02-17 |  | 0 | 0 | 0 | 0 | 491950 | 0 | 0 | 0 | 0 | 491950
North Central | 2 | Clearfield | 119876 | Butterbaugh Road Bridge | 3004 | A01 | Bridge Replacement | ROW | BOF | 2028-02-17 |  | 0 | 0 | 0 | 0 | 0 | 67196 | 0 | 0 | 0 | 67196
North Central | 2 | Clearfield | 119876 | Butterbaugh Road Bridge | 3004 | A01 | Bridge Replacement | UTL | BOF | 2028-02-17 |  | 0 | 0 | 0 | 0 | 0 | 67196 | 0 | 0 | 0 | 67196
North Central | 2 | Clearfield | 119876 | Butterbaugh Road Bridge | 3004 | A01 | Bridge Replacement | CON | BOF | 2028-02-17 |  | 0 | 0 | 0 | 0 | 0 | 640093 | 500000 | 0 | 0 | 1140093
North Central | 2 | Clearfield | 119878 | SR 3017 Line Road Bridge | 3017 | P03 | Bridge Replacement | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 245975 | 0 | 0 | 0 | 245975
North Central | 2 | Clearfield | 119878 | SR 3017 Line Road Bridge | 3017 | P03 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521909 | 0 | 521909
North Central | 2 | Clearfield | 120099 | SR 879 HFST | 879 | HFS | Safety Improvement | CON | HSIP | 2024-06-13 | 2024-06-13 | 23285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23285
North Central | 2 | Clearfield | 120101 | SR 219 HFST | 219 | HFS | Safety Improvement | CON | HSIP | 2024-06-13 | 2024-06-13 | 64212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64212
North Central | 2 | Clearfield | 120575 | SR 1011 Rapid Rectangular Flashing Beacon | 1011 | BCN | Safety Improvement | CON | HVRU | 2024-10-10 | 2024-10-10 | 155314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155314
North Central | 2 | Clearfield | 121302 | Rolling Stone Rd over WB Susq Rvr/RJC RR | 1011 | A05 | Bridge Preservation - Federal | CON | STP | 2024-10-10 | 2024-10-10 | 92408 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119408
North Central | 2 | Clearfield | 121374 | Fiber Install I-80 Exit 120 to District Office | 80 | 0 | Intelligent Transportation System | CON | CRP | 2024-04-18 | 2024-04-18 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
North Central | 2 | Clearfield | 121374 | Fiber Install I-80 Exit 120 to District Office | 80 | 0 | Intelligent Transportation System | CON | CRP | 2024-04-18 | 2024-04-18 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
North Central | 2 | Clearfield | 121830 | SR 2024 over Clfd Rail Trail | 2024 | A06 | Bridge Restoration | CON | BRIP | 2025-10-23 | 2025-10-23 | 61600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61600
North Central | 2 | Clearfield | 121830 | SR 2024 over Clfd Rail Trail | 2024 | A06 | Bridge Restoration | CON | STP | 2025-10-23 | 2025-10-23 | 628400 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 713400
North Central | 2 | Clearfield | 122135 | City of DuBois Trail |  |  | Congestion Reduction | PE | CRP | 2027-11-04 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
North Central | 2 | Clearfield | 122470 | Clearfield Bypass Drainage | 879 | 279 | Highway Restoration | PE | PRTCT | 2026-10-01 |  | 300000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
North Central | 2 | Clearfield | 122470 | Clearfield Bypass Drainage | 879 | 279 | Highway Restoration | PE | 581 | 2026-10-01 |  | 75000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
North Central | 2 | Clearfield | 122470 | Clearfield Bypass Drainage | 879 | 279 | Highway Restoration | CON | PRTCT | 2026-10-01 |  | 0 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000
North Central | 2 | Clearfield | 122633 | 2026 Clearfield HFST-Lane Departures | 729 | HFS | Safety Improvement | CON | HSIP | 2026-04-23 |  | 437000 | 203639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640639
North Central | 2 | Elk | 3997 | US 219 Rockey Run Br. | 219 | P02 | Bridge Replacement | PE | NHPP |  |  | 0 | 0 | 0 | 0 | 491950 | 0 | 0 | 0 | 0 | 491950
North Central | 2 | Elk | 3997 | US 219 Rockey Run Br. | 219 | P02 | Bridge Replacement | ROW | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 134392 | 0 | 0 | 0 | 134392
North Central | 2 | Elk | 3997 | US 219 Rockey Run Br. | 219 | P02 | Bridge Replacement | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 271265 | 767437 | 0 | 0 | 1038702
North Central | 2 | Elk | 69052 | Bridge Over Little Mill Ck | 948 | A02 | Bridge Replacement | FD | BRIP | 2025-12-11 | 2025-12-11 | 240225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240225
North Central | 2 | Elk | 69052 | Bridge Over Little Mill Ck | 948 | A02 | Bridge Replacement | ROW | BRIP | 2025-12-11 | 2025-12-11 | 22523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22523
North Central | 2 | Elk | 69052 | Bridge Over Little Mill Ck | 948 | A02 | Bridge Replacement | UTL | BRIP | 2025-12-11 | 2025-12-11 | 10609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10609
North Central | 2 | Elk | 69052 | Bridge Over Little Mill Ck | 948 | A02 | Bridge Replacement | CON | BRIP | 2025-12-11 | 2025-12-11 | 1078633 | 1521467 | 312305 | 0 | 0 | 0 | 0 | 0 | 0 | 2912405
North Central | 2 | Elk | 69080 | Bridge over Trib Elk Cr. | 120 | A09 | Bridge Restoration | PE | STP | 2028-01-27 |  | 0 | 467141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467141
North Central | 2 | Elk | 69080 | Bridge over Trib Elk Cr. | 120 | A09 | Bridge Restoration | FD | 185 | 2028-01-27 |  | 0 | 0 | 281377 | 0 | 0 | 0 | 0 | 0 | 0 | 281377
North Central | 2 | Elk | 69080 | Bridge over Trib Elk Cr. | 120 | A09 | Bridge Restoration | ROW | 185 | 2028-01-27 |  | 0 | 0 | 84414 | 0 | 0 | 0 | 0 | 0 | 0 | 84414
North Central | 2 | Elk | 69080 | Bridge over Trib Elk Cr. | 120 | A09 | Bridge Restoration | UTL | 185 | 2028-01-27 |  | 0 | 0 | 84414 | 0 | 0 | 0 | 0 | 0 | 0 | 84414
North Central | 2 | Elk | 69080 | Bridge over Trib Elk Cr. | 120 | A09 | Bridge Restoration | CON | 581 | 2028-01-27 |  | 0 | 0 | 0 | 979680 | 0 | 0 | 0 | 0 | 0 | 979680
North Central | 2 | Elk | 69085 | Bridge over Big Run | 120 | A08 | Bridge Replacement | PE | STP | 2025-04-10 | 2025-04-10 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Elk | 69085 | Bridge over Big Run | 120 | A08 | Bridge Replacement | CON | BRIP | 2025-04-10 | 2025-04-10 | 1856210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1856210
North Central | 2 | Elk | 83528 | Wyncoop Run Bridge | 3005 | A01 | Bridge Replacement | PE | BOF | 2026-08-13 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Elk | 83528 | Wyncoop Run Bridge | 3005 | A01 | Bridge Replacement | ROW | BOF | 2026-08-13 |  | 10543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10543
North Central | 2 | Elk | 83528 | Wyncoop Run Bridge | 3005 | A01 | Bridge Replacement | UTL | BOF | 2026-08-13 |  | 20543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20543
North Central | 2 | Elk | 83528 | Wyncoop Run Bridge | 3005 | A01 | Bridge Replacement | CON | BOF | 2026-08-13 |  | 0 | 0 | 2511082 | 0 | 0 | 0 | 0 | 0 | 0 | 2511082
North Central | 2 | Elk | 85158 | Trib to Elk Creek | 1005 | A01 | Bridge Replacement | ROW | 581 | 2025-01-30 | 2025-01-30 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Elk | 85158 | Trib to Elk Creek | 1005 | A01 | Bridge Replacement | CON | BRIP | 2025-01-30 | 2025-01-30 | 1514380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1514380
North Central | 2 | Elk | 85158 | Trib to Elk Creek | 1005 | A01 | Bridge Replacement | CON | 581 | 2025-01-30 | 2025-01-30 | 139310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139310
North Central | 2 | Elk | 89982 | East Branch of Clarion Rv | 1009 | P01 | Bridge Restoration | PE | NHPP | 2029-01-30 |  | 0 | 0 | 0 | 0 | 501502 | 0 | 0 | 0 | 0 | 501502
North Central | 2 | Elk | 89982 | East Branch of Clarion Rv | 1009 | P01 | Bridge Restoration | FD | NHPP | 2029-01-30 |  | 0 | 0 | 0 | 0 | 0 | 368962 | 0 | 0 | 0 | 368962
North Central | 2 | Elk | 89982 | East Branch of Clarion Rv | 1009 | P01 | Bridge Restoration | ROW | NHPP | 2029-01-30 |  | 0 | 0 | 0 | 0 | 0 | 92241 | 0 | 0 | 0 | 92241
North Central | 2 | Elk | 89982 | East Branch of Clarion Rv | 1009 | P01 | Bridge Restoration | UTL | NHPP | 2029-01-30 |  | 0 | 0 | 0 | 0 | 0 | 92241 | 0 | 0 | 0 | 92241
North Central | 2 | Elk | 89982 | East Branch of Clarion Rv | 1009 | P01 | Bridge Restoration | CON | NHPP | 2029-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1175563 | 0 | 0 | 1175563
North Central | 2 | Elk | 89982 | East Branch of Clarion Rv | 1009 | P01 | Bridge Restoration | CON | 185 | 2029-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 293891 | 0 | 0 | 293891
North Central | 2 | Elk | 101107 | Weedville twd Benezette | 555 | 0 | Highway Restoration | CON | 581 | 2029-03-30 |  | 0 | 0 | 0 | 0 | 0 | 3933003 | 0 | 0 | 0 | 3933003
North Central | 2 | Elk | 101110 | W. Benezette to Cameron | 555 | 0 | Highway Restoration | CON | 581 | 2029-03-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3914320 | 0 | 3914320
North Central | 2 | Elk | 101115 | Mahood Run twd Island Run | 949 | 0 | Highway Restoration | CON | 581 | 2029-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750000 | 2750000
North Central | 2 | Elk | 101123 | W.Island Run to PA 948 | 949 | 0 | Highway Restoration | CON | 581 | 2029-03-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750000 | 2750000
North Central | 2 | Elk | 101147 | 255 Clearfield Co-Rita Ln | 255 | 823 | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5700465 | 0 | 0 | 5700465
North Central | 2 | Elk | 103701 | T-333 ov Little Toby Crk | 7205 | 0 | Bridge Replacement | CON | 183 |  |  | 0 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440000
North Central | 2 | Elk | 103701 | T-333 ov Little Toby Crk | 7205 | 0 | Bridge Replacement | CON | ACT13 |  |  | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
North Central | 2 | Elk | 105943 | Boot Jack Bypass | 2219 | 822 | Highway Restoration | PE | NHPP | 2027-06-24 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Elk | 105943 | Boot Jack Bypass | 2219 | 822 | Highway Restoration | ROW | NHPP | 2027-06-24 |  | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57964
North Central | 2 | Elk | 105943 | Boot Jack Bypass | 2219 | 822 | Highway Restoration | UTL | NHPP | 2027-06-24 |  | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57964
North Central | 2 | Elk | 105943 | Boot Jack Bypass | 2219 | 822 | Highway Restoration | CON | NHPP | 2027-06-24 |  | 0 | 0 | 2673705 | 3294877 | 351035 | 0 | 0 | 0 | 0 | 6319617
North Central | 2 | Elk | 109706 | SR 255 over Powers Run | 255 | A04 | Bridge Restoration | PE | 185 | 2031-01-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537566 | 537566
North Central | 2 | Elk | 109706 | SR 255 over Powers Run | 255 | A04 | Bridge Restoration | FD | 185 | 2031-01-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 436773 | 436773
North Central | 2 | Elk | 109706 | SR 255 over Powers Run | 255 | A04 | Bridge Restoration | ROW | 185 | 2031-01-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134392 | 134392
North Central | 2 | Elk | 109706 | SR 255 over Powers Run | 255 | A04 | Bridge Restoration | UTL | 185 | 2031-01-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | Elk | 109706 | SR 255 over Powers Run | 255 | A04 | Bridge Restoration | CON | 185 | 2031-01-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1807937 | 1807937
North Central | 2 | Elk | 113951 | City of St.Marys SR 120 Connector | 120 | C02 | New Alignment | FD | 581 |  |  | 45000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145000
North Central | 2 | Elk | 113951 | City of St.Marys SR 120 Connector | 120 | C02 | New Alignment | UTL | 581 |  |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
North Central | 2 | Elk | 113951 | City of St.Marys SR 120 Connector | 120 | C02 | New Alignment | CON | 581 |  |  | 1971624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1971624
North Central | 2 | Elk | 116861 | SR 2003 over Branch of Toby Creek | 2003 | A01 | Bridge Replacement | PE | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456932 | 456932
North Central | 2 | Elk | 116861 | SR 2003 over Branch of Toby Creek | 2003 | A01 | Bridge Replacement | ROW | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | Elk | 116861 | SR 2003 over Branch of Toby Creek | 2003 | A01 | Bridge Replacement | UTL | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | Elk | 116861 | SR 2003 over Branch of Toby Creek | 2003 | A01 | Bridge Replacement | CON | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1807937 | 1807937
North Central | 2 | Elk | 117032 | NC Bridge Preservation 1 | 219 | P58 | Bridge Restoration | PE | NHPP | 2030-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403175 | 403175
North Central | 2 | Elk | 117032 | NC Bridge Preservation 1 | 219 | P58 | Bridge Restoration | ROW | NHPP | 2030-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | Elk | 117032 | NC Bridge Preservation 1 | 219 | P58 | Bridge Restoration | UTL | NHPP | 2030-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | Elk | 117032 | NC Bridge Preservation 1 | 219 | P58 | Bridge Restoration | CON | NHPP | 2030-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3361791 | 3361791
North Central | 2 | Elk | 117032 | NC Bridge Preservation 1 | 219 | P58 | Bridge Restoration | CON | 185 | 2030-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
North Central | 2 | Elk | 117069 | St Michaels Street to Sorg Street | 120 | 821 | Highway Restoration | FD | 581 | 2027-02-11 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Elk | 117069 | St Michaels Street to Sorg Street | 120 | 821 | Highway Restoration | ROW | 581 | 2027-02-11 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Elk | 117069 | St Michaels Street to Sorg Street | 120 | 821 | Highway Restoration | UTL | 581 | 2027-02-11 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Elk | 117069 | St Michaels Street to Sorg Street | 120 | 821 | Highway Restoration | CON | 581 | 2027-02-11 |  | 0 | 0 | 1384368 | 900000 | 0 | 0 | 0 | 0 | 0 | 2284368
North Central | 2 | Elk | 118541 | T-368 Horner Road Bridge |  | 000 | General Maintenance | CON | 183 |  |  | 160936 | 40987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201923
North Central | 2 | Elk | 118541 | T-368 Horner Road Bridge |  | 000 | General Maintenance | CON | LOC |  |  | 0 | 50481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50481
North Central | 2 | Elk | 118543 | T-464 Caledonia Pike Bridge (I) | 7206 | LOC | Bridge Restoration | PE | BOF | 2026-04-09 |  | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000
North Central | 2 | Elk | 118543 | T-464 Caledonia Pike Bridge (I) | 7206 | LOC | Bridge Restoration | FD | BOF | 2026-04-09 |  | 456185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456185
North Central | 2 | Elk | 118543 | T-464 Caledonia Pike Bridge (I) | 7206 | LOC | Bridge Restoration | ROW | BOF | 2026-04-09 |  | 15914 | 63656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79570
North Central | 2 | Elk | 118543 | T-464 Caledonia Pike Bridge (I) | 7206 | LOC | Bridge Restoration | UTL | BOF | 2026-04-09 |  | 10609 | 164391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
North Central | 2 | Elk | 118543 | T-464 Caledonia Pike Bridge (I) | 7206 | LOC | Bridge Restoration | CON | BOF | 2026-04-09 |  | 136000 | 1113977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1249977
North Central | 2 | Elk | 118543 | T-464 Caledonia Pike Bridge (I) | 7206 | LOC | Bridge Restoration | CON | RURAL | 2026-04-09 |  | 0 | 3183218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3183218
North Central | 2 | Elk | 118543 | T-464 Caledonia Pike Bridge (I) | 7206 | LOC | Bridge Restoration | CON | 185 | 2026-04-09 |  | 0 | 795805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 795805
North Central | 2 | Elk | 119241 | US 219 Johnsonburg toward Wilcox | 219 | 826 | Highway Restoration | CON | 581 | 2025-06-26 | 2025-06-26 | 1697260 | 1202740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2900000
North Central | 2 | Elk | 119330 | Twin Lakes Access | 7207 | 0 | Highway Restoration | PE | STP | 2026-08-27 |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
North Central | 2 | Elk | 119330 | Twin Lakes Access | 7207 | 0 | Highway Restoration | FD | BOF | 2026-08-27 |  | 0 | 137346 | 92654 | 0 | 0 | 0 | 0 | 0 | 0 | 230000
North Central | 2 | Elk | 119330 | Twin Lakes Access | 7207 | 0 | Highway Restoration | CON | FLAP | 2026-08-27 |  | 0 | 2450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2450000
North Central | 2 | Elk | 119907 | SR 2001 over Little Toby Creek | 2001 | A01 | Bridge Replacement | PE | BOF |  |  | 0 | 0 | 0 | 0 | 491950 | 0 | 0 | 0 | 0 | 491950
North Central | 2 | Elk | 119907 | SR 2001 over Little Toby Creek | 2001 | A01 | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 67196 | 0 | 0 | 0 | 67196
North Central | 2 | Elk | 119907 | SR 2001 over Little Toby Creek | 2001 | A01 | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 67196 | 0 | 0 | 0 | 67196
North Central | 2 | Elk | 119907 | SR 2001 over Little Toby Creek | 2001 | A01 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 837198 | 696099 | 0 | 0 | 1533297
North Central | 2 | Elk | 120133 | Wilcox SR 219/321 Intersection Improvement | 219 | CRP | Air Quality | FD | CRP | 2027-11-25 |  | 424360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424360
North Central | 2 | Elk | 120133 | Wilcox SR 219/321 Intersection Improvement | 219 | CRP | Air Quality | ROW | CRP | 2027-11-25 |  | 53090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53090
North Central | 2 | Elk | 120133 | Wilcox SR 219/321 Intersection Improvement | 219 | CRP | Air Quality | UTL | CRP | 2027-11-25 |  | 53090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53090
North Central | 2 | Elk | 120133 | Wilcox SR 219/321 Intersection Improvement | 219 | CRP | Air Quality | CON | CRP | 2027-11-25 |  | 0 | 0 | 875712 | 700000 | 0 | 0 | 0 | 0 | 0 | 1575712
North Central | 2 | Elk | 120133 | Wilcox SR 219/321 Intersection Improvement | 219 | CRP | Air Quality | CON | 581 | 2027-11-25 |  | 0 | 0 | 393928 | 0 | 0 | 0 | 0 | 0 | 0 | 393928
North Central | 2 | Elk | 120679 | SR 219 over Br Clarion River | 219 | A10 | Bridge Restoration | CON | STP | 2029-05-31 |  | 0 | 0 | 0 | 0 | 1194052 | 0 | 0 | 0 | 0 | 1194052
North Central | 2 | Elk | 121032 | SR 120 Depot/Front Street | 120 | 824 | Highway Restoration | PE | NHPP | 2028-09-28 |  | 445578 | 0 | 354422 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
North Central | 2 | Elk | 121032 | SR 120 Depot/Front Street | 120 | 824 | Highway Restoration | FD | NHPP | 2028-09-28 |  | 0 | 0 | 327818 | 0 | 0 | 0 | 0 | 0 | 0 | 327818
North Central | 2 | Elk | 121032 | SR 120 Depot/Front Street | 120 | 824 | Highway Restoration | ROW | NHPP | 2028-09-28 |  | 0 | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
North Central | 2 | Elk | 121032 | SR 120 Depot/Front Street | 120 | 824 | Highway Restoration | UTL | NHPP | 2028-09-28 |  | 0 | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
North Central | 2 | Elk | 121032 | SR 120 Depot/Front Street | 120 | 824 | Highway Restoration | CON | 581 | 2028-09-28 |  | 0 | 0 | 0 | 1643707 | 4326555 | 0 | 0 | 0 | 0 | 5970262
North Central | 2 | Elk | 121215 | St. Marys RR Crossing | 120 | R28 | Safety Improvement | CON | RRX | 2027-08-12 |  | 0 | 0 | 0 | 171000 | 0 | 0 | 0 | 0 | 0 | 171000
North Central | 2 | Elk | 121422 | SR 219 Bootjack Hill Drainage | 219 | 825 | Highway Restoration | PE | NHPP | 2027-09-30 |  | 124000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124000
North Central | 2 | Elk | 121422 | SR 219 Bootjack Hill Drainage | 219 | 825 | Highway Restoration | PE | 581 | 2027-09-30 |  | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31000
North Central | 2 | Elk | 123460 | T-314, Arroyo Bridge Preservation | 7210 | LOC | Bridge Preservation - State Funded | CON | ACT13 |  |  | 14850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14850
North Central | 2 | McKean | 4333 | T-385 over Potato Creek | 7209 | HTB | Bridge Restoration | FD | STP | 2027-04-01 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
North Central | 2 | McKean | 4334 | Pennbrook Run Bridge 2 | 646 | A01 | Bridge Restoration | PE | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537566 | 537566
North Central | 2 | McKean | 4334 | Pennbrook Run Bridge 2 | 646 | A01 | Bridge Restoration | FD | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403175 | 403175
North Central | 2 | McKean | 4334 | Pennbrook Run Bridge 2 | 646 | A01 | Bridge Restoration | ROW | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 4334 | Pennbrook Run Bridge 2 | 646 | A01 | Bridge Restoration | UTL | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 4334 | Pennbrook Run Bridge 2 | 646 | A01 | Bridge Restoration | CON | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1007937 | 1007937
North Central | 2 | McKean | 4334 | Pennbrook Run Bridge 2 | 646 | A01 | Bridge Restoration | CON | 581 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
North Central | 2 | McKean | 4383 | T-437 Oswayo Creek | 7203 | REM | Bridge Removal | PE | 581 | 2027-12-16 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
North Central | 2 | McKean | 4383 | T-437 Oswayo Creek | 7203 | REM | Bridge Removal | ROW | 581 | 2027-12-16 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | McKean | 4383 | T-437 Oswayo Creek | 7203 | REM | Bridge Removal | CON | 581 | 2027-12-16 |  | 0 | 0 | 0 | 345000 | 0 | 0 | 0 | 0 | 0 | 345000
North Central | 2 | McKean | 69304 | SR 4013 Bolivar Run | 4013 | A01 | Bridge Restoration | PE | 581 | 2030-02-28 |  | 0 | 0 | 0 | 393928 | 0 | 0 | 0 | 0 | 0 | 393928
North Central | 2 | McKean | 69304 | SR 4013 Bolivar Run | 4013 | A01 | Bridge Restoration | FD | STP | 2030-02-28 |  | 0 | 0 | 0 | 0 | 358216 | 0 | 0 | 0 | 0 | 358216
North Central | 2 | McKean | 69304 | SR 4013 Bolivar Run | 4013 | A01 | Bridge Restoration | ROW | STP | 2030-02-28 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
North Central | 2 | McKean | 69304 | SR 4013 Bolivar Run | 4013 | A01 | Bridge Restoration | UTL | STP | 2030-02-28 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
North Central | 2 | McKean | 69304 | SR 4013 Bolivar Run | 4013 | A01 | Bridge Restoration | CON | STP | 2030-02-28 |  | 0 | 0 | 0 | 0 | 0 | 1537342 | 0 | 0 | 0 | 1537342
North Central | 2 | McKean | 81410 | SR 246 Baker Run | 246 | A05 | Bridge Restoration | CON | 581 | 2023-12-07 | 2023-12-07 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | McKean | 85232 | Gates Hollow | 346 | A09 | Bridge Restoration | FD | 581 | 2024-12-12 | 2024-12-12 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | McKean | 85232 | Gates Hollow | 346 | A09 | Bridge Restoration | ROW | 581 | 2024-12-12 | 2024-12-12 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | McKean | 85232 | Gates Hollow | 346 | A09 | Bridge Restoration | UTL | 581 | 2024-12-12 | 2024-12-12 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | McKean | 85232 | Gates Hollow | 346 | A09 | Bridge Restoration | CON | 581 | 2024-12-12 | 2024-12-12 | 1035383 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1635383
North Central | 2 | McKean | 85236 | SR 446 Canfield Creek | 446 | A06 | Bridge Restoration | FD | 185 | 2029-02-22 |  | 0 | 0 | 0 | 213855 | 0 | 0 | 0 | 0 | 0 | 213855
North Central | 2 | McKean | 85236 | SR 446 Canfield Creek | 446 | A06 | Bridge Restoration | ROW | 185 | 2029-02-22 |  | 0 | 0 | 0 | 57963 | 0 | 0 | 0 | 0 | 0 | 57963
North Central | 2 | McKean | 85236 | SR 446 Canfield Creek | 446 | A06 | Bridge Restoration | UTL | 185 | 2029-02-22 |  | 0 | 0 | 0 | 57963 | 0 | 0 | 0 | 0 | 0 | 57963
North Central | 2 | McKean | 85236 | SR 446 Canfield Creek | 446 | A06 | Bridge Restoration | CON | 185 | 2029-02-22 |  | 0 | 0 | 0 | 0 | 716431 | 0 | 0 | 0 | 0 | 716431
North Central | 2 | McKean | 85241 | SR 2001 over Smith Run | 2001 | A02 | Bridge Restoration | CON | 581 | 2023-12-07 | 2023-12-07 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | McKean | 85250 | SR 3006 over Windfall Run | 3006 | A02 | Bridge Restoration | PE | 581 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537567 | 537567
North Central | 2 | McKean | 85250 | SR 3006 over Windfall Run | 3006 | A02 | Bridge Restoration | ROW | 581 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 85250 | SR 3006 over Windfall Run | 3006 | A02 | Bridge Restoration | UTL | 581 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 85250 | SR 3006 over Windfall Run | 3006 | A02 | Bridge Restoration | CON | 581 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411112 | 1411112
North Central | 2 | McKean | 85260 | SR 0346 over Willow Creek | 346 | A16 | Bridge Replacement | PE | BRIP | 2031-05-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 505000 | 0 | 0 | 505000
North Central | 2 | McKean | 85260 | SR 0346 over Willow Creek | 346 | A16 | Bridge Replacement | FD | BRIP | 2031-05-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374522 | 0 | 374522
North Central | 2 | McKean | 85260 | SR 0346 over Willow Creek | 346 | A16 | Bridge Replacement | ROW | BRIP | 2031-05-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65239 | 0 | 65239
North Central | 2 | McKean | 85260 | SR 0346 over Willow Creek | 346 | A16 | Bridge Replacement | UTL | BRIP | 2031-05-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65239 | 0 | 65239
North Central | 2 | McKean | 85260 | SR 0346 over Willow Creek | 346 | A16 | Bridge Replacement | CON | 581 | 2031-05-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1343916 | 1343916
North Central | 2 | McKean | 85261 | Foster Brook BOX | 346 | A12 | Bridge Restoration | PE | 185 | 2025-10-09 | 2025-10-09 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
North Central | 2 | McKean | 85261 | Foster Brook BOX | 346 | A12 | Bridge Restoration | ROW | 185 | 2025-10-09 | 2025-10-09 | 34890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34890
North Central | 2 | McKean | 85261 | Foster Brook BOX | 346 | A12 | Bridge Restoration | UTL | 185 | 2025-10-09 | 2025-10-09 | 108826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108826
North Central | 2 | McKean | 85261 | Foster Brook BOX | 346 | A12 | Bridge Restoration | CON | 185 | 2025-10-09 | 2025-10-09 | 597156 | 246364 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 1143520
North Central | 2 | McKean | 85264 | SR 446 over Br. Allegheny | 446 | A05 | Bridge Restoration | PE | 185 | 2028-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521909 | 0 | 521909
North Central | 2 | McKean | 85264 | SR 446 over Br. Allegheny | 446 | A05 | Bridge Restoration | FD | 185 | 2028-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268783 | 268783
North Central | 2 | McKean | 85264 | SR 446 over Br. Allegheny | 446 | A05 | Bridge Restoration | ROW | 185 | 2028-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 85264 | SR 446 over Br. Allegheny | 446 | A05 | Bridge Restoration | UTL | 185 | 2028-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 85264 | SR 446 over Br. Allegheny | 446 | A05 | Bridge Restoration | CON | 185 | 2028-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 806350 | 806350
North Central | 2 | McKean | 85264 | SR 446 over Br. Allegheny | 446 | A05 | Bridge Restoration | CON | 581 | 2028-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000 | 480000
North Central | 2 | McKean | 85269 | SR 1011 over Fowler Run BOX | 1011 | A05 | Bridge Restoration | CON | 581 | 2024-09-26 | 2024-09-26 | 530450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530450
North Central | 2 | McKean | 88628 | Bridge on Tram Hollow Run | 346 | A13 | Bridge Replacement | CON | 185 | 2024-01-11 | 2024-01-11 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | McKean | 88665 | Bridge on IRON HOLLOW RUN | 6 | A15 | Bridge Restoration | PE | NHPP | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457496 | 457496
North Central | 2 | McKean | 88665 | Bridge on IRON HOLLOW RUN | 6 | A15 | Bridge Restoration | ROW | NHPP | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 88665 | Bridge on IRON HOLLOW RUN | 6 | A15 | Bridge Restoration | UTL | NHPP | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 88665 | Bridge on IRON HOLLOW RUN | 6 | A15 | Bridge Restoration | CON | NHPP | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411112 | 1411112
North Central | 2 | McKean | 91547 | SR 346 Marilla Creek Br | 346 | A14 | Bridge Restoration | PE | 185 | 2027-08-26 |  | 364360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364360
North Central | 2 | McKean | 91547 | SR 346 Marilla Creek Br | 346 | A14 | Bridge Restoration | FD | 185 | 2027-08-26 |  | 0 | 261377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261377
North Central | 2 | McKean | 91547 | SR 346 Marilla Creek Br | 346 | A14 | Bridge Restoration | ROW | 185 | 2027-08-26 |  | 0 | 37963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37963
North Central | 2 | McKean | 91547 | SR 346 Marilla Creek Br | 346 | A14 | Bridge Restoration | UTL | 185 | 2027-08-26 |  | 0 | 37963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37963
North Central | 2 | McKean | 91547 | SR 346 Marilla Creek Br | 346 | A14 | Bridge Restoration | CON | 581 | 2027-08-26 |  | 0 | 0 | 789853 | 0 | 0 | 0 | 0 | 0 | 0 | 789853
North Central | 2 | McKean | 91549 | SR 155 Br. Portage Creek | 155 | A08 | Bridge Restoration | PE | 185 | 2028-10-26 |  | 0 | 0 | 172714 | 300000 | 0 | 0 | 0 | 0 | 0 | 472714
North Central | 2 | McKean | 91549 | SR 155 Br. Portage Creek | 155 | A08 | Bridge Restoration | ROW | 185 | 2028-10-26 |  | 0 | 0 | 0 | 46371 | 0 | 0 | 0 | 0 | 0 | 46371
North Central | 2 | McKean | 91549 | SR 155 Br. Portage Creek | 155 | A08 | Bridge Restoration | UTL | 185 | 2028-10-26 |  | 0 | 0 | 0 | 46371 | 0 | 0 | 0 | 0 | 0 | 46371
North Central | 2 | McKean | 91549 | SR 155 Br. Portage Creek | 155 | A08 | Bridge Restoration | CON | 185 | 2028-10-26 |  | 0 | 0 | 0 | 0 | 597026 | 0 | 0 | 0 | 0 | 597026
North Central | 2 | McKean | 101326 | Resurface US 6 to PA 646 | 46 | 0 | Highway Restoration | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3792680 | 0 | 3792680
North Central | 2 | McKean | 101336 | PA 46 to State Line Road | 446 | 0 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 3445814 | 0 | 0 | 0 | 0 | 3445814
North Central | 2 | McKean | 101510 | Bridge over Bennett Brook | 4011 | A02 | Bridge Restoration | PE | BRIP | 2027-03-11 |  | 150000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000
North Central | 2 | McKean | 101510 | Bridge over Bennett Brook | 4011 | A02 | Bridge Restoration | FD | BRIP | 2027-03-11 |  | 168151 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328151
North Central | 2 | McKean | 101510 | Bridge over Bennett Brook | 4011 | A02 | Bridge Restoration | ROW | BRIP | 2027-03-11 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
North Central | 2 | McKean | 101510 | Bridge over Bennett Brook | 4011 | A02 | Bridge Restoration | UTL | BRIP | 2027-03-11 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
North Central | 2 | McKean | 101510 | Bridge over Bennett Brook | 4011 | A02 | Bridge Restoration | CON | BRIP | 2027-03-11 |  | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
North Central | 2 | McKean | 108850 | Group 2-24-ST52 | 446 | 0 | General Maintenance | CON | 581 | 2024-06-13 | 2024-06-13 | 100000 | 95600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195600
North Central | 2 | McKean | 109705 | SR 346 over Meadow Branch | 346 | A15 | Bridge Restoration | PE | 185 | 2027-08-26 |  | 332360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332360
North Central | 2 | McKean | 109705 | SR 346 over Meadow Branch | 346 | A15 | Bridge Restoration | ROW | 185 | 2027-08-26 |  | 0 | 55502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55502
North Central | 2 | McKean | 109705 | SR 346 over Meadow Branch | 346 | A15 | Bridge Restoration | CON | 581 | 2027-08-26 |  | 0 | 0 | 900407 | 0 | 0 | 0 | 0 | 0 | 0 | 900407
North Central | 2 | McKean | 109707 | SR 321 over Trib Hurbert Run BOX | 321 | A03 | Bridge Restoration | PE | 185 | 2032-06-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 503175 | 503175
North Central | 2 | McKean | 109707 | SR 321 over Trib Hurbert Run BOX | 321 | A03 | Bridge Restoration | ROW | 185 | 2032-06-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 109707 | SR 321 over Trib Hurbert Run BOX | 321 | A03 | Bridge Restoration | UTL | 185 | 2032-06-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 109707 | SR 321 over Trib Hurbert Run BOX | 321 | A03 | Bridge Restoration | CON | 185 | 2032-06-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440981 | 1440981
North Central | 2 | McKean | 109873 | SR 346/4009 Signals/Roadway Improvements | 346 | 538 | Safety Improvement | FD | STP | 2026-08-13 |  | 300000 | 153000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 453000
North Central | 2 | McKean | 109873 | SR 346/4009 Signals/Roadway Improvements | 346 | 538 | Safety Improvement | ROW | STP | 2026-08-13 |  | 76321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76321
North Central | 2 | McKean | 109873 | SR 346/4009 Signals/Roadway Improvements | 346 | 538 | Safety Improvement | UTL | 581 | 2026-08-13 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | McKean | 109873 | SR 346/4009 Signals/Roadway Improvements | 346 | 538 | Safety Improvement | CON | HVRU | 2026-08-13 |  | 140000 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420000
North Central | 2 | McKean | 109873 | SR 346/4009 Signals/Roadway Improvements | 346 | 538 | Safety Improvement | CON | STP | 2026-08-13 |  | 0 | 1426746 | 1116680 | 854000 | 0 | 0 | 0 | 0 | 0 | 3397426
North Central | 2 | McKean | 109873 | SR 346/4009 Signals/Roadway Improvements | 346 | 538 | Safety Improvement | CON | 581 | 2026-08-13 |  | 0 | 1077172 | 2425466 | 0 | 0 | 0 | 0 | 0 | 0 | 3502638
North Central | 2 | McKean | 110672 | 2023 NC Bridge Preservation | 6 | P38 | Bridge Restoration | CON | NHPP | 2023-04-27 | 2023-04-27 | 91211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91211
North Central | 2 | McKean | 113148 | SR 1002 over Trib Potato Creek | 1002 | A05 | Bridge Replacement | PE | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537567 | 537567
North Central | 2 | McKean | 113148 | SR 1002 over Trib Potato Creek | 1002 | A05 | Bridge Replacement | ROW | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 113148 | SR 1002 over Trib Potato Creek | 1002 | A05 | Bridge Replacement | UTL | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 113148 | SR 1002 over Trib Potato Creek | 1002 | A05 | Bridge Replacement | CON | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411112 | 1411112
North Central | 2 | McKean | 113149 | SR 646 over Pennbrook Run | 646 | A04 | Bridge Restoration | PE | STP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537566 | 537566
North Central | 2 | McKean | 113149 | SR 646 over Pennbrook Run | 646 | A04 | Bridge Restoration | ROW | STP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 113149 | SR 646 over Pennbrook Run | 646 | A04 | Bridge Restoration | UTL | STP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 113149 | SR 646 over Pennbrook Run | 646 | A04 | Bridge Restoration | CON | STP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2116669 | 2116669
North Central | 2 | McKean | 116852 | SR 446 over Carpenter Creek | 446 | A07 | Bridge Restoration | PE | 185 | 2030-02-01 |  | 0 | 0 | 0 | 0 | 0 | 418157 | 0 | 0 | 0 | 418157
North Central | 2 | McKean | 116852 | SR 446 over Carpenter Creek | 446 | A07 | Bridge Restoration | ROW | 185 | 2030-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 63339 | 0 | 0 | 63339
North Central | 2 | McKean | 116852 | SR 446 over Carpenter Creek | 446 | A07 | Bridge Restoration | UTL | 185 | 2030-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 63339 | 0 | 0 | 63339
North Central | 2 | McKean | 116852 | SR 446 over Carpenter Creek | 446 | A07 | Bridge Restoration | CON | 185 | 2030-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 978580 | 0 | 978580
North Central | 2 | McKean | 116860 | SR 346 over Cobbs Hollow Run BOX | 346 | A17 | Bridge Replacement | PE | 185 | 2028-08-24 |  | 0 | 371527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371527
North Central | 2 | McKean | 116860 | SR 346 over Cobbs Hollow Run BOX | 346 | A17 | Bridge Replacement | ROW | 581 | 2028-08-24 |  | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 0 | 56275
North Central | 2 | McKean | 116860 | SR 346 over Cobbs Hollow Run BOX | 346 | A17 | Bridge Replacement | UTL | 581 | 2028-08-24 |  | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 0 | 56275
North Central | 2 | McKean | 116860 | SR 346 over Cobbs Hollow Run BOX | 346 | A17 | Bridge Replacement | CON | 185 | 2028-08-24 |  | 0 | 0 | 0 | 869456 | 0 | 0 | 0 | 0 | 0 | 869456
North Central | 2 | McKean | 117037 | NC Bridge Preservation 3 | 246 | P62 | Bridge Restoration | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 503175 | 503175
North Central | 2 | McKean | 117037 | NC Bridge Preservation 3 | 246 | P62 | Bridge Restoration | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 117037 | NC Bridge Preservation 3 | 246 | P62 | Bridge Restoration | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | McKean | 117037 | NC Bridge Preservation 3 | 246 | P62 | Bridge Restoration | CON | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3337503 | 3337503
North Central | 2 | McKean | 117037 | NC Bridge Preservation 3 | 246 | P62 | Bridge Restoration | CON | 581 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
North Central | 2 | McKean | 117079 | SR 446 Main St. Recon. | 446 | 543 | Highway Restoration | FD | STP | 2025-12-11 | 2025-12-11 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000
North Central | 2 | McKean | 117079 | SR 446 Main St. Recon. | 446 | 543 | Highway Restoration | ROW | STP | 2025-12-11 | 2025-12-11 | 67000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67000
North Central | 2 | McKean | 117079 | SR 446 Main St. Recon. | 446 | 543 | Highway Restoration | UTL | STP | 2025-12-11 | 2025-12-11 | 34571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34571
North Central | 2 | McKean | 117079 | SR 446 Main St. Recon. | 446 | 543 | Highway Restoration | CON | STP | 2025-12-11 | 2025-12-11 | 0 | 2181545 | 1311000 | 596412 | 0 | 0 | 0 | 0 | 0 | 4088957
North Central | 2 | McKean | 117079 | SR 446 Main St. Recon. | 446 | 543 | Highway Restoration | CON | 581 | 2025-12-11 | 2025-12-11 | 0 | 355636 | 565579 | 0 | 0 | 0 | 0 | 0 | 0 | 921215
North Central | 2 | McKean | 117802 | SR 59 Drainage Improvements | 59 | 542 | Highway Restoration | PE | STP | 2026-02-12 | 2026-02-26 | 52905 | 87670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140575
North Central | 2 | McKean | 117802 | SR 59 Drainage Improvements | 59 | 542 | Highway Restoration | CON | STP | 2026-02-12 | 2026-02-26 | 850000 | 202697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1052697
North Central | 2 | McKean | 117878 | SR 46 Roadway Restoration | 46 | 541 | Highway Restoration | ROW | 581 | 2027-06-24 |  | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000
North Central | 2 | McKean | 117878 | SR 46 Roadway Restoration | 46 | 541 | Highway Restoration | UTL | 581 | 2027-06-24 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | McKean | 117878 | SR 46 Roadway Restoration | 46 | 541 | Highway Restoration | CON | HSIP | 2027-06-24 |  | 0 | 0 | 0 | 371000 | 1228813 | 0 | 592379 | 934800 | 415058 | 3542050
North Central | 2 | McKean | 118630 | Arnold Avenue Bridge (II) | 7405 | LOC | Bridge Replacement | FD | BOF | 2026-01-29 | 2026-02-12 | 304172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304172
North Central | 2 | McKean | 118630 | Arnold Avenue Bridge (II) | 7405 | LOC | Bridge Replacement | ROW | BOF | 2026-01-29 | 2026-02-12 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000
North Central | 2 | McKean | 118630 | Arnold Avenue Bridge (II) | 7405 | LOC | Bridge Replacement | UTL | BOF | 2026-01-29 | 2026-02-12 | 10609 | 42436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53045
North Central | 2 | McKean | 118630 | Arnold Avenue Bridge (II) | 7405 | LOC | Bridge Replacement | CON | BOF | 2026-01-29 | 2026-02-12 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
North Central | 2 | McKean | 118630 | Arnold Avenue Bridge (II) | 7405 | LOC | Bridge Replacement | CON | RURAL | 2026-01-29 | 2026-02-12 | 0 | 719201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719201
North Central | 2 | McKean | 118671 | SR 770 Roadway and Slope Stability | 770 | 545 | Highway Restoration | PE | 581 | 2026-07-02 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | McKean | 118671 | SR 770 Roadway and Slope Stability | 770 | 545 | Highway Restoration | FD | PRTCT | 2026-07-02 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
North Central | 2 | McKean | 118671 | SR 770 Roadway and Slope Stability | 770 | 545 | Highway Restoration | ROW | 581 | 2026-07-02 |  | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000
North Central | 2 | McKean | 118671 | SR 770 Roadway and Slope Stability | 770 | 545 | Highway Restoration | CON | PRTCT | 2026-07-02 |  | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
North Central | 2 | McKean | 118671 | SR 770 Roadway and Slope Stability | 770 | 545 | Highway Restoration | CON | 581 | 2026-07-02 |  | 0 | 0 | 639000 | 0 | 0 | 0 | 0 | 0 | 0 | 639000
North Central | 2 | McKean | 119251 | Ormsby to Cyclone | 646 | 544 | Highway Restoration | CON | 581 | 2023-12-14 | 2023-12-14 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
North Central | 2 | McKean | 120102 | SR 770 HFST | 770 | HFS | Safety Improvement | CON | HSIP | 2024-06-13 | 2024-06-13 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
North Central | 2 | McKean | 120107 | SR 46 HFST | 46 | HFS | Safety Improvement | CON | HSIP | 2024-06-13 | 2024-06-13 | 33013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33013
North Central | 2 | McKean | 120132 | Seaward Ave & 219 Ramps Intersection Improvement | 4013 | N48 | Safety Improvement | PE | 581 | 2027-06-24 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
North Central | 2 | McKean | 120132 | Seaward Ave & 219 Ramps Intersection Improvement | 4013 | N48 | Safety Improvement | FD | HSIP | 2027-06-24 |  | 0 | 0 | 196000 | 200000 | 0 | 0 | 0 | 0 | 0 | 396000
North Central | 2 | McKean | 120132 | Seaward Ave & 219 Ramps Intersection Improvement | 4013 | N48 | Safety Improvement | ROW | HSIP | 2027-06-24 |  | 0 | 0 | 20000 | 29500 | 0 | 0 | 0 | 0 | 0 | 49500
North Central | 2 | McKean | 120132 | Seaward Ave & 219 Ramps Intersection Improvement | 4013 | N48 | Safety Improvement | UTL | HSIP | 2027-06-24 |  | 0 | 0 | 20000 | 29500 | 0 | 0 | 0 | 0 | 0 | 49500
North Central | 2 | McKean | 120132 | Seaward Ave & 219 Ramps Intersection Improvement | 4013 | N48 | Safety Improvement | CON | HSIP | 2027-06-24 |  | 0 | 0 | 0 | 234800 | 35987 | 934800 | 342421 | 0 | 0 | 1548008
North Central | 2 | McKean | 120289 | SR 6 HFST Hamlin Twp | 6 | HFS | Safety Improvement | CON | HSIP | 2024-06-13 | 2024-06-13 | 83286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83286
North Central | 2 | McKean | 120290 | State Route 46 HFST Foster Twp | 46 | HFS | Safety Improvement | CON | HSIP | 2024-06-13 | 2024-06-13 | 104052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104052
North Central | 2 | McKean | 120511 | SR 446 over Branch Cole Creek | 446 | A08 | Bridge Replacement | FD | 581 | 2029-02-22 |  | 0 | 0 | 0 | 347782 | 0 | 0 | 0 | 0 | 0 | 347782
North Central | 2 | McKean | 120511 | SR 446 over Branch Cole Creek | 446 | A08 | Bridge Replacement | ROW | 581 | 2029-02-22 |  | 0 | 0 | 0 | 57963 | 0 | 0 | 0 | 0 | 0 | 57963
North Central | 2 | McKean | 120511 | SR 446 over Branch Cole Creek | 446 | A08 | Bridge Replacement | UTL | 581 | 2029-02-22 |  | 0 | 0 | 0 | 57963 | 0 | 0 | 0 | 0 | 0 | 57963
North Central | 2 | McKean | 120511 | SR 446 over Branch Cole Creek | 446 | A08 | Bridge Replacement | CON | 581 | 2029-02-22 |  | 0 | 0 | 0 | 0 | 955242 | 0 | 0 | 0 | 0 | 955242
North Central | 2 | McKean | 121376 | East Main Street Retaining Wall |  |  | Highway Restoration | FD | PRTCT | 2027-10-21 |  | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
North Central | 2 | McKean | 121376 | East Main Street Retaining Wall |  |  | Highway Restoration | FD | LOC | 2027-10-21 |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
North Central | 2 | McKean | 121376 | East Main Street Retaining Wall |  |  | Highway Restoration | CON | PRTCT | 2027-10-21 |  | 0 | 810750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810750
North Central | 2 | McKean | 121376 | East Main Street Retaining Wall |  |  | Highway Restoration | CON | LOC | 2027-10-21 |  | 0 | 202688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202688
North Central | 2 | McKean | 121547 | N Bennett St/Campus Dr Ped Imprv, TASA |  | TSA | Bicycle Pedestrian Highway | CON | TAP | 2025-05-08 | 2025-05-08 | 704840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704840
North Central | 2 | McKean | 121657 | SR 46 Kendall Ave RRFB | 46 | RFB | Safety Improvement | PE | HVRU | 2025-12-11 | 2025-12-11 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
North Central | 2 | McKean | 121657 | SR 46 Kendall Ave RRFB | 46 | RFB | Safety Improvement | ROW | 581 | 2025-12-11 | 2025-12-11 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
North Central | 2 | McKean | 121657 | SR 46 Kendall Ave RRFB | 46 | RFB | Safety Improvement | CON | HVRU | 2025-12-11 | 2025-12-11 | 150000 | 95470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245470
North Central | 2 | McKean | 122199 | 2025 North Central Bridge Epoxy | 246 | EPX | Bridge Preservation - State Funded | CON | 185 | 2025-04-17 | 2025-04-17 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
North Central | 2 | McKean | 122547 | SR 446 Paving | 446 | 546 | Highway Restoration | CON | 581 | 2025-06-26 | 2025-06-26 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000
North Central | 2 | McKean | 122547 | SR 446 Paving | 446 | 546 | Highway Restoration | CON | 185 | 2025-06-26 | 2025-06-26 | 62068 | 137932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
North Central | 2 | McKean | 122547 | SR 446 Paving | 446 | 546 | Highway Restoration | CON | 581 | 2025-06-26 | 2025-06-26 | 198914 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248914
North Central | 2 | Potter | 4854 | Elliot Street Bridge |  | BR | Bridge Replacement | CON | 581 |  |  | 104624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104624
North Central | 2 | Potter | 4854 | Elliot Street Bridge |  | BR | Bridge Replacement | CON | 581 |  |  | 270496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270496
North Central | 2 | Potter | 4915 | PA 144 Pine Ck. Br. | 144 | P02 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 477621 | 0 | 0 | 0 | 0 | 477621
North Central | 2 | Potter | 4915 | PA 144 Pine Ck. Br. | 144 | P02 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 354199 | 0 | 0 | 0 | 354199
North Central | 2 | Potter | 4915 | PA 144 Pine Ck. Br. | 144 | P02 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 122988 | 0 | 0 | 0 | 122988
North Central | 2 | Potter | 4915 | PA 144 Pine Ck. Br. | 144 | P02 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 690535 | 0 | 0 | 690535
North Central | 2 | Potter | 4915 | PA 144 Pine Ck. Br. | 144 | P02 | Bridge Replacement | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 1583463 | 0 | 0 | 0 | 1583463
North Central | 2 | Potter | 69438 | Phoenix Run Bridge | 1005 | A04 | Bridge Restoration | PE | BOF | 2028-08-30 |  | 0 | 258945 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 308945
North Central | 2 | Potter | 69438 | Phoenix Run Bridge | 1005 | A04 | Bridge Restoration | PE | STP | 2028-08-30 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
North Central | 2 | Potter | 69438 | Phoenix Run Bridge | 1005 | A04 | Bridge Restoration | FD | BOF | 2028-08-30 |  | 0 | 0 | 337652 | 0 | 0 | 0 | 0 | 0 | 0 | 337652
North Central | 2 | Potter | 69438 | Phoenix Run Bridge | 1005 | A04 | Bridge Restoration | ROW | BOF | 2028-08-30 |  | 0 | 0 | 56276 | 0 | 0 | 0 | 0 | 0 | 0 | 56276
North Central | 2 | Potter | 69438 | Phoenix Run Bridge | 1005 | A04 | Bridge Restoration | UTL | BOF | 2028-08-30 |  | 0 | 0 | 56276 | 0 | 0 | 0 | 0 | 0 | 0 | 56276
North Central | 2 | Potter | 69438 | Phoenix Run Bridge | 1005 | A04 | Bridge Restoration | CON | BOF | 2028-08-30 |  | 0 | 0 | 0 | 1159274 | 290000 | 0 | 0 | 0 | 0 | 1449274
North Central | 2 | Potter | 78637 | SR 1022 over Pine Creek | 1022 | A02 | Bridge Restoration | CON | 185 | 2024-02-15 | 2024-02-15 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
North Central | 2 | Potter | 78647 | SR 4003 over Allegheny Rv | 4003 | A09 | Bridge Replacement | PE | BOF | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537567 | 537567
North Central | 2 | Potter | 78647 | SR 4003 over Allegheny Rv | 4003 | A09 | Bridge Replacement | FD | BOF | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403175 | 403175
North Central | 2 | Potter | 78647 | SR 4003 over Allegheny Rv | 4003 | A09 | Bridge Replacement | ROW | BOF | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | Potter | 78647 | SR 4003 over Allegheny Rv | 4003 | A09 | Bridge Replacement | UTL | BOF | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | Potter | 78647 | SR 4003 over Allegheny Rv | 4003 | A09 | Bridge Replacement | CON | BOF | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1181483 | 1181483
North Central | 2 | Potter | 78647 | SR 4003 over Allegheny Rv | 4003 | A09 | Bridge Replacement | CON | NHPP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1870642 | 1870642
North Central | 2 | Potter | 78647 | SR 4003 over Allegheny Rv | 4003 | A09 | Bridge Replacement | CON | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763032 | 763032
North Central | 2 | Potter | 83526 | SR 3002 Cowley Run Bridge | 3002 | A01 | Bridge Restoration | PE | BRIP | 2028-09-30 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Potter | 83526 | SR 3002 Cowley Run Bridge | 3002 | A01 | Bridge Restoration | FD | BRIP | 2028-09-30 |  | 0 | 327818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327818
North Central | 2 | Potter | 83526 | SR 3002 Cowley Run Bridge | 3002 | A01 | Bridge Restoration | ROW | BRIP | 2028-09-30 |  | 0 | 109272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109272
North Central | 2 | Potter | 83526 | SR 3002 Cowley Run Bridge | 3002 | A01 | Bridge Restoration | UTL | BRIP | 2028-09-30 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
North Central | 2 | Potter | 83526 | SR 3002 Cowley Run Bridge | 3002 | A01 | Bridge Restoration | CON | BRIP | 2028-09-30 |  | 0 | 0 | 0 | 298114 | 0 | 0 | 0 | 0 | 0 | 298114
North Central | 2 | Potter | 83526 | SR 3002 Cowley Run Bridge | 3002 | A01 | Bridge Restoration | CON | STP | 2028-09-30 |  | 0 | 0 | 0 | 747000 | 0 | 0 | 0 | 0 | 0 | 747000
North Central | 2 | Potter | 83526 | SR 3002 Cowley Run Bridge | 3002 | A01 | Bridge Restoration | CON | 581 | 2028-09-30 |  | 0 | 0 | 0 | 744510 | 0 | 0 | 0 | 0 | 0 | 744510
North Central | 2 | Potter | 83527 | Brizzee Hollow Run | 4025 | A01 | Bridge Replacement | FD | 185 | 2024-09-12 | 2024-09-12 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Potter | 83527 | Brizzee Hollow Run | 4025 | A01 | Bridge Replacement | CON | BOF | 2024-09-12 | 2024-09-12 | 436168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 436168
North Central | 2 | Potter | 83527 | Brizzee Hollow Run | 4025 | A01 | Bridge Replacement | CON | BRIP | 2024-09-12 | 2024-09-12 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
North Central | 2 | Potter | 84099 | Marsh Creek | 49 | A08 | Bridge Restoration | PE | 185 | 2026-02-26 | 2026-02-26 | 20500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20500
North Central | 2 | Potter | 84099 | Marsh Creek | 49 | A08 | Bridge Restoration | FD | 581 | 2026-02-26 | 2026-02-26 | 270036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270036
North Central | 2 | Potter | 84099 | Marsh Creek | 49 | A08 | Bridge Restoration | ROW | 185 | 2026-02-26 | 2026-02-26 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000
North Central | 2 | Potter | 84099 | Marsh Creek | 49 | A08 | Bridge Restoration | CON | 185 | 2026-02-26 | 2026-02-26 | 0 | 565909 | 730000 | 0 | 0 | 0 | 0 | 0 | 0 | 1295909
North Central | 2 | Potter | 85310 | SR 49 over Steer Run | 49 | A10 | Bridge Restoration | PE | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537567 | 537567
North Central | 2 | Potter | 85310 | SR 49 over Steer Run | 49 | A10 | Bridge Restoration | ROW | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | Potter | 85310 | SR 49 over Steer Run | 49 | A10 | Bridge Restoration | UTL | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | Potter | 85310 | SR 49 over Steer Run | 49 | A10 | Bridge Restoration | CON | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411112 | 1411112
North Central | 2 | Potter | 85313 | SR 49 over Trib. Allegh | 49 | A14 | Highway Restoration | PE | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 358216 | 0 | 0 | 0 | 0 | 358216
North Central | 2 | Potter | 85313 | SR 49 over Trib. Allegh | 49 | A14 | Highway Restoration | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 307468 | 0 | 0 | 0 | 307468
North Central | 2 | Potter | 85313 | SR 49 over Trib. Allegh | 49 | A14 | Highway Restoration | ROW | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 92241 | 0 | 0 | 0 | 92241
North Central | 2 | Potter | 85313 | SR 49 over Trib. Allegh | 49 | A14 | Highway Restoration | UTL | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 92241 | 0 | 0 | 0 | 92241
North Central | 2 | Potter | 85313 | SR 49 over Trib. Allegh | 49 | A14 | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1013416 | 0 | 0 | 1013416
North Central | 2 | Potter | 85314 | SR 49 over Marsh Creek Box | 49 | A13 | Bridge Restoration | FD | 581 | 2026-02-26 | 2026-02-26 | 290443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290443
North Central | 2 | Potter | 85314 | SR 49 over Marsh Creek Box | 49 | A13 | Bridge Restoration | ROW | 581 | 2026-02-26 | 2026-02-26 | 10000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
North Central | 2 | Potter | 85314 | SR 49 over Marsh Creek Box | 49 | A13 | Bridge Restoration | UTL | 581 | 2026-02-26 | 2026-02-26 | 133020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133020
North Central | 2 | Potter | 85314 | SR 49 over Marsh Creek Box | 49 | A13 | Bridge Restoration | CON | STP | 2026-02-26 | 2026-02-26 | 0 | 1058325 | 341675 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
North Central | 2 | Potter | 85314 | SR 49 over Marsh Creek Box | 49 | A13 | Bridge Restoration | CON | 581 | 2026-02-26 | 2026-02-26 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
North Central | 2 | Potter | 85388 | SR 1003 over Br Genesee | 1003 | A06 | Bridge Restoration | PE | 185 | 2026-07-30 |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
North Central | 2 | Potter | 85388 | SR 1003 over Br Genesee | 1003 | A06 | Bridge Restoration | FD | 185 | 2026-07-30 |  | 265225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265225
North Central | 2 | Potter | 85388 | SR 1003 over Br Genesee | 1003 | A06 | Bridge Restoration | ROW | 185 | 2026-07-30 |  | 22436 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42436
North Central | 2 | Potter | 85388 | SR 1003 over Br Genesee | 1003 | A06 | Bridge Restoration | UTL | 185 | 2026-07-30 |  | 22436 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42436
North Central | 2 | Potter | 85388 | SR 1003 over Br Genesee | 1003 | A06 | Bridge Restoration | CON | 185 | 2026-07-30 |  | 0 | 0 | 290000 | 0 | 0 | 0 | 0 | 0 | 0 | 290000
North Central | 2 | Potter | 85388 | SR 1003 over Br Genesee | 1003 | A06 | Bridge Restoration | CON | 581 | 2026-07-30 |  | 0 | 869143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869143
North Central | 2 | Potter | 85489 | SR 49 over Ludington Rn | 49 | A15 | Bridge Restoration | PE | STP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537567 | 537567
North Central | 2 | Potter | 85489 | SR 49 over Ludington Rn | 49 | A15 | Bridge Restoration | FD | STP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403175 | 403175
North Central | 2 | Potter | 85489 | SR 49 over Ludington Rn | 49 | A15 | Bridge Restoration | ROW | STP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | Potter | 85489 | SR 49 over Ludington Rn | 49 | A15 | Bridge Restoration | UTL | STP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 67196
North Central | 2 | Potter | 85489 | SR 49 over Ludington Rn | 49 | A15 | Bridge Restoration | CON | STP | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1343916 | 1343916
North Central | 2 | Potter | 85489 | SR 49 over Ludington Rn | 49 | A15 | Bridge Restoration | CON | 581 | 2033-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
North Central | 2 | Potter | 85490 | SR 0144 over Kettle Creek | 144 | P01 | Bridge Replacement | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 505000 | 0 | 0 | 0 | 505000
North Central | 2 | Potter | 85490 | SR 0144 over Kettle Creek | 144 | P01 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 0 | 0 | 67196
North Central | 2 | Potter | 85490 | SR 0144 over Kettle Creek | 144 | P01 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 67196 | 0 | 0 | 67196
North Central | 2 | Potter | 85490 | SR 0144 over Kettle Creek | 144 | P01 | Bridge Replacement | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 957300 | 1449563 | 0 | 2406863
North Central | 2 | Potter | 85535 | T-351 over Oswayo Creek, | 7204 | REM | Bridge Removal | ROW | 581 | 2025-05-22 | 2025-05-22 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
North Central | 2 | Potter | 85535 | T-351 over Oswayo Creek, | 7204 | REM | Bridge Removal | CON | 581 | 2025-05-22 | 2025-05-22 | 290000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290000
North Central | 2 | Potter | 91273 | SR 49 Trib Cowanesque Bridge | 49 | A11 | Bridge Replacement | PE | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 506708 | 0 | 0 | 0 | 0 | 506708
North Central | 2 | Potter | 91273 | SR 49 Trib Cowanesque Bridge | 49 | A11 | Bridge Replacement | ROW | 185 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 65239 | 0 | 0 | 0 | 65239
North Central | 2 | Potter | 91273 | SR 49 Trib Cowanesque Bridge | 49 | A11 | Bridge Replacement | UTL | 185 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 65239 | 0 | 0 | 0 | 65239
North Central | 2 | Potter | 91273 | SR 49 Trib Cowanesque Bridge | 49 | A11 | Bridge Replacement | CON | 581 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1007937 | 0 | 0 | 1007937
North Central | 2 | Potter | 91602 | SR 449 W. Br Genesee R | 449 | A09 | Bridge Replacement | PE | 185 | 2032-06-17 |  | 0 | 0 | 0 | 0 | 0 | 260955 | 0 | 0 | 0 | 260955
North Central | 2 | Potter | 91602 | SR 449 W. Br Genesee R | 449 | A09 | Bridge Replacement | CON | NHPP | 2032-06-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 703465 | 0 | 703465
North Central | 2 | Potter | 91602 | SR 449 W. Br Genesee R | 449 | A09 | Bridge Replacement | CON | STP | 2032-06-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 400000
North Central | 2 | Potter | 93331 | Camp Run BOX | 3001 | A05 | Bridge Replacement | PE | 581 | 2026-10-01 |  | 288270 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318270
North Central | 2 | Potter | 93331 | Camp Run BOX | 3001 | A05 | Bridge Replacement | ROW | 581 | 2026-10-01 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
North Central | 2 | Potter | 93331 | Camp Run BOX | 3001 | A05 | Bridge Replacement | UTL | 581 | 2026-10-01 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
North Central | 2 | Potter | 93331 | Camp Run BOX | 3001 | A05 | Bridge Replacement | CON | 581 | 2026-10-01 |  | 0 | 0 | 844132 | 0 | 0 | 0 | 0 | 0 | 0 | 844132
North Central | 2 | Potter | 96267 | Fessenden Road to Mina | 6 | 0 | Highway Restoration | CON | 581 | 2032-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750000 | 0 | 2750000
North Central | 2 | Potter | 100555 | SR 6, McKean Co to Fishing Crk | 6 | 626 | Highway Restoration | CON | NHPP | 2022-04-28 | 2022-04-28 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500
North Central | 2 | Potter | 100569 | Nine Mile to Leek Hollow | 6 | 0 | Highway Restoration | CON | 581 | 2028-08-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750000 | 2750000
North Central | 2 | Potter | 101040 | PA 49 to New York | 449 | 0 | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750000 | 2750000
North Central | 2 | Potter | 101049 | US 6 to PA 49 | 449 | 0 | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750000 | 2750000
North Central | 2 | Potter | 101891 | US 6 Resurfacing | 6 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 4500000 | 5750000
North Central | 2 | Potter | 108859 | Group 2-25-ST6 | 1010 | ST6 | Highway Restoration | CON | 581 | 2025-03-27 | 2025-03-27 | 277740 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577740
North Central | 2 | Potter | 113160 | SR 49 over Allegheny River | 49 | A16 | Bridge Replacement | PE | 581 | 2031-02-01 |  | 0 | 0 | 0 | 0 | 506708 | 0 | 0 | 0 | 0 | 506708
North Central | 2 | Potter | 113160 | SR 49 over Allegheny River | 49 | A16 | Bridge Replacement | ROW | 185 | 2031-02-01 |  | 0 | 0 | 0 | 0 | 0 | 65239 | 0 | 0 | 0 | 65239
North Central | 2 | Potter | 113160 | SR 49 over Allegheny River | 49 | A16 | Bridge Replacement | UTL | 185 | 2031-02-01 |  | 0 | 0 | 0 | 0 | 0 | 65239 | 0 | 0 | 0 | 65239
North Central | 2 | Potter | 113160 | SR 49 over Allegheny River | 49 | A16 | Bridge Replacement | CON | 185 | 2031-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1243288 | 0 | 0 | 1243288
North Central | 2 | Potter | 114317 | 2024 NC Bridge Preservation | 244 | P43 | Bridge Restoration | CON | BRIP | 2024-05-09 | 2024-05-09 | 150000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
North Central | 2 | Potter | 116890 | 2027 North Central Bridge Preservation | 44 | P52 | Bridge Restoration | PE | BOF | 2027-04-29 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Potter | 116890 | 2027 North Central Bridge Preservation | 44 | P52 | Bridge Restoration | CON | BOF | 2027-04-29 |  | 0 | 0 | 276257 | 0 | 0 | 0 | 0 | 0 | 0 | 276257
North Central | 2 | Potter | 116890 | 2027 North Central Bridge Preservation | 44 | P52 | Bridge Restoration | CON | BRIP | 2027-04-29 |  | 0 | 0 | 376999 | 1262360 | 0 | 0 | 0 | 0 | 0 | 1639359
North Central | 2 | Potter | 117122 | East Fork Sinnamahoning Creek BOX | 3001 | A07 | Bridge Replacement | CON | 581 | 2023-10-05 | 2023-10-05 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Potter | 118631 | T-304 Big Moores Run Bridge (II) | 7211 | LOC | Bridge Replacement | PE | BOF | 2026-02-12 | 2026-02-12 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Potter | 118631 | T-304 Big Moores Run Bridge (II) | 7211 | LOC | Bridge Replacement | FD | BOF | 2026-02-12 | 2026-02-12 | 270000 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289000
North Central | 2 | Potter | 118631 | T-304 Big Moores Run Bridge (II) | 7211 | LOC | Bridge Replacement | ROW | BOF | 2026-02-12 | 2026-02-12 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Potter | 118631 | T-304 Big Moores Run Bridge (II) | 7211 | LOC | Bridge Replacement | CON | RURAL | 2026-02-12 | 2026-02-12 | 0 | 1386628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1386628
North Central | 2 | Potter | 118631 | T-304 Big Moores Run Bridge (II) | 7211 | LOC | Bridge Replacement | CON | 185 | 2026-02-12 | 2026-02-12 | 0 | 346657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346657
North Central | 2 | Potter | 118672 | SR 872 Roadway and Slope Stability | 872 | 628 | Highway Restoration | PE | 581 | 2026-12-10 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
North Central | 2 | Potter | 118672 | SR 872 Roadway and Slope Stability | 872 | 628 | Highway Restoration | FD | STP | 2026-12-10 |  | 0 | 328000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328000
North Central | 2 | Potter | 118672 | SR 872 Roadway and Slope Stability | 872 | 628 | Highway Restoration | FD | 581 | 2026-12-10 |  | 0 | 82000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82000
North Central | 2 | Potter | 118672 | SR 872 Roadway and Slope Stability | 872 | 628 | Highway Restoration | CON | STP | 2026-12-10 |  | 0 | 0 | 2100000 | 0 | 0 | 1790844 | 261518 | 0 | 0 | 4152362
North Central | 2 | Potter | 118672 | SR 872 Roadway and Slope Stability | 872 | 628 | Highway Restoration | CON | 581 | 2026-12-10 |  | 0 | 0 | 411000 | 0 | 0 | 0 | 0 | 0 | 0 | 411000
North Central | 2 | Potter | 119915 | SR 6 over Allegheny River | 6 | A05 | Bridge Replacement | PE | NHPP | 2027-09-16 |  | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000
North Central | 2 | Potter | 119915 | SR 6 over Allegheny River | 6 | A05 | Bridge Replacement | PE | 581 | 2027-09-16 |  | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
North Central | 2 | Potter | 119915 | SR 6 over Allegheny River | 6 | A05 | Bridge Replacement | FD | BRIP | 2027-09-16 |  | 0 | 371527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371527
North Central | 2 | Potter | 119915 | SR 6 over Allegheny River | 6 | A05 | Bridge Replacement | ROW | BRIP | 2027-09-16 |  | 0 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43709
North Central | 2 | Potter | 119915 | SR 6 over Allegheny River | 6 | A05 | Bridge Replacement | UTL | BRIP | 2027-09-16 |  | 0 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43709
North Central | 2 | Potter | 119915 | SR 6 over Allegheny River | 6 | A05 | Bridge Replacement | CON | BRIP | 2027-09-16 |  | 0 | 0 | 1918262 | 670408 | 0 | 0 | 0 | 0 | 0 | 2588670
North Central | 2 | Potter | 119922 | SR 144 over Cross Fork Creek | 144 | P74 | Bridge Replacement | CON | BRIP | 2028-01-13 |  | 0 | 128000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128000
North Central | 2 | Potter | 119925 | SR 1011 over Genesee River | 1011 | A06 | Bridge Replacement | PE | BOF | 2028-06-30 |  | 0 | 258945 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 308945
North Central | 2 | Potter | 119925 | SR 1011 over Genesee River | 1011 | A06 | Bridge Replacement | PE | STP | 2028-06-30 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
North Central | 2 | Potter | 119925 | SR 1011 over Genesee River | 1011 | A06 | Bridge Replacement | FD | BOF | 2028-06-30 |  | 0 | 0 | 337652 | 0 | 0 | 0 | 0 | 0 | 0 | 337652
North Central | 2 | Potter | 119925 | SR 1011 over Genesee River | 1011 | A06 | Bridge Replacement | ROW | BOF | 2028-06-30 |  | 0 | 0 | 56276 | 0 | 0 | 0 | 0 | 0 | 0 | 56276
North Central | 2 | Potter | 119925 | SR 1011 over Genesee River | 1011 | A06 | Bridge Replacement | UTL | BOF | 2028-06-30 |  | 0 | 0 | 56276 | 0 | 0 | 0 | 0 | 0 | 0 | 56276
North Central | 2 | Potter | 119925 | SR 1011 over Genesee River | 1011 | A06 | Bridge Replacement | CON | BOF | 2028-06-30 |  | 0 | 0 | 0 | 1999748 | 290000 | 0 | 0 | 0 | 0 | 2289748
North Central | 2 | Potter | 122367 | T399 Gross Hollow Rd Br II |  | BR | General Maintenance | CON | 185 |  |  | 143060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143060
North Central | 2 | Potter | 122367 | T399 Gross Hollow Rd Br II |  | BR | General Maintenance | CON | LOC |  |  | 35765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35765
North Central | 10 | Elk | 119292 | Knox Kane Ped Hwy Crossing Safety | 4009 | SAF | General Maintenance | CON | HSIP | 2025-04-17 | 2025-04-17 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
North Central | 10 | Elk | 119292 | Knox Kane Ped Hwy Crossing Safety | 4009 | SAF | General Maintenance | CON | SXF | 2025-04-17 | 2025-04-17 | 322435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322435
North Central | 10 | Jefferson | 25938 | T-353 Mill Run Bridge | 7205 | 550 | Bridge Replacement | CON | BOF | 2025-10-09 | 2025-10-09 | 0 | 863420 | 636580 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
North Central | 10 | Jefferson | 25944 | T-396 Seldom Seen Bridge | 7217 | 550 | Bridge Removal | ROW | 581 | 2026-10-01 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
North Central | 10 | Jefferson | 25944 | T-396 Seldom Seen Bridge | 7217 | 550 | Bridge Removal | CON | 581 | 2026-10-01 |  | 0 | 291740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291740
North Central | 10 | Jefferson | 25962 | T-346 Hominy Bridge | 7201 | 0 | Bridge Replacement | PE | BOF | 2029-03-01 |  | 253400 | 196600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
North Central | 10 | Jefferson | 25962 | T-346 Hominy Bridge | 7201 | 0 | Bridge Replacement | FD | BOF | 2029-03-01 |  | 0 | 0 | 0 | 0 | 139120 | 210880 | 0 | 0 | 0 | 350000
North Central | 10 | Jefferson | 25962 | T-346 Hominy Bridge | 7201 | 0 | Bridge Replacement | ROW | BOF | 2029-03-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
North Central | 10 | Jefferson | 25962 | T-346 Hominy Bridge | 7201 | 0 | Bridge Replacement | UTL | BOF | 2029-03-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
North Central | 10 | Jefferson | 25962 | T-346 Hominy Bridge | 7201 | 0 | Bridge Replacement | CON | BOF | 2029-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 178429 | 663491 | 757580 | 1599500
North Central | 10 | Jefferson | 26020 | Valier Bridge Rehabilitation | 3013 |  | Bridge Restoration | PE | BOF | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 240000
North Central | 10 | Jefferson | 26020 | Valier Bridge Rehabilitation | 3013 |  | Bridge Restoration | PE | 185 | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000
North Central | 10 | Jefferson | 26020 | Valier Bridge Rehabilitation | 3013 |  | Bridge Restoration | FD | BOF | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 240000
North Central | 10 | Jefferson | 26020 | Valier Bridge Rehabilitation | 3013 |  | Bridge Restoration | FD | 185 | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000
North Central | 10 | Jefferson | 26020 | Valier Bridge Rehabilitation | 3013 |  | Bridge Restoration | ROW | BOF | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 24000
North Central | 10 | Jefferson | 26020 | Valier Bridge Rehabilitation | 3013 |  | Bridge Restoration | ROW | 185 | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000
North Central | 10 | Jefferson | 26020 | Valier Bridge Rehabilitation | 3013 |  | Bridge Restoration | UTL | BOF | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000
North Central | 10 | Jefferson | 26020 | Valier Bridge Rehabilitation | 3013 |  | Bridge Restoration | UTL | 185 | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000
North Central | 10 | Jefferson | 26020 | Valier Bridge Rehabilitation | 3013 |  | Bridge Restoration | CON | BOF | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1449736 | 1449736
North Central | 10 | Jefferson | 26020 | Valier Bridge Rehabilitation | 3013 |  | Bridge Restoration | CON | 185 | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399140 | 399140
North Central | 10 | Jefferson | 26160 | Sprankle Mills Bridge #1 | 3014 | 554 | Bridge Replacement | PE | BOF | 2029-01-11 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
North Central | 10 | Jefferson | 68204 | Jeff Hwy/Bridge Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 376367 | 754420 | 708180 | 0 | 0 | 0 | 0 | 0 | 1838967
North Central | 10 | Jefferson | 68204 | Jeff Hwy/Bridge Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 427042 | 1175000 | 625545 | 201370 | 0 | 0 | 0 | 0 | 2428957
North Central | 10 | Jefferson | 68204 | Jeff Hwy/Bridge Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 44098 | 316200 | 316200 | 316200 | 316200 | 316200 | 316200 | 1265000 | 3206298
North Central | 10 | Jefferson | 68204 | Jeff Hwy/Bridge Line Item |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 121000 | 236000 | 27000 | 0 | 0 | 0 | 0 | 384000
North Central | 10 | Jefferson | 68204 | Jeff Hwy/Bridge Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 9545 | 686640 | 0 | 493000 | 0 | 0 | 0 | 0 | 1189185
North Central | 10 | Jefferson | 68204 | Jeff Hwy/Bridge Line Item |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 282224 | 629398 | 0 | 0 | 0 | 0 | 0 | 911622
North Central | 10 | Jefferson | 68204 | Jeff Hwy/Bridge Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 61368 | 1844353 | 1403272 | 123300 | 0 | 308600 | 91400 | 0 | 3832293
North Central | 10 | Jefferson | 78134 | Near Cool Spring Bridge | 3031 | 551 | Bridge Replacement | UTL | BOF | 2027-10-21 |  | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
North Central | 10 | Jefferson | 78134 | Near Cool Spring Bridge | 3031 | 551 | Bridge Replacement | CON | BOF | 2027-10-21 |  | 0 | 0 | 0 | 682820 | 823111 | 0 | 0 | 0 | 0 | 1505931
North Central | 10 | Jefferson | 83322 | SR 2011 ov Trib Canoe Creek | 2011 | 551 | Bridge Replacement | CON | STP | 2023-10-19 | 2023-10-19 | 2682 | 2728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5410
North Central | 10 | Jefferson | 83329 | Near Roseville Bridge | 3003 | 000 | Bridge Replacement | PE | BOF | 2031-10-09 |  | 0 | 0 | 0 | 0 | 178769 | 221231 | 0 | 0 | 0 | 400000
North Central | 10 | Jefferson | 83329 | Near Roseville Bridge | 3003 | 000 | Bridge Replacement | FD | BOF | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 202238 | 221231 | 0 | 0 | 423469
North Central | 10 | Jefferson | 83329 | Near Roseville Bridge | 3003 | 000 | Bridge Replacement | ROW | BOF | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
North Central | 10 | Jefferson | 83329 | Near Roseville Bridge | 3003 | 000 | Bridge Replacement | UTL | BOF | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
North Central | 10 | Jefferson | 83329 | Near Roseville Bridge | 3003 | 000 | Bridge Replacement | CON | BOF | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 350340 | 600160 | 0 | 950500
North Central | 10 | Jefferson | 84828 | US 322 over Campbell Run | 322 | 555 | Bridge Replacement | UTL | STP | 2026-08-27 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
North Central | 10 | Jefferson | 84828 | US 322 over Campbell Run | 322 | 555 | Bridge Replacement | CON | STP | 2026-08-27 |  | 0 | 1503120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1503120
North Central | 10 | Jefferson | 84828 | US 322 over Campbell Run | 322 | 555 | Bridge Replacement | CON | 185 | 2026-08-27 |  | 0 | 213302 | 162478 | 0 | 770860 | 157140 | 320860 | 0 | 0 | 1624640
North Central | 10 | Jefferson | 98132 | T-385 Dobson Road Bridge | 7216 | 550 | Bridge Removal | ROW | 581 | 2026-10-01 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
North Central | 10 | Jefferson | 98132 | T-385 Dobson Road Bridge | 7216 | 550 | Bridge Removal | CON | 581 | 2026-10-01 |  | 0 | 229252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229252
North Central | 10 | Jefferson | 98137 | T-517 Kramer Road Bridge | 7210 | 550 | Bridge Restoration | CON | RURAL | 2025-12-11 | 2025-12-11 | 0 | 992000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992000
North Central | 10 | Jefferson | 99464 | SR 3033 over Redbank Cr. | 3033 | 0 | Bridge Preservation - Federal | PE | BOF | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 375000
North Central | 10 | Jefferson | 99464 | SR 3033 over Redbank Cr. | 3033 | 0 | Bridge Preservation - Federal | FD | BOF | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 375000
North Central | 10 | Jefferson | 99464 | SR 3033 over Redbank Cr. | 3033 | 0 | Bridge Preservation - Federal | ROW | BOF | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
North Central | 10 | Jefferson | 99464 | SR 3033 over Redbank Cr. | 3033 | 0 | Bridge Preservation - Federal | UTL | BOF | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
North Central | 10 | Jefferson | 99464 | SR 3033 over Redbank Cr. | 3033 | 0 | Bridge Preservation - Federal | CON | BOF | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791684 | 1791684
North Central | 10 | Jefferson | 99498 | SR 3003 over Redbank Cr. | 3003 | 553 | Bridge Replacement | CON | BOF | 2023-10-19 | 2023-10-19 | 637600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637600
North Central | 10 | Jefferson | 99498 | SR 3003 over Redbank Cr. | 3003 | 553 | Bridge Replacement | CON | BRIP | 2023-10-19 | 2023-10-19 | 869597 | 565558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1435155
North Central | 10 | Jefferson | 99498 | SR 3003 over Redbank Cr. | 3003 | 553 | Bridge Replacement | CON | SXF | 2023-10-19 | 2023-10-19 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
North Central | 10 | Jefferson | 100188 | SR 28 West Hill Rd North Resurfacing | 28 | 512 | Preventive Maintenance | CON | 581 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4517920 | 4517920
North Central | 10 | Jefferson | 100212 | PA 28 Clarion Line-Snyder | 28 | 501 | Highway Restoration | CON | NHPP | 2025-01-30 | 2025-01-30 | 308003 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583003
North Central | 10 | Jefferson | 100212 | PA 28 Clarion Line-Snyder | 28 | 501 | Highway Restoration | CON | STP | 2025-01-30 | 2025-01-30 | 2867118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2867118
North Central | 10 | Jefferson | 100226 | US 322 Segmnt 300-PA950 | 322 | 509 | Preventive Maintenance | CON | 581 | 2024-01-25 | 2024-01-25 | 2197950 | 2247997 | 0 | 0 | 600335 | 0 | 0 | 0 | 0 | 5046282
North Central | 10 | Jefferson | 100273 | PA 536 Armstrong Co-PA 36 | 536 | 0 | Preventive Maintenance | CON | STP | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1628000 | 1628000
North Central | 10 | Jefferson | 100273 | PA 536 Armstrong Co-PA 36 | 536 | 0 | Preventive Maintenance | CON | 581 | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407000 | 407000
North Central | 10 | Jefferson | 100274 | SR 3021 PA 119 to PA 36 | 3021 | 0 | Preventive Maintenance | CON | 581 | 2031-09-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 0 | 1750000
North Central | 10 | Jefferson | 102752 | US 219/PA 28 Brockway Intersection | 219 | 571 | Safety Improvement | UTL | 581 | 2023-09-14 | 2023-09-28 | 13332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13332
North Central | 10 | Jefferson | 105576 | Rikers Road Crossing | 2009 | 0 | Rail Highway Grade Crossing | CON | RRX | 2029-01-11 |  | 0 | 0 | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 225000
North Central | 10 | Jefferson | 109387 | South Park Street Crossing |  |  | Rail Highway Grade Crossing | CON | RRX | 2029-01-11 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
North Central | 10 | Jefferson | 109571 | Ugly Run Bridge | 2001 | 550 | Bridge Replacement | CON | 185 | 2024-10-10 | 2024-10-10 | 341832 | 390258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732090
North Central | 10 | Jefferson | 109782 | Soldier Bridge | 2031 | 550 | Bridge Replacement | FD | 185 | 2026-07-30 |  | 310000 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344000
North Central | 10 | Jefferson | 109782 | Soldier Bridge | 2031 | 550 | Bridge Replacement | ROW | 185 | 2026-07-30 |  | 36100 | 13900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
North Central | 10 | Jefferson | 109782 | Soldier Bridge | 2031 | 550 | Bridge Replacement | UTL | 185 | 2026-07-30 |  | 92840 | 48160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141000
North Central | 10 | Jefferson | 109782 | Soldier Bridge | 2031 | 550 | Bridge Replacement | CON | PRTCT | 2026-07-30 |  | 0 | 1220800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220800
North Central | 10 | Jefferson | 109836 | Local Retro Line Item |  |  | Reserve Line Item | CON | 185 |  |  | 118760 | 144680 | 114000 | 118900 | 118000 | 118000 | 118000 | 118000 | 472000 | 1440340
North Central | 10 | Jefferson | 110141 | SR 410 Resurfacing | 410 | 501 | 409 Expanded Maintenance | CON | STP | 2027-03-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422710 | 2747616 | 3170326
North Central | 10 | Jefferson | 110767 | Mitchell Avenue Crossing |  |  | Rail Highway Grade Crossing | CON | RRX | 2029-01-11 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
North Central | 10 | Jefferson | 111830 | Jefferson Co. Department Force Bridge Maintenance | 119 | 0 | Bridge Restoration | CON | 185 | 2026-10-01 |  | 206000 | 212200 | 218600 | 281400 | 225200 | 225200 | 225200 | 225200 | 900800 | 2719800
North Central | 10 | Jefferson | 113711 | Mary A. Wilson Bridge | 36 | 0 | Bridge Restoration | PE | 185 | 2031-10-09 |  | 0 | 0 | 0 | 0 | 37940 | 362060 | 0 | 0 | 0 | 400000
North Central | 10 | Jefferson | 113711 | Mary A. Wilson Bridge | 36 | 0 | Bridge Restoration | FD | 185 | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 289600 | 60400 | 0 | 0 | 350000
North Central | 10 | Jefferson | 113711 | Mary A. Wilson Bridge | 36 | 0 | Bridge Restoration | CON | 185 | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200940 | 819060 | 1020000
North Central | 10 | Jefferson | 114845 | PA 28 Coder Station North Resurfacing | 28 | 0 | Preventive Maintenance | CON | NHPP | 2027-02-11 |  | 0 | 0 | 0 | 0 | 539000 | 566000 | 414387 | 0 | 0 | 1519387
North Central | 10 | Jefferson | 114845 | PA 28 Coder Station North Resurfacing | 28 | 0 | Preventive Maintenance | CON | 581 | 2027-02-11 |  | 0 | 0 | 0 | 0 | 134750 | 366093 | 103597 | 0 | 0 | 604440
North Central | 10 | Jefferson | 115187 | SR 28 Hazen North Resurfacing | 28 | 504 | Preventive Maintenance | FD | 581 | 2027-02-11 |  | 0 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145000
North Central | 10 | Jefferson | 115187 | SR 28 Hazen North Resurfacing | 28 | 504 | Preventive Maintenance | CON | 581 | 2027-02-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1656081 | 1500782 | 3156863
North Central | 10 | Jefferson | 115191 | SR 28 Warsaw to West Hill Rd Resurfacing | 28 | 505 | Preventive Maintenance | CON | STP | 2029-01-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824290 | 812384 | 1636674
North Central | 10 | Jefferson | 115191 | SR 28 Warsaw to West Hill Rd Resurfacing | 28 | 505 | Preventive Maintenance | CON | 581 | 2029-01-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206072 | 203096 | 409168
North Central | 10 | Jefferson | 115192 | US 219 Elk County South Resurfacing | 219 | 0 | Preventive Maintenance | CON | 581 | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1572153 | 1621847 | 0 | 3194000
North Central | 10 | Jefferson | 115193 | US 119 Big Run Resurfacing | 119 | 503 | Preventive Maintenance | CON | 581 | 2029-01-25 |  | 0 | 0 | 0 | 1460600 | 745679 | 1236971 | 59250 | 0 | 0 | 3502500
North Central | 10 | Jefferson | 115194 | US 119 Stump Creek North Resurfacing | 119 | 0 | Preventive Maintenance | CON | 581 | 2029-01-25 |  | 0 | 0 | 0 | 623128 | 1882936 | 1882936 | 0 | 0 | 0 | 4389000
North Central | 10 | Jefferson | 115195 | SR 36 Punxsy North Resurfacing | 36 | 0 | Preventive Maintenance | CON | 581 | 2031-10-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3167750 | 3167750
North Central | 10 | Jefferson | 115196 | PA 36 Cool Spring South Resurfacing | 36 | 511 | Preventive Maintenance | CON | STP | 2029-02-08 |  | 0 | 0 | 0 | 296350 | 800410 | 1697000 | 477400 | 0 | 0 | 3271160
North Central | 10 | Jefferson | 116508 | Stump Creek Bridge #3 | 2012 | 550 | Bridge Replacement | CON | 185 | 2024-08-08 | 2024-08-08 | 26468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26468
North Central | 10 | Jefferson | 117204 | SR 36/SR 949 Crash Avoidance System | 36 | 572 | Safety Improvement | CON | CRP | 2023-12-07 | 2023-12-07 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
North Central | 10 | Jefferson | 117206 | Jefferson Bridge Latex Group | 28 | 556 | Bridge Preservation - Federal | PE | STP | 2028-02-03 |  | 25000 | 56328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81328
North Central | 10 | Jefferson | 117206 | Jefferson Bridge Latex Group | 28 | 556 | Bridge Preservation - Federal | FD | STP | 2028-02-03 |  | 0 | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194000
North Central | 10 | Jefferson | 117206 | Jefferson Bridge Latex Group | 28 | 556 | Bridge Preservation - Federal | UTL | STP | 2028-02-03 |  | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
North Central | 10 | Jefferson | 117206 | Jefferson Bridge Latex Group | 28 | 556 | Bridge Preservation - Federal | CON | STP | 2028-02-03 |  | 0 | 0 | 411360 | 900650 | 403590 | 0 | 0 | 0 | 0 | 1715600
North Central | 10 | Jefferson | 117335 | Jefferson Epoxy Group | 119 | 0 | Bridge Preservation - State Funded | CON | 185 | 2032-07-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1225000 | 1225000
North Central | 10 | Jefferson | 117353 | Sandy Valley Bridge #1 | 950 | 0 | Bridge Restoration | PE | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 400000
North Central | 10 | Jefferson | 117353 | Sandy Valley Bridge #1 | 950 | 0 | Bridge Restoration | FD | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
North Central | 10 | Jefferson | 117353 | Sandy Valley Bridge #1 | 950 | 0 | Bridge Restoration | CON | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 865000 | 865000
North Central | 10 | Jefferson | 117356 | Pancoast Bridge | 950 | 0 | Bridge Restoration | PE | 185 | 2033-05-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 117940 | 320860 | 0 | 438800
North Central | 10 | Jefferson | 117356 | Pancoast Bridge | 950 | 0 | Bridge Restoration | FD | 185 | 2033-05-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193600 | 256400 | 450000
North Central | 10 | Jefferson | 117356 | Pancoast Bridge | 950 | 0 | Bridge Restoration | CON | STP | 2033-05-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000 | 850000
North Central | 10 | Jefferson | 117357 | South of Allens Mills Bridge | 1830 | 551 | Bridge Restoration | PE | 581 | 2033-02-17 |  | 278718 | 121282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
North Central | 10 | Jefferson | 117357 | South of Allens Mills Bridge | 1830 | 551 | Bridge Restoration | FD | 185 | 2033-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168600 | 168600
North Central | 10 | Jefferson | 117358 | Prescott Bridge #5 | 2007 | 0 | Bridge Restoration | PE | BRIP | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
North Central | 10 | Jefferson | 117358 | Prescott Bridge #5 | 2007 | 0 | Bridge Restoration | FD | BRIP | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000
North Central | 10 | Jefferson | 117358 | Prescott Bridge #5 | 2007 | 0 | Bridge Restoration | FD | 185 | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 80000
North Central | 10 | Jefferson | 117358 | Prescott Bridge #5 | 2007 | 0 | Bridge Restoration | CON | BRIP | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000
North Central | 10 | Jefferson | 117358 | Prescott Bridge #5 | 2007 | 0 | Bridge Restoration | CON | 185 | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
North Central | 10 | Jefferson | 117359 | Bells Mills Bridge Rehabilitation | 2019 | 0 | Bridge Restoration | PE | BRIP | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000
North Central | 10 | Jefferson | 117359 | Bells Mills Bridge Rehabilitation | 2019 | 0 | Bridge Restoration | FD | BRIP | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000
North Central | 10 | Jefferson | 117359 | Bells Mills Bridge Rehabilitation | 2019 | 0 | Bridge Restoration | CON | BRIP | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1206785 | 1206785
North Central | 10 | Jefferson | 117360 | Mill Run Bridge #1 Rehabilitation | 4004 | 0 | Bridge Restoration | PE | STP | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 365800 | 0 | 0 | 365800
North Central | 10 | Jefferson | 117360 | Mill Run Bridge #1 Rehabilitation | 4004 | 0 | Bridge Restoration | FD | STP | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 450000
North Central | 10 | Jefferson | 117360 | Mill Run Bridge #1 Rehabilitation | 4004 | 0 | Bridge Restoration | CON | STP | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000
North Central | 10 | Jefferson | 117363 | Reynoldsville Bridge #1 Tickle Belly | 322 | 556 | Bridge Replacement | PE | BRIP | 2027-03-25 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
North Central | 10 | Jefferson | 117363 | Reynoldsville Bridge #1 Tickle Belly | 322 | 556 | Bridge Replacement | FD | BRIP | 2027-03-25 |  | 400000 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545000
North Central | 10 | Jefferson | 117363 | Reynoldsville Bridge #1 Tickle Belly | 322 | 556 | Bridge Replacement | ROW | BRIP | 2027-03-25 |  | 112600 | 37400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
North Central | 10 | Jefferson | 117363 | Reynoldsville Bridge #1 Tickle Belly | 322 | 556 | Bridge Replacement | UTL | BRIP | 2027-03-25 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
North Central | 10 | Jefferson | 117363 | Reynoldsville Bridge #1 Tickle Belly | 322 | 556 | Bridge Replacement | CON | BRIP | 2027-03-25 |  | 0 | 0 | 0 | 549455 | 973630 | 1175000 | 1175000 | 775000 | 8215 | 4656300
North Central | 10 | Jefferson | 117373 | Glen-Gery Group Bridges | 28 | 555 | Bridge Replacement | FD | STP | 2026-07-16 |  | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
North Central | 10 | Jefferson | 117373 | Glen-Gery Group Bridges | 28 | 555 | Bridge Replacement | ROW | STP | 2026-07-16 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
North Central | 10 | Jefferson | 117373 | Glen-Gery Group Bridges | 28 | 555 | Bridge Replacement | UTL | STP | 2026-07-16 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
North Central | 10 | Jefferson | 117373 | Glen-Gery Group Bridges | 28 | 555 | Bridge Replacement | CON | NHPP | 2026-07-16 |  | 0 | 433000 | 506000 | 330000 | 0 | 0 | 0 | 0 | 0 | 1269000
North Central | 10 | Jefferson | 117373 | Glen-Gery Group Bridges | 28 | 555 | Bridge Replacement | CON | STP | 2026-07-16 |  | 0 | 0 | 600000 | 500000 | 0 | 0 | 0 | 0 | 0 | 1100000
North Central | 10 | Jefferson | 117715 | PA 28 Moore Road Intersection (28 Study) | 28 | 0 | Safety Improvement | PE | NHPP | 2034-08-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
North Central | 10 | Jefferson | 117718 | Timblin Boro Bridge #1 | 3004 | 0 | Bridge Replacement | PE | BOF | 2031-10-09 |  | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000
North Central | 10 | Jefferson | 117718 | Timblin Boro Bridge #1 | 3004 | 0 | Bridge Replacement | FD | BOF | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 300000
North Central | 10 | Jefferson | 117718 | Timblin Boro Bridge #1 | 3004 | 0 | Bridge Replacement | ROW | BOF | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 10000
North Central | 10 | Jefferson | 117718 | Timblin Boro Bridge #1 | 3004 | 0 | Bridge Replacement | UTL | BOF | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 15000
North Central | 10 | Jefferson | 117718 | Timblin Boro Bridge #1 | 3004 | 0 | Bridge Replacement | CON | BOF | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 231651 | 641000 | 127349 | 0 | 1000000
North Central | 10 | Jefferson | 117786 | Elk Run Bridge #1 Latex | 119 | 0 | Bridge Preservation - Federal | FD | NHPP | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 151613 | 148387 | 0 | 300000
North Central | 10 | Jefferson | 117786 | Elk Run Bridge #1 Latex | 119 | 0 | Bridge Preservation - Federal | CON | NHPP | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417613 | 332387 | 750000
North Central | 10 | Jefferson | 117787 | Christopher E. Loudon Bridge Latex | 219 | 0 | Bridge Preservation - Federal | FD | NHPP | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390807 | 390807
North Central | 10 | Jefferson | 117787 | Christopher E. Loudon Bridge Latex | 219 | 0 | Bridge Preservation - Federal | CON | NHPP | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000
North Central | 10 | Jefferson | 117789 | Purple Heart Memorial Bridge Latex | 322 | 0 | Bridge Preservation - Federal | CON | STP | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 853800 | 0 | 0 | 853800
North Central | 10 | Jefferson | 117805 | SFC Scott R. Smith Bridge Epoxy | 119 | 0 | Bridge Preservation - Federal | CON | NHPP | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390806 | 390806
North Central | 10 | Jefferson | 119694 | D10/Jefferson Carbon Reduction Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 260000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 1068000 | 3197000
North Central | 10 | Jefferson | 119733 | US 322 - PA 28 to Segmnt 300 | 322 | 511 | Preventive Maintenance | CON | 581 | 2033-10-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2790040 | 2790040
North Central | 10 | Jefferson | 120375 | (RAID) - South 5th Street Extension Project |  |  | New Alignment | PE | APL | 2027-05-27 |  | 164302 | 147505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311807
North Central | 10 | Jefferson | 120375 | (RAID) - South 5th Street Extension Project |  |  | New Alignment | ROW | APL | 2027-05-27 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
North Central | 10 | Jefferson | 120375 | (RAID) - South 5th Street Extension Project |  |  | New Alignment | CON | APL | 2027-05-27 |  | 0 | 0 | 1446314 | 0 | 0 | 0 | 0 | 0 | 0 | 1446314
North Central | 10 | Jefferson | 120989 | US-219 - I-80 to Clearfield County Line | 219 | 572 | Preventive Maintenance | CON | 581 | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1349412 | 1349412
North Central | 10 | Jefferson | 121429 | Dinsmore Avenue Reconstruction MTF |  | 590 | MultiModal | CON | 411 |  |  | 428009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428009
North Central | 10 | Jefferson | 121429 | Dinsmore Avenue Reconstruction MTF |  | 590 | MultiModal | CON | LOC |  |  | 183433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183433
North Central | 10 | Jefferson | 122010 | District 10 HFST North Central 2026 | 36 | ST2 | Safety Improvement | CON | HSIP | 2025-11-06 | 2025-11-06 | 352098 | 272102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624200
North Central | 10 | Jefferson | 122143 | Runaway Run Bridge | 28 | 557 | Bridge Replacement | FD | NHPP | 2026-07-16 |  | 308200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308200
North Central | 10 | Jefferson | 122143 | Runaway Run Bridge | 28 | 557 | Bridge Replacement | FD | STP | 2026-07-16 |  | 66800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66800
North Central | 10 | Jefferson | 122143 | Runaway Run Bridge | 28 | 557 | Bridge Replacement | ROW | NHPP | 2026-07-16 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
North Central | 10 | Jefferson | 122143 | Runaway Run Bridge | 28 | 557 | Bridge Replacement | UTL | NHPP | 2026-07-16 |  | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
North Central | 10 | Jefferson | 122143 | Runaway Run Bridge | 28 | 557 | Bridge Replacement | CON | 581 | 2026-07-16 |  | 0 | 227353 | 1330647 | 0 | 0 | 0 | 0 | 0 | 0 | 1558000
North Central | 10 | Jefferson | 122179 | Sprankle Mills Bridge #2 - DFB | 3014 | 553 | Bridge Replacement | PE | 185 | 2026-10-22 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
North Central | 10 | Jefferson | 122179 | Sprankle Mills Bridge #2 - DFB | 3014 | 553 | Bridge Replacement | ROW | 185 | 2026-10-22 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
North Central | 10 | Jefferson | 122179 | Sprankle Mills Bridge #2 - DFB | 3014 | 553 | Bridge Replacement | UTL | 185 | 2026-10-22 |  | 0 | 119500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119500
North Central | 10 | Jefferson | 122179 | Sprankle Mills Bridge #2 - DFB | 3014 | 553 | Bridge Replacement | CON | 185 | 2026-10-22 |  | 0 | 0 | 376698 | 123302 | 0 | 0 | 0 | 0 | 0 | 500000
North Central | 10 | Jefferson | 122473 | T-508 Big Run Road MTF |  | 591 | MultiModal | CON | 411 |  |  | 924000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 924000
North Central | 10 | Jefferson | 122473 | T-508 Big Run Road MTF |  | 591 | MultiModal | CON | LOC |  |  | 277200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277200
Northern Tier | 3 | Bradford | 5088 | SR 4034 over Roaring Run | 4034 | 005 | Bridge Replacement | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 125000
Northern Tier | 3 | Bradford | 5088 | SR 4034 over Roaring Run | 4034 | 005 | Bridge Replacement | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 5088 | SR 4034 over Roaring Run | 4034 | 005 | Bridge Replacement | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
Northern Tier | 3 | Bradford | 5088 | SR 4034 over Roaring Run | 4034 | 005 | Bridge Replacement | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 5088 | SR 4034 over Roaring Run | 4034 | 005 | Bridge Replacement | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
Northern Tier | 3 | Bradford | 5112 | Redington Ave ov W Branch of Sugar Creek |  | LBR | Bridge Replacement | FD | BOF | 2026-09-17 |  | 120000 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 5112 | Redington Ave ov W Branch of Sugar Creek |  | LBR | Bridge Replacement | ROW | BOF | 2026-09-17 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Northern Tier | 3 | Bradford | 5112 | Redington Ave ov W Branch of Sugar Creek |  | LBR | Bridge Replacement | UTL | BOF | 2026-09-17 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 5112 | Redington Ave ov W Branch of Sugar Creek |  | LBR | Bridge Replacement | CON | BOF | 2026-09-17 |  | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
Northern Tier | 3 | Bradford | 5129 | S Railroad St ov Fk Sugar Crk |  | LBR | Bridge Replacement | FD | BOF | 2026-09-17 |  | 218000 | 57000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275000
Northern Tier | 3 | Bradford | 5129 | S Railroad St ov Fk Sugar Crk |  | LBR | Bridge Replacement | ROW | BOF | 2026-09-17 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 5129 | S Railroad St ov Fk Sugar Crk |  | LBR | Bridge Replacement | UTL | BOF | 2026-09-17 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Bradford | 5129 | S Railroad St ov Fk Sugar Crk |  | LBR | Bridge Replacement | CON | BOF | 2026-09-17 |  | 0 | 387000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387000
Northern Tier | 3 | Bradford | 5129 | S Railroad St ov Fk Sugar Crk |  | LBR | Bridge Replacement | CON | BRIP | 2026-09-17 |  | 0 | 863000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863000
Northern Tier | 3 | Bradford | 5137 | SR 4027 over South Creek | 4027 | 009 | Bridge Restoration | PE | 185 | 2028-08-24 |  | 0 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 5137 | SR 4027 over South Creek | 4027 | 009 | Bridge Restoration | FD | 185 | 2028-08-24 |  | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Bradford | 5137 | SR 4027 over South Creek | 4027 | 009 | Bridge Restoration | ROW | 185 | 2028-08-24 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Bradford | 5137 | SR 4027 over South Creek | 4027 | 009 | Bridge Restoration | UTL | 185 | 2028-08-24 |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Bradford | 5137 | SR 4027 over South Creek | 4027 | 009 | Bridge Restoration | CON | BOF | 2028-08-24 |  | 0 | 0 | 0 | 0 | 412000 | 250000 | 255000 | 0 | 0 | 917000
Northern Tier | 3 | Bradford | 5138 | SR 4027 over Buck Creek | 4027 | 007 | Bridge Replacement | PE | 185 | 2028-08-24 |  | 100000 | 183000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 308000
Northern Tier | 3 | Bradford | 5138 | SR 4027 over Buck Creek | 4027 | 007 | Bridge Replacement | FD | 185 | 2028-08-24 |  | 0 | 0 | 0 | 125000 | 25000 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Bradford | 5138 | SR 4027 over Buck Creek | 4027 | 007 | Bridge Replacement | ROW | 185 | 2028-08-24 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Bradford | 5138 | SR 4027 over Buck Creek | 4027 | 007 | Bridge Replacement | UTL | 185 | 2028-08-24 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 5138 | SR 4027 over Buck Creek | 4027 | 007 | Bridge Replacement | CON | BOF | 2028-08-24 |  | 0 | 0 | 0 | 0 | 500000 | 200000 | 300000 | 0 | 0 | 1000000
Northern Tier | 3 | Bradford | 5166 | T-821 over Beckwith Creek |  | LBR | Bridge Removal | FD | BOF | 2027-01-01 |  | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Northern Tier | 3 | Bradford | 5166 | T-821 over Beckwith Creek |  | LBR | Bridge Removal | FD | 183 | 2027-01-01 |  | 0 | 0 | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 11250
Northern Tier | 3 | Bradford | 5166 | T-821 over Beckwith Creek |  | LBR | Bridge Removal | FD | LOC | 2027-01-01 |  | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
Northern Tier | 3 | Bradford | 5166 | T-821 over Beckwith Creek |  | LBR | Bridge Removal | UTL | BOF | 2027-01-01 |  | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
Northern Tier | 3 | Bradford | 5166 | T-821 over Beckwith Creek |  | LBR | Bridge Removal | UTL | 183 | 2027-01-01 |  | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
Northern Tier | 3 | Bradford | 5166 | T-821 over Beckwith Creek |  | LBR | Bridge Removal | CON | BOF | 2027-01-01 |  | 0 | 0 | 560000 | 560000 | 0 | 0 | 0 | 0 | 0 | 1120000
Northern Tier | 3 | Bradford | 5166 | T-821 over Beckwith Creek |  | LBR | Bridge Removal | CON | 183 | 2027-01-01 |  | 0 | 0 | 105000 | 105000 | 0 | 0 | 0 | 0 | 0 | 210000
Northern Tier | 3 | Bradford | 5191 | SR 3008 over Tributary to Towanda Creek | 3008 | 018 | Bridge Replacement | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 125000
Northern Tier | 3 | Bradford | 5191 | SR 3008 over Tributary to Towanda Creek | 3008 | 018 | Bridge Replacement | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
Northern Tier | 3 | Bradford | 5191 | SR 3008 over Tributary to Towanda Creek | 3008 | 018 | Bridge Replacement | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000
Northern Tier | 3 | Bradford | 5191 | SR 3008 over Tributary to Towanda Creek | 3008 | 018 | Bridge Replacement | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 5191 | SR 3008 over Tributary to Towanda Creek | 3008 | 018 | Bridge Replacement | CON | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000
Northern Tier | 3 | Bradford | 5192 | SR 4001 over Tributary to Browns Creek | 4001 | 045 | Bridge Replacement | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 5192 | SR 4001 over Tributary to Browns Creek | 4001 | 045 | Bridge Replacement | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 150000
Northern Tier | 3 | Bradford | 5192 | SR 4001 over Tributary to Browns Creek | 4001 | 045 | Bridge Replacement | ROW | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000
Northern Tier | 3 | Bradford | 5192 | SR 4001 over Tributary to Browns Creek | 4001 | 045 | Bridge Replacement | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Bradford | 5192 | SR 4001 over Tributary to Browns Creek | 4001 | 045 | Bridge Replacement | CON | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495000 | 200000 | 695000
Northern Tier | 3 | Bradford | 5204 | SR 3029 over Gulf Creek | 3029 | 009 | Bridge Replacement | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 75000
Northern Tier | 3 | Bradford | 5204 | SR 3029 over Gulf Creek | 3029 | 009 | Bridge Replacement | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 5204 | SR 3029 over Gulf Creek | 3029 | 009 | Bridge Replacement | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 18000
Northern Tier | 3 | Bradford | 5204 | SR 3029 over Gulf Creek | 3029 | 009 | Bridge Replacement | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 5204 | SR 3029 over Gulf Creek | 3029 | 009 | Bridge Replacement | CON | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 289000 | 0 | 0 | 289000
Northern Tier | 3 | Bradford | 5223 | Prospect Street over Fall Brook |  | LBR | Bridge Restoration | FD | BOF | 2027-01-01 |  | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Northern Tier | 3 | Bradford | 5223 | Prospect Street over Fall Brook |  | LBR | Bridge Restoration | ROW | BOF | 2027-01-01 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Northern Tier | 3 | Bradford | 5223 | Prospect Street over Fall Brook |  | LBR | Bridge Restoration | UTL | BOF | 2027-01-01 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Northern Tier | 3 | Bradford | 5223 | Prospect Street over Fall Brook |  | LBR | Bridge Restoration | CON | BOF | 2027-01-01 |  | 0 | 0 | 250000 | 300000 | 0 | 0 | 0 | 0 | 0 | 550000
Northern Tier | 3 | Bradford | 5289 | SR 1049 over Trib Pendleton Crk | 1049 | 027 | Bridge Restoration | PE | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 25000 | 150000
Northern Tier | 3 | Bradford | 5289 | SR 1049 over Trib Pendleton Crk | 1049 | 027 | Bridge Restoration | FD | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
Northern Tier | 3 | Bradford | 5289 | SR 1049 over Trib Pendleton Crk | 1049 | 027 | Bridge Restoration | ROW | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Bradford | 5289 | SR 1049 over Trib Pendleton Crk | 1049 | 027 | Bridge Restoration | UTL | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 5289 | SR 1049 over Trib Pendleton Crk | 1049 | 027 | Bridge Restoration | CON | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Northern Tier | 3 | Bradford | 68018 | NTIER TIP reserve D3 |  | 000 | Reserve Line Item | CON | BOF |  |  | 0 | 182910 | 2000 | 1482000 | 1356000 | 1320000 | 1500000 | 1500000 | 6000000 | 13342910
Northern Tier | 3 | Bradford | 68018 | NTIER TIP reserve D3 |  | 000 | Reserve Line Item | CON | BRIP |  |  | 0 | 31072 | 1813678 | 5032000 | 6572000 | 6572000 | 6572000 | 6572000 | 26289000 | 59453750
Northern Tier | 3 | Bradford | 68018 | NTIER TIP reserve D3 |  | 000 | Reserve Line Item | CON | CRP |  |  | 0 | 88960 | 778000 | 778000 | 778000 | 778000 | 778000 | 778000 | 3113000 | 7869960
Northern Tier | 3 | Bradford | 68018 | NTIER TIP reserve D3 |  | 000 | Reserve Line Item | CON | HSIP |  |  | 0 | 22500 | 0 | 800 | 871800 | 871800 | 871800 | 871800 | 3487800 | 6998300
Northern Tier | 3 | Bradford | 68018 | NTIER TIP reserve D3 |  | 000 | Reserve Line Item | CON | NHPP |  |  | 0 | 576299 | 953678 | 500000 | 200000 | 0 | 0 | 0 | 0 | 2229977
Northern Tier | 3 | Bradford | 68018 | NTIER TIP reserve D3 |  | 000 | Reserve Line Item | CON | STP |  |  | 0 | 1463591 | 1161607 | 0 | 0 | 0 | 0 | 0 | 0 | 2625198
Northern Tier | 3 | Bradford | 68018 | NTIER TIP reserve D3 |  | 000 | Reserve Line Item | CON | 185 |  |  | 0 | 267000 | 50000 | 0 | 141750 | 183000 | 0 | 0 | 0 | 641750
Northern Tier | 3 | Bradford | 68018 | NTIER TIP reserve D3 |  | 000 | Reserve Line Item | CON | 581 |  |  | 0 | 832000 | 1336964 | 0 | 0 | 500000 | 250000 | 250000 | 0 | 3168964
Northern Tier | 3 | Bradford | 74024 | SR3002 over Ladds Creek | 3002 | 016 | Bridge Replacement | PE | BRIP | 2026-02-12 | 2026-02-12 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Northern Tier | 3 | Bradford | 74024 | SR3002 over Ladds Creek | 3002 | 016 | Bridge Replacement | FD | 185 | 2026-02-12 | 2026-02-12 | 100000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000
Northern Tier | 3 | Bradford | 74024 | SR3002 over Ladds Creek | 3002 | 016 | Bridge Replacement | ROW | 185 | 2026-02-12 | 2026-02-12 | 19000 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57000
Northern Tier | 3 | Bradford | 74024 | SR3002 over Ladds Creek | 3002 | 016 | Bridge Replacement | CON | 185 | 2026-02-12 | 2026-02-12 | 220000 | 700000 | 580000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Northern Tier | 3 | Bradford | 76157 | SR4022 ov Chemung River | 4022 | 017 | Bridge Restoration | FD | 185 | 2025-09-11 | 2025-09-11 | 494000 | 46000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000
Northern Tier | 3 | Bradford | 76157 | SR4022 ov Chemung River | 4022 | 017 | Bridge Restoration | CON | BRIP | 2025-09-11 | 2025-09-11 | 3823600 | 2606928 | 113322 | 0 | 0 | 0 | 0 | 0 | 0 | 6543850
Northern Tier | 3 | Bradford | 76157 | SR4022 ov Chemung River | 4022 | 017 | Bridge Restoration | CON | STP | 2025-09-11 | 2025-09-11 | 4653416 | 701354 | 93124 | 0 | 0 | 0 | 0 | 0 | 0 | 5447894
Northern Tier | 3 | Bradford | 78772 | SR1049ovPrinceHollowRun | 1049 | 024 | Bridge Restoration | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Northern Tier | 3 | Bradford | 78772 | SR1049ovPrinceHollowRun | 1049 | 024 | Bridge Restoration | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
Northern Tier | 3 | Bradford | 78772 | SR1049ovPrinceHollowRun | 1049 | 024 | Bridge Restoration | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 78772 | SR1049ovPrinceHollowRun | 1049 | 024 | Bridge Restoration | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 78772 | SR1049ovPrinceHollowRun | 1049 | 024 | Bridge Restoration | CON | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120000 | 1120000
Northern Tier | 3 | Bradford | 78773 | SR 1055 Over Parks Creek | 1055 | 014 | Bridge Restoration | CON | 185 | 2024-10-01 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Northern Tier | 3 | Bradford | 78776 | SR2007 ov Sugar Run | 2007 | 021 | Bridge Restoration | CON | 185 |  |  | 30000 | 30000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Northern Tier | 3 | Bradford | 78786 | SR3001ovTowandaCreek | 3001 | 017 | Bridge Restoration | PE | 185 | 2027-10-08 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Bradford | 78786 | SR3001ovTowandaCreek | 3001 | 017 | Bridge Restoration | FD | 185 | 2027-10-08 |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Northern Tier | 3 | Bradford | 78786 | SR3001ovTowandaCreek | 3001 | 017 | Bridge Restoration | CON | 185 | 2027-10-08 |  | 0 | 0 | 30000 | 30000 | 15000 | 0 | 0 | 0 | 0 | 75000
Northern Tier | 3 | Bradford | 78797 | SR 4016 Over South Creek | 4016 | 007 | Bridge Restoration | FD | 185 | 2026-10-08 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 3 | Bradford | 78797 | SR 4016 Over South Creek | 4016 | 007 | Bridge Restoration | CON | 185 | 2026-10-08 |  | 0 | 30000 | 30000 | 15000 | 0 | 0 | 0 | 0 | 0 | 75000
Northern Tier | 3 | Bradford | 88915 | SR 14 over Tannery Creek | 14 | 077 | General Maintenance | FD | STP | 2026-12-10 |  | 254000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354000
Northern Tier | 3 | Bradford | 88915 | SR 14 over Tannery Creek | 14 | 077 | General Maintenance | UTL | 185 | 2026-12-10 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 88915 | SR 14 over Tannery Creek | 14 | 077 | General Maintenance | CON | STP | 2026-12-10 |  | 0 | 0 | 1000000 | 500000 | 0 | 0 | 0 | 0 | 0 | 1500000
Northern Tier | 3 | Bradford | 89906 | SR 4015 ov Tb Sugar Creek | 4015 | 005 | Bridge Replacement | FD | 185 | 2026-11-05 |  | 5000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 89906 | SR 4015 ov Tb Sugar Creek | 4015 | 005 | Bridge Replacement | ROW | 185 | 2026-11-05 |  | 20000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
Northern Tier | 3 | Bradford | 89906 | SR 4015 ov Tb Sugar Creek | 4015 | 005 | Bridge Replacement | CON | 185 | 2026-11-05 |  | 100000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Northern Tier | 3 | Bradford | 97598 | PA 14 over South Creek | 14 | 117 | Bridge Restoration | FD | BRIP | 2026-07-30 |  | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
Northern Tier | 3 | Bradford | 97598 | PA 14 over South Creek | 14 | 117 | Bridge Restoration | ROW | BRIP | 2026-07-30 |  | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
Northern Tier | 3 | Bradford | 97598 | PA 14 over South Creek | 14 | 117 | Bridge Restoration | UTL | STP | 2026-07-30 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Bradford | 97598 | PA 14 over South Creek | 14 | 117 | Bridge Restoration | CON | STP | 2026-07-30 |  | 0 | 0 | 1614000 | 1585000 | 1801000 | 0 | 0 | 0 | 0 | 5000000
Northern Tier | 3 | Bradford | 97599 | PA 14 ov Tb to Towanda Cr | 14 | 123 | Bridge Restoration | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 250000
Northern Tier | 3 | Bradford | 97599 | PA 14 ov Tb to Towanda Cr | 14 | 123 | Bridge Restoration | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 150000 | 200000
Northern Tier | 3 | Bradford | 97599 | PA 14 ov Tb to Towanda Cr | 14 | 123 | Bridge Restoration | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Bradford | 97599 | PA 14 ov Tb to Towanda Cr | 14 | 123 | Bridge Restoration | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 97599 | PA 14 ov Tb to Towanda Cr | 14 | 123 | Bridge Restoration | CON | STP | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Northern Tier | 3 | Bradford | 97621 | SR 187 ov Tr Wysox Cr | 187 | 076 | Bridge Replacement | FD | 185 | 2026-12-10 |  | 0 | 231500 | 218500 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
Northern Tier | 3 | Bradford | 97621 | SR 187 ov Tr Wysox Cr | 187 | 076 | Bridge Replacement | ROW | 185 | 2026-12-10 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Northern Tier | 3 | Bradford | 97621 | SR 187 ov Tr Wysox Cr | 187 | 076 | Bridge Replacement | UTL | 185 | 2026-12-10 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 97621 | SR 187 ov Tr Wysox Cr | 187 | 076 | Bridge Replacement | CON | 185 | 2026-12-10 |  | 0 | 0 | 1100000 | 400000 | 0 | 0 | 0 | 0 | 0 | 1500000
Northern Tier | 3 | Bradford | 97628 | SR 187 over Parks Creek | 187 | 075 | Bridge Replacement | FD | BRIP | 2028-09-01 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Bradford | 97628 | SR 187 over Parks Creek | 187 | 075 | Bridge Replacement | ROW | BRIP | 2028-09-01 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Bradford | 97628 | SR 187 over Parks Creek | 187 | 075 | Bridge Replacement | UTL | STP | 2028-09-01 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 97628 | SR 187 over Parks Creek | 187 | 075 | Bridge Replacement | CON | STP | 2028-09-01 |  | 0 | 0 | 0 | 0 | 363000 | 1914000 | 723000 | 0 | 0 | 3000000
Northern Tier | 3 | Bradford | 97637 | SR1056 ov Satterlee Cr | 1056 | 013 | Bridge Restoration | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northern Tier | 3 | Bradford | 97637 | SR1056 ov Satterlee Cr | 1056 | 013 | Bridge Restoration | CON | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 900000
Northern Tier | 3 | Bradford | 97640 | SR 1067 over Tributary to Satterlee Creek | 1067 | 002 | Bridge Restoration | PE | 185 | 2031-01-16 |  | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 97640 | SR 1067 over Tributary to Satterlee Creek | 1067 | 002 | Bridge Restoration | FD | 185 | 2031-01-16 |  | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 150000
Northern Tier | 3 | Bradford | 97640 | SR 1067 over Tributary to Satterlee Creek | 1067 | 002 | Bridge Restoration | ROW | 185 | 2031-01-16 |  | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Bradford | 97640 | SR 1067 over Tributary to Satterlee Creek | 1067 | 002 | Bridge Restoration | UTL | 185 | 2031-01-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 97640 | SR 1067 over Tributary to Satterlee Creek | 1067 | 002 | Bridge Restoration | CON | BOF | 2031-01-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 245000 | 0 | 0 | 245000
Northern Tier | 3 | Bradford | 97640 | SR 1067 over Tributary to Satterlee Creek | 1067 | 002 | Bridge Restoration | CON | STP | 2031-01-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000
Northern Tier | 3 | Bradford | 97644 | SR4027 ov Bucks Cr | 4027 | 008 | Bridge Replacement | PE | 185 | 2028-08-24 |  | 100000 | 184000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 309000
Northern Tier | 3 | Bradford | 97644 | SR4027 ov Bucks Cr | 4027 | 008 | Bridge Replacement | FD | 185 | 2028-08-24 |  | 0 | 0 | 0 | 125000 | 25000 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Bradford | 97644 | SR4027 ov Bucks Cr | 4027 | 008 | Bridge Replacement | ROW | 185 | 2028-08-24 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Bradford | 97644 | SR4027 ov Bucks Cr | 4027 | 008 | Bridge Replacement | UTL | 185 | 2028-08-24 |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Bradford | 97644 | SR4027 ov Bucks Cr | 4027 | 008 | Bridge Replacement | CON | BOF | 2028-08-24 |  | 0 | 0 | 0 | 0 | 350000 | 169000 | 231000 | 0 | 0 | 750000
Northern Tier | 3 | Bradford | 98518 | SR367 ov Tuscarora Creek | 367 | 008 | Bridge Replacement | CON | BOF | 2038-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2435000 | 2435000
Northern Tier | 3 | Bradford | 98534 | SR1021 ov Rummerfield Crk | 1021 | 004 | Bridge Replacement | PE | 185 | 2027-01-14 |  | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
Northern Tier | 3 | Bradford | 98534 | SR1021 ov Rummerfield Crk | 1021 | 004 | Bridge Replacement | FD | BOF | 2027-01-14 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Bradford | 98534 | SR1021 ov Rummerfield Crk | 1021 | 004 | Bridge Replacement | ROW | BOF | 2027-01-14 |  | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000
Northern Tier | 3 | Bradford | 98534 | SR1021 ov Rummerfield Crk | 1021 | 004 | Bridge Replacement | UTL | BOF | 2027-01-14 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 98534 | SR1021 ov Rummerfield Crk | 1021 | 004 | Bridge Replacement | CON | BOF | 2027-01-14 |  | 0 | 0 | 300000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 1800000
Northern Tier | 3 | Bradford | 98910 | SR1058ovTbSatterleeCrk | 1058 | 008 | Bridge Replacement | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 125000
Northern Tier | 3 | Bradford | 98910 | SR1058ovTbSatterleeCrk | 1058 | 008 | Bridge Replacement | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 98910 | SR1058ovTbSatterleeCrk | 1058 | 008 | Bridge Replacement | ROW | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 98910 | SR1058ovTbSatterleeCrk | 1058 | 008 | Bridge Replacement | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Bradford | 98910 | SR1058ovTbSatterleeCrk | 1058 | 008 | Bridge Replacement | CON | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 500000
Northern Tier | 3 | Bradford | 98937 | SR187ovTbNBrSusquehanna | 187 | 102 | Bridge Replacement | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Northern Tier | 3 | Bradford | 98937 | SR187ovTbNBrSusquehanna | 187 | 102 | Bridge Replacement | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Bradford | 98937 | SR187ovTbNBrSusquehanna | 187 | 102 | Bridge Replacement | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Bradford | 98937 | SR187ovTbNBrSusquehanna | 187 | 102 | Bridge Replacement | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 98937 | SR187ovTbNBrSusquehanna | 187 | 102 | Bridge Replacement | CON | STP | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000
Northern Tier | 3 | Bradford | 98967 | SR414ovTbTowandaCreek | 414 | 080 | Bridge Restoration | CON | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
Northern Tier | 3 | Bradford | 98970 | SR414 ov Gulf Brook | 414 | 081 | Bridge Restoration | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 98970 | SR414 ov Gulf Brook | 414 | 081 | Bridge Restoration | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 150000
Northern Tier | 3 | Bradford | 98970 | SR414 ov Gulf Brook | 414 | 081 | Bridge Restoration | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 98970 | SR414 ov Gulf Brook | 414 | 081 | Bridge Restoration | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
Northern Tier | 3 | Bradford | 98970 | SR414 ov Gulf Brook | 414 | 081 | Bridge Restoration | CON | STP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 620000 | 900000
Northern Tier | 3 | Bradford | 98975 | SR 1022 (North Rome Road) to Seven Hills Drive | 187 | 071 | 409 Expanded Maintenance | PE | 581 | 2026-12-10 |  | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000
Northern Tier | 3 | Bradford | 99018 | Potter Rd to NY Line | 1043 | 019 | 409 Expanded Maintenance | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 99018 | Potter Rd to NY Line | 1043 | 019 | 409 Expanded Maintenance | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1700000 | 800000 | 600000 | 0 | 3100000
Northern Tier | 3 | Bradford | 99063 | SR 1049 over Russel Run | 1049 | 023 | Bridge Restoration | PE | 185 | 2031-10-01 |  | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
Northern Tier | 3 | Bradford | 99063 | SR 1049 over Russel Run | 1049 | 023 | Bridge Restoration | FD | 185 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Bradford | 99063 | SR 1049 over Russel Run | 1049 | 023 | Bridge Restoration | ROW | 185 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 99063 | SR 1049 over Russel Run | 1049 | 023 | Bridge Restoration | UTL | 185 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 99063 | SR 1049 over Russel Run | 1049 | 023 | Bridge Restoration | CON | 185 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 99069 | SR2010ovSugarRun | 2010 | 022 | Bridge Restoration | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 250000
Northern Tier | 3 | Bradford | 99069 | SR2010ovSugarRun | 2010 | 022 | Bridge Restoration | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Bradford | 99069 | SR2010ovSugarRun | 2010 | 022 | Bridge Restoration | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Bradford | 99069 | SR2010ovSugarRun | 2010 | 022 | Bridge Restoration | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 99069 | SR2010ovSugarRun | 2010 | 022 | Bridge Restoration | CON | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northern Tier | 3 | Bradford | 99072 | SR3017ovNBrTowandaCrk | 3017 | 005 | Bridge Replacement | ROW | BOF | 2025-01-09 | 2025-01-09 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Bradford | 99072 | SR3017ovNBrTowandaCrk | 3017 | 005 | Bridge Replacement | CON | BOF | 2025-01-09 | 2025-01-09 | 1435000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1435000
Northern Tier | 3 | Bradford | 99076 | SR4022 ov US220 | 4022 | 016 | Bridge Restoration | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 99076 | SR4022 ov US220 | 4022 | 016 | Bridge Restoration | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 150000
Northern Tier | 3 | Bradford | 99076 | SR4022 ov US220 | 4022 | 016 | Bridge Restoration | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 99076 | SR4022 ov US220 | 4022 | 016 | Bridge Restoration | CON | STP | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 822873 | 877127 | 0 | 1700000
Northern Tier | 3 | Bradford | 99142 | SR1043ovSpauldingsCreek | 1043 | 018 | Bridge Restoration | PE | 185 | 2028-10-01 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Bradford | 99142 | SR1043ovSpauldingsCreek | 1043 | 018 | Bridge Restoration | FD | 185 | 2028-10-01 |  | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 3 | Bradford | 99142 | SR1043ovSpauldingsCreek | 1043 | 018 | Bridge Restoration | CON | 185 | 2028-10-01 |  | 0 | 0 | 0 | 30000 | 30000 | 40000 | 0 | 0 | 0 | 100000
Northern Tier | 3 | Bradford | 99158 | SR220 Major Guide Signs | 220 | 267 | Safety Improvement | CON | 581 | 2027-04-08 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 3 | Bradford | 99278 | SR187 over Wysox Creek | 187 | 074 | Bridge Replacement | FD | BRIP | 2026-12-10 |  | 0 | 355000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355000
Northern Tier | 3 | Bradford | 99278 | SR187 over Wysox Creek | 187 | 074 | Bridge Replacement | ROW | BRIP | 2026-12-10 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Bradford | 99278 | SR187 over Wysox Creek | 187 | 074 | Bridge Replacement | UTL | BRIP | 2026-12-10 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 99278 | SR187 over Wysox Creek | 187 | 074 | Bridge Replacement | CON | BRIP | 2026-12-10 |  | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Northern Tier | 3 | Bradford | 99278 | SR187 over Wysox Creek | 187 | 074 | Bridge Replacement | CON | STP | 2026-12-10 |  | 0 | 0 | 0 | 1000000 | 1305000 | 0 | 0 | 0 | 0 | 2305000
Northern Tier | 3 | Bradford | 99358 | SR1040ovPrinceHollowRun | 1040 | 014 | Bridge Restoration | CON | 185 |  |  | 32000 | 110000 | 58000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Bradford | 99360 | SR1058ovSackett Run | 1058 | 007 | Bridge Replacement | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 125000
Northern Tier | 3 | Bradford | 99360 | SR1058ovSackett Run | 1058 | 007 | Bridge Replacement | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 99360 | SR1058ovSackett Run | 1058 | 007 | Bridge Replacement | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 99360 | SR1058ovSackett Run | 1058 | 007 | Bridge Replacement | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 99360 | SR1058ovSackett Run | 1058 | 007 | Bridge Replacement | CON | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 500000
Northern Tier | 3 | Bradford | 101052 | Old Mills Rd to State St | 6 | 133 | Highway Restoration | PE | NHPP | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000
Northern Tier | 3 | Bradford | 101052 | Old Mills Rd to State St | 6 | 133 | Highway Restoration | FD | NHPP | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000
Northern Tier | 3 | Bradford | 101052 | Old Mills Rd to State St | 6 | 133 | Highway Restoration | ROW | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
Northern Tier | 3 | Bradford | 101052 | Old Mills Rd to State St | 6 | 133 | Highway Restoration | UTL | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Northern Tier | 3 | Bradford | 101052 | Old Mills Rd to State St | 6 | 133 | Highway Restoration | CON | NHPP | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Northern Tier | 3 | Bradford | 101052 | Old Mills Rd to State St | 6 | 133 | Highway Restoration | CON | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000000 | 9000000
Northern Tier | 3 | Bradford | 101100 | SR6 & SR 187 Intersection | 6 | 131 | Safety Improvement | FD | NHPP | 2026-09-03 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Bradford | 101100 | SR6 & SR 187 Intersection | 6 | 131 | Safety Improvement | ROW | NHPP | 2026-09-03 |  | 689000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 689000
Northern Tier | 3 | Bradford | 101100 | SR6 & SR 187 Intersection | 6 | 131 | Safety Improvement | CON | NHPP | 2026-09-03 |  | 0 | 0 | 3342607 | 0 | 0 | 0 | 0 | 0 | 0 | 3342607
Northern Tier | 3 | Bradford | 101100 | SR6 & SR 187 Intersection | 6 | 131 | Safety Improvement | CON | STP | 2026-09-03 |  | 0 | 0 | 157393 | 0 | 0 | 0 | 0 | 0 | 0 | 157393
Northern Tier | 3 | Bradford | 101109 | SR199 to NY State Line SB | 220 | 199 | General Maintenance | CON | 581 | 2024-01-25 | 2024-01-25 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 103156 | Grover Rd to South Ave | 154 | 072 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Northern Tier | 3 | Bradford | 106267 | NTIER Cable Guide Rail Upgrade | 2023 | CGR | Safety Improvement | CON | HSIP | 2025-05-22 | 2025-05-22 | 0 | 141500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141500
Northern Tier | 3 | Bradford | 110161 | SR 1029 over Pond Hill Run | 1029 | 008 | Bridge Replacement | FD | BOF | 2025-10-23 | 2025-10-23 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000
Northern Tier | 3 | Bradford | 110161 | SR 1029 over Pond Hill Run | 1029 | 008 | Bridge Replacement | ROW | BOF | 2025-10-23 | 2025-10-23 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000
Northern Tier | 3 | Bradford | 110161 | SR 1029 over Pond Hill Run | 1029 | 008 | Bridge Replacement | UTL | BOF | 2025-10-23 | 2025-10-23 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Bradford | 110161 | SR 1029 over Pond Hill Run | 1029 | 008 | Bridge Replacement | UTL | BRIP | 2025-10-23 | 2025-10-23 | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000
Northern Tier | 3 | Bradford | 110161 | SR 1029 over Pond Hill Run | 1029 | 008 | Bridge Replacement | CON | BOF | 2025-10-23 | 2025-10-23 | 0 | 729000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 1479000
Northern Tier | 3 | Bradford | 110161 | SR 1029 over Pond Hill Run | 1029 | 008 | Bridge Replacement | CON | BRIP | 2025-10-23 | 2025-10-23 | 0 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000
Northern Tier | 3 | Bradford | 110238 | SR 1012 over Trib to Cold Creek | 1012 | 009 | Bridge Replacement | PE | 185 | 2026-01-08 | 2026-01-08 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000
Northern Tier | 3 | Bradford | 110238 | SR 1012 over Trib to Cold Creek | 1012 | 009 | Bridge Replacement | FD | 185 | 2026-01-08 | 2026-01-08 | 20000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 110238 | SR 1012 over Trib to Cold Creek | 1012 | 009 | Bridge Replacement | ROW | 185 | 2026-01-08 | 2026-01-08 | 15000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000
Northern Tier | 3 | Bradford | 110238 | SR 1012 over Trib to Cold Creek | 1012 | 009 | Bridge Replacement | CON | 185 | 2026-01-08 | 2026-01-08 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Northern Tier | 3 | Bradford | 110241 | SR 1029 over Bullards Creek | 1029 | 009 | Bridge Replacement | PE | 185 | 2029-09-01 |  | 0 | 0 | 125000 | 25000 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Bradford | 110241 | SR 1029 over Bullards Creek | 1029 | 009 | Bridge Replacement | FD | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 110241 | SR 1029 over Bullards Creek | 1029 | 009 | Bridge Replacement | ROW | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 110241 | SR 1029 over Bullards Creek | 1029 | 009 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 110241 | SR 1029 over Bullards Creek | 1029 | 009 | Bridge Replacement | CON | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 0 | 500000
Northern Tier | 3 | Bradford | 110242 | SR 2009 over Trib to Foster Branch | 2009 | 015 | Bridge Replacement | PE | 185 | 2036-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Bradford | 110242 | SR 2009 over Trib to Foster Branch | 2009 | 015 | Bridge Replacement | FD | 185 | 2036-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Northern Tier | 3 | Bradford | 110242 | SR 2009 over Trib to Foster Branch | 2009 | 015 | Bridge Replacement | ROW | 185 | 2036-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 110242 | SR 2009 over Trib to Foster Branch | 2009 | 015 | Bridge Replacement | UTL | 185 | 2036-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 110242 | SR 2009 over Trib to Foster Branch | 2009 | 015 | Bridge Replacement | CON | 185 | 2036-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Northern Tier | 3 | Bradford | 110253 | SR 3023 over Tributary to Sugar Creek | 3026 | 004 | Bridge Replacement | PE | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000
Northern Tier | 3 | Bradford | 110253 | SR 3023 over Tributary to Sugar Creek | 3026 | 004 | Bridge Replacement | FD | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 110253 | SR 3023 over Tributary to Sugar Creek | 3026 | 004 | Bridge Replacement | ROW | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 110253 | SR 3023 over Tributary to Sugar Creek | 3026 | 004 | Bridge Replacement | UTL | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
Northern Tier | 3 | Bradford | 110253 | SR 3023 over Tributary to Sugar Creek | 3026 | 004 | Bridge Replacement | CON | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Northern Tier | 3 | Bradford | 110254 | SR4014 over West Branch Tomjack Creek | 4014 | 025 | Bridge Replacement | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 125000
Northern Tier | 3 | Bradford | 110254 | SR4014 over West Branch Tomjack Creek | 4014 | 025 | Bridge Replacement | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
Northern Tier | 3 | Bradford | 110254 | SR4014 over West Branch Tomjack Creek | 4014 | 025 | Bridge Replacement | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 110254 | SR4014 over West Branch Tomjack Creek | 4014 | 025 | Bridge Replacement | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Bradford | 110254 | SR4014 over West Branch Tomjack Creek | 4014 | 025 | Bridge Replacement | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
Northern Tier | 3 | Bradford | 110264 | SR 1049 over Branch of Pendleton Creek | 1049 | 028 | Bridge Restoration | PE | 185 | 2031-10-01 |  | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 125000
Northern Tier | 3 | Bradford | 110264 | SR 1049 over Branch of Pendleton Creek | 1049 | 028 | Bridge Restoration | FD | 185 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Bradford | 110264 | SR 1049 over Branch of Pendleton Creek | 1049 | 028 | Bridge Restoration | ROW | 185 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 110264 | SR 1049 over Branch of Pendleton Creek | 1049 | 028 | Bridge Restoration | UTL | 185 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 110264 | SR 1049 over Branch of Pendleton Creek | 1049 | 028 | Bridge Restoration | CON | 185 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 250000
Northern Tier | 3 | Bradford | 110272 | SR 1043 over Tributary to Susquehanna River | 1043 | 020 | Bridge Replacement | PE | 185 | 2037-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
Northern Tier | 3 | Bradford | 110272 | SR 1043 over Tributary to Susquehanna River | 1043 | 020 | Bridge Replacement | CON | 185 | 2037-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
Northern Tier | 3 | Bradford | 110294 | SR 3011 over Pine Run | 3011 | 007 | Bridge Replacement | PE | 185 | 2036-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Northern Tier | 3 | Bradford | 110294 | SR 3011 over Pine Run | 3011 | 007 | Bridge Replacement | FD | 185 | 2036-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
Northern Tier | 3 | Bradford | 110294 | SR 3011 over Pine Run | 3011 | 007 | Bridge Replacement | ROW | 185 | 2036-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 110294 | SR 3011 over Pine Run | 3011 | 007 | Bridge Replacement | UTL | 185 | 2036-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 110294 | SR 3011 over Pine Run | 3011 | 007 | Bridge Replacement | CON | 185 | 2036-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Northern Tier | 3 | Bradford | 110295 | SR 4014 over Seeley Creek | 4014 | 026 | Bridge Replacement | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 125000
Northern Tier | 3 | Bradford | 110295 | SR 4014 over Seeley Creek | 4014 | 026 | Bridge Replacement | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
Northern Tier | 3 | Bradford | 110295 | SR 4014 over Seeley Creek | 4014 | 026 | Bridge Replacement | ROW | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 110295 | SR 4014 over Seeley Creek | 4014 | 026 | Bridge Replacement | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Bradford | 110295 | SR 4014 over Seeley Creek | 4014 | 026 | Bridge Replacement | CON | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 250000
Northern Tier | 3 | Bradford | 110394 | State Street to Susquehanna River | 6 | 145 | Highway Reconstruction | PE | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
Northern Tier | 3 | Bradford | 110394 | State Street to Susquehanna River | 6 | 145 | Highway Reconstruction | CON | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Northern Tier | 3 | Bradford | 110394 | State Street to Susquehanna River | 6 | 145 | Highway Reconstruction | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000000 | 7000000
Northern Tier | 3 | Bradford | 110406 | SR6 from Tracey Rd to Rummerfield Rd | 6 | 147 | Highway Restoration | CON | NHPP | 2030-01-01 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 3 | Bradford | 112732 | SR 4024 Slide Repair | 4024 | 023 | Highway Restoration | FD | 581 | 2026-01-29 | 2026-01-29 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 112732 | SR 4024 Slide Repair | 4024 | 023 | Highway Restoration | ROW | 581 | 2026-01-29 | 2026-01-29 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Bradford | 112732 | SR 4024 Slide Repair | 4024 | 023 | Highway Restoration | CON | 581 | 2026-01-29 | 2026-01-29 | 948775 | 724225 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 1788000
Northern Tier | 3 | Bradford | 113489 | SCM Monitoring NTIER |  |  | Stormwater Management | STUDY | 581 |  |  | 45000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 300000 | 870000
Northern Tier | 3 | Bradford | 114016 | West of SR 3011 to Wonder View Lane | 6 | 159 | Highway Restoration | CON | NHPP | 2029-01-01 |  | 0 | 0 | 809020 | 250000 | 0 | 0 | 0 | 0 | 0 | 1059020
Northern Tier | 3 | Bradford | 114016 | West of SR 3011 to Wonder View Lane | 6 | 159 | Highway Restoration | CON | STP | 2029-01-01 |  | 0 | 0 | 980 | 0 | 0 | 0 | 0 | 0 | 0 | 980
Northern Tier | 3 | Bradford | 114017 | Burlington to East of SR 3011 | 6 | 160 | Highway Restoration | PE | 581 | 2027-03-11 |  | 380000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430000
Northern Tier | 3 | Bradford | 114017 | Burlington to East of SR 3011 | 6 | 160 | Highway Restoration | FD | 581 | 2027-03-11 |  | 0 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000
Northern Tier | 3 | Bradford | 114017 | Burlington to East of SR 3011 | 6 | 160 | Highway Restoration | CON | 581 | 2027-03-11 |  | 0 | 0 | 1079000 | 1160000 | 900000 | 0 | 0 | 0 | 0 | 3139000
Northern Tier | 3 | Bradford | 114018 | Wyalusing Boro Line to Mile Post 290 | 6 | 161 | Highway Restoration | PE | 581 | 2028-01-01 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Bradford | 114018 | Wyalusing Boro Line to Mile Post 290 | 6 | 161 | Highway Restoration | CON | NHPP | 2028-01-01 |  | 0 | 0 | 0 | 1946980 | 664127 | 0 | 0 | 0 | 0 | 2611107
Northern Tier | 3 | Bradford | 114018 | Wyalusing Boro Line to Mile Post 290 | 6 | 161 | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 0 | 1445000 | 1550000 | 0 | 0 | 0 | 0 | 2995000
Northern Tier | 3 | Bradford | 114019 | SR 4019 to SR 3033 | 6 | 162 | Highway Restoration | PE | 581 | 2027-04-29 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Bradford | 114019 | SR 4019 to SR 3033 | 6 | 162 | Highway Restoration | CON | NHPP | 2027-04-29 |  | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 800000
Northern Tier | 3 | Bradford | 114019 | SR 4019 to SR 3033 | 6 | 162 | Highway Restoration | CON | 581 | 2027-04-29 |  | 0 | 0 | 300000 | 600000 | 0 | 0 | 0 | 0 | 0 | 900000
Northern Tier | 3 | Bradford | 114021 | Susquehanna River to Laning Creek | 6 | 164 | Highway Restoration | PE | 581 | 2028-07-01 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Bradford | 114098 | T-377 over Sugar Run |  | LBR | Bridge Replacement | PE | BOF | 2028-10-19 |  | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Northern Tier | 3 | Bradford | 114098 | T-377 over Sugar Run |  | LBR | Bridge Replacement | PE | 183 | 2028-10-19 |  | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
Northern Tier | 3 | Bradford | 114098 | T-377 over Sugar Run |  | LBR | Bridge Replacement | PE | LOC | 2028-10-19 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Bradford | 114098 | T-377 over Sugar Run |  | LBR | Bridge Replacement | CON | BOF | 2028-10-19 |  | 0 | 0 | 320000 | 320000 | 0 | 0 | 0 | 0 | 0 | 640000
Northern Tier | 3 | Bradford | 114098 | T-377 over Sugar Run |  | LBR | Bridge Replacement | CON | 183 | 2028-10-19 |  | 0 | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 120000
Northern Tier | 3 | Bradford | 114103 | SR 1015 over Branch of Cold Creek | 1015 | 013 | Bridge Replacement | PE | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Northern Tier | 3 | Bradford | 114103 | SR 1015 over Branch of Cold Creek | 1015 | 013 | Bridge Replacement | CON | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Northern Tier | 3 | Bradford | 114104 | SR 4010 over Sugar Creek | 4010 | 014 | Bridge Restoration | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 114104 | SR 4010 over Sugar Creek | 4010 | 014 | Bridge Restoration | FD | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Northern Tier | 3 | Bradford | 114104 | SR 4010 over Sugar Creek | 4010 | 014 | Bridge Restoration | ROW | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000
Northern Tier | 3 | Bradford | 114104 | SR 4010 over Sugar Creek | 4010 | 014 | Bridge Restoration | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
Northern Tier | 3 | Bradford | 114104 | SR 4010 over Sugar Creek | 4010 | 014 | Bridge Restoration | CON | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northern Tier | 3 | Bradford | 114168 | SR 1056 over Trib Wappasening Creek | 1056 | 014 | Bridge Replacement | FD | 185 | 2025-11-06 | 2025-11-06 | 38000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 114168 | SR 1056 over Trib Wappasening Creek | 1056 | 014 | Bridge Replacement | ROW | 185 | 2025-11-06 | 2025-11-06 | 39000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49000
Northern Tier | 3 | Bradford | 114168 | SR 1056 over Trib Wappasening Creek | 1056 | 014 | Bridge Replacement | CON | 185 | 2025-11-06 | 2025-11-06 | 400000 | 826000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1226000
Northern Tier | 3 | Bradford | 114169 | SR 4031 over Wolfe Creek | 4031 | 014 | Bridge Replacement | FD | 185 | 2024-12-12 | 2024-12-12 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Bradford | 114169 | SR 4031 over Wolfe Creek | 4031 | 014 | Bridge Replacement | CON | 185 | 2024-12-12 | 2024-12-12 | 277000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 527000
Northern Tier | 3 | Bradford | 114178 | SR154 over Beech Flats Creek | 154 | 090 | Bridge Replacement | FD | 185 | 2028-09-12 |  | 17625 | 241875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259500
Northern Tier | 3 | Bradford | 114178 | SR154 over Beech Flats Creek | 154 | 090 | Bridge Replacement | ROW | 185 | 2028-09-12 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Bradford | 114178 | SR154 over Beech Flats Creek | 154 | 090 | Bridge Replacement | UTL | 185 | 2028-09-12 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Bradford | 114178 | SR154 over Beech Flats Creek | 154 | 090 | Bridge Replacement | CON | 185 | 2028-09-12 |  | 0 | 0 | 0 | 0 | 1909787 | 1000000 | 190213 | 0 | 0 | 3100000
Northern Tier | 3 | Bradford | 114180 | SR1062 over Cayuta Crk and NS | 1062 | 005 | Bridge Replacement | PE | 185 | 2025-10-09 | 2025-10-09 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000
Northern Tier | 3 | Bradford | 114180 | SR1062 over Cayuta Crk and NS | 1062 | 005 | Bridge Replacement | FD | 185 | 2025-10-09 | 2025-10-09 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 114180 | SR1062 over Cayuta Crk and NS | 1062 | 005 | Bridge Replacement | CON | 185 | 2025-10-09 | 2025-10-09 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
Northern Tier | 3 | Bradford | 114183 | SR3008 over Tributary to Towanda Creek | 3008 | 016 | Bridge Replacement | FD | 185 | 2028-08-24 |  | 0 | 15000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Northern Tier | 3 | Bradford | 114183 | SR3008 over Tributary to Towanda Creek | 3008 | 016 | Bridge Replacement | ROW | 185 | 2028-08-24 |  | 11000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Bradford | 114183 | SR3008 over Tributary to Towanda Creek | 3008 | 016 | Bridge Replacement | UTL | 185 | 2028-08-24 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 114183 | SR3008 over Tributary to Towanda Creek | 3008 | 016 | Bridge Replacement | CON | 185 | 2028-08-24 |  | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 3 | Bradford | 114190 | SR 3008 over Trib Towanda Creek 2 | 3008 | 017 | Bridge Replacement | FD | 185 | 2027-09-16 |  | 0 | 10000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Northern Tier | 3 | Bradford | 114190 | SR 3008 over Trib Towanda Creek 2 | 3008 | 017 | Bridge Replacement | ROW | 185 | 2027-09-16 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Bradford | 114190 | SR 3008 over Trib Towanda Creek 2 | 3008 | 017 | Bridge Replacement | UTL | 185 | 2027-09-16 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 114190 | SR 3008 over Trib Towanda Creek 2 | 3008 | 017 | Bridge Replacement | CON | 185 | 2027-09-16 |  | 0 | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | 500000
Northern Tier | 3 | Bradford | 114192 | SR1040 over Branch Prince Hollow Run | 1040 | 008 | Bridge Replacement | PE | 185 | 2028-09-01 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Bradford | 114192 | SR1040 over Branch Prince Hollow Run | 1040 | 008 | Bridge Replacement | FD | 185 | 2028-09-01 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 114192 | SR1040 over Branch Prince Hollow Run | 1040 | 008 | Bridge Replacement | ROW | 185 | 2028-09-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 114192 | SR1040 over Branch Prince Hollow Run | 1040 | 008 | Bridge Replacement | UTL | 185 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 114192 | SR1040 over Branch Prince Hollow Run | 1040 | 008 | Bridge Replacement | CON | 185 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 500000
Northern Tier | 3 | Bradford | 114203 | SR 3020 over Overshot Brook | 3020 | 008 | Bridge Replacement | PE | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Northern Tier | 3 | Bradford | 114203 | SR 3020 over Overshot Brook | 3020 | 008 | Bridge Replacement | FD | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Northern Tier | 3 | Bradford | 114203 | SR 3020 over Overshot Brook | 3020 | 008 | Bridge Replacement | ROW | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 114203 | SR 3020 over Overshot Brook | 3020 | 008 | Bridge Replacement | UTL | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 114203 | SR 3020 over Overshot Brook | 3020 | 008 | Bridge Replacement | CON | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Northern Tier | 3 | Bradford | 114209 | SR 2014 over Durell Creek | 2014 | 108 | Bridge Replacement | PE | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 114209 | SR 2014 over Durell Creek | 2014 | 108 | Bridge Replacement | FD | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Bradford | 114209 | SR 2014 over Durell Creek | 2014 | 108 | Bridge Replacement | ROW | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 114209 | SR 2014 over Durell Creek | 2014 | 108 | Bridge Replacement | UTL | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 114209 | SR 2014 over Durell Creek | 2014 | 108 | Bridge Replacement | CON | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 900000
Northern Tier | 3 | Bradford | 115243 | Sullivan Co to Stevenson Hill Rd | 220 | 240 | Highway Restoration | PE | 581 | 2026-04-23 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 115243 | Sullivan Co to Stevenson Hill Rd | 220 | 240 | Highway Restoration | CON | STP | 2026-04-23 |  | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
Northern Tier | 3 | Bradford | 115282 | Bradford SR 1033 Slide Repair | 1033 | 006 | Highway Restoration | FD | 581 | 2027-01-01 |  | 0 | 150000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 115282 | Bradford SR 1033 Slide Repair | 1033 | 006 | Highway Restoration | ROW | 581 | 2027-01-01 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 115282 | Bradford SR 1033 Slide Repair | 1033 | 006 | Highway Restoration | UTL | 581 | 2027-01-01 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 115282 | Bradford SR 1033 Slide Repair | 1033 | 006 | Highway Restoration | CON | 581 | 2027-01-01 |  | 0 | 0 | 1515000 | 2097382 | 295000 | 0 | 0 | 0 | 0 | 3907382
Northern Tier | 3 | Bradford | 115287 | Bradford SR 3015 Slide Repair | 3015 | 014 | Highway Restoration | PE | 581 | 2028-01-01 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 3 | Bradford | 115287 | Bradford SR 3015 Slide Repair | 3015 | 014 | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Bradford | 115637 | Cty #13 Cons Road (T-348) over Towanda Creek |  | LBR | Bridge Restoration | FD | STP | 2026-02-12 | 2026-02-12 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Bradford | 115637 | Cty #13 Cons Road (T-348) over Towanda Creek |  | LBR | Bridge Restoration | ROW | STP | 2026-02-12 | 2026-02-12 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 115637 | Cty #13 Cons Road (T-348) over Towanda Creek |  | LBR | Bridge Restoration | CON | BOF | 2026-02-12 | 2026-02-12 | 0 | 97200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97200
Northern Tier | 3 | Bradford | 115637 | Cty #13 Cons Road (T-348) over Towanda Creek |  | LBR | Bridge Restoration | CON | STP | 2026-02-12 | 2026-02-12 | 0 | 1102800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1102800
Northern Tier | 3 | Bradford | 115979 | South Branch Village to SR 414 | 220 | 244 | Highway Restoration | CON | 581 | 2026-04-23 |  | 0 | 200000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 116504 | Mill Street over Sugar Creek |  | LBR | Bridge Removal | FD | BOF | 2027-01-01 |  | 0 | 61000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
Northern Tier | 3 | Bradford | 116504 | Mill Street over Sugar Creek |  | LBR | Bridge Removal | ROW | BOF | 2027-01-01 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Bradford | 116504 | Mill Street over Sugar Creek |  | LBR | Bridge Removal | UTL | BOF | 2027-01-01 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Northern Tier | 3 | Bradford | 116504 | Mill Street over Sugar Creek |  | LBR | Bridge Removal | CON | BOF | 2027-01-01 |  | 0 | 0 | 180000 | 210000 | 0 | 0 | 0 | 0 | 0 | 390000
Northern Tier | 3 | Bradford | 116524 | T-799 over Gaylord Creek |  | LBR | Bridge Restoration | FD | BOF | 2027-01-01 |  | 0 | 61000 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 3 | Bradford | 116524 | T-799 over Gaylord Creek |  | LBR | Bridge Restoration | ROW | BOF | 2027-01-01 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Northern Tier | 3 | Bradford | 116524 | T-799 over Gaylord Creek |  | LBR | Bridge Restoration | CON | BOF | 2027-01-01 |  | 0 | 0 | 130000 | 216000 | 0 | 0 | 0 | 0 | 0 | 346000
Northern Tier | 3 | Bradford | 116533 | T-321 over Murray Creek Road |  | LBR | Bridge Restoration | CON | BOF | 2025-01-09 | 2025-01-09 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
Northern Tier | 3 | Bradford | 116535 | T-348 over Millstone Creek |  | LBR | Bridge Restoration | CON | BOF | 2025-01-09 | 2025-01-09 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Northern Tier | 3 | Bradford | 116535 | T-348 over Millstone Creek |  | LBR | Bridge Restoration | CON | BRIP | 2025-01-09 | 2025-01-09 | 0 | 94000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94000
Northern Tier | 3 | Bradford | 116556 | T-372 over South Branch Millstone Creek |  | LBR | Bridge Restoration | CON | BOF | 2024-12-12 | 2025-01-09 | 209000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209000
Northern Tier | 3 | Bradford | 117188 | P3 Pipe Replacement | 220 | 249 | Highway Restoration | PE | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 117188 | P3 Pipe Replacement | 220 | 249 | Highway Restoration | FD | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Bradford | 117188 | P3 Pipe Replacement | 220 | 249 | Highway Restoration | ROW | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 117188 | P3 Pipe Replacement | 220 | 249 | Highway Restoration | UTL | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Bradford | 117188 | P3 Pipe Replacement | 220 | 249 | Highway Restoration | CON | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 800000
Northern Tier | 3 | Bradford | 117190 | Sullivan County to Berwick Dr | 220 | 250 | Highway Restoration | CON | STP | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4426037 | 4426037
Northern Tier | 3 | Bradford | 117190 | Sullivan County to Berwick Dr | 220 | 250 | Highway Restoration | CON | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6033000 | 6033000
Northern Tier | 3 | Bradford | 117191 | Old Kennedy Rd to South Creek Trib | 14 | 128 | Highway Restoration | FD | 581 | 2026-04-23 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Bradford | 117191 | Old Kennedy Rd to South Creek Trib | 14 | 128 | Highway Restoration | CON | 581 | 2026-04-23 |  | 650000 | 3000000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 3750000
Northern Tier | 3 | Bradford | 117193 | Glen Valley Rd to Miller Rd | 1056 | 015 | General Maintenance | CON | 581 |  |  | 0 | 299000 | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Northern Tier | 3 | Bradford | 117194 | Little Wysox Cr to SR 187 | 6 | 206 | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Bradford | 117195 | Tioga Co to Sullivan St | 14 | 129 | Highway Restoration | FD | 581 | 2030-07-01 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Bradford | 117195 | Tioga Co to Sullivan St | 14 | 129 | Highway Restoration | CON | 581 | 2030-07-01 |  | 0 | 0 | 0 | 0 | 0 | 1400000 | 800000 | 1919000 | 0 | 4119000
Northern Tier | 3 | Bradford | 117198 | Mile Post 290 to Diner Rd | 6 | 190 | Highway Restoration | FD | 581 | 2030-01-01 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Bradford | 117198 | Mile Post 290 to Diner Rd | 6 | 190 | Highway Restoration | CON | NHPP | 2030-01-01 |  | 0 | 0 | 0 | 1200000 | 300000 | 0 | 0 | 0 | 0 | 1500000
Northern Tier | 3 | Bradford | 117201 | Tomahawk Rd to Murray Cr | 220 | 251 | Highway Restoration | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Bradford | 117201 | Tomahawk Rd to Murray Cr | 220 | 251 | Highway Restoration | CON | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 2200000 | 3000000 | 1000000 | 0 | 6200000
Northern Tier | 3 | Bradford | 117201 | Tomahawk Rd to Murray Cr | 220 | 251 | Highway Restoration | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 2000000 | 725000 | 0 | 0 | 2725000
Northern Tier | 3 | Bradford | 117202 | SR 6 to Susquehanna River | 1041 | 009 | Highway Restoration | CON | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000
Northern Tier | 3 | Bradford | 117249 | SR 220 Pipe Replacement | 220 | 252 | Bridge Replacement | CON | NHPP | 2025-02-13 | 2025-02-13 | 900000 | 112000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012000
Northern Tier | 3 | Bradford | 117374 | SR 467 over Rockwell Creek | 467 | 027 | Bridge Replacement | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 117374 | SR 467 over Rockwell Creek | 467 | 027 | Bridge Replacement | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 150000
Northern Tier | 3 | Bradford | 117374 | SR 467 over Rockwell Creek | 467 | 027 | Bridge Replacement | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000
Northern Tier | 3 | Bradford | 117374 | SR 467 over Rockwell Creek | 467 | 027 | Bridge Replacement | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
Northern Tier | 3 | Bradford | 117374 | SR 467 over Rockwell Creek | 467 | 027 | Bridge Replacement | CON | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Northern Tier | 3 | Bradford | 117375 | SR 1055 over Parks Creek | 1055 | 015 | Bridge Replacement | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 250000
Northern Tier | 3 | Bradford | 117375 | SR 1055 over Parks Creek | 1055 | 015 | Bridge Replacement | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
Northern Tier | 3 | Bradford | 117375 | SR 1055 over Parks Creek | 1055 | 015 | Bridge Replacement | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Bradford | 117375 | SR 1055 over Parks Creek | 1055 | 015 | Bridge Replacement | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 117375 | SR 1055 over Parks Creek | 1055 | 015 | Bridge Replacement | CON | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northern Tier | 3 | Bradford | 117443 | SR 3008 over Trib Towanda Creek | 3008 | 019 | Bridge Replacement | FD | 185 | 2026-09-17 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Northern Tier | 3 | Bradford | 117443 | SR 3008 over Trib Towanda Creek | 3008 | 019 | Bridge Replacement | ROW | 185 | 2026-09-17 |  | 0 | 41215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41215
Northern Tier | 3 | Bradford | 117443 | SR 3008 over Trib Towanda Creek | 3008 | 019 | Bridge Replacement | UTL | 185 | 2026-09-17 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 117443 | SR 3008 over Trib Towanda Creek | 3008 | 019 | Bridge Replacement | CON | 185 | 2026-09-17 |  | 0 | 0 | 350000 | 150000 | 0 | 0 | 0 | 0 | 0 | 500000
Northern Tier | 3 | Bradford | 117446 | SR 3019 over Tributary North Branch Towanda Creek | 3019 | 006 | Bridge Replacement | FD | 185 | 2027-09-16 |  | 0 | 200000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 117446 | SR 3019 over Tributary North Branch Towanda Creek | 3019 | 006 | Bridge Replacement | UTL | 185 | 2027-09-16 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 117446 | SR 3019 over Tributary North Branch Towanda Creek | 3019 | 006 | Bridge Replacement | CON | 185 | 2027-09-16 |  | 0 | 0 | 24000 | 51000 | 0 | 0 | 0 | 0 | 0 | 75000
Northern Tier | 3 | Bradford | 117447 | SR 3020 over Tributary of Susquehanna River | 3020 | 010 | Bridge Replacement | ROW | 185 | 2035-10-01 |  | 21235 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28235
Northern Tier | 3 | Bradford | 117447 | SR 3020 over Tributary of Susquehanna River | 3020 | 010 | Bridge Replacement | UTL | 185 | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 117447 | SR 3020 over Tributary of Susquehanna River | 3020 | 010 | Bridge Replacement | CON | 185 | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Bradford | 117458 | SR 3030 over Tributary to Alba Creek | 3030 | 001 | Bridge Replacement | FD | 185 | 2029-09-01 |  | 0 | 26000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 117458 | SR 3030 over Tributary to Alba Creek | 3030 | 001 | Bridge Replacement | ROW | 185 | 2029-09-01 |  | 17000 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Northern Tier | 3 | Bradford | 117458 | SR 3030 over Tributary to Alba Creek | 3030 | 001 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 117458 | SR 3030 over Tributary to Alba Creek | 3030 | 001 | Bridge Replacement | CON | 185 | 2029-09-01 |  | 0 | 0 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 75000
Northern Tier | 3 | Bradford | 117462 | SR 3034 over South Fork Sugar Creek | 3034 | 001 | Bridge Replacement | PE | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Bradford | 117462 | SR 3034 over South Fork Sugar Creek | 3034 | 001 | Bridge Replacement | FD | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 150000
Northern Tier | 3 | Bradford | 117462 | SR 3034 over South Fork Sugar Creek | 3034 | 001 | Bridge Replacement | ROW | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000
Northern Tier | 3 | Bradford | 117462 | SR 3034 over South Fork Sugar Creek | 3034 | 001 | Bridge Replacement | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 117462 | SR 3034 over South Fork Sugar Creek | 3034 | 001 | Bridge Replacement | CON | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Northern Tier | 3 | Bradford | 117477 | SR 4013 over West Branch Tomjack Creek | 4013 | 049 | Bridge Replacement | PE | 185 | 2031-09-01 |  | 17000 | 158000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
Northern Tier | 3 | Bradford | 117477 | SR 4013 over West Branch Tomjack Creek | 4013 | 049 | Bridge Replacement | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 117477 | SR 4013 over West Branch Tomjack Creek | 4013 | 049 | Bridge Replacement | CON | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 3 | Bradford | 117483 | SR4013 over Bentley Creek | 4013 | 050 | Bridge Replacement | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 117483 | SR4013 over Bentley Creek | 4013 | 050 | Bridge Replacement | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 150000
Northern Tier | 3 | Bradford | 117483 | SR4013 over Bentley Creek | 4013 | 050 | Bridge Replacement | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Bradford | 117483 | SR4013 over Bentley Creek | 4013 | 050 | Bridge Replacement | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 117483 | SR4013 over Bentley Creek | 4013 | 050 | Bridge Replacement | CON | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northern Tier | 3 | Bradford | 117489 | SR 4015 over Mill Creek | 4015 | 010 | Bridge Replacement | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 117489 | SR 4015 over Mill Creek | 4015 | 010 | Bridge Replacement | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 150000
Northern Tier | 3 | Bradford | 117489 | SR 4015 over Mill Creek | 4015 | 010 | Bridge Replacement | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Bradford | 117489 | SR 4015 over Mill Creek | 4015 | 010 | Bridge Replacement | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 117489 | SR 4015 over Mill Creek | 4015 | 010 | Bridge Replacement | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 900000
Northern Tier | 3 | Bradford | 117491 | SR4018 over Tributary to Wolcott Creek | 4018 | 027 | Bridge Replacement | PE | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 125000
Northern Tier | 3 | Bradford | 117491 | SR4018 over Tributary to Wolcott Creek | 4018 | 027 | Bridge Replacement | FD | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000
Northern Tier | 3 | Bradford | 117491 | SR4018 over Tributary to Wolcott Creek | 4018 | 027 | Bridge Replacement | ROW | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Bradford | 117491 | SR4018 over Tributary to Wolcott Creek | 4018 | 027 | Bridge Replacement | UTL | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Bradford | 117491 | SR4018 over Tributary to Wolcott Creek | 4018 | 027 | Bridge Replacement | CON | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Bradford | 117581 | SR187 near Wyoming County | 187 | 109 | Highway Restoration | FD | 581 | 2024-07-04 | 2024-09-12 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Bradford | 117581 | SR187 near Wyoming County | 187 | 109 | Highway Restoration | ROW | 581 | 2024-07-04 | 2024-09-12 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 117581 | SR187 near Wyoming County | 187 | 109 | Highway Restoration | CON | 581 | 2024-07-04 | 2024-09-12 | 88000 | 0 | 0 | 0 | 1009873 | 590127 | 0 | 0 | 0 | 1688000
Northern Tier | 3 | Bradford | 117806 | NTIER Consultant Reserve Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 0 | 37876 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 537876
Northern Tier | 3 | Bradford | 117806 | NTIER Consultant Reserve Line Item |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 0 | 300000
Northern Tier | 3 | Bradford | 117806 | NTIER Consultant Reserve Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 50000 | 50000 | 50000 | 0 | 0 | 250000 | 0 | 400000
Northern Tier | 3 | Bradford | 118008 | Sayre Traffic Signal Improvements | 1069 | TSO | Safety Improvement | CON | CRP | 2024-10-10 | 2024-10-10 | 128000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128000
Northern Tier | 3 | Bradford | 118016 | Bridge Improvement LIne Item | 4016 | 014 | Study Phase of Project | STUDY | 185 |  |  | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
Northern Tier | 3 | Bradford | 118051 | SR 3027 over UNT Alba Creek | 3027 | 011 | Bridge Replacement | FD | 185 | 2025-10-23 | 2025-10-23 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
Northern Tier | 3 | Bradford | 118051 | SR 3027 over UNT Alba Creek | 3027 | 011 | Bridge Replacement | ROW | 185 | 2025-10-23 | 2025-10-23 | 36000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
Northern Tier | 3 | Bradford | 118051 | SR 3027 over UNT Alba Creek | 3027 | 011 | Bridge Replacement | CON | 185 | 2025-10-23 | 2025-10-23 | 515000 | 208785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 723785
Northern Tier | 3 | Bradford | 118371 | SR6 East of Wyalusing | 6 | 196 | Highway Restoration | PE | 581 | 2026-09-17 |  | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000
Northern Tier | 3 | Bradford | 118371 | SR6 East of Wyalusing | 6 | 196 | Highway Restoration | FD | NHPP | 2026-09-17 |  | 0 | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000
Northern Tier | 3 | Bradford | 118371 | SR6 East of Wyalusing | 6 | 196 | Highway Restoration | ROW | 581 | 2026-09-17 |  | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000
Northern Tier | 3 | Bradford | 118371 | SR6 East of Wyalusing | 6 | 196 | Highway Restoration | CON | NHPP | 2026-09-17 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Bradford | 118371 | SR6 East of Wyalusing | 6 | 196 | Highway Restoration | CON | PRTCT | 2026-09-17 |  | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Northern Tier | 3 | Bradford | 120683 | SR 1039 to Means St | 6 | 203 | General Maintenance | PE | 581 | 2026-03-12 | 2026-03-12 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 120683 | SR 1039 to Means St | 6 | 203 | General Maintenance | FD | 581 | 2026-03-12 | 2026-03-12 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Northern Tier | 3 | Bradford | 120683 | SR 1039 to Means St | 6 | 203 | General Maintenance | CON | NHPP | 2026-03-12 | 2026-03-12 | 0 | 816530 | 266000 | 0 | 0 | 0 | 0 | 0 | 0 | 1082530
Northern Tier | 3 | Bradford | 120683 | SR 1039 to Means St | 6 | 203 | General Maintenance | CON | STP | 2026-03-12 | 2026-03-12 | 0 | 268393 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 368393
Northern Tier | 3 | Bradford | 120685 | SR 0199 to SR 1070 | 1069 | 014 | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 150000 | 0 | 0 | 200000
Northern Tier | 3 | Bradford | 120686 | SR 4022 Ramps to SR 1069 | 4022 | 021 | Highway Restoration | PE | 581 | 2025-09-11 | 2025-09-11 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 120686 | SR 4022 Ramps to SR 1069 | 4022 | 021 | Highway Restoration | FD | 581 | 2025-09-11 | 2025-09-11 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
Northern Tier | 3 | Bradford | 120686 | SR 4022 Ramps to SR 1069 | 4022 | 021 | Highway Restoration | CON | 581 | 2025-09-11 | 2025-09-11 | 867282 | 1496662 | 468000 | 0 | 0 | 0 | 0 | 0 | 0 | 2831944
Northern Tier | 3 | Bradford | 120896 | Old Mills Rd to State St | 6 | 204 | Highway Restoration | CON | NHPP |  |  | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 450000
Northern Tier | 3 | Bradford | 120902 | Murray Creek to NY State Line | 220 | 259 | Highway Restoration | PE | NHPP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 300000 | 200000 | 0 | 0 | 500000
Northern Tier | 3 | Bradford | 120902 | Murray Creek to NY State Line | 220 | 259 | Highway Restoration | FD | NHPP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000
Northern Tier | 3 | Bradford | 120902 | Murray Creek to NY State Line | 220 | 259 | Highway Restoration | CON | NHPP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 3500000
Northern Tier | 3 | Bradford | 120902 | Murray Creek to NY State Line | 220 | 259 | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500000 | 5500000
Northern Tier | 3 | Bradford | 120935 | Yanuzzi Dr Intersection NB & SB | 220 | 258 | Highway Restoration | CON | 581 | 2025-04-10 | 2025-04-10 | 140000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161000
Northern Tier | 3 | Bradford | 120936 | Shiner Rd to SR 6 | 2032 | 014 | Highway Restoration | PE | 581 | 2028-01-01 |  | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Bradford | 120936 | Shiner Rd to SR 6 | 2032 | 014 | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 120937 | SR 6 to SR 706 | 409 | 011 | Highway Restoration | CON | 581 | 2027-07-01 |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Bradford | 121026 | SR 414 over Trib Towanda Creek | 414 | 090 | Bridge Replacement | CON | STP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
Northern Tier | 3 | Bradford | 121034 | T-109 (Moore Rd) ov Satterlee Creek |  | LBR | Bridge Replacement | PE | BOF | 2029-01-01 |  | 0 | 235000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 285000
Northern Tier | 3 | Bradford | 121034 | T-109 (Moore Rd) ov Satterlee Creek |  | LBR | Bridge Replacement | PE | BRIP | 2029-01-01 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 3 | Bradford | 121034 | T-109 (Moore Rd) ov Satterlee Creek |  | LBR | Bridge Replacement | ROW | BOF | 2029-01-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 121034 | T-109 (Moore Rd) ov Satterlee Creek |  | LBR | Bridge Replacement | CON | BOF | 2029-01-01 |  | 0 | 0 | 0 | 0 | 400000 | 400000 | 0 | 0 | 0 | 800000
Northern Tier | 3 | Bradford | 121043 | NTIER Bridge Lighting Upgrades to LED | 199 | 013 | Bridge Restoration | PE | CRP | 2026-01-15 | 2026-01-15 | 246000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246000
Northern Tier | 3 | Bradford | 121043 | NTIER Bridge Lighting Upgrades to LED | 199 | 013 | Bridge Restoration | FD | CRP | 2026-01-15 | 2026-01-15 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 121043 | NTIER Bridge Lighting Upgrades to LED | 199 | 013 | Bridge Restoration | CON | CRP | 2026-01-15 | 2026-01-15 | 162400 | 407600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 570000
Northern Tier | 3 | Bradford | 121543 | Embankment north of New Albany | 220 | 264 | Preventive Maintenance | STUDY | 581 | 2031-01-01 |  | 325000 | 297000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 622000
Northern Tier | 3 | Bradford | 121633 | T-751 over Canaan Run | 7223 | RBR | Bridge Restoration | CON | 183 | 2025-10-01 |  | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68000
Northern Tier | 3 | Bradford | 121633 | T-751 over Canaan Run | 7223 | RBR | Bridge Restoration | CON | LOC | 2025-10-01 |  | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000
Northern Tier | 3 | Bradford | 122372 | T-876 (Miller Road) over Satterlee Creek |  | LBR | Bridge Replacement | PE | BOF | 2029-01-01 |  | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275000
Northern Tier | 3 | Bradford | 122372 | T-876 (Miller Road) over Satterlee Creek |  | LBR | Bridge Replacement | PE | BRIP | 2029-01-01 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Bradford | 122372 | T-876 (Miller Road) over Satterlee Creek |  | LBR | Bridge Replacement | ROW | BOF | 2029-01-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Bradford | 122372 | T-876 (Miller Road) over Satterlee Creek |  | LBR | Bridge Replacement | CON | BOF | 2029-01-01 |  | 0 | 0 | 0 | 0 | 500000 | 500000 | 0 | 0 | 0 | 1000000
Northern Tier | 3 | Bradford | 122403 | T-623 (Neiley Road) over Cold Creek |  | A13 | Bridge Replacement | CON | ACT13 |  |  | 984000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 984000
Northern Tier | 3 | Bradford | 122597 | SR 1029 to SR 1022 | 187 | 112 | Highway Restoration | CON | 581 | 2025-07-01 |  | 0 | 876603 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 1026603
Northern Tier | 3 | Bradford | 123011 | NTIER T&E Reserve D3 |  |  | Reserve Line Item | STUDY | 185 |  |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Bradford | 123200 | Lampman Dr (T-550) to Carman Rd (T-885) | 6 | 218 | Highway Restoration | STUDY | 581 |  |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Bradford | 123205 | SR 6 over Susquehanna & Local Bridges Preservation | 6 | 219 | Bridge Preservation - Federal | PE | 185 | 2026-05-07 |  | 0 | 120000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 220000
Northern Tier | 3 | Bradford | 123205 | SR 6 over Susquehanna & Local Bridges Preservation | 6 | 219 | Bridge Preservation - Federal | FD | BRIP | 2026-05-07 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Northern Tier | 3 | Bradford | 123205 | SR 6 over Susquehanna & Local Bridges Preservation | 6 | 219 | Bridge Preservation - Federal | CON | BOF | 2026-05-07 |  | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
Northern Tier | 3 | Bradford | 123205 | SR 6 over Susquehanna & Local Bridges Preservation | 6 | 219 | Bridge Preservation - Federal | CON | BRIP | 2026-05-07 |  | 0 | 0 | 2980000 | 0 | 0 | 0 | 0 | 0 | 0 | 2980000
Northern Tier | 3 | Sullivan | 6936 | T-416 over Porter Creek |  | LBR | Bridge Replacement | PE | BOF | 2028-09-01 |  | 160000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Northern Tier | 3 | Sullivan | 6936 | T-416 over Porter Creek |  | LBR | Bridge Replacement | PE | 183 | 2028-09-01 |  | 30000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
Northern Tier | 3 | Sullivan | 6936 | T-416 over Porter Creek |  | LBR | Bridge Replacement | PE | LOC | 2028-09-01 |  | 10000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Sullivan | 6936 | T-416 over Porter Creek |  | LBR | Bridge Replacement | FD | BOF | 2028-09-01 |  | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000
Northern Tier | 3 | Sullivan | 6936 | T-416 over Porter Creek |  | LBR | Bridge Replacement | FD | 183 | 2028-09-01 |  | 0 | 0 | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 22500
Northern Tier | 3 | Sullivan | 6936 | T-416 over Porter Creek |  | LBR | Bridge Replacement | ROW | BOF | 2028-09-01 |  | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 12000
Northern Tier | 3 | Sullivan | 6936 | T-416 over Porter Creek |  | LBR | Bridge Replacement | ROW | 183 | 2028-09-01 |  | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 2250
Northern Tier | 3 | Sullivan | 6936 | T-416 over Porter Creek |  | LBR | Bridge Replacement | UTL | BOF | 2028-09-01 |  | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 16000
Northern Tier | 3 | Sullivan | 6936 | T-416 over Porter Creek |  | LBR | Bridge Replacement | UTL | 183 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000
Northern Tier | 3 | Sullivan | 6936 | T-416 over Porter Creek |  | LBR | Bridge Replacement | CON | BOF | 2028-09-01 |  | 0 | 0 | 0 | 0 | 280000 | 280000 | 0 | 0 | 0 | 560000
Northern Tier | 3 | Sullivan | 6936 | T-416 over Porter Creek |  | LBR | Bridge Replacement | CON | 183 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 52500 | 52500 | 0 | 0 | 0 | 105000
Northern Tier | 3 | Sullivan | 6954 | T-460 ov Lick Creek |  | LBR | Bridge Replacement | PE | BOF | 2030-09-01 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Sullivan | 6954 | T-460 ov Lick Creek |  | LBR | Bridge Replacement | PE | 183 | 2030-09-01 |  | 0 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 37500
Northern Tier | 3 | Sullivan | 6954 | T-460 ov Lick Creek |  | LBR | Bridge Replacement | PE | LOC | 2030-09-01 |  | 0 | 0 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 12500
Northern Tier | 3 | Sullivan | 6954 | T-460 ov Lick Creek |  | LBR | Bridge Replacement | FD | BOF | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 60000 | 60000 | 0 | 0 | 120000
Northern Tier | 3 | Sullivan | 6954 | T-460 ov Lick Creek |  | LBR | Bridge Replacement | FD | 183 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 11250 | 11250 | 0 | 0 | 22500
Northern Tier | 3 | Sullivan | 6954 | T-460 ov Lick Creek |  | LBR | Bridge Replacement | FD | LOC | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 3750 | 3750 | 0 | 0 | 7500
Northern Tier | 3 | Sullivan | 6954 | T-460 ov Lick Creek |  | LBR | Bridge Replacement | ROW | BOF | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 16000
Northern Tier | 3 | Sullivan | 6954 | T-460 ov Lick Creek |  | LBR | Bridge Replacement | ROW | 183 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 3000
Northern Tier | 3 | Sullivan | 6954 | T-460 ov Lick Creek |  | LBR | Bridge Replacement | ROW | LOC | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000
Northern Tier | 3 | Sullivan | 6954 | T-460 ov Lick Creek |  | LBR | Bridge Replacement | UTL | BOF | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 6954 | T-460 ov Lick Creek |  | LBR | Bridge Replacement | UTL | 183 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3750 | 0 | 0 | 3750
Northern Tier | 3 | Sullivan | 6954 | T-460 ov Lick Creek |  | LBR | Bridge Replacement | CON | BOF | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 368000 | 272000 | 0 | 640000
Northern Tier | 3 | Sullivan | 6954 | T-460 ov Lick Creek |  | LBR | Bridge Replacement | CON | 183 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 69000 | 51000 | 0 | 120000
Northern Tier | 3 | Sullivan | 6994 | T-328 ovr Muncy Creek |  | LBR | Bridge Replacement | PE | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Sullivan | 6994 | T-328 ovr Muncy Creek |  | LBR | Bridge Replacement | PE | 183 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 18750 | 18750 | 0 | 0 | 0 | 37500
Northern Tier | 3 | Sullivan | 6994 | T-328 ovr Muncy Creek |  | LBR | Bridge Replacement | FD | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000 | 0 | 120000
Northern Tier | 3 | Sullivan | 6994 | T-328 ovr Muncy Creek |  | LBR | Bridge Replacement | FD | 183 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 11250 | 0 | 22500
Northern Tier | 3 | Sullivan | 6994 | T-328 ovr Muncy Creek |  | LBR | Bridge Replacement | ROW | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 16000
Northern Tier | 3 | Sullivan | 6994 | T-328 ovr Muncy Creek |  | LBR | Bridge Replacement | ROW | 183 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 3000
Northern Tier | 3 | Sullivan | 6994 | T-328 ovr Muncy Creek |  | LBR | Bridge Replacement | UTL | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 12000
Northern Tier | 3 | Sullivan | 6994 | T-328 ovr Muncy Creek |  | LBR | Bridge Replacement | UTL | 183 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 2250
Northern Tier | 3 | Sullivan | 6994 | T-328 ovr Muncy Creek |  | LBR | Bridge Replacement | CON | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000 | 1200000
Northern Tier | 3 | Sullivan | 6994 | T-328 ovr Muncy Creek |  | LBR | Bridge Replacement | CON | 183 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112500 | 112500 | 225000
Northern Tier | 3 | Sullivan | 7006 | SR 87 over Dry Run | 87 | 128 | Bridge Restoration | ROW | 185 | 2025-01-09 | 2025-01-09 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Northern Tier | 3 | Sullivan | 7006 | SR 87 over Dry Run | 87 | 128 | Bridge Restoration | CON | BRIP | 2025-01-09 | 2025-01-09 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Northern Tier | 3 | Sullivan | 7006 | SR 87 over Dry Run | 87 | 128 | Bridge Restoration | CON | STP | 2025-01-09 | 2025-01-09 | 489000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489000
Northern Tier | 3 | Sullivan | 7007 | SR 87 over Slab Run | 87 | 127 | Bridge Restoration | FD | 185 | 2025-09-11 | 2025-09-11 | 26000 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91000
Northern Tier | 3 | Sullivan | 7007 | SR 87 over Slab Run | 87 | 127 | Bridge Restoration | CON | BRIP | 2025-09-11 | 2025-09-11 | 0 | 1428000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1428000
Northern Tier | 3 | Sullivan | 7007 | SR 87 over Slab Run | 87 | 127 | Bridge Restoration | CON | STP | 2025-09-11 | 2025-09-11 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Sullivan | 7025 | T-325 over Trout Run Bridge |  | RBR | Bridge Replacement | CON | 183 | 2027-01-01 |  | 0 | 0 | 125000 | 275000 | 0 | 0 | 0 | 0 | 0 | 400000
Northern Tier | 3 | Sullivan | 7030 | Lycoming Co to Sonestown | 220 | 197 | Highway Restoration | CON | STP | 2029-01-01 |  | 0 | 0 | 0 | 1400000 | 0 | 0 | 0 | 0 | 0 | 1400000
Northern Tier | 3 | Sullivan | 7030 | Lycoming Co to Sonestown | 220 | 197 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 1200000 | 900000 | 0 | 0 | 0 | 0 | 2100000
Northern Tier | 3 | Sullivan | 67743 | T-346 over Kings Creek |  | LBR | Bridge Replacement | FD | BOF | 2024-12-12 | 2024-12-12 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 3 | Sullivan | 67743 | T-346 over Kings Creek |  | LBR | Bridge Replacement | UTL | BOF | 2024-12-12 | 2024-12-12 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
Northern Tier | 3 | Sullivan | 67743 | T-346 over Kings Creek |  | LBR | Bridge Replacement | CON | BOF | 2024-12-12 | 2024-12-12 | 852000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852000
Northern Tier | 3 | Sullivan | 67743 | T-346 over Kings Creek |  | LBR | Bridge Replacement | CON | 183 | 2024-12-12 | 2024-12-12 | 159750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159750
Northern Tier | 3 | Sullivan | 67743 | T-346 over Kings Creek |  | LBR | Bridge Replacement | CON | LOC | 2024-12-12 | 2024-12-12 | 53250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53250
Northern Tier | 3 | Sullivan | 67746 | T-420 over Elk Creek |  | RBR | Bridge Replacement | CON | 183 | 2024-09-01 |  | 0 | 198488 | 121400 | 358600 | 0 | 0 | 0 | 0 | 0 | 678488
Northern Tier | 3 | Sullivan | 67746 | T-420 over Elk Creek |  | RBR | Bridge Replacement | CON | LOC | 2024-09-01 |  | 0 | 49622 | 30350 | 0 | 0 | 0 | 0 | 0 | 0 | 79972
Northern Tier | 3 | Sullivan | 78938 | SR87 ov Ogdonia Creek | 87 | 130 | Bridge Replacement | CON | BRIP | 2024-12-12 | 2024-12-12 | 1298400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1298400
Northern Tier | 3 | Sullivan | 78938 | SR87 ov Ogdonia Creek | 87 | 130 | Bridge Replacement | CON | STP | 2024-12-12 | 2024-12-12 | 1113123 | 84477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1197600
Northern Tier | 3 | Sullivan | 97779 | SR 2003 to Main Street | 2002 | 023 | Highway Restoration | CON | 581 | 2024-04-01 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Sullivan | 99102 | US220 ov Mill Creek | 220 | 235 | Bridge Replacement | PE | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 250000
Northern Tier | 3 | Sullivan | 99102 | US220 ov Mill Creek | 220 | 235 | Bridge Replacement | FD | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Sullivan | 99102 | US220 ov Mill Creek | 220 | 235 | Bridge Replacement | ROW | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Sullivan | 99102 | US220 ov Mill Creek | 220 | 235 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Sullivan | 99102 | US220 ov Mill Creek | 220 | 235 | Bridge Replacement | CON | STP | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 1400000
Northern Tier | 3 | Sullivan | 99114 | SR 87 to Marsh Crk | 220 | 206 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 500000 | 400000 | 0 | 0 | 0 | 0 | 0 | 900000
Northern Tier | 3 | Sullivan | 99159 | LycoCotoLoyalsockCrk | 87 | 111 | Highway Restoration | CON | 581 | 2027-07-01 |  | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Northern Tier | 3 | Sullivan | 99166 | Chesock Rd to SR220 | 87 | 110 | Highway Restoration | PE | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 300000 | 50000 | 0 | 0 | 0 | 350000
Northern Tier | 3 | Sullivan | 99166 | Chesock Rd to SR220 | 87 | 110 | Highway Restoration | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 149000 | 0 | 449000
Northern Tier | 3 | Sullivan | 99166 | Chesock Rd to SR220 | 87 | 110 | Highway Restoration | ROW | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 300000
Northern Tier | 3 | Sullivan | 99166 | Chesock Rd to SR220 | 87 | 110 | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 3000000 | 1800000 | 7300000
Northern Tier | 3 | Sullivan | 99275 | SR220 over Marsh Creek | 220 | 214 | Bridge Replacement | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Sullivan | 99275 | SR220 over Marsh Creek | 220 | 214 | Bridge Replacement | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 150000
Northern Tier | 3 | Sullivan | 99275 | SR220 over Marsh Creek | 220 | 214 | Bridge Replacement | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Sullivan | 99275 | SR220 over Marsh Creek | 220 | 214 | Bridge Replacement | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 99275 | SR220 over Marsh Creek | 220 | 214 | Bridge Replacement | CON | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 204037 | 1216250 | 329713 | 1750000
Northern Tier | 3 | Sullivan | 99382 | Shanerburg Rd to SR 3009 | 154 | 077 | Highway Restoration | CON | 581 |  | 2024-07-01 | 138000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138000
Northern Tier | 3 | Sullivan | 99422 | SR220 to Muncy Valley Road | 42 | 095 | Highway Restoration | FD | 581 | 2026-04-23 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Sullivan | 99422 | SR220 to Muncy Valley Road | 42 | 095 | Highway Restoration | CON | PRTCT | 2026-04-23 |  | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Northern Tier | 3 | Sullivan | 99422 | SR220 to Muncy Valley Road | 42 | 095 | Highway Restoration | CON | STP | 2026-04-23 |  | 0 | 100000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Northern Tier | 3 | Sullivan | 102938 | SR 42 to Loyalsock Cr | 220 | 190 | Highway Restoration | FD | 581 | 2030-01-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Sullivan | 102938 | SR 42 to Loyalsock Cr | 220 | 190 | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 750000
Northern Tier | 3 | Sullivan | 107304 | Golder Hill Rd to SR 42 | 3001 | 015 | Highway Restoration | CON | 581 |  |  | 30000 | 209353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239353
Northern Tier | 3 | Sullivan | 109757 | Hillsgrove Post Flood Survey | 4010 | 012 | Bridge Restoration | FD | 185 |  | 2025-10-09 | 20000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Sullivan | 109757 | Hillsgrove Post Flood Survey | 4010 | 012 | Bridge Restoration | ROW | 185 |  | 2025-10-09 | 31000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Northern Tier | 3 | Sullivan | 109757 | Hillsgrove Post Flood Survey | 4010 | 012 | Bridge Restoration | CON | 185 |  | 2025-10-09 | 0 | 0 | 436517 | 0 | 0 | 0 | 0 | 0 | 0 | 436517
Northern Tier | 3 | Sullivan | 110166 | SR 87 over Little Loyalsock Creek | 87 | 129 | Bridge Restoration | PE | BRIP | 2027-12-09 |  | 0 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
Northern Tier | 3 | Sullivan | 110166 | SR 87 over Little Loyalsock Creek | 87 | 129 | Bridge Restoration | FD | BRIP | 2027-12-09 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Sullivan | 110166 | SR 87 over Little Loyalsock Creek | 87 | 129 | Bridge Restoration | ROW | BRIP | 2027-12-09 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Sullivan | 110166 | SR 87 over Little Loyalsock Creek | 87 | 129 | Bridge Restoration | UTL | BRIP | 2027-12-09 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 110166 | SR 87 over Little Loyalsock Creek | 87 | 129 | Bridge Restoration | CON | BRIP | 2027-12-09 |  | 0 | 0 | 460000 | 1540000 | 0 | 0 | 0 | 0 | 0 | 2000000
Northern Tier | 3 | Sullivan | 110188 | SR 3001 over Spring Run | 3001 | 016 | Bridge Replacement | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 65000 | 65000 | 0 | 0 | 130000
Northern Tier | 3 | Sullivan | 110188 | SR 3001 over Spring Run | 3001 | 016 | Bridge Replacement | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Sullivan | 110188 | SR 3001 over Spring Run | 3001 | 016 | Bridge Replacement | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000
Northern Tier | 3 | Sullivan | 110188 | SR 3001 over Spring Run | 3001 | 016 | Bridge Replacement | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Sullivan | 110188 | SR 3001 over Spring Run | 3001 | 016 | Bridge Replacement | CON | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
Northern Tier | 3 | Sullivan | 110235 | SR 4005 over Fall Run | 4005 | 012 | Bridge Replacement | CON | 185 | 2024-06-06 | 2024-06-06 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Sullivan | 110240 | SR4020 over Lick Creek | 4020 | 014 | Bridge Replacement | FD | 185 | 2025-10-09 | 2025-10-09 | 2000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 110240 | SR4020 over Lick Creek | 4020 | 014 | Bridge Replacement | ROW | 185 | 2025-10-09 | 2025-10-09 | 9000 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 110240 | SR4020 over Lick Creek | 4020 | 014 | Bridge Replacement | CON | 185 | 2025-10-09 | 2025-10-09 | 100000 | 111387 | 150000 | 138613 | 0 | 0 | 0 | 0 | 0 | 500000
Northern Tier | 3 | Sullivan | 110243 | SR1006 over Trib to Birch Creek | 1006 | 036 | Bridge Replacement | UTL | 185 | 2027-09-16 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 110243 | SR1006 over Trib to Birch Creek | 1006 | 036 | Bridge Replacement | CON | 185 | 2027-09-16 |  | 0 | 0 | 0 | 350000 | 150000 | 0 | 0 | 0 | 0 | 500000
Northern Tier | 3 | Sullivan | 110251 | SR 2003 over Bloody Run | 2003 | 018 | Bridge Restoration | PE | 185 | 2027-10-01 |  | 20000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Northern Tier | 3 | Sullivan | 110251 | SR 2003 over Bloody Run | 2003 | 018 | Bridge Restoration | UTL | 185 | 2027-10-01 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 110251 | SR 2003 over Bloody Run | 2003 | 018 | Bridge Restoration | CON | 185 | 2027-10-01 |  | 0 | 0 | 100000 | 100000 | 150000 | 0 | 0 | 0 | 0 | 350000
Northern Tier | 3 | Sullivan | 110259 | SR1002 over Branch of Little Loyalsock Creek | 1002 | 020 | Bridge Replacement | PE | 185 | 2027-09-16 |  | 20000 | 75000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Sullivan | 110259 | SR1002 over Branch of Little Loyalsock Creek | 1002 | 020 | Bridge Replacement | FD | 185 | 2027-09-16 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Sullivan | 110259 | SR1002 over Branch of Little Loyalsock Creek | 1002 | 020 | Bridge Replacement | ROW | 185 | 2027-09-16 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Sullivan | 110259 | SR1002 over Branch of Little Loyalsock Creek | 1002 | 020 | Bridge Replacement | UTL | 185 | 2027-09-16 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 110259 | SR1002 over Branch of Little Loyalsock Creek | 1002 | 020 | Bridge Replacement | CON | 185 | 2027-09-16 |  | 0 | 0 | 0 | 350000 | 150000 | 0 | 0 | 0 | 0 | 500000
Northern Tier | 3 | Sullivan | 110267 | SR 1001 over Loyalsock Creek | 1001 | 023 | Bridge Replacement | PE | 185 | 2029-09-01 |  | 0 | 0 | 65000 | 65000 | 0 | 0 | 0 | 0 | 0 | 130000
Northern Tier | 3 | Sullivan | 110267 | SR 1001 over Loyalsock Creek | 1001 | 023 | Bridge Replacement | FD | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 110267 | SR 1001 over Loyalsock Creek | 1001 | 023 | Bridge Replacement | ROW | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 110267 | SR 1001 over Loyalsock Creek | 1001 | 023 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 110267 | SR 1001 over Loyalsock Creek | 1001 | 023 | Bridge Replacement | CON | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 0 | 500000
Northern Tier | 3 | Sullivan | 110275 | SR 1002 over Trib to Pigeon Creek | 1002 | 021 | Bridge Replacement | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Sullivan | 110275 | SR 1002 over Trib to Pigeon Creek | 1002 | 021 | Bridge Replacement | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Sullivan | 110275 | SR 1002 over Trib to Pigeon Creek | 1002 | 021 | Bridge Replacement | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Sullivan | 110275 | SR 1002 over Trib to Pigeon Creek | 1002 | 021 | Bridge Replacement | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 110275 | SR 1002 over Trib to Pigeon Creek | 1002 | 021 | Bridge Replacement | CON | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 500000
Northern Tier | 3 | Sullivan | 110293 | SR2002 over Tributary to Muncy Creek | 2002 | 025 | Bridge Replacement | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 65000 | 65000 | 0 | 0 | 0 | 130000
Northern Tier | 3 | Sullivan | 110293 | SR2002 over Tributary to Muncy Creek | 2002 | 025 | Bridge Replacement | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 110293 | SR2002 over Tributary to Muncy Creek | 2002 | 025 | Bridge Replacement | ROW | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000
Northern Tier | 3 | Sullivan | 110293 | SR2002 over Tributary to Muncy Creek | 2002 | 025 | Bridge Replacement | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Sullivan | 110293 | SR2002 over Tributary to Muncy Creek | 2002 | 025 | Bridge Replacement | CON | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 50000 | 300000
Northern Tier | 3 | Sullivan | 110404 | Allegheny Ave to Lakewood Ave | 42 | 109 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Sullivan | 110404 | Allegheny Ave to Lakewood Ave | 42 | 109 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 1300000 | 150000 | 0 | 0 | 0 | 0 | 1450000
Northern Tier | 3 | Sullivan | 110435 | T-410 over N Branch of Mehoopany Creek |  | LBR | Bridge Replacement | PE | BOF | 2028-09-01 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Sullivan | 110435 | T-410 over N Branch of Mehoopany Creek |  | LBR | Bridge Replacement | PE | 183 | 2028-09-01 |  | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500
Northern Tier | 3 | Sullivan | 110435 | T-410 over N Branch of Mehoopany Creek |  | LBR | Bridge Replacement | PE | LOC | 2028-09-01 |  | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500
Northern Tier | 3 | Sullivan | 110435 | T-410 over N Branch of Mehoopany Creek |  | LBR | Bridge Replacement | FD | BOF | 2028-09-01 |  | 0 | 0 | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 120000
Northern Tier | 3 | Sullivan | 110435 | T-410 over N Branch of Mehoopany Creek |  | LBR | Bridge Replacement | FD | 183 | 2028-09-01 |  | 0 | 0 | 0 | 11250 | 11250 | 0 | 0 | 0 | 0 | 22500
Northern Tier | 3 | Sullivan | 110435 | T-410 over N Branch of Mehoopany Creek |  | LBR | Bridge Replacement | ROW | BOF | 2028-09-01 |  | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 12000
Northern Tier | 3 | Sullivan | 110435 | T-410 over N Branch of Mehoopany Creek |  | LBR | Bridge Replacement | ROW | 183 | 2028-09-01 |  | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 2250
Northern Tier | 3 | Sullivan | 110435 | T-410 over N Branch of Mehoopany Creek |  | LBR | Bridge Replacement | UTL | BOF | 2028-09-01 |  | 0 | 0 | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 24000
Northern Tier | 3 | Sullivan | 110435 | T-410 over N Branch of Mehoopany Creek |  | LBR | Bridge Replacement | UTL | 183 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 4500
Northern Tier | 3 | Sullivan | 110435 | T-410 over N Branch of Mehoopany Creek |  | LBR | Bridge Replacement | CON | BOF | 2028-09-01 |  | 0 | 0 | 0 | 0 | 320000 | 320000 | 0 | 0 | 0 | 640000
Northern Tier | 3 | Sullivan | 110435 | T-410 over N Branch of Mehoopany Creek |  | LBR | Bridge Replacement | CON | 183 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 60000 | 60000 | 0 | 0 | 0 | 120000
Northern Tier | 3 | Sullivan | 110438 | SR87 over Loyalsock Creek | 87 | 131 | Bridge Replacement | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Sullivan | 110438 | SR87 over Loyalsock Creek | 87 | 131 | Bridge Replacement | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 150000
Northern Tier | 3 | Sullivan | 110438 | SR87 over Loyalsock Creek | 87 | 131 | Bridge Replacement | ROW | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000
Northern Tier | 3 | Sullivan | 110438 | SR87 over Loyalsock Creek | 87 | 131 | Bridge Replacement | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000
Northern Tier | 3 | Sullivan | 110438 | SR87 over Loyalsock Creek | 87 | 131 | Bridge Replacement | CON | STP | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682000 | 350000 | 1032000
Northern Tier | 3 | Sullivan | 110440 | SR87 over Loyalsock Creek | 87 | 132 | Bridge Replacement | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Sullivan | 110440 | SR87 over Loyalsock Creek | 87 | 132 | Bridge Replacement | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 150000
Northern Tier | 3 | Sullivan | 110440 | SR87 over Loyalsock Creek | 87 | 132 | Bridge Replacement | ROW | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000
Northern Tier | 3 | Sullivan | 110440 | SR87 over Loyalsock Creek | 87 | 132 | Bridge Replacement | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Sullivan | 110440 | SR87 over Loyalsock Creek | 87 | 132 | Bridge Replacement | CON | STP | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1084000 | 916000 | 2000000
Northern Tier | 3 | Sullivan | 110441 | SR 87 over Loyalsock Creek | 87 | 133 | Bridge Restoration | PE | 185 | 2028-09-01 |  | 30000 | 125000 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Sullivan | 110441 | SR 87 over Loyalsock Creek | 87 | 133 | Bridge Restoration | FD | 185 | 2028-09-01 |  | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Sullivan | 110441 | SR 87 over Loyalsock Creek | 87 | 133 | Bridge Restoration | ROW | 185 | 2028-09-01 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Sullivan | 110441 | SR 87 over Loyalsock Creek | 87 | 133 | Bridge Restoration | UTL | 185 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 110441 | SR 87 over Loyalsock Creek | 87 | 133 | Bridge Restoration | CON | STP | 2028-09-01 |  | 0 | 0 | 0 | 0 | 1610000 | 675000 | 0 | 0 | 0 | 2285000
Northern Tier | 3 | Sullivan | 110442 | SR87 over Little Loyalsock Creek | 87 | 134 | Bridge Restoration | PE | 185 | 2028-09-01 |  | 30000 | 125000 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Sullivan | 110442 | SR87 over Little Loyalsock Creek | 87 | 134 | Bridge Restoration | FD | 185 | 2028-09-01 |  | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Sullivan | 110442 | SR87 over Little Loyalsock Creek | 87 | 134 | Bridge Restoration | ROW | 185 | 2028-09-01 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Sullivan | 110442 | SR87 over Little Loyalsock Creek | 87 | 134 | Bridge Restoration | UTL | 185 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Sullivan | 110442 | SR87 over Little Loyalsock Creek | 87 | 134 | Bridge Restoration | CON | STP | 2028-09-01 |  | 0 | 0 | 0 | 0 | 536000 | 500000 | 0 | 0 | 0 | 1036000
Northern Tier | 3 | Sullivan | 111899 | SR 220 Flood Repair 2018 | 220 | 223 | Disaster (Initial Reponse/Non Cap Budg) | ROW | 581 | 2018-10-25 | 2018-11-06 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500
Northern Tier | 3 | Sullivan | 113545 | SR 4002 to SR 154 | 4005 | 014 | Highway Restoration | CON | 581 | 2031-07-01 |  | 0 | 0 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 230000
Northern Tier | 3 | Sullivan | 114053 | SR 154 over Shanerburg Run | 154 | 088 | Bridge Replacement | PE | 185 | 2029-09-01 |  | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Sullivan | 114053 | SR 154 over Shanerburg Run | 154 | 088 | Bridge Replacement | FD | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Sullivan | 114053 | SR 154 over Shanerburg Run | 154 | 088 | Bridge Replacement | ROW | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Sullivan | 114053 | SR 154 over Shanerburg Run | 154 | 088 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 114053 | SR 154 over Shanerburg Run | 154 | 088 | Bridge Replacement | CON | STP | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 996000 | 305000 | 0 | 0 | 1301000
Northern Tier | 3 | Sullivan | 114055 | SR 154 over Elk Creek | 154 | 089 | Bridge Replacement | PE | 185 | 2029-09-01 |  | 33000 | 125000 | 222000 | 0 | 0 | 0 | 0 | 0 | 0 | 380000
Northern Tier | 3 | Sullivan | 114055 | SR 154 over Elk Creek | 154 | 089 | Bridge Replacement | FD | 185 | 2029-09-01 |  | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Sullivan | 114055 | SR 154 over Elk Creek | 154 | 089 | Bridge Replacement | ROW | 185 | 2029-09-01 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Sullivan | 114055 | SR 154 over Elk Creek | 154 | 089 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Sullivan | 114055 | SR 154 over Elk Creek | 154 | 089 | Bridge Replacement | CON | STP | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1766000 | 0 | 0 | 1766000
Northern Tier | 3 | Sullivan | 115358 | SR 42 to Morgan Ave | 3007 | 025 | Highway Restoration | FD | 581 | 2030-01-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Sullivan | 115358 | SR 42 to Morgan Ave | 3007 | 025 | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 650000 | 0 | 0 | 0 | 0 | 0 | 650000
Northern Tier | 3 | Sullivan | 115986 | SR 220 to Big Run | 2002 | 036 | Highway Restoration | CON | 581 | 2027-07-01 |  | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 450000
Northern Tier | 3 | Sullivan | 115987 | SR 87 to Marsh Crk | 220 | 245 | General Maintenance | FD | 581 | 2028-01-01 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Sullivan | 115987 | SR 87 to Marsh Crk | 220 | 245 | General Maintenance | CON | 581 | 2028-01-01 |  | 0 | 0 | 0 | 600000 | 200000 | 0 | 0 | 0 | 0 | 800000
Northern Tier | 3 | Sullivan | 115988 | SR 220 to Dutch Mtn Rd | 87 | 152 | General Maintenance | FD | 581 | 2028-01-01 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Sullivan | 115988 | SR 220 to Dutch Mtn Rd | 87 | 152 | General Maintenance | CON | 581 | 2028-01-01 |  | 0 | 0 | 0 | 700000 | 300000 | 0 | 0 | 0 | 0 | 1000000
Northern Tier | 3 | Sullivan | 115995 | Edkin Hill Rd to Allegheny Ave | 42 | 120 | Highway Restoration | CON | 581 | 2031-07-01 |  | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
Northern Tier | 3 | Sullivan | 116129 | US220 over Birch Creek 2 | 220 | 243 | Bridge Restoration | PE | 185 |  |  | 178750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178750
Northern Tier | 3 | Sullivan | 116129 | US220 over Birch Creek 2 | 220 | 243 | Bridge Restoration | CON | 185 |  |  | 444000 | 356000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Northern Tier | 3 | Sullivan | 116158 | 1 mile N of Georges Rd to Edkin Hill Rd | 42 | 121 | Highway Restoration | FD | 581 | 2031-07-01 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Sullivan | 116158 | 1 mile N of Georges Rd to Edkin Hill Rd | 42 | 121 | Highway Restoration | CON | 581 | 2031-07-01 |  | 0 | 0 | 0 | 1000000 | 200000 | 0 | 0 | 0 | 0 | 1200000
Northern Tier | 3 | Sullivan | 117371 | SR 2002 over Muncy Creek | 2002 | 037 | Bridge Preservation - Federal | PE | BOF | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000
Northern Tier | 3 | Sullivan | 117371 | SR 2002 over Muncy Creek | 2002 | 037 | Bridge Preservation - Federal | FD | BOF | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
Northern Tier | 3 | Sullivan | 117371 | SR 2002 over Muncy Creek | 2002 | 037 | Bridge Preservation - Federal | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Northern Tier | 3 | Sullivan | 117372 | SR4001 over Hoagland Branch | 4001 | 044 | Bridge Preservation - Federal | PE | BOF | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000
Northern Tier | 3 | Sullivan | 117372 | SR4001 over Hoagland Branch | 4001 | 044 | Bridge Preservation - Federal | FD | BOF | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
Northern Tier | 3 | Sullivan | 117372 | SR4001 over Hoagland Branch | 4001 | 044 | Bridge Preservation - Federal | CON | BOF | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Northern Tier | 3 | Sullivan | 117492 | SR2003 over Painter Run | 2003 | 027 | Bridge Replacement | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 65000 | 0 | 130000
Northern Tier | 3 | Sullivan | 117492 | SR2003 over Painter Run | 2003 | 027 | Bridge Replacement | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Sullivan | 117492 | SR2003 over Painter Run | 2003 | 027 | Bridge Replacement | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Sullivan | 117492 | SR2003 over Painter Run | 2003 | 027 | Bridge Replacement | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Sullivan | 117492 | SR2003 over Painter Run | 2003 | 027 | Bridge Replacement | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Northern Tier | 3 | Sullivan | 122595 | SR 3002 to Lake Ave | 42 | 137 | Highway Restoration | CON | 581 | 2026-07-01 |  | 0 | 68211 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 118211
Northern Tier | 3 | Sullivan | 122596 | Morgan Ave to SR 42 | 3007 | 030 | Highway Restoration | CON | 581 | 2025-07-01 |  | 0 | 2229 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 52229
Northern Tier | 3 | Sullivan | 122997 | SR 220 over Mosey Run | 220 | 271 | Highway Restoration | STUDY | 581 |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 3 | Sullivan | 123366 | 2026 Sullivan ADA Upgrade | 42 | 142 | Highway Restoration | CON | 581 | 2026-05-07 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Northern Tier | 3 | Tioga | 7266 | SR 4017 over Buckley Hollow Run | 4017 | 001 | Bridge Replacement | PE | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Tioga | 7266 | SR 4017 over Buckley Hollow Run | 4017 | 001 | Bridge Replacement | FD | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Northern Tier | 3 | Tioga | 7266 | SR 4017 over Buckley Hollow Run | 4017 | 001 | Bridge Replacement | ROW | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Tioga | 7266 | SR 4017 over Buckley Hollow Run | 4017 | 001 | Bridge Replacement | UTL | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 7266 | SR 4017 over Buckley Hollow Run | 4017 | 001 | Bridge Replacement | CON | BOF | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Northern Tier | 3 | Tioga | 7290 | T-894 ovr Bailey Crk |  | LBR | Bridge Replacement | FD | BOF | 2028-01-01 |  | 0 | 0 | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 120000
Northern Tier | 3 | Tioga | 7290 | T-894 ovr Bailey Crk |  | LBR | Bridge Replacement | FD | 183 | 2028-01-01 |  | 0 | 0 | 0 | 11250 | 11250 | 0 | 0 | 0 | 0 | 22500
Northern Tier | 3 | Tioga | 7290 | T-894 ovr Bailey Crk |  | LBR | Bridge Replacement | ROW | BOF | 2028-01-01 |  | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 12000
Northern Tier | 3 | Tioga | 7290 | T-894 ovr Bailey Crk |  | LBR | Bridge Replacement | ROW | 183 | 2028-01-01 |  | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 750
Northern Tier | 3 | Tioga | 7290 | T-894 ovr Bailey Crk |  | LBR | Bridge Replacement | UTL | BOF | 2028-01-01 |  | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 16000
Northern Tier | 3 | Tioga | 7290 | T-894 ovr Bailey Crk |  | LBR | Bridge Replacement | UTL | 183 | 2028-01-01 |  | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000
Northern Tier | 3 | Tioga | 7290 | T-894 ovr Bailey Crk |  | LBR | Bridge Replacement | CON | BOF | 2028-01-01 |  | 0 | 0 | 0 | 0 | 400000 | 400000 | 0 | 0 | 0 | 800000
Northern Tier | 3 | Tioga | 7290 | T-894 ovr Bailey Crk |  | LBR | Bridge Replacement | CON | 183 | 2028-01-01 |  | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 7315 | SR 2016 over Dyke Creek | 2016 | 022 | Bridge Replacement | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 65000 | 0 | 130000
Northern Tier | 3 | Tioga | 7315 | SR 2016 over Dyke Creek | 2016 | 022 | Bridge Replacement | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 7315 | SR 2016 over Dyke Creek | 2016 | 022 | Bridge Replacement | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Tioga | 7315 | SR 2016 over Dyke Creek | 2016 | 022 | Bridge Replacement | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 7315 | SR 2016 over Dyke Creek | 2016 | 022 | Bridge Replacement | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
Northern Tier | 3 | Tioga | 7327 | SR 4002 ovr Charleston Rn | 4002 | 012 | Bridge Restoration | PE | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 250000
Northern Tier | 3 | Tioga | 7327 | SR 4002 ovr Charleston Rn | 4002 | 012 | Bridge Restoration | FD | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
Northern Tier | 3 | Tioga | 7327 | SR 4002 ovr Charleston Rn | 4002 | 012 | Bridge Restoration | ROW | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Tioga | 7327 | SR 4002 ovr Charleston Rn | 4002 | 012 | Bridge Restoration | UTL | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 7327 | SR 4002 ovr Charleston Rn | 4002 | 012 | Bridge Restoration | CON | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 863500 | 636500 | 0 | 0 | 1500000
Northern Tier | 3 | Tioga | 7368 | SR 328 over West Creek | 328 | 032 | Bridge Replacement | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 250000
Northern Tier | 3 | Tioga | 7368 | SR 328 over West Creek | 328 | 032 | Bridge Replacement | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Tioga | 7368 | SR 328 over West Creek | 328 | 032 | Bridge Replacement | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Tioga | 7368 | SR 328 over West Creek | 328 | 032 | Bridge Replacement | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 7368 | SR 328 over West Creek | 328 | 032 | Bridge Replacement | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northern Tier | 3 | Tioga | 7371 | SR 3007 ovr Tb Stoney Frk | 3007 | 018 | Bridge Replacement | PE | 185 | 2029-09-01 |  | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 7371 | SR 3007 ovr Tb Stoney Frk | 3007 | 018 | Bridge Replacement | FD | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Tioga | 7371 | SR 3007 ovr Tb Stoney Frk | 3007 | 018 | Bridge Replacement | ROW | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 7371 | SR 3007 ovr Tb Stoney Frk | 3007 | 018 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 7371 | SR 3007 ovr Tb Stoney Frk | 3007 | 018 | Bridge Replacement | CON | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 0 | 500000
Northern Tier | 3 | Tioga | 7372 | SR 49 over Cowanesque River | 49 | 041 | Bridge Preservation - State Funded | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 7372 | SR 49 over Cowanesque River | 49 | 041 | Bridge Preservation - State Funded | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000
Northern Tier | 3 | Tioga | 7372 | SR 49 over Cowanesque River | 49 | 041 | Bridge Preservation - State Funded | CON | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 700000 | 1700000
Northern Tier | 3 | Tioga | 86917 | SR 2005 to Welcome Cntr | 15 | M53 | Highway Restoration | CON | NHPP | 2025-05-08 | 2025-05-08 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600000
Northern Tier | 3 | Tioga | 97677 | SR 1001 over Lambs Creek | 1001 | 022 | Bridge Restoration | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Tioga | 97677 | SR 1001 over Lambs Creek | 1001 | 022 | Bridge Restoration | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 97677 | SR 1001 over Lambs Creek | 1001 | 022 | Bridge Restoration | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Tioga | 97677 | SR 1001 over Lambs Creek | 1001 | 022 | Bridge Restoration | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
Northern Tier | 3 | Tioga | 97677 | SR 1001 over Lambs Creek | 1001 | 022 | Bridge Restoration | CON | BOF | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 820000 | 1270000
Northern Tier | 3 | Tioga | 97677 | SR 1001 over Lambs Creek | 1001 | 022 | Bridge Restoration | CON | STP | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000
Northern Tier | 3 | Tioga | 97678 | SR 1005 over Mill Creek | 1005 | 033 | Bridge Restoration | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Tioga | 97678 | SR 1005 over Mill Creek | 1005 | 033 | Bridge Restoration | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 97678 | SR 1005 over Mill Creek | 1005 | 033 | Bridge Restoration | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Tioga | 97678 | SR 1005 over Mill Creek | 1005 | 033 | Bridge Restoration | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 97678 | SR 1005 over Mill Creek | 1005 | 033 | Bridge Restoration | CON | BOF | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 604000 | 0 | 1054000
Northern Tier | 3 | Tioga | 97678 | SR 1005 over Mill Creek | 1005 | 033 | Bridge Restoration | CON | STP | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61873 | 0 | 61873
Northern Tier | 3 | Tioga | 97680 | SR2017 ov Tioga River | 2017 | 016 | Bridge Restoration | FD | 185 | 2030-09-01 |  | 0 | 0 | 100000 | 150000 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Tioga | 97680 | SR2017 ov Tioga River | 2017 | 016 | Bridge Restoration | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 97680 | SR2017 ov Tioga River | 2017 | 016 | Bridge Restoration | CON | STP | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000 | 0 | 1500000
Northern Tier | 3 | Tioga | 97684 | SR4007 ov N Brook | 4007 | 007 | Bridge Replacement | PE | 185 | 2028-09-28 |  | 30000 | 125000 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Tioga | 97684 | SR4007 ov N Brook | 4007 | 007 | Bridge Replacement | FD | 185 | 2028-09-28 |  | 0 | 0 | 0 | 100000 | 50000 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 97684 | SR4007 ov N Brook | 4007 | 007 | Bridge Replacement | ROW | 185 | 2028-09-28 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 97684 | SR4007 ov N Brook | 4007 | 007 | Bridge Replacement | UTL | 185 | 2028-09-28 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 97684 | SR4007 ov N Brook | 4007 | 007 | Bridge Replacement | CON | BOF | 2028-09-28 |  | 0 | 0 | 0 | 0 | 205000 | 500000 | 795000 | 0 | 0 | 1500000
Northern Tier | 3 | Tioga | 97689 | T-385 ov Stoney Fork Cr |  | RBR | Bridge Replacement | CON | 183 | 2028-01-01 |  | 0 | 0 | 0 | 320000 | 320000 | 0 | 0 | 0 | 0 | 640000
Northern Tier | 3 | Tioga | 98465 | SR 2017 ov Taylor Run | 2017 | 017 | Bridge Restoration | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 50000 | 0 | 0 | 300000
Northern Tier | 3 | Tioga | 98465 | SR 2017 ov Taylor Run | 2017 | 017 | Bridge Restoration | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 150000
Northern Tier | 3 | Tioga | 98465 | SR 2017 ov Taylor Run | 2017 | 017 | Bridge Restoration | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Tioga | 98465 | SR 2017 ov Taylor Run | 2017 | 017 | Bridge Restoration | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 98465 | SR 2017 ov Taylor Run | 2017 | 017 | Bridge Restoration | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Northern Tier | 3 | Tioga | 98470 | SR2020 ov N Elk Run | 2020 | 005 | Bridge Restoration | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Tioga | 98470 | SR2020 ov N Elk Run | 2020 | 005 | Bridge Restoration | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 150000
Northern Tier | 3 | Tioga | 98470 | SR2020 ov N Elk Run | 2020 | 005 | Bridge Restoration | ROW | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 98470 | SR2020 ov N Elk Run | 2020 | 005 | Bridge Restoration | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Tioga | 98470 | SR2020 ov N Elk Run | 2020 | 005 | Bridge Restoration | CON | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 250000 | 1000000
Northern Tier | 3 | Tioga | 98478 | SR 2022 Ov Tb to Corey Crk | 2022 | 010 | Bridge Restoration | FD | 185 | 2025-11-06 | 2025-11-06 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Tioga | 98478 | SR 2022 Ov Tb to Corey Crk | 2022 | 010 | Bridge Restoration | ROW | 185 | 2025-11-06 | 2025-11-06 | 20000 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26750
Northern Tier | 3 | Tioga | 98478 | SR 2022 Ov Tb to Corey Crk | 2022 | 010 | Bridge Restoration | CON | BOF | 2025-11-06 | 2025-11-06 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Northern Tier | 3 | Tioga | 98478 | SR 2022 Ov Tb to Corey Crk | 2022 | 010 | Bridge Restoration | CON | 185 | 2025-11-06 | 2025-11-06 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 3 | Tioga | 98514 | SR2027 ov Canoe Camp Crk | 2027 | 014 | Bridge Restoration | PE | 185 | 2026-12-10 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Tioga | 98514 | SR2027 ov Canoe Camp Crk | 2027 | 014 | Bridge Restoration | FD | 185 | 2026-12-10 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 98514 | SR2027 ov Canoe Camp Crk | 2027 | 014 | Bridge Restoration | ROW | 185 | 2026-12-10 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 98514 | SR2027 ov Canoe Camp Crk | 2027 | 014 | Bridge Restoration | UTL | 185 | 2026-12-10 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 98514 | SR2027 ov Canoe Camp Crk | 2027 | 014 | Bridge Restoration | CON | BOF | 2026-12-10 |  | 0 | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 300000
Northern Tier | 3 | Tioga | 98539 | SR2016 ov Bellman Run | 2016 | 020 | Bridge Replacement | PE | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Tioga | 98539 | SR2016 ov Bellman Run | 2016 | 020 | Bridge Replacement | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 98539 | SR2016 ov Bellman Run | 2016 | 020 | Bridge Replacement | ROW | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 98539 | SR2016 ov Bellman Run | 2016 | 020 | Bridge Replacement | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Tioga | 98539 | SR2016 ov Bellman Run | 2016 | 020 | Bridge Replacement | CON | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000 | 1500000
Northern Tier | 3 | Tioga | 99107 | US6ovTb N Elk Run | 6 | 130 | Bridge Replacement | CON | BRIP | 2024-06-06 | 2024-06-06 | 0 | 595000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595000
Northern Tier | 3 | Tioga | 99107 | US6ovTb N Elk Run | 6 | 130 | Bridge Replacement | CON | NHPP | 2024-06-06 | 2024-06-06 | 500000 | 595000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1095000
Northern Tier | 3 | Tioga | 99113 | SR14ovTbLycomingCreek | 14 | 121 | Bridge Replacement | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 250000
Northern Tier | 3 | Tioga | 99113 | SR14ovTbLycomingCreek | 14 | 121 | Bridge Replacement | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Tioga | 99113 | SR14ovTbLycomingCreek | 14 | 121 | Bridge Replacement | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Tioga | 99113 | SR14ovTbLycomingCreek | 14 | 121 | Bridge Replacement | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 99113 | SR14ovTbLycomingCreek | 14 | 121 | Bridge Replacement | CON | STP | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1278963 | 1278963
Northern Tier | 3 | Tioga | 99113 | SR14ovTbLycomingCreek | 14 | 121 | Bridge Replacement | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321037 | 321037
Northern Tier | 3 | Tioga | 99171 | Ladd Rd to SR 49 | 349 | 008 | Highway Reconstruction | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 300000
Northern Tier | 3 | Tioga | 99171 | Ladd Rd to SR 49 | 349 | 008 | Highway Reconstruction | ROW | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 435000 | 0 | 0 | 435000
Northern Tier | 3 | Tioga | 99171 | Ladd Rd to SR 49 | 349 | 008 | Highway Reconstruction | UTL | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 200000
Northern Tier | 3 | Tioga | 99173 | SR15 to SR2005 | 414 | 059 | Highway Restoration | CON | 581 | 2023-09-28 | 2023-10-05 | 700998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700998
Northern Tier | 3 | Tioga | 99189 | Tioga River to Covington | 2005 | 016 | Highway Restoration | PE | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Tioga | 99191 | Covington to Cowan Rd | 2005 | 018 | 409 Expanded Maintenance | FD | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Tioga | 99368 | SR2011 ov Blockhouse Crk | 2011 | 002 | Bridge Replacement | PE | 185 | 2028-09-14 |  | 0 | 65000 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Tioga | 99368 | SR2011 ov Blockhouse Crk | 2011 | 002 | Bridge Replacement | FD | 185 | 2028-09-14 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Tioga | 99368 | SR2011 ov Blockhouse Crk | 2011 | 002 | Bridge Replacement | ROW | 185 | 2028-09-14 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 99368 | SR2011 ov Blockhouse Crk | 2011 | 002 | Bridge Replacement | UTL | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 99368 | SR2011 ov Blockhouse Crk | 2011 | 002 | Bridge Replacement | CON | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 500000
Northern Tier | 3 | Tioga | 99369 | SR2022 ov Howland Crk | 2022 | 011 | Bridge Replacement | PE | 185 | 2028-10-01 |  | 16000 | 75000 | 59000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 99369 | SR2022 ov Howland Crk | 2022 | 011 | Bridge Replacement | FD | 185 | 2028-10-01 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Tioga | 99369 | SR2022 ov Howland Crk | 2022 | 011 | Bridge Replacement | ROW | 185 | 2028-10-01 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 99369 | SR2022 ov Howland Crk | 2022 | 011 | Bridge Replacement | UTL | 185 | 2028-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 99369 | SR2022 ov Howland Crk | 2022 | 011 | Bridge Replacement | CON | 185 | 2028-10-01 |  | 0 | 0 | 0 | 150000 | 125000 | 150000 | 0 | 0 | 0 | 425000
Northern Tier | 3 | Tioga | 99370 | SR3007ovWBrStoneyFork | 3007 | 017 | Bridge Replacement | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 99370 | SR3007ovWBrStoneyFork | 3007 | 017 | Bridge Replacement | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Tioga | 99370 | SR3007ovWBrStoneyFork | 3007 | 017 | Bridge Replacement | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 99370 | SR3007ovWBrStoneyFork | 3007 | 017 | Bridge Replacement | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 99370 | SR3007ovWBrStoneyFork | 3007 | 017 | Bridge Replacement | CON | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 500000
Northern Tier | 3 | Tioga | 99387 | Dantz Run to PA 287 | 6 | 065 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Tioga | 99387 | Dantz Run to PA 287 | 6 | 065 | Highway Restoration | FD | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000
Northern Tier | 3 | Tioga | 99387 | Dantz Run to PA 287 | 6 | 065 | Highway Restoration | ROW | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Tioga | 99387 | Dantz Run to PA 287 | 6 | 065 | Highway Restoration | UTL | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Tioga | 99387 | Dantz Run to PA 287 | 6 | 065 | Highway Restoration | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 3400000
Northern Tier | 3 | Tioga | 99387 | Dantz Run to PA 287 | 6 | 065 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000 | 1100000
Northern Tier | 3 | Tioga | 99388 | East St to Renkin St | 49 | 070 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 99388 | East St to Renkin St | 49 | 070 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 418127 | 0 | 0 | 418127
Northern Tier | 3 | Tioga | 99388 | East St to Renkin St | 49 | 070 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 3961873 | 1120000 | 0 | 0 | 5081873
Northern Tier | 3 | Tioga | 99394 | Lycoming Co to Creamery St | 2007 | 016 | Highway Restoration | CON | 581 | 2023-09-28 | 2023-10-05 | 186225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186225
Northern Tier | 3 | Tioga | 99412 | SR3016ovTbZimmermanCrk | 3016 | 009 | Bridge Replacement | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 90000 | 90000 | 0 | 0 | 0 | 180000
Northern Tier | 3 | Tioga | 99412 | SR3016ovTbZimmermanCrk | 3016 | 009 | Bridge Replacement | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 60000
Northern Tier | 3 | Tioga | 99412 | SR3016ovTbZimmermanCrk | 3016 | 009 | Bridge Replacement | ROW | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 99412 | SR3016ovTbZimmermanCrk | 3016 | 009 | Bridge Replacement | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Tioga | 99412 | SR3016ovTbZimmermanCrk | 3016 | 009 | Bridge Replacement | CON | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 150000 | 400000
Northern Tier | 3 | Tioga | 99413 | SR3023ovHeiseRun #2 | 3023 | 003 | Bridge Replacement | CON | 185 | 2024-01-11 | 2024-01-11 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Northern Tier | 3 | Tioga | 99414 | SR3023ovHeiseRun | 3023 | 004 | Bridge Replacement | CON | 185 | 2024-01-11 | 2024-01-11 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 3 | Tioga | 99415 | SR 4001 ov Potter Brook | 4001 | 027 | Disaster Permanent Repair | FD | 185 | 2025-01-16 | 2025-01-16 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000
Northern Tier | 3 | Tioga | 99415 | SR 4001 ov Potter Brook | 4001 | 027 | Disaster Permanent Repair | CON | 185 | 2025-01-16 | 2025-01-16 | 0 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66000
Northern Tier | 3 | Tioga | 99415 | SR 4001 ov Potter Brook | 4001 | 027 | Disaster Permanent Repair | CON | 582 | 2025-01-16 | 2025-01-16 | 0 | 434000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434000
Northern Tier | 3 | Tioga | 99416 | SR4027ovBrCummingsCrk | 4027 | 006 | Bridge Replacement | FD | 185 | 2025-01-09 | 2025-01-09 | 21000 | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Tioga | 99416 | SR4027ovBrCummingsCrk | 4027 | 006 | Bridge Replacement | CON | 185 | 2025-01-09 | 2025-01-09 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Northern Tier | 3 | Tioga | 99424 | Sassafras St to Sherwood St | 6 | 136 | Highway Reconstruction | PE | 581 | 2034-01-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000
Northern Tier | 3 | Tioga | 99424 | Sassafras St to Sherwood St | 6 | 136 | Highway Reconstruction | ROW | 581 | 2034-01-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
Northern Tier | 3 | Tioga | 99424 | Sassafras St to Sherwood St | 6 | 136 | Highway Reconstruction | UTL | 581 | 2034-01-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Northern Tier | 3 | Tioga | 99426 | Old Mainesburg Rd to Strange Rd | 6 | 137 | Highway Restoration | PE | NHPP |  |  | 0 | 0 | 447980 | 303020 | 0 | 0 | 0 | 0 | 0 | 751000
Northern Tier | 3 | Tioga | 99426 | Old Mainesburg Rd to Strange Rd | 6 | 137 | Highway Restoration | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000 | 1300000
Northern Tier | 3 | Tioga | 99426 | Old Mainesburg Rd to Strange Rd | 6 | 137 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300000 | 2300000
Northern Tier | 3 | Tioga | 99426 | Old Mainesburg Rd to Strange Rd | 6 | 137 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000 | 2400000
Northern Tier | 3 | Tioga | 101278 | North of Scott Road | 349 | 009 | Highway Reconstruction | CON | 581 | 2027-01-01 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Tioga | 101285 | Main St to Decker St | 2005 | 014 | Highway Reconstruction | FD | 581 | 2034-01-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northern Tier | 3 | Tioga | 101285 | Main St to Decker St | 2005 | 014 | Highway Reconstruction | ROW | 581 | 2034-01-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Northern Tier | 3 | Tioga | 101285 | Main St to Decker St | 2005 | 014 | Highway Reconstruction | CON | STP | 2034-01-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
Northern Tier | 3 | Tioga | 101285 | Main St to Decker St | 2005 | 014 | Highway Reconstruction | CON | 581 | 2034-01-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300000 | 3300000
Northern Tier | 3 | Tioga | 101335 | Welcome Center to Tioga River | 15 | 186 | Highway Restoration | CON | NHPP | 2025-05-08 | 2025-05-08 | 4930000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4930000
Northern Tier | 3 | Tioga | 102684 | SR 2005 to Westgate Rd | 2027 | 12S | Highway Restoration | ROW | 581 | 2025-12-04 | 2025-12-04 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000
Northern Tier | 3 | Tioga | 102684 | SR 2005 to Westgate Rd | 2027 | 12S | Highway Restoration | CON | 581 | 2025-12-04 | 2025-12-04 | 100000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Northern Tier | 3 | Tioga | 105066 | Marsh Creek Greenway North |  | MCG | Bicycle Pedestrian Highway | CON | TAP | 2024-07-25 | 2024-07-25 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 3 | Tioga | 106235 | SR414 ov W Mill Creek | 414 | 064 | Bridge Replacement | PE | 185 | 2029-09-01 |  | 45375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45375
Northern Tier | 3 | Tioga | 106235 | SR414 ov W Mill Creek | 414 | 064 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 106235 | SR414 ov W Mill Creek | 414 | 064 | Bridge Replacement | CON | STP | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
Northern Tier | 3 | Tioga | 106235 | SR414 ov W Mill Creek | 414 | 064 | Bridge Replacement | CON | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000
Northern Tier | 3 | Tioga | 106236 | SR 4021 over Cowanesque River | 4021 | 007 | Bridge Replacement | PE | BOF | 2027-04-29 |  | 176000 | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 631000
Northern Tier | 3 | Tioga | 106236 | SR 4021 over Cowanesque River | 4021 | 007 | Bridge Replacement | FD | BOF | 2027-04-29 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 106236 | SR 4021 over Cowanesque River | 4021 | 007 | Bridge Replacement | ROW | BOF | 2027-04-29 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 106236 | SR 4021 over Cowanesque River | 4021 | 007 | Bridge Replacement | CON | BOF | 2027-04-29 |  | 0 | 0 | 2212000 | 250000 | 0 | 0 | 0 | 0 | 0 | 2462000
Northern Tier | 3 | Tioga | 108985 | SR 15 to SR 2027 | 2005 | 020 | Safety Improvement | FD | HSIP | 2025-12-04 | 2025-12-04 | 366000 | 262000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628000
Northern Tier | 3 | Tioga | 108985 | SR 15 to SR 2027 | 2005 | 020 | Safety Improvement | ROW | HSIP | 2025-12-04 | 2025-12-04 | 275000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307000
Northern Tier | 3 | Tioga | 108985 | SR 15 to SR 2027 | 2005 | 020 | Safety Improvement | UTL | HSIP | 2025-12-04 | 2025-12-04 | 209200 | 90800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Northern Tier | 3 | Tioga | 108985 | SR 15 to SR 2027 | 2005 | 020 | Safety Improvement | CON | HSIP | 2025-12-04 | 2025-12-04 | 776441 | 323000 | 871800 | 871000 | 0 | 0 | 0 | 0 | 0 | 2842241
Northern Tier | 3 | Tioga | 108985 | SR 15 to SR 2027 | 2005 | 020 | Safety Improvement | CON | STP | 2025-12-04 | 2025-12-04 | 0 | 3412848 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 4112848
Northern Tier | 3 | Tioga | 110236 | SR4027 over Cummings Creek | 4027 | 010 | Bridge Replacement | CON | 185 | 2024-09-12 | 2024-09-12 | 250000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Northern Tier | 3 | Tioga | 110269 | SR 2021 over Tributary to South Creek | 2021 | 005 | Bridge Replacement | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 65000 | 65000 | 0 | 0 | 130000
Northern Tier | 3 | Tioga | 110269 | SR 2021 over Tributary to South Creek | 2021 | 005 | Bridge Replacement | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Tioga | 110269 | SR 2021 over Tributary to South Creek | 2021 | 005 | Bridge Replacement | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Tioga | 110269 | SR 2021 over Tributary to South Creek | 2021 | 005 | Bridge Replacement | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110269 | SR 2021 over Tributary to South Creek | 2021 | 005 | Bridge Replacement | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
Northern Tier | 3 | Tioga | 110289 | SR 1028 over Smith Creek | 1028 | 004 | Bridge Replacement | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 10000 | 75000
Northern Tier | 3 | Tioga | 110289 | SR 1028 over Smith Creek | 1028 | 004 | Bridge Replacement | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110289 | SR 1028 over Smith Creek | 1028 | 004 | Bridge Replacement | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Tioga | 110289 | SR 1028 over Smith Creek | 1028 | 004 | Bridge Replacement | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110289 | SR 1028 over Smith Creek | 1028 | 004 | Bridge Replacement | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Northern Tier | 3 | Tioga | 110290 | SR 2017 over West Mill Creek | 2017 | 020 | Bridge Replacement | PE | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
Northern Tier | 3 | Tioga | 110290 | SR 2017 over West Mill Creek | 2017 | 020 | Bridge Replacement | FD | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110290 | SR 2017 over West Mill Creek | 2017 | 020 | Bridge Replacement | ROW | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110290 | SR 2017 over West Mill Creek | 2017 | 020 | Bridge Replacement | UTL | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110290 | SR 2017 over West Mill Creek | 2017 | 020 | Bridge Replacement | CON | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Northern Tier | 3 | Tioga | 110296 | SR 1004 over Bailey Creek | 1004 | 036 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
Northern Tier | 3 | Tioga | 110296 | SR 1004 over Bailey Creek | 1004 | 036 | Bridge Restoration | FD | 185 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110296 | SR 1004 over Bailey Creek | 1004 | 036 | Bridge Restoration | ROW | 185 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110296 | SR 1004 over Bailey Creek | 1004 | 036 | Bridge Restoration | UTL | 185 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110296 | SR 1004 over Bailey Creek | 1004 | 036 | Bridge Restoration | CON | 185 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Northern Tier | 3 | Tioga | 110297 | SR 2017 over Carpenter Run | 2017 | 021 | Bridge Replacement | PE | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Northern Tier | 3 | Tioga | 110297 | SR 2017 over Carpenter Run | 2017 | 021 | Bridge Replacement | FD | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110297 | SR 2017 over Carpenter Run | 2017 | 021 | Bridge Replacement | ROW | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Tioga | 110297 | SR 2017 over Carpenter Run | 2017 | 021 | Bridge Replacement | UTL | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
Northern Tier | 3 | Tioga | 110297 | SR 2017 over Carpenter Run | 2017 | 021 | Bridge Replacement | CON | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Northern Tier | 3 | Tioga | 110299 | SR 2025 over Marvin Creek | 2025 | 002 | Bridge Replacement | PE | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Northern Tier | 3 | Tioga | 110299 | SR 2025 over Marvin Creek | 2025 | 002 | Bridge Replacement | FD | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110299 | SR 2025 over Marvin Creek | 2025 | 002 | Bridge Replacement | ROW | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110299 | SR 2025 over Marvin Creek | 2025 | 002 | Bridge Replacement | UTL | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110299 | SR 2025 over Marvin Creek | 2025 | 002 | Bridge Replacement | CON | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Northern Tier | 3 | Tioga | 110300 | SR 3014 over Tributary to Zimmerman Creek | 3014 | 010 | Bridge Replacement | PE | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Northern Tier | 3 | Tioga | 110300 | SR 3014 over Tributary to Zimmerman Creek | 3014 | 010 | Bridge Replacement | FD | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110300 | SR 3014 over Tributary to Zimmerman Creek | 3014 | 010 | Bridge Replacement | ROW | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Tioga | 110300 | SR 3014 over Tributary to Zimmerman Creek | 3014 | 010 | Bridge Replacement | UTL | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110300 | SR 3014 over Tributary to Zimmerman Creek | 3014 | 010 | Bridge Replacement | CON | BOF | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275000 | 275000
Northern Tier | 3 | Tioga | 110302 | SR 4012 over Mill Creek | 4012 | 038 | Bridge Replacement | PE | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Northern Tier | 3 | Tioga | 110302 | SR 4012 over Mill Creek | 4012 | 038 | Bridge Replacement | FD | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110302 | SR 4012 over Mill Creek | 4012 | 038 | Bridge Replacement | ROW | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110302 | SR 4012 over Mill Creek | 4012 | 038 | Bridge Replacement | UTL | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110302 | SR 4012 over Mill Creek | 4012 | 038 | Bridge Replacement | CON | BOF | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Northern Tier | 3 | Tioga | 110304 | SR 4027 over Tributary to Crooked Creek | 4027 | 011 | Bridge Replacement | PE | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Northern Tier | 3 | Tioga | 110304 | SR 4027 over Tributary to Crooked Creek | 4027 | 011 | Bridge Replacement | FD | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110304 | SR 4027 over Tributary to Crooked Creek | 4027 | 011 | Bridge Replacement | ROW | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110304 | SR 4027 over Tributary to Crooked Creek | 4027 | 011 | Bridge Replacement | UTL | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 110304 | SR 4027 over Tributary to Crooked Creek | 4027 | 011 | Bridge Replacement | CON | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Northern Tier | 3 | Tioga | 110405 | SR 2018 to SR 660 | 6 | 146 | Highway Restoration | CON | NHPP | 2028-01-01 |  | 0 | 0 | 708715 | 500000 | 0 | 0 | 0 | 0 | 0 | 1208715
Northern Tier | 3 | Tioga | 110405 | SR 2018 to SR 660 | 6 | 146 | Highway Restoration | CON | STP | 2028-01-01 |  | 0 | 0 | 797020 | 0 | 0 | 0 | 0 | 0 | 0 | 797020
Northern Tier | 3 | Tioga | 110405 | SR 2018 to SR 660 | 6 | 146 | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 1181647 | 512618 | 0 | 0 | 0 | 0 | 0 | 1694265
Northern Tier | 3 | Tioga | 113806 | Sebring to SR 2005 | 15 | 217 | General Maintenance | PE | 581 | 2030-01-01 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Tioga | 113896 | North of Mack Road | 660 | 015 | Highway Restoration | STUDY | 581 | 2031-01-01 |  | 70000 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Northern Tier | 3 | Tioga | 113896 | North of Mack Road | 660 | 015 | Highway Restoration | PE | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Tioga | 113896 | North of Mack Road | 660 | 015 | Highway Restoration | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Tioga | 113896 | North of Mack Road | 660 | 015 | Highway Restoration | ROW | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Northern Tier | 3 | Tioga | 113896 | North of Mack Road | 660 | 015 | Highway Restoration | UTL | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 200000
Northern Tier | 3 | Tioga | 113896 | North of Mack Road | 660 | 015 | Highway Restoration | CON | STP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 200000 | 1200000
Northern Tier | 3 | Tioga | 113896 | North of Mack Road | 660 | 015 | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3800000 | 3500000 | 1000000 | 8300000
Northern Tier | 3 | Tioga | 114014 | SR 15 SB Mansfield to Tioga Twp | 15 | 218 | Highway Restoration | PE | 581 | 2030-01-01 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Tioga | 114014 | SR 15 SB Mansfield to Tioga Twp | 15 | 218 | Highway Restoration | CON | NHPP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 500000 | 2200000 | 0 | 0 | 0 | 2700000
Northern Tier | 3 | Tioga | 114014 | SR 15 SB Mansfield to Tioga Twp | 15 | 218 | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 0 | 1800000
Northern Tier | 3 | Tioga | 114020 | E of Mainesburg to Bradford Co Line | 6 | 163 | Highway Restoration | PE | 581 | 2029-01-01 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Tioga | 114020 | E of Mainesburg to Bradford Co Line | 6 | 163 | Highway Restoration | CON | NHPP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 2685873 | 0 | 0 | 0 | 0 | 2685873
Northern Tier | 3 | Tioga | 114020 | E of Mainesburg to Bradford Co Line | 6 | 163 | Highway Restoration | CON | STP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 0 | 700000
Northern Tier | 3 | Tioga | 114020 | E of Mainesburg to Bradford Co Line | 6 | 163 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 914127 | 0 | 0 | 0 | 0 | 914127
Northern Tier | 3 | Tioga | 114022 | SR 15 to East of Schodac Road | 6 | 165 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Tioga | 114023 | SR 6 to South of SR 1038 | 15 | 219 | Highway Restoration | PE | 581 | 2029-01-01 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Tioga | 114023 | SR 6 to South of SR 1038 | 15 | 219 | Highway Restoration | CON | NHPP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 2000000 | 950000 | 610000 | 390000 | 0 | 3950000
Northern Tier | 3 | Tioga | 114023 | SR 6 to South of SR 1038 | 15 | 219 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 2425000 | 1075000 | 0 | 0 | 0 | 3500000
Northern Tier | 3 | Tioga | 114027 | SR 660 to E of Schodac Rd | 6 | 167 | Highway Restoration | PE | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Tioga | 114052 | SR6 over Tributary to North Elk Run | 6 | 168 | Bridge Replacement | PE | NHPP | 2029-09-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 400000
Northern Tier | 3 | Tioga | 114052 | SR6 over Tributary to North Elk Run | 6 | 168 | Bridge Replacement | FD | 185 | 2029-09-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Tioga | 114052 | SR6 over Tributary to North Elk Run | 6 | 168 | Bridge Replacement | ROW | 185 | 2029-09-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Tioga | 114052 | SR6 over Tributary to North Elk Run | 6 | 168 | Bridge Replacement | UTL | 185 | 2029-09-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 114052 | SR6 over Tributary to North Elk Run | 6 | 168 | Bridge Replacement | CON | NHPP | 2029-09-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 1500000
Northern Tier | 3 | Tioga | 114094 | T-526 over Wilson Creek |  | LBR | Bridge Replacement | PE | BOF | 2027-02-25 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Tioga | 114094 | T-526 over Wilson Creek |  | LBR | Bridge Replacement | PE | 183 | 2027-02-25 |  | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500
Northern Tier | 3 | Tioga | 114094 | T-526 over Wilson Creek |  | LBR | Bridge Replacement | PE | LOC | 2027-02-25 |  | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500
Northern Tier | 3 | Tioga | 114094 | T-526 over Wilson Creek |  | LBR | Bridge Replacement | FD | BOF | 2027-02-25 |  | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 140000
Northern Tier | 3 | Tioga | 114094 | T-526 over Wilson Creek |  | LBR | Bridge Replacement | FD | 183 | 2027-02-25 |  | 0 | 0 | 0 | 26250 | 0 | 0 | 0 | 0 | 0 | 26250
Northern Tier | 3 | Tioga | 114094 | T-526 over Wilson Creek |  | LBR | Bridge Replacement | ROW | BOF | 2027-02-25 |  | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 16000
Northern Tier | 3 | Tioga | 114094 | T-526 over Wilson Creek |  | LBR | Bridge Replacement | ROW | 183 | 2027-02-25 |  | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000
Northern Tier | 3 | Tioga | 114094 | T-526 over Wilson Creek |  | LBR | Bridge Replacement | UTL | BOF | 2027-02-25 |  | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 16000
Northern Tier | 3 | Tioga | 114094 | T-526 over Wilson Creek |  | LBR | Bridge Replacement | UTL | 183 | 2027-02-25 |  | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000
Northern Tier | 3 | Tioga | 114094 | T-526 over Wilson Creek |  | LBR | Bridge Replacement | CON | BOF | 2027-02-25 |  | 0 | 0 | 0 | 0 | 320000 | 320000 | 160000 | 0 | 0 | 800000
Northern Tier | 3 | Tioga | 114094 | T-526 over Wilson Creek |  | LBR | Bridge Replacement | CON | 183 | 2027-02-25 |  | 0 | 0 | 0 | 0 | 60000 | 60000 | 30000 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 114100 | T-533 over Tributary to Marsh Creek |  | LBR | Bridge Replacement | PE | BOF | 2027-09-16 |  | 0 | 48000 | 152000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 3 | Tioga | 114100 | T-533 over Tributary to Marsh Creek |  | LBR | Bridge Replacement | PE | 183 | 2027-09-16 |  | 0 | 9000 | 28500 | 0 | 0 | 0 | 0 | 0 | 0 | 37500
Northern Tier | 3 | Tioga | 114100 | T-533 over Tributary to Marsh Creek |  | LBR | Bridge Replacement | FD | BOF | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 120000
Northern Tier | 3 | Tioga | 114100 | T-533 over Tributary to Marsh Creek |  | LBR | Bridge Replacement | FD | 183 | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500 | 0 | 22500
Northern Tier | 3 | Tioga | 114100 | T-533 over Tributary to Marsh Creek |  | LBR | Bridge Replacement | ROW | BOF | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 12000
Northern Tier | 3 | Tioga | 114100 | T-533 over Tributary to Marsh Creek |  | LBR | Bridge Replacement | ROW | 183 | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 2250
Northern Tier | 3 | Tioga | 114100 | T-533 over Tributary to Marsh Creek |  | LBR | Bridge Replacement | UTL | BOF | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000
Northern Tier | 3 | Tioga | 114100 | T-533 over Tributary to Marsh Creek |  | LBR | Bridge Replacement | UTL | 183 | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500
Northern Tier | 3 | Tioga | 114100 | T-533 over Tributary to Marsh Creek |  | LBR | Bridge Replacement | CON | BOF | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640000 | 640000
Northern Tier | 3 | Tioga | 114100 | T-533 over Tributary to Marsh Creek |  | LBR | Bridge Replacement | CON | 183 | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000
Northern Tier | 3 | Tioga | 114170 | SR4002 over Trib Catlin Hollow Crk | 4002 | 016 | Bridge Replacement | PE | 185 | 2026-09-03 |  | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000
Northern Tier | 3 | Tioga | 114170 | SR4002 over Trib Catlin Hollow Crk | 4002 | 016 | Bridge Replacement | FD | 185 | 2026-09-03 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Northern Tier | 3 | Tioga | 114170 | SR4002 over Trib Catlin Hollow Crk | 4002 | 016 | Bridge Replacement | ROW | 185 | 2026-09-03 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Northern Tier | 3 | Tioga | 114170 | SR4002 over Trib Catlin Hollow Crk | 4002 | 016 | Bridge Replacement | UTL | 185 | 2026-09-03 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Tioga | 114170 | SR4002 over Trib Catlin Hollow Crk | 4002 | 016 | Bridge Replacement | CON | 185 | 2026-09-03 |  | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 500000
Northern Tier | 3 | Tioga | 114191 | SR 2019 over Tributary to Towanda Creek | 2019 | 007 | Bridge Replacement | PE | 185 | 2027-09-16 |  | 13000 | 85000 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 114191 | SR 2019 over Tributary to Towanda Creek | 2019 | 007 | Bridge Replacement | FD | 185 | 2027-09-16 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Tioga | 114191 | SR 2019 over Tributary to Towanda Creek | 2019 | 007 | Bridge Replacement | ROW | 185 | 2027-09-16 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 114191 | SR 2019 over Tributary to Towanda Creek | 2019 | 007 | Bridge Replacement | UTL | 185 | 2027-09-16 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 114191 | SR 2019 over Tributary to Towanda Creek | 2019 | 007 | Bridge Replacement | CON | 185 | 2027-09-16 |  | 0 | 0 | 0 | 329787 | 170213 | 0 | 0 | 0 | 0 | 500000
Northern Tier | 3 | Tioga | 115158 | SR 15 Drainage (Mahosky Concern) | 15 | 223 | Highway Restoration | PE | NHPP | 2025-03-13 | 2025-03-13 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 115158 | SR 15 Drainage (Mahosky Concern) | 15 | 223 | Highway Restoration | FD | NHPP | 2025-03-13 | 2025-03-13 | 100000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 115158 | SR 15 Drainage (Mahosky Concern) | 15 | 223 | Highway Restoration | CON | 581 | 2025-03-13 | 2025-03-13 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
Northern Tier | 3 | Tioga | 115841 | SR 4009 over Troups Creek | 4009 | 022 | Highway Restoration | CON | BOF | 2025-02-27 | 2025-02-27 | 1162000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1162000
Northern Tier | 3 | Tioga | 115841 | SR 4009 over Troups Creek | 4009 | 022 | Highway Restoration | CON | BRIP | 2025-02-27 | 2025-02-27 | 218000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218000
Northern Tier | 3 | Tioga | 115993 | Ladd Rd to SR 49 | 349 | 010 | Highway Restoration | UTL | 581 | 2025-07-24 | 2025-07-24 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000
Northern Tier | 3 | Tioga | 115993 | Ladd Rd to SR 49 | 349 | 010 | Highway Restoration | CON | STP | 2025-07-24 | 2025-07-24 | 340000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340000
Northern Tier | 3 | Tioga | 115993 | Ladd Rd to SR 49 | 349 | 010 | Highway Restoration | CON | 581 | 2025-07-24 | 2025-07-24 | 1870500 | 165113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035613
Northern Tier | 3 | Tioga | 115993 | Ladd Rd to SR 49 | 349 | 010 | Highway Restoration | CON | LOC | 2025-07-24 | 2025-07-24 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000
Northern Tier | 3 | Tioga | 116505 | Tioga River to Swan Street | 6 | 179 | Highway Restoration | CON | NHPP | 2024-01-11 | 2024-01-11 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Northern Tier | 3 | Tioga | 116507 | SR15 Ramp to S Mansfield Levee | 2005 | 026 | Highway Restoration | CON | STP | 2024-01-11 | 2024-01-11 | 26316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26316
Northern Tier | 3 | Tioga | 116507 | SR15 Ramp to S Mansfield Levee | 2005 | 026 | Highway Restoration | CON | 581 | 2024-01-11 | 2024-01-11 | 629720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629720
Northern Tier | 3 | Tioga | 117166 | Ramp I (SR8007) to SR 2005 | 15 | 246 | Highway Restoration | CON | NHPP | 2027-01-01 |  | 0 | 0 | 200000 | 150000 | 0 | 0 | 0 | 0 | 0 | 350000
Northern Tier | 3 | Tioga | 117168 | Ramp H to Liberty Boro line | 414 | 086 | General Maintenance | FD | 581 | 2029-01-01 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Tioga | 117170 | Bloss Mountain Rd (SR 2005) to Arnot Rd (SR 2016) | 15 | 247 | Highway Restoration | PE | 581 | 2026-04-23 |  | 0 | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000
Northern Tier | 3 | Tioga | 117170 | Bloss Mountain Rd (SR 2005) to Arnot Rd (SR 2016) | 15 | 247 | Highway Restoration | FD | 581 | 2026-04-23 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Tioga | 117170 | Bloss Mountain Rd (SR 2005) to Arnot Rd (SR 2016) | 15 | 247 | Highway Restoration | CON | NHPP | 2026-04-23 |  | 0 | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500000
Northern Tier | 3 | Tioga | 117173 | Lycoming Co to Ramp I (SR 8007) | 15 | 248 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 700000 | 200000 | 0 | 0 | 0 | 0 | 0 | 900000
Northern Tier | 3 | Tioga | 117175 | Tioga River to SR 6 | 15 | 249 | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 420000
Northern Tier | 3 | Tioga | 117279 | SR 249 over Crooked Creek | 249 | 032 | Bridge Replacement | PE | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 250000
Northern Tier | 3 | Tioga | 117279 | SR 249 over Crooked Creek | 249 | 032 | Bridge Replacement | FD | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 150000
Northern Tier | 3 | Tioga | 117279 | SR 249 over Crooked Creek | 249 | 032 | Bridge Replacement | ROW | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northern Tier | 3 | Tioga | 117279 | SR 249 over Crooked Creek | 249 | 032 | Bridge Replacement | UTL | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 117279 | SR 249 over Crooked Creek | 249 | 032 | Bridge Replacement | CON | STP | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700000 | 1700000
Northern Tier | 3 | Tioga | 117302 | Tioga County Preservation | 49 | 082 | Bridge Preservation - Federal | PE | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Tioga | 117302 | Tioga County Preservation | 49 | 082 | Bridge Preservation - Federal | CON | BOF | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1491873 | 1491873
Northern Tier | 3 | Tioga | 117302 | Tioga County Preservation | 49 | 082 | Bridge Preservation - Federal | CON | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308127 | 1308127
Northern Tier | 3 | Tioga | 117304 | SR 4024 over Cummings Creek | 4024 | 025 | Bridge Replacement | PE | 185 | 2029-09-01 |  | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 250000
Northern Tier | 3 | Tioga | 117304 | SR 4024 over Cummings Creek | 4024 | 025 | Bridge Replacement | FD | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 117304 | SR 4024 over Cummings Creek | 4024 | 025 | Bridge Replacement | ROW | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 117304 | SR 4024 over Cummings Creek | 4024 | 025 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 117304 | SR 4024 over Cummings Creek | 4024 | 025 | Bridge Replacement | CON | BOF | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 0 | 0 | 600000
Northern Tier | 3 | Tioga | 117361 | T-387 over Stony Fork Creek |  | LBR | Bridge Replacement | PE | BOF | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northern Tier | 3 | Tioga | 117361 | T-387 over Stony Fork Creek |  | LBR | Bridge Replacement | PE | 183 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500
Northern Tier | 3 | Tioga | 117361 | T-387 over Stony Fork Creek |  | LBR | Bridge Replacement | FD | BOF | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000
Northern Tier | 3 | Tioga | 117361 | T-387 over Stony Fork Creek |  | LBR | Bridge Replacement | FD | 183 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500 | 22500
Northern Tier | 3 | Tioga | 117361 | T-387 over Stony Fork Creek |  | LBR | Bridge Replacement | ROW | BOF | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000
Northern Tier | 3 | Tioga | 117361 | T-387 over Stony Fork Creek |  | LBR | Bridge Replacement | ROW | 183 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 2250
Northern Tier | 3 | Tioga | 117361 | T-387 over Stony Fork Creek |  | LBR | Bridge Replacement | UTL | BOF | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 16000
Northern Tier | 3 | Tioga | 117361 | T-387 over Stony Fork Creek |  | LBR | Bridge Replacement | UTL | 183 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000
Northern Tier | 3 | Tioga | 117361 | T-387 over Stony Fork Creek |  | LBR | Bridge Replacement | CON | BOF | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northern Tier | 3 | Tioga | 117361 | T-387 over Stony Fork Creek |  | LBR | Bridge Replacement | CON | 183 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Tioga | 117494 | SR 2027 over Canoe Camp Creek | 2027 | 016 | Bridge Replacement | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 250000
Northern Tier | 3 | Tioga | 117494 | SR 2027 over Canoe Camp Creek | 2027 | 016 | Bridge Replacement | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Tioga | 117494 | SR 2027 over Canoe Camp Creek | 2027 | 016 | Bridge Replacement | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Tioga | 117494 | SR 2027 over Canoe Camp Creek | 2027 | 016 | Bridge Replacement | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 117494 | SR 2027 over Canoe Camp Creek | 2027 | 016 | Bridge Replacement | CON | BOF | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northern Tier | 3 | Tioga | 117500 | SR 4027 over Cummings Creek | 4027 | 016 | Bridge Replacement | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 250000
Northern Tier | 3 | Tioga | 117500 | SR 4027 over Cummings Creek | 4027 | 016 | Bridge Replacement | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northern Tier | 3 | Tioga | 117500 | SR 4027 over Cummings Creek | 4027 | 016 | Bridge Replacement | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 3 | Tioga | 117500 | SR 4027 over Cummings Creek | 4027 | 016 | Bridge Replacement | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northern Tier | 3 | Tioga | 117500 | SR 4027 over Cummings Creek | 4027 | 016 | Bridge Replacement | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Northern Tier | 3 | Tioga | 117507 | Tioga Bridge Painting | 2022 | 019 | Bridge Preservation - State Funded | PE | 185 | 2027-01-14 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 3 | Tioga | 117507 | Tioga Bridge Painting | 2022 | 019 | Bridge Preservation - State Funded | CON | 185 | 2027-01-14 |  | 0 | 0 | 428833 | 275000 | 0 | 0 | 0 | 0 | 0 | 703833
Northern Tier | 3 | Tioga | 117832 | SR 1007 near Reynolds Road | 1007 | 029 | Bridge Replacement | FD | 581 | 2025-10-23 | 2025-10-23 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Northern Tier | 3 | Tioga | 117832 | SR 1007 near Reynolds Road | 1007 | 029 | Bridge Replacement | ROW | 185 | 2025-10-23 | 2025-10-23 | 10265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10265
Northern Tier | 3 | Tioga | 117832 | SR 1007 near Reynolds Road | 1007 | 029 | Bridge Replacement | CON | 581 | 2025-10-23 | 2025-10-23 | 0 | 100000 | 489389 | 0 | 0 | 0 | 0 | 0 | 0 | 589389
Northern Tier | 3 | Tioga | 118342 | Confluence of Marsh Cr & Pine Cr | 362 | 001 | Highway Restoration | PE | 581 | 2028-01-01 |  | 100000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Northern Tier | 3 | Tioga | 118342 | Confluence of Marsh Cr & Pine Cr | 362 | 001 | Highway Restoration | FD | 581 | 2028-01-01 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 3 | Tioga | 118342 | Confluence of Marsh Cr & Pine Cr | 362 | 001 | Highway Restoration | ROW | 581 | 2028-01-01 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 3 | Tioga | 118342 | Confluence of Marsh Cr & Pine Cr | 362 | 001 | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 0 | 2000000 | 1000000 | 0 | 0 | 0 | 0 | 3000000
Northern Tier | 3 | Tioga | 119591 | Tioga River to SR 49 NB & SB | 15 | 263 | Highway Restoration | CON | NHPP | 2024-02-15 | 2024-02-15 | 31498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31498
Northern Tier | 3 | Tioga | 119591 | Tioga River to SR 49 NB & SB | 15 | 263 | Highway Restoration | CON | STP | 2024-02-15 | 2024-02-15 | 90445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90445
Northern Tier | 3 | Tioga | 119657 | Lycoming Cr at Ogdensburg Rd | 14 | 132 | Study Phase of Project | STUDY | 581 |  |  | 0 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000
Northern Tier | 3 | Tioga | 120010 | Barber Hollow Road Over Shanty Creek |  | RBR | Bridge Replacement | CON | 183 | 2027-01-01 |  | 0 | 0 | 250000 | 390000 | 0 | 0 | 0 | 0 | 0 | 640000
Northern Tier | 3 | Tioga | 120699 | Tioga Multimodal Rail |  |  | MultiModal | FD | 411 |  |  | 14992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14992
Northern Tier | 3 | Tioga | 120699 | Tioga Multimodal Rail |  |  | MultiModal | FD | LOC |  |  | 27508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27508
Northern Tier | 3 | Tioga | 120699 | Tioga Multimodal Rail |  |  | MultiModal | CON | 411 |  |  | 134930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134930
Northern Tier | 3 | Tioga | 120699 | Tioga Multimodal Rail |  |  | MultiModal | CON | LOC |  |  | 36745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36745
Northern Tier | 3 | Tioga | 120897 | SR 287 to SR 15 Resurface | 414 | 091 | Highway Restoration | CON | 581 | 2029-07-01 |  | 0 | 0 | 0 | 0 | 1000000 | 300000 | 0 | 0 | 0 | 1300000
Northern Tier | 3 | Tioga | 120924 | Tioga River to NY line NB & SB | 15 | 269 | Highway Restoration | PE | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 300000
Northern Tier | 3 | Tioga | 120924 | Tioga River to NY line NB & SB | 15 | 269 | Highway Restoration | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 500000 | 0 | 650000
Northern Tier | 3 | Tioga | 120924 | Tioga River to NY line NB & SB | 15 | 269 | Highway Restoration | CON | NHPP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1040000 | 3160000 | 400000 | 4600000
Northern Tier | 3 | Tioga | 120924 | Tioga River to NY line NB & SB | 15 | 269 | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1460000 | 3100000 | 0 | 4560000
Northern Tier | 3 | Tioga | 120925 | Williamson Rd (SR 2005) to Richmond Twp | 15 | 270 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Northern Tier | 3 | Tioga | 120925 | Williamson Rd (SR 2005) to Richmond Twp | 15 | 270 | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Northern Tier | 3 | Tioga | 120925 | Williamson Rd (SR 2005) to Richmond Twp | 15 | 270 | Highway Restoration | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750000 | 7750000
Northern Tier | 3 | Tioga | 120925 | Williamson Rd (SR 2005) to Richmond Twp | 15 | 270 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1250000
Northern Tier | 3 | Tioga | 120925 | Williamson Rd (SR 2005) to Richmond Twp | 15 | 270 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
Northern Tier | 3 | Tioga | 120927 | Lycoming Co Line to S of Williamson Rd (SR 2005) | 15 | 271 | Highway Restoration | PE | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Northern Tier | 3 | Tioga | 120927 | Lycoming Co Line to S of Williamson Rd (SR 2005) | 15 | 271 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northern Tier | 3 | Tioga | 120927 | Lycoming Co Line to S of Williamson Rd (SR 2005) | 15 | 271 | Highway Restoration | CON | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
Northern Tier | 3 | Tioga | 120927 | Lycoming Co Line to S of Williamson Rd (SR 2005) | 15 | 271 | Highway Restoration | CON | STP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Northern Tier | 3 | Tioga | 120927 | Lycoming Co Line to S of Williamson Rd (SR 2005) | 15 | 271 | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000
Northern Tier | 3 | Tioga | 121027 | SR 2025 over Marvin Creek | 2025 | 006 | Bridge Replacement | CON | BOF | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1387127 | 1387127
Northern Tier | 3 | Tioga | 121027 | SR 2025 over Marvin Creek | 2025 | 006 | Bridge Replacement | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1112873 | 1112873
Northern Tier | 3 | Tioga | 121554 | East of Spencer Rd | 660 | 135 | Preventive Maintenance | STUDY | 581 |  |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Northern Tier | 3 | Tioga | 121920 | SR 6 to State Police | 1001 | 027 | Highway Restoration | PE | 581 |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 3 | Tioga | 122320 | 15 North ITS | 15 | 283 | Intelligent Transportation System | PE | CRP | 2026-11-05 |  | 104000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104000
Northern Tier | 3 | Tioga | 122320 | 15 North ITS | 15 | 283 | Intelligent Transportation System | PE | CRP | 2026-11-05 |  | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111000
Northern Tier | 3 | Tioga | 122320 | 15 North ITS | 15 | 283 | Intelligent Transportation System | FD | CRP | 2026-11-05 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Northern Tier | 3 | Tioga | 122320 | 15 North ITS | 15 | 283 | Intelligent Transportation System | FD | CRP | 2026-11-05 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 3 | Tioga | 122320 | 15 North ITS | 15 | 283 | Intelligent Transportation System | UTL | CRP | 2026-11-05 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 3 | Tioga | 122320 | 15 North ITS | 15 | 283 | Intelligent Transportation System | UTL | CRP | 2026-11-05 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 3 | Tioga | 122320 | 15 North ITS | 15 | 283 | Intelligent Transportation System | CON | CRP | 2026-11-05 |  | 0 | 907340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 907340
Northern Tier | 3 | Tioga | 122320 | 15 North ITS | 15 | 283 | Intelligent Transportation System | CON | CRP | 2026-11-05 |  | 0 | 271440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271440
Northern Tier | 3 | Tioga | 122964 | D3 NTIER CRP Flex Fuel Station |  |  | Public Transit | PRA | CRP |  |  | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17600
Northern Tier | 3 | Tioga | 122964 | D3 NTIER CRP Flex Fuel Station |  |  | Public Transit | PRA | OTH |  |  | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4400
Northern Tier | 3 | Tioga | 122965 | D3 NTIER CRP Flex Bus Shelter |  |  | Public Transit | PRA | CRP |  |  | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
Northern Tier | 3 | Tioga | 122965 | D3 NTIER CRP Flex Bus Shelter |  |  | Public Transit | PRA | OTH |  |  | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
Northern Tier | 3 | Tioga | 123067 | SR 287 over Trib Tioga River | 287 | 186 | Highway Restoration | STUDY | 581 |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 4 | Susquehanna | 9546 | Johnston Street over Salt Lick Creek | 7409 | 552 | Bridge Replacement | PE | BOF | 2027-10-01 |  | 880000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880000
Northern Tier | 4 | Susquehanna | 9546 | Johnston Street over Salt Lick Creek | 7409 | 552 | Bridge Replacement | PE | 183 | 2027-10-01 |  | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000
Northern Tier | 4 | Susquehanna | 9546 | Johnston Street over Salt Lick Creek | 7409 | 552 | Bridge Replacement | PE | LOC | 2027-10-01 |  | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
Northern Tier | 4 | Susquehanna | 9546 | Johnston Street over Salt Lick Creek | 7409 | 552 | Bridge Replacement | CON | BOF | 2027-10-01 |  | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 1600000
Northern Tier | 4 | Susquehanna | 9546 | Johnston Street over Salt Lick Creek | 7409 | 552 | Bridge Replacement | CON | 183 | 2027-10-01 |  | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000
Northern Tier | 4 | Susquehanna | 9583 | Water Street over Starrucca Creek - SCB 33 | 7227 | BRG | Bridge Restoration | PE | 183 |  |  | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000
Northern Tier | 4 | Susquehanna | 9583 | Water Street over Starrucca Creek - SCB 33 | 7227 | BRG | Bridge Restoration | PE | LOC |  |  | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000
Northern Tier | 4 | Susquehanna | 9631 | SR 1007 over South Branch Canawacta Creek | 1007 | D51 | Bridge Replacement | PE | 185 | 2033-10-01 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 4 | Susquehanna | 9631 | SR 1007 over South Branch Canawacta Creek | 1007 | D51 | Bridge Replacement | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393300 | 0 | 393300
Northern Tier | 4 | Susquehanna | 9643 | SR 2036 over Rock Hill Creek | 2036 | 570 | Bridge Replacement | ROW | 185 | 2026-10-22 |  | 53003 | 5462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58465
Northern Tier | 4 | Susquehanna | 9643 | SR 2036 over Rock Hill Creek | 2036 | 570 | Bridge Replacement | CON | 581 | 2026-10-22 |  | 0 | 0 | 0 | 100000 | 1400000 | 0 | 0 | 0 | 0 | 1500000
Northern Tier | 4 | Susquehanna | 9654 | SR 2096 over Horton Creek | 2096 | 550 | Bridge Replacement | PE | BOF | 2033-10-01 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 4 | Susquehanna | 9654 | SR 2096 over Horton Creek | 2096 | 550 | Bridge Replacement | PE | 581 | 2033-10-01 |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 4 | Susquehanna | 9654 | SR 2096 over Horton Creek | 2096 | 550 | Bridge Replacement | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
Northern Tier | 4 | Susquehanna | 9668 | SR 706 over Branch Wyalusing Creek | 706 | 555 | Bridge Replacement | PE | 581 |  |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 9668 | SR 706 over Branch Wyalusing Creek | 706 | 555 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 747000 | 0 | 0 | 747000
Northern Tier | 4 | Susquehanna | 9698 | SR 29 over Branch of Wyalusing Creek | 29 | 552 | Bridge Replacement | PE | STP | 2038-10-01 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 9698 | SR 29 over Branch of Wyalusing Creek | 29 | 552 | Bridge Replacement | PE | 581 | 2038-10-01 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 9698 | SR 29 over Branch of Wyalusing Creek | 29 | 552 | Bridge Replacement | CON | STP | 2038-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 400000
Northern Tier | 4 | Susquehanna | 9698 | SR 29 over Branch of Wyalusing Creek | 29 | 552 | Bridge Replacement | CON | 581 | 2038-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Northern Tier | 4 | Susquehanna | 9699 | SR 11 over East Branch Martins Creek | 11 | 551 | Bridge Replacement | FD | STP | 2027-01-14 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 9699 | SR 11 over East Branch Martins Creek | 11 | 551 | Bridge Replacement | FD | 185 | 2027-01-14 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 9699 | SR 11 over East Branch Martins Creek | 11 | 551 | Bridge Replacement | CON | STP | 2027-01-14 |  | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 600000
Northern Tier | 4 | Susquehanna | 9699 | SR 11 over East Branch Martins Creek | 11 | 551 | Bridge Replacement | CON | 185 | 2027-01-14 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
Northern Tier | 4 | Susquehanna | 9701 | SR 29 over Tributary Snake Creek | 29 | D50 | Bridge Preservation - State Funded | PE | STP | 2026-10-01 |  | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Northern Tier | 4 | Susquehanna | 9701 | SR 29 over Tributary Snake Creek | 29 | D50 | Bridge Preservation - State Funded | PE | 185 | 2026-10-01 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Northern Tier | 4 | Susquehanna | 9701 | SR 29 over Tributary Snake Creek | 29 | D50 | Bridge Preservation - State Funded | CON | STP | 2026-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 400000
Northern Tier | 4 | Susquehanna | 9701 | SR 29 over Tributary Snake Creek | 29 | D50 | Bridge Preservation - State Funded | CON | 185 | 2026-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Northern Tier | 4 | Susquehanna | 9704 | SR 92 over Hillborn Creek | 92 | 550 | Bridge Replacement | PE | STP | 2027-10-21 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 4 | Susquehanna | 9704 | SR 92 over Hillborn Creek | 92 | 550 | Bridge Replacement | PE | 185 | 2027-10-21 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 4 | Susquehanna | 9704 | SR 92 over Hillborn Creek | 92 | 550 | Bridge Replacement | CON | STP | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805000 | 0 | 805000
Northern Tier | 4 | Susquehanna | 9709 | SR 367 over Branch Tuscarora Creek | 367 | 550 | Bridge Replacement | CON | BOF | 2024-08-22 | 2024-08-22 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
Northern Tier | 4 | Susquehanna | 9709 | SR 367 over Branch Tuscarora Creek | 367 | 550 | Bridge Replacement | CON | 185 | 2024-08-22 | 2024-08-22 | 137500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137500
Northern Tier | 4 | Susquehanna | 9720 | SR 706 over East Branch of Wyalusing Creek | 706 | 552 | Bridge Replacement | UTL | 581 | 2024-07-11 | 2024-07-11 | 65000 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78000
Northern Tier | 4 | Susquehanna | 9720 | SR 706 over East Branch of Wyalusing Creek | 706 | 552 | Bridge Replacement | CON | STP | 2024-07-11 | 2024-07-11 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Northern Tier | 4 | Susquehanna | 9720 | SR 706 over East Branch of Wyalusing Creek | 706 | 552 | Bridge Replacement | CON | 185 | 2024-07-11 | 2024-07-11 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 4 | Susquehanna | 9723 | SR 492 over Little Butler Creek | 492 | D50 | Bridge Replacement | FD | STP | 2025-12-04 | 2025-12-04 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 9723 | SR 492 over Little Butler Creek | 492 | D50 | Bridge Replacement | FD | 185 | 2025-12-04 | 2025-12-04 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 9723 | SR 492 over Little Butler Creek | 492 | D50 | Bridge Replacement | CON | PRTCT | 2025-12-04 | 2025-12-04 | 0 | 1625158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1625158
Northern Tier | 4 | Susquehanna | 9742 | SR 3017 over Thomas Creek | 3017 | 571 | Bridge Restoration | PE | BOF | 2030-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 9742 | SR 3017 over Thomas Creek | 3017 | 571 | Bridge Restoration | PE | 185 | 2030-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 9742 | SR 3017 over Thomas Creek | 3017 | 571 | Bridge Restoration | FD | BOF | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 0 | 0 | 240000
Northern Tier | 4 | Susquehanna | 9742 | SR 3017 over Thomas Creek | 3017 | 571 | Bridge Restoration | FD | 581 | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 60000
Northern Tier | 4 | Susquehanna | 9742 | SR 3017 over Thomas Creek | 3017 | 571 | Bridge Restoration | CON | BOF | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 1200000
Northern Tier | 4 | Susquehanna | 9742 | SR 3017 over Thomas Creek | 3017 | 571 | Bridge Restoration | CON | 581 | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 300000
Northern Tier | 4 | Susquehanna | 9745 | Bradford to Rush | 706 | 501 | Highway Restoration | CON | STP | 2021-04-08 | 2021-04-08 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Northern Tier | 4 | Susquehanna | 9745 | Bradford to Rush | 706 | 501 | Highway Restoration | CON | 581 | 2021-04-08 | 2021-04-08 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 4 | Susquehanna | 47034 | SR 171 over Canawacta Creek | 171 | 502 | Bridge Replacement | PE | STP | 2027-02-11 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 47034 | SR 171 over Canawacta Creek | 171 | 502 | Bridge Replacement | PE | 185 | 2027-02-11 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 47034 | SR 171 over Canawacta Creek | 171 | 502 | Bridge Replacement | FD | STP | 2027-02-11 |  | 244000 | 61000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305000
Northern Tier | 4 | Susquehanna | 47034 | SR 171 over Canawacta Creek | 171 | 502 | Bridge Replacement | ROW | 581 | 2027-02-11 |  | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000
Northern Tier | 4 | Susquehanna | 47034 | SR 171 over Canawacta Creek | 171 | 502 | Bridge Replacement | UTL | 183 | 2027-02-11 |  | 0 | 47500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47500
Northern Tier | 4 | Susquehanna | 47034 | SR 171 over Canawacta Creek | 171 | 502 | Bridge Replacement | UTL | LOC | 2027-02-11 |  | 0 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24500
Northern Tier | 4 | Susquehanna | 47034 | SR 171 over Canawacta Creek | 171 | 502 | Bridge Replacement | CON | STP | 2027-02-11 |  | 0 | 0 | 0 | 250000 | 530000 | 500000 | 0 | 0 | 0 | 1280000
Northern Tier | 4 | Susquehanna | 47034 | SR 171 over Canawacta Creek | 171 | 502 | Bridge Replacement | CON | 185 | 2027-02-11 |  | 0 | 0 | 0 | 62500 | 132500 | 125000 | 0 | 0 | 0 | 320000
Northern Tier | 4 | Susquehanna | 56738 | SR 4008 over Laurel Lake Creek | 4008 | D50 | Bridge Replacement | CON | BRIP | 2023-04-13 | 2023-04-13 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
Northern Tier | 4 | Susquehanna | 56738 | SR 4008 over Laurel Lake Creek | 4008 | D50 | Bridge Replacement | CON | 185 | 2023-04-13 | 2023-04-13 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
Northern Tier | 4 | Susquehanna | 65189 | Church Street over Salt Lick Creek | 7409 | 551 | Bridge Replacement | PE | BOF | 2036-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 80000
Northern Tier | 4 | Susquehanna | 65189 | Church Street over Salt Lick Creek | 7409 | 551 | Bridge Replacement | PE | 183 | 2036-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northern Tier | 4 | Susquehanna | 67523 | SR 267 over Middle Branch Wyalusing Creek | 267 | 555 | Bridge Replacement | CON | STP | 2023-05-25 | 2023-05-25 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
Northern Tier | 4 | Susquehanna | 67523 | SR 267 over Middle Branch Wyalusing Creek | 267 | 555 | Bridge Replacement | CON | 185 | 2023-05-25 | 2023-05-25 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Northern Tier | 4 | Susquehanna | 67525 | SR 706 over East Branch Wyalusing Creek | 706 | 554 | Bridge Replacement | CON | STP | 2027-01-14 |  | 0 | 0 | 1400000 | 0 | 1600000 | 0 | 0 | 0 | 0 | 3000000
Northern Tier | 4 | Susquehanna | 67525 | SR 706 over East Branch Wyalusing Creek | 706 | 554 | Bridge Replacement | CON | 581 | 2027-01-14 |  | 0 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 2500000
Northern Tier | 4 | Susquehanna | 67546 | SR 4014 over Branch of Apolacon Creek | 4014 | 550 | Bridge Replacement | PE | STP | 2028-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 4 | Susquehanna | 67546 | SR 4014 over Branch of Apolacon Creek | 4014 | 550 | Bridge Replacement | PE | 185 | 2028-10-01 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 4 | Susquehanna | 67546 | SR 4014 over Branch of Apolacon Creek | 4014 | 550 | Bridge Replacement | CON | 581 | 2028-10-01 |  | 0 | 0 | 0 | 0 | 634000 | 0 | 0 | 0 | 0 | 634000
Northern Tier | 4 | Susquehanna | 67548 | SR 3004 over Tributary to Riley Creek | 3004 | D51 | Bridge Replacement | CON | 581 | 2024-10-10 | 2024-10-10 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Northern Tier | 4 | Susquehanna | 67550 | SR 11 over Tributary Salt Lick Creek | 11 | 555 | Bridge Replacement | PE | STP | 2035-10-01 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 67550 | SR 11 over Tributary Salt Lick Creek | 11 | 555 | Bridge Replacement | PE | 185 | 2035-10-01 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 67550 | SR 11 over Tributary Salt Lick Creek | 11 | 555 | Bridge Replacement | CON | 581 | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747500 | 0 | 747500
Northern Tier | 4 | Susquehanna | 67560 | SR 4008 over Silver Creek | 4008 | D01 | Bridge Replacement | CON | BOF | 2024-12-12 | 2024-12-12 | 480000 | 1520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Northern Tier | 4 | Susquehanna | 67560 | SR 4008 over Silver Creek | 4008 | D01 | Bridge Replacement | CON | 185 | 2024-12-12 | 2024-12-12 | 120000 | 380000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Northern Tier | 4 | Susquehanna | 67565 | SR 1022 over Tributary Dubois Creek | 1022 | 552 | Bridge Replacement | FD | 185 | 2026-10-01 |  | 0 | 220000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 270000
Northern Tier | 4 | Susquehanna | 67565 | SR 1022 over Tributary Dubois Creek | 1022 | 552 | Bridge Replacement | ROW | 581 | 2026-10-01 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Northern Tier | 4 | Susquehanna | 67565 | SR 1022 over Tributary Dubois Creek | 1022 | 552 | Bridge Replacement | CON | 581 | 2026-10-01 |  | 0 | 0 | 0 | 0 | 0 | 650000 | 0 | 0 | 0 | 650000
Northern Tier | 4 | Susquehanna | 68926 | SR 106 over Round Pond Creek | 106 | 573 | Bridge Restoration | PE | STP | 2034-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 68926 | SR 106 over Round Pond Creek | 106 | 573 | Bridge Restoration | PE | 185 | 2034-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 68926 | SR 106 over Round Pond Creek | 106 | 573 | Bridge Restoration | CON | STP | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640000 | 640000
Northern Tier | 4 | Susquehanna | 68926 | SR 106 over Round Pond Creek | 106 | 573 | Bridge Restoration | CON | 581 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 160000
Northern Tier | 4 | Susquehanna | 68936 | SR 167 over Martins Creek | 167 | D54 | Bridge Replacement | CON | PRTCT | 2025-01-09 | 2025-01-09 | 7775086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7775086
Northern Tier | 4 | Susquehanna | 68940 | SR 171 over Lackawanna River | 171 | 573 | Bridge Restoration | PE | STP | 2027-07-15 |  | 92000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000
Northern Tier | 4 | Susquehanna | 68940 | SR 171 over Lackawanna River | 171 | 573 | Bridge Restoration | PE | 185 | 2027-07-15 |  | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000
Northern Tier | 4 | Susquehanna | 68940 | SR 171 over Lackawanna River | 171 | 573 | Bridge Restoration | CON | STP | 2027-07-15 |  | 0 | 95000 | 705000 | 1600000 | 0 | 0 | 0 | 0 | 0 | 2400000
Northern Tier | 4 | Susquehanna | 68940 | SR 171 over Lackawanna River | 171 | 573 | Bridge Restoration | CON | 185 | 2027-07-15 |  | 0 | 23750 | 176250 | 400000 | 0 | 0 | 0 | 0 | 0 | 600000
Northern Tier | 4 | Susquehanna | 69008 | SR 1017 over Tributary to Susquehanna River | 1017 | 571 | Bridge Restoration | PE | 185 | 2032-10-01 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 69008 | SR 1017 over Tributary to Susquehanna River | 1017 | 571 | Bridge Restoration | CON | 185 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northern Tier | 4 | Susquehanna | 69012 | SR 2008 over Dundaff Creek | 2008 | 570 | Bridge Restoration | PE | STP | 2032-10-01 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 69012 | SR 2008 over Dundaff Creek | 2008 | 570 | Bridge Restoration | PE | 185 | 2032-10-01 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 69012 | SR 2008 over Dundaff Creek | 2008 | 570 | Bridge Restoration | CON | STP | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640000 | 640000
Northern Tier | 4 | Susquehanna | 69012 | SR 2008 over Dundaff Creek | 2008 | 570 | Bridge Restoration | CON | 581 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 160000
Northern Tier | 4 | Susquehanna | 69016 | SR 2016 over Tributary E. Branch Tunkhannock Creek | 2016 | 570 | Bridge Replacement | PE | 185 | 2029-10-11 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 4 | Susquehanna | 69016 | SR 2016 over Tributary E. Branch Tunkhannock Creek | 2016 | 570 | Bridge Replacement | CON | 581 | 2029-10-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546250 | 0 | 546250
Northern Tier | 4 | Susquehanna | 69020 | SR 2017 over Norfolk Southern RR | 2017 | 570 | Bridge Replacement | FD | BOF | 2027-07-15 |  | 0 | 40000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 640000
Northern Tier | 4 | Susquehanna | 69020 | SR 2017 over Norfolk Southern RR | 2017 | 570 | Bridge Replacement | FD | 185 | 2027-07-15 |  | 0 | 10000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Northern Tier | 4 | Susquehanna | 69020 | SR 2017 over Norfolk Southern RR | 2017 | 570 | Bridge Replacement | CON | BOF | 2027-07-15 |  | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
Northern Tier | 4 | Susquehanna | 69020 | SR 2017 over Norfolk Southern RR | 2017 | 570 | Bridge Replacement | CON | 185 | 2027-07-15 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Northern Tier | 4 | Susquehanna | 69023 | SR 2036 over Overflow Channel | 2036 | D50 | Bridge Replacement | FD | 185 | 2026-10-22 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 69023 | SR 2036 over Overflow Channel | 2036 | D50 | Bridge Replacement | CON | 581 | 2026-10-22 |  | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 750000
Northern Tier | 4 | Susquehanna | 73298 | NTier D4 Hwy Reserve |  |  | Reserve Line Item | CON | BOF |  |  | 3000 | 110051 | 48000 | 8000 | 98000 | 140442 | 0 | 261136 | 9836800 | 10505429
Northern Tier | 4 | Susquehanna | 73298 | NTier D4 Hwy Reserve |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 6108 | 163000 | 20000 | 820000 | 2420000 | 20000 | 608000 | 8478000 | 12535108
Northern Tier | 4 | Susquehanna | 73298 | NTier D4 Hwy Reserve |  |  | Reserve Line Item | CON | CRP |  |  | 389265 | 250000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 1800000 | 5139265
Northern Tier | 4 | Susquehanna | 73298 | NTier D4 Hwy Reserve |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 581200 | 581200 | 520055 | 1200 | 1200 | 458345 | 581200 | 2325200 | 5049600
Northern Tier | 4 | Susquehanna | 73298 | NTier D4 Hwy Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 2000 | 219000 | 256000 | 135000 | 135000 | 135000 | 35000 | 135000 | 1541000 | 2593000
Northern Tier | 4 | Susquehanna | 73298 | NTier D4 Hwy Reserve |  |  | Reserve Line Item | CON | STP |  |  | 0 | 57491 | 141320 | 32000 | 997000 | 1827000 | 48750 | 1322000 | 3587000 | 8012561
Northern Tier | 4 | Susquehanna | 73298 | NTier D4 Hwy Reserve |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 51999 | 70250 | 480000 | 468750 | 206250 | 0 | 793284 | 5358000 | 7428533
Northern Tier | 4 | Susquehanna | 73298 | NTier D4 Hwy Reserve |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 2985 | 1524 | 2000 | 262030 | 709000 | 315400 | 329281 | 445000 | 2067220
Northern Tier | 4 | Susquehanna | 79569 | SR 3001 over Carter Creek | 3001 | 550 | Bridge Replacement | CON | 581 | 2023-12-14 | 2023-12-14 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 4 | Susquehanna | 79570 | SR 3004 over Riley Creek | 3004 | 550 | Bridge Replacement | CON | 581 | 2024-10-10 | 2024-10-10 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Northern Tier | 4 | Susquehanna | 79574 | SR 1037 over Tributary to Dubois Creek | 1037 | 552 | Bridge Restoration | PE | 185 | 2030-10-24 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 79574 | SR 1037 over Tributary to Dubois Creek | 1037 | 552 | Bridge Restoration | CON | 581 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 800000
Northern Tier | 4 | Susquehanna | 79578 | SR 3023 over Hortons Creek | 3023 | 554 | Bridge Restoration | PE | BOF | 2030-10-01 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 79578 | SR 3023 over Hortons Creek | 3023 | 554 | Bridge Restoration | PE | 185 | 2030-10-01 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 79578 | SR 3023 over Hortons Creek | 3023 | 554 | Bridge Restoration | CON | BOF | 2030-10-01 |  | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 2000000
Northern Tier | 4 | Susquehanna | 79578 | SR 3023 over Hortons Creek | 3023 | 554 | Bridge Restoration | CON | 185 | 2030-10-01 |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
Northern Tier | 4 | Susquehanna | 85720 | SR 1018 over Tributary Dubois Creek | 1018 | 550 | Bridge Replacement | FD | 581 | 2026-10-22 |  | 315000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315000
Northern Tier | 4 | Susquehanna | 85720 | SR 1018 over Tributary Dubois Creek | 1018 | 550 | Bridge Replacement | ROW | 185 | 2026-10-22 |  | 0 | 51566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51566
Northern Tier | 4 | Susquehanna | 85720 | SR 1018 over Tributary Dubois Creek | 1018 | 550 | Bridge Replacement | CON | 581 | 2026-10-22 |  | 221695 | 378305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Northern Tier | 4 | Susquehanna | 85729 | SR 92 over Tributary Tunkhannock Creek | 92 | 551 | Bridge Replacement | PE | STP | 2027-10-21 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 4 | Susquehanna | 85729 | SR 92 over Tributary Tunkhannock Creek | 92 | 551 | Bridge Replacement | PE | 185 | 2027-10-21 |  | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 4 | Susquehanna | 85729 | SR 92 over Tributary Tunkhannock Creek | 92 | 551 | Bridge Replacement | CON | 581 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747500 | 0 | 747500
Northern Tier | 4 | Susquehanna | 85731 | SR 2043 over Millard Creek | 2043 | 550 | Bridge Restoration | PE | BOF | 2027-02-11 |  | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 220000
Northern Tier | 4 | Susquehanna | 85731 | SR 2043 over Millard Creek | 2043 | 550 | Bridge Restoration | PE | 185 | 2027-02-11 |  | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
Northern Tier | 4 | Susquehanna | 85731 | SR 2043 over Millard Creek | 2043 | 550 | Bridge Restoration | CON | 581 | 2027-02-11 |  | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0 | 170000
Northern Tier | 4 | Susquehanna | 89698 | SR 1018 over Snake Creek | 1018 | 551 | Bridge Replacement | FD | 185 | 2027-03-25 |  | 0 | 0 | 0 | 445000 | 0 | 0 | 0 | 0 | 0 | 445000
Northern Tier | 4 | Susquehanna | 89698 | SR 1018 over Snake Creek | 1018 | 551 | Bridge Replacement | ROW | 581 | 2027-03-25 |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Northern Tier | 4 | Susquehanna | 89698 | SR 1018 over Snake Creek | 1018 | 551 | Bridge Replacement | CON | BRIP | 2027-03-25 |  | 0 | 1000000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
Northern Tier | 4 | Susquehanna | 89698 | SR 1018 over Snake Creek | 1018 | 551 | Bridge Replacement | CON | 185 | 2027-03-25 |  | 0 | 250000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Northern Tier | 4 | Susquehanna | 89699 | SR 2067 over Tunkhannock Creek | 2067 | 552 | Bridge Replacement | PE | BOF | 2032-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 4 | Susquehanna | 89699 | SR 2067 over Tunkhannock Creek | 2067 | 552 | Bridge Replacement | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 4 | Susquehanna | 89699 | SR 2067 over Tunkhannock Creek | 2067 | 552 | Bridge Replacement | FD | BOF | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 280000
Northern Tier | 4 | Susquehanna | 89699 | SR 2067 over Tunkhannock Creek | 2067 | 552 | Bridge Replacement | FD | 185 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 70000
Northern Tier | 4 | Susquehanna | 89699 | SR 2067 over Tunkhannock Creek | 2067 | 552 | Bridge Replacement | CON | BOF | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1576064 | 0 | 1576064
Northern Tier | 4 | Susquehanna | 89699 | SR 2067 over Tunkhannock Creek | 2067 | 552 | Bridge Replacement | CON | 185 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394016 | 0 | 394016
Northern Tier | 4 | Susquehanna | 89705 | SR 171 over Denton Creek | 171 | 552 | Bridge Replacement | PE | STP | 2032-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 89705 | SR 171 over Denton Creek | 171 | 552 | Bridge Replacement | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 89705 | SR 171 over Denton Creek | 171 | 552 | Bridge Replacement | CON | BRIP | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
Northern Tier | 4 | Susquehanna | 89710 | SR 11 over Tributary to Susquehanna River | 11 | P11 | Bridge Restoration | PE | STP | 2027-02-18 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 89710 | SR 11 over Tributary to Susquehanna River | 11 | P11 | Bridge Restoration | PE | 185 | 2027-02-18 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 89710 | SR 11 over Tributary to Susquehanna River | 11 | P11 | Bridge Restoration | FD | 581 | 2027-02-18 |  | 0 | 0 | 625500 | 0 | 0 | 0 | 0 | 0 | 0 | 625500
Northern Tier | 4 | Susquehanna | 89710 | SR 11 over Tributary to Susquehanna River | 11 | P11 | Bridge Restoration | CON | STP | 2027-02-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 800000
Northern Tier | 4 | Susquehanna | 89710 | SR 11 over Tributary to Susquehanna River | 11 | P11 | Bridge Restoration | CON | 185 | 2027-02-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 200000
Northern Tier | 4 | Susquehanna | 89711 | SR 2046 over West Branch Lackawanna River | 2046 | D50 | Bridge Replacement | PE | 185 | 2030-10-24 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 4 | Susquehanna | 89711 | SR 2046 over West Branch Lackawanna River | 2046 | D50 | Bridge Replacement | FD | 185 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000
Northern Tier | 4 | Susquehanna | 89711 | SR 2046 over West Branch Lackawanna River | 2046 | D50 | Bridge Replacement | CON | 581 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
Northern Tier | 4 | Susquehanna | 89908 | SR 2022 over Branch Martins Creek | 2022 | D50 | Bridge Replacement | PE | 185 | 2034-10-01 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 4 | Susquehanna | 89908 | SR 2022 over Branch Martins Creek | 2022 | D50 | Bridge Replacement | CON | 581 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 234600 | 0 | 0 | 234600
Northern Tier | 4 | Susquehanna | 94741 | SR 11 Shoulder / ELRS. | 11 | RS2 | Safety Improvement | CON | HSIP | 2024-12-12 | 2024-12-12 | 1652657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1652657
Northern Tier | 4 | Susquehanna | 94741 | SR 11 Shoulder / ELRS. | 11 | RS2 | Safety Improvement | CON | STR | 2024-12-12 | 2024-12-12 | 1227955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1227955
Northern Tier | 4 | Susquehanna | 96207 | SR 2067 over Bell Creek | 2067 | 555 | Bridge Replacement | PE | 581 | 2038-10-01 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 96207 | SR 2067 over Bell Creek | 2067 | 555 | Bridge Replacement | CON | 581 | 2038-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501169 | 0 | 501169
Northern Tier | 4 | Susquehanna | 96728 | SR 11 over Tannery Street | 11 | D51 | Bridge Replacement | FD | STP | 2027-01-14 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 96728 | SR 11 over Tannery Street | 11 | D51 | Bridge Replacement | FD | 185 | 2027-01-14 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 96728 | SR 11 over Tannery Street | 11 | D51 | Bridge Replacement | CON | STP | 2027-01-14 |  | 0 | 0 | 0 | 200000 | 200000 | 400000 | 0 | 0 | 0 | 800000
Northern Tier | 4 | Susquehanna | 96728 | SR 11 over Tannery Street | 11 | D51 | Bridge Replacement | CON | 185 | 2027-01-14 |  | 0 | 0 | 0 | 50000 | 50000 | 100000 | 0 | 0 | 0 | 200000
Northern Tier | 4 | Susquehanna | 96730 | SR 706 over Branch Wyalusing Creek 2 | 706 | 556 | Bridge Replacement | CON | STP | 2024-07-11 | 2024-07-11 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Northern Tier | 4 | Susquehanna | 96730 | SR 706 over Branch Wyalusing Creek 2 | 706 | 556 | Bridge Replacement | CON | 185 | 2024-07-11 | 2024-07-11 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 4 | Susquehanna | 96732 | SR 1018 over Norfolk Southern RR | 1018 | D50 | Bridge Replacement | PE | STP | 2027-04-08 |  | 0 | 205000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205000
Northern Tier | 4 | Susquehanna | 96732 | SR 1018 over Norfolk Southern RR | 1018 | D50 | Bridge Replacement | FD | BRIP | 2027-04-08 |  | 0 | 570000 | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 755000
Northern Tier | 4 | Susquehanna | 96732 | SR 1018 over Norfolk Southern RR | 1018 | D50 | Bridge Replacement | ROW | BRIP | 2027-04-08 |  | 0 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000
Northern Tier | 4 | Susquehanna | 96732 | SR 1018 over Norfolk Southern RR | 1018 | D50 | Bridge Replacement | CON | BRIP | 2027-04-08 |  | 0 | 0 | 640000 | 2400000 | 0 | 0 | 0 | 0 | 0 | 3040000
Northern Tier | 4 | Susquehanna | 96732 | SR 1018 over Norfolk Southern RR | 1018 | D50 | Bridge Replacement | CON | 581 | 2027-04-08 |  | 0 | 0 | 160000 | 760000 | 0 | 0 | 0 | 0 | 0 | 920000
Northern Tier | 4 | Susquehanna | 96733 | SR 167 over Hop Bottom Creek | 167 | D52 | Bridge Restoration | PE | STP | 2034-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 96733 | SR 167 over Hop Bottom Creek | 167 | D52 | Bridge Restoration | PE | 185 | 2034-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 96733 | SR 167 over Hop Bottom Creek | 167 | D52 | Bridge Restoration | CON | STP | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640000 | 640000
Northern Tier | 4 | Susquehanna | 96733 | SR 167 over Hop Bottom Creek | 167 | D52 | Bridge Restoration | CON | 581 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 160000
Northern Tier | 4 | Susquehanna | 96735 | SR 3029 over Forest Lake Creek | 3029 | D50 | Bridge Replacement | PE | BOF | 2034-10-01 |  | 0 | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 220000
Northern Tier | 4 | Susquehanna | 96735 | SR 3029 over Forest Lake Creek | 3029 | D50 | Bridge Replacement | PE | 185 | 2034-10-01 |  | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 55000
Northern Tier | 4 | Susquehanna | 96735 | SR 3029 over Forest Lake Creek | 3029 | D50 | Bridge Replacement | CON | BOF | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 727558 | 0 | 0 | 0 | 727558
Northern Tier | 4 | Susquehanna | 96735 | SR 3029 over Forest Lake Creek | 3029 | D50 | Bridge Replacement | CON | 185 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 181890 | 0 | 0 | 0 | 181890
Northern Tier | 4 | Susquehanna | 100452 | SR 4002 over Snake Creek | 4002 | D51 | Bridge Restoration | PE | BOF | 2034-11-01 |  | 0 | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 220000
Northern Tier | 4 | Susquehanna | 100452 | SR 4002 over Snake Creek | 4002 | D51 | Bridge Restoration | PE | 185 | 2034-11-01 |  | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 55000
Northern Tier | 4 | Susquehanna | 100452 | SR 4002 over Snake Creek | 4002 | D51 | Bridge Restoration | CON | 185 | 2034-11-01 |  | 0 | 0 | 0 | 0 | 0 | 290950 | 0 | 0 | 0 | 290950
Northern Tier | 4 | Susquehanna | 100596 | SR 1049 over Branch of Snake Creek | 1049 | D50 | Bridge Replacement | FD | 581 | 2027-03-25 |  | 328305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328305
Northern Tier | 4 | Susquehanna | 100596 | SR 1049 over Branch of Snake Creek | 1049 | D50 | Bridge Replacement | ROW | 581 | 2027-03-25 |  | 0 | 0 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 85000
Northern Tier | 4 | Susquehanna | 100596 | SR 1049 over Branch of Snake Creek | 1049 | D50 | Bridge Replacement | CON | 581 | 2027-03-25 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
Northern Tier | 4 | Susquehanna | 101043 | SR 171 over High Bridge Creek | 171 | D52 | Bridge Restoration | PE | 581 | 2027-11-04 |  | 290350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290350
Northern Tier | 4 | Susquehanna | 101043 | SR 171 over High Bridge Creek | 171 | D52 | Bridge Restoration | FD | STP | 2027-11-04 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 101043 | SR 171 over High Bridge Creek | 171 | D52 | Bridge Restoration | FD | 185 | 2027-11-04 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 101043 | SR 171 over High Bridge Creek | 171 | D52 | Bridge Restoration | CON | 185 | 2027-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Northern Tier | 4 | Susquehanna | 107009 | Bridge Preservation Ln Item |  |  | Reserve Line Item | PE | BRIP |  |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 109879 | SR 267 over Branch Little Meshoppen Creek | 267 | 554 | Bridge Replacement | PE | STP | 2029-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 4 | Susquehanna | 109879 | SR 267 over Branch Little Meshoppen Creek | 267 | 554 | Bridge Replacement | PE | 185 | 2029-10-01 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 4 | Susquehanna | 109879 | SR 267 over Branch Little Meshoppen Creek | 267 | 554 | Bridge Replacement | CON | 581 | 2029-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563000 | 0 | 563000
Northern Tier | 4 | Susquehanna | 109880 | SR 706 over Snell Creek | 706 | 553 | Bridge Replacement | CON | BRIP | 2024-07-11 | 2024-07-11 | 678892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 678892
Northern Tier | 4 | Susquehanna | 109880 | SR 706 over Snell Creek | 706 | 553 | Bridge Replacement | CON | 185 | 2024-07-11 | 2024-07-11 | 169723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169723
Northern Tier | 4 | Susquehanna | 109882 | SR 2023 over Outlet Lewis Lake | 2023 | 550 | Bridge Replacement | CON | 581 | 2026-06-04 |  | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 2000000
Northern Tier | 4 | Susquehanna | 112539 | SR 2046 over Tunkhannock Creek | 2046 | 570 | Bridge Restoration | PE | 185 | 2025-05-08 | 2025-05-08 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 4 | Susquehanna | 112539 | SR 2046 over Tunkhannock Creek | 2046 | 570 | Bridge Restoration | CON | 581 | 2025-05-08 | 2025-05-08 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Northern Tier | 4 | Susquehanna | 112737 | SR 11, SR 492, SR 848 Intersection Improvement | 11 | IMP | Safety Improvement | PE | STP | 2027-10-07 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 112737 | SR 11, SR 492, SR 848 Intersection Improvement | 11 | IMP | Safety Improvement | FD | STP | 2027-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 350000
Northern Tier | 4 | Susquehanna | 112737 | SR 11, SR 492, SR 848 Intersection Improvement | 11 | IMP | Safety Improvement | CON | STP | 2027-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 1200000
Northern Tier | 4 | Susquehanna | 113986 | Guiderail Mash Upgrades - N. Tier |  |  | Reserve Line Item | CON | 581 |  |  | 95592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95592
Northern Tier | 4 | Susquehanna | 114026 | T-821 (Old Route 11) over DLW Railroad | 7212 | BRG | Bridge Replacement | PE | BOF | 2027-10-21 |  | 527983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 527983
Northern Tier | 4 | Susquehanna | 114026 | T-821 (Old Route 11) over DLW Railroad | 7212 | BRG | Bridge Replacement | PE | 183 | 2027-10-21 |  | 98997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98997
Northern Tier | 4 | Susquehanna | 114026 | T-821 (Old Route 11) over DLW Railroad | 7212 | BRG | Bridge Replacement | PE | LOC | 2027-10-21 |  | 32999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32999
Northern Tier | 4 | Susquehanna | 114026 | T-821 (Old Route 11) over DLW Railroad | 7212 | BRG | Bridge Replacement | FD | BOF | 2027-10-21 |  | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 600000
Northern Tier | 4 | Susquehanna | 114026 | T-821 (Old Route 11) over DLW Railroad | 7212 | BRG | Bridge Replacement | FD | 183 | 2027-10-21 |  | 0 | 0 | 0 | 112500 | 0 | 0 | 0 | 0 | 0 | 112500
Northern Tier | 4 | Susquehanna | 114026 | T-821 (Old Route 11) over DLW Railroad | 7212 | BRG | Bridge Replacement | FD | LOC | 2027-10-21 |  | 0 | 0 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 37500
Northern Tier | 4 | Susquehanna | 114029 | Asset Management Phase 2 Ln Item |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 1000000
Northern Tier | 4 | Susquehanna | 114079 | Susquehanna County Paving | 106 | PAV | Highway Restoration | CON | 581 | 2025-06-05 | 2025-06-05 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Northern Tier | 4 | Susquehanna | 114911 | I-81 Guiderail/Cable Median Barrier | 81 | CM2 | Safety Improvement | CON | HSIP | 2025-02-27 | 2025-02-27 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
Northern Tier | 4 | Susquehanna | 116705 | SR 11 over Branch of Martins Creek | 11 | 552 | Bridge Restoration | PE | STP | 2032-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 116705 | SR 11 over Branch of Martins Creek | 11 | 552 | Bridge Restoration | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 116705 | SR 11 over Branch of Martins Creek | 11 | 552 | Bridge Restoration | CON | STP | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northern Tier | 4 | Susquehanna | 116705 | SR 11 over Branch of Martins Creek | 11 | 552 | Bridge Restoration | CON | 581 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northern Tier | 4 | Susquehanna | 116706 | SR 11 over Tributary to Salt Lick Creek | 11 | 553 | Bridge Restoration | PE | STP | 2032-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 116706 | SR 11 over Tributary to Salt Lick Creek | 11 | 553 | Bridge Restoration | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 116706 | SR 11 over Tributary to Salt Lick Creek | 11 | 553 | Bridge Restoration | CON | BRIP | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000
Northern Tier | 4 | Susquehanna | 116707 | SR 11 over Norfolk Southern Railroad | 11 | P10 | Bridge Restoration | PE | STP | 2027-10-01 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 4 | Susquehanna | 116707 | SR 11 over Norfolk Southern Railroad | 11 | P10 | Bridge Restoration | PE | 185 | 2027-10-01 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 4 | Susquehanna | 116707 | SR 11 over Norfolk Southern Railroad | 11 | P10 | Bridge Restoration | FD | 185 | 2027-10-01 |  | 0 | 0 | 0 | 0 | 269750 | 0 | 0 | 0 | 0 | 269750
Northern Tier | 4 | Susquehanna | 116707 | SR 11 over Norfolk Southern Railroad | 11 | P10 | Bridge Restoration | CON | 581 | 2027-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 4000000
Northern Tier | 4 | Susquehanna | 116708 | SR 92 over Drinkers Creek | 92 | 553 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 4 | Susquehanna | 116708 | SR 92 over Drinkers Creek | 92 | 553 | Bridge Restoration | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 800000
Northern Tier | 4 | Susquehanna | 116709 | SR 92 over Branch of Drinkers Creek | 92 | 554 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 4 | Susquehanna | 116709 | SR 92 over Branch of Drinkers Creek | 92 | 554 | Bridge Restoration | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 800000
Northern Tier | 4 | Susquehanna | 116710 | SR 167 over East Branch of Wyalusing Creek | 167 | 554 | Bridge Restoration | PE | 185 | 2030-10-24 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 116710 | SR 167 over East Branch of Wyalusing Creek | 167 | 554 | Bridge Restoration | CON | 185 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northern Tier | 4 | Susquehanna | 116711 | SR 492 over Branch of Butler Creek | 492 | 550 | Bridge Restoration | PE | STP | 2032-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 116711 | SR 492 over Branch of Butler Creek | 492 | 550 | Bridge Restoration | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 116711 | SR 492 over Branch of Butler Creek | 492 | 550 | Bridge Restoration | CON | 581 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 800000
Northern Tier | 4 | Susquehanna | 116712 | SR 1002 over Tunkhannock Creek | 1002 | 550 | Bridge Restoration | PE | STP | 2033-10-01 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 116712 | SR 1002 over Tunkhannock Creek | 1002 | 550 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 116712 | SR 1002 over Tunkhannock Creek | 1002 | 550 | Bridge Restoration | CON | BRIP | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 800000
Northern Tier | 4 | Susquehanna | 116713 | SR 1010 over Bedbug Creek | 1010 | 552 | Bridge Restoration | PE | 185 | 2030-10-24 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 116713 | SR 1010 over Bedbug Creek | 1010 | 552 | Bridge Restoration | CON | 581 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northern Tier | 4 | Susquehanna | 116714 | SR 1011 over East Branch of Hemlock Creek | 1011 | 553 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 116714 | SR 1011 over East Branch of Hemlock Creek | 1011 | 553 | Bridge Restoration | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northern Tier | 4 | Susquehanna | 116715 | SR 2020 over Tower Creek | 2020 | 550 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 116715 | SR 2020 over Tower Creek | 2020 | 550 | Bridge Restoration | CON | 185 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 800000
Northern Tier | 4 | Susquehanna | 116716 | SR 2020 over Outlet of Acre Lake | 2020 | 551 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 116716 | SR 2020 over Outlet of Acre Lake | 2020 | 551 | Bridge Restoration | CON | 185 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 794910 | 0 | 0 | 0 | 794910
Northern Tier | 4 | Susquehanna | 116717 | SR 2053 over Johnson Pond Creek | 2053 | 550 | Bridge Restoration | PE | BOF | 2033-10-01 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 116717 | SR 2053 over Johnson Pond Creek | 2053 | 550 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 116717 | SR 2053 over Johnson Pond Creek | 2053 | 550 | Bridge Restoration | CON | BOF | 2033-10-01 |  | 0 | 0 | 0 | 0 | 650000 | 0 | 0 | 0 | 0 | 650000
Northern Tier | 4 | Susquehanna | 116717 | SR 2053 over Johnson Pond Creek | 2053 | 550 | Bridge Restoration | CON | 185 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
Northern Tier | 4 | Susquehanna | 116718 | SR 2063 over Branch of Leslie Creek | 2063 | 550 | Bridge Restoration | PE | 185 | 2033-10-10 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 116718 | SR 2063 over Branch of Leslie Creek | 2063 | 550 | Bridge Restoration | CON | 185 | 2033-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 800000
Northern Tier | 4 | Susquehanna | 116719 | SR 3050 over Elk Lake Stream | 3050 | 550 | Bridge Restoration | PE | BOF | 2030-10-01 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Susquehanna | 116719 | SR 3050 over Elk Lake Stream | 3050 | 550 | Bridge Restoration | PE | 185 | 2030-10-01 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 116719 | SR 3050 over Elk Lake Stream | 3050 | 550 | Bridge Restoration | CON | BRIP | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 400000 | 0 | 2000000
Northern Tier | 4 | Susquehanna | 116719 | SR 3050 over Elk Lake Stream | 3050 | 550 | Bridge Restoration | CON | 185 | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 100000 | 0 | 500000
Northern Tier | 4 | Susquehanna | 116720 | SR 4016 over Choconut Creek | 4016 | 550 | Bridge Restoration | PE | BOF | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 0 | 0 | 280000
Northern Tier | 4 | Susquehanna | 116720 | SR 4016 over Choconut Creek | 4016 | 550 | Bridge Restoration | PE | 185 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 70000
Northern Tier | 4 | Susquehanna | 116720 | SR 4016 over Choconut Creek | 4016 | 550 | Bridge Restoration | FD | BOF | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 0 | 0 | 240000
Northern Tier | 4 | Susquehanna | 116720 | SR 4016 over Choconut Creek | 4016 | 550 | Bridge Restoration | FD | 581 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 60000
Northern Tier | 4 | Susquehanna | 116720 | SR 4016 over Choconut Creek | 4016 | 550 | Bridge Restoration | CON | BOF | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 788000 | 0 | 0 | 788000
Northern Tier | 4 | Susquehanna | 116720 | SR 4016 over Choconut Creek | 4016 | 550 | Bridge Restoration | CON | BRIP | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412000 | 0 | 412000
Northern Tier | 4 | Susquehanna | 116720 | SR 4016 over Choconut Creek | 4016 | 550 | Bridge Restoration | CON | 581 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 197000 | 103000 | 0 | 300000
Northern Tier | 4 | Susquehanna | 116732 | SR 4005 over McCormick Run | 4005 | 550 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 116732 | SR 4005 over McCormick Run | 4005 | 550 | Bridge Restoration | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northern Tier | 4 | Susquehanna | 117297 | Asset Management 3 | 11 | AST | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Northern Tier | 4 | Susquehanna | 117297 | Asset Management 3 | 11 | AST | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 118120 | SR 374 over Outlet of Lowe Lake | 374 | 553 | Bridge Replacement | PE | 185 | 2026-07-16 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Susquehanna | 118120 | SR 374 over Outlet of Lowe Lake | 374 | 553 | Bridge Replacement | CON | 581 | 2026-07-16 |  | 0 | 715000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715000
Northern Tier | 4 | Susquehanna | 118218 | Susq County NYSW Corridor Crossing | 1017 | RRX | Rail Highway Grade Crossing | CON | RRX | 2026-07-01 |  | 0 | 0 | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 360000
Northern Tier | 4 | Susquehanna | 118433 | Harmony Township Trail Pedestrian Enhancement TASA |  | TAP | Transportation Enhancement | CON | TAP | 2025-09-11 | 2025-09-11 | 1350595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350595
Northern Tier | 4 | Susquehanna | 119606 | SR 2073 Pipe Replacement | 2073 | P01 | 409 Expanded Maintenance | PE | 582 |  |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 4 | Susquehanna | 120412 | State Route 374 over East Branch Tunkhannock Creek | 374 | 200 | Bridge Replacement | PE | 185 | 2026-03-12 | 2026-03-12 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Northern Tier | 4 | Susquehanna | 120412 | State Route 374 over East Branch Tunkhannock Creek | 374 | 200 | Bridge Replacement | CON | 581 | 2026-03-12 | 2026-03-12 | 0 | 190000 | 1076476 | 0 | 0 | 0 | 0 | 0 | 0 | 1266476
Northern Tier | 4 | Susquehanna | 121058 | Fed Aid Paving 4-24-FP1 | 11 | FP1 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
Northern Tier | 4 | Susquehanna | 121058 | Fed Aid Paving 4-24-FP1 | 11 | FP1 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000
Northern Tier | 4 | Susquehanna | 121178 | Susq/Wyoming High Friction Surface Treatment | 171 | HFS | Safety Improvement | PE | HSIP | 2025-06-05 | 2025-06-05 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Susquehanna | 121178 | Susq/Wyoming High Friction Surface Treatment | 171 | HFS | Safety Improvement | CON | HSIP | 2025-06-05 | 2025-06-05 | 615866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615866
Northern Tier | 4 | Susquehanna | 121292 | I-81 Cameras - Susquehanna County | 81 | CAM | Intelligent Transportation System | CON | CRP | 2025-02-27 | 2025-02-27 | 234706 | 173506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408212
Northern Tier | 4 | Susquehanna | 121292 | I-81 Cameras - Susquehanna County | 81 | CAM | Intelligent Transportation System | CON | CRP | 2025-02-27 | 2025-02-27 | 49735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49735
Northern Tier | 4 | Susquehanna | 121292 | I-81 Cameras - Susquehanna County | 81 | CAM | Intelligent Transportation System | CON | CRPU | 2025-02-27 | 2025-02-27 | 58677 | 43376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102053
Northern Tier | 4 | Susquehanna | 122226 | Forest City Borough Streetscape | 171 | MTM | MultiModal | CON | 411 |  |  | 0 | 212682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212682
Northern Tier | 4 | Susquehanna | 122246 | Creamery Hill Road over Elk Lake Stream - SCB 37 | 7224 | LOC | Bridge Restoration | PE | 183 |  |  | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000
Northern Tier | 4 | Susquehanna | 122246 | Creamery Hill Road over Elk Lake Stream - SCB 37 | 7224 | LOC | Bridge Restoration | PE | LOC |  |  | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000
Northern Tier | 4 | Susquehanna | 122494 | ROW Claims Assistance - N. Tier |  |  | Reserve Line Item | ROW | 581 |  |  | 55500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55500
Northern Tier | 4 | Susquehanna | 122919 | D&H Bucks Falls North - Thompson |  | TAP | Transportation Enhancement | CON | CRP | 2026-01-30 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 4 | Susquehanna | 124000 | SR 247 over D&H Railroad | 247 | P01 | Bridge Preservation - State Funded | CON | 185 | 2026-03-27 | 2025-02-27 | 0 | 58000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 76000
Northern Tier | 4 | Wyoming | 10137 | SR 1015 over Field Brook Creek | 1015 | 770 | Bridge Replacement | FD | BOF | 2026-03-12 | 2026-03-12 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Wyoming | 10137 | SR 1015 over Field Brook Creek | 1015 | 770 | Bridge Replacement | FD | 185 | 2026-03-12 | 2026-03-12 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Wyoming | 10137 | SR 1015 over Field Brook Creek | 1015 | 770 | Bridge Replacement | UTL | 185 | 2026-03-12 | 2026-03-12 | 0 | 20500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20500
Northern Tier | 4 | Wyoming | 10137 | SR 1015 over Field Brook Creek | 1015 | 770 | Bridge Replacement | CON | BOF | 2026-03-12 | 2026-03-12 | 0 | 1640000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000
Northern Tier | 4 | Wyoming | 10137 | SR 1015 over Field Brook Creek | 1015 | 770 | Bridge Replacement | CON | 185 | 2026-03-12 | 2026-03-12 | 0 | 410000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
Northern Tier | 4 | Wyoming | 10138 | SR 2012 over Tunkhannock Creek | 2012 | 772 | Bridge Replacement | CON | BOF | 2025-02-27 | 2025-02-27 | 1109159 | 30841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1140000
Northern Tier | 4 | Wyoming | 10138 | SR 2012 over Tunkhannock Creek | 2012 | 772 | Bridge Replacement | CON | BRIP | 2025-02-27 | 2025-02-27 | 0 | 0 | 692000 | 0 | 0 | 0 | 0 | 0 | 0 | 692000
Northern Tier | 4 | Wyoming | 10138 | SR 2012 over Tunkhannock Creek | 2012 | 772 | Bridge Replacement | CON | 185 | 2025-02-27 | 2025-02-27 | 100000 | 10000 | 223000 | 125000 | 0 | 0 | 0 | 0 | 0 | 458000
Northern Tier | 4 | Wyoming | 10139 | SR 267 over Meshoppen Creek | 267 | 770 | Bridge Replacement | FD | STP | 2027-05-27 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Wyoming | 10139 | SR 267 over Meshoppen Creek | 267 | 770 | Bridge Replacement | FD | 185 | 2027-05-27 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Wyoming | 10139 | SR 267 over Meshoppen Creek | 267 | 770 | Bridge Replacement | CON | 581 | 2027-05-27 |  | 0 | 0 | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 3500000
Northern Tier | 4 | Wyoming | 10162 | SR 3003 over Sugar Hollow Creek | 3003 | D01 | Bridge Replacement | PE | STP | 2034-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 4 | Wyoming | 10162 | SR 3003 over Sugar Hollow Creek | 3003 | D01 | Bridge Replacement | PE | 185 | 2034-10-01 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 4 | Wyoming | 10162 | SR 3003 over Sugar Hollow Creek | 3003 | D01 | Bridge Replacement | CON | 581 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1456000 | 1456000
Northern Tier | 4 | Wyoming | 10174 | SR 92 over Monroe Creek | 92 | 772 | Bridge Replacement | CON | BRIP | 2025-05-22 | 2025-05-22 | 0 | 0 | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 540000
Northern Tier | 4 | Wyoming | 10174 | SR 92 over Monroe Creek | 92 | 772 | Bridge Replacement | CON | PRTCT | 2025-05-22 | 2025-05-22 | 2882000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2882000
Northern Tier | 4 | Wyoming | 10174 | SR 92 over Monroe Creek | 92 | 772 | Bridge Replacement | CON | 185 | 2025-05-22 | 2025-05-22 | 200000 | 175000 | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 560000
Northern Tier | 4 | Wyoming | 10181 | SR 92 over Field Brook | 92 | 751 | Bridge Replacement | PE | STP | 2028-10-19 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 4 | Wyoming | 10181 | SR 92 over Field Brook | 92 | 751 | Bridge Replacement | CON | STP | 2028-10-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 897000 | 0 | 0 | 897000
Northern Tier | 4 | Wyoming | 10192 | SR 3002 over Bowmans Creek | 3002 | 750 | Bridge Replacement | CON | BRIP | 2024-12-12 | 2024-12-12 | 2601524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2601524
Northern Tier | 4 | Wyoming | 10192 | SR 3002 over Bowmans Creek | 3002 | 750 | Bridge Replacement | CON | STP | 2024-12-12 | 2024-12-12 | 222000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222000
Northern Tier | 4 | Wyoming | 10192 | SR 3002 over Bowmans Creek | 3002 | 750 | Bridge Replacement | CON | 185 | 2024-12-12 | 2024-12-12 | 490777 | 173223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 664000
Northern Tier | 4 | Wyoming | 10222 | SR 6 over Branch of Tunkhannock Creek | 6 | 751 | Bridge Replacement | PE | NHPP | 2030-10-01 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Northern Tier | 4 | Wyoming | 10222 | SR 6 over Branch of Tunkhannock Creek | 6 | 751 | Bridge Replacement | CON | NHPP | 2030-10-01 |  | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 1000000 | 1000000 | 0 | 4000000
Northern Tier | 4 | Wyoming | 10223 | SR 6 over South Branch of Tunkhannock Creek | 6 | 776 | Bridge Restoration | FD | NHPP | 2027-01-14 |  | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000
Northern Tier | 4 | Wyoming | 10223 | SR 6 over South Branch of Tunkhannock Creek | 6 | 776 | Bridge Restoration | ROW | NHPP | 2027-01-14 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 4 | Wyoming | 10223 | SR 6 over South Branch of Tunkhannock Creek | 6 | 776 | Bridge Restoration | UTL | NHPP | 2027-01-14 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Wyoming | 10223 | SR 6 over South Branch of Tunkhannock Creek | 6 | 776 | Bridge Restoration | CON | NHPP | 2027-01-14 |  | 0 | 1200000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000
Northern Tier | 4 | Wyoming | 10223 | SR 6 over South Branch of Tunkhannock Creek | 6 | 776 | Bridge Restoration | CON | 185 | 2027-01-14 |  | 0 | 0 | 162500 | 0 | 0 | 0 | 0 | 0 | 0 | 162500
Northern Tier | 4 | Wyoming | 10223 | SR 6 over South Branch of Tunkhannock Creek | 6 | 776 | Bridge Restoration | CON | 581 | 2027-01-14 |  | 0 | 300000 | 137500 | 0 | 0 | 0 | 0 | 0 | 0 | 437500
Northern Tier | 4 | Wyoming | 10224 | SR 29 over Inlet Lake Carey | 29 | D51 | Bridge Replacement | UTL | 581 | 2024-07-25 | 2024-07-25 | 97113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97113
Northern Tier | 4 | Wyoming | 10224 | SR 29 over Inlet Lake Carey | 29 | D51 | Bridge Replacement | CON | STP | 2024-07-25 | 2024-07-25 | 0 | 580000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580000
Northern Tier | 4 | Wyoming | 10224 | SR 29 over Inlet Lake Carey | 29 | D51 | Bridge Replacement | CON | 185 | 2024-07-25 | 2024-07-25 | 0 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145000
Northern Tier | 4 | Wyoming | 10228 | SR 92 over Fitch Creek | 92 | D50 | Bridge Replacement | UTL | 581 | 2025-11-06 | 2025-11-06 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Northern Tier | 4 | Wyoming | 10228 | SR 92 over Fitch Creek | 92 | D50 | Bridge Replacement | CON | STP | 2025-11-06 | 2025-11-06 | 251045 | 1368955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620000
Northern Tier | 4 | Wyoming | 10228 | SR 92 over Fitch Creek | 92 | D50 | Bridge Replacement | CON | 581 | 2025-11-06 | 2025-11-06 | 62761 | 342239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405000
Northern Tier | 4 | Wyoming | 10232 | SR 307 over Branch Osterhout Creek | 307 | 750 | Bridge Replacement | PE | 581 | 2027-04-08 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 4 | Wyoming | 10232 | SR 307 over Branch Osterhout Creek | 307 | 750 | Bridge Replacement | CON | STP | 2027-04-08 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Northern Tier | 4 | Wyoming | 10232 | SR 307 over Branch Osterhout Creek | 307 | 750 | Bridge Replacement | CON | 185 | 2027-04-08 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northern Tier | 4 | Wyoming | 68808 | SR 2001 over South Run Creek C-3 | 2001 | 772 | Bridge Replacement | PE | BOF | 2030-11-07 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 4 | Wyoming | 68808 | SR 2001 over South Run Creek C-3 | 2001 | 772 | Bridge Replacement | PE | 185 | 2030-11-07 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 4 | Wyoming | 68808 | SR 2001 over South Run Creek C-3 | 2001 | 772 | Bridge Replacement | CON | BOF | 2030-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075200 | 1075200
Northern Tier | 4 | Wyoming | 68808 | SR 2001 over South Run Creek C-3 | 2001 | 772 | Bridge Replacement | CON | 185 | 2030-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269000 | 269000
Northern Tier | 4 | Wyoming | 68841 | SR 2018 over Leonard Creek | 2018 | 770 | Bridge Replacement | PE | 185 | 2035-10-01 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northern Tier | 4 | Wyoming | 68841 | SR 2018 over Leonard Creek | 2018 | 770 | Bridge Replacement | CON | 581 | 2035-10-01 |  | 0 | 0 | 0 | 0 | 434970 | 0 | 0 | 0 | 0 | 434970
Northern Tier | 4 | Wyoming | 68874 | SR 3002 over Stone Run | 3002 | 770 | Bridge Replacement | CON | 581 | 2027-08-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 0 | 1000000
Northern Tier | 4 | Wyoming | 85773 | SR 87 over Little Mehoopany Creek | 87 | D51 | Bridge Restoration | PE | STP | 2035-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 4 | Wyoming | 85773 | SR 87 over Little Mehoopany Creek | 87 | D51 | Bridge Restoration | PE | 185 | 2035-10-01 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 4 | Wyoming | 85773 | SR 87 over Little Mehoopany Creek | 87 | D51 | Bridge Restoration | CON | 581 | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344000 | 0 | 1344000
Northern Tier | 4 | Wyoming | 94688 | SR 29/3003 Sugar Hollow | 29 | 791 | Safety Improvement | CON | HSIP | 2025-01-30 | 2025-01-30 | 812479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812479
Northern Tier | 4 | Wyoming | 94688 | SR 29/3003 Sugar Hollow | 29 | 791 | Safety Improvement | CON | HSIP | 2025-01-30 | 2025-01-30 | 1280784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280784
Northern Tier | 4 | Wyoming | 96746 | SR 2021 over Beaver Creek | 2021 | D50 | Bridge Replacement | CON | STP | 2025-12-11 | 2025-12-11 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 800000
Northern Tier | 4 | Wyoming | 96746 | SR 2021 over Beaver Creek | 2021 | D50 | Bridge Replacement | CON | 581 | 2025-12-11 | 2025-12-11 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 4 | Wyoming | 96747 | SR 4006 over Little Tuscarora Creek | 4006 | 771 | Bridge Replacement | ROW | 581 | 2026-07-16 |  | 141085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141085
Northern Tier | 4 | Wyoming | 96747 | SR 4006 over Little Tuscarora Creek | 4006 | 771 | Bridge Replacement | CON | 581 | 2026-07-16 |  | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Northern Tier | 4 | Wyoming | 96750 | SR 2007 over Tributary to Susquehanna River | 2007 | D52 | Bridge Replacement | CON | 581 | 2025-06-26 | 2025-06-26 | 1728949 | 415051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2144000
Northern Tier | 4 | Wyoming | 96756 | SR 2031 over Outlet Lake Winola | 2031 | D50 | Bridge Replacement | ROW | 581 | 2026-06-18 |  | 33650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33650
Northern Tier | 4 | Wyoming | 96756 | SR 2031 over Outlet Lake Winola | 2031 | D50 | Bridge Replacement | CON | 581 | 2026-06-18 |  | 0 | 1105420 | 94580 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
Northern Tier | 4 | Wyoming | 96757 | SR 4002 over Little Mehoopany Creek | 4002 | D52 | Bridge Replacement | CON | 581 | 2025-11-06 | 2025-11-06 | 1000000 | 600000 | 20000 | 20000 | 350000 | 0 | 0 | 0 | 0 | 1990000
Northern Tier | 4 | Wyoming | 97847 | SR 29 Vertical Correction | 29 | RP1 | Highway Restoration | CON | PRTCT | 2025-01-30 | 2025-01-30 | 1076856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1076856
Northern Tier | 4 | Wyoming | 100469 | SR 4002 over Little Mehoopany Creek | 4002 | D53 | Bridge Restoration | CON | BOF | 2023-04-13 | 2023-04-13 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Wyoming | 100469 | SR 4002 over Little Mehoopany Creek | 4002 | D53 | Bridge Restoration | CON | 185 | 2023-04-13 | 2023-04-13 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Wyoming | 101146 | SR 3001 over Kasson Brook | 3001 | D50 | Bridge Restoration | PE | BOF | 2028-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 4 | Wyoming | 101146 | SR 3001 over Kasson Brook | 3001 | D50 | Bridge Restoration | PE | 185 | 2028-10-01 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 4 | Wyoming | 101146 | SR 3001 over Kasson Brook | 3001 | D50 | Bridge Restoration | CON | BOF | 2028-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910800 | 0 | 910800
Northern Tier | 4 | Wyoming | 101146 | SR 3001 over Kasson Brook | 3001 | D50 | Bridge Restoration | CON | 185 | 2028-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227700 | 0 | 227700
Northern Tier | 4 | Wyoming | 101154 | SR 11 over Branch of Tunkhannock Creek | 11 | D53 | Bridge Replacement | CON | STP | 2025-12-11 | 2025-12-11 | 0 | 600000 | 421680 | 0 | 0 | 0 | 0 | 0 | 0 | 1021680
Northern Tier | 4 | Wyoming | 101154 | SR 11 over Branch of Tunkhannock Creek | 11 | D53 | Bridge Replacement | CON | 581 | 2025-12-11 | 2025-12-11 | 0 | 150000 | 105420 | 0 | 0 | 0 | 0 | 0 | 0 | 255420
Northern Tier | 4 | Wyoming | 107970 | Nicholson Streetscape Project |  |  | Transportation Enhancement | CON | TAP | 2024-06-06 | 2024-06-06 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northern Tier | 4 | Wyoming | 111778 | SR 29 and Keelersburg Road | 29 | 792 | Safety Improvement | PE | 581 | 2027-02-11 |  | 0 | 205000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205000
Northern Tier | 4 | Wyoming | 111778 | SR 29 and Keelersburg Road | 29 | 792 | Safety Improvement | CON | HSIP | 2027-02-11 |  | 0 | 0 | 0 | 61145 | 580000 | 580000 | 122855 | 0 | 0 | 1344000
Northern Tier | 4 | Wyoming | 111778 | SR 29 and Keelersburg Road | 29 | 792 | Safety Improvement | CON | 581 | 2027-02-11 |  | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 1000000
Northern Tier | 4 | Wyoming | 113850 | SR 87 over Branch Mehoopany Creek | 87 | 751 | Bridge Replacement | PE | STP | 2034-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 4 | Wyoming | 113850 | SR 87 over Branch Mehoopany Creek | 87 | 751 | Bridge Replacement | PE | 185 | 2034-10-01 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 4 | Wyoming | 113850 | SR 87 over Branch Mehoopany Creek | 87 | 751 | Bridge Replacement | CON | 581 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Northern Tier | 4 | Wyoming | 116721 | SR 92 over Tributary to Susquehanna River | 92 | 754 | Bridge Restoration | PE | STP | 2033-10-01 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Wyoming | 116721 | SR 92 over Tributary to Susquehanna River | 92 | 754 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Wyoming | 116721 | SR 92 over Tributary to Susquehanna River | 92 | 754 | Bridge Restoration | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northern Tier | 4 | Wyoming | 116722 | SR 2008 over Outlet from American Asphalt | 2008 | 750 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northern Tier | 4 | Wyoming | 116722 | SR 2008 over Outlet from American Asphalt | 2008 | 750 | Bridge Restoration | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 800000
Northern Tier | 4 | Wyoming | 116723 | SR 3001 over Mehoopany Creek | 3001 | 750 | Bridge Restoration | PE | BOF | 2030-11-07 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northern Tier | 4 | Wyoming | 116723 | SR 3001 over Mehoopany Creek | 3001 | 750 | Bridge Restoration | PE | 185 | 2030-11-07 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
Northern Tier | 4 | Wyoming | 116723 | SR 3001 over Mehoopany Creek | 3001 | 750 | Bridge Restoration | CON | BOF | 2030-11-07 |  | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 1600000
Northern Tier | 4 | Wyoming | 116723 | SR 3001 over Mehoopany Creek | 3001 | 750 | Bridge Restoration | CON | 185 | 2030-11-07 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
Northern Tier | 4 | Wyoming | 116724 | SR 4027 over West Branch of Meshoppen Creek | 4027 | 751 | Bridge Restoration | PE | BOF | 2030-01-10 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Wyoming | 116724 | SR 4027 over West Branch of Meshoppen Creek | 4027 | 751 | Bridge Restoration | PE | 183 | 2030-01-10 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Wyoming | 116724 | SR 4027 over West Branch of Meshoppen Creek | 4027 | 751 | Bridge Restoration | CON | BRIP | 2030-01-10 |  | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 1600000
Northern Tier | 4 | Wyoming | 116724 | SR 4027 over West Branch of Meshoppen Creek | 4027 | 751 | Bridge Restoration | CON | 185 | 2030-01-10 |  | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000
Northern Tier | 4 | Wyoming | 117267 | SR 29 over Trib Meshoppen Creek | 29 | PRS | Bridge Preservation - State Funded | PE | STP | 2030-11-07 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northern Tier | 4 | Wyoming | 117267 | SR 29 over Trib Meshoppen Creek | 29 | PRS | Bridge Preservation - State Funded | PE | 185 | 2030-11-07 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northern Tier | 4 | Wyoming | 117267 | SR 29 over Trib Meshoppen Creek | 29 | PRS | Bridge Preservation - State Funded | CON | STP | 2030-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 431250 | 0 | 0 | 431250
Northern Tier | 4 | Wyoming | 121059 | Fed Aid Paving 4-24-FP2 | 6 | FP2 | Highway Restoration | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
Northern Tier | 4 | Wyoming | 121059 | Fed Aid Paving 4-24-FP2 | 6 | FP2 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Northern Tier | 4 | Wyoming | 121059 | Fed Aid Paving 4-24-FP2 | 6 | FP2 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000
Northern Tier | 4 | Wyoming | 121536 | Clinton TWP & Factoryville Borough Joint Trail |  | TAS | Transportation Enhancement | CON | TAP | 2026-05-21 |  | 851439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851439
Northwest | 1 | Crawford | 307 | Plank Road - Act 13 | 7209 | ACT | Bridge Restoration | CON | ACT13 |  |  | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000
Northwest | 1 | Crawford | 323 | Wightman Road Bridge (T-620) | 7210 | L00 | Bridge Preservation - Federal | CON | BOF | 2027-01-01 |  | 0 | 462000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462000
Northwest | 1 | Crawford | 323 | Wightman Road Bridge (T-620) | 7210 | L00 | Bridge Preservation - Federal | CON | 183 | 2027-01-01 |  | 0 | 86625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86625
Northwest | 1 | Crawford | 323 | Wightman Road Bridge (T-620) | 7210 | L00 | Bridge Preservation - Federal | CON | LOC | 2027-01-01 |  | 34375 | 28875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63250
Northwest | 1 | Crawford | 328 | Dotyville Rd (T-926) Br ov Pine Ck | 7214 | L00 | Bridge Replacement | PE | BOF | 2026-03-12 | 2026-03-12 | 42400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42400
Northwest | 1 | Crawford | 328 | Dotyville Rd (T-926) Br ov Pine Ck | 7214 | L00 | Bridge Replacement | PE | 185 | 2026-03-12 | 2026-03-12 | 7950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7950
Northwest | 1 | Crawford | 328 | Dotyville Rd (T-926) Br ov Pine Ck | 7214 | L00 | Bridge Replacement | PE | LOC | 2026-03-12 | 2026-03-12 | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2650
Northwest | 1 | Crawford | 328 | Dotyville Rd (T-926) Br ov Pine Ck | 7214 | L00 | Bridge Replacement | FD | BOF | 2026-03-12 | 2026-03-12 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northwest | 1 | Crawford | 328 | Dotyville Rd (T-926) Br ov Pine Ck | 7214 | L00 | Bridge Replacement | FD | 183 | 2026-03-12 | 2026-03-12 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500
Northwest | 1 | Crawford | 328 | Dotyville Rd (T-926) Br ov Pine Ck | 7214 | L00 | Bridge Replacement | FD | LOC | 2026-03-12 | 2026-03-12 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500
Northwest | 1 | Crawford | 328 | Dotyville Rd (T-926) Br ov Pine Ck | 7214 | L00 | Bridge Replacement | ROW | BOF | 2026-03-12 | 2026-03-12 | 18174 | 482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18656
Northwest | 1 | Crawford | 328 | Dotyville Rd (T-926) Br ov Pine Ck | 7214 | L00 | Bridge Replacement | ROW | 183 | 2026-03-12 | 2026-03-12 | 3408 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3499
Northwest | 1 | Crawford | 328 | Dotyville Rd (T-926) Br ov Pine Ck | 7214 | L00 | Bridge Replacement | ROW | LOC | 2026-03-12 | 2026-03-12 | 1136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1136
Northwest | 1 | Crawford | 328 | Dotyville Rd (T-926) Br ov Pine Ck | 7214 | L00 | Bridge Replacement | CON | BOF | 2026-03-12 | 2026-03-12 | 841387 | 490820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332207
Northwest | 1 | Crawford | 328 | Dotyville Rd (T-926) Br ov Pine Ck | 7214 | L00 | Bridge Replacement | CON | BRIP | 2026-03-12 | 2026-03-12 | 91413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91413
Northwest | 1 | Crawford | 328 | Dotyville Rd (T-926) Br ov Pine Ck | 7214 | L00 | Bridge Replacement | CON | 183 | 2026-03-12 | 2026-03-12 | 264450 | 91453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355903
Northwest | 1 | Crawford | 353 | SR 6: Erie Street Brdg | 6 | B24 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000
Northwest | 1 | Crawford | 375 | SR 89: Fairview Road to Erie Countyline | 89 | 08M | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Crawford | 375 | SR 89: Fairview Road to Erie Countyline | 89 | 08M | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2030728 | 2030728
Northwest | 1 | Crawford | 413 | SR 2034: Spring Street Viaduct | 2034 | B02 | Bridge Restoration | CON | BRIP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 778000 | 4868000 | 3154000 | 0 | 0 | 8800000
Northwest | 1 | Crawford | 413 | SR 2034: Spring Street Viaduct | 2034 | B02 | Bridge Restoration | CON | 185 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 657000 | 1012079 | 530921 | 0 | 0 | 2200000
Northwest | 1 | Crawford | 420 | SR 1007 over Federal Run | 1007 | DF1 | Bridge Replacement | CON | 185 | 2024-11-07 | 2024-11-07 | 77200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77200
Northwest | 1 | Crawford | 423 | SR 1014: Johnstown Rd Br | 1014 | B02 | Bridge Restoration | PE | BOF | 2027-11-04 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northwest | 1 | Crawford | 423 | SR 1014: Johnstown Rd Br | 1014 | B02 | Bridge Restoration | ROW | BOF | 2027-11-04 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northwest | 1 | Crawford | 423 | SR 1014: Johnstown Rd Br | 1014 | B02 | Bridge Restoration | CON | BOF | 2027-11-04 |  | 0 | 0 | 0 | 0 | 200000 | 100000 | 0 | 0 | 0 | 300000
Northwest | 1 | Crawford | 499 | SR 3021 Brdg/Outlet Creek | 3021 | B01 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Northwest | 1 | Crawford | 499 | SR 3021 Brdg/Outlet Creek | 3021 | B01 | Bridge Restoration | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northwest | 1 | Crawford | 499 | SR 3021 Brdg/Outlet Creek | 3021 | B01 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Northwest | 1 | Crawford | 514 | PA 8 Bridge over Thompson Ck | 8 | B03 | Bridge Restoration | PE | 185 | 2033-01-01 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northwest | 1 | Crawford | 514 | PA 8 Bridge over Thompson Ck | 8 | B03 | Bridge Restoration | ROW | 185 | 2033-01-01 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northwest | 1 | Crawford | 514 | PA 8 Bridge over Thompson Ck | 8 | B03 | Bridge Restoration | CON | BRIP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1100000 | 0 | 0 | 0 | 1100000
Northwest | 1 | Crawford | 516 | SR 2039: Dunham Rd Br | 2039 | B00 | Bridge Replacement | UTL | BRIP | 2025-08-07 | 2025-08-21 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northwest | 1 | Crawford | 516 | SR 2039: Dunham Rd Br | 2039 | B00 | Bridge Replacement | UTL | STP | 2025-08-07 | 2025-08-21 | 255770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255770
Northwest | 1 | Crawford | 516 | SR 2039: Dunham Rd Br | 2039 | B00 | Bridge Replacement | CON | BRIP | 2025-08-07 | 2025-08-21 | 2810799 | 2250388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5061187
Northwest | 1 | Crawford | 516 | SR 2039: Dunham Rd Br | 2039 | B00 | Bridge Replacement | CON | STP | 2025-08-07 | 2025-08-21 | 1359409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1359409
Northwest | 1 | Crawford | 553 | SR 322: Jamestown to Main St. | 322 | 20M | Highway Restoration | PE | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northwest | 1 | Crawford | 553 | SR 322: Jamestown to Main St. | 322 | 20M | Highway Restoration | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6354037 | 6354037
Northwest | 1 | Crawford | 561 | SR 18: SR 322 to Harmonsburg | 18 | 03M | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Crawford | 561 | SR 18: SR 322 to Harmonsburg | 18 | 03M | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4861000 | 4861000
Northwest | 1 | Crawford | 562 | US 6: Venango to Cambridge Springs | 6 | 26M | Highway Restoration | PE | 581 | 2027-06-24 |  | 121895 | 28105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Crawford | 562 | US 6: Venango to Cambridge Springs | 6 | 26M | Highway Restoration | CON | 581 | 2027-06-24 |  | 0 | 0 | 1539000 | 4761000 | 0 | 0 | 0 | 0 | 0 | 6300000
Northwest | 1 | Crawford | 563 | US 322: Harvey Road to Mercer Co. Line | 322 | 17M | Highway Restoration | PE | STP | 2027-03-25 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Crawford | 563 | US 322: Harvey Road to Mercer Co. Line | 322 | 17M | Highway Restoration | CON | NHPP | 2027-03-25 |  | 0 | 0 | 368852 | 5317000 | 3077000 | 0 | 0 | 0 | 0 | 8762852
Northwest | 1 | Crawford | 573 | US 6 French Creek Br #1 | 6 | B13 | Bridge Replacement | ROW | BRIP | 2024-09-12 | 2024-09-12 | 2116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2116
Northwest | 1 | Crawford | 573 | US 6 French Creek Br #1 | 6 | B13 | Bridge Replacement | CON | 185 | 2024-09-12 | 2024-09-12 | 1745959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1745959
Northwest | 1 | Crawford | 573 | US 6 French Creek Br #1 | 6 | B13 | Bridge Replacement | CON | 581 | 2024-09-12 | 2024-09-12 | 500000 | 1239526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1739526
Northwest | 1 | Crawford | 575 | SR 89 Brdg/Shirley Run | 89 | B07 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Crawford | 575 | SR 89 Brdg/Shirley Run | 89 | B07 | Bridge Restoration | ROW | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northwest | 1 | Crawford | 575 | SR 89 Brdg/Shirley Run | 89 | B07 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 1400000
Northwest | 1 | Crawford | 579 | PA 173 Cochranton Tr Brdg | 173 | B02 | Bridge Replacement | PE | STP | 2015-01-29 | 2015-01-29 | 1592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1592
Northwest | 1 | Crawford | 579 | PA 173 Cochranton Tr Brdg | 173 | B02 | Bridge Replacement | PE | 185 | 2015-01-29 | 2015-01-29 | 398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398
Northwest | 1 | Crawford | 585 | SR 1024 Bridge over Britton Run | 1024 | B02 | Bridge Restoration | PE | BOF | 2029-01-01 |  | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northwest | 1 | Crawford | 585 | SR 1024 Bridge over Britton Run | 1024 | B02 | Bridge Restoration | CON | BOF | 2029-01-01 |  | 0 | 0 | 0 | 300000 | 900000 | 0 | 0 | 0 | 0 | 1200000
Northwest | 1 | Crawford | 32157 | SR 285: SR 19 to SR 173 | 285 | 05M | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Crawford | 32157 | SR 285: SR 19 to SR 173 | 285 | 05M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8726000 | 8726000
Northwest | 1 | Crawford | 47272 | PA 408 and Maplewood Rd. Intersection Imp. | 408 | 15M | Highway Restoration | PE | 581 | 2033-01-01 |  | 0 | 15447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15447
Northwest | 1 | Crawford | 47491 | SR 4001/Connt Ck E Brnch | 4001 | B05 | Bridge Restoration | FD | BOF | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
Northwest | 1 | Crawford | 47491 | SR 4001/Connt Ck E Brnch | 4001 | B05 | Bridge Restoration | ROW | BOF | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 10000
Northwest | 1 | Crawford | 47491 | SR 4001/Connt Ck E Brnch | 4001 | B05 | Bridge Restoration | CON | BOF | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 750000
Northwest | 1 | Crawford | 57945 | US 6 French Ck Br #3 | 6 | B12 | Bridge Replacement | FD | NHPP | 2025-09-25 | 2025-09-25 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Crawford | 57945 | US 6 French Ck Br #3 | 6 | B12 | Bridge Replacement | UTL | 185 | 2025-09-25 | 2025-09-25 | 23435 | 14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38227
Northwest | 1 | Crawford | 57945 | US 6 French Ck Br #3 | 6 | B12 | Bridge Replacement | CON | 185 | 2025-09-25 | 2025-09-25 | 0 | 667823 | 3814262 | 3144242 | 0 | 0 | 0 | 0 | 0 | 7626327
Northwest | 1 | Crawford | 57962 | SR 89: Hummer Ck Brdg | 89 | B06 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Crawford | 57962 | SR 89: Hummer Ck Brdg | 89 | B06 | Bridge Restoration | ROW | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northwest | 1 | Crawford | 57962 | SR 89: Hummer Ck Brdg | 89 | B06 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 1400000
Northwest | 1 | Crawford | 57970 | SR 1013: McLaughlin Ck Br | 1013 | B04 | Bridge Replacement | PE | BOF | 2030-01-01 |  | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Crawford | 57970 | SR 1013: McLaughlin Ck Br | 1013 | B04 | Bridge Replacement | ROW | BOF | 2030-01-01 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northwest | 1 | Crawford | 57970 | SR 1013: McLaughlin Ck Br | 1013 | B04 | Bridge Replacement | CON | BOF | 2030-01-01 |  | 0 | 0 | 0 | 384000 | 616000 | 0 | 0 | 0 | 0 | 1000000
Northwest | 1 | Crawford | 57971 | SR 1015: Hotch Kiss Run | 1015 | B00 | Bridge Restoration | PE | BOF | 2030-01-01 |  | 85000 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Crawford | 57971 | SR 1015: Hotch Kiss Run | 1015 | B00 | Bridge Restoration | ROW | BOF | 2030-01-01 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northwest | 1 | Crawford | 57971 | SR 1015: Hotch Kiss Run | 1015 | B00 | Bridge Restoration | CON | BOF | 2030-01-01 |  | 0 | 0 | 0 | 400000 | 400000 | 0 | 0 | 0 | 0 | 800000
Northwest | 1 | Crawford | 57972 | SR 1033: Muddy Ck Brdg | 1033 | B01 | Bridge Restoration | FD | BOF | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 200000
Northwest | 1 | Crawford | 57972 | SR 1033: Muddy Ck Brdg | 1033 | B01 | Bridge Restoration | ROW | BOF | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
Northwest | 1 | Crawford | 57972 | SR 1033: Muddy Ck Brdg | 1033 | B01 | Bridge Restoration | CON | BOF | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 1200000
Northwest | 1 | Crawford | 57973 | SR 1037 over Little Federal Run | 1037 | B00 | Bridge Replacement | CON | BOF | 2026-05-21 |  | 0 | 500000 | 637703 | 0 | 0 | 0 | 0 | 0 | 0 | 1137703
Northwest | 1 | Crawford | 57975 | SR 1039: Mosey Run Brdg | 1039 | B01 | Bridge Restoration | FD | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Northwest | 1 | Crawford | 57975 | SR 1039: Mosey Run Brdg | 1039 | B01 | Bridge Restoration | ROW | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000
Northwest | 1 | Crawford | 57975 | SR 1039: Mosey Run Brdg | 1039 | B01 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
Northwest | 1 | Crawford | 57976 | SR 2017: Sugar Ck Brdg | 2017 | B01 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Northwest | 1 | Crawford | 57976 | SR 2017: Sugar Ck Brdg | 2017 | B01 | Bridge Restoration | ROW | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northwest | 1 | Crawford | 57976 | SR 2017: Sugar Ck Brdg | 2017 | B01 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 1400000
Northwest | 1 | Crawford | 57978 | Deckards Run Br #2 | 2018 | B02 | Bridge Restoration | CON | BRIP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 1107941 | 0 | 0 | 0 | 0 | 1107941
Northwest | 1 | Crawford | 57984 | Pymatuning Reservoir Br | 3011 | B01 | Bridge Restoration | CON | BRIP | 2027-01-01 |  | 0 | 0 | 532541 | 2467459 | 0 | 0 | 0 | 0 | 0 | 3000000
Northwest | 1 | Crawford | 57988 | Bridge Shotcrete Group - 2025 | 4004 | BSC | Bridge Preservation - Federal | PE | 185 | 2026-06-18 |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Northwest | 1 | Crawford | 57988 | Bridge Shotcrete Group - 2025 | 4004 | BSC | Bridge Preservation - Federal | ROW | 185 | 2026-06-18 |  | 10000 | 8600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18600
Northwest | 1 | Crawford | 57988 | Bridge Shotcrete Group - 2025 | 4004 | BSC | Bridge Preservation - Federal | CON | 185 | 2026-06-18 |  | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000
Northwest | 1 | Crawford | 74563 | SR 4004 over Summit Run | 4004 | B00 | Bridge Restoration | FD | 185 | 2026-06-04 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northwest | 1 | Crawford | 74563 | SR 4004 over Summit Run | 4004 | B00 | Bridge Restoration | ROW | 185 | 2026-06-04 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northwest | 1 | Crawford | 74563 | SR 4004 over Summit Run | 4004 | B00 | Bridge Restoration | CON | 185 | 2026-06-04 |  | 0 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325000
Northwest | 1 | Crawford | 74579 | SR 4008/Conneaut Ck E. Brch | 4008 | DF1 | Bridge Restoration | CON | 185 | 2027-12-09 |  | 0 | 0 | 0 | 0 | 375000 | 0 | 0 | 0 | 0 | 375000
Northwest | 1 | Crawford | 74646 | SR 285 over Adsit Run - Scour Group | 285 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 249000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319000
Northwest | 1 | Crawford | 74646 | SR 285 over Adsit Run - Scour Group | 285 | BSC | Bridge Preservation - Federal | ROW | PRTCT | 2026-06-18 |  | 0 | 82500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500
Northwest | 1 | Crawford | 74646 | SR 285 over Adsit Run - Scour Group | 285 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Northwest | 1 | Crawford | 74646 | SR 285 over Adsit Run - Scour Group | 285 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 301302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301302
Northwest | 1 | Crawford | 74664 | SR 2007 over Mud Run | 2007 | B00 | Bridge Restoration | ROW | BOF | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northwest | 1 | Crawford | 74664 | SR 2007 over Mud Run | 2007 | B00 | Bridge Restoration | CON | BOF | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 875000 | 325000 | 0 | 1200000
Northwest | 1 | Crawford | 76858 | I-79: Mercer Co Ln to the Geneva Swamp Br | 79 | A09 | Highway Restoration | CON | 581 | 2024-02-29 | 2024-02-29 | 21672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21672
Northwest | 1 | Crawford | 78584 | SR 18 /Trib #1 Crooked Ck | 18 | B03 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 125000
Northwest | 1 | Crawford | 78584 | SR 18 /Trib #1 Crooked Ck | 18 | B03 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000
Northwest | 1 | Crawford | 78584 | SR 18 /Trib #1 Crooked Ck | 18 | B03 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 900000
Northwest | 1 | Crawford | 78763 | SR 1013 ov Thompson Ck | 1013 | B01 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 160000
Northwest | 1 | Crawford | 78763 | SR 1013 ov Thompson Ck | 1013 | B01 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000
Northwest | 1 | Crawford | 78763 | SR 1013 ov Thompson Ck | 1013 | B01 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 900000
Northwest | 1 | Crawford | 78836 | US 6 over West NY & PA RR | 6 | B08 | Bridge Restoration | CON | 185 | 2030-01-01 |  | 0 | 0 | 0 | 20000 | 600000 | 0 | 0 | 0 | 0 | 620000
Northwest | 1 | Crawford | 78841 | PA 77 over Trib Muddy Ck | 77 | B03 | Bridge Restoration | FD | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 80000
Northwest | 1 | Crawford | 78841 | PA 77 over Trib Muddy Ck | 77 | B03 | Bridge Restoration | ROW | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
Northwest | 1 | Crawford | 78841 | PA 77 over Trib Muddy Ck | 77 | B03 | Bridge Restoration | CON | BRIP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 700000
Northwest | 1 | Crawford | 79875 | SR 8: SR 77 to Erie Countyline | 8 | 19M | Highway Restoration | PE | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
Northwest | 1 | Crawford | 79875 | SR 8: SR 77 to Erie Countyline | 8 | 19M | Highway Restoration | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3521027 | 2170000 | 5691027
Northwest | 1 | Crawford | 82113 | Cussewago St/French Creek | 6 | B10 | Bridge Restoration | FD | BRIP | 2029-01-01 |  | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Northwest | 1 | Crawford | 82113 | Cussewago St/French Creek | 6 | B10 | Bridge Restoration | ROW | BRIP | 2029-01-01 |  | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
Northwest | 1 | Crawford | 82113 | Cussewago St/French Creek | 6 | B10 | Bridge Restoration | CON | BRIP | 2029-01-01 |  | 0 | 0 | 0 | 2400000 | 2400000 | 0 | 0 | 0 | 0 | 4800000
Northwest | 1 | Crawford | 82113 | Cussewago St/French Creek | 6 | B10 | Bridge Restoration | CON | 185 | 2029-01-01 |  | 0 | 0 | 0 | 600000 | 600000 | 0 | 0 | 0 | 0 | 1200000
Northwest | 1 | Crawford | 84921 | SR 8 over East Branch of Oil Creek | 8 | B01 | Bridge Restoration | PE | BRIP | 2027-08-26 |  | 28384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28384
Northwest | 1 | Crawford | 84921 | SR 8 over East Branch of Oil Creek | 8 | B01 | Bridge Restoration | PE | STP | 2027-08-26 |  | 296616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296616
Northwest | 1 | Crawford | 84921 | SR 8 over East Branch of Oil Creek | 8 | B01 | Bridge Restoration | CON | BRIP | 2027-08-26 |  | 0 | 1738587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1738587
Northwest | 1 | Crawford | 84924 | SR 27 over Pine Creek | 27 | B06 | Bridge Restoration | PE | BRIP | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 184315 | 515685 | 0 | 700000
Northwest | 1 | Crawford | 84924 | SR 27 over Pine Creek | 27 | B06 | Bridge Restoration | CON | BRIP | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732315 | 2267685 | 3000000
Northwest | 1 | Crawford | 84927 | SR 408 over Mohawk Run | 408 | B05 | Bridge Replacement | PE | STP | 2026-02-26 | 2026-02-26 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northwest | 1 | Crawford | 84927 | SR 408 over Mohawk Run | 408 | B05 | Bridge Replacement | ROW | BRIP | 2026-02-26 | 2026-02-26 | 0 | 9100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100
Northwest | 1 | Crawford | 84927 | SR 408 over Mohawk Run | 408 | B05 | Bridge Replacement | CON | BRIP | 2026-02-26 | 2026-02-26 | 606206 | 533415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1139621
Northwest | 1 | Crawford | 84931 | SR 1016 ov French Ck Trib | 1016 | B02 | Bridge Restoration | PE | STP | 2027-11-04 |  | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Northwest | 1 | Crawford | 84931 | SR 1016 ov French Ck Trib | 1016 | B02 | Bridge Restoration | PE | 185 | 2027-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000
Northwest | 1 | Crawford | 84931 | SR 1016 ov French Ck Trib | 1016 | B02 | Bridge Restoration | ROW | 185 | 2027-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northwest | 1 | Crawford | 84931 | SR 1016 ov French Ck Trib | 1016 | B02 | Bridge Restoration | CON | 185 | 2027-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Northwest | 1 | Crawford | 84938 | Bridge Shotcrete Group - SR 3019 | 3019 | BSC | Bridge Preservation - State Funded | ROW | 185 |  |  | 10000 | 8600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18600
Northwest | 1 | Crawford | 84942 | SR 4010 ov Cussewago Ck | 4010 | B05 | Bridge Restoration | PE | BOF | 2030-01-01 |  | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000
Northwest | 1 | Crawford | 84942 | SR 4010 ov Cussewago Ck | 4010 | B05 | Bridge Restoration | CON | BOF | 2030-01-01 |  | 0 | 0 | 0 | 0 | 480000 | 520000 | 0 | 0 | 0 | 1000000
Northwest | 1 | Crawford | 85627 | SR 18: Dickensburg Rd - SR 198 | 18 | 192 | 409 Expanded Maintenance | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Crawford | 85627 | SR 18: Dickensburg Rd - SR 198 | 18 | 192 | 409 Expanded Maintenance | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7442000 | 7442000
Northwest | 1 | Crawford | 85776 | US 6: Spring St - Baldwin St Ext | 6 | A06 | Highway Reconstruction | CON | NHPP | 2024-06-06 | 2024-06-06 | 1002294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1002294
Northwest | 1 | Crawford | 85776 | US 6: Spring St - Baldwin St Ext | 6 | A06 | Highway Reconstruction | CON | 581 | 2024-06-06 | 2024-06-06 | 736585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 736585
Northwest | 1 | Crawford | 88440 | Harmonsburg Rd Br/I-79 | 3016 | B00 | Bridge Restoration | FD | BRIP | 2036-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 140000
Northwest | 1 | Crawford | 88440 | Harmonsburg Rd Br/I-79 | 3016 | B00 | Bridge Restoration | CON | BRIP | 2036-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 1350000
Northwest | 1 | Crawford | 88452 | SR 1016 over Kelly Run | 1016 | DF1 | Bridge Restoration | PE | BOF | 2029-01-01 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northwest | 1 | Crawford | 88452 | SR 1016 over Kelly Run | 1016 | DF1 | Bridge Restoration | CON | BOF | 2029-01-01 |  | 0 | 0 | 0 | 452000 | 0 | 0 | 0 | 0 | 0 | 452000
Northwest | 1 | Crawford | 89125 | US 6 Bridge ov Fr Ck Trib | 6 | B15 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 125000
Northwest | 1 | Crawford | 89125 | US 6 Bridge ov Fr Ck Trib | 6 | B15 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000
Northwest | 1 | Crawford | 89125 | US 6 Bridge ov Fr Ck Trib | 6 | B15 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 900000
Northwest | 1 | Crawford | 89172 | SR 6: SR 98 to Park Ave Plaza | 6 | 31M | Highway Restoration | PE | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Crawford | 89172 | SR 6: SR 98 to Park Ave Plaza | 6 | 31M | Highway Restoration | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5322000 | 5322000
Northwest | 1 | Crawford | 89173 | SR 285: US 19 to SR 173 | 285 | 06M | Highway Restoration | CON | STP | 2026-04-09 |  | 1685306 | 3834694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520000
Northwest | 1 | Crawford | 89173 | SR 285: US 19 to SR 173 | 285 | 06M | Highway Restoration | CON | 581 | 2026-04-09 |  | 375000 | 1005001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380001
Northwest | 1 | Crawford | 89174 | SR 18: SR 6 to SR 618 | 18 | 162 | General Maintenance | CON | HSIP | 2026-03-26 | 2026-03-26 | 0 | 43644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43644
Northwest | 1 | Crawford | 90161 | Shotcrete Group Crawford/Warren | 3005 | B04 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Northwest | 1 | Crawford | 90161 | Shotcrete Group Crawford/Warren | 3005 | B04 | Bridge Preservation - Federal | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000
Northwest | 1 | Crawford | 90161 | Shotcrete Group Crawford/Warren | 3005 | B04 | Bridge Preservation - Federal | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000 | 850000
Northwest | 1 | Crawford | 90274 | US 6: Baldwin St. Ext. to Peters Road | 6 | 27M | Highway Restoration | PE | 581 | 2028-01-01 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Crawford | 90274 | US 6: Baldwin St. Ext. to Peters Road | 6 | 27M | Highway Restoration | CON | NHPP | 2028-01-01 |  | 0 | 0 | 0 | 0 | 1140000 | 1060000 | 0 | 0 | 0 | 2200000
Northwest | 1 | Crawford | 92509 | SR 3016: Hrmsburg Rd Brdg | 3016 | B01 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Crawford | 92509 | SR 3016: Hrmsburg Rd Brdg | 3016 | B01 | Bridge Restoration | ROW | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northwest | 1 | Crawford | 92509 | SR 3016: Hrmsburg Rd Brdg | 3016 | B01 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 1400000
Northwest | 1 | Crawford | 97056 | SR 3004 Bridge over I-79 | 3004 | B00 | Bridge Restoration | FD | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 140000
Northwest | 1 | Crawford | 97056 | SR 3004 Bridge over I-79 | 3004 | B00 | Bridge Restoration | ROW | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19685 | 0 | 19685
Northwest | 1 | Crawford | 97056 | SR 3004 Bridge over I-79 | 3004 | B00 | Bridge Restoration | CON | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000 | 1500000
Northwest | 1 | Crawford | 97057 | SR 27 Brdg over Mill Run | 27 | B09 | Bridge Restoration | FD | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 169685 | 80315 | 0 | 250000
Northwest | 1 | Crawford | 97057 | SR 27 Brdg over Mill Run | 27 | B09 | Bridge Restoration | ROW | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
Northwest | 1 | Crawford | 97057 | SR 27 Brdg over Mill Run | 27 | B09 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000
Northwest | 1 | Crawford | 97065 | SR 1015: Bridge over French Creek Tributary | 1015 | DF1 | Bridge Replacement | CON | 185 | 2024-11-07 | 2024-11-07 | 1091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1091
Northwest | 1 | Crawford | 97077 | SR 4006 over Turkey Track Run - Scour Group | 4006 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Northwest | 1 | Crawford | 97077 | SR 4006 over Turkey Track Run - Scour Group | 4006 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Northwest | 1 | Crawford | 97077 | SR 4006 over Turkey Track Run - Scour Group | 4006 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 200970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200970
Northwest | 1 | Crawford | 97090 | PA 98 Bridge/Cuswgo Ck Trib | 98 | B02 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Northwest | 1 | Crawford | 97090 | PA 98 Bridge/Cuswgo Ck Trib | 98 | B02 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000
Northwest | 1 | Crawford | 97090 | PA 98 Bridge/Cuswgo Ck Trib | 98 | B02 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 900000
Northwest | 1 | Crawford | 97091 | SR 1011 Brdg/Oil Creek - Scour Group | 1011 | B00 | Bridge Preservation - Federal | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Northwest | 1 | Crawford | 97091 | SR 1011 Brdg/Oil Creek - Scour Group | 1011 | B00 | Bridge Preservation - Federal | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 926600 | 926600
Northwest | 1 | Crawford | 97092 | Crawford County Tbeam Rehab Group | 322 | TBR | Bridge Restoration | ROW | BRIP | 2029-01-01 |  | 0 | 0 | 12324 | 0 | 0 | 0 | 0 | 0 | 0 | 12324
Northwest | 1 | Crawford | 97092 | Crawford County Tbeam Rehab Group | 322 | TBR | Bridge Restoration | CON | BRIP | 2029-01-01 |  | 0 | 0 | 0 | 43818 | 706182 | 0 | 0 | 0 | 0 | 750000
Northwest | 1 | Crawford | 97101 | SR 27 Br #1/Lil Sugar Ck - Bridge Sediment Removal | 27 | BSR | Stormwater Management | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Northwest | 1 | Crawford | 97101 | SR 27 Br #1/Lil Sugar Ck - Bridge Sediment Removal | 27 | BSR | Stormwater Management | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Northwest | 1 | Crawford | 97101 | SR 27 Br #1/Lil Sugar Ck - Bridge Sediment Removal | 27 | BSR | Stormwater Management | CON | PRTCT | 2026-06-18 |  | 0 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000
Northwest | 1 | Crawford | 97103 | SR 27 Br #2/Lil Sugar Ck - Bridge Sediment Removal | 27 | BSR | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Northwest | 1 | Crawford | 97103 | SR 27 Br #2/Lil Sugar Ck - Bridge Sediment Removal | 27 | BSR | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Northwest | 1 | Crawford | 97103 | SR 27 Br #2/Lil Sugar Ck - Bridge Sediment Removal | 27 | BSR | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 121000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121000
Northwest | 1 | Crawford | 97107 | PA 18 Brdg/Conneaut Ck Trib | 18 | B10 | Bridge Restoration | PE | 185 | 2033-01-01 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northwest | 1 | Crawford | 97107 | PA 18 Brdg/Conneaut Ck Trib | 18 | B10 | Bridge Restoration | ROW | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000
Northwest | 1 | Crawford | 97107 | PA 18 Brdg/Conneaut Ck Trib | 18 | B10 | Bridge Restoration | CON | BRIP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 0 | 550000
Northwest | 1 | Crawford | 97122 | SR 3004 Brdg/Crooked Ck | 3004 | B02 | Bridge Restoration | PE | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 260000 | 0 | 0 | 0 | 0 | 260000
Northwest | 1 | Crawford | 97122 | SR 3004 Brdg/Crooked Ck | 3004 | B02 | Bridge Restoration | ROW | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Northwest | 1 | Crawford | 97122 | SR 3004 Brdg/Crooked Ck | 3004 | B02 | Bridge Restoration | CON | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 0 | 0 | 1400000
Northwest | 1 | Crawford | 97123 | SR 4004 Bridge over Paden Creek | 4004 | B02 | Bridge Replacement | CON | BOF | 2024-06-06 | 2024-06-06 | 43487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43487
Northwest | 1 | Crawford | 97878 | SR 8: Venago Co. Ln. to SR 408 | 8 | 11M | Highway Restoration | PE | 581 | 2031-01-01 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Crawford | 97878 | SR 8: Venago Co. Ln. to SR 408 | 8 | 11M | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 1003522 | 2500000 | 0 | 0 | 0 | 0 | 0 | 3503522
Northwest | 1 | Crawford | 98635 | SR 18 Brdg/Inlet Ck Brnch | 18 | B11 | Bridge Restoration | CON | BRIP | 2027-10-31 |  | 0 | 0 | 0 | 370477 | 0 | 0 | 0 | 0 | 0 | 370477
Northwest | 1 | Crawford | 98899 | SR 18: Conneautville - Erie Co. Ln. | 18 | 11M | Highway Restoration | PE | 581 | 2027-04-08 |  | 100000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Crawford | 98899 | SR 18: Conneautville - Erie Co. Ln. | 18 | 11M | Highway Restoration | CON | STP | 2027-04-08 |  | 0 | 0 | 0 | 3513702 | 3386298 | 0 | 0 | 0 | 0 | 6900000
Northwest | 1 | Crawford | 99603 | US 322: Pine Rd to US 6 | 322 | 14M | Highway Restoration | CON | 581 |  |  | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000
Northwest | 1 | Crawford | 106162 | Mt Pleasant Rd RR Crossing |  | R13 | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 0 | 0 | 318500 | 0 | 0 | 0 | 0 | 0 | 318500
Northwest | 1 | Crawford | 106584 | US 322 over Barber Run | 322 | B04 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Northwest | 1 | Crawford | 106584 | US 322 over Barber Run | 322 | B04 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000
Northwest | 1 | Crawford | 106584 | US 322 over Barber Run | 322 | B04 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 900000
Northwest | 1 | Crawford | 109996 | SR 8 and SR 77 Intersection | 8 | S01 | Safety Improvement | PE | HSIP | 2024-08-22 | 2024-08-22 | 2879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879
Northwest | 1 | Crawford | 109996 | SR 8 and SR 77 Intersection | 8 | S01 | Safety Improvement | PE | 581 | 2024-08-22 | 2024-08-22 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320
Northwest | 1 | Crawford | 110842 | US 6: SR 618 to US 19 | 6 | 01M | Highway Restoration | CON | 581 | 2024-09-12 | 2024-10-10 | 4596384 | 1106043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5702427
Northwest | 1 | Crawford | 110853 | US 322: Linden St to Wilson Chute Rd | 322 | 16M | Highway Restoration | PE | 581 | 2025-03-27 | 2025-03-27 | 33604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33604
Northwest | 1 | Crawford | 110853 | US 322: Linden St to Wilson Chute Rd | 322 | 16M | Highway Restoration | CON | STP | 2025-03-27 | 2025-03-27 | 1705327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1705327
Northwest | 1 | Crawford | 110853 | US 322: Linden St to Wilson Chute Rd | 322 | 16M | Highway Restoration | CON | 581 | 2025-03-27 | 2025-03-27 | 426332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426332
Northwest | 1 | Crawford | 110987 | SR 4003 over Foster Run - Bridge Sediment Removal | 4003 | BSR | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Northwest | 1 | Crawford | 110987 | SR 4003 over Foster Run - Bridge Sediment Removal | 4003 | BSR | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Northwest | 1 | Crawford | 110987 | SR 4003 over Foster Run - Bridge Sediment Removal | 4003 | BSR | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000
Northwest | 1 | Crawford | 113216 | Shaw's Landing RRX | 2005 | RRX | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 375000
Northwest | 1 | Crawford | 114035 | SR 102: US 6 to SR 98 | 102 | 01M | Highway Restoration | CON | STP | 2024-05-09 | 2024-05-09 | 228112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228112
Northwest | 1 | Crawford | 114035 | SR 102: US 6 to SR 98 | 102 | 01M | Highway Restoration | CON | 581 | 2024-05-09 | 2024-05-09 | 253091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253091
Northwest | 1 | Crawford | 114138 | SR 1032 Bridge over Shirley Run (D.D.P.) | 1032 | B00 | Bridge Replacement | CON | BOF | 2023-12-14 | 2023-12-14 | 243500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243500
Northwest | 1 | Crawford | 115353 | SR 18: Mercer Co. Line to US 322 | 18 | 12M | Highway Restoration | PE | 581 | 2028-01-01 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Crawford | 115353 | SR 18: Mercer Co. Line to US 322 | 18 | 12M | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 3600000 | 600000 | 0 | 0 | 0 | 0 | 0 | 4200000
Northwest | 1 | Crawford | 115366 | US 19: SR 285 to US 6 | 19 | 05M | Highway Restoration | PE | 581 | 2026-03-26 | 2026-03-26 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Crawford | 115366 | US 19: SR 285 to US 6 | 19 | 05M | Highway Restoration | CON | HSIP | 2026-03-26 | 2026-03-26 | 0 | 48339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48339
Northwest | 1 | Crawford | 115366 | US 19: SR 285 to US 6 | 19 | 05M | Highway Restoration | CON | 581 | 2026-03-26 | 2026-03-26 | 743653 | 3157750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3901403
Northwest | 1 | Crawford | 115533 | Crawford - SR 1041 Slide (GRP #2) | 1041 | SL1 | Safety Improvement | PE | PRTCT | 2027-01-14 |  | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
Northwest | 1 | Crawford | 115533 | Crawford - SR 1041 Slide (GRP #2) | 1041 | SL1 | Safety Improvement | CON | PRTCT | 2027-01-14 |  | 0 | 0 | 720000 | 0 | 0 | 0 | 0 | 0 | 0 | 720000
Northwest | 1 | Crawford | 117436 | SR 98: From SR 198 to SR 6 | 98 | 161 | General Maintenance | CON | HSIP | 2026-03-26 | 2026-03-26 | 0 | 67445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67445
Northwest | 1 | Crawford | 117512 | SR 77: Meadville - Blooming Valley | 77 | 18M | Highway Restoration | PE | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Crawford | 117512 | SR 77: Meadville - Blooming Valley | 77 | 18M | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 4020000 | 0 | 0 | 5020000
Northwest | 1 | Crawford | 117798 | US 6 Bridge over French Creek Trib | 6 | B14 | Bridge Restoration | ROW | 185 | 2030-01-01 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northwest | 1 | Crawford | 117798 | US 6 Bridge over French Creek Trib | 6 | B14 | Bridge Restoration | CON | 185 | 2030-01-01 |  | 0 | 0 | 0 | 457392 | 442608 | 0 | 0 | 0 | 0 | 900000
Northwest | 1 | Crawford | 119781 | SR 618: US 6 to US 18 | 618 | 01M | Highway Restoration | PE | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Crawford | 119781 | SR 618: US 6 to US 18 | 618 | 01M | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 600000 | 2850000 | 170000 | 0 | 3620000
Northwest | 1 | Crawford | 120816 | SR 3023: S. Watson Run Road Bridge #2 | 3023 | B02 | Bridge Restoration | PE | BOF | 2035-01-01 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Crawford | 120816 | SR 3023: S. Watson Run Road Bridge #2 | 3023 | B02 | Bridge Restoration | ROW | BOF | 2035-01-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Northwest | 1 | Crawford | 120816 | SR 3023: S. Watson Run Road Bridge #2 | 3023 | B02 | Bridge Restoration | CON | BOF | 2035-01-01 |  | 0 | 0 | 0 | 480000 | 520000 | 0 | 0 | 0 | 0 | 1000000
Northwest | 1 | Crawford | 120831 | SR 6 over Watson Run | 6 | B28 | Bridge Restoration | PE | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 600000
Northwest | 1 | Crawford | 120831 | SR 6 over Watson Run | 6 | B28 | Bridge Restoration | CON | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
Northwest | 1 | Crawford | 120842 | SR 408 over Muddy Creek Trib | 408 | B15 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Crawford | 120842 | SR 408 over Muddy Creek Trib | 408 | B15 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
Northwest | 1 | Crawford | 120842 | SR 408 over Muddy Creek Trib | 408 | B15 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000 | 1100000
Northwest | 1 | Crawford | 120843 | SR 173 over Lake Creek | 173 | B3 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Crawford | 120843 | SR 173 over Lake Creek | 173 | B3 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Northwest | 1 | Crawford | 120846 | SR 285 over McMichael Run | 285 | B11 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Crawford | 120846 | SR 285 over McMichael Run | 285 | B11 | Bridge Restoration | ROW | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Northwest | 1 | Crawford | 120846 | SR 285 over McMichael Run | 285 | B11 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000 | 1300000
Northwest | 1 | Crawford | 120849 | SR 2014 over Little Sugar Ck | 2014 | 0 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
Northwest | 1 | Crawford | 120849 | SR 2014 over Little Sugar Ck | 2014 | 0 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 900000
Northwest | 1 | Crawford | 121183 | Crawford HFST - 2025 | 322 | S01 | Safety Improvement | PE | HSIP | 2025-05-22 | 2025-05-22 | 10956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10956
Northwest | 1 | Crawford | 121183 | Crawford HFST - 2025 | 322 | S01 | Safety Improvement | CON | HSIP | 2025-05-22 | 2025-05-22 | 674088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 674088
Northwest | 1 | Crawford | 121183 | Crawford HFST - 2025 | 322 | S01 | Safety Improvement | CON | HSIP | 2025-05-22 | 2025-05-22 | 245688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245688
Northwest | 1 | Crawford | 121730 | Allegheny College Safety Improvements | 886 | S01 | General Maintenance | PE | HVRU |  |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Northwest | 1 | Crawford | 122342 | Dept. Force Br. Crawford |  |  | Bridge Preservation - State Funded | CON | 185 |  |  | 60000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Northwest | 1 | Crawford | 122685 | District 1 NW CRP Flex - Transit - 2025-2026 |  |  | Public Transit | PRA | CRP |  |  | 24000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000
Northwest | 1 | Crawford | 123058 | Mercer Pike Deep Pipe Replacement | 2003 | DP1 | Highway Restoration | PE | 581 | 2026-07-02 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Northwest | 1 | Crawford | 123058 | Mercer Pike Deep Pipe Replacement | 2003 | DP1 | Highway Restoration | CON | 581 | 2026-07-02 |  | 175000 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Northwest | 1 | Crawford | 123060 | Bridge Shotcrete Group - SR 3005 | 3005 | BSC | Bridge Preservation - State Funded | ROW | 185 |  |  | 10000 | 7550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17550
Northwest | 1 | Crawford | 123093 | SR 1011 over Oil Creek - Scour Group | 1011 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Northwest | 1 | Crawford | 123093 | SR 1011 over Oil Creek - Scour Group | 1011 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 470224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470224
Northwest | 1 | Crawford | 123098 | US 322 over Shenango River Trib - Scour Group | 322 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Northwest | 1 | Crawford | 123098 | US 322 over Shenango River Trib - Scour Group | 322 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 117244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117244
Northwest | 1 | Crawford | 123781 | WNYPA RR Crossing Upgrades |  | RRX | Safety Improvement | CON | RRX | 2027-01-01 |  | 0 | 100000 | 851312 | 0 | 0 | 0 | 0 | 0 | 0 | 951312
Northwest | 1 | Forest | 47276 | SR 666: Brecht Rd. to Old Kelletville Rd. | 666 | 11M | Highway Reconstruction | FD | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 125000
Northwest | 1 | Forest | 47276 | SR 666: Brecht Rd. to Old Kelletville Rd. | 666 | 11M | Highway Reconstruction | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 846847 | 846847
Northwest | 1 | Forest | 47276 | SR 666: Brecht Rd. to Old Kelletville Rd. | 666 | 11M | Highway Reconstruction | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211712 | 211712
Northwest | 1 | Forest | 57935 | SR 3004 Brdg/Piney Run | 3004 | B04 | Bridge Restoration | FD | BOF | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 180000
Northwest | 1 | Forest | 57935 | SR 3004 Brdg/Piney Run | 3004 | B04 | Bridge Restoration | CON | BOF | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223400 | 0 | 1223400
Northwest | 1 | Forest | 74693 | PA 36 over Tionesta Creek | 36 | B00 | Bridge Restoration | FD | 185 | 2030-01-01 |  | 0 | 0 | 140338 | 0 | 0 | 0 | 0 | 0 | 0 | 140338
Northwest | 1 | Forest | 74693 | PA 36 over Tionesta Creek | 36 | B00 | Bridge Restoration | CON | 185 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1235313 | 2764687 | 0 | 0 | 4000000
Northwest | 1 | Forest | 74695 | SR 62-Tionesta River Br. | 62 | B03 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Forest | 74695 | SR 62-Tionesta River Br. | 62 | B03 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Northwest | 1 | Forest | 78837 | SR 666/Upper Sheriff Run | 666 | B01 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 160000
Northwest | 1 | Forest | 78837 | SR 666/Upper Sheriff Run | 666 | B01 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northwest | 1 | Forest | 84944 | SR 2002 over Coleman Run | 2002 | B02 | Bridge Restoration | PE | 185 | 2026-01-15 | 2026-01-15 | 53054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53054
Northwest | 1 | Forest | 84944 | SR 2002 over Coleman Run | 2002 | B02 | Bridge Restoration | CON | 185 | 2026-01-15 | 2026-01-15 | 380000 | 804671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1184671
Northwest | 1 | Forest | 88475 | US 62 Bridge over Prather Run | 62 | B05 | Bridge Replacement | PE | BRIP | 2026-12-03 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northwest | 1 | Forest | 88475 | US 62 Bridge over Prather Run | 62 | B05 | Bridge Replacement | PE | NHPP | 2026-12-03 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Northwest | 1 | Forest | 88475 | US 62 Bridge over Prather Run | 62 | B05 | Bridge Replacement | CON | BRIP | 2026-12-03 |  | 0 | 520418 | 879582 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
Northwest | 1 | Forest | 116650 | US 62: SR 3004 to SR 127 | 62 | M01 | Highway Restoration | CON | 581 | 2024-03-28 | 2024-03-28 | 154130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154130
Northwest | 1 | Forest | 116652 | SR 66: SR 2003 to SR 899 | 66 | 13M | Highway Restoration | CON | STP | 2028-01-01 |  | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
Northwest | 1 | Forest | 117484 | SR 66: Seg 290 to Elk Co Ln | 66 | 12M | Highway Restoration | PE | 581 | 2027-02-11 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Forest | 117484 | SR 66: Seg 290 to Elk Co Ln | 66 | 12M | Highway Restoration | CON | 581 | 2027-02-11 |  | 0 | 0 | 0 | 3611000 | 0 | 0 | 0 | 0 | 0 | 3611000
Northwest | 1 | Forest | 117571 | SR 666 over Little Minister Run - Scour Group | 666 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Northwest | 1 | Forest | 117571 | SR 666 over Little Minister Run - Scour Group | 666 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Northwest | 1 | Forest | 117571 | SR 666 over Little Minister Run - Scour Group | 666 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 113013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113013
Northwest | 1 | Forest | 123094 | SR 36 over Hunter Run - Scour Group | 36 | BSC | Bridge Preservation - State Funded | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Northwest | 1 | Forest | 123094 | SR 36 over Hunter Run - Scour Group | 36 | BSC | Bridge Preservation - State Funded | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Northwest | 1 | Forest | 123094 | SR 36 over Hunter Run - Scour Group | 36 | BSC | Bridge Preservation - State Funded | CON | PRTCT | 2026-06-18 |  | 0 | 150062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150062
Northwest | 1 | Forest | 123095 | SR 666 over Bush Creek - Scour Group | 666 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Northwest | 1 | Forest | 123095 | SR 666 over Bush Creek - Scour Group | 666 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Northwest | 1 | Forest | 123095 | SR 666 over Bush Creek - Scour Group | 666 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 173461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173461
Northwest | 1 | Venango | 1979 | SR 3023 Bridge over Mill Creek | 3023 | B00 | Bridge Replacement | CON | BOF | 2023-12-14 | 2023-12-14 | 71872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71872
Northwest | 1 | Venango | 2107 | Petroleum Center Bridge | 1004 | B00 | Bridge Restoration | ROW | BOF | 2026-06-18 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northwest | 1 | Venango | 2107 | Petroleum Center Bridge | 1004 | B00 | Bridge Restoration | CON | BOF | 2026-06-18 |  | 0 | 1230000 | 1270000 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
Northwest | 1 | Venango | 2161 | Dean Road over Little Sandy Creek |  | L00 | Bridge Replacement | CON | BRIP | 2025-11-06 | 2025-11-06 | 1570000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570000
Northwest | 1 | Venango | 2232 | SR 208 Brdg over I-80 EB/WB | 208 | B04 | Bridge Restoration | CON | 185 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 500000 | 1000000 | 0 | 0 | 0 | 1500000
Northwest | 1 | Venango | 2235 | SR 2023 over Porcupine Ck | 2023 | B00 | Bridge Replacement | ROW | 185 | 2024-08-08 | 2024-08-22 | 855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855
Northwest | 1 | Venango | 2235 | SR 2023 over Porcupine Ck | 2023 | B00 | Bridge Replacement | CON | BOF | 2024-08-08 | 2024-08-22 | 360749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360749
Northwest | 1 | Venango | 2263 | Miller Farm (T-635) Bridge | 7212 | L00 | Bridge Restoration | CON | BOF | 2028-01-01 |  | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 800000
Northwest | 1 | Venango | 2263 | Miller Farm (T-635) Bridge | 7212 | L00 | Bridge Restoration | CON | 183 | 2028-01-01 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Venango | 51193 | US 62: Allegheny Boulevard | 62 | 06M | Highway Restoration | PE | 581 | 2030-01-01 |  | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
Northwest | 1 | Venango | 51193 | US 62: Allegheny Boulevard | 62 | 06M | Highway Restoration | CON | NHPP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1457000 | 1043000 | 0 | 0 | 2500000
Northwest | 1 | Venango | 51195 | US 322 Grant & Thirteenth Streets | 322 | 04M | Highway Restoration | PE | STP | 2027-09-16 |  | 0 | 0 | 0 | 0 | 130000 | 0 | 0 | 0 | 0 | 130000
Northwest | 1 | Venango | 51195 | US 322 Grant & Thirteenth Streets | 322 | 04M | Highway Restoration | PE | 581 | 2027-09-16 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northwest | 1 | Venango | 51195 | US 322 Grant & Thirteenth Streets | 322 | 04M | Highway Restoration | CON | NHPP | 2027-09-16 |  | 0 | 0 | 1500000 | 300000 | 0 | 0 | 1079500 | 0 | 0 | 2879500
Northwest | 1 | Venango | 51195 | US 322 Grant & Thirteenth Streets | 322 | 04M | Highway Restoration | CON | STP | 2027-09-16 |  | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 0 | 0 | 1800000
Northwest | 1 | Venango | 51195 | US 322 Grant & Thirteenth Streets | 322 | 04M | Highway Restoration | CON | 581 | 2027-09-16 |  | 0 | 0 | 910000 | 0 | 0 | 0 | 0 | 0 | 0 | 910000
Northwest | 1 | Venango | 58248 | Venango County T-Beam Rehab Group | 62 | B10 | Bridge Restoration | PE | BRIP | 2027-01-01 |  | 0 | 349612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349612
Northwest | 1 | Venango | 58248 | Venango County T-Beam Rehab Group | 62 | B10 | Bridge Restoration | CON | BRIP | 2027-01-01 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Northwest | 1 | Venango | 58248 | Venango County T-Beam Rehab Group | 62 | B10 | Bridge Restoration | CON | 185 | 2027-01-01 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northwest | 1 | Venango | 58266 | SR 1006 Brdg/Allender Run | 1006 | B01 | Bridge Restoration | FD | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 120392 | 29608 | 0 | 0 | 0 | 150000
Northwest | 1 | Venango | 58266 | SR 1006 Brdg/Allender Run | 1006 | B01 | Bridge Restoration | ROW | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 10000
Northwest | 1 | Venango | 58266 | SR 1006 Brdg/Allender Run | 1006 | B01 | Bridge Restoration | CON | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 900000
Northwest | 1 | Venango | 67098 | On Demand Bridge Repair Contract - 2025 |  |  | Bridge Restoration | CON | 185 | 2024-10-24 | 2024-10-24 | 500000 | 670361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1170361
Northwest | 1 | Venango | 67102 | On Demand Bridge Repair Line Item |  |  | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 3500000
Northwest | 1 | Venango | 73249 | SR 157: SR 2017 to Clarion Co Ln | 157 | 03M | Highway Restoration | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
Northwest | 1 | Venango | 73249 | SR 157: SR 2017 to Clarion Co Ln | 157 | 03M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6407793 | 6407793
Northwest | 1 | Venango | 75383 | SR 227: SR 8 to SR 1006 | 227 | 04M | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 4059000 | 1241000 | 0 | 0 | 0 | 5300000
Northwest | 1 | Venango | 75597 | Slide Repair Resrv |  | SLR | Reserve Line Item | CON | 581 |  |  | 0 | 330000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 2000000 | 5330000
Northwest | 1 | Venango | 78464 | Williams Road Bridge (T-627) | 7214 | L00 | Bridge Replacement | PE | BOF | 2026-06-18 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
Northwest | 1 | Venango | 78464 | Williams Road Bridge (T-627) | 7214 | L00 | Bridge Replacement | PE | 183 | 2026-06-18 |  | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
Northwest | 1 | Venango | 78464 | Williams Road Bridge (T-627) | 7214 | L00 | Bridge Replacement | FD | BOF | 2026-06-18 |  | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Northwest | 1 | Venango | 78464 | Williams Road Bridge (T-627) | 7214 | L00 | Bridge Replacement | FD | 183 | 2026-06-18 |  | 22500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
Northwest | 1 | Venango | 78464 | Williams Road Bridge (T-627) | 7214 | L00 | Bridge Replacement | FD | LOC | 2026-06-18 |  | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
Northwest | 1 | Venango | 78464 | Williams Road Bridge (T-627) | 7214 | L00 | Bridge Replacement | ROW | BOF | 2026-06-18 |  | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
Northwest | 1 | Venango | 78464 | Williams Road Bridge (T-627) | 7214 | L00 | Bridge Replacement | ROW | 183 | 2026-06-18 |  | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
Northwest | 1 | Venango | 78464 | Williams Road Bridge (T-627) | 7214 | L00 | Bridge Replacement | UTL | BOF | 2026-06-18 |  | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
Northwest | 1 | Venango | 78464 | Williams Road Bridge (T-627) | 7214 | L00 | Bridge Replacement | UTL | 183 | 2026-06-18 |  | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
Northwest | 1 | Venango | 78464 | Williams Road Bridge (T-627) | 7214 | L00 | Bridge Replacement | CON | BOF | 2026-06-18 |  | 0 | 802000 | 580000 | 1046300 | 0 | 0 | 0 | 0 | 0 | 2428300
Northwest | 1 | Venango | 78465 | Fisherman's Cove (T-370) Bridge | 7220 | L00 | Bridge Restoration | CON | 185 | 2023-05-11 | 2023-05-11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Northwest | 1 | Venango | 84307 | Dept. Force Br Line Item |  |  | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 483200 | 1923200
Northwest | 1 | Venango | 85442 | SR 8: SR 428 to SR 227 | 8 | 16M | Highway Restoration | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Northwest | 1 | Venango | 85442 | SR 8: SR 428 to SR 227 | 8 | 16M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4008741 | 4008741
Northwest | 1 | Venango | 86950 | SR 417: SR 322 - Keely Rd | 417 | 04M | Highway Restoration | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Northwest | 1 | Venango | 86950 | SR 417: SR 322 - Keely Rd | 417 | 04M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4507065 | 4507065
Northwest | 1 | Venango | 90271 | SR 257: Fletcher Ln to US 62 | 257 | 02M | Highway Restoration | PE | NHPP | 2026-01-08 | 2026-01-08 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Venango | 90271 | SR 257: Fletcher Ln to US 62 | 257 | 02M | Highway Restoration | CON | NHPP | 2026-01-08 | 2026-01-08 | 1600000 | 893699 | 24932 | 0 | 0 | 0 | 0 | 0 | 0 | 2518631
Northwest | 1 | Venango | 90446 | Northwest Safety Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 500000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 1000000 | 3000000
Northwest | 1 | Venango | 93599 | SR 36 ov Pithole Ck Brnch | 36 | B01 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000
Northwest | 1 | Venango | 93599 | SR 36 ov Pithole Ck Brnch | 36 | B01 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000
Northwest | 1 | Venango | 97340 | SR 3101 Bridge over I-80 | 3101 | B00 | Bridge Restoration | PE | BOF |  |  | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000
Northwest | 1 | Venango | 97340 | SR 3101 Bridge over I-80 | 3101 | B00 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 730000 | 270000 | 0 | 0 | 0 | 0 | 0 | 1000000
Northwest | 1 | Venango | 97358 | SR 4016 Brdg/Beatty Run | 4016 | B00 | Bridge Restoration | PE | BOF | 2030-01-01 |  | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 180000
Northwest | 1 | Venango | 97358 | SR 4016 Brdg/Beatty Run | 4016 | B00 | Bridge Restoration | ROW | BOF | 2030-01-01 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Northwest | 1 | Venango | 97358 | SR 4016 Brdg/Beatty Run | 4016 | B00 | Bridge Restoration | CON | BOF | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1228800 | 0 | 0 | 0 | 1228800
Northwest | 1 | Venango | 97359 | SR 4022 Brdg/Prather Ck - Scour Group | 4022 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Northwest | 1 | Venango | 97359 | SR 4022 Brdg/Prather Ck - Scour Group | 4022 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Northwest | 1 | Venango | 97359 | SR 4022 Brdg/Prather Ck - Scour Group | 4022 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 231317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231317
Northwest | 1 | Venango | 97364 | SR 3003 Bridges over I-80 EB & WB | 3003 | B00 | Bridge Restoration | CON | BOF | 2024-03-14 | 2024-03-14 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Northwest | 1 | Venango | 97380 | SR 3102: Bridge over SR 8 | 3102 | B00 | Bridge Restoration | PE | BOF |  |  | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000
Northwest | 1 | Venango | 97380 | SR 3102: Bridge over SR 8 | 3102 | B00 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Northwest | 1 | Venango | 97401 | SR 208 Bridge over Little Scrubgrass Creek | 208 | B03 | Bridge Replacement | FD | 185 | 2026-06-04 |  | 0 | 306562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306562
Northwest | 1 | Venango | 97401 | SR 208 Bridge over Little Scrubgrass Creek | 208 | B03 | Bridge Replacement | ROW | 185 | 2026-06-04 |  | 24767 | 11621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36388
Northwest | 1 | Venango | 97401 | SR 208 Bridge over Little Scrubgrass Creek | 208 | B03 | Bridge Replacement | CON | 185 | 2026-06-04 |  | 2205722 | 2634278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4840000
Northwest | 1 | Venango | 98262 | NW Local Brdg Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 26397 | 1600000 | 1600000 | 1600000 | 1600000 | 6400000 | 12826397
Northwest | 1 | Venango | 98262 | NW Local Brdg Line Item |  |  | Reserve Line Item | CON | 183 |  |  | 0 | 5485 | 0 | 103424 | 30000 | 300000 | 300000 | 300000 | 1200000 | 2238909
Northwest | 1 | Venango | 98532 | SR 417: Keeley Rd - SR 4020 | 417 | 03M | Highway Restoration | PE | STP |  | 2033-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
Northwest | 1 | Venango | 98532 | SR 417: Keeley Rd - SR 4020 | 417 | 03M | Highway Restoration | CON | 581 |  | 2033-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8644070 | 8644070
Northwest | 1 | Venango | 98544 | US 62 & SR 4002: Resurfacing | 62 | 11M | Highway Restoration | PE | 185 | 2029-01-01 |  | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Northwest | 1 | Venango | 98544 | US 62 & SR 4002: Resurfacing | 62 | 11M | Highway Restoration | CON | 185 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 800000 | 600000 | 0 | 0 | 0 | 1400000
Northwest | 1 | Venango | 98544 | US 62 & SR 4002: Resurfacing | 62 | 11M | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 6100000 | 0 | 0 | 0 | 0 | 6100000
Northwest | 1 | Venango | 100152 | SR 157: US 62 - SR 2017 | 157 | 04M | 409 Expanded Maintenance | PE | STP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
Northwest | 1 | Venango | 100152 | SR 157: US 62 - SR 2017 | 157 | 04M | 409 Expanded Maintenance | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3161681 | 2338319 | 5500000
Northwest | 1 | Venango | 100171 | US 322: Whippoorwill Rd. - Clarion Co | 322 | 16M | Highway Restoration | CON | NHPP | 2024-04-11 | 2024-04-11 | 0 | 18074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18074
Northwest | 1 | Venango | 100171 | US 322: Whippoorwill Rd. - Clarion Co | 322 | 16M | Highway Restoration | CON | 581 | 2024-04-11 | 2024-04-11 | 724718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 724718
Northwest | 1 | Venango | 106422 | NW Highway/Bridge Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 850698 | 1003297 | 490000 | 455000 | 551600 | 551600 | 551600 | 2206300 | 6660095
Northwest | 1 | Venango | 106422 | NW Highway/Bridge Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 276980 | 25299 | 300500 | 300500 | 300500 | 300500 | 300500 | 1200000 | 3004779
Northwest | 1 | Venango | 106422 | NW Highway/Bridge Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 0 | 0 | 0 | 982000 | 982000 | 982000 | 982000 | 3928000 | 7856000
Northwest | 1 | Venango | 106422 | NW Highway/Bridge Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 791530 | 1377680 | 1377680 | 1377680 | 1377680 | 1377680 | 1377680 | 5510722 | 14568332
Northwest | 1 | Venango | 106422 | NW Highway/Bridge Line Item |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 472737 | 230651 | 0 | 5520500 | 300000 | 300000 | 300000 | 1200000 | 8323888
Northwest | 1 | Venango | 106422 | NW Highway/Bridge Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 255077 | 52442 | 0 | 2820000 | 300000 | 300000 | 300000 | 1200000 | 5227519
Northwest | 1 | Venango | 106422 | NW Highway/Bridge Line Item |  |  | Reserve Line Item | CON | 183 |  |  | 0 | 40238 | 40900 | 0 | 0 | 0 | 0 | 0 | 0 | 81138
Northwest | 1 | Venango | 106422 | NW Highway/Bridge Line Item |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 0 | 8116 | 300000 | 300500 | 300000 | 299500 | 1200000 | 2408116
Northwest | 1 | Venango | 106422 | NW Highway/Bridge Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 1151681 | 628491 | 988000 | 300500 | 300000 | 300000 | 299500 | 1200000 | 5168172
Northwest | 1 | Venango | 106581 | NW Local Fed Aid Rt Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 195677 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 4000000 | 10195677
Northwest | 1 | Venango | 106582 | NW Betterment Line Item |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2251963 | 2251963
Northwest | 1 | Venango | 106582 | NW Betterment Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7155710 | 7155710
Northwest | 1 | Venango | 106582 | NW Betterment Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3577737 | 3577737
Northwest | 1 | Venango | 109153 | US 62 & 322 from SR 8 to US 322 | 62 | 13M | Highway Restoration | PE | HSIP | 2026-02-26 | 2026-02-26 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northwest | 1 | Venango | 109153 | US 62 & 322 from SR 8 to US 322 | 62 | 13M | Highway Restoration | FD | NHPP | 2026-02-26 | 2026-02-26 | 580800 | 92065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672865
Northwest | 1 | Venango | 109153 | US 62 & 322 from SR 8 to US 322 | 62 | 13M | Highway Restoration | FD | 581 | 2026-02-26 | 2026-02-26 | 145200 | 23016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168216
Northwest | 1 | Venango | 109153 | US 62 & 322 from SR 8 to US 322 | 62 | 13M | Highway Restoration | ROW | NHPP | 2026-02-26 | 2026-02-26 | 88539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88539
Northwest | 1 | Venango | 109153 | US 62 & 322 from SR 8 to US 322 | 62 | 13M | Highway Restoration | ROW | 581 | 2026-02-26 | 2026-02-26 | 22135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22135
Northwest | 1 | Venango | 109153 | US 62 & 322 from SR 8 to US 322 | 62 | 13M | Highway Restoration | CON | HSIP | 2026-02-26 | 2026-02-26 | 0 | 313290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313290
Northwest | 1 | Venango | 109153 | US 62 & 322 from SR 8 to US 322 | 62 | 13M | Highway Restoration | CON | CRP | 2026-02-26 | 2026-02-26 | 933500 | 1098801 | 982000 | 982000 | 0 | 0 | 0 | 0 | 0 | 3996301
Northwest | 1 | Venango | 109153 | US 62 & 322 from SR 8 to US 322 | 62 | 13M | Highway Restoration | CON | HVRU | 2026-02-26 | 2026-02-26 | 291481 | 586150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 877631
Northwest | 1 | Venango | 109153 | US 62 & 322 from SR 8 to US 322 | 62 | 13M | Highway Restoration | CON | NHPP | 2026-02-26 | 2026-02-26 | 0 | 4180513 | 4092065 | 0 | 0 | 0 | 0 | 0 | 0 | 8272578
Northwest | 1 | Venango | 109153 | US 62 & 322 from SR 8 to US 322 | 62 | 13M | Highway Restoration | CON | STP | 2026-02-26 | 2026-02-26 | 0 | 794239 | 326856 | 0 | 0 | 0 | 0 | 0 | 0 | 1121095
Northwest | 1 | Venango | 109153 | US 62 & 322 from SR 8 to US 322 | 62 | 13M | Highway Restoration | CON | 581 | 2026-02-26 | 2026-02-26 | 0 | 762431 | 1585987 | 0 | 0 | 0 | 0 | 0 | 0 | 2348418
Northwest | 1 | Venango | 110984 | SR 227: SR 1006 to SR 27 | 227 | 05M | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 3251942 | 1754605 | 1093453 | 0 | 6100000
Northwest | 1 | Venango | 113217 | 13th Street Franklin RRX | 322 | RRX | Rail Highway Grade Crossing | CON | RRX | 2024-10-23 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Northwest | 1 | Venango | 115532 | Venango SR 3021 Slide (GRP #1) | 3021 | SL1 | Safety Improvement | PE | PRTCT | 2026-06-04 |  | 209000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209000
Northwest | 1 | Venango | 115532 | Venango SR 3021 Slide (GRP #1) | 3021 | SL1 | Safety Improvement | CON | PRTCT | 2026-06-04 |  | 0 | 2090000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2090000
Northwest | 1 | Venango | 116197 | Northwest 2025 RPM |  |  | Safety Improvement | CON | STP | 2025-03-13 | 2025-03-13 | 174935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174935
Northwest | 1 | Venango | 116198 | Northwest 2026 RPM |  |  | Safety Improvement | CON | STP | 2026-03-12 | 2026-03-12 | 0 | 146272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146272
Northwest | 1 | Venango | 116632 | US 62: SR 157 - SR 2025 | 62 | 10M | Highway Restoration | CON | NHPP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1874000 | 4681000 | 490000 | 7045000
Northwest | 1 | Venango | 116633 | SR 27: Venango County | 27 | 02M | Highway Restoration | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
Northwest | 1 | Venango | 116633 | SR 27: Venango County | 27 | 02M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6706779 | 6706779
Northwest | 1 | Venango | 117449 | US 62/SR 8: Start of 4 lanes to SR 428 | 62 | 14M | Highway Restoration | PE | 581 | 2029-01-01 |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Northwest | 1 | Venango | 117449 | US 62/SR 8: Start of 4 lanes to SR 428 | 62 | 14M | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 2200000 | 2000000 | 0 | 0 | 0 | 4200000
Northwest | 1 | Venango | 118221 | Oil City Corridor WNYPA | 1001 | RRX | Rail Highway Grade Crossing | CON | RRX | 2024-07-01 |  | 500000 | 800000 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000
Northwest | 1 | Venango | 118375 | City of Franklin TASA Project 2022 | 62 | T01 | Transportation Enhancement | CON | TAP | 2026-02-26 | 2026-02-26 | 1110000 | 571748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1681748
Northwest | 1 | Venango | 120634 | Northwest 2027 RPM |  |  | Safety Improvement | CON | STP | 2027-02-25 |  | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Northwest | 1 | Venango | 120635 | Northwest 2028 RPM |  |  | Safety Improvement | CON | STP | 2028-01-01 |  | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 160000
Northwest | 1 | Venango | 120814 | US 62: Bridge over Twomile Run | 62 | B23 | Bridge Restoration | PE | 185 | 2030-01-01 |  | 0 | 0 | 0 | 110000 | 140000 | 0 | 0 | 0 | 0 | 250000
Northwest | 1 | Venango | 120814 | US 62: Bridge over Twomile Run | 62 | B23 | Bridge Restoration | CON | 185 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 860000 | 1540392 | 0 | 0 | 2400392
Northwest | 1 | Venango | 121314 | I-80 Venango Co ITS Add at Barkeyville - TSMO | 80 | TS3 | Intelligent Transportation System | CON | CRP | 2025-03-27 | 2025-03-27 | 475122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475122
Northwest | 1 | Venango | 121314 | I-80 Venango Co ITS Add at Barkeyville - TSMO | 80 | TS3 | Intelligent Transportation System | CON | 581 | 2025-03-27 | 2025-03-27 | 118781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118781
Northwest | 1 | Venango | 122343 | Dept. Force Br. Venango |  |  | Bridge Preservation - State Funded | CON | 185 |  |  | 120000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northwest | 1 | Venango | 123350 | SR 38 - Emlenton Hill Imp. | 38 | A01 | Stormwater Management | PE | 581 |  |  | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
Northwest | 1 | Warren | 2474 | PA 426: Corry Road Bridge | 426 | B04 | Bridge Restoration | FD | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 180000
Northwest | 1 | Warren | 2474 | PA 426: Corry Road Bridge | 426 | B04 | Bridge Restoration | ROW | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000
Northwest | 1 | Warren | 2474 | PA 426: Corry Road Bridge | 426 | B04 | Bridge Restoration | CON | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 840000 | 1000000
Northwest | 1 | Warren | 2477 | SR 27: Grand Street Bridge | 27 | B12 | Bridge Replacement | PE | BRIP | 2026-11-05 |  | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Northwest | 1 | Warren | 2477 | SR 27: Grand Street Bridge | 27 | B12 | Bridge Replacement | PE | 185 | 2026-11-05 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Northwest | 1 | Warren | 2477 | SR 27: Grand Street Bridge | 27 | B12 | Bridge Replacement | FD | BRIP | 2026-11-05 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Warren | 2477 | SR 27: Grand Street Bridge | 27 | B12 | Bridge Replacement | ROW | BRIP | 2026-11-05 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northwest | 1 | Warren | 2477 | SR 27: Grand Street Bridge | 27 | B12 | Bridge Replacement | CON | BRIP | 2026-11-05 |  | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Northwest | 1 | Warren | 2477 | SR 27: Grand Street Bridge | 27 | B12 | Bridge Replacement | CON | 185 | 2026-11-05 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northwest | 1 | Warren | 2521 | SR 69: Jackson Run Brdg | 69 | B07 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Warren | 2521 | SR 69: Jackson Run Brdg | 69 | B07 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661315 | 661315
Northwest | 1 | Warren | 2560 | Stewart Rd (T-639) Bridge | 7203 | L00 | Bridge Restoration | FD | BOF | 2028-01-01 |  | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Northwest | 1 | Warren | 2560 | Stewart Rd (T-639) Bridge | 7203 | L00 | Bridge Restoration | FD | 183 | 2028-01-01 |  | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500
Northwest | 1 | Warren | 2560 | Stewart Rd (T-639) Bridge | 7203 | L00 | Bridge Restoration | FD | LOC | 2028-01-01 |  | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
Northwest | 1 | Warren | 2560 | Stewart Rd (T-639) Bridge | 7203 | L00 | Bridge Restoration | ROW | BOF | 2028-01-01 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northwest | 1 | Warren | 2560 | Stewart Rd (T-639) Bridge | 7203 | L00 | Bridge Restoration | ROW | 183 | 2028-01-01 |  | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
Northwest | 1 | Warren | 2560 | Stewart Rd (T-639) Bridge | 7203 | L00 | Bridge Restoration | ROW | LOC | 2028-01-01 |  | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250
Northwest | 1 | Warren | 2560 | Stewart Rd (T-639) Bridge | 7203 | L00 | Bridge Restoration | CON | BOF | 2028-01-01 |  | 0 | 0 | 0 | 527303 | 0 | 0 | 0 | 0 | 0 | 527303
Northwest | 1 | Warren | 2560 | Stewart Rd (T-639) Bridge | 7203 | L00 | Bridge Restoration | CON | 183 | 2028-01-01 |  | 0 | 0 | 0 | 140326 | 0 | 0 | 0 | 0 | 0 | 140326
Northwest | 1 | Warren | 2560 | Stewart Rd (T-639) Bridge | 7203 | L00 | Bridge Restoration | CON | LOC | 2028-01-01 |  | 0 | 0 | 0 | 31579 | 0 | 0 | 0 | 0 | 0 | 31579
Northwest | 1 | Warren | 2581 | SR 62 Bridge over Bully Run | 62 | B06 | Bridge Restoration | PE | 185 | 2031-01-01 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Warren | 2581 | SR 62 Bridge over Bully Run | 62 | B06 | Bridge Restoration | FD | 185 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000
Northwest | 1 | Warren | 2581 | SR 62 Bridge over Bully Run | 62 | B06 | Bridge Restoration | CON | BRIP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 1200000
Northwest | 1 | Warren | 32411 | US 6: Sheffield Resurfacing | 6 | 33M | Highway Restoration | PE | NHPP | 2026-06-18 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Warren | 32411 | US 6: Sheffield Resurfacing | 6 | 33M | Highway Restoration | CON | HSIP | 2026-06-18 |  | 0 | 25180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25180
Northwest | 1 | Warren | 32411 | US 6: Sheffield Resurfacing | 6 | 33M | Highway Restoration | CON | NHPP | 2026-06-18 |  | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000
Northwest | 1 | Warren | 47289 | US 6: Railroad St. to US 6 & 62 Interchange | 6 | 31M | Highway Restoration | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1193161 | 5706839 | 0 | 6900000
Northwest | 1 | Warren | 47290 | US 6: Sheffield to Clarendon | 6 | 32M | Highway Restoration | CON | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636000 | 6500000 | 7136000
Northwest | 1 | Warren | 47291 | US 62: Forest County line to SR 127 | 62 | 32M | Highway Restoration | CON | HSIP | 2026-02-26 | 2026-02-26 | 0 | 45198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45198
Northwest | 1 | Warren | 47291 | US 62: Forest County line to SR 127 | 62 | 32M | Highway Restoration | CON | NHPP | 2026-02-26 | 2026-02-26 | 927063 | 1858622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2785685
Northwest | 1 | Warren | 57178 | US 6: Bridge over Dutchman Run #1 | 6 | B12 | Bridge Restoration | FD | BRIP | 2029-01-01 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Warren | 57178 | US 6: Bridge over Dutchman Run #1 | 6 | B12 | Bridge Restoration | ROW | BRIP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 10877 | 0 | 0 | 0 | 0 | 10877
Northwest | 1 | Warren | 57178 | US 6: Bridge over Dutchman Run #1 | 6 | B12 | Bridge Restoration | CON | BRIP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 750000
Northwest | 1 | Warren | 58298 | SR 27: Matthews Run Bridge | 27 | B11 | Bridge Replacement | CON | 185 | 2024-09-26 | 2024-09-26 | 354041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354041
Northwest | 1 | Warren | 58301 | PA 59: Morrison Run Bridge | 59 | B03 | Bridge Replacement | PE | BRIP | 2028-01-01 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Warren | 58301 | PA 59: Morrison Run Bridge | 59 | B03 | Bridge Replacement | ROW | BRIP | 2028-01-01 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northwest | 1 | Warren | 58301 | PA 59: Morrison Run Bridge | 59 | B03 | Bridge Replacement | CON | 185 | 2028-01-01 |  | 0 | 0 | 0 | 95000 | 905000 | 0 | 0 | 0 | 0 | 1000000
Northwest | 1 | Warren | 58306 | PA 957: Kianetone Creek Bridge - Scour Group | 957 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Northwest | 1 | Warren | 58306 | PA 957: Kianetone Creek Bridge - Scour Group | 957 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Northwest | 1 | Warren | 58306 | PA 957: Kianetone Creek Bridge - Scour Group | 957 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 141210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141210
Northwest | 1 | Warren | 58307 | SR 1011: Conewango Ave Bridge #1 | 1011 | B00 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 0 | 410000
Northwest | 1 | Warren | 58307 | SR 1011: Conewango Ave Bridge #1 | 1011 | B00 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 35000
Northwest | 1 | Warren | 58307 | SR 1011: Conewango Ave Bridge #1 | 1011 | B00 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300000 | 2300000
Northwest | 1 | Warren | 58311 | SR 3004: Caldwell Ck Bridge | 3004 | 000 | Bridge Restoration | PE | BOF | 2030-01-01 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Warren | 58311 | SR 3004: Caldwell Ck Bridge | 3004 | 000 | Bridge Restoration | ROW | BOF | 2030-01-01 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Northwest | 1 | Warren | 58311 | SR 3004: Caldwell Ck Bridge | 3004 | 000 | Bridge Restoration | CON | BOF | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
Northwest | 1 | Warren | 74673 | Warren County TBeam Rehab Group | 62 | B02 | Bridge Restoration | PE | 185 | 2028-01-01 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Northwest | 1 | Warren | 74673 | Warren County TBeam Rehab Group | 62 | B02 | Bridge Restoration | CON | 185 | 2028-01-01 |  | 0 | 0 | 360000 | 140000 | 0 | 0 | 0 | 0 | 0 | 500000
Northwest | 1 | Warren | 78792 | SR 27 over Pine Creek - Bridge Sediment Removal | 27 | BSR | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Northwest | 1 | Warren | 78792 | SR 27 over Pine Creek - Bridge Sediment Removal | 27 | BSR | Bridge Preservation - Federal | ROW | PRTCT | 2026-06-18 |  | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
Northwest | 1 | Warren | 78792 | SR 27 over Pine Creek - Bridge Sediment Removal | 27 | BSR | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Northwest | 1 | Warren | 78792 | SR 27 over Pine Creek - Bridge Sediment Removal | 27 | BSR | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northwest | 1 | Warren | 78941 | SR 1013 Brdg/Glade Run | 1013 | B01 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Warren | 78941 | SR 1013 Brdg/Glade Run | 1013 | B01 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Northwest | 1 | Warren | 78945 | SR 4004 Bridge over Pine Valley | 4004 | B00 | Bridge Restoration | PE | BOF | 2024-09-12 | 2024-09-12 | 1532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1532
Northwest | 1 | Warren | 78945 | SR 4004 Bridge over Pine Valley | 4004 | B00 | Bridge Restoration | CON | BOF | 2024-09-12 | 2024-09-12 | 583082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583082
Northwest | 1 | Warren | 78952 | SR 4015 Bridge over Mill Brook | 4015 | B00 | Bridge Restoration | CON | BOF | 2024-09-12 | 2024-09-12 | 261731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261731
Northwest | 1 | Warren | 78962 | SR 3009 Brdg/Tidioute Creek | 3009 | B05 | Bridge Restoration | FD | BRIP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 120000
Northwest | 1 | Warren | 78962 | SR 3009 Brdg/Tidioute Creek | 3009 | B05 | Bridge Restoration | CON | BRIP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 750000
Northwest | 1 | Warren | 78976 | SR 3009 Brdg/Tidioute Ck | 3009 | B06 | Bridge Restoration | FD | BRIP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
Northwest | 1 | Warren | 78976 | SR 3009 Brdg/Tidioute Ck | 3009 | B06 | Bridge Restoration | CON | BRIP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 300000
Northwest | 1 | Warren | 83015 | US 6: Nelson Road to Barton Run Road | 6 | 19M | Highway Restoration | PE | 581 | 2031-01-01 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northwest | 1 | Warren | 83015 | US 6: Nelson Road to Barton Run Road | 6 | 19M | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 2500000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 3500000
Northwest | 1 | Warren | 84955 | SR 1013 over Fishburn Run | 1013 | B03 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67000 | 33000 | 100000
Northwest | 1 | Warren | 84955 | SR 1013 over Fishburn Run | 1013 | B03 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northwest | 1 | Warren | 84960 | SR 4013 ov Matthews Run | 4013 | B00 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northwest | 1 | Warren | 84960 | SR 4013 ov Matthews Run | 4013 | B00 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000
Northwest | 1 | Warren | 86954 | Warren - SR 59/ SR 3017 Slide (GRP #2) | 59 | SL2 | Safety Improvement | PE | PRTCT | 2027-01-01 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northwest | 1 | Warren | 86954 | Warren - SR 59/ SR 3017 Slide (GRP #2) | 59 | SL2 | Safety Improvement | CON | PRTCT | 2027-01-01 |  | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
Northwest | 1 | Warren | 88491 | SR 3022 Bridge over Brokenstraw Creek | 3022 | B04 | Bridge Restoration | FD | BOF | 2030-01-01 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Northwest | 1 | Warren | 88491 | SR 3022 Bridge over Brokenstraw Creek | 3022 | B04 | Bridge Restoration | ROW | BOF | 2030-01-01 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Northwest | 1 | Warren | 88491 | SR 3022 Bridge over Brokenstraw Creek | 3022 | B04 | Bridge Restoration | CON | BOF | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 365600 | 634400 | 0 | 0 | 1000000
Northwest | 1 | Warren | 88493 | SR 2001 Br ov Tionesta Ck | 2001 | B00 | Bridge Restoration | PE | BOF | 2029-01-01 |  | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
Northwest | 1 | Warren | 88493 | SR 2001 Br ov Tionesta Ck | 2001 | B00 | Bridge Restoration | CON | BOF | 2029-01-01 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
Northwest | 1 | Warren | 89203 | SR 666: SR 948 to US 6 | 666 | 03M | Highway Restoration | CON | HSIP | 2026-06-18 |  | 0 | 26455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26455
Northwest | 1 | Warren | 89203 | SR 666: SR 948 to US 6 | 666 | 03M | Highway Restoration | CON | STP | 2026-06-18 |  | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000
Northwest | 1 | Warren | 97419 | PA 127 Bridge/Allegheny River | 127 | B01 | Bridge Restoration | ROW | BRIP | 2027-09-16 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northwest | 1 | Warren | 97419 | PA 127 Bridge/Allegheny River | 127 | B01 | Bridge Restoration | CON | BRIP | 2027-09-16 |  | 0 | 0 | 2823754 | 776246 | 0 | 0 | 0 | 0 | 0 | 3600000
Northwest | 1 | Warren | 97419 | PA 127 Bridge/Allegheny River | 127 | B01 | Bridge Restoration | CON | 185 | 2027-09-16 |  | 0 | 0 | 562500 | 337500 | 0 | 0 | 0 | 0 | 0 | 900000
Northwest | 1 | Warren | 97432 | SR 3016 Bridge over Brokenstraw Creek | 3016 | B01 | Bridge Restoration | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northwest | 1 | Warren | 97432 | SR 3016 Bridge over Brokenstraw Creek | 3016 | B01 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4390100 | 4390100
Northwest | 1 | Warren | 97436 | PA 666 Bridge/Tionesta Ck | 666 | B03 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 750000
Northwest | 1 | Warren | 97436 | PA 666 Bridge/Tionesta Ck | 666 | B03 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
Northwest | 1 | Warren | 97436 | PA 666 Bridge/Tionesta Ck | 666 | B03 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
Northwest | 1 | Warren | 97437 | PA 957 Bridge / Brokenstraw Ck | 957 | B05 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215000 | 0 | 215000
Northwest | 1 | Warren | 97437 | PA 957 Bridge / Brokenstraw Ck | 957 | B05 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northwest | 1 | Warren | 97437 | PA 957 Bridge / Brokenstraw Ck | 957 | B05 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Northwest | 1 | Warren | 97439 | SR 1005 Br/Kiantone Ck #1 | 1005 | B00 | Bridge Restoration | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
Northwest | 1 | Warren | 97439 | SR 1005 Br/Kiantone Ck #1 | 1005 | B00 | Bridge Restoration | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northwest | 1 | Warren | 97439 | SR 1005 Br/Kiantone Ck #1 | 1005 | B00 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000 | 1300000
Northwest | 1 | Warren | 97446 | SR 1012 Brdg/Akeley Run | 1012 | B03 | Bridge Restoration | CON | 185 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 124000 | 876000 | 0 | 1000000
Northwest | 1 | Warren | 97448 | SR 3014 Br/Brokenstraw Ck | 3014 | B01 | Bridge Replacement | FD | BOF | 2024-12-12 | 2024-12-12 | 136577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136577
Northwest | 1 | Warren | 97448 | SR 3014 Br/Brokenstraw Ck | 3014 | B01 | Bridge Replacement | ROW | BOF | 2024-12-12 | 2024-12-12 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206
Northwest | 1 | Warren | 97448 | SR 3014 Br/Brokenstraw Ck | 3014 | B01 | Bridge Replacement | CON | BOF | 2024-12-12 | 2024-12-12 | 3360793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3360793
Northwest | 1 | Warren | 97449 | US 6 Warren Co. Bridges | 6 | B18 | Bridge Restoration | CON | 185 | 2023-05-11 | 2023-05-11 | 224659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224659
Northwest | 1 | Warren | 97450 | SR 1006 Brdg/Hemlock Run | 1006 | B00 | Bridge Replacement | PE | BOF | 2028-11-02 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northwest | 1 | Warren | 97450 | SR 1006 Brdg/Hemlock Run | 1006 | B00 | Bridge Replacement | FD | BOF | 2028-11-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
Northwest | 1 | Warren | 97450 | SR 1006 Brdg/Hemlock Run | 1006 | B00 | Bridge Replacement | ROW | BOF | 2028-11-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northwest | 1 | Warren | 97450 | SR 1006 Brdg/Hemlock Run | 1006 | B00 | Bridge Replacement | CON | BOF | 2028-11-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
Northwest | 1 | Warren | 97451 | PA 69 Bridge over Jackson Run #2 | 69 | B05 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 180000
Northwest | 1 | Warren | 97451 | PA 69 Bridge over Jackson Run #2 | 69 | B05 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Northwest | 1 | Warren | 97451 | PA 69 Bridge over Jackson Run #2 | 69 | B05 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
Northwest | 1 | Warren | 97458 | US 6 Br/Dutchmans Run #1 | 6 | B20 | Bridge Replacement | PE | BRIP |  |  | 50000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Warren | 97458 | US 6 Br/Dutchmans Run #1 | 6 | B20 | Bridge Replacement | FD | BRIP |  |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Warren | 97458 | US 6 Br/Dutchmans Run #1 | 6 | B20 | Bridge Replacement | ROW | BRIP |  |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northwest | 1 | Warren | 97458 | US 6 Br/Dutchmans Run #1 | 6 | B20 | Bridge Replacement | CON | BRIP |  |  | 0 | 0 | 500000 | 100000 | 0 | 0 | 0 | 0 | 0 | 600000
Northwest | 1 | Warren | 97458 | US 6 Br/Dutchmans Run #1 | 6 | B20 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 125000 | 25000 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Warren | 97919 | SR 3007: Davey Hill Slide | 3007 | SL1 | Safety Improvement | CON | 581 | 2026-05-07 |  | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
Northwest | 1 | Warren | 98579 | US 6 & SR 27 & US 6 & SR 3016 Intersections | 27 | A00 | Highway Reconstruction | PE | 581 | 2029-01-01 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Northwest | 1 | Warren | 100323 | Pennsylvania Ave/Market St Intersection | 1017 | A00 | Highway Restoration | CON | NHPP | 2022-07-28 | 2022-07-28 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Northwest | 1 | Warren | 100323 | Pennsylvania Ave/Market St Intersection | 1017 | A00 | Highway Restoration | CON | 581 | 2022-07-28 | 2022-07-28 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Northwest | 1 | Warren | 100366 | SR 127, 3007, and 3009 in Tidioute | 127 | 01M | Highway Restoration | PE | 581 | 2026-06-18 | 2017-05-18 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Northwest | 1 | Warren | 100366 | SR 127, 3007, and 3009 in Tidioute | 127 | 01M | Highway Restoration | CON | STP | 2026-06-18 | 2017-05-18 | 0 | 1473000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1473000
Northwest | 1 | Warren | 100366 | SR 127, 3007, and 3009 in Tidioute | 127 | 01M | Highway Restoration | CON | 581 | 2026-06-18 | 2017-05-18 | 0 | 1560000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1560000
Northwest | 1 | Warren | 100445 | Pennsylvania Ave to Cole Hill Road | 1013 | 02M | Highway Restoration | PE | 581 | 2029-01-01 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Warren | 100445 | Pennsylvania Ave to Cole Hill Road | 1013 | 02M | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 1000000 | 4564058 | 3114634 | 0 | 0 | 8678692
Northwest | 1 | Warren | 100504 | SR 3007: PBR | 3007 | PBR | Safety Improvement | PE | 581 | 2017-05-08 | 2017-05-18 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000
Northwest | 1 | Warren | 100504 | SR 3007: PBR | 3007 | PBR | Safety Improvement | CON | 581 | 2017-05-08 | 2017-05-18 | 198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198000
Northwest | 1 | Warren | 110818 | James Morrison Bridge Rehabilitation Phase 2 | 59 | B07 | Bridge Restoration | CON | BRIP | 2024-02-29 | 2024-02-29 | 879582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 879582
Northwest | 1 | Warren | 115377 | SR 27: SR 3011 to Depot Street | 27 | 671 | 409 Expanded Maintenance | CON | STP | 2026-12-03 |  | 0 | 0 | 1918702 | 981298 | 0 | 0 | 0 | 0 | 0 | 2900000
Northwest | 1 | Warren | 116656 | State Route 958 | 958 | 01M | Highway Restoration | PE | 581 | 2030-01-01 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
Northwest | 1 | Warren | 116656 | State Route 958 | 958 | 01M | Highway Restoration | CON | STP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 4000000 | 2290400 | 0 | 0 | 6290400
Northwest | 1 | Warren | 116656 | State Route 958 | 958 | 01M | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 572600 | 0 | 0 | 1572600
Northwest | 1 | Warren | 116870 | SR 69: SR 62 - Creamer Road | 69 | 02M | Highway Restoration | PE | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Northwest | 1 | Warren | 116870 | SR 69: SR 62 - Creamer Road | 69 | 02M | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6341784 | 6341784
Northwest | 1 | Warren | 117657 | SR 59: Kinzua Road | 59 | 12M | Highway Restoration | PE | STP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 118702 | 0 | 0 | 0 | 0 | 118702
Northwest | 1 | Warren | 117657 | SR 59: Kinzua Road | 59 | 12M | Highway Restoration | CON | STP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 2155000 | 3414600 | 5580000 | 2284715 | 13434315
Northwest | 1 | Warren | 117804 | SR 62 Bridge over Wiltse Run | 62 | B07 | Bridge Restoration | FD | 185 | 2031-01-01 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Northwest | 1 | Warren | 117804 | SR 62 Bridge over Wiltse Run | 62 | B07 | Bridge Restoration | ROW | 185 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000
Northwest | 1 | Warren | 117804 | SR 62 Bridge over Wiltse Run | 62 | B07 | Bridge Restoration | CON | BRIP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 900000
Northwest | 1 | Warren | 117841 | US 6 over Dutchman Run - Scour Group | 6 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Northwest | 1 | Warren | 117841 | US 6 over Dutchman Run - Scour Group | 6 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Northwest | 1 | Warren | 117841 | US 6 over Dutchman Run - Scour Group | 6 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 306101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306101
Northwest | 1 | Warren | 119782 | SR 2004: Horton Avenue | 2004 | 01M | Highway Restoration | CON | STP | 2026-06-18 |  | 620000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620000
Northwest | 1 | Warren | 120815 | State Route 3007 Bridge | 3007 | B05 | Bridge Restoration | PE | BOF | 2031-01-01 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Northwest | 1 | Warren | 120815 | State Route 3007 Bridge | 3007 | B05 | Bridge Restoration | ROW | BOF | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000
Northwest | 1 | Warren | 120815 | State Route 3007 Bridge | 3007 | B05 | Bridge Restoration | CON | BOF | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 0 | 0 | 650000
Northwest | 1 | Warren | 120832 | SR 1011: Conewango Ave Bridges #2 | 1011 | B01 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000 | 0 | 360000
Northwest | 1 | Warren | 120832 | SR 1011: Conewango Ave Bridges #2 | 1011 | B01 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000
Northwest | 1 | Warren | 120832 | SR 1011: Conewango Ave Bridges #2 | 1011 | B01 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 1900000
Northwest | 1 | Warren | 120844 | SR 62 over Slater Run | 62 | B10 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Northwest | 1 | Warren | 120844 | SR 62 over Slater Run | 62 | B10 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000
Northwest | 1 | Warren | 120844 | SR 62 over Slater Run | 62 | B10 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165800 | 1165800
Northwest | 1 | Warren | 120847 | SR 666 over Two Mile Run | 666 | B04 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 140000
Northwest | 1 | Warren | 120847 | SR 666 over Two Mile Run | 666 | B04 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Northwest | 1 | Warren | 120848 | SR 2004 over Two Mile Run | 2004 | 0 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 180000
Northwest | 1 | Warren | 120848 | SR 2004 over Two Mile Run | 2004 | 0 | Bridge Restoration | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 16000
Northwest | 1 | Warren | 120848 | SR 2004 over Two Mile Run | 2004 | 0 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000 | 1100000
Northwest | 1 | Warren | 121704 | City of Warren LFAR - 2025-2026 |  | F05 | Highway Restoration | CON | STP | 2026-02-12 | 2026-02-12 | 800000 | 804323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1604323
Northwest | 1 | Warren | 122344 | Dept. Force Br. Warren |  |  | Bridge Preservation - State Funded | CON | 185 |  |  | 100000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000
Northwest | 1 | Warren | 123096 | SR 4010 over Jackson Run - Scour Group | 4010 | BSC | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Northwest | 1 | Warren | 123096 | SR 4010 over Jackson Run - Scour Group | 4010 | BSC | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Northwest | 1 | Warren | 123096 | SR 4010 over Jackson Run - Scour Group | 4010 | BSC | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 129011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129011
Northwest | 10 | Clarion | 25087 | T-327 Shettler Bridge | 7202 | 350 | Bridge Replacement | PE | BOF | 2027-10-07 |  | 0 | 70400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70400
Northwest | 10 | Clarion | 25087 | T-327 Shettler Bridge | 7202 | 350 | Bridge Replacement | FD | BOF | 2027-10-07 |  | 0 | 333600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333600
Northwest | 10 | Clarion | 25087 | T-327 Shettler Bridge | 7202 | 350 | Bridge Replacement | ROW | BOF | 2027-10-07 |  | 0 | 21300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21300
Northwest | 10 | Clarion | 25087 | T-327 Shettler Bridge | 7202 | 350 | Bridge Replacement | UTL | BOF | 2027-10-07 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Northwest | 10 | Clarion | 25087 | T-327 Shettler Bridge | 7202 | 350 | Bridge Replacement | CON | BOF | 2027-10-07 |  | 0 | 0 | 327916 | 600984 | 0 | 0 | 0 | 0 | 0 | 928900
Northwest | 10 | Clarion | 25090 | T-385 Eagle Furnace Bridge | 7202 | 351 | Bridge Restoration | PE | BOF | 2029-02-15 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Northwest | 10 | Clarion | 25090 | T-385 Eagle Furnace Bridge | 7202 | 351 | Bridge Restoration | FD | BOF | 2029-02-15 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
Northwest | 10 | Clarion | 25090 | T-385 Eagle Furnace Bridge | 7202 | 351 | Bridge Restoration | ROW | BOF | 2029-02-15 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
Northwest | 10 | Clarion | 25090 | T-385 Eagle Furnace Bridge | 7202 | 351 | Bridge Restoration | UTL | BOF | 2029-02-15 |  | 0 | 0 | 0 | 0 | 0 | 64000 | 0 | 0 | 0 | 64000
Northwest | 10 | Clarion | 25090 | T-385 Eagle Furnace Bridge | 7202 | 351 | Bridge Restoration | UTL | 185 | 2029-02-15 |  | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 16000
Northwest | 10 | Clarion | 25090 | T-385 Eagle Furnace Bridge | 7202 | 351 | Bridge Restoration | CON | BOF | 2029-02-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 423200 | 604800 | 0 | 1028000
Northwest | 10 | Clarion | 25121 | Groce Hill Bridge | 4001 | 351 | Bridge Replacement | PE | BOF | 2028-10-19 |  | 318058 | 151942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470000
Northwest | 10 | Clarion | 25121 | Groce Hill Bridge | 4001 | 351 | Bridge Replacement | FD | BOF | 2028-10-19 |  | 0 | 0 | 0 | 0 | 0 | 360000 | 0 | 0 | 0 | 360000
Northwest | 10 | Clarion | 25121 | Groce Hill Bridge | 4001 | 351 | Bridge Replacement | FD | 185 | 2028-10-19 |  | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 90000
Northwest | 10 | Clarion | 25121 | Groce Hill Bridge | 4001 | 351 | Bridge Replacement | ROW | BOF | 2028-10-19 |  | 0 | 0 | 0 | 0 | 0 | 79816 | 0 | 0 | 0 | 79816
Northwest | 10 | Clarion | 25121 | Groce Hill Bridge | 4001 | 351 | Bridge Replacement | UTL | BOF | 2028-10-19 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
Northwest | 10 | Clarion | 25121 | Groce Hill Bridge | 4001 | 351 | Bridge Replacement | CON | BOF | 2028-10-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630200 | 4939000 | 5569200
Northwest | 10 | Clarion | 25170 | Little Licking Creek Bridge #1 | 68 | 362 | Bridge Replacement | FD | BRIP | 2026-06-04 |  | 483300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483300
Northwest | 10 | Clarion | 25170 | Little Licking Creek Bridge #1 | 68 | 362 | Bridge Replacement | ROW | 185 | 2026-06-04 |  | 0 | 112832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112832
Northwest | 10 | Clarion | 25170 | Little Licking Creek Bridge #1 | 68 | 362 | Bridge Replacement | UTL | BRIP | 2026-06-04 |  | 115270 | 134730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Northwest | 10 | Clarion | 25170 | Little Licking Creek Bridge #1 | 68 | 362 | Bridge Replacement | CON | CRP | 2026-06-04 |  | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000
Northwest | 10 | Clarion | 25170 | Little Licking Creek Bridge #1 | 68 | 362 | Bridge Replacement | CON | 185 | 2026-06-04 |  | 0 | 80000 | 470421 | 599904 | 864847 | 341166 | 143662 | 0 | 0 | 2500000
Northwest | 10 | Clarion | 25249 | Huefner Bridge #2 | 4008 | 352 | Bridge Replacement | PE | BOF | 2050-01-01 |  | 0 | 0 | 0 | 391316 | 84684 | 0 | 0 | 0 | 0 | 476000
Northwest | 10 | Clarion | 25249 | Huefner Bridge #2 | 4008 | 352 | Bridge Replacement | FD | BOF | 2050-01-01 |  | 0 | 0 | 0 | 0 | 200316 | 147784 | 0 | 0 | 0 | 348100
Northwest | 10 | Clarion | 25249 | Huefner Bridge #2 | 4008 | 352 | Bridge Replacement | ROW | BOF | 2050-01-01 |  | 0 | 0 | 0 | 0 | 0 | 116000 | 0 | 0 | 0 | 116000
Northwest | 10 | Clarion | 25249 | Huefner Bridge #2 | 4008 | 352 | Bridge Replacement | UTL | BOF | 2050-01-01 |  | 0 | 0 | 0 | 0 | 0 | 17400 | 0 | 0 | 0 | 17400
Northwest | 10 | Clarion | 25249 | Huefner Bridge #2 | 4008 | 352 | Bridge Replacement | CON | BOF | 2050-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 811800 | 0 | 0 | 811800
Northwest | 10 | Clarion | 70209 | Clarion Hwy/Bridge Line |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 218002 | 665510 | 0 | 0 | 0 | 0 | 883512
Northwest | 10 | Clarion | 70209 | Clarion Hwy/Bridge Line |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 0 | 220697 | 802018 | 548941 | 0 | 0 | 0 | 1571656
Northwest | 10 | Clarion | 70209 | Clarion Hwy/Bridge Line |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 0 | 297320 | 320 | 16320 | 308320 | 308320 | 308320 | 1233278 | 2472198
Northwest | 10 | Clarion | 70209 | Clarion Hwy/Bridge Line |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 65760 | 0 | 686000 | 0 | 0 | 0 | 0 | 751760
Northwest | 10 | Clarion | 70209 | Clarion Hwy/Bridge Line |  |  | Reserve Line Item | CON | STP |  |  | 0 | 0 | 102603 | 893743 | 1300000 | 1456625 | 0 | 0 | 0 | 3752971
Northwest | 10 | Clarion | 70209 | Clarion Hwy/Bridge Line |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 80676 | 375196 | 113153 | 107347 | 0 | 0 | 0 | 676372
Northwest | 10 | Clarion | 70209 | Clarion Hwy/Bridge Line |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 801142 | 0 | 0 | 0 | 0 | 801142
Northwest | 10 | Clarion | 78061 | T-619 Moore Drive Bridge | 7206 | 350 | Bridge Replacement | PE | BOF | 2029-10-18 |  | 406942 | 47058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454000
Northwest | 10 | Clarion | 78061 | T-619 Moore Drive Bridge | 7206 | 350 | Bridge Replacement | FD | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 350000
Northwest | 10 | Clarion | 78061 | T-619 Moore Drive Bridge | 7206 | 350 | Bridge Replacement | ROW | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 25500 | 0 | 0 | 0 | 25500
Northwest | 10 | Clarion | 78061 | T-619 Moore Drive Bridge | 7206 | 350 | Bridge Replacement | UTL | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
Northwest | 10 | Clarion | 78061 | T-619 Moore Drive Bridge | 7206 | 350 | Bridge Replacement | CON | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075000 | 1075000
Northwest | 10 | Clarion | 78062 | Pilgrimham Bridge #2 | 208 | 354 | Bridge Replacement | PE | BRIP | 2027-10-21 |  | 300000 | 119000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 419000
Northwest | 10 | Clarion | 78062 | Pilgrimham Bridge #2 | 208 | 354 | Bridge Replacement | FD | BRIP | 2027-10-21 |  | 0 | 240751 | 240249 | 0 | 0 | 0 | 0 | 0 | 0 | 481000
Northwest | 10 | Clarion | 78062 | Pilgrimham Bridge #2 | 208 | 354 | Bridge Replacement | ROW | BRIP | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Northwest | 10 | Clarion | 78062 | Pilgrimham Bridge #2 | 208 | 354 | Bridge Replacement | ROW | 185 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 5000
Northwest | 10 | Clarion | 78062 | Pilgrimham Bridge #2 | 208 | 354 | Bridge Replacement | UTL | BRIP | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 12000
Northwest | 10 | Clarion | 78062 | Pilgrimham Bridge #2 | 208 | 354 | Bridge Replacement | UTL | 185 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 3000
Northwest | 10 | Clarion | 78062 | Pilgrimham Bridge #2 | 208 | 354 | Bridge Replacement | CON | BRIP | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 976059 | 63941 | 0 | 1040000
Northwest | 10 | Clarion | 78062 | Pilgrimham Bridge #2 | 208 | 354 | Bridge Replacement | CON | 185 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 244015 | 15985 | 0 | 260000
Northwest | 10 | Clarion | 91864 | SR1007 Greenville Pike Resurf | 1007 | 307 | Preventive Maintenance | CON | 581 | 2031-04-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647756 | 1371844 | 2019600
Northwest | 10 | Clarion | 99588 | Knox North PM | 338 | 304 | Preventive Maintenance | CON | STP | 2050-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2470713 | 2470713
Northwest | 10 | Clarion | 99595 | SR 861-Leatherwood West Resurfacing | 861 | 303 | Highway Restoration | CON | 581 | 2030-03-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2292336 | 2292336
Northwest | 10 | Clarion | 99659 | US 322 Clarion to Strattanville Resurfacing | 322 | 310 | Preventive Maintenance | CON | 581 | 2026-09-03 |  | 0 | 1570000 | 499123 | 0 | 0 | 0 | 0 | 0 | 0 | 2069123
Northwest | 10 | Clarion | 100126 | PA68 Rimersburg Resurface | 68 | 304 | General Maintenance | CON | 581 | 2025-03-27 | 2025-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 3047880 | 2120800 | 0 | 5168680
Northwest | 10 | Clarion | 106502 | PA 68 Dolby Street to Trout Run | 68 | 376 | Safety Improvement | ROW | STP | 2024-09-26 | 2024-09-26 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000
Northwest | 10 | Clarion | 106502 | PA 68 Dolby Street to Trout Run | 68 | 376 | Safety Improvement | ROW | 581 | 2024-09-26 | 2024-09-26 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
Northwest | 10 | Clarion | 106502 | PA 68 Dolby Street to Trout Run | 68 | 376 | Safety Improvement | UTL | NHPP | 2024-09-26 | 2024-09-26 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
Northwest | 10 | Clarion | 106502 | PA 68 Dolby Street to Trout Run | 68 | 376 | Safety Improvement | UTL | 581 | 2024-09-26 | 2024-09-26 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
Northwest | 10 | Clarion | 106502 | PA 68 Dolby Street to Trout Run | 68 | 376 | Safety Improvement | CON | NHPP | 2024-09-26 | 2024-09-26 | 875500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875500
Northwest | 10 | Clarion | 106502 | PA 68 Dolby Street to Trout Run | 68 | 376 | Safety Improvement | CON | STP | 2024-09-26 | 2024-09-26 | 2495825 | 2169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2497994
Northwest | 10 | Clarion | 106502 | PA 68 Dolby Street to Trout Run | 68 | 376 | Safety Improvement | CON | SXF | 2024-09-26 | 2024-09-26 | 93258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93258
Northwest | 10 | Clarion | 106502 | PA 68 Dolby Street to Trout Run | 68 | 376 | Safety Improvement | CON | 581 | 2024-09-26 | 2024-09-26 | 0 | 0 | 170890 | 3541405 | 589123 | 0 | 0 | 0 | 0 | 4301418
Northwest | 10 | Clarion | 110092 | SR 2009 Rimersburg Bridge | 2009 | 351 | Bridge Replacement | UTL | 185 | 2023-10-19 | 2023-10-19 | 4879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4879
Northwest | 10 | Clarion | 110092 | SR 2009 Rimersburg Bridge | 2009 | 351 | Bridge Replacement | CON | 185 | 2023-10-19 | 2023-10-19 | 2860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2860
Northwest | 10 | Clarion | 110093 | US 322 Paint Creek Bridge | 322 | 353 | Bridge Replacement | FD | BRIP | 2026-08-13 |  | 49209 | 132498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181707
Northwest | 10 | Clarion | 110093 | US 322 Paint Creek Bridge | 322 | 353 | Bridge Replacement | ROW | 185 | 2026-08-13 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Northwest | 10 | Clarion | 110093 | US 322 Paint Creek Bridge | 322 | 353 | Bridge Replacement | UTL | 581 | 2026-08-13 |  | 143800 | 143800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287600
Northwest | 10 | Clarion | 110093 | US 322 Paint Creek Bridge | 322 | 353 | Bridge Replacement | CON | BRIP | 2026-08-13 |  | 0 | 329417 | 911251 | 426987 | 0 | 0 | 0 | 0 | 0 | 1667655
Northwest | 10 | Clarion | 110093 | US 322 Paint Creek Bridge | 322 | 353 | Bridge Replacement | CON | NHPP | 2026-08-13 |  | 0 | 858000 | 693740 | 686000 | 0 | 0 | 0 | 0 | 0 | 2237740
Northwest | 10 | Clarion | 110093 | US 322 Paint Creek Bridge | 322 | 353 | Bridge Replacement | CON | STP | 2026-08-13 |  | 0 | 1518831 | 1417397 | 266457 | 0 | 0 | 0 | 0 | 0 | 3202685
Northwest | 10 | Clarion | 111828 | Clarion Co. Department Force Bridge Maintenance | 28 | 0 | Bridge Restoration | CON | 185 | 2026-10-01 |  | 113300 | 116700 | 120200 | 123900 | 120000 | 120000 | 120000 | 120000 | 480000 | 1434100
Northwest | 10 | Clarion | 112946 | SR 66 PM Phase 2 | 66 | 310 | Preventive Maintenance | CON | 581 | 2024-01-11 | 2024-01-11 | 1837826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1837826
Northwest | 10 | Clarion | 113663 | SR 66 Leeper to County Line | 66 | 312 | General Maintenance | CON | 581 | 2029-02-15 |  | 0 | 0 | 0 | 0 | 411176 | 2644679 | 326620 | 604444 | 784821 | 4771740
Northwest | 10 | Clarion | 114518 | SR 68 Reidsburg PM | 68 | 305 | Preventive Maintenance | CON | 581 | 2033-03-10 |  | 0 | 0 | 0 | 0 | 347299 | 729821 | 0 | 0 | 674952 | 1752072
Northwest | 10 | Clarion | 114858 | US 322 Elmo to Shippenville | 322 | 308 | Preventive Maintenance | CON | 581 | 2026-04-09 |  | 473418 | 1134200 | 2175487 | 6595 | 0 | 0 | 0 | 0 | 0 | 3789700
Northwest | 10 | Clarion | 115141 | SR 66 - I-80 North Resurfacing | 66 | 313 | Highway Restoration | CON | 581 | 2027-04-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1815179 | 1815179
Northwest | 10 | Clarion | 115163 | US 322 County Line East PM | 322 | 312 | Preventive Maintenance | CON | NHPP | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 343000 | 343000 | 343000 | 1460344 | 2489344
Northwest | 10 | Clarion | 115163 | US 322 County Line East PM | 322 | 312 | Preventive Maintenance | CON | 581 | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 85750 | 85750 | 85750 | 365086 | 622336
Northwest | 10 | Clarion | 117212 | Clarion Bridge Epoxy Group | 28 | 352 | Bridge Preservation - Federal | CON | BRIP | 2025-01-30 | 2025-01-30 | 203721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203721
Northwest | 10 | Clarion | 117296 | Paint Mills Bridge | 4029 | 350 | Bridge Replacement | CON | BOF | 2025-08-07 | 2025-08-07 | 0 | 535700 | 907084 | 24698 | 284490 | 0 | 0 | 0 | 0 | 1751972
Northwest | 10 | Clarion | 117296 | Paint Mills Bridge | 4029 | 350 | Bridge Replacement | CON | BRIP | 2025-08-07 | 2025-08-07 | 0 | 195104 | 0 | 503816 | 0 | 0 | 0 | 0 | 0 | 698920
Northwest | 10 | Clarion | 117303 | Frank James Walls Memorial Bridge | 322 | 356 | Bridge Restoration | PE | 581 |  |  | 0 | 0 | 382500 | 0 | 0 | 0 | 0 | 0 | 0 | 382500
Northwest | 10 | Clarion | 117303 | Frank James Walls Memorial Bridge | 322 | 356 | Bridge Restoration | FD | STP |  |  | 0 | 0 | 0 | 230300 | 220000 | 0 | 0 | 0 | 0 | 450300
Northwest | 10 | Clarion | 117303 | Frank James Walls Memorial Bridge | 322 | 356 | Bridge Restoration | ROW | STP |  |  | 0 | 0 | 0 | 16900 | 0 | 0 | 0 | 0 | 0 | 16900
Northwest | 10 | Clarion | 117303 | Frank James Walls Memorial Bridge | 322 | 356 | Bridge Restoration | UTL | STP |  |  | 0 | 0 | 0 | 112600 | 0 | 0 | 0 | 0 | 0 | 112600
Northwest | 10 | Clarion | 117303 | Frank James Walls Memorial Bridge | 322 | 356 | Bridge Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 63375 | 1520000 | 1520000 | 2676625 | 5780000
Northwest | 10 | Clarion | 117309 | Huckleberry Ridge Bridge Preservation | 2007 | 355 | Bridge Restoration | CON | BRIP | 2028-10-05 |  | 0 | 0 | 0 | 0 | 349482 | 0 | 0 | 0 | 0 | 349482
Northwest | 10 | Clarion | 117313 | Alum Rock Bridge #3 Preservation | 3020 | 353 | Bridge Preservation - State Funded | CON | 185 | 2031-10-02 |  | 0 | 0 | 147400 | 0 | 0 | 0 | 0 | 0 | 0 | 147400
Northwest | 10 | Clarion | 117316 | Canoe Furnace Bridge | 4005 | 352 | Bridge Preservation - State Funded | CON | 185 | 2027-11-25 |  | 0 | 0 | 156900 | 0 | 0 | 0 | 0 | 0 | 0 | 156900
Northwest | 10 | Clarion | 117318 | East Sligo Bridge | 68 | 357 | Bridge Preservation - State Funded | CON | 185 | 2050-01-01 |  | 0 | 0 | 93700 | 0 | 0 | 0 | 0 | 0 | 0 | 93700
Northwest | 10 | Clarion | 117319 | SR 28 Hawthorn North PM | 28 | 311 | Preventive Maintenance | CON | 581 | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4024240 | 4024240
Northwest | 10 | Clarion | 117322 | Cooksburg Bridge Preservation | 36 | 351 | Bridge Restoration | FD | BRIP | 2031-10-02 |  | 0 | 0 | 0 | 0 | 0 | 170059 | 149941 | 0 | 0 | 320000
Northwest | 10 | Clarion | 117322 | Cooksburg Bridge Preservation | 36 | 351 | Bridge Restoration | FD | 185 | 2031-10-02 |  | 0 | 0 | 0 | 0 | 0 | 42515 | 37485 | 0 | 0 | 80000
Northwest | 10 | Clarion | 117322 | Cooksburg Bridge Preservation | 36 | 351 | Bridge Restoration | UTL | BRIP | 2031-10-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25500 | 0 | 0 | 25500
Northwest | 10 | Clarion | 117322 | Cooksburg Bridge Preservation | 36 | 351 | Bridge Restoration | CON | BRIP | 2031-10-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1087559 | 1012941 | 2100500
Northwest | 10 | Clarion | 117325 | Craig Road Bridge | 3013 | 350 | Bridge Preservation - Federal | PE | BOF | 2027-01-28 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Northwest | 10 | Clarion | 117325 | Craig Road Bridge | 3013 | 350 | Bridge Preservation - Federal | FD | BRIP | 2027-01-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000
Northwest | 10 | Clarion | 117325 | Craig Road Bridge | 3013 | 350 | Bridge Preservation - Federal | ROW | BRIP | 2027-01-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
Northwest | 10 | Clarion | 117325 | Craig Road Bridge | 3013 | 350 | Bridge Preservation - Federal | UTL | BRIP | 2027-01-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
Northwest | 10 | Clarion | 117325 | Craig Road Bridge | 3013 | 350 | Bridge Preservation - Federal | CON | BRIP | 2027-01-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1688300 | 1688300
Northwest | 10 | Clarion | 117328 | SR 157/SR 208 Ramp Removal | 157 | 0 | Safety Improvement | FD | HSIP | 2050-01-01 |  | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 5500
Northwest | 10 | Clarion | 117328 | SR 157/SR 208 Ramp Removal | 157 | 0 | Safety Improvement | CON | HSIP | 2050-01-01 |  | 0 | 0 | 0 | 154000 | 146000 | 0 | 0 | 0 | 0 | 300000
Northwest | 10 | Clarion | 117329 | SR 36/SR 208 Ramp Removal | 36 | 0 | Safety Improvement | FD | HSIP | 2050-01-01 |  | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 5500
Northwest | 10 | Clarion | 117329 | SR 36/SR 208 Ramp Removal | 36 | 0 | Safety Improvement | CON | HSIP | 2050-01-01 |  | 0 | 0 | 0 | 154000 | 146000 | 0 | 0 | 0 | 0 | 300000
Northwest | 10 | Clarion | 117547 | Pilgrimham Bridge #1 | 208 | 353 | Bridge Replacement | UTL | 185 | 2025-01-09 | 2025-01-09 | 0 | 2972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2972
Northwest | 10 | Clarion | 117547 | Pilgrimham Bridge #1 | 208 | 353 | Bridge Replacement | CON | 185 | 2025-01-09 | 2025-01-09 | 751961 | 639496 | 30703 | 0 | 0 | 0 | 0 | 0 | 0 | 1422160
Northwest | 10 | Clarion | 117749 | SR 4029 Little Paint Creek Bridge | 4029 | 351 | Bridge Replacement | PE | 185 | 2032-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 160638 | 0 | 0 | 160638
Northwest | 10 | Clarion | 117749 | SR 4029 Little Paint Creek Bridge | 4029 | 351 | Bridge Replacement | FD | 185 | 2032-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 17862 | 182138 | 0 | 200000
Northwest | 10 | Clarion | 117749 | SR 4029 Little Paint Creek Bridge | 4029 | 351 | Bridge Replacement | ROW | 185 | 2032-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000
Northwest | 10 | Clarion | 117749 | SR 4029 Little Paint Creek Bridge | 4029 | 351 | Bridge Replacement | UTL | 185 | 2032-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 30000
Northwest | 10 | Clarion | 117749 | SR 4029 Little Paint Creek Bridge | 4029 | 351 | Bridge Replacement | CON | 185 | 2032-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339362 | 100000 | 439362
Northwest | 10 | Clarion | 117751 | Huefner Bridge #1 | 4008 | 351 | Bridge Replacement | PE | 185 | 2028-10-05 |  | 250000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
Northwest | 10 | Clarion | 117751 | Huefner Bridge #1 | 4008 | 351 | Bridge Replacement | FD | 185 | 2028-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 56338 | 143662 | 0 | 200000
Northwest | 10 | Clarion | 117751 | Huefner Bridge #1 | 4008 | 351 | Bridge Replacement | ROW | 185 | 2028-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000
Northwest | 10 | Clarion | 117751 | Huefner Bridge #1 | 4008 | 351 | Bridge Replacement | UTL | 185 | 2028-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 10000
Northwest | 10 | Clarion | 117751 | Huefner Bridge #1 | 4008 | 351 | Bridge Replacement | CON | 185 | 2028-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113825 | 342013 | 455838
Northwest | 10 | Clarion | 118049 | SR 68 Clarion South PM | 68 | 306 | Preventive Maintenance | CON | 581 |  |  | 0 | 0 | 0 | 0 | 1398760 | 0 | 0 | 0 | 0 | 1398760
Northwest | 10 | Clarion | 118370 | Sligo Pedestrian Bridge |  | 382 | Federal Safe Routes to Schools | CON | SRTSF | 2025-10-09 | 2025-10-09 | 761500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 761500
Northwest | 10 | Clarion | 118370 | Sligo Pedestrian Bridge |  | 382 | Federal Safe Routes to Schools | CON | TAP | 2025-10-09 | 2025-10-09 | 471531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471531
Northwest | 10 | Clarion | 119693 | D10/Clarion Carbon Reduction Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 28500 | 269000 | 269000 | 269000 | 269000 | 269000 | 269000 | 269000 | 1077000 | 2988500
Northwest | 10 | Clarion | 119889 | US 322 Marianne to Clarion Resurfacing | 322 | 310 | Preventive Maintenance | CON | NHPP | 2033-03-10 |  | 0 | 0 | 0 | 0 | 0 | 343000 | 343000 | 343000 | 778168 | 1807168
Northwest | 10 | Clarion | 119889 | US 322 Marianne to Clarion Resurfacing | 322 | 310 | Preventive Maintenance | CON | 581 | 2033-03-10 |  | 0 | 0 | 0 | 0 | 0 | 85750 | 85750 | 85750 | 194542 | 451792
Northwest | 10 | Clarion | 120043 | District 10/NW High Friction Surface Treatment | 66 | ST1 | Safety Improvement | CON | HSIP | 2023-12-14 | 2023-12-14 | 43807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43807
Northwest | 10 | Clarion | 120140 | Clarion Area Congested Corridor Improvements |  |  | Congestion Reduction | PE | CRP |  |  | 119000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119000
Northwest | 10 | Clarion | 120895 | Clarion Concrete Group PM | 28 | 311 | Preventive Maintenance | CON | NHPP | 2029-01-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 505488 | 505488
Northwest | 10 | Clarion | 120895 | Clarion Concrete Group PM | 28 | 311 | Preventive Maintenance | CON | STP | 2029-01-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931662 | 931662
Northwest | 10 | Clarion | 120921 | Engle Run Bridge | 1006 | 350 | Bridge Replacement | PE | 185 | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 300000 | 100000 | 0 | 0 | 400000
Northwest | 10 | Clarion | 120921 | Engle Run Bridge | 1006 | 350 | Bridge Replacement | FD | 185 | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 72472 | 147000 | 180528 | 0 | 400000
Northwest | 10 | Clarion | 120921 | Engle Run Bridge | 1006 | 350 | Bridge Replacement | ROW | 185 | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Northwest | 10 | Clarion | 120921 | Engle Run Bridge | 1006 | 350 | Bridge Replacement | UTL | 185 | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Northwest | 10 | Clarion | 120921 | Engle Run Bridge | 1006 | 350 | Bridge Replacement | CON | 185 | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 650000
Northwest | 10 | Clarion | 120922 | Veterans Memorial Bridge Preservation | 368 | 351 | Bridge Preservation - Federal | FD | 185 | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Northwest | 10 | Clarion | 120922 | Veterans Memorial Bridge Preservation | 368 | 351 | Bridge Preservation - Federal | UTL | 185 | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
Northwest | 10 | Clarion | 120922 | Veterans Memorial Bridge Preservation | 368 | 351 | Bridge Preservation - Federal | CON | BRIP | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 427759 | 427759
Northwest | 10 | Clarion | 120922 | Veterans Memorial Bridge Preservation | 368 | 351 | Bridge Preservation - Federal | CON | 185 | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2191987 | 2191987
Northwest | 10 | Clarion | 120998 | PA 28 Shannondale Resurfacing | 28 | 312 | Preventive Maintenance | CON | 581 | 2034-01-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2648000 | 2648000
Northwest | 10 | Clarion | 121428 | PA 66 Emergency Slide | 66 | 392 | Safety Improvement | FD | 581 | 2024-04-18 |  | 3956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3956
Northwest | 10 | Clarion | 121428 | PA 66 Emergency Slide | 66 | 392 | Safety Improvement | ROW | 581 | 2024-04-18 |  | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500
Northwest | 10 | Clarion | 121828 | Clarion Boro Safe Routes to School and Recreation |  | 383 | Federal Safe Routes to Schools | CON | TAP | 2027-07-29 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Northwest | 10 | Clarion | 122009 | District 10 High Friction Surface Treatment 2026 | 36 | ST2 | Safety Improvement | CON | HSIP | 2025-11-06 | 2025-11-06 | 257145 | 308320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 565465
Reading | 5 | Berks | 10328 | PA 61 Restoration Phase 2A | 61 | 16M | Highway Restoration | CON | NHPP | 2023-09-14 | 2023-09-14 | 714784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 714784
Reading | 5 | Berks | 10328 | PA 61 Restoration Phase 2A | 61 | 16M | Highway Restoration | CON | STU | 2023-09-14 | 2023-09-14 | 30000 | 76000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106000
Reading | 5 | Berks | 10328 | PA 61 Restoration Phase 2A | 61 | 16M | Highway Restoration | CON | 581 | 2023-09-14 | 2023-09-14 | 186196 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205196
Reading | 5 | Berks | 10527 | Bellevue Avenue over Readng Blue Mtn & Northern RR | 2016 | 01B | Bridge Replacement | FD | BRIP | 2026-07-30 |  | 89128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89128
Reading | 5 | Berks | 10527 | Bellevue Avenue over Readng Blue Mtn & Northern RR | 2016 | 01B | Bridge Replacement | FD | 185 | 2026-07-30 |  | 22282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22282
Reading | 5 | Berks | 10527 | Bellevue Avenue over Readng Blue Mtn & Northern RR | 2016 | 01B | Bridge Replacement | CON | BRIP | 2026-07-30 |  | 0 | 3113494 | 363964 | 459396 | 469424 | 537722 | 0 | 0 | 0 | 4944000
Reading | 5 | Berks | 10527 | Bellevue Avenue over Readng Blue Mtn & Northern RR | 2016 | 01B | Bridge Replacement | CON | 185 | 2026-07-30 |  | 0 | 921492 | 91741 | 114849 | 103336 | 4582 | 0 | 0 | 0 | 1236000
Reading | 5 | Berks | 10613 | 5th Street Bridge over NS RR | 2005 | 03B | Bridge Replacement | FD | BRIP | 2030-07-11 |  | 0 | 0 | 600000 | 36540 | 0 | 0 | 0 | 0 | 0 | 636540
Reading | 5 | Berks | 10613 | 5th Street Bridge over NS RR | 2005 | 03B | Bridge Replacement | FD | 185 | 2030-07-11 |  | 0 | 0 | 150000 | 9135 | 0 | 0 | 0 | 0 | 0 | 159135
Reading | 5 | Berks | 10613 | 5th Street Bridge over NS RR | 2005 | 03B | Bridge Replacement | ROW | NHPP | 2030-07-11 |  | 0 | 30000 | 37416 | 17456 | 0 | 0 | 0 | 0 | 0 | 84872
Reading | 5 | Berks | 10613 | 5th Street Bridge over NS RR | 2005 | 03B | Bridge Replacement | ROW | 185 | 2030-07-11 |  | 0 | 7500 | 9354 | 4364 | 0 | 0 | 0 | 0 | 0 | 21218
Reading | 5 | Berks | 10613 | 5th Street Bridge over NS RR | 2005 | 03B | Bridge Replacement | UTL | NHPP | 2030-07-11 |  | 0 | 0 | 0 | 45020 | 0 | 0 | 0 | 0 | 0 | 45020
Reading | 5 | Berks | 10613 | 5th Street Bridge over NS RR | 2005 | 03B | Bridge Replacement | UTL | 185 | 2030-07-11 |  | 0 | 0 | 0 | 11255 | 0 | 0 | 0 | 0 | 0 | 11255
Reading | 5 | Berks | 10613 | 5th Street Bridge over NS RR | 2005 | 03B | Bridge Replacement | CON | BRIP | 2030-07-11 |  | 0 | 0 | 0 | 0 | 1000000 | 1000 | 0 | 0 | 0 | 1001000
Reading | 5 | Berks | 10613 | 5th Street Bridge over NS RR | 2005 | 03B | Bridge Replacement | CON | STU | 2030-07-11 |  | 0 | 0 | 0 | 250000 | 1000000 | 0 | 0 | 0 | 0 | 1250000
Reading | 5 | Berks | 10613 | 5th Street Bridge over NS RR | 2005 | 03B | Bridge Replacement | CON | 185 | 2030-07-11 |  | 0 | 0 | 0 | 62500 | 500000 | 250 | 0 | 0 | 0 | 562750
Reading | 5 | Berks | 10700 | Main Street over Allegheny Creek | 724 | 02B | Bridge Replacement | FD | BRIP | 2025-04-10 | 2025-04-10 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Reading | 5 | Berks | 10700 | Main Street over Allegheny Creek | 724 | 02B | Bridge Replacement | FD | 185 | 2025-04-10 | 2025-04-10 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Reading | 5 | Berks | 10700 | Main Street over Allegheny Creek | 724 | 02B | Bridge Replacement | UTL | BRIP | 2025-04-10 | 2025-04-10 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Reading | 5 | Berks | 10700 | Main Street over Allegheny Creek | 724 | 02B | Bridge Replacement | UTL | 185 | 2025-04-10 | 2025-04-10 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Reading | 5 | Berks | 10700 | Main Street over Allegheny Creek | 724 | 02B | Bridge Replacement | CON | BRIP | 2025-04-10 | 2025-04-10 | 2418324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2418324
Reading | 5 | Berks | 10700 | Main Street over Allegheny Creek | 724 | 02B | Bridge Replacement | CON | 185 | 2025-04-10 | 2025-04-10 | 604581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604581
Reading | 5 | Berks | 10702 | Tilden Road Bridge | 4015 | 02B | Bridge Replacement | CON | 185 | 2025-03-27 | 2025-03-27 | 300000 | 393422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693422
Reading | 5 | Berks | 10727 | Dwight Street Bridge | 7237 | 01B | Bridge Restoration | PE | BOF | 2033-04-14 |  | 762080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 762080
Reading | 5 | Berks | 10727 | Dwight Street Bridge | 7237 | 01B | Bridge Restoration | PE | 183 | 2033-04-14 |  | 142890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142890
Reading | 5 | Berks | 10727 | Dwight Street Bridge | 7237 | 01B | Bridge Restoration | PE | LOC | 2033-04-14 |  | 47630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47630
Reading | 5 | Berks | 10727 | Dwight Street Bridge | 7237 | 01B | Bridge Restoration | FD | BOF | 2033-04-14 |  | 0 | 0 | 0 | 0 | 510092 | 0 | 0 | 0 | 0 | 510092
Reading | 5 | Berks | 10727 | Dwight Street Bridge | 7237 | 01B | Bridge Restoration | FD | 183 | 2033-04-14 |  | 0 | 0 | 0 | 0 | 95643 | 0 | 0 | 0 | 0 | 95643
Reading | 5 | Berks | 10727 | Dwight Street Bridge | 7237 | 01B | Bridge Restoration | ROW | BOF | 2033-04-14 |  | 0 | 0 | 0 | 0 | 92744 | 0 | 0 | 0 | 0 | 92744
Reading | 5 | Berks | 10727 | Dwight Street Bridge | 7237 | 01B | Bridge Restoration | ROW | 183 | 2033-04-14 |  | 0 | 0 | 0 | 0 | 17390 | 0 | 0 | 0 | 0 | 17390
Reading | 5 | Berks | 10727 | Dwight Street Bridge | 7237 | 01B | Bridge Restoration | UTL | BOF | 2033-04-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78288 | 78288
Reading | 5 | Berks | 10727 | Dwight Street Bridge | 7237 | 01B | Bridge Restoration | UTL | 183 | 2033-04-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14679 | 14679
Reading | 5 | Berks | 10727 | Dwight Street Bridge | 7237 | 01B | Bridge Restoration | CON | BOF | 2033-04-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7828800 | 7828800
Reading | 5 | Berks | 10730 | Old River Road Bridge | 7233 | ORR | Bridge Restoration | PE | BOF | 2030-04-01 |  | 410644 | 288500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 699144
Reading | 5 | Berks | 10730 | Old River Road Bridge | 7233 | ORR | Bridge Restoration | FD | BOF | 2030-04-01 |  | 0 | 0 | 327810 | 0 | 0 | 0 | 0 | 0 | 0 | 327810
Reading | 5 | Berks | 10730 | Old River Road Bridge | 7233 | ORR | Bridge Restoration | ROW | BOF | 2030-04-01 |  | 0 | 0 | 109270 | 0 | 0 | 0 | 0 | 0 | 0 | 109270
Reading | 5 | Berks | 10730 | Old River Road Bridge | 7233 | ORR | Bridge Restoration | UTL | BOF | 2030-04-01 |  | 0 | 0 | 0 | 0 | 57965 | 0 | 0 | 0 | 0 | 57965
Reading | 5 | Berks | 10730 | Old River Road Bridge | 7233 | ORR | Bridge Restoration | CON | BOF | 2030-04-01 |  | 0 | 0 | 0 | 0 | 1000000 | 1318600 | 0 | 0 | 0 | 2318600
Reading | 5 | Berks | 10751 | Funk Road over Trib to Ironstone Creek | 2045 | 01B | Bridge Replacement | PE | BRIP | 2027-02-25 |  | 154566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154566
Reading | 5 | Berks | 10751 | Funk Road over Trib to Ironstone Creek | 2045 | 01B | Bridge Replacement | FD | BRIP | 2027-02-25 |  | 172800 | 255888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428688
Reading | 5 | Berks | 10751 | Funk Road over Trib to Ironstone Creek | 2045 | 01B | Bridge Replacement | FD | 185 | 2027-02-25 |  | 43200 | 63972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107172
Reading | 5 | Berks | 10751 | Funk Road over Trib to Ironstone Creek | 2045 | 01B | Bridge Replacement | ROW | BRIP | 2027-02-25 |  | 0 | 42436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42436
Reading | 5 | Berks | 10751 | Funk Road over Trib to Ironstone Creek | 2045 | 01B | Bridge Replacement | ROW | 185 | 2027-02-25 |  | 0 | 10609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10609
Reading | 5 | Berks | 10751 | Funk Road over Trib to Ironstone Creek | 2045 | 01B | Bridge Replacement | UTL | 185 | 2027-02-25 |  | 0 | 0 | 54635 | 0 | 0 | 0 | 0 | 0 | 0 | 54635
Reading | 5 | Berks | 10751 | Funk Road over Trib to Ironstone Creek | 2045 | 01B | Bridge Replacement | CON | BRIP | 2027-02-25 |  | 0 | 0 | 800000 | 292700 | 0 | 0 | 0 | 0 | 0 | 1092700
Reading | 5 | Berks | 10751 | Funk Road over Trib to Ironstone Creek | 2045 | 01B | Bridge Replacement | CON | 185 | 2027-02-25 |  | 0 | 0 | 200000 | 73175 | 0 | 0 | 0 | 0 | 0 | 273175
Reading | 5 | Berks | 10753 | Weavertown Road Bridge | 2041 | 03B | Bridge Replacement | CON | BOF | 2023-03-30 | 2023-03-23 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Reading | 5 | Berks | 10753 | Weavertown Road Bridge | 2041 | 03B | Bridge Replacement | CON | 185 | 2023-03-30 | 2023-03-23 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Reading | 5 | Berks | 10774 | Parkview Road Bridge | 7417 | BR | Bridge Replacement | PE | BOF | 2031-04-01 |  | 0 | 0 | 132000 | 283232 | 0 | 0 | 0 | 0 | 0 | 415232
Reading | 5 | Berks | 10774 | Parkview Road Bridge | 7417 | BR | Bridge Replacement | PE | 183 | 2031-04-01 |  | 0 | 0 | 24750 | 53106 | 0 | 0 | 0 | 0 | 0 | 77856
Reading | 5 | Berks | 10774 | Parkview Road Bridge | 7417 | BR | Bridge Replacement | FD | BOF | 2031-04-01 |  | 0 | 0 | 0 | 0 | 180000 | 144608 | 0 | 0 | 0 | 324608
Reading | 5 | Berks | 10774 | Parkview Road Bridge | 7417 | BR | Bridge Replacement | FD | 183 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 30000 | 27114 | 0 | 0 | 0 | 57114
Reading | 5 | Berks | 10774 | Parkview Road Bridge | 7417 | BR | Bridge Replacement | ROW | BOF | 2031-04-01 |  | 0 | 0 | 0 | 0 | 50000 | 42752 | 0 | 0 | 0 | 92752
Reading | 5 | Berks | 10774 | Parkview Road Bridge | 7417 | BR | Bridge Replacement | ROW | 183 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 9000 | 8016 | 0 | 0 | 0 | 17016
Reading | 5 | Berks | 10774 | Parkview Road Bridge | 7417 | BR | Bridge Replacement | UTL | BOF | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 23888 | 0 | 0 | 0 | 23888
Reading | 5 | Berks | 10774 | Parkview Road Bridge | 7417 | BR | Bridge Replacement | UTL | 183 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 4479 | 0 | 0 | 0 | 4479
Reading | 5 | Berks | 10774 | Parkview Road Bridge | 7417 | BR | Bridge Replacement | CON | BOF | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 910560 | 0 | 0 | 1910560
Reading | 5 | Berks | 10774 | Parkview Road Bridge | 7417 | BR | Bridge Replacement | CON | 183 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 180000 | 170730 | 0 | 0 | 350730
Reading | 5 | Berks | 10815 | SR 73 & Friedensburg Road (SR 2023) | 73 | 0 | Safety Improvement | PE | CAQ |  |  | 0 | 0 | 0 | 200000 | 250200 | 0 | 0 | 0 | 0 | 450200
Reading | 5 | Berks | 10815 | SR 73 & Friedensburg Road (SR 2023) | 73 | 0 | Safety Improvement | PE | 581 |  |  | 0 | 0 | 0 | 50000 | 62550 | 0 | 0 | 0 | 0 | 112550
Reading | 5 | Berks | 10815 | SR 73 & Friedensburg Road (SR 2023) | 73 | 0 | Safety Improvement | FD | CAQ |  |  | 0 | 0 | 0 | 0 | 0 | 382112 | 0 | 0 | 0 | 382112
Reading | 5 | Berks | 10815 | SR 73 & Friedensburg Road (SR 2023) | 73 | 0 | Safety Improvement | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 95528 | 0 | 0 | 0 | 95528
Reading | 5 | Berks | 10815 | SR 73 & Friedensburg Road (SR 2023) | 73 | 0 | Safety Improvement | ROW | CAQ |  |  | 0 | 0 | 0 | 0 | 0 | 477640 | 0 | 0 | 0 | 477640
Reading | 5 | Berks | 10815 | SR 73 & Friedensburg Road (SR 2023) | 73 | 0 | Safety Improvement | ROW | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 119410 | 0 | 0 | 0 | 119410
Reading | 5 | Berks | 10815 | SR 73 & Friedensburg Road (SR 2023) | 73 | 0 | Safety Improvement | UTL | CAQ |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 73796 | 0 | 0 | 73796
Reading | 5 | Berks | 10815 | SR 73 & Friedensburg Road (SR 2023) | 73 | 0 | Safety Improvement | UTL | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18449 | 0 | 0 | 18449
Reading | 5 | Berks | 10815 | SR 73 & Friedensburg Road (SR 2023) | 73 | 0 | Safety Improvement | CON | CAQ |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 3035680 | 0 | 3935680
Reading | 5 | Berks | 10815 | SR 73 & Friedensburg Road (SR 2023) | 73 | 0 | Safety Improvement | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 758920 | 0 | 983920
Reading | 5 | Berks | 10859 | Race Street over Swamp Creek | 2032 | 02B | Bridge Replacement | UTL | 185 | 2026-05-07 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Reading | 5 | Berks | 10859 | Race Street over Swamp Creek | 2032 | 02B | Bridge Replacement | CON | PRTCT | 2026-05-07 |  | 742500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 742500
Reading | 5 | Berks | 10867 | PA 61 Restoration Phase 2B | 61 | 15M | Highway Restoration | FD | NHPP | 2027-08-12 |  | 476448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476448
Reading | 5 | Berks | 10867 | PA 61 Restoration Phase 2B | 61 | 15M | Highway Restoration | FD | 581 | 2027-08-12 |  | 119112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119112
Reading | 5 | Berks | 10867 | PA 61 Restoration Phase 2B | 61 | 15M | Highway Restoration | UTL | NHPP | 2027-08-12 |  | 0 | 23620 | 14932 | 3884 | 0 | 0 | 0 | 0 | 0 | 42436
Reading | 5 | Berks | 10867 | PA 61 Restoration Phase 2B | 61 | 15M | Highway Restoration | UTL | 581 | 2027-08-12 |  | 0 | 5905 | 3733 | 971 | 0 | 0 | 0 | 0 | 0 | 10609
Reading | 5 | Berks | 10867 | PA 61 Restoration Phase 2B | 61 | 15M | Highway Restoration | CON | NHPP | 2027-08-12 |  | 0 | 3421509 | 1000000 | 526856 | 84872 | 25612 | 95080 | 90376 | 88800 | 5333105
Reading | 5 | Berks | 10867 | PA 61 Restoration Phase 2B | 61 | 15M | Highway Restoration | CON | STP | 2027-08-12 |  | 0 | 0 | 0 | 46996 | 0 | 0 | 0 | 0 | 903004 | 950000
Reading | 5 | Berks | 10867 | PA 61 Restoration Phase 2B | 61 | 15M | Highway Restoration | CON | STU | 2027-08-12 |  | 0 | 543617 | 842937 | 888503 | 456361 | 2848357 | 540123 | 337582 | 0 | 6457480
Reading | 5 | Berks | 10943 | Morgantown Road over trib Conestoga Creek | 10 | 02B | Bridge Restoration | CON | BRIP | 2024-03-14 | 2024-03-14 | 293004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 293004
Reading | 5 | Berks | 56728 | Pigeon Creek Bridge | 7419 | 0 | Bridge Replacement | PE | BOF | 2038-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417536 | 417536
Reading | 5 | Berks | 56728 | Pigeon Creek Bridge | 7419 | 0 | Bridge Replacement | PE | 183 | 2038-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78288 | 78288
Reading | 5 | Berks | 61972 | US 222 Widening | 222 | 28M | Highway Restoration | ROW | NHPP | 2026-10-22 |  | 412936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412936
Reading | 5 | Berks | 61972 | US 222 Widening | 222 | 28M | Highway Restoration | ROW | 581 | 2026-10-22 |  | 103234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103234
Reading | 5 | Berks | 61972 | US 222 Widening | 222 | 28M | Highway Restoration | CON | STP | 2026-10-22 |  | 0 | 11717324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11717324
Reading | 5 | Berks | 61972 | US 222 Widening | 222 | 28M | Highway Restoration | CON | BRIP | 2026-10-22 |  | 0 | 1000000 | 2375000 | 0 | 0 | 0 | 0 | 0 | 0 | 3375000
Reading | 5 | Berks | 61972 | US 222 Widening | 222 | 28M | Highway Restoration | CON | HSIP | 2026-10-22 |  | 0 | 1450000 | 0 | 0 | 100000 | 100000 | 2500000 | 0 | 0 | 4150000
Reading | 5 | Berks | 61972 | US 222 Widening | 222 | 28M | Highway Restoration | CON | NHPP | 2026-10-22 |  | 0 | 4250000 | 1500000 | 3550000 | 6200000 | 8179388 | 0 | 0 | 0 | 23679388
Reading | 5 | Berks | 61972 | US 222 Widening | 222 | 28M | Highway Restoration | CON | STP | 2026-10-22 |  | 0 | 1785000 | 0 | 300000 | 1400000 | 4400000 | 0 | 15000 | 0 | 7900000
Reading | 5 | Berks | 61972 | US 222 Widening | 222 | 28M | Highway Restoration | CON | STU | 2026-10-22 |  | 0 | 2150000 | 2000000 | 4350000 | 2100000 | 700000 | 0 | 0 | 0 | 11300000
Reading | 5 | Berks | 61972 | US 222 Widening | 222 | 28M | Highway Restoration | CON | 581 | 2026-10-22 |  | 0 | 2929331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2929331
Reading | 5 | Berks | 61972 | US 222 Widening | 222 | 28M | Highway Restoration | CON | 185 | 2026-10-22 |  | 0 | 0 | 675000 | 0 | 0 | 0 | 0 | 0 | 0 | 675000
Reading | 5 | Berks | 61972 | US 222 Widening | 222 | 28M | Highway Restoration | CON | 581 | 2026-10-22 |  | 0 | 1979331 | 3200000 | 2050000 | 2425000 | 3319847 | 0 | 0 | 0 | 12974178
Reading | 5 | Berks | 69335 | RATS BARTA Flex |  |  | Public Transit | CON | CAQ |  |  | 0 | 0 | 450000 | 900000 | 900000 | 900000 | 900000 | 900000 | 3600000 | 8550000
Reading | 5 | Berks | 72814 | West Shore (US 422) Reconstruction Phase 2 | 422 | 29M | Highway Reconstruction | FD | NHPP | 2034-04-01 |  | 0 | 0 | 1000000 | 2500000 | 2500000 | 1700000 | 1915760 | 0 | 0 | 9615760
Reading | 5 | Berks | 72814 | West Shore (US 422) Reconstruction Phase 2 | 422 | 29M | Highway Reconstruction | FD | 581 | 2034-04-01 |  | 0 | 0 | 250000 | 625000 | 625000 | 425000 | 478940 | 0 | 0 | 2403940
Reading | 5 | Berks | 72814 | West Shore (US 422) Reconstruction Phase 2 | 422 | 29M | Highway Reconstruction | ROW | NHPP | 2034-04-01 |  | 0 | 0 | 30000 | 250000 | 250000 | 250000 | 94160 | 0 | 0 | 874160
Reading | 5 | Berks | 72814 | West Shore (US 422) Reconstruction Phase 2 | 422 | 29M | Highway Reconstruction | ROW | 581 | 2034-04-01 |  | 0 | 0 | 7500 | 62500 | 62500 | 62500 | 23540 | 0 | 0 | 218540
Reading | 5 | Berks | 72814 | West Shore (US 422) Reconstruction Phase 2 | 422 | 29M | Highway Reconstruction | UTL | NHPP | 2034-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 264624 | 0 | 2164624
Reading | 5 | Berks | 72814 | West Shore (US 422) Reconstruction Phase 2 | 422 | 29M | Highway Reconstruction | UTL | 581 | 2034-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 475000 | 66156 | 0 | 541156
Reading | 5 | Berks | 72814 | West Shore (US 422) Reconstruction Phase 2 | 422 | 29M | Highway Reconstruction | CON | NHPP | 2034-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6100000 | 9800000 | 40331200 | 56231200
Reading | 5 | Berks | 72814 | West Shore (US 422) Reconstruction Phase 2 | 422 | 29M | Highway Reconstruction | CON | STP | 2034-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 21000000 | 31000000
Reading | 5 | Berks | 72814 | West Shore (US 422) Reconstruction Phase 2 | 422 | 29M | Highway Reconstruction | CON | STU | 2034-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000 | 9000000 | 21000000
Reading | 5 | Berks | 72814 | West Shore (US 422) Reconstruction Phase 2 | 422 | 29M | Highway Reconstruction | CON | 581 | 2034-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4275000 | 5200000 | 17582800 | 27057800
Reading | 5 | Berks | 79467 | SR 12 Elizabeth Avenue | 12 | 03S | Safety Improvement | ROW | HSIP | 2027-03-25 |  | 894967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 894967
Reading | 5 | Berks | 79467 | SR 12 Elizabeth Avenue | 12 | 03S | Safety Improvement | UTL | STP | 2027-03-25 |  | 0 | 391400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391400
Reading | 5 | Berks | 79467 | SR 12 Elizabeth Avenue | 12 | 03S | Safety Improvement | CON | CAQ | 2027-03-25 |  | 0 | 3000000 | 1200000 | 1700000 | 1141060 | 0 | 0 | 0 | 0 | 7041060
Reading | 5 | Berks | 79467 | SR 12 Elizabeth Avenue | 12 | 03S | Safety Improvement | CON | CRP | 2027-03-25 |  | 0 | 0 | 0 | 400000 | 400000 | 0 | 0 | 0 | 0 | 800000
Reading | 5 | Berks | 79467 | SR 12 Elizabeth Avenue | 12 | 03S | Safety Improvement | CON | CRPU | 2027-03-25 |  | 0 | 725000 | 0 | 725000 | 725000 | 0 | 0 | 0 | 0 | 2175000
Reading | 5 | Berks | 79467 | SR 12 Elizabeth Avenue | 12 | 03S | Safety Improvement | CON | HSIP | 2027-03-25 |  | 0 | 57449 | 400000 | 0 | 28784 | 73700 | 408000 | 1132067 | 0 | 2100000
Reading | 5 | Berks | 79467 | SR 12 Elizabeth Avenue | 12 | 03S | Safety Improvement | CON | 185 | 2027-03-25 |  | 0 | 0 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000
Reading | 5 | Berks | 80070 | RATS In-house Bridge Design Assistance |  |  | Bridge Replacement | PE | 185 |  |  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 200000 | 600000
Reading | 5 | Berks | 82791 | CMAQ Reserve Line Item |  |  | Reserve Line Item | CON | CAQ |  |  | 0 | 1079703 | 0 | 0 | 0 | 0 | 0 | 0 | 10267160 | 11346863
Reading | 5 | Berks | 82793 | Alternative Transporation (TAP) Line Item |  |  | Reserve Line Item | CON | TAU |  |  | 0 | 75774 | 448295 | 606000 | 606000 | 606000 | 606000 | 606000 | 2423000 | 5977069
Reading | 5 | Berks | 82795 | Safety Reserve Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2175933 | 13231000 | 15406933
Reading | 5 | Berks | 82796 | Urban Reserve Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 413000 | 0 | 13000 | 0 | 0 | 26000 | 413000 | 1651000 | 2516000
Reading | 5 | Berks | 82796 | Urban Reserve Line Item |  |  | Reserve Line Item | CON | CRPU |  |  | 0 | 36000 | 0 | 36000 | 36000 | 61000 | 57492 | 761000 | 3043000 | 4030492
Reading | 5 | Berks | 82796 | Urban Reserve Line Item |  |  | Reserve Line Item | CON | STU |  |  | 0 | 0 | 0 | 75632 | 0 | 0 | 0 | 0 | 13403059 | 13478691
Reading | 5 | Berks | 83081 | Delivery Consult Assistance |  | DCA | Reserve Line Item | PE | 185 |  |  | 800000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
Reading | 5 | Berks | 83081 | Delivery Consult Assistance |  | DCA | Reserve Line Item | PE | 581 |  |  | 2017613 | 1000000 | 1000000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 6000000 | 17517613
Reading | 5 | Berks | 85643 | Donat Road over Stoney Run | 1015 | 02B | Bridge Replacement | UTL | 185 | 2026-01-29 | 2026-01-29 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
Reading | 5 | Berks | 85643 | Donat Road over Stoney Run | 1015 | 02B | Bridge Replacement | CON | 185 | 2026-01-29 | 2026-01-29 | 941123 | 421978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1363101
Reading | 5 | Berks | 85648 | Stoney Run Valley Road over Maiden Creek | 1018 | 03B | Bridge Replacement | UTL | 185 | 2024-07-11 | 2024-07-11 | 93114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93114
Reading | 5 | Berks | 85650 | Valley Road over Toad Creek | 1035 | 01B | Bridge Replacement | UTL | 185 | 2025-02-13 | 2025-02-27 | 54075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54075
Reading | 5 | Berks | 85650 | Valley Road over Toad Creek | 1035 | 01B | Bridge Replacement | CON | 185 | 2025-02-13 | 2025-02-27 | 782678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782678
Reading | 5 | Berks | 85670 | Camp Swatara Road over Little Swatara Creek | 645 | 02B | Bridge Replacement | UTL | BOF | 2025-06-26 | 2025-06-26 | 50512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50512
Reading | 5 | Berks | 85670 | Camp Swatara Road over Little Swatara Creek | 645 | 02B | Bridge Replacement | UTL | 185 | 2025-06-26 | 2025-06-26 | 12628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12628
Reading | 5 | Berks | 85670 | Camp Swatara Road over Little Swatara Creek | 645 | 02B | Bridge Replacement | CON | BOF | 2025-06-26 | 2025-06-26 | 664080 | 1500000 | 331382 | 0 | 0 | 0 | 0 | 0 | 0 | 2495462
Reading | 5 | Berks | 85670 | Camp Swatara Road over Little Swatara Creek | 645 | 02B | Bridge Replacement | CON | BRIP | 2025-06-26 | 2025-06-26 | 664854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 664854
Reading | 5 | Berks | 85670 | Camp Swatara Road over Little Swatara Creek | 645 | 02B | Bridge Replacement | CON | 185 | 2025-06-26 | 2025-06-26 | 332234 | 375000 | 82845 | 0 | 0 | 0 | 0 | 0 | 0 | 790079
Reading | 5 | Berks | 86420 | Berks Commuter Services |  | BCS | Air Quality | CON | CAQ |  |  | 0 | 295297 | 299000 | 304000 | 304000 | 304000 | 304000 | 304000 | 1216000 | 3330297
Reading | 5 | Berks | 87688 | SR 422 in Sinking Spring | 422 | 30M | Congestion Reduction | FD | 581 | 2027-06-24 |  | 472621 | 327462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800083
Reading | 5 | Berks | 87688 | SR 422 in Sinking Spring | 422 | 30M | Congestion Reduction | ROW | NHPP | 2027-06-24 |  | 824000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824000
Reading | 5 | Berks | 87688 | SR 422 in Sinking Spring | 422 | 30M | Congestion Reduction | ROW | 581 | 2027-06-24 |  | 206000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206000
Reading | 5 | Berks | 87688 | SR 422 in Sinking Spring | 422 | 30M | Congestion Reduction | UTL | NHPP | 2027-06-24 |  | 0 | 40000 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 103000
Reading | 5 | Berks | 87688 | SR 422 in Sinking Spring | 422 | 30M | Congestion Reduction | UTL | 581 | 2027-06-24 |  | 0 | 10000 | 15750 | 0 | 0 | 0 | 0 | 0 | 0 | 25750
Reading | 5 | Berks | 87688 | SR 422 in Sinking Spring | 422 | 30M | Congestion Reduction | CON | NHPP | 2027-06-24 |  | 0 | 1500000 | 1500000 | 589344 | 0 | 0 | 0 | 0 | 0 | 3589344
Reading | 5 | Berks | 87688 | SR 422 in Sinking Spring | 422 | 30M | Congestion Reduction | CON | 581 | 2027-06-24 |  | 0 | 375000 | 375000 | 147336 | 0 | 0 | 0 | 0 | 0 | 897336
Reading | 5 | Berks | 88781 | SR 12 and SR 73 | 12 | 01S | Congestion Reduction | CON | STP | 2022-10-20 | 2022-10-20 | 61344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61344
Reading | 5 | Berks | 89056 | Transp Alternative Project Mngmt |  | TEM | Transportation Enhancement | PE | STP |  |  | 30000 | 40000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 120000
Reading | 5 | Berks | 89634 | Trap Rock Bridge Removal | 2082 | 0 | Bridge Removal | PE | 185 | 2029-04-01 |  | 0 | 50000 | 56090 | 0 | 0 | 0 | 0 | 0 | 0 | 106090
Reading | 5 | Berks | 89634 | Trap Rock Bridge Removal | 2082 | 0 | Bridge Removal | FD | 185 | 2029-04-01 |  | 0 | 0 | 50000 | 59270 | 0 | 0 | 0 | 0 | 0 | 109270
Reading | 5 | Berks | 89634 | Trap Rock Bridge Removal | 2082 | 0 | Bridge Removal | ROW | 185 | 2029-04-01 |  | 0 | 0 | 0 | 12500 | 15638 | 0 | 0 | 0 | 0 | 28138
Reading | 5 | Berks | 89634 | Trap Rock Bridge Removal | 2082 | 0 | Bridge Removal | UTL | 185 | 2029-04-01 |  | 0 | 0 | 0 | 11255 | 0 | 0 | 0 | 0 | 0 | 11255
Reading | 5 | Berks | 89634 | Trap Rock Bridge Removal | 2082 | 0 | Bridge Removal | CON | 185 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 231860 | 0 | 0 | 0 | 0 | 231860
Reading | 5 | Berks | 90569 | SR 222 and Long Lane Intersection Improvements | 222 | 23S | Highway Reconstruction | CON | CAQ | 2025-01-09 | 2025-01-09 | 869872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869872
Reading | 5 | Berks | 90569 | SR 222 and Long Lane Intersection Improvements | 222 | 23S | Highway Reconstruction | CON | 581 | 2025-01-09 | 2025-01-09 | 164519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164519
Reading | 5 | Berks | 91091 | Schuylkill Ave Bridge SB | 183 | 05B | Bridge Replacement | CON | BRIP | 2023-06-08 | 2023-06-08 | 75000 | 43152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118152
Reading | 5 | Berks | 91091 | Schuylkill Ave Bridge SB | 183 | 05B | Bridge Replacement | CON | STU | 2023-06-08 | 2023-06-08 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Reading | 5 | Berks | 91091 | Schuylkill Ave Bridge SB | 183 | 05B | Bridge Replacement | CON | 185 | 2023-06-08 | 2023-06-08 | 25000 | 10788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35788
Reading | 5 | Berks | 91658 | TOC Operator-Berks | 78 | TOC | Intelligent Transportation System | CON | NHPP |  |  | 125000 | 75000 | 125000 | 75000 | 125000 | 75000 | 125000 | 75000 | 500000 | 1300000
Reading | 5 | Berks | 91908 | North Third Street over Tulpehocken Creek | 419 | 02B | Bridge Replacement | FD | BRIP | 2027-01-14 |  | 55684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55684
Reading | 5 | Berks | 91908 | North Third Street over Tulpehocken Creek | 419 | 02B | Bridge Replacement | FD | 185 | 2027-01-14 |  | 13921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13921
Reading | 5 | Berks | 91908 | North Third Street over Tulpehocken Creek | 419 | 02B | Bridge Replacement | UTL | BRIP | 2027-01-14 |  | 0 | 106092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106092
Reading | 5 | Berks | 91908 | North Third Street over Tulpehocken Creek | 419 | 02B | Bridge Replacement | UTL | 581 | 2027-01-14 |  | 0 | 26523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26523
Reading | 5 | Berks | 91908 | North Third Street over Tulpehocken Creek | 419 | 02B | Bridge Replacement | CON | BRIP | 2027-01-14 |  | 0 | 0 | 350000 | 4500000 | 1437324 | 400000 | 0 | 0 | 0 | 6687324
Reading | 5 | Berks | 91908 | North Third Street over Tulpehocken Creek | 419 | 02B | Bridge Replacement | CON | 185 | 2027-01-14 |  | 0 | 0 | 87500 | 1125000 | 359331 | 100000 | 0 | 0 | 0 | 1671831
Reading | 5 | Berks | 91976 | PA183 o'r Little Northkill Ck & Trib to LNorthkill | 183 | 06B | Bridge Replacement | PE | 185 | 2028-04-01 |  | 847955 | 547407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395362
Reading | 5 | Berks | 91976 | PA183 o'r Little Northkill Ck & Trib to LNorthkill | 183 | 06B | Bridge Replacement | FD | 185 | 2028-04-01 |  | 0 | 0 | 175000 | 589890 | 0 | 0 | 0 | 0 | 0 | 764890
Reading | 5 | Berks | 91976 | PA183 o'r Little Northkill Ck & Trib to LNorthkill | 183 | 06B | Bridge Replacement | ROW | BRIP | 2028-04-01 |  | 0 | 0 | 61192 | 0 | 0 | 0 | 0 | 0 | 0 | 61192
Reading | 5 | Berks | 91976 | PA183 o'r Little Northkill Ck & Trib to LNorthkill | 183 | 06B | Bridge Replacement | ROW | 185 | 2028-04-01 |  | 0 | 0 | 15298 | 0 | 0 | 0 | 0 | 0 | 0 | 15298
Reading | 5 | Berks | 91976 | PA183 o'r Little Northkill Ck & Trib to LNorthkill | 183 | 06B | Bridge Replacement | UTL | 185 | 2028-04-01 |  | 0 | 0 | 0 | 11255 | 0 | 0 | 0 | 0 | 0 | 11255
Reading | 5 | Berks | 91976 | PA183 o'r Little Northkill Ck & Trib to LNorthkill | 183 | 06B | Bridge Replacement | CON | BRIP | 2028-04-01 |  | 0 | 0 | 0 | 0 | 900000 | 954880 | 0 | 0 | 0 | 1854880
Reading | 5 | Berks | 91976 | PA183 o'r Little Northkill Ck & Trib to LNorthkill | 183 | 06B | Bridge Replacement | CON | 185 | 2028-04-01 |  | 0 | 0 | 0 | 0 | 225000 | 238720 | 0 | 0 | 0 | 463720
Reading | 5 | Berks | 91995 | Centre Avenue over Norfolk Southern RR | 2087 | 02B | Bridge Replacement | FD | NHPP | 2030-07-11 |  | 0 | 100000 | 400000 | 136540 | 0 | 0 | 0 | 0 | 0 | 636540
Reading | 5 | Berks | 91995 | Centre Avenue over Norfolk Southern RR | 2087 | 02B | Bridge Replacement | FD | 185 | 2030-07-11 |  | 0 | 25000 | 100000 | 34135 | 0 | 0 | 0 | 0 | 0 | 159135
Reading | 5 | Berks | 91995 | Centre Avenue over Norfolk Southern RR | 2087 | 02B | Bridge Replacement | ROW | NHPP | 2030-07-11 |  | 0 | 50000 | 100000 | 115232 | 0 | 0 | 0 | 0 | 0 | 265232
Reading | 5 | Berks | 91995 | Centre Avenue over Norfolk Southern RR | 2087 | 02B | Bridge Replacement | ROW | 185 | 2030-07-11 |  | 0 | 12500 | 25000 | 28808 | 0 | 0 | 0 | 0 | 0 | 66308
Reading | 5 | Berks | 91995 | Centre Avenue over Norfolk Southern RR | 2087 | 02B | Bridge Replacement | UTL | NHPP | 2030-07-11 |  | 0 | 0 | 0 | 56276 | 0 | 0 | 0 | 0 | 0 | 56276
Reading | 5 | Berks | 91995 | Centre Avenue over Norfolk Southern RR | 2087 | 02B | Bridge Replacement | UTL | 185 | 2030-07-11 |  | 0 | 0 | 0 | 14069 | 0 | 0 | 0 | 0 | 0 | 14069
Reading | 5 | Berks | 91995 | Centre Avenue over Norfolk Southern RR | 2087 | 02B | Bridge Replacement | CON | BRIP | 2030-07-11 |  | 0 | 0 | 0 | 1000000 | 2500000 | 2500000 | 1203200 | 0 | 0 | 7203200
Reading | 5 | Berks | 91995 | Centre Avenue over Norfolk Southern RR | 2087 | 02B | Bridge Replacement | CON | 185 | 2030-07-11 |  | 0 | 0 | 0 | 250000 | 625000 | 625000 | 300800 | 0 | 0 | 1800800
Reading | 5 | Berks | 92009 | SR 100 over trib to Perkiomen Creek | 100 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 16884 | 0 | 0 | 0 | 0 | 0 | 16884
Reading | 5 | Berks | 92009 | SR 100 over trib to Perkiomen Creek | 100 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 11593 | 0 | 0 | 0 | 0 | 11593
Reading | 5 | Berks | 92070 | Penn Avenue over Cacoosing Creek | 422 | 21B | Bridge Replacement | PE | BRIP | 2027-02-25 |  | 56196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56196
Reading | 5 | Berks | 92070 | Penn Avenue over Cacoosing Creek | 422 | 21B | Bridge Replacement | PE | STU | 2027-02-25 |  | 86372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86372
Reading | 5 | Berks | 92070 | Penn Avenue over Cacoosing Creek | 422 | 21B | Bridge Replacement | PE | 185 | 2027-02-25 |  | 35642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35642
Reading | 5 | Berks | 92070 | Penn Avenue over Cacoosing Creek | 422 | 21B | Bridge Replacement | FD | NHPP | 2027-02-25 |  | 485267 | 27871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513138
Reading | 5 | Berks | 92070 | Penn Avenue over Cacoosing Creek | 422 | 21B | Bridge Replacement | ROW | NHPP | 2027-02-25 |  | 133600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133600
Reading | 5 | Berks | 92070 | Penn Avenue over Cacoosing Creek | 422 | 21B | Bridge Replacement | UTL | BRIP | 2027-02-25 |  | 0 | 16976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16976
Reading | 5 | Berks | 92070 | Penn Avenue over Cacoosing Creek | 422 | 21B | Bridge Replacement | UTL | 185 | 2027-02-25 |  | 0 | 4244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4244
Reading | 5 | Berks | 92070 | Penn Avenue over Cacoosing Creek | 422 | 21B | Bridge Replacement | CON | BRIP | 2027-02-25 |  | 0 | 153180 | 696820 | 168464 | 0 | 0 | 0 | 0 | 0 | 1018464
Reading | 5 | Berks | 92070 | Penn Avenue over Cacoosing Creek | 422 | 21B | Bridge Replacement | CON | 185 | 2027-02-25 |  | 0 | 38295 | 174205 | 42116 | 0 | 0 | 0 | 0 | 0 | 254616
Reading | 5 | Berks | 92079 | Rehrersburg Road over Mill Creek | 419 | 01B | Bridge Replacement | FD | STP | 2025-06-26 | 2025-06-26 | 35784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35784
Reading | 5 | Berks | 92079 | Rehrersburg Road over Mill Creek | 419 | 01B | Bridge Replacement | FD | 185 | 2025-06-26 | 2025-06-26 | 8946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8946
Reading | 5 | Berks | 92079 | Rehrersburg Road over Mill Creek | 419 | 01B | Bridge Replacement | UTL | STP | 2025-06-26 | 2025-06-26 | 43260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43260
Reading | 5 | Berks | 92079 | Rehrersburg Road over Mill Creek | 419 | 01B | Bridge Replacement | UTL | 185 | 2025-06-26 | 2025-06-26 | 10815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10815
Reading | 5 | Berks | 92079 | Rehrersburg Road over Mill Creek | 419 | 01B | Bridge Replacement | CON | STP | 2025-06-26 | 2025-06-26 | 835760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835760
Reading | 5 | Berks | 92079 | Rehrersburg Road over Mill Creek | 419 | 01B | Bridge Replacement | CON | 185 | 2025-06-26 | 2025-06-26 | 208940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208940
Reading | 5 | Berks | 94287 | Long Lane over West Pine Creek Bridge | 1026 | 04B | Bridge Replacement | UTL | 185 | 2026-05-07 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Reading | 5 | Berks | 94287 | Long Lane over West Pine Creek Bridge | 1026 | 04B | Bridge Replacement | CON | PRTCT | 2026-05-07 |  | 772800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772800
Reading | 5 | Berks | 94290 | Charming Forge over Mill Race Creek | 3037 | 01B | Bridge Restoration | FD | BOF | 2027-07-29 |  | 0 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260000
Reading | 5 | Berks | 94290 | Charming Forge over Mill Race Creek | 3037 | 01B | Bridge Restoration | FD | 185 | 2027-07-29 |  | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000
Reading | 5 | Berks | 94290 | Charming Forge over Mill Race Creek | 3037 | 01B | Bridge Restoration | ROW | BOF | 2027-07-29 |  | 0 | 14080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14080
Reading | 5 | Berks | 94290 | Charming Forge over Mill Race Creek | 3037 | 01B | Bridge Restoration | ROW | 185 | 2027-07-29 |  | 0 | 3520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3520
Reading | 5 | Berks | 94290 | Charming Forge over Mill Race Creek | 3037 | 01B | Bridge Restoration | UTL | BOF | 2027-07-29 |  | 0 | 0 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 46332
Reading | 5 | Berks | 94290 | Charming Forge over Mill Race Creek | 3037 | 01B | Bridge Restoration | UTL | 185 | 2027-07-29 |  | 0 | 0 | 11583 | 0 | 0 | 0 | 0 | 0 | 0 | 11583
Reading | 5 | Berks | 94290 | Charming Forge over Mill Race Creek | 3037 | 01B | Bridge Restoration | CON | BOF | 2027-07-29 |  | 0 | 0 | 300000 | 355620 | 0 | 0 | 0 | 0 | 0 | 655620
Reading | 5 | Berks | 94290 | Charming Forge over Mill Race Creek | 3037 | 01B | Bridge Restoration | CON | 185 | 2027-07-29 |  | 0 | 0 | 75000 | 88905 | 0 | 0 | 0 | 0 | 0 | 163905
Reading | 5 | Berks | 94900 | Freeway Service Patrol | 422 | FSP | Intelligent Transportation System | CON | STU | 2018-11-01 | 2018-11-01 | 709896 | 105230 | 251321 | 258865 | 266639 | 274643 | 282877 | 291364 | 1200416 | 3641251
Reading | 5 | Berks | 95399 | Environmental Impacts Resolution LI |  | EIR | Planning/Research/Administration | PE | 581 |  |  | 133053 | 104580 | 104580 | 104580 | 104580 | 125000 | 125000 | 125000 | 500000 | 1426373
Reading | 5 | Berks | 96373 | PA 61 Restoration Phase 1 | 61 | 14M | Highway Restoration | CON | NHPP | 2024-10-24 | 2024-10-24 | 5610145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5610145
Reading | 5 | Berks | 96373 | PA 61 Restoration Phase 1 | 61 | 14M | Highway Restoration | CON | STP | 2024-10-24 | 2024-10-24 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000
Reading | 5 | Berks | 96373 | PA 61 Restoration Phase 1 | 61 | 14M | Highway Restoration | CON | 581 | 2024-10-24 | 2024-10-24 | 1640036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1640036
Reading | 5 | Berks | 97234 | 222 Kutztown Bypass to Lehigh County Line | 222 | 29M | Highway Reconstruction | PE | 581 | 2036-04-01 |  | 0 | 0 | 0 | 0 | 1800000 | 500000 | 3032780 | 0 | 0 | 5332780
Reading | 5 | Berks | 97258 | SR 61 Med Barrier - Perry Wind | 61 | 18S | Safety Improvement | CON | NHPP | 2027-08-12 |  | 250000 | 250000 | 30450 | 0 | 0 | 0 | 0 | 0 | 0 | 530450
Reading | 5 | Berks | 97417 | Construction Assistance |  | CAS | Reserve Line Item | CON | 581 |  |  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 200000 | 600000
Reading | 5 | Berks | 97838 | Construction Assistance |  | CAF | Reserve Line Item | CON | STP |  |  | 99853 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 200000 | 649853
Reading | 5 | Berks | 102161 | Lancaster (US 222 Bus) Corridor Imp | 3222 | 01S | Safety Improvement | STUDY | STU | 2028-04-01 |  | 379104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379104
Reading | 5 | Berks | 102189 | RATS Hwy & Bridge Reserve |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 1648360 | 2136206 | 976476 | 508215 | 747744 | 1303470 | 998860 | 4399456 | 12718787
Reading | 5 | Berks | 102189 | RATS Hwy & Bridge Reserve |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 168152 | 0 | 0 | 1781698 | 5741780 | 7418000 | 29671000 | 44780630
Reading | 5 | Berks | 102189 | RATS Hwy & Bridge Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Reading | 5 | Berks | 102189 | RATS Hwy & Bridge Reserve |  |  | Reserve Line Item | CON | STP |  |  | 0 | 0 | 7814 | 0 | 142050 | 25216 | 81000 | 252050 | 22996 | 531126
Reading | 5 | Berks | 102189 | RATS Hwy & Bridge Reserve |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 243813 | 1385145 | 1034837 | 0 | 4213850 | 1594835 | 4129110 | 26648873 | 39250463
Reading | 5 | Berks | 102189 | RATS Hwy & Bridge Reserve |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 37082 | 52882 | 82180 | 0 | 0 | 2511258 | 5211544 | 24674880 | 32569826
Reading | 5 | Berks | 102763 | RATS Traffic Review Assistance |  |  | Reserve Line Item | PE | 581 |  |  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 200000 | 600000
Reading | 5 | Berks | 103882 | Eagle Road Bridge over Moselem Creek | 7232 | A13 | Bridge Replacement | PE | ACT13 |  |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Reading | 5 | Berks | 103882 | Eagle Road Bridge over Moselem Creek | 7232 | A13 | Bridge Replacement | FD | ACT13 |  |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Reading | 5 | Berks | 103882 | Eagle Road Bridge over Moselem Creek | 7232 | A13 | Bridge Replacement | ROW | ACT13 |  |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Reading | 5 | Berks | 103882 | Eagle Road Bridge over Moselem Creek | 7232 | A13 | Bridge Replacement | UTL | ACT13 |  |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Reading | 5 | Berks | 103882 | Eagle Road Bridge over Moselem Creek | 7232 | A13 | Bridge Replacement | CON | ACT13 |  |  | 0 | 0 | 1000000 | 850000 | 0 | 0 | 0 | 0 | 0 | 1850000
Reading | 5 | Berks | 103908 | Swamp Creek Road Bridge | 7101 | A13 | Bridge Restoration | PE | ACT13 |  |  | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
Reading | 5 | Berks | 103908 | Swamp Creek Road Bridge | 7101 | A13 | Bridge Restoration | FD | ACT13 |  |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Reading | 5 | Berks | 103908 | Swamp Creek Road Bridge | 7101 | A13 | Bridge Restoration | ROW | ACT13 |  |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Reading | 5 | Berks | 103908 | Swamp Creek Road Bridge | 7101 | A13 | Bridge Restoration | UTL | ACT13 |  |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Reading | 5 | Berks | 103908 | Swamp Creek Road Bridge | 7101 | A13 | Bridge Restoration | CON | ACT13 |  |  | 0 | 0 | 600000 | 200000 | 0 | 0 | 0 | 0 | 0 | 800000
Reading | 5 | Berks | 105954 | State Hill Rd from Colony Dr. to SR 222 SB Ramps | 3023 | 04S | Congestion Reduction | FD | HSIP | 2028-05-11 |  | 0 | 359843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359843
Reading | 5 | Berks | 105954 | State Hill Rd from Colony Dr. to SR 222 SB Ramps | 3023 | 04S | Congestion Reduction | ROW | HSIP | 2028-05-11 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Reading | 5 | Berks | 105954 | State Hill Rd from Colony Dr. to SR 222 SB Ramps | 3023 | 04S | Congestion Reduction | ROW | HSIP | 2028-05-11 |  | 2199000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2199000
Reading | 5 | Berks | 105954 | State Hill Rd from Colony Dr. to SR 222 SB Ramps | 3023 | 04S | Congestion Reduction | UTL | STP | 2028-05-11 |  | 806928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 806928
Reading | 5 | Berks | 105954 | State Hill Rd from Colony Dr. to SR 222 SB Ramps | 3023 | 04S | Congestion Reduction | UTL | STU | 2028-05-11 |  | 193072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193072
Reading | 5 | Berks | 105954 | State Hill Rd from Colony Dr. to SR 222 SB Ramps | 3023 | 04S | Congestion Reduction | CON | STP | 2028-05-11 |  | 0 | 0 | 3500000 | 4100000 | 1300000 | 628344 | 0 | 0 | 0 | 9528344
Reading | 5 | Berks | 105954 | State Hill Rd from Colony Dr. to SR 222 SB Ramps | 3023 | 04S | Congestion Reduction | CON | 581 | 2028-05-11 |  | 0 | 0 | 875000 | 1025000 | 325000 | 157086 | 0 | 0 | 0 | 2382086
Reading | 5 | Berks | 105963 | Route 662 and Oley Turnpike Intersection | 662 | 02S | Safety Improvement | FD | STP | 2028-02-17 |  | 721000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 721000
Reading | 5 | Berks | 105963 | Route 662 and Oley Turnpike Intersection | 662 | 02S | Safety Improvement | ROW | STP | 2028-02-17 |  | 68800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68800
Reading | 5 | Berks | 105963 | Route 662 and Oley Turnpike Intersection | 662 | 02S | Safety Improvement | UTL | HSIP | 2028-02-17 |  | 0 | 0 | 61496 | 0 | 0 | 0 | 0 | 0 | 0 | 61496
Reading | 5 | Berks | 105963 | Route 662 and Oley Turnpike Intersection | 662 | 02S | Safety Improvement | CON | HSIP | 2028-02-17 |  | 0 | 0 | 2337234 | 1208000 | 279216 | 0 | 0 | 0 | 0 | 3824450
Reading | 5 | Berks | 109222 | SR 73 and 1005 Intersection Improvement | 73 | 06S | New Alignment | FD | STP | 2029-04-01 |  | 247200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247200
Reading | 5 | Berks | 109222 | SR 73 and 1005 Intersection Improvement | 73 | 06S | New Alignment | FD | 581 | 2029-04-01 |  | 61800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800
Reading | 5 | Berks | 109222 | SR 73 and 1005 Intersection Improvement | 73 | 06S | New Alignment | ROW | STP | 2029-04-01 |  | 82400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82400
Reading | 5 | Berks | 109222 | SR 73 and 1005 Intersection Improvement | 73 | 06S | New Alignment | ROW | 581 | 2029-04-01 |  | 20600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20600
Reading | 5 | Berks | 109222 | SR 73 and 1005 Intersection Improvement | 73 | 06S | New Alignment | UTL | STP | 2029-04-01 |  | 0 | 0 | 0 | 9004 | 0 | 0 | 0 | 0 | 0 | 9004
Reading | 5 | Berks | 109222 | SR 73 and 1005 Intersection Improvement | 73 | 06S | New Alignment | UTL | 581 | 2029-04-01 |  | 0 | 0 | 0 | 2251 | 0 | 0 | 0 | 0 | 0 | 2251
Reading | 5 | Berks | 109222 | SR 73 and 1005 Intersection Improvement | 73 | 06S | New Alignment | CON | STP | 2029-04-01 |  | 0 | 0 | 0 | 0 | 500000 | 427440 | 0 | 0 | 0 | 927440
Reading | 5 | Berks | 109222 | SR 73 and 1005 Intersection Improvement | 73 | 06S | New Alignment | CON | 581 | 2029-04-01 |  | 0 | 0 | 0 | 0 | 125000 | 106860 | 0 | 0 | 0 | 231860
Reading | 5 | Berks | 109337 | 61 Med Barr - Tilden Twp | 61 | 17S | Safety Improvement | CON | STU | 2024-10-24 | 2024-10-24 | 672132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672132
Reading | 5 | Berks | 109894 | SR 61 Bridge Rehabilitation | 61 | 10B | Bridge Restoration | CON | BRIP | 2023-09-14 | 2023-09-14 | 0 | 3668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3668
Reading | 5 | Berks | 109894 | SR 61 Bridge Rehabilitation | 61 | 10B | Bridge Restoration | CON | NHPP | 2023-09-14 | 2023-09-14 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Reading | 5 | Berks | 109894 | SR 61 Bridge Rehabilitation | 61 | 10B | Bridge Restoration | CON | 581 | 2023-09-14 | 2023-09-14 | 62500 | 917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63417
Reading | 5 | Berks | 110008 | 222 Auxiliary Lane-Wyomissing "Hard Shoulder" | 222 | 24S | Safety Improvement | ROW | STP | 2027-09-30 |  | 84880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84880
Reading | 5 | Berks | 110008 | 222 Auxiliary Lane-Wyomissing "Hard Shoulder" | 222 | 24S | Safety Improvement | ROW | 581 | 2027-09-30 |  | 21220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21220
Reading | 5 | Berks | 110008 | 222 Auxiliary Lane-Wyomissing "Hard Shoulder" | 222 | 24S | Safety Improvement | UTL | NHPP | 2027-09-30 |  | 0 | 20000 | 21200 | 0 | 0 | 0 | 0 | 0 | 0 | 41200
Reading | 5 | Berks | 110008 | 222 Auxiliary Lane-Wyomissing "Hard Shoulder" | 222 | 24S | Safety Improvement | UTL | 581 | 2027-09-30 |  | 0 | 5000 | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 10300
Reading | 5 | Berks | 110008 | 222 Auxiliary Lane-Wyomissing "Hard Shoulder" | 222 | 24S | Safety Improvement | CON | NHPP | 2027-09-30 |  | 0 | 3000000 | 2500000 | 1364392 | 0 | 0 | 0 | 0 | 0 | 6864392
Reading | 5 | Berks | 110008 | 222 Auxiliary Lane-Wyomissing "Hard Shoulder" | 222 | 24S | Safety Improvement | CON | STP | 2027-09-30 |  | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 1000000
Reading | 5 | Berks | 110008 | 222 Auxiliary Lane-Wyomissing "Hard Shoulder" | 222 | 24S | Safety Improvement | CON | STU | 2027-09-30 |  | 0 | 1960709 | 2300000 | 1000000 | 0 | 0 | 0 | 194054 | 345237 | 5800000
Reading | 5 | Berks | 110008 | 222 Auxiliary Lane-Wyomissing "Hard Shoulder" | 222 | 24S | Safety Improvement | CON | 581 | 2027-09-30 |  | 0 | 1356000 | 1200000 | 841098 | 0 | 0 | 0 | 0 | 19000 | 3416098
Reading | 5 | Berks | 110011 | Berks Box Culvert Bundle | 2032 | BCB | Bridge Replacement | CON | 185 | 2026-05-07 |  | 0 | 1469593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1469593
Reading | 5 | Berks | 110012 | 724 Fence Barrier | 724 | 06M | Preventive Maintenance | CON | STP | 2029-04-01 |  | 0 | 0 | 0 | 0 | 1738950 | 0 | 0 | 0 | 0 | 1738950
Reading | 5 | Berks | 110013 | SR 4040 (Old Route 22) Bridge Bundle | 4040 | BRB | Bridge Replacement | CON | STP | 2027-02-25 |  | 0 | 2641490 | 1553664 | 0 | 0 | 0 | 0 | 213950 | 0 | 4409104
Reading | 5 | Berks | 110013 | SR 4040 (Old Route 22) Bridge Bundle | 4040 | BRB | Bridge Replacement | CON | 185 | 2027-02-25 |  | 0 | 660372 | 388416 | 0 | 0 | 0 | 0 | 53488 | 0 | 1102276
Reading | 5 | Berks | 110014 | Rehrersburg Road over Trib Mill Creek | 419 | 03B | Bridge Replacement | FD | BRIP | 2026-12-10 |  | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475000
Reading | 5 | Berks | 110014 | Rehrersburg Road over Trib Mill Creek | 419 | 03B | Bridge Replacement | ROW | BRIP | 2026-12-10 |  | 0 | 127520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127520
Reading | 5 | Berks | 110014 | Rehrersburg Road over Trib Mill Creek | 419 | 03B | Bridge Replacement | ROW | 581 | 2026-12-10 |  | 0 | 31880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31880
Reading | 5 | Berks | 110014 | Rehrersburg Road over Trib Mill Creek | 419 | 03B | Bridge Replacement | UTL | BRIP | 2026-12-10 |  | 10000 | 30000 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 41200
Reading | 5 | Berks | 110014 | Rehrersburg Road over Trib Mill Creek | 419 | 03B | Bridge Replacement | UTL | 581 | 2026-12-10 |  | 2500 | 7500 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 10300
Reading | 5 | Berks | 110014 | Rehrersburg Road over Trib Mill Creek | 419 | 03B | Bridge Replacement | CON | BRIP | 2026-12-10 |  | 0 | 0 | 100000 | 900000 | 92700 | 0 | 0 | 0 | 0 | 1092700
Reading | 5 | Berks | 110014 | Rehrersburg Road over Trib Mill Creek | 419 | 03B | Bridge Replacement | CON | 581 | 2026-12-10 |  | 0 | 0 | 25000 | 225000 | 23175 | 0 | 0 | 0 | 0 | 273175
Reading | 5 | Berks | 110016 | Lancaster Ave over Swatara Creek | 501 | 02B | Bridge Replacement | FD | BRIP | 2026-09-17 |  | 172428 | 147200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319628
Reading | 5 | Berks | 110016 | Lancaster Ave over Swatara Creek | 501 | 02B | Bridge Replacement | FD | 185 | 2026-09-17 |  | 43107 | 36800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79907
Reading | 5 | Berks | 110016 | Lancaster Ave over Swatara Creek | 501 | 02B | Bridge Replacement | ROW | BRIP | 2026-09-17 |  | 51760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51760
Reading | 5 | Berks | 110016 | Lancaster Ave over Swatara Creek | 501 | 02B | Bridge Replacement | ROW | 185 | 2026-09-17 |  | 12940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12940
Reading | 5 | Berks | 110016 | Lancaster Ave over Swatara Creek | 501 | 02B | Bridge Replacement | UTL | BRIP | 2026-09-17 |  | 0 | 30000 | 12436 | 0 | 0 | 0 | 0 | 0 | 0 | 42436
Reading | 5 | Berks | 110016 | Lancaster Ave over Swatara Creek | 501 | 02B | Bridge Replacement | UTL | 185 | 2026-09-17 |  | 0 | 7500 | 3109 | 0 | 0 | 0 | 0 | 0 | 0 | 10609
Reading | 5 | Berks | 110016 | Lancaster Ave over Swatara Creek | 501 | 02B | Bridge Replacement | CON | BRIP | 2026-09-17 |  | 0 | 100000 | 900000 | 60900 | 0 | 0 | 0 | 0 | 0 | 1060900
Reading | 5 | Berks | 110016 | Lancaster Ave over Swatara Creek | 501 | 02B | Bridge Replacement | CON | 185 | 2026-09-17 |  | 0 | 25000 | 225000 | 15225 | 0 | 0 | 0 | 0 | 0 | 265225
Reading | 5 | Berks | 110017 | Alleghenyville Road (SR 3024) over I-176 | 3024 | 01B | Bridge Replacement | UTL | BOF | 2025-02-27 | 2025-02-27 | 23512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23512
Reading | 5 | Berks | 110017 | Alleghenyville Road (SR 3024) over I-176 | 3024 | 01B | Bridge Replacement | UTL | 185 | 2025-02-27 | 2025-02-27 | 5878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5878
Reading | 5 | Berks | 110017 | Alleghenyville Road (SR 3024) over I-176 | 3024 | 01B | Bridge Replacement | CON | BOF | 2025-02-27 | 2025-02-27 | 4244532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4244532
Reading | 5 | Berks | 110017 | Alleghenyville Road (SR 3024) over I-176 | 3024 | 01B | Bridge Replacement | CON | 185 | 2025-02-27 | 2025-02-27 | 544515 | 502422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1046937
Reading | 5 | Berks | 110075 | SR 422 Ben Franklin Congested Corridor | 422 | 23S | Congestion Reduction | FD | CAQ | 2027-03-11 |  | 773794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 773794
Reading | 5 | Berks | 110075 | SR 422 Ben Franklin Congested Corridor | 422 | 23S | Congestion Reduction | ROW | CAQ | 2027-03-11 |  | 145440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145440
Reading | 5 | Berks | 110075 | SR 422 Ben Franklin Congested Corridor | 422 | 23S | Congestion Reduction | ROW | 581 | 2027-03-11 |  | 36360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36360
Reading | 5 | Berks | 110075 | SR 422 Ben Franklin Congested Corridor | 422 | 23S | Congestion Reduction | UTL | CAQ | 2027-03-11 |  | 185484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185484
Reading | 5 | Berks | 110075 | SR 422 Ben Franklin Congested Corridor | 422 | 23S | Congestion Reduction | UTL | 581 | 2027-03-11 |  | 46371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46371
Reading | 5 | Berks | 110075 | SR 422 Ben Franklin Congested Corridor | 422 | 23S | Congestion Reduction | CON | CAQ | 2027-03-11 |  | 0 | 0 | 1488920 | 59760 | 24120 | 11248 | 17204 | 14400 | 2418840 | 4034492
Reading | 5 | Berks | 110075 | SR 422 Ben Franklin Congested Corridor | 422 | 23S | Congestion Reduction | CON | CRP | 2027-03-11 |  | 0 | 0 | 413000 | 0 | 13000 | 13000 | 387000 | 0 | 0 | 826000
Reading | 5 | Berks | 110075 | SR 422 Ben Franklin Congested Corridor | 422 | 23S | Congestion Reduction | CON | CRPU | 2027-03-11 |  | 0 | 0 | 761000 | 0 | 0 | 0 | 703508 | 0 | 0 | 1464508
Reading | 5 | Berks | 110075 | SR 422 Ben Franklin Congested Corridor | 422 | 23S | Congestion Reduction | CON | 581 | 2027-03-11 |  | 0 | 0 | 653000 | 102379 | 98881 | 86957 | 640033 | 0 | 0 | 1581250
Reading | 5 | Berks | 110078 | SR 4040 (Old Route 22) over Trib to Northkill Crk | 4040 | 01B | Bridge Replacement | UTL | STP | 2027-02-25 |  | 107120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107120
Reading | 5 | Berks | 110078 | SR 4040 (Old Route 22) over Trib to Northkill Crk | 4040 | 01B | Bridge Replacement | UTL | 185 | 2027-02-25 |  | 26780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26780
Reading | 5 | Berks | 110078 | SR 4040 (Old Route 22) over Trib to Northkill Crk | 4040 | 01B | Bridge Replacement | CON | BRIP | 2027-02-25 |  | 0 | 1000000 | 867184 | 0 | 0 | 0 | 0 | 0 | 0 | 1867184
Reading | 5 | Berks | 110078 | SR 4040 (Old Route 22) over Trib to Northkill Crk | 4040 | 01B | Bridge Replacement | CON | 185 | 2027-02-25 |  | 0 | 250000 | 216796 | 0 | 0 | 0 | 0 | 0 | 0 | 466796
Reading | 5 | Berks | 110079 | Penn Street over Maiden Creek | 7412 | 0 | Bridge Removal | PE | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 368970 | 0 | 0 | 368970
Reading | 5 | Berks | 110079 | Penn Street over Maiden Creek | 7412 | 0 | Bridge Removal | FD | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 76680 | 126680
Reading | 5 | Berks | 110079 | Penn Street over Maiden Creek | 7412 | 0 | Bridge Removal | ROW | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 39340 | 63340
Reading | 5 | Berks | 110079 | Penn Street over Maiden Creek | 7412 | 0 | Bridge Removal | UTL | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34050 | 34050
Reading | 5 | Berks | 110079 | Penn Street over Maiden Creek | 7412 | 0 | Bridge Removal | CON | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1304800 | 1304800
Reading | 5 | Berks | 110088 | High Boulevard Bridge | 7103 | 01B | Bridge Restoration | PE | BOF | 2033-04-01 |  | 0 | 0 | 100000 | 249664 | 0 | 0 | 0 | 0 | 0 | 349664
Reading | 5 | Berks | 110088 | High Boulevard Bridge | 7103 | 01B | Bridge Restoration | PE | 183 | 2033-04-01 |  | 0 | 0 | 18750 | 46812 | 0 | 0 | 0 | 0 | 0 | 65562
Reading | 5 | Berks | 110088 | High Boulevard Bridge | 7103 | 01B | Bridge Restoration | FD | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 180080 | 5408 | 0 | 0 | 0 | 185488
Reading | 5 | Berks | 110088 | High Boulevard Bridge | 7103 | 01B | Bridge Restoration | FD | 183 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 33765 | 1014 | 0 | 0 | 0 | 34779
Reading | 5 | Berks | 110088 | High Boulevard Bridge | 7103 | 01B | Bridge Restoration | ROW | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 23424 | 0 | 0 | 0 | 0 | 23424
Reading | 5 | Berks | 110088 | High Boulevard Bridge | 7103 | 01B | Bridge Restoration | ROW | 183 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 4392 | 0 | 0 | 0 | 0 | 4392
Reading | 5 | Berks | 110088 | High Boulevard Bridge | 7103 | 01B | Bridge Restoration | UTL | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10140 | 0 | 10140
Reading | 5 | Berks | 110088 | High Boulevard Bridge | 7103 | 01B | Bridge Restoration | UTL | 183 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1902 | 0 | 1902
Reading | 5 | Berks | 110088 | High Boulevard Bridge | 7103 | 01B | Bridge Restoration | CON | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 459800 | 2459800
Reading | 5 | Berks | 110189 | Old Rte 22 Ovr Birch Creek | 4040 | 02B | Bridge Restoration | UTL | 185 | 2027-02-25 |  | 61800 | 138200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Reading | 5 | Berks | 110192 | SR 4040 ovr Trib Little Northkill Crk | 4040 | 04B | Bridge Restoration | UTL | 185 | 2027-02-25 |  | 30900 | 109100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Reading | 5 | Berks | 110193 | SR 4040 over Mollhead Creek | 4040 | 05B | Bridge Restoration | UTL | 185 | 2027-02-25 |  | 30900 | 59100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
Reading | 5 | Berks | 110194 | SR 4040 ovr Trib Mollhead Crk | 4040 | 06B | Bridge Restoration | UTL | 185 | 2027-02-25 |  | 30900 | 79100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
Reading | 5 | Berks | 110318 | SR 12 Alsace Manor Int Impvmnts | 12 | 04S | Congestion Reduction | ROW | CAQ | 2026-10-22 |  | 1250220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250220
Reading | 5 | Berks | 110318 | SR 12 Alsace Manor Int Impvmnts | 12 | 04S | Congestion Reduction | ROW | CRP | 2026-10-22 |  | 398000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398000
Reading | 5 | Berks | 110318 | SR 12 Alsace Manor Int Impvmnts | 12 | 04S | Congestion Reduction | ROW | CRPU | 2026-10-22 |  | 123460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123460
Reading | 5 | Berks | 110318 | SR 12 Alsace Manor Int Impvmnts | 12 | 04S | Congestion Reduction | ROW | 581 | 2026-10-22 |  | 442920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 442920
Reading | 5 | Berks | 110318 | SR 12 Alsace Manor Int Impvmnts | 12 | 04S | Congestion Reduction | UTL | CAQ | 2026-10-22 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Reading | 5 | Berks | 110318 | SR 12 Alsace Manor Int Impvmnts | 12 | 04S | Congestion Reduction | UTL | STP | 2026-10-22 |  | 279600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279600
Reading | 5 | Berks | 110318 | SR 12 Alsace Manor Int Impvmnts | 12 | 04S | Congestion Reduction | UTL | 581 | 2026-10-22 |  | 82400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82400
Reading | 5 | Berks | 110318 | SR 12 Alsace Manor Int Impvmnts | 12 | 04S | Congestion Reduction | CON | CAQ | 2026-10-22 |  | 703508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 703508
Reading | 5 | Berks | 110318 | SR 12 Alsace Manor Int Impvmnts | 12 | 04S | Congestion Reduction | CON | CRPU | 2026-10-22 |  | 622540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 622540
Reading | 5 | Berks | 110318 | SR 12 Alsace Manor Int Impvmnts | 12 | 04S | Congestion Reduction | CON | STP | 2026-10-22 |  | 154350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154350
Reading | 5 | Berks | 110318 | SR 12 Alsace Manor Int Impvmnts | 12 | 04S | Congestion Reduction | CON | STU | 2026-10-22 |  | 367352 | 1300000 | 1352250 | 0 | 0 | 0 | 0 | 0 | 0 | 3019602
Reading | 5 | Berks | 111811 | SR 4040 Northkill Creek UBT | 4040 | 07B | Bridge Replacement | UTL | 185 | 2027-02-25 |  | 30900 | 59100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
Reading | 5 | Berks | 113325 | Hamburg Traffic Improvements | 4028 | HAM | Highway Reconstruction | PE | STU | 2033-04-01 |  | 185000 | 54764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239764
Reading | 5 | Berks | 113325 | Hamburg Traffic Improvements | 4028 | HAM | Highway Reconstruction | FD | STU | 2033-04-01 |  | 0 | 0 | 76492 | 0 | 0 | 0 | 0 | 0 | 0 | 76492
Reading | 5 | Berks | 113325 | Hamburg Traffic Improvements | 4028 | HAM | Highway Reconstruction | FD | 581 | 2033-04-01 |  | 0 | 0 | 19123 | 0 | 0 | 0 | 0 | 0 | 0 | 19123
Reading | 5 | Berks | 113325 | Hamburg Traffic Improvements | 4028 | HAM | Highway Reconstruction | CON | STU | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1304800 | 1304800
Reading | 5 | Berks | 113325 | Hamburg Traffic Improvements | 4028 | HAM | Highway Reconstruction | CON | 581 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326200 | 326200
Reading | 5 | Berks | 113821 | Antietem Rd Resurf-SR 562 to Carsonia | 2025 | 04M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 1159300 | 0 | 0 | 0 | 1159300
Reading | 5 | Berks | 113825 | Limekiln Road Resurface SR 562 to US 422 WB Ramps | 2025 | 03M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 550000 | 125300 | 0 | 0 | 0 | 0 | 675300
Reading | 5 | Berks | 113841 | SR 3055 (Mull Avenue/Van Reed Road) Resurface | 3055 | 05M | Highway Restoration | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035488 | 2035488
Reading | 5 | Berks | 114378 | RATS Bridge Preservation #9 | 662 | BRM | Preventive Maintenance | CON | 185 | 2023-08-24 | 2023-08-24 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Reading | 5 | Berks | 114386 | Route 419 Culvert Replacement | 419 | 04B | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 16884 | 0 | 0 | 0 | 0 | 0 | 16884
Reading | 5 | Berks | 114386 | Route 419 Culvert Replacement | 419 | 04B | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 11593 | 0 | 0 | 0 | 0 | 11593
Reading | 5 | Berks | 114392 | Berks Box Culvert Bundle #2 | 100 | BCB | Bridge Restoration | PE | 185 | 2031-04-01 |  | 0 | 0 | 400000 | 965875 | 0 | 0 | 0 | 0 | 0 | 1365875
Reading | 5 | Berks | 114392 | Berks Box Culvert Bundle #2 | 100 | BCB | Bridge Restoration | FD | 185 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 375000 | 88720 | 0 | 0 | 0 | 463720
Reading | 5 | Berks | 114392 | Berks Box Culvert Bundle #2 | 100 | BCB | Bridge Restoration | CON | 185 | 2031-04-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 1149380 | 0 | 0 | 2149380
Reading | 5 | Berks | 114408 | SR 143 Over unnamed trib to Maiden Creek | 143 | 03B | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 587160 | 587160
Reading | 5 | Berks | 114439 | West Shore Bypass - Phase 1 | 422 | PH1 | Highway Reconstruction | FD | NHPP | 2028-07-13 |  | 6474889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6474889
Reading | 5 | Berks | 114439 | West Shore Bypass - Phase 1 | 422 | PH1 | Highway Reconstruction | FD | STP | 2028-07-13 |  | 1003000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1003000
Reading | 5 | Berks | 114439 | West Shore Bypass - Phase 1 | 422 | PH1 | Highway Reconstruction | FD | STU | 2028-07-13 |  | 1733145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1733145
Reading | 5 | Berks | 114439 | West Shore Bypass - Phase 1 | 422 | PH1 | Highway Reconstruction | ROW | NHPP | 2028-07-13 |  | 0 | 2414772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2414772
Reading | 5 | Berks | 114439 | West Shore Bypass - Phase 1 | 422 | PH1 | Highway Reconstruction | ROW | STP | 2028-07-13 |  | 0 | 360563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360563
Reading | 5 | Berks | 114439 | West Shore Bypass - Phase 1 | 422 | PH1 | Highway Reconstruction | ROW | STU | 2028-07-13 |  | 0 | 4083965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4083965
Reading | 5 | Berks | 114439 | West Shore Bypass - Phase 1 | 422 | PH1 | Highway Reconstruction | UTL | NHPP | 2028-07-13 |  | 0 | 0 | 3000000 | 1000000 | 1070128 | 0 | 0 | 0 | 0 | 5070128
Reading | 5 | Berks | 114439 | West Shore Bypass - Phase 1 | 422 | PH1 | Highway Reconstruction | UTL | 581 | 2028-07-13 |  | 0 | 0 | 750000 | 250000 | 267532 | 0 | 0 | 0 | 0 | 1267532
Reading | 5 | Berks | 114439 | West Shore Bypass - Phase 1 | 422 | PH1 | Highway Reconstruction | CON | STP | 2028-07-13 |  | 0 | 0 | 0 | 31000000 | 35000000 | 35000000 | 35000000 | 35000000 | 74238924 | 245238924
Reading | 5 | Berks | 114439 | West Shore Bypass - Phase 1 | 422 | PH1 | Highway Reconstruction | CON | OTH-F | 2028-07-13 |  | 0 | 0 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 0 | 0 | 75000000
Reading | 5 | Berks | 114439 | West Shore Bypass - Phase 1 | 422 | PH1 | Highway Reconstruction | CON | STU | 2028-07-13 |  | 0 | 0 | 0 | 0 | 3000000 | 3000000 | 0 | 0 | 0 | 6000000
Reading | 5 | Berks | 114439 | West Shore Bypass - Phase 1 | 422 | PH1 | Highway Reconstruction | CON | 581 | 2028-07-13 |  | 0 | 0 | 0 | 14000000 | 28000000 | 19309731 | 0 | 0 | 0 | 61309731
Reading | 5 | Berks | 114439 | West Shore Bypass - Phase 1 | 422 | PH1 | Highway Reconstruction | CON | 581 | 2028-07-13 |  | 0 | 0 | 0 | 0 | 750000 | 750000 | 0 | 0 | 0 | 1500000
Reading | 5 | Berks | 114459 | Huffs Church Rd over Br Perkiomen Creek | 1022 | BCB | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 22510 | 0 | 0 | 0 | 0 | 0 | 22510
Reading | 5 | Berks | 114459 | Huffs Church Rd over Br Perkiomen Creek | 1022 | BCB | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 13912 | 0 | 0 | 0 | 0 | 13912
Reading | 5 | Berks | 114485 | RATS Bridge Preservation #10 | 568 | BRM | Bridge Restoration | CON | BRIP | 2026-03-26 | 2026-03-26 | 2346400 | 1030958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3377358
Reading | 5 | Berks | 114485 | RATS Bridge Preservation #10 | 568 | BRM | Bridge Restoration | CON | STP | 2026-03-26 | 2026-03-26 | 0 | 213950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213950
Reading | 5 | Berks | 114489 | RATS Bridge Preservation #11 | 422 | BRM | Bridge Preservation - State Funded | PE | 185 | 2027-01-28 |  | 526620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 526620
Reading | 5 | Berks | 114489 | RATS Bridge Preservation #11 | 422 | BRM | Bridge Preservation - State Funded | CON | 185 | 2027-01-28 |  | 0 | 0 | 0 | 2000000 | 3627500 | 0 | 0 | 0 | 0 | 5627500
Reading | 5 | Berks | 115991 | Centennial Road Dual Pipe Replacement | 1025 | BCB | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 16884 | 0 | 0 | 0 | 0 | 0 | 16884
Reading | 5 | Berks | 115991 | Centennial Road Dual Pipe Replacement | 1025 | BCB | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 8696 | 0 | 0 | 0 | 0 | 8696
Reading | 5 | Berks | 116478 | Smoketown Road over Little Sacony Creek | 1029 | 01B | Bridge Replacement | FD | STU | 2026-07-30 |  | 98944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98944
Reading | 5 | Berks | 116478 | Smoketown Road over Little Sacony Creek | 1029 | 01B | Bridge Replacement | FD | 185 | 2026-07-30 |  | 24736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24736
Reading | 5 | Berks | 116478 | Smoketown Road over Little Sacony Creek | 1029 | 01B | Bridge Replacement | UTL | 185 | 2026-07-30 |  | 15000 | 15900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30900
Reading | 5 | Berks | 116478 | Smoketown Road over Little Sacony Creek | 1029 | 01B | Bridge Replacement | CON | PRTCT | 2026-07-30 |  | 0 | 2121800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2121800
Reading | 5 | Berks | 116907 | Geotech In-House Assistance | 143 | GTA | Bridge Restoration | PE | 581 |  |  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 200000 | 600000
Reading | 5 | Berks | 117603 | State Hill Road - SR 222 SB to Norfolk Southern RR | 3023 | 05S | Congestion Reduction | FD | HSIP | 2027-05-13 |  | 438577 | 1132173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570750
Reading | 5 | Berks | 117603 | State Hill Road - SR 222 SB to Norfolk Southern RR | 3023 | 05S | Congestion Reduction | ROW | HSIP | 2027-05-13 |  | 0 | 309000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309000
Reading | 5 | Berks | 117603 | State Hill Road - SR 222 SB to Norfolk Southern RR | 3023 | 05S | Congestion Reduction | UTL | HSIP | 2027-05-13 |  | 0 | 0 | 109270 | 0 | 0 | 0 | 0 | 0 | 0 | 109270
Reading | 5 | Berks | 117603 | State Hill Road - SR 222 SB to Norfolk Southern RR | 3023 | 05S | Congestion Reduction | CON | CAQ | 2027-05-13 |  | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000
Reading | 5 | Berks | 117603 | State Hill Road - SR 222 SB to Norfolk Southern RR | 3023 | 05S | Congestion Reduction | CON | CRP | 2027-05-13 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
Reading | 5 | Berks | 117603 | State Hill Road - SR 222 SB to Norfolk Southern RR | 3023 | 05S | Congestion Reduction | CON | CRPU | 2027-05-13 |  | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 0 | 700000
Reading | 5 | Berks | 117603 | State Hill Road - SR 222 SB to Norfolk Southern RR | 3023 | 05S | Congestion Reduction | CON | HSIP | 2027-05-13 |  | 0 | 0 | 0 | 2100000 | 2500000 | 3134300 | 0 | 0 | 0 | 7734300
Reading | 5 | Berks | 117620 | State Hill Road - Norfolk Southern RR to Penn Ave. | 3023 | 06S | Congestion Reduction | PE | CAQ | 2029-01-18 |  | 0 | 56653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56653
Reading | 5 | Berks | 117620 | State Hill Road - Norfolk Southern RR to Penn Ave. | 3023 | 06S | Congestion Reduction | FD | CAQ | 2029-01-18 |  | 0 | 0 | 437080 | 0 | 0 | 0 | 0 | 0 | 0 | 437080
Reading | 5 | Berks | 117620 | State Hill Road - Norfolk Southern RR to Penn Ave. | 3023 | 06S | Congestion Reduction | FD | 581 | 2029-01-18 |  | 0 | 0 | 109270 | 0 | 0 | 0 | 0 | 0 | 0 | 109270
Reading | 5 | Berks | 117620 | State Hill Road - Norfolk Southern RR to Penn Ave. | 3023 | 06S | Congestion Reduction | ROW | CAQ | 2029-01-18 |  | 0 | 0 | 400000 | 911240 | 0 | 0 | 0 | 0 | 0 | 1311240
Reading | 5 | Berks | 117620 | State Hill Road - Norfolk Southern RR to Penn Ave. | 3023 | 06S | Congestion Reduction | ROW | 581 | 2029-01-18 |  | 0 | 0 | 100000 | 227810 | 0 | 0 | 0 | 0 | 0 | 327810
Reading | 5 | Berks | 117620 | State Hill Road - Norfolk Southern RR to Penn Ave. | 3023 | 06S | Congestion Reduction | UTL | CAQ | 2029-01-18 |  | 0 | 0 | 100000 | 300000 | 255620 | 0 | 0 | 0 | 0 | 655620
Reading | 5 | Berks | 117620 | State Hill Road - Norfolk Southern RR to Penn Ave. | 3023 | 06S | Congestion Reduction | CON | CAQ | 2029-01-18 |  | 0 | 0 | 0 | 0 | 500000 | 2300000 | 2180000 | 120920 | 0 | 5100920
Reading | 5 | Berks | 117622 | RATS AWPM - 2025 | 61 | AWT | Safety Improvement | CON | STP | 2025-03-13 | 2025-03-13 | 199379 | 0 | 355440 | 0 | 400000 | 0 | 400000 | 0 | 0 | 1354819
Reading | 5 | Berks | 117719 | Bernville Rd Study - New Schaefferstown Rd North | 183 | 01S | Highway Restoration | PE | 581 | 2028-07-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443380 | 0 | 443380
Reading | 5 | Berks | 117719 | Bernville Rd Study - New Schaefferstown Rd North | 183 | 01S | Highway Restoration | FD | 581 | 2028-07-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521920 | 521920
Reading | 5 | Berks | 117719 | Bernville Rd Study - New Schaefferstown Rd North | 183 | 01S | Highway Restoration | ROW | 581 | 2028-07-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195720 | 195720
Reading | 5 | Berks | 117719 | Bernville Rd Study - New Schaefferstown Rd North | 183 | 01S | Highway Restoration | UTL | 581 | 2028-07-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130480 | 130480
Reading | 5 | Berks | 117719 | Bernville Rd Study - New Schaefferstown Rd North | 183 | 01S | Highway Restoration | CON | 581 | 2028-07-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3262000 | 3262000
Reading | 5 | Berks | 117721 | SR 183 (Bernville Road) Lane Drop Hourglass Fix | 183 | 03S | Highway Restoration | STUDY | STP | 2030-04-01 |  | 0 | 155066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155066
Reading | 5 | Berks | 117721 | SR 183 (Bernville Road) Lane Drop Hourglass Fix | 183 | 03S | Highway Restoration | STUDY | STU | 2030-04-01 |  | 614428 | 3006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617434
Reading | 5 | Berks | 117723 | SR 737 (Krumsville Road) Slope Repair | 737 | SLR | Highway Restoration | PE | PRTCT |  |  | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
Reading | 5 | Berks | 117724 | Long Lane (SR 1024) over Mill Creek | 1024 | 01B | Bridge Replacement | PE | BOF | 2028-08-17 |  | 23500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23500
Reading | 5 | Berks | 117724 | Long Lane (SR 1024) over Mill Creek | 1024 | 01B | Bridge Replacement | PE | BRIP | 2028-08-17 |  | 42856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42856
Reading | 5 | Berks | 117724 | Long Lane (SR 1024) over Mill Creek | 1024 | 01B | Bridge Replacement | PE | 581 | 2028-08-17 |  | 16589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16589
Reading | 5 | Berks | 117724 | Long Lane (SR 1024) over Mill Creek | 1024 | 01B | Bridge Replacement | FD | BRIP | 2028-08-17 |  | 0 | 175000 | 122052 | 0 | 0 | 0 | 0 | 0 | 0 | 297052
Reading | 5 | Berks | 117724 | Long Lane (SR 1024) over Mill Creek | 1024 | 01B | Bridge Replacement | FD | 185 | 2028-08-17 |  | 0 | 43750 | 30513 | 0 | 0 | 0 | 0 | 0 | 0 | 74263
Reading | 5 | Berks | 117724 | Long Lane (SR 1024) over Mill Creek | 1024 | 01B | Bridge Replacement | ROW | BRIP | 2028-08-17 |  | 0 | 42436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42436
Reading | 5 | Berks | 117724 | Long Lane (SR 1024) over Mill Creek | 1024 | 01B | Bridge Replacement | ROW | 185 | 2028-08-17 |  | 0 | 10609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10609
Reading | 5 | Berks | 117724 | Long Lane (SR 1024) over Mill Creek | 1024 | 01B | Bridge Replacement | UTL | BRIP | 2028-08-17 |  | 0 | 0 | 0 | 0 | 18552 | 0 | 0 | 0 | 0 | 18552
Reading | 5 | Berks | 117724 | Long Lane (SR 1024) over Mill Creek | 1024 | 01B | Bridge Replacement | UTL | 185 | 2028-08-17 |  | 0 | 0 | 0 | 0 | 4638 | 0 | 0 | 0 | 0 | 4638
Reading | 5 | Berks | 117724 | Long Lane (SR 1024) over Mill Creek | 1024 | 01B | Bridge Replacement | CON | BRIP | 2028-08-17 |  | 0 | 0 | 0 | 0 | 400000 | 692700 | 0 | 0 | 0 | 1092700
Reading | 5 | Berks | 117724 | Long Lane (SR 1024) over Mill Creek | 1024 | 01B | Bridge Replacement | CON | 581 | 2028-08-17 |  | 0 | 0 | 0 | 0 | 100000 | 173175 | 0 | 0 | 0 | 273175
Reading | 5 | Berks | 117725 | Meckville Road over Meck Creek | 4005 | 01B | Bridge Replacement | FD | BOF | 2027-10-21 |  | 0 | 308940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308940
Reading | 5 | Berks | 117725 | Meckville Road over Meck Creek | 4005 | 01B | Bridge Replacement | FD | 185 | 2027-10-21 |  | 0 | 77235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77235
Reading | 5 | Berks | 117725 | Meckville Road over Meck Creek | 4005 | 01B | Bridge Replacement | ROW | BOF | 2027-10-21 |  | 0 | 63120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63120
Reading | 5 | Berks | 117725 | Meckville Road over Meck Creek | 4005 | 01B | Bridge Replacement | ROW | 185 | 2027-10-21 |  | 0 | 15780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15780
Reading | 5 | Berks | 117725 | Meckville Road over Meck Creek | 4005 | 01B | Bridge Replacement | UTL | BOF | 2027-10-21 |  | 0 | 0 | 0 | 18008 | 0 | 0 | 0 | 0 | 0 | 18008
Reading | 5 | Berks | 117725 | Meckville Road over Meck Creek | 4005 | 01B | Bridge Replacement | UTL | 185 | 2027-10-21 |  | 0 | 0 | 0 | 4502 | 0 | 0 | 0 | 0 | 0 | 4502
Reading | 5 | Berks | 117725 | Meckville Road over Meck Creek | 4005 | 01B | Bridge Replacement | CON | BOF | 2027-10-21 |  | 0 | 0 | 0 | 400000 | 680480 | 0 | 0 | 0 | 0 | 1080480
Reading | 5 | Berks | 117725 | Meckville Road over Meck Creek | 4005 | 01B | Bridge Replacement | CON | 185 | 2027-10-21 |  | 0 | 0 | 0 | 100000 | 170120 | 0 | 0 | 0 | 0 | 270120
Reading | 5 | Berks | 117726 | SR 4028 (Old Route 22) over Maiden Creek Tributary | 4028 | 03B | Bridge Replacement | PE | STP | 2028-02-17 |  | 257481 | 44560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302041
Reading | 5 | Berks | 117726 | SR 4028 (Old Route 22) over Maiden Creek Tributary | 4028 | 03B | Bridge Replacement | FD | STP | 2028-02-17 |  | 0 | 213534 | 41082 | 0 | 0 | 0 | 0 | 0 | 0 | 254616
Reading | 5 | Berks | 117726 | SR 4028 (Old Route 22) over Maiden Creek Tributary | 4028 | 03B | Bridge Replacement | FD | 185 | 2028-02-17 |  | 0 | 53384 | 10270 | 0 | 0 | 0 | 0 | 0 | 0 | 63654
Reading | 5 | Berks | 117726 | SR 4028 (Old Route 22) over Maiden Creek Tributary | 4028 | 03B | Bridge Replacement | ROW | 185 | 2028-02-17 |  | 0 | 21218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21218
Reading | 5 | Berks | 117726 | SR 4028 (Old Route 22) over Maiden Creek Tributary | 4028 | 03B | Bridge Replacement | UTL | 185 | 2028-02-17 |  | 0 | 0 | 0 | 0 | 11593 | 0 | 0 | 0 | 0 | 11593
Reading | 5 | Berks | 117726 | SR 4028 (Old Route 22) over Maiden Creek Tributary | 4028 | 03B | Bridge Replacement | CON | BRIP | 2028-02-17 |  | 0 | 0 | 0 | 0 | 600000 | 550000 | 473020 | 0 | 0 | 1623020
Reading | 5 | Berks | 117726 | SR 4028 (Old Route 22) over Maiden Creek Tributary | 4028 | 03B | Bridge Replacement | CON | 185 | 2028-02-17 |  | 0 | 0 | 0 | 0 | 150000 | 137500 | 118255 | 0 | 0 | 405755
Reading | 5 | Berks | 117973 | Walnuttown Road Crossing | 1011 | 09X | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 0 | 454000 | 0 | 0 | 0 | 0 | 0 | 0 | 454000
Reading | 5 | Berks | 117975 | Manatawny Drive Crossing | 2036 | 10X | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 0 | 0 | 0 | 380000 | 0 | 0 | 0 | 0 | 380000
Reading | 5 | Berks | 118408 | Ontelaunee Township Stormwater Improvements | 4029 | OTS | Transportation Enhancement | CON | TAU | 2025-09-11 | 2025-07-24 | 233705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233705
Reading | 5 | Berks | 120983 | High Friction Surface Treatments (Berks 2025) | 61 | HFS | Safety Improvement | CON | HSIP | 2025-07-10 | 2025-07-10 | 288295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288295
Reading | 5 | Berks | 120983 | High Friction Surface Treatments (Berks 2025) | 61 | HFS | Safety Improvement | CON | HSIP | 2025-07-10 | 2025-07-10 | 0 | 0 | 400000 | 0 | 400000 | 0 | 400000 | 0 | 0 | 1200000
Reading | 5 | Berks | 120988 | BPN-4 Guiderail Upgrades | 2065 | BPN | Highway Restoration | CON | 581 |  |  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 200000 | 600000
Reading | 5 | Berks | 120990 | RATS Bridge Preservation #12 | 4021 | 0 | Bridge Preservation - State Funded | PE | 185 |  |  | 0 | 0 | 0 | 0 | 200000 | 205755 | 0 | 0 | 0 | 405755
Reading | 5 | Berks | 120990 | RATS Bridge Preservation #12 | 4021 | 0 | Bridge Preservation - State Funded | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 2649500 | 0 | 6149500
Reading | 5 | Berks | 120991 | RATS ITS Camera Gaps | 78 | ITC | Intelligent Transportation System | PE | CRP | 2026-01-15 | 2026-01-15 | 49100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49100
Reading | 5 | Berks | 120991 | RATS ITS Camera Gaps | 78 | ITC | Intelligent Transportation System | PE | STP | 2026-01-15 | 2026-01-15 | 12275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12275
Reading | 5 | Berks | 120991 | RATS ITS Camera Gaps | 78 | ITC | Intelligent Transportation System | FD | CRP | 2026-01-15 | 2026-01-15 | 4236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4236
Reading | 5 | Berks | 120991 | RATS ITS Camera Gaps | 78 | ITC | Intelligent Transportation System | FD | STP | 2026-01-15 | 2026-01-15 | 1059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1059
Reading | 5 | Berks | 120991 | RATS ITS Camera Gaps | 78 | ITC | Intelligent Transportation System | CON | CRP | 2026-01-15 | 2026-01-15 | 631852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 631852
Reading | 5 | Berks | 120991 | RATS ITS Camera Gaps | 78 | ITC | Intelligent Transportation System | CON | STP | 2026-01-15 | 2026-01-15 | 157963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157963
Reading | 5 | Berks | 120995 | Municipal Bridge Line Item |  |  | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 600000 | 1800000 | 800000 | 800000 | 1500000 | 1000000 | 1695250 | 8195250
Reading | 5 | Berks | 121039 | Berks High Volume Ralumac Microsurfacings | 3222 | 0 | Highway Restoration | CON | 581 | 413181 |  | 0 | 0 | 3402562 | 5460895 | 4911482 | 4725337 | 0 | 0 | 0 | 18500276
Reading | 5 | Berks | 121057 | Berks High Volume Ralumac Microsurfacings #1 | 3222 | BO1 | Highway Restoration | CON | 581 | 2025-05-08 | 2025-05-08 | 3779356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3779356
Reading | 5 | Berks | 121555 | Angelica Creek Trail Extension | 625 | ACT | Bicycle Pedestrian Highway | CON | TAP | 2026-10-22 |  | 0 | 376774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376774
Reading | 5 | Berks | 121555 | Angelica Creek Trail Extension | 625 | ACT | Bicycle Pedestrian Highway | CON | TAU | 2026-10-22 |  | 435295 | 530226 | 157705 | 0 | 0 | 0 | 0 | 0 | 0 | 1123226
Reading | 5 | Berks | 123129 | Levengood Road Bridge over Manatawny Creek | 7203 | A13 | Bridge Restoration | PE | ACT13 |  |  | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
Reading | 5 | Berks | 123129 | Levengood Road Bridge over Manatawny Creek | 7203 | A13 | Bridge Restoration | FD | ACT13 |  |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Reading | 5 | Berks | 123129 | Levengood Road Bridge over Manatawny Creek | 7203 | A13 | Bridge Restoration | ROW | ACT13 |  |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Reading | 5 | Berks | 123129 | Levengood Road Bridge over Manatawny Creek | 7203 | A13 | Bridge Restoration | UTL | ACT13 |  |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Reading | 5 | Berks | 123129 | Levengood Road Bridge over Manatawny Creek | 7203 | A13 | Bridge Restoration | CON | ACT13 |  |  | 0 | 0 | 600000 | 200000 | 0 | 0 | 0 | 0 | 0 | 800000
Reading | 5 | Berks | 123318 | Berks High Volume Ralumac Microsurfacing # 2 | 2082 | BO2 | Highway Restoration | CON | 581 | 2026-03-26 | 2026-03-26 | 0 | 5508117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5508117
S. Alleghenies | 9 | Bedford | 21366 | SR 1005 over Beaver Creek | 1005 | 09B | Bridge Restoration | PE | 185 | 2030-02-14 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 21366 | SR 1005 over Beaver Creek | 1005 | 09B | Bridge Restoration | ROW | 185 | 2030-02-14 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Bedford | 21366 | SR 1005 over Beaver Creek | 1005 | 09B | Bridge Restoration | CON | 185 | 2030-02-14 |  | 0 | 0 | 0 | 0 | 0 | 255000 | 1444000 | 0 | 0 | 1699000
S. Alleghenies | 9 | Bedford | 21443 | PA 31 over Raystown Branch Juniata River | 31 | 0 | Bridge Restoration | PE | BRIP | 2034-01-05 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 21443 | PA 31 over Raystown Branch Juniata River | 31 | 0 | Bridge Restoration | ROW | BRIP | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 21443 | PA 31 over Raystown Branch Juniata River | 31 | 0 | Bridge Restoration | UTL | BRIP | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 21443 | PA 31 over Raystown Branch Juniata River | 31 | 0 | Bridge Restoration | CON | BRIP | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1025000 | 525000 | 1550000
S. Alleghenies | 9 | Bedford | 21449 | Osterburg Scrubgrass Crk | 869 | 01B | Bridge Replacement | FD | 185 | 2027-08-26 |  | 0 | 0 | 100000 | 200000 | 0 | 0 | 0 | 0 | 0 | 300000
S. Alleghenies | 9 | Bedford | 21449 | Osterburg Scrubgrass Crk | 869 | 01B | Bridge Replacement | ROW | 185 | 2027-08-26 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Bedford | 21449 | Osterburg Scrubgrass Crk | 869 | 01B | Bridge Replacement | UTL | 185 | 2027-08-26 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Bedford | 21449 | Osterburg Scrubgrass Crk | 869 | 01B | Bridge Replacement | CON | 185 | 2027-08-26 |  | 0 | 0 | 0 | 322300 | 234203 | 1113750 | 340000 | 0 | 0 | 2010253
S. Alleghenies | 9 | Bedford | 21465 | SR 1015 Beaver Crk Bridge | 1015 | 03B | Bridge Replacement | PE | BOF | 2027-12-16 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
S. Alleghenies | 9 | Bedford | 21465 | SR 1015 Beaver Crk Bridge | 1015 | 03B | Bridge Replacement | ROW | BOF | 2027-12-16 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Bedford | 21465 | SR 1015 Beaver Crk Bridge | 1015 | 03B | Bridge Replacement | UTL | BOF | 2027-12-16 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Bedford | 21465 | SR 1015 Beaver Crk Bridge | 1015 | 03B | Bridge Replacement | CON | BOF | 2027-12-16 |  | 0 | 0 | 131127 | 469873 | 0 | 0 | 0 | 0 | 0 | 601000
S. Alleghenies | 9 | Bedford | 21480 | US 30 over Former RR | 30 | 43B | Bridge Preservation - Federal | CON | BRIP | 2024-04-11 | 2024-04-11 | 576868 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626868
S. Alleghenies | 9 | Bedford | 21481 | US 30 over PA 26 | 30 | 44B | Bridge Preservation - Federal | CON | BRIP | 2024-04-11 | 2024-04-11 | 0 | 318000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318000
S. Alleghenies | 9 | Bedford | 21481 | US 30 over PA 26 | 30 | 44B | Bridge Preservation - Federal | CON | STP | 2024-04-11 | 2024-04-11 | 975149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975149
S. Alleghenies | 9 | Bedford | 21483 | SR 1007 over US 30 | 1007 | 0 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000
S. Alleghenies | 9 | Bedford | 21483 | SR 1007 over US 30 | 1007 | 0 | Bridge Restoration | FD | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430000 | 430000
S. Alleghenies | 9 | Bedford | 21483 | SR 1007 over US 30 | 1007 | 0 | Bridge Restoration | ROW | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 21483 | SR 1007 over US 30 | 1007 | 0 | Bridge Restoration | UTL | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 21483 | SR 1007 over US 30 | 1007 | 0 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
S. Alleghenies | 9 | Bedford | 21523 | SR 4027 over Scrubgrass Creek | 4027 | 02B | Bridge Restoration | PE | BOF | 2030-12-12 |  | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000
S. Alleghenies | 9 | Bedford | 21523 | SR 4027 over Scrubgrass Creek | 4027 | 02B | Bridge Restoration | FD | BRIP | 2030-12-12 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
S. Alleghenies | 9 | Bedford | 21523 | SR 4027 over Scrubgrass Creek | 4027 | 02B | Bridge Restoration | ROW | BRIP | 2030-12-12 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 21523 | SR 4027 over Scrubgrass Creek | 4027 | 02B | Bridge Restoration | UTL | BRIP | 2030-12-12 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 21523 | SR 4027 over Scrubgrass Creek | 4027 | 02B | Bridge Restoration | CON | BRIP | 2030-12-12 |  | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 1500000
S. Alleghenies | 9 | Bedford | 21561 | US 30 Cliffs Br | 30 | 38B | Bridge Restoration | CON | BRIP | 2025-09-11 | 2025-09-11 | 795000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 795000
S. Alleghenies | 9 | Bedford | 21570 | Bobs Creek Bridge | 869 | 10B | Bridge Restoration | FD | BRIP | 2027-12-16 |  | 0 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325000
S. Alleghenies | 9 | Bedford | 21570 | Bobs Creek Bridge | 869 | 10B | Bridge Restoration | ROW | BRIP | 2027-12-16 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 21570 | Bobs Creek Bridge | 869 | 10B | Bridge Restoration | UTL | BRIP | 2027-12-16 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 21570 | Bobs Creek Bridge | 869 | 10B | Bridge Restoration | CON | BRIP | 2027-12-16 |  | 0 | 0 | 629000 | 564000 | 400000 | 0 | 0 | 0 | 0 | 1593000
S. Alleghenies | 9 | Bedford | 21576 | SR 2025 over Clear Creek | 2025 | 03B | Bridge Replacement | PE | 185 | 2028-02-03 |  | 370566 | 79434 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
S. Alleghenies | 9 | Bedford | 21576 | SR 2025 over Clear Creek | 2025 | 03B | Bridge Replacement | FD | 185 | 2028-02-03 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
S. Alleghenies | 9 | Bedford | 21576 | SR 2025 over Clear Creek | 2025 | 03B | Bridge Replacement | ROW | 185 | 2028-02-03 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 21576 | SR 2025 over Clear Creek | 2025 | 03B | Bridge Replacement | UTL | 185 | 2028-02-03 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 21576 | SR 2025 over Clear Creek | 2025 | 03B | Bridge Replacement | CON | BOF | 2028-02-03 |  | 0 | 0 | 0 | 1000000 | 568000 | 348125 | 83875 | 0 | 0 | 2000000
S. Alleghenies | 9 | Bedford | 21588 | PA 26 over Ravers Run | 26 | 27B | Bridge Replacement | CON | BRIP | 2025-01-09 | 2025-01-09 | 1206783.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1206783.05
S. Alleghenies | 9 | Bedford | 21589 | US 220 over Oster Run | 220 | 0 | Bridge Restoration | PE | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
S. Alleghenies | 9 | Bedford | 21589 | US 220 over Oster Run | 220 | 0 | Bridge Restoration | ROW | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Bedford | 21589 | US 220 over Oster Run | 220 | 0 | Bridge Restoration | UTL | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Bedford | 21589 | US 220 over Oster Run | 220 | 0 | Bridge Restoration | CON | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1048000 | 1048000
S. Alleghenies | 9 | Bedford | 21611 | T-705 Over Three Springs Run 1 | 7221 | 3SP | Bridge Restoration | FD | BOF | 2026-09-03 |  | 57200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57200
S. Alleghenies | 9 | Bedford | 21611 | T-705 Over Three Springs Run 1 | 7221 | 3SP | Bridge Restoration | FD | 183 | 2026-09-03 |  | 10725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10725
S. Alleghenies | 9 | Bedford | 21611 | T-705 Over Three Springs Run 1 | 7221 | 3SP | Bridge Restoration | FD | LOC | 2026-09-03 |  | 3575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3575
S. Alleghenies | 9 | Bedford | 21611 | T-705 Over Three Springs Run 1 | 7221 | 3SP | Bridge Restoration | ROW | BOF | 2026-09-03 |  | 50160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50160
S. Alleghenies | 9 | Bedford | 21611 | T-705 Over Three Springs Run 1 | 7221 | 3SP | Bridge Restoration | ROW | 183 | 2026-09-03 |  | 9405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9405
S. Alleghenies | 9 | Bedford | 21611 | T-705 Over Three Springs Run 1 | 7221 | 3SP | Bridge Restoration | ROW | LOC | 2026-09-03 |  | 3135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3135
S. Alleghenies | 9 | Bedford | 21611 | T-705 Over Three Springs Run 1 | 7221 | 3SP | Bridge Restoration | UTL | BOF | 2026-09-03 |  | 24640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24640
S. Alleghenies | 9 | Bedford | 21611 | T-705 Over Three Springs Run 1 | 7221 | 3SP | Bridge Restoration | UTL | 183 | 2026-09-03 |  | 4620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4620
S. Alleghenies | 9 | Bedford | 21611 | T-705 Over Three Springs Run 1 | 7221 | 3SP | Bridge Restoration | UTL | LOC | 2026-09-03 |  | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1540
S. Alleghenies | 9 | Bedford | 21611 | T-705 Over Three Springs Run 1 | 7221 | 3SP | Bridge Restoration | CON | BOF | 2026-09-03 |  | 0 | 396000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396000
S. Alleghenies | 9 | Bedford | 21611 | T-705 Over Three Springs Run 1 | 7221 | 3SP | Bridge Restoration | CON | 183 | 2026-09-03 |  | 0 | 74250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74250
S. Alleghenies | 9 | Bedford | 21611 | T-705 Over Three Springs Run 1 | 7221 | 3SP | Bridge Restoration | CON | LOC | 2026-09-03 |  | 0 | 24750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24750
S. Alleghenies | 9 | Bedford | 22594 | Local Bridge Reserve |  | LBR | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 3200000 | 4200000
S. Alleghenies | 9 | Bedford | 22594 | Local Bridge Reserve |  | LBR | Reserve Line Item | CON | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 625000
S. Alleghenies | 9 | Bedford | 22594 | Local Bridge Reserve |  | LBR | Reserve Line Item | CON | LOC |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 250000 | 300000
S. Alleghenies | 9 | Bedford | 63857 | US 30 - Somerset Co Line to T-496 | 30 | 049 | Highway Restoration | PE | 581 | 2029-11-08 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
S. Alleghenies | 9 | Bedford | 63857 | US 30 - Somerset Co Line to T-496 | 30 | 049 | Highway Restoration | CON | NHPP | 2029-11-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5113000 | 2000000 | 0 | 7113000
S. Alleghenies | 9 | Bedford | 63857 | US 30 - Somerset Co Line to T-496 | 30 | 049 | Highway Restoration | CON | STP | 2029-11-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1001094 | 0 | 1001094
S. Alleghenies | 9 | Bedford | 63857 | US 30 - Somerset Co Line to T-496 | 30 | 049 | Highway Restoration | CON | 581 | 2029-11-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084906 | 0 | 2084906
S. Alleghenies | 9 | Bedford | 72234 | SA Bridge & Hwy Reserve |  | RLI | Reserve Line Item | CON | BOF |  |  | 0 | 614715 | 306720 | 0 | 0 | 0 | 1916125 | 1000000 | 2000000 | 5837560
S. Alleghenies | 9 | Bedford | 72234 | SA Bridge & Hwy Reserve |  | RLI | Reserve Line Item | CON | BRIP |  |  | 0 | 2008637 | 962633 | 66000 | 0 | 0 | 0 | 0 | 0 | 3037270
S. Alleghenies | 9 | Bedford | 72234 | SA Bridge & Hwy Reserve |  | RLI | Reserve Line Item | CON | CRP |  |  | 0 | 716876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716876
S. Alleghenies | 9 | Bedford | 72234 | SA Bridge & Hwy Reserve |  | RLI | Reserve Line Item | CON | HSIP |  |  | 0 | 143753 | 584000 | 0 | 0 | 0 | 0 | 0 | 4736000 | 5463753
S. Alleghenies | 9 | Bedford | 72234 | SA Bridge & Hwy Reserve |  | RLI | Reserve Line Item | CON | NHPP |  |  | 0 | 711230 | 1159738 | 500000 | 0 | 0 | 0 | 0 | 1000000 | 3370968
S. Alleghenies | 9 | Bedford | 72234 | SA Bridge & Hwy Reserve |  | RLI | Reserve Line Item | CON | STP |  |  | 0 | 230309 | 0 | 0 | 0 | 0 | 671580 | 0 | 2000000 | 2901889
S. Alleghenies | 9 | Bedford | 72234 | SA Bridge & Hwy Reserve |  | RLI | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 369891 | 674090 | 0 | 0 | 0 | 0 | 0 | 1043981
S. Alleghenies | 9 | Bedford | 72234 | SA Bridge & Hwy Reserve |  | RLI | Reserve Line Item | CON | 581 |  |  | 98318 | 671018 | 1432695 | 1260099 | 1000000 | 0 | 0 | 0 | 2000000 | 6462130
S. Alleghenies | 9 | Bedford | 72234 | SA Bridge & Hwy Reserve |  | RLI | Reserve Line Item | CON | LOC |  |  | 0 | 44538.65 | 103945.3 | 0 | 4250 | 0 | 0 | 0 | 0 | 152733.95
S. Alleghenies | 9 | Bedford | 74405 | SR 2017 over Cove Creek Trib | 2017 | 000 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
S. Alleghenies | 9 | Bedford | 74405 | SR 2017 over Cove Creek Trib | 2017 | 000 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 74405 | SR 2017 over Cove Creek Trib | 2017 | 000 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 74405 | SR 2017 over Cove Creek Trib | 2017 | 000 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Bedford | 74407 | Evitts Creek Trib | 3011 | 01B | Bridge Replacement | CON | 185 | 2025-01-09 | 2025-01-09 | 512758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512758
S. Alleghenies | 9 | Bedford | 74415 | SR 4010 over Shobers Run | 4010 | 02B | Bridge Restoration | PE | 185 | 2031-12-04 |  | 0 | 0 | 0 | 0 | 0 | 254000 | 746000 | 0 | 0 | 1000000
S. Alleghenies | 9 | Bedford | 74415 | SR 4010 over Shobers Run | 4010 | 02B | Bridge Restoration | FD | 185 | 2031-12-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 700000
S. Alleghenies | 9 | Bedford | 74415 | SR 4010 over Shobers Run | 4010 | 02B | Bridge Restoration | ROW | 185 | 2031-12-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
S. Alleghenies | 9 | Bedford | 74415 | SR 4010 over Shobers Run | 4010 | 02B | Bridge Restoration | UTL | 185 | 2031-12-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
S. Alleghenies | 9 | Bedford | 74415 | SR 4010 over Shobers Run | 4010 | 02B | Bridge Restoration | CON | BRIP | 2031-12-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500000 | 6500000
S. Alleghenies | 9 | Bedford | 84878 | PA 31 over Finn Run | 31 | 12B | Bridge Restoration | PE | BRIP | 2029-01-18 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
S. Alleghenies | 9 | Bedford | 84878 | PA 31 over Finn Run | 31 | 12B | Bridge Restoration | FD | BRIP | 2029-01-18 |  | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
S. Alleghenies | 9 | Bedford | 84878 | PA 31 over Finn Run | 31 | 12B | Bridge Restoration | ROW | BRIP | 2029-01-18 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
S. Alleghenies | 9 | Bedford | 84878 | PA 31 over Finn Run | 31 | 12B | Bridge Restoration | UTL | BRIP | 2029-01-18 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
S. Alleghenies | 9 | Bedford | 84878 | PA 31 over Finn Run | 31 | 12B | Bridge Restoration | CON | BRIP | 2029-01-18 |  | 0 | 0 | 0 | 0 | 305000 | 385000 | 510000 | 0 | 0 | 1200000
S. Alleghenies | 9 | Bedford | 88125 | SR 1018 over Oppenheimer Run | 1018 | 000 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
S. Alleghenies | 9 | Bedford | 88125 | SR 1018 over Oppenheimer Run | 1018 | 000 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 88125 | SR 1018 over Oppenheimer Run | 1018 | 000 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 88125 | SR 1018 over Oppenheimer Run | 1018 | 000 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Bedford | 88131 | Cumberland Vlly Run Br | 3021 | 02B | Bridge Replacement | CON | 185 | 2025-04-17 | 2025-04-17 | 397211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397211
S. Alleghenies | 9 | Bedford | 91440 | Hopewell Bridge Replace | 915 | 03B | Bridge Replacement | CON | NHPP | 2017-11-09 | 2017-11-09 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000
S. Alleghenies | 9 | Bedford | 94346 | PA 26 over Piney Creek | 26 | 000 | Bridge Restoration | PE | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 94346 | PA 26 over Piney Creek | 26 | 000 | Bridge Restoration | ROW | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 94346 | PA 26 over Piney Creek | 26 | 000 | Bridge Restoration | UTL | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 94346 | PA 26 over Piney Creek | 26 | 000 | Bridge Restoration | CON | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000 | 0 | 1300000
S. Alleghenies | 9 | Bedford | 96349 | PA 96 Mryland Ln-Washgtn St | 96 | 022 | Highway Restoration | PE | 581 | 2028-03-23 |  | 0 | 637852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637852
S. Alleghenies | 9 | Bedford | 96349 | PA 96 Mryland Ln-Washgtn St | 96 | 022 | Highway Restoration | ROW | 581 | 2028-03-23 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
S. Alleghenies | 9 | Bedford | 96349 | PA 96 Mryland Ln-Washgtn St | 96 | 022 | Highway Restoration | UTL | 581 | 2028-03-23 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Bedford | 96349 | PA 96 Mryland Ln-Washgtn St | 96 | 022 | Highway Restoration | CON | 581 | 2028-03-23 |  | 0 | 0 | 0 | 3698977 | 3352005 | 0 | 0 | 0 | 0 | 7050982
S. Alleghenies | 9 | Bedford | 96517 | Reynldsdale Rd-Red Oak Rd | 56 | 029 | Highway Restoration | CON | NHPP | 2024-09-26 | 2024-09-26 | 2202748 | 769156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2971904
S. Alleghenies | 9 | Bedford | 96675 | Manns Choice Buffalo Run | 31 | 11B | Bridge Restoration | UTL | 185 | 2025-01-16 | 2025-01-16 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
S. Alleghenies | 9 | Bedford | 96675 | Manns Choice Buffalo Run | 31 | 11B | Bridge Restoration | CON | BRIP | 2025-01-16 | 2025-01-16 | 1812487 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1837487
S. Alleghenies | 9 | Bedford | 98773 | PA26 Riddlesburg - Saxton | 26 | 021 | Highway Restoration | PE | 581 | 2027-11-04 |  | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
S. Alleghenies | 9 | Bedford | 98773 | PA26 Riddlesburg - Saxton | 26 | 021 | Highway Restoration | ROW | 581 | 2027-11-04 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
S. Alleghenies | 9 | Bedford | 98773 | PA26 Riddlesburg - Saxton | 26 | 021 | Highway Restoration | UTL | 581 | 2027-11-04 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 98773 | PA26 Riddlesburg - Saxton | 26 | 021 | Highway Restoration | CON | 581 | 2027-11-04 |  | 0 | 0 | 0 | 1100000 | 2000000 | 1010000 | 0 | 0 | 0 | 4110000
S. Alleghenies | 9 | Bedford | 108153 | SR 1033 - US 30 to SR 1001 | 1033 | 002 | Highway Restoration | CON | 581 | 2025-09-11 | 2025-09-11 | 135932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135932
S. Alleghenies | 9 | Bedford | 108154 | US 30 - Scenic Rd to SR 4010 | 30 | 034 | Highway Restoration | CON | 581 | 2025-09-11 | 2025-09-11 | 2752700 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4852700
S. Alleghenies | 9 | Bedford | 108154 | US 30 - Scenic Rd to SR 4010 | 30 | 034 | Highway Restoration | CON | 581 | 2025-09-11 | 2025-09-11 | 0 | 0 | 468662 | 0 | 0 | 0 | 0 | 0 | 0 | 468662
S. Alleghenies | 9 | Bedford | 108163 | US 220 - MD State Line to Narrow Lane | 220 | 018 | Highway Restoration | CON | NHPP | 2023-12-14 | 2023-12-14 | 620000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620000
S. Alleghenies | 9 | Bedford | 110422 | PA 56 Tributary to Barefoot Run Bridge | 56 | 27B | Bridge Replacement | CON | NHPP | 2024-09-12 | 2024-09-12 | 1265362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1265362
S. Alleghenies | 9 | Bedford | 110492 | US 220 - Cumberland Valley Rd to Turnpike Inter | 220 | 0 | Highway Restoration | PE | 581 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 110492 | US 220 - Cumberland Valley Rd to Turnpike Inter | 220 | 0 | Highway Restoration | CON | NHPP | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
S. Alleghenies | 9 | Bedford | 111988 | SR 1015 over Potter Creek | 1015 | 05B | Bridge Restoration | PE | BRIP | 2030-12-05 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 111988 | SR 1015 over Potter Creek | 1015 | 05B | Bridge Restoration | ROW | BRIP | 2030-12-05 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Bedford | 111988 | SR 1015 over Potter Creek | 1015 | 05B | Bridge Restoration | UTL | BRIP | 2030-12-05 |  | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Bedford | 111988 | SR 1015 over Potter Creek | 1015 | 05B | Bridge Restoration | CON | BRIP | 2030-12-05 |  | 0 | 0 | 0 | 0 | 0 | 900000 | 100000 | 0 | 0 | 1000000
S. Alleghenies | 9 | Bedford | 111996 | SR 4034 over Mud Run | 4034 | 03B | Bridge Restoration | PE | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
S. Alleghenies | 9 | Bedford | 111996 | SR 4034 over Mud Run | 4034 | 03B | Bridge Restoration | ROW | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Bedford | 111996 | SR 4034 over Mud Run | 4034 | 03B | Bridge Restoration | UTL | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Bedford | 111996 | SR 4034 over Mud Run | 4034 | 03B | Bridge Restoration | CON | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Bedford | 114115 | US30 Seg 370 o. Raystown Br Jnt Rvr | 30 | 39B | Bridge Restoration | CON | BRIP | 2025-09-11 | 2025-09-11 | 382881 | 54228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437109
S. Alleghenies | 9 | Bedford | 114117 | US30 Seg 397 o. Raystown Br Jnt Rvr | 30 | 40B | Bridge Restoration | CON | BRIP | 2027-04-08 |  | 0 | 0 | 605237 | 0 | 0 | 0 | 0 | 0 | 0 | 605237
S. Alleghenies | 9 | Bedford | 114118 | PA 56 - Rouzer Rd to SR 4030 | 56 | 028 | Safety Improvement | CON | HSIP |  |  | 0 | 0 | 0 | 1584000 | 1584000 | 832000 | 0 | 0 | 0 | 4000000
S. Alleghenies | 9 | Bedford | 114118 | PA 56 - Rouzer Rd to SR 4030 | 56 | 028 | Safety Improvement | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 1000000 | 5000000 | 1000000 | 0 | 0 | 7000000
S. Alleghenies | 9 | Bedford | 114118 | PA 56 - Rouzer Rd to SR 4030 | 56 | 028 | Safety Improvement | CON | STP |  |  | 0 | 0 | 0 | 0 | 81412 | 704588 | 85000 | 0 | 0 | 871000
S. Alleghenies | 9 | Bedford | 116153 | Everett Bus. Park - Industrial Blvd Ext. |  | EBP | New Alignment | UTL | APL | 2026-05-07 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Bedford | 116153 | Everett Bus. Park - Industrial Blvd Ext. |  | EBP | New Alignment | CON | APL | 2026-05-07 |  | 1501960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1501960
S. Alleghenies | 9 | Bedford | 116801 | US 30 - Breezewood to Everett | 30 | 045 | Highway Restoration | FD | 581 | 2026-05-21 |  | 1110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110000
S. Alleghenies | 9 | Bedford | 116801 | US 30 - Breezewood to Everett | 30 | 045 | Highway Restoration | UTL | 581 | 2026-05-21 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Bedford | 116801 | US 30 - Breezewood to Everett | 30 | 045 | Highway Restoration | CON | CRP | 2026-05-21 |  | 333070 | 25930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359000
S. Alleghenies | 9 | Bedford | 116801 | US 30 - Breezewood to Everett | 30 | 045 | Highway Restoration | CON | STP | 2026-05-21 |  | 1643842 | 3448822 | 4878006 | 1710000 | 0 | 0 | 0 | 0 | 0 | 11680670
S. Alleghenies | 9 | Bedford | 116801 | US 30 - Breezewood to Everett | 30 | 045 | Highway Restoration | CON | 581 | 2026-05-21 |  | 0 | 1362825 | 1367403 | 273600 | 0 | 0 | 0 | 0 | 0 | 3003828
S. Alleghenies | 9 | Bedford | 116960 | US 30 - SR 4010 to SR 8014 | 30 | 046 | Highway Restoration | ROW | 581 | 2027-04-08 |  | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 56000
S. Alleghenies | 9 | Bedford | 116960 | US 30 - SR 4010 to SR 8014 | 30 | 046 | Highway Restoration | UTL | 581 | 2027-04-08 |  | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 56000
S. Alleghenies | 9 | Bedford | 116960 | US 30 - SR 4010 to SR 8014 | 30 | 046 | Highway Restoration | CON | 581 | 2027-04-08 |  | 0 | 0 | 0 | 3791000 | 3303000 | 573089 | 0 | 0 | 0 | 7667089
S. Alleghenies | 9 | Bedford | 116966 | SR 1027 over Beaver Creek | 1027 | 01B | Bridge Restoration | PE | BOF | 2029-12-06 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
S. Alleghenies | 9 | Bedford | 116966 | SR 1027 over Beaver Creek | 1027 | 01B | Bridge Restoration | FD | BOF | 2029-12-06 |  | 0 | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 225000
S. Alleghenies | 9 | Bedford | 116966 | SR 1027 over Beaver Creek | 1027 | 01B | Bridge Restoration | ROW | 185 | 2029-12-06 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 116966 | SR 1027 over Beaver Creek | 1027 | 01B | Bridge Restoration | UTL | 185 | 2029-12-06 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 116966 | SR 1027 over Beaver Creek | 1027 | 01B | Bridge Restoration | CON | BRIP | 2029-12-06 |  | 0 | 0 | 0 | 0 | 953000 | 400000 | 0 | 0 | 0 | 1353000
S. Alleghenies | 9 | Bedford | 116991 | SR 1005 over Snake Spring Valley Run | 1005 | 08B | Bridge Restoration | PE | 185 | 2029-01-11 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 116991 | SR 1005 over Snake Spring Valley Run | 1005 | 08B | Bridge Restoration | ROW | 185 | 2029-01-11 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 116991 | SR 1005 over Snake Spring Valley Run | 1005 | 08B | Bridge Restoration | UTL | 185 | 2029-01-11 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 116991 | SR 1005 over Snake Spring Valley Run | 1005 | 08B | Bridge Restoration | CON | 185 | 2029-01-11 |  | 0 | 0 | 0 | 0 | 174797 | 325203 | 500000 | 0 | 0 | 1000000
S. Alleghenies | 9 | Bedford | 116993 | SR 2010 over Chapmans Run | 2010 | 02B | Bridge Restoration | PE | 185 | 2028-12-14 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 116993 | SR 2010 over Chapmans Run | 2010 | 02B | Bridge Restoration | ROW | 185 | 2028-12-14 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 116993 | SR 2010 over Chapmans Run | 2010 | 02B | Bridge Restoration | UTL | 185 | 2028-12-14 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 116993 | SR 2010 over Chapmans Run | 2010 | 02B | Bridge Restoration | CON | 185 | 2028-12-14 |  | 0 | 0 | 0 | 0 | 0 | 657000 | 0 | 0 | 0 | 657000
S. Alleghenies | 9 | Bedford | 117023 | SR 4019 Oppenheimer Run Bridge | 4019 | 03B | Bridge Restoration | CON | BOF | 2026-04-23 |  | 0 | 530247 | 371753 | 0 | 0 | 0 | 0 | 0 | 0 | 902000
S. Alleghenies | 9 | Bedford | 117024 | SA Bridge PM Reserve Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 1015000 | 1000000 | 1000000 | 3200000 | 6215000
S. Alleghenies | 9 | Bedford | 117024 | SA Bridge PM Reserve Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 490000 | 1000000 | 2000000 | 3490000
S. Alleghenies | 9 | Bedford | 117084 | T-526 over Yellow Creek | 7209 | 526 | Bridge Restoration | CON | 183 | 2025-12-04 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
S. Alleghenies | 9 | Bedford | 117087 | T-705 Over Three Springs Run 2 | 7221 | 705 | Bridge Replacement | FD | BOF | 2026-09-03 |  | 160000 | 6080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166080
S. Alleghenies | 9 | Bedford | 117087 | T-705 Over Three Springs Run 2 | 7221 | 705 | Bridge Replacement | FD | 183 | 2026-09-03 |  | 30000 | 1140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31140
S. Alleghenies | 9 | Bedford | 117087 | T-705 Over Three Springs Run 2 | 7221 | 705 | Bridge Replacement | FD | LOC | 2026-09-03 |  | 10000 | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10380
S. Alleghenies | 9 | Bedford | 117087 | T-705 Over Three Springs Run 2 | 7221 | 705 | Bridge Replacement | ROW | BOF | 2026-09-03 |  | 40000 | 10160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50160
S. Alleghenies | 9 | Bedford | 117087 | T-705 Over Three Springs Run 2 | 7221 | 705 | Bridge Replacement | ROW | 183 | 2026-09-03 |  | 7500 | 1905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9405
S. Alleghenies | 9 | Bedford | 117087 | T-705 Over Three Springs Run 2 | 7221 | 705 | Bridge Replacement | ROW | LOC | 2026-09-03 |  | 2500 | 635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3135
S. Alleghenies | 9 | Bedford | 117087 | T-705 Over Three Springs Run 2 | 7221 | 705 | Bridge Replacement | UTL | BOF | 2026-09-03 |  | 20000 | 4640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24640
S. Alleghenies | 9 | Bedford | 117087 | T-705 Over Three Springs Run 2 | 7221 | 705 | Bridge Replacement | UTL | 183 | 2026-09-03 |  | 3750 | 870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4620
S. Alleghenies | 9 | Bedford | 117087 | T-705 Over Three Springs Run 2 | 7221 | 705 | Bridge Replacement | UTL | LOC | 2026-09-03 |  | 1250 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1540
S. Alleghenies | 9 | Bedford | 117087 | T-705 Over Three Springs Run 2 | 7221 | 705 | Bridge Replacement | CON | BOF | 2026-09-03 |  | 0 | 350309 | 765691 | 0 | 0 | 0 | 0 | 0 | 0 | 1116000
S. Alleghenies | 9 | Bedford | 117087 | T-705 Over Three Springs Run 2 | 7221 | 705 | Bridge Replacement | CON | 183 | 2026-09-03 |  | 0 | 64020 | 145230 | 0 | 0 | 0 | 0 | 0 | 0 | 209250
S. Alleghenies | 9 | Bedford | 117087 | T-705 Over Three Springs Run 2 | 7221 | 705 | Bridge Replacement | CON | LOC | 2026-09-03 |  | 0 | 21340 | 48410 | 0 | 0 | 0 | 0 | 0 | 0 | 69750
S. Alleghenies | 9 | Bedford | 118412 | 2025 RPM Installation Southern Alleghenies |  |  | Safety Improvement | CON | 581 | 2025-02-13 | 2025-02-13 | 292911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292911
S. Alleghenies | 9 | Bedford | 118421 | 2026 SA Interchange Lighting | 99 | L15 | Congestion Reduction | CON | CRP | 2025-10-09 | 2025-10-09 | 712930 | 330194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1043124
S. Alleghenies | 9 | Bedford | 119331 | Southern Alleghenies CRP Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 0 | 1073000 | 1073000 | 1073000 | 1073000 | 1073000 | 1073000 | 4291000 | 10729000
S. Alleghenies | 9 | Bedford | 120310 | PA 56 - Trib Dunnings Creek to SR 4009 | 56 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Bedford | 120310 | PA 56 - Trib Dunnings Creek to SR 4009 | 56 | 0 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 700000
S. Alleghenies | 9 | Bedford | 120313 | PA 866 - PA 36 to Blair County Line | 866 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 120313 | PA 866 - PA 36 to Blair County Line | 866 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2922000 | 2922000
S. Alleghenies | 9 | Bedford | 120315 | PA 869 - PA 867 to PA 36 | 869 | 011 | Highway Restoration | PE | 581 | 2030-08-22 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 120315 | PA 869 - PA 867 to PA 36 | 869 | 011 | Highway Restoration | CON | 581 | 2030-08-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2180000 | 1730000 | 0 | 3910000
S. Alleghenies | 9 | Bedford | 120318 | SR 4010 - US 30 to US 30 | 4010 | 003 | Highway Restoration | PE | 581 | 2032-05-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 120318 | SR 4010 - US 30 to US 30 | 4010 | 003 | Highway Restoration | CON | 581 | 2032-05-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
S. Alleghenies | 9 | Bedford | 120319 | SR 1007 - SR 8004 to PA 26 | 1007 | 0 | Highway Restoration | PE | 581 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 120319 | SR 1007 - SR 8004 to PA 26 | 1007 | 0 | Highway Restoration | CON | 581 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
S. Alleghenies | 9 | Bedford | 120401 | SR 3013 over Cole Trout Run | 3013 | 01B | Bridge Restoration | PE | 185 | 2030-10-25 |  | 35000 | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
S. Alleghenies | 9 | Bedford | 120401 | SR 3013 over Cole Trout Run | 3013 | 01B | Bridge Restoration | FD | 185 | 2030-10-25 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
S. Alleghenies | 9 | Bedford | 120401 | SR 3013 over Cole Trout Run | 3013 | 01B | Bridge Restoration | ROW | 185 | 2030-10-25 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 120401 | SR 3013 over Cole Trout Run | 3013 | 01B | Bridge Restoration | UTL | 185 | 2030-10-25 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 120401 | SR 3013 over Cole Trout Run | 3013 | 01B | Bridge Restoration | CON | 185 | 2030-10-25 |  | 0 | 0 | 0 | 0 | 0 | 310000 | 590000 | 0 | 0 | 900000
S. Alleghenies | 9 | Bedford | 120455 | SR 1020 over Sherman Valley Run 2 | 1020 | 04B | Bridge Restoration | PE | 185 | 2029-11-01 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 120455 | SR 1020 over Sherman Valley Run 2 | 1020 | 04B | Bridge Restoration | ROW | BRIP | 2029-11-01 |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000
S. Alleghenies | 9 | Bedford | 120455 | SR 1020 over Sherman Valley Run 2 | 1020 | 04B | Bridge Restoration | UTL | BRIP | 2029-11-01 |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000
S. Alleghenies | 9 | Bedford | 120455 | SR 1020 over Sherman Valley Run 2 | 1020 | 04B | Bridge Restoration | CON | BRIP | 2029-11-01 |  | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 750000
S. Alleghenies | 9 | Bedford | 120456 | SR 1036 over Six Mile Run | 1036 | 06B | Bridge Restoration | PE | 185 | 2031-10-23 |  | 0 | 0 | 0 | 100000 | 150000 | 0 | 0 | 0 | 0 | 250000
S. Alleghenies | 9 | Bedford | 120456 | SR 1036 over Six Mile Run | 1036 | 06B | Bridge Restoration | FD | 185 | 2031-10-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 250000
S. Alleghenies | 9 | Bedford | 120456 | SR 1036 over Six Mile Run | 1036 | 06B | Bridge Restoration | ROW | 185 | 2031-10-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 120456 | SR 1036 over Six Mile Run | 1036 | 06B | Bridge Restoration | UTL | 185 | 2031-10-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
S. Alleghenies | 9 | Bedford | 120456 | SR 1036 over Six Mile Run | 1036 | 06B | Bridge Restoration | CON | 185 | 2031-10-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25750 | 724250 | 0 | 750000
S. Alleghenies | 9 | Bedford | 120464 | US 30 over US 220 | 30 | 0 | Bridge Restoration | PE | 185 | 2031-01-09 |  | 0 | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | 500000
S. Alleghenies | 9 | Bedford | 120464 | US 30 over US 220 | 30 | 0 | Bridge Restoration | ROW | 185 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 120464 | US 30 over US 220 | 30 | 0 | Bridge Restoration | UTL | 185 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 120464 | US 30 over US 220 | 30 | 0 | Bridge Restoration | CON | BRIP | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3420000 | 0 | 0 | 3420000
S. Alleghenies | 9 | Bedford | 120469 | SR 1014 over Tributary Dunnings Creek | 1014 | 0 | Bridge Restoration | PE | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
S. Alleghenies | 9 | Bedford | 120469 | SR 1014 over Tributary Dunnings Creek | 1014 | 0 | Bridge Restoration | ROW | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Bedford | 120469 | SR 1014 over Tributary Dunnings Creek | 1014 | 0 | Bridge Restoration | UTL | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Bedford | 120469 | SR 1014 over Tributary Dunnings Creek | 1014 | 0 | Bridge Restoration | CON | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Bedford | 120472 | SR 2015 over Black Valley Run | 2015 | 000 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
S. Alleghenies | 9 | Bedford | 120472 | SR 2015 over Black Valley Run | 2015 | 000 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
S. Alleghenies | 9 | Bedford | 120472 | SR 2015 over Black Valley Run | 2015 | 000 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 120472 | SR 2015 over Black Valley Run | 2015 | 000 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 120472 | SR 2015 over Black Valley Run | 2015 | 000 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Bedford | 120476 | PA 96 over Fleegles Run | 96 | 0 | Bridge Restoration | PE | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
S. Alleghenies | 9 | Bedford | 120476 | PA 96 over Fleegles Run | 96 | 0 | Bridge Restoration | ROW | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 120476 | PA 96 over Fleegles Run | 96 | 0 | Bridge Restoration | UTL | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 120476 | PA 96 over Fleegles Run | 96 | 0 | Bridge Restoration | CON | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 1400000
S. Alleghenies | 9 | Bedford | 120479 | SR 1020 over Sherman Valley Run 1 | 1020 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 210000
S. Alleghenies | 9 | Bedford | 120479 | SR 1020 over Sherman Valley Run 1 | 1020 | 0 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000 | 155000
S. Alleghenies | 9 | Bedford | 120479 | SR 1020 over Sherman Valley Run 1 | 1020 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 120479 | SR 1020 over Sherman Valley Run 1 | 1020 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 120479 | SR 1020 over Sherman Valley Run 1 | 1020 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Bedford | 120480 | SR 2020 over Greys Run | 2020 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
S. Alleghenies | 9 | Bedford | 120480 | SR 2020 over Greys Run | 2020 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 120480 | SR 2020 over Greys Run | 2020 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 120480 | SR 2020 over Greys Run | 2020 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
S. Alleghenies | 9 | Bedford | 120486 | PA 36 over Yellow Creek | 36 | 0 | Bridge Restoration | PE | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315000 | 315000
S. Alleghenies | 9 | Bedford | 120486 | PA 36 over Yellow Creek | 36 | 0 | Bridge Restoration | FD | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000 | 230000
S. Alleghenies | 9 | Bedford | 120486 | PA 36 over Yellow Creek | 36 | 0 | Bridge Restoration | ROW | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 120486 | PA 36 over Yellow Creek | 36 | 0 | Bridge Restoration | UTL | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 120486 | PA 36 over Yellow Creek | 36 | 0 | Bridge Restoration | CON | BRIP | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000
S. Alleghenies | 9 | Bedford | 120488 | SR 1020 over Tributary to Pipers Run | 1020 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000 | 155000
S. Alleghenies | 9 | Bedford | 120488 | SR 1020 over Tributary to Pipers Run | 1020 | 0 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000 | 115000
S. Alleghenies | 9 | Bedford | 120488 | SR 1020 over Tributary to Pipers Run | 1020 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 120488 | SR 1020 over Tributary to Pipers Run | 1020 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Bedford | 120488 | SR 1020 over Tributary to Pipers Run | 1020 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Bedford | 120515 | SR 2016 over Shaffers Creek | 2016 | 0 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
S. Alleghenies | 9 | Bedford | 120515 | SR 2016 over Shaffers Creek | 2016 | 0 | Bridge Restoration | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
S. Alleghenies | 9 | Bedford | 120515 | SR 2016 over Shaffers Creek | 2016 | 0 | Bridge Restoration | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
S. Alleghenies | 9 | Bedford | 120515 | SR 2016 over Shaffers Creek | 2016 | 0 | Bridge Restoration | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
S. Alleghenies | 9 | Bedford | 120515 | SR 2016 over Shaffers Creek | 2016 | 0 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000
S. Alleghenies | 9 | Bedford | 120625 | SR 4009 - Concrete to Concrete | 4009 | 022 | Highway Restoration | PE | 581 | 2029-02-22 |  | 1460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1460000
S. Alleghenies | 9 | Bedford | 120625 | SR 4009 - Concrete to Concrete | 4009 | 022 | Highway Restoration | FD | 581 | 2029-02-22 |  | 0 | 0 | 880000 | 0 | 0 | 0 | 0 | 0 | 0 | 880000
S. Alleghenies | 9 | Bedford | 120625 | SR 4009 - Concrete to Concrete | 4009 | 022 | Highway Restoration | CON | STP | 2029-02-22 |  | 0 | 0 | 0 | 3028000 | 3640000 | 2407088 | 930000 | 0 | 0 | 10005088
S. Alleghenies | 9 | Bedford | 120825 | 2026 RPM Installation Southern Alleghenies |  |  | Safety Improvement | CON | 581 | 2026-03-12 | 2026-03-12 | 0 | 160050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160050
S. Alleghenies | 9 | Bedford | 120854 | Southern Alleghenies Environmental Monitoring |  |  | Planning/Research/Administration | PE | 581 |  |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Bedford | 120856 | 2025 S Alleghenies HFST | 36 | 08S | Safety Improvement | CON | HSIP | 2025-04-17 | 2025-04-17 | 1577927 | 1442878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3020805
S. Alleghenies | 9 | Bedford | 120874 | SR 0867 Seg 0180 D/B Under 8ft Clvt | 867 | 002 | Stormwater Management | ROW | 581 | 2025-08-21 | 2025-08-21 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Bedford | 120874 | SR 0867 Seg 0180 D/B Under 8ft Clvt | 867 | 002 | Stormwater Management | CON | STP | 2025-08-21 | 2025-08-21 | 400827 | 33861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434688
S. Alleghenies | 9 | Bedford | 120876 | SR 4019 Seg 0120 D/B under 8ft Clvt | 4019 | 004 | Stormwater Management | ROW | 581 | 2025-08-21 | 2025-08-21 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Bedford | 120876 | SR 4019 Seg 0120 D/B under 8ft Clvt | 4019 | 004 | Stormwater Management | CON | STP | 2025-08-21 | 2025-08-21 | 163520 | 163076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326596
S. Alleghenies | 9 | Bedford | 121560 | H&BT Trail Final Phase 6 |  | HB6 | Transportation Enhancement | CON | TAP | 2024-12-12 | 2024-12-20 | 504924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504924
S. Alleghenies | 9 | Bedford | 122192 | SR 36- SR 26 to Blair Line | 36 | 009 | 409 Expanded Maintenance | CON | 409 | 2025-04-10 | 2025-04-10 | 3730000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3730000
S. Alleghenies | 9 | Bedford | 123436 | US 30 West of Breezewood Rock Fall | 30 | 053 | General Maintenance | PE | 581 | 2026-05-21 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Bedford | 123436 | US 30 West of Breezewood Rock Fall | 30 | 053 | General Maintenance | CON | PRTCT | 2026-05-21 |  | 0 | 3045000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3045000
S. Alleghenies | 9 | Fulton | 22757 | SR 4001 over Sindeldecker Run | 4001 | 02B | Bridge Restoration | PE | 185 | 2030-10-24 |  | 0 | 0 | 0 | 50000 | 70000 | 0 | 0 | 0 | 0 | 120000
S. Alleghenies | 9 | Fulton | 22757 | SR 4001 over Sindeldecker Run | 4001 | 02B | Bridge Restoration | FD | 185 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 90000
S. Alleghenies | 9 | Fulton | 22757 | SR 4001 over Sindeldecker Run | 4001 | 02B | Bridge Restoration | ROW | 185 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Fulton | 22757 | SR 4001 over Sindeldecker Run | 4001 | 02B | Bridge Restoration | UTL | 185 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Fulton | 22757 | SR 4001 over Sindeldecker Run | 4001 | 02B | Bridge Restoration | CON | BOF | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 550000 | 0 | 1050000
S. Alleghenies | 9 | Fulton | 22767 | T-428 over Wooden Bridge Creek | 7207 | 428 | Bridge Restoration | PE | BOF | 2028-01-13 |  | 211008 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263008
S. Alleghenies | 9 | Fulton | 22767 | T-428 over Wooden Bridge Creek | 7207 | 428 | Bridge Restoration | PE | 183 | 2028-01-13 |  | 39564 | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49314
S. Alleghenies | 9 | Fulton | 22767 | T-428 over Wooden Bridge Creek | 7207 | 428 | Bridge Restoration | PE | LOC | 2028-01-13 |  | 13188 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16438
S. Alleghenies | 9 | Fulton | 22767 | T-428 over Wooden Bridge Creek | 7207 | 428 | Bridge Restoration | FD | BOF | 2028-01-13 |  | 0 | 0 | 85800 | 0 | 0 | 0 | 0 | 0 | 0 | 85800
S. Alleghenies | 9 | Fulton | 22767 | T-428 over Wooden Bridge Creek | 7207 | 428 | Bridge Restoration | FD | 183 | 2028-01-13 |  | 0 | 0 | 16087.5 | 0 | 0 | 0 | 0 | 0 | 0 | 16087.5
S. Alleghenies | 9 | Fulton | 22767 | T-428 over Wooden Bridge Creek | 7207 | 428 | Bridge Restoration | FD | LOC | 2028-01-13 |  | 0 | 0 | 5362.5 | 0 | 0 | 0 | 0 | 0 | 0 | 5362.5
S. Alleghenies | 9 | Fulton | 22767 | T-428 over Wooden Bridge Creek | 7207 | 428 | Bridge Restoration | ROW | BOF | 2028-01-13 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Fulton | 22767 | T-428 over Wooden Bridge Creek | 7207 | 428 | Bridge Restoration | ROW | 183 | 2028-01-13 |  | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750
S. Alleghenies | 9 | Fulton | 22767 | T-428 over Wooden Bridge Creek | 7207 | 428 | Bridge Restoration | UTL | BOF | 2028-01-13 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Fulton | 22767 | T-428 over Wooden Bridge Creek | 7207 | 428 | Bridge Restoration | UTL | 183 | 2028-01-13 |  | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750
S. Alleghenies | 9 | Fulton | 22767 | T-428 over Wooden Bridge Creek | 7207 | 428 | Bridge Restoration | CON | BOF | 2028-01-13 |  | 0 | 0 | 0 | 320000 | 252000 | 0 | 0 | 0 | 0 | 572000
S. Alleghenies | 9 | Fulton | 22767 | T-428 over Wooden Bridge Creek | 7207 | 428 | Bridge Restoration | CON | 183 | 2028-01-13 |  | 0 | 0 | 0 | 80000 | 27250 | 0 | 0 | 0 | 0 | 107250
S. Alleghenies | 9 | Fulton | 22767 | T-428 over Wooden Bridge Creek | 7207 | 428 | Bridge Restoration | CON | LOC | 2028-01-13 |  | 0 | 0 | 0 | 20000 | 15750 | 0 | 0 | 0 | 0 | 35750
S. Alleghenies | 9 | Fulton | 22786 | SR 655 over Owl Run | 655 | 09B | Bridge Restoration | PE | 185 | 2030-01-17 |  | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Fulton | 22786 | SR 655 over Owl Run | 655 | 09B | Bridge Restoration | ROW | 185 | 2030-01-17 |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000
S. Alleghenies | 9 | Fulton | 22786 | SR 655 over Owl Run | 655 | 09B | Bridge Restoration | UTL | 185 | 2030-01-17 |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000
S. Alleghenies | 9 | Fulton | 22786 | SR 655 over Owl Run | 655 | 09B | Bridge Restoration | CON | BRIP | 2030-01-17 |  | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 0 | 700000
S. Alleghenies | 9 | Fulton | 22788 | SR 731 over I-70 | 731 | 0 | Bridge Restoration | PE | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
S. Alleghenies | 9 | Fulton | 22788 | SR 731 over I-70 | 731 | 0 | Bridge Restoration | ROW | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Fulton | 22788 | SR 731 over I-70 | 731 | 0 | Bridge Restoration | UTL | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Fulton | 22788 | SR 731 over I-70 | 731 | 0 | Bridge Restoration | CON | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1504000 | 1504000
S. Alleghenies | 9 | Fulton | 22790 | Barnett's Run | 3013 | 04B | Bridge Restoration | PE | BRIP | 2028-07-13 |  | 144207.95 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344207.95
S. Alleghenies | 9 | Fulton | 22790 | Barnett's Run | 3013 | 04B | Bridge Restoration | ROW | BRIP | 2028-07-13 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Fulton | 22790 | Barnett's Run | 3013 | 04B | Bridge Restoration | UTL | BRIP | 2028-07-13 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Fulton | 22790 | Barnett's Run | 3013 | 04B | Bridge Restoration | CON | BOF | 2028-07-13 |  | 0 | 0 | 0 | 489563 | 362875 | 0 | 0 | 0 | 0 | 852438
S. Alleghenies | 9 | Fulton | 22802 | Sipes Mill Bridge | 3013 | 03B | Bridge Restoration | ROW | 185 | 2026-09-03 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Fulton | 22802 | Sipes Mill Bridge | 3013 | 03B | Bridge Restoration | UTL | 185 | 2026-09-03 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Fulton | 22802 | Sipes Mill Bridge | 3013 | 03B | Bridge Restoration | CON | BOF | 2026-09-03 |  | 0 | 109927 | 1165073 | 0 | 0 | 0 | 0 | 0 | 0 | 1275000
S. Alleghenies | 9 | Fulton | 22812 | T-313 Sawmill Hollow | 7203 | 313 | Bridge Replacement | FD | BOF | 2026-01-29 | 2026-01-29 | 132000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132000
S. Alleghenies | 9 | Fulton | 22812 | T-313 Sawmill Hollow | 7203 | 313 | Bridge Replacement | FD | 183 | 2026-01-29 | 2026-01-29 | 24750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24750
S. Alleghenies | 9 | Fulton | 22812 | T-313 Sawmill Hollow | 7203 | 313 | Bridge Replacement | FD | LOC | 2026-01-29 | 2026-01-29 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8250
S. Alleghenies | 9 | Fulton | 22812 | T-313 Sawmill Hollow | 7203 | 313 | Bridge Replacement | ROW | BOF | 2026-01-29 | 2026-01-29 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
S. Alleghenies | 9 | Fulton | 22812 | T-313 Sawmill Hollow | 7203 | 313 | Bridge Replacement | ROW | 183 | 2026-01-29 | 2026-01-29 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
S. Alleghenies | 9 | Fulton | 22812 | T-313 Sawmill Hollow | 7203 | 313 | Bridge Replacement | UTL | BOF | 2026-01-29 | 2026-01-29 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
S. Alleghenies | 9 | Fulton | 22812 | T-313 Sawmill Hollow | 7203 | 313 | Bridge Replacement | UTL | 183 | 2026-01-29 | 2026-01-29 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
S. Alleghenies | 9 | Fulton | 22812 | T-313 Sawmill Hollow | 7203 | 313 | Bridge Replacement | CON | BOF | 2026-01-29 | 2026-01-29 | 0 | 911232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911232
S. Alleghenies | 9 | Fulton | 22812 | T-313 Sawmill Hollow | 7203 | 313 | Bridge Replacement | CON | 183 | 2026-01-29 | 2026-01-29 | 0 | 170856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170856
S. Alleghenies | 9 | Fulton | 22812 | T-313 Sawmill Hollow | 7203 | 313 | Bridge Replacement | CON | LOC | 2026-01-29 | 2026-01-29 | 0 | 56952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56952
S. Alleghenies | 9 | Fulton | 22828 | US 522 over Kendall's Run | 522 | 22B | Bridge Restoration | PE | BRIP | 2028-12-07 |  | 250000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
S. Alleghenies | 9 | Fulton | 22828 | US 522 over Kendall's Run | 522 | 22B | Bridge Restoration | FD | BRIP | 2028-12-07 |  | 0 | 0 | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 155000
S. Alleghenies | 9 | Fulton | 22828 | US 522 over Kendall's Run | 522 | 22B | Bridge Restoration | ROW | BRIP | 2028-12-07 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
S. Alleghenies | 9 | Fulton | 22828 | US 522 over Kendall's Run | 522 | 22B | Bridge Restoration | UTL | BRIP | 2028-12-07 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Fulton | 22828 | US 522 over Kendall's Run | 522 | 22B | Bridge Restoration | CON | BRIP | 2028-12-07 |  | 0 | 0 | 0 | 510000 | 250000 | 374000 | 0 | 0 | 0 | 1134000
S. Alleghenies | 9 | Fulton | 22830 | PA 655/Barnett's Run | 655 | 08B | Bridge Restoration | PE | BRIP | 2026-01-29 | 2026-01-29 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Fulton | 22830 | PA 655/Barnett's Run | 655 | 08B | Bridge Restoration | CON | BRIP | 2026-01-29 | 2026-01-29 | 0 | 959100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959100
S. Alleghenies | 9 | Fulton | 22835 | SR 3011 over Barnett's Run | 3011 | 02B | Bridge Restoration | PE | 185 | 2030-01-17 |  | 0 | 0 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 325000
S. Alleghenies | 9 | Fulton | 22835 | SR 3011 over Barnett's Run | 3011 | 02B | Bridge Restoration | FD | 185 | 2030-01-17 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Fulton | 22835 | SR 3011 over Barnett's Run | 3011 | 02B | Bridge Restoration | ROW | 185 | 2030-01-17 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Fulton | 22835 | SR 3011 over Barnett's Run | 3011 | 02B | Bridge Restoration | UTL | 185 | 2030-01-17 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Fulton | 22835 | SR 3011 over Barnett's Run | 3011 | 02B | Bridge Restoration | CON | BRIP | 2030-01-17 |  | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 0 | 700000
S. Alleghenies | 9 | Fulton | 22846 | PA 915 over UNT to Laurel Fork | 915 | 03B | Bridge Replacement | CON | BRIP | 2024-09-12 | 2024-09-12 | 1287249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1287249
S. Alleghenies | 9 | Fulton | 22855 | US 522 over Ten Mile Run | 522 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000 | 270000
S. Alleghenies | 9 | Fulton | 22855 | US 522 over Ten Mile Run | 522 | 0 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
S. Alleghenies | 9 | Fulton | 22855 | US 522 over Ten Mile Run | 522 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Fulton | 22855 | US 522 over Ten Mile Run | 522 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Fulton | 22855 | US 522 over Ten Mile Run | 522 | 0 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
S. Alleghenies | 9 | Fulton | 22858 | PA 655 over Wooden Bridge Creek | 655 | 0 | Bridge Restoration | PE | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 300000
S. Alleghenies | 9 | Fulton | 22858 | PA 655 over Wooden Bridge Creek | 655 | 0 | Bridge Restoration | FD | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215000 | 0 | 215000
S. Alleghenies | 9 | Fulton | 22858 | PA 655 over Wooden Bridge Creek | 655 | 0 | Bridge Restoration | ROW | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Fulton | 22858 | PA 655 over Wooden Bridge Creek | 655 | 0 | Bridge Restoration | UTL | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Fulton | 22858 | PA 655 over Wooden Bridge Creek | 655 | 0 | Bridge Restoration | CON | BRIP | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2296000 | 2296000
S. Alleghenies | 9 | Fulton | 22860 | SR 1005 over Aughwick Creek | 1005 | 02B | Bridge Restoration | PE | 185 | 2030-01-17 |  | 0 | 0 | 435000 | 0 | 0 | 0 | 0 | 0 | 0 | 435000
S. Alleghenies | 9 | Fulton | 22860 | SR 1005 over Aughwick Creek | 1005 | 02B | Bridge Restoration | FD | 185 | 2030-01-17 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Fulton | 22860 | SR 1005 over Aughwick Creek | 1005 | 02B | Bridge Restoration | ROW | 185 | 2030-01-17 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Fulton | 22860 | SR 1005 over Aughwick Creek | 1005 | 02B | Bridge Restoration | UTL | 185 | 2030-01-17 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Fulton | 22860 | SR 1005 over Aughwick Creek | 1005 | 02B | Bridge Restoration | CON | BOF | 2030-01-17 |  | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 0 | 0 | 2500000
S. Alleghenies | 9 | Fulton | 74377 | S Big Cove Tannery Rd over Esther Run | 928 | 04B | Bridge Replacement | CON | BOF | 2025-01-30 | 2025-01-30 | 1285238.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285238.44
S. Alleghenies | 9 | Fulton | 88144 | SR 4007 over Sipes Branch | 4007 | 02B | Bridge Restoration | PE | 185 | 2031-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
S. Alleghenies | 9 | Fulton | 88144 | SR 4007 over Sipes Branch | 4007 | 02B | Bridge Restoration | ROW | 185 | 2031-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Fulton | 88144 | SR 4007 over Sipes Branch | 4007 | 02B | Bridge Restoration | UTL | 185 | 2031-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Fulton | 88144 | SR 4007 over Sipes Branch | 4007 | 02B | Bridge Restoration | CON | 185 | 2031-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
S. Alleghenies | 9 | Fulton | 91650 | Dott to Needmore Resurf | 522 | 014 | Highway Restoration | CON | STP | 2028-10-19 |  | 0 | 0 | 0 | 1273228 | 85000 | 1703324 | 291848 | 0 | 0 | 3353400
S. Alleghenies | 9 | Fulton | 96545 | PA 655 - Barnetts Run to US 522 | 655 | 000 | Highway Restoration | PE | 581 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
S. Alleghenies | 9 | Fulton | 96545 | PA 655 - Barnetts Run to US 522 | 655 | 000 | Highway Restoration | CON | STP | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6844000 | 6844000
S. Alleghenies | 9 | Fulton | 96546 | US 30 - Bedford County to Bark Road | 30 | 013 | Highway Restoration | CON | NHPP | 2027-04-11 |  | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
S. Alleghenies | 9 | Fulton | 96548 | PA 655 - Pitt Street to SR 4008 | 655 | 010 | Highway Restoration | PE | 581 | 2030-11-07 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Fulton | 96548 | PA 655 - Pitt Street to SR 4008 | 655 | 010 | Highway Restoration | CON | STP | 2030-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1225000 | 0 | 2475000
S. Alleghenies | 9 | Fulton | 96550 | Dublin Mills Road-Huntingdon County | 655 | 000 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Fulton | 96550 | Dublin Mills Road-Huntingdon County | 655 | 000 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 0 | 0 | 1400000
S. Alleghenies | 9 | Fulton | 102781 | SR 4015 over Roaring Run | 4015 | 01B | Bridge Restoration | PE | 185 | 2032-01-08 |  | 0 | 0 | 0 | 50000 | 75000 | 0 | 0 | 0 | 0 | 125000
S. Alleghenies | 9 | Fulton | 102781 | SR 4015 over Roaring Run | 4015 | 01B | Bridge Restoration | FD | 185 | 2032-01-08 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Fulton | 102781 | SR 4015 over Roaring Run | 4015 | 01B | Bridge Restoration | ROW | 185 | 2032-01-08 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Fulton | 102781 | SR 4015 over Roaring Run | 4015 | 01B | Bridge Restoration | UTL | 185 | 2032-01-08 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Fulton | 102781 | SR 4015 over Roaring Run | 4015 | 01B | Bridge Restoration | CON | BOF | 2032-01-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 550000 | 0 | 1050000
S. Alleghenies | 9 | Fulton | 106491 | SR 3017 over S Brush Creek | 3017 | 01B | Bridge Restoration | PE | 185 | 2029-02-15 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Fulton | 106491 | SR 3017 over S Brush Creek | 3017 | 01B | Bridge Restoration | ROW | BOF | 2029-02-15 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Fulton | 106491 | SR 3017 over S Brush Creek | 3017 | 01B | Bridge Restoration | UTL | BOF | 2029-02-15 |  | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 80000
S. Alleghenies | 9 | Fulton | 106491 | SR 3017 over S Brush Creek | 3017 | 01B | Bridge Restoration | CON | BOF | 2029-02-15 |  | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 1600000
S. Alleghenies | 9 | Fulton | 108199 | SR 1011 - US 522 to Huntingdon Co Line | 1011 | 000 | Highway Restoration | PE | 581 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
S. Alleghenies | 9 | Fulton | 108199 | SR 1011 - US 522 to Huntingdon Co Line | 1011 | 000 | Highway Restoration | CON | 581 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 3500000
S. Alleghenies | 9 | Fulton | 114119 | US 30 Truck Study Turnaround | 30 | 011 | Safety Improvement | CON | STP | 2025-02-27 | 2025-02-27 | 818822 | 14928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833750
S. Alleghenies | 9 | Fulton | 114179 | T-330 Zachs Ridge Road | 7210 | 330 | Bridge Replacement | FD | BOF | 2026-01-29 | 2026-01-29 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
S. Alleghenies | 9 | Fulton | 114179 | T-330 Zachs Ridge Road | 7210 | 330 | Bridge Replacement | FD | 183 | 2026-01-29 | 2026-01-29 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Fulton | 114179 | T-330 Zachs Ridge Road | 7210 | 330 | Bridge Replacement | ROW | BOF | 2026-01-29 | 2026-01-29 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
S. Alleghenies | 9 | Fulton | 114179 | T-330 Zachs Ridge Road | 7210 | 330 | Bridge Replacement | ROW | 183 | 2026-01-29 | 2026-01-29 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
S. Alleghenies | 9 | Fulton | 114179 | T-330 Zachs Ridge Road | 7210 | 330 | Bridge Replacement | UTL | BOF | 2026-01-29 | 2026-01-29 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
S. Alleghenies | 9 | Fulton | 114179 | T-330 Zachs Ridge Road | 7210 | 330 | Bridge Replacement | UTL | 183 | 2026-01-29 | 2026-01-29 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
S. Alleghenies | 9 | Fulton | 114179 | T-330 Zachs Ridge Road | 7210 | 330 | Bridge Replacement | CON | BOF | 2026-01-29 | 2026-01-29 | 0 | 713996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 713996
S. Alleghenies | 9 | Fulton | 114179 | T-330 Zachs Ridge Road | 7210 | 330 | Bridge Replacement | CON | 183 | 2026-01-29 | 2026-01-29 | 0 | 133876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133876
S. Alleghenies | 9 | Fulton | 114179 | T-330 Zachs Ridge Road | 7210 | 330 | Bridge Replacement | CON | LOC | 2026-01-29 | 2026-01-29 | 0 | 44625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44625
S. Alleghenies | 9 | Fulton | 116985 | PA 484 over Trough Run | 484 | 06B | Bridge Restoration | PE | 185 | 2028-11-09 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Fulton | 116985 | PA 484 over Trough Run | 484 | 06B | Bridge Restoration | ROW | 185 | 2028-11-09 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Fulton | 116985 | PA 484 over Trough Run | 484 | 06B | Bridge Restoration | UTL | 185 | 2028-11-09 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Fulton | 116985 | PA 484 over Trough Run | 484 | 06B | Bridge Restoration | CON | 185 | 2028-11-09 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 400000 | 0 | 0 | 900000
S. Alleghenies | 9 | Fulton | 117004 | SR 1004 Over US 30 | 1004 | 02B | Bridge Restoration | CON | BRIP | 2025-03-13 | 2025-03-13 | 456783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456783
S. Alleghenies | 9 | Fulton | 117352 | SR 1003 Peach Orchard Rd over US 30 | 1003 | 01B | Bridge Restoration | PE | BOF | 2025-03-13 | 2025-03-13 | 25968.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25968.16
S. Alleghenies | 9 | Fulton | 117352 | SR 1003 Peach Orchard Rd over US 30 | 1003 | 01B | Bridge Restoration | PE | 185 | 2025-03-13 | 2025-03-13 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Fulton | 117352 | SR 1003 Peach Orchard Rd over US 30 | 1003 | 01B | Bridge Restoration | CON | BOF | 2025-03-13 | 2025-03-13 | 196720 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571720
S. Alleghenies | 9 | Fulton | 120348 | US 522 - SR 3019 to PA 643 | 522 | 023 | Highway Restoration | PE | 581 | 2031-12-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
S. Alleghenies | 9 | Fulton | 120348 | US 522 - SR 3019 to PA 643 | 522 | 023 | Highway Restoration | CON | 581 | 2031-12-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
S. Alleghenies | 9 | Fulton | 120349 | SR 522 - PA 655 to SR 1001 | 522 | 0 | Highway Restoration | PE | 581 | 2031-01-09 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Fulton | 120349 | SR 522 - PA 655 to SR 1001 | 522 | 0 | Highway Restoration | CON | STP | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1072500 | 2607500 | 2580000 | 6260000
S. Alleghenies | 9 | Fulton | 120460 | Fort Littleton Intersection Improvement | 522 | 03S | Safety Improvement | PE | 581 | 2028-02-03 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
S. Alleghenies | 9 | Fulton | 120460 | Fort Littleton Intersection Improvement | 522 | 03S | Safety Improvement | FD | 581 | 2028-02-03 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
S. Alleghenies | 9 | Fulton | 120460 | Fort Littleton Intersection Improvement | 522 | 03S | Safety Improvement | ROW | 581 | 2028-02-03 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Fulton | 120460 | Fort Littleton Intersection Improvement | 522 | 03S | Safety Improvement | UTL | 581 | 2028-02-03 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
S. Alleghenies | 9 | Fulton | 120460 | Fort Littleton Intersection Improvement | 522 | 03S | Safety Improvement | CON | 581 | 2028-02-03 |  | 0 | 0 | 0 | 1045000 | 1585000 | 870000 | 0 | 0 | 0 | 3500000
S. Alleghenies | 9 | Fulton | 120484 | US 522 over I-70 | 522 | 0 | Bridge Restoration | PE | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
S. Alleghenies | 9 | Fulton | 120484 | US 522 over I-70 | 522 | 0 | Bridge Restoration | ROW | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
S. Alleghenies | 9 | Fulton | 120484 | US 522 over I-70 | 522 | 0 | Bridge Restoration | UTL | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
S. Alleghenies | 9 | Fulton | 120484 | US 522 over I-70 | 522 | 0 | Bridge Restoration | CON | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
S. Alleghenies | 9 | Fulton | 120485 | PA 643 over I-70 | 643 | 0 | Bridge Restoration | PE | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
S. Alleghenies | 9 | Fulton | 120485 | PA 643 over I-70 | 643 | 0 | Bridge Restoration | ROW | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Fulton | 120485 | PA 643 over I-70 | 643 | 0 | Bridge Restoration | UTL | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Fulton | 120485 | PA 643 over I-70 | 643 | 0 | Bridge Restoration | CON | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
S. Alleghenies | 9 | Fulton | 120494 | US 522 over Tributary to Ten Mile Run | 522 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
S. Alleghenies | 9 | Fulton | 120494 | US 522 over Tributary to Ten Mile Run | 522 | 0 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 140000
S. Alleghenies | 9 | Fulton | 120494 | US 522 over Tributary to Ten Mile Run | 522 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Fulton | 120494 | US 522 over Tributary to Ten Mile Run | 522 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Fulton | 120494 | US 522 over Tributary to Ten Mile Run | 522 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Fulton | 120496 | US 522 over Tributary to Big Cove Creek | 522 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 175000
S. Alleghenies | 9 | Fulton | 120496 | US 522 over Tributary to Big Cove Creek | 522 | 0 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | 130000
S. Alleghenies | 9 | Fulton | 120496 | US 522 over Tributary to Big Cove Creek | 522 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Fulton | 120496 | US 522 over Tributary to Big Cove Creek | 522 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Fulton | 120496 | US 522 over Tributary to Big Cove Creek | 522 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Fulton | 120499 | PA 484 over Piney Run | 484 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
S. Alleghenies | 9 | Fulton | 120499 | PA 484 over Piney Run | 484 | 0 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
S. Alleghenies | 9 | Fulton | 120499 | PA 484 over Piney Run | 484 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Fulton | 120499 | PA 484 over Piney Run | 484 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Fulton | 120499 | PA 484 over Piney Run | 484 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Fulton | 120855 | PA 484 over I-70 | 484 | 0 | Bridge Restoration | PE | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
S. Alleghenies | 9 | Fulton | 120855 | PA 484 over I-70 | 484 | 0 | Bridge Restoration | ROW | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
S. Alleghenies | 9 | Fulton | 120855 | PA 484 over I-70 | 484 | 0 | Bridge Restoration | UTL | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
S. Alleghenies | 9 | Fulton | 120855 | PA 484 over I-70 | 484 | 0 | Bridge Restoration | CON | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
S. Alleghenies | 9 | Huntingdon | 21861 | SR 3006 over Great Trough Creek | 3006 | 0 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
S. Alleghenies | 9 | Huntingdon | 21861 | SR 3006 over Great Trough Creek | 3006 | 0 | Bridge Restoration | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
S. Alleghenies | 9 | Huntingdon | 21861 | SR 3006 over Great Trough Creek | 3006 | 0 | Bridge Restoration | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 21861 | SR 3006 over Great Trough Creek | 3006 | 0 | Bridge Restoration | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 21861 | SR 3006 over Great Trough Creek | 3006 | 0 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
S. Alleghenies | 9 | Huntingdon | 22963 | SR 2009 over Tuscarora Creek | 2009 | 03B | Bridge Restoration | PE | BOF | 2028-07-13 |  | 348000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348000
S. Alleghenies | 9 | Huntingdon | 22963 | SR 2009 over Tuscarora Creek | 2009 | 03B | Bridge Restoration | PE | BRIP | 2028-07-13 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 22963 | SR 2009 over Tuscarora Creek | 2009 | 03B | Bridge Restoration | FD | BOF | 2028-07-13 |  | 0 | 0 | 64436 | 160564 | 0 | 0 | 0 | 0 | 0 | 225000
S. Alleghenies | 9 | Huntingdon | 22963 | SR 2009 over Tuscarora Creek | 2009 | 03B | Bridge Restoration | ROW | BOF | 2028-07-13 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 22963 | SR 2009 over Tuscarora Creek | 2009 | 03B | Bridge Restoration | UTL | BOF | 2028-07-13 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 22963 | SR 2009 over Tuscarora Creek | 2009 | 03B | Bridge Restoration | CON | BOF | 2028-07-13 |  | 0 | 0 | 0 | 800000 | 800000 | 0 | 0 | 0 | 0 | 1600000
S. Alleghenies | 9 | Huntingdon | 22989 | SR 305 over Phrantons Run | 305 | 000 | Bridge Restoration | PE | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
S. Alleghenies | 9 | Huntingdon | 22989 | SR 305 over Phrantons Run | 305 | 000 | Bridge Restoration | ROW | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Huntingdon | 22989 | SR 305 over Phrantons Run | 305 | 000 | Bridge Restoration | UTL | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Huntingdon | 22989 | SR 305 over Phrantons Run | 305 | 000 | Bridge Restoration | CON | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
S. Alleghenies | 9 | Huntingdon | 23009 | T-368 Gr Trough Cr 1 | 7225 | 368 | Bridge Restoration | FD | BOF | 2027-12-16 |  | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
S. Alleghenies | 9 | Huntingdon | 23009 | T-368 Gr Trough Cr 1 | 7225 | 368 | Bridge Restoration | FD | 183 | 2027-12-16 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Huntingdon | 23009 | T-368 Gr Trough Cr 1 | 7225 | 368 | Bridge Restoration | FD | LOC | 2027-12-16 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Huntingdon | 23009 | T-368 Gr Trough Cr 1 | 7225 | 368 | Bridge Restoration | ROW | BOF | 2027-12-16 |  | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
S. Alleghenies | 9 | Huntingdon | 23009 | T-368 Gr Trough Cr 1 | 7225 | 368 | Bridge Restoration | ROW | 183 | 2027-12-16 |  | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
S. Alleghenies | 9 | Huntingdon | 23009 | T-368 Gr Trough Cr 1 | 7225 | 368 | Bridge Restoration | ROW | LOC | 2027-12-16 |  | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500
S. Alleghenies | 9 | Huntingdon | 23009 | T-368 Gr Trough Cr 1 | 7225 | 368 | Bridge Restoration | CON | BOF | 2027-12-16 |  | 0 | 634637 | 165363 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
S. Alleghenies | 9 | Huntingdon | 23009 | T-368 Gr Trough Cr 1 | 7225 | 368 | Bridge Restoration | CON | 183 | 2027-12-16 |  | 0 | 118994 | 31006 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
S. Alleghenies | 9 | Huntingdon | 23009 | T-368 Gr Trough Cr 1 | 7225 | 368 | Bridge Restoration | CON | LOC | 2027-12-16 |  | 0 | 39665 | 10335 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Huntingdon | 23031 | SR 350 over Warriors Mark Run | 350 | 0 | Bridge Restoration | PE | 185 | 2031-01-09 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 23031 | SR 350 over Warriors Mark Run | 350 | 0 | Bridge Restoration | ROW | 185 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 23031 | SR 350 over Warriors Mark Run | 350 | 0 | Bridge Restoration | UTL | 185 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 23031 | SR 350 over Warriors Mark Run | 350 | 0 | Bridge Restoration | CON | 185 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 1200000
S. Alleghenies | 9 | Huntingdon | 23054 | SR 2009 over Tuscarora Creek | 2009 |  | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 350000
S. Alleghenies | 9 | Huntingdon | 23054 | SR 2009 over Tuscarora Creek | 2009 |  | Bridge Restoration | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
S. Alleghenies | 9 | Huntingdon | 23054 | SR 2009 over Tuscarora Creek | 2009 |  | Bridge Restoration | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Huntingdon | 23054 | SR 2009 over Tuscarora Creek | 2009 |  | Bridge Restoration | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Huntingdon | 23054 | SR 2009 over Tuscarora Creek | 2009 |  | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
S. Alleghenies | 9 | Huntingdon | 23102 | SR 350 over Warriors Mark Run 2 | 350 | 0 | Bridge Restoration | PE | 185 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 23102 | SR 350 over Warriors Mark Run 2 | 350 | 0 | Bridge Restoration | ROW | 185 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 23102 | SR 350 over Warriors Mark Run 2 | 350 | 0 | Bridge Restoration | UTL | 185 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 23102 | SR 350 over Warriors Mark Run 2 | 350 | 0 | Bridge Restoration | CON | 185 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
S. Alleghenies | 9 | Huntingdon | 23103 | PA 550 over Logan Spring Run | 550 | 0 | Bridge Restoration | PE | BRIP | 2033-01-06 |  | 0 | 0 | 0 | 0 | 285000 | 0 | 0 | 0 | 0 | 285000
S. Alleghenies | 9 | Huntingdon | 23103 | PA 550 over Logan Spring Run | 550 | 0 | Bridge Restoration | FD | BRIP | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 0 | 0 | 210000
S. Alleghenies | 9 | Huntingdon | 23103 | PA 550 over Logan Spring Run | 550 | 0 | Bridge Restoration | ROW | BRIP | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 23103 | PA 550 over Logan Spring Run | 550 | 0 | Bridge Restoration | UTL | BRIP | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 23103 | PA 550 over Logan Spring Run | 550 | 0 | Bridge Restoration | CON | BRIP | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 2000000
S. Alleghenies | 9 | Huntingdon | 23109 | PA 994 over Jordans Creek | 994 | 15B | Bridge Restoration | PE | 185 | 2028-07-13 |  | 0 | 250000 | 289000 | 0 | 0 | 0 | 0 | 0 | 0 | 539000
S. Alleghenies | 9 | Huntingdon | 23109 | PA 994 over Jordans Creek | 994 | 15B | Bridge Restoration | FD | 185 | 2028-07-13 |  | 0 | 0 | 100000 | 50000 | 0 | 0 | 0 | 0 | 0 | 150000
S. Alleghenies | 9 | Huntingdon | 23109 | PA 994 over Jordans Creek | 994 | 15B | Bridge Restoration | ROW | 185 | 2028-07-13 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 23109 | PA 994 over Jordans Creek | 994 | 15B | Bridge Restoration | UTL | 185 | 2028-07-13 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 23109 | PA 994 over Jordans Creek | 994 | 15B | Bridge Restoration | CON | 185 | 2028-07-13 |  | 0 | 0 | 0 | 200000 | 375000 | 800000 | 0 | 0 | 0 | 1375000
S. Alleghenies | 9 | Huntingdon | 23112 | SR 3027 over Little Trough Creek | 3027 | 000 | Bridge Restoration | PE | 185 | 2031-01-09 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 23112 | SR 3027 over Little Trough Creek | 3027 | 000 | Bridge Restoration | ROW | 185 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 23112 | SR 3027 over Little Trough Creek | 3027 | 000 | Bridge Restoration | UTL | 185 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 23112 | SR 3027 over Little Trough Creek | 3027 | 000 | Bridge Restoration | CON | 185 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 364797 | 1000000 | 0 | 1364797
S. Alleghenies | 9 | Huntingdon | 23115 | Tuscarora Creek Br. | 2009 | 04B | Bridge Restoration | PE | 185 | 2029-09-12 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Huntingdon | 23115 | Tuscarora Creek Br. | 2009 | 04B | Bridge Restoration | ROW | BOF | 2029-09-12 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Huntingdon | 23115 | Tuscarora Creek Br. | 2009 | 04B | Bridge Restoration | UTL | BOF | 2029-09-12 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Huntingdon | 23115 | Tuscarora Creek Br. | 2009 | 04B | Bridge Restoration | CON | BOF | 2029-09-12 |  | 0 | 0 | 0 | 0 | 437125 | 1162875 | 0 | 0 | 0 | 1600000
S. Alleghenies | 9 | Huntingdon | 23129 | SR 2009 over Tuscarora Creek Br. 4 | 2009 | 05B | Bridge Restoration | PE | 185 | 2029-09-12 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Huntingdon | 23129 | SR 2009 over Tuscarora Creek Br. 4 | 2009 | 05B | Bridge Restoration | ROW | BOF | 2029-09-12 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Huntingdon | 23129 | SR 2009 over Tuscarora Creek Br. 4 | 2009 | 05B | Bridge Restoration | UTL | BOF | 2029-09-12 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Huntingdon | 23129 | SR 2009 over Tuscarora Creek Br. 4 | 2009 | 05B | Bridge Restoration | CON | BOF | 2029-09-12 |  | 0 | 0 | 0 | 0 | 600000 | 600000 | 0 | 0 | 0 | 1200000
S. Alleghenies | 9 | Huntingdon | 23130 | SR 2009 over Parsons Run | 2009 | 06B | Bridge Restoration | PE | 185 | 2029-09-12 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Huntingdon | 23130 | SR 2009 over Parsons Run | 2009 | 06B | Bridge Restoration | ROW | 185 | 2029-09-12 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Huntingdon | 23130 | SR 2009 over Parsons Run | 2009 | 06B | Bridge Restoration | UTL | 185 | 2029-09-12 |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Huntingdon | 23130 | SR 2009 over Parsons Run | 2009 | 06B | Bridge Restoration | CON | 185 | 2029-09-12 |  | 0 | 0 | 0 | 0 | 0 | 414797 | 385203 | 0 | 0 | 800000
S. Alleghenies | 9 | Huntingdon | 23133 | PA 103/Barnes Run | 103 | 02B | Bridge Restoration | FD | 185 | 2028-12-07 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 23133 | PA 103/Barnes Run | 103 | 02B | Bridge Restoration | ROW | 185 | 2028-12-07 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Huntingdon | 23133 | PA 103/Barnes Run | 103 | 02B | Bridge Restoration | UTL | 185 | 2028-12-07 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 23133 | PA 103/Barnes Run | 103 | 02B | Bridge Restoration | CON | 185 | 2028-12-07 |  | 0 | 0 | 0 | 200000 | 207000 | 793000 | 0 | 0 | 0 | 1200000
S. Alleghenies | 9 | Huntingdon | 49336 | Lick Run Bridge | 2004 | 04B | Bridge Replacement | CON | 185 | 2025-09-25 | 2025-09-25 | 700000 | 222546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 922546
S. Alleghenies | 9 | Huntingdon | 56678 | SR 2019 over West Licking Creek | 2019 | 000 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
S. Alleghenies | 9 | Huntingdon | 56678 | SR 2019 over West Licking Creek | 2019 | 000 | Bridge Restoration | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 56678 | SR 2019 over West Licking Creek | 2019 | 000 | Bridge Restoration | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 56678 | SR 2019 over West Licking Creek | 2019 | 000 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700000 | 1700000
S. Alleghenies | 9 | Huntingdon | 56686 | TR Sugar Run Bridge | 747 | 06B | Bridge Replacement | ROW | 185 | 2026-08-13 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 56686 | TR Sugar Run Bridge | 747 | 06B | Bridge Replacement | UTL | 185 | 2026-08-13 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 56686 | TR Sugar Run Bridge | 747 | 06B | Bridge Replacement | CON | 185 | 2026-08-13 |  | 0 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000
S. Alleghenies | 9 | Huntingdon | 56687 | PA 994 Trib to Great Trough Creek | 994 | 14B | Bridge Restoration | ROW | 185 | 2025-09-11 | 2025-09-11 | 25000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 56687 | PA 994 Trib to Great Trough Creek | 994 | 14B | Bridge Restoration | UTL | 185 | 2025-09-11 | 2025-09-11 | 25000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
S. Alleghenies | 9 | Huntingdon | 56687 | PA 994 Trib to Great Trough Creek | 994 | 14B | Bridge Restoration | CON | 185 | 2025-09-11 | 2025-09-11 | 497764 | 408601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 906365
S. Alleghenies | 9 | Huntingdon | 56689 | Elliot's Run Bridge #1 | 2005 | 02B | Bridge Restoration | FD | 185 | 2027-11-04 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 56689 | Elliot's Run Bridge #1 | 2005 | 02B | Bridge Restoration | ROW | 185 | 2027-11-04 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Huntingdon | 56689 | Elliot's Run Bridge #1 | 2005 | 02B | Bridge Restoration | UTL | 185 | 2027-11-04 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Huntingdon | 56689 | Elliot's Run Bridge #1 | 2005 | 02B | Bridge Restoration | CON | 185 | 2027-11-04 |  | 0 | 0 | 0 | 100000 | 270000 | 0 | 0 | 0 | 0 | 370000
S. Alleghenies | 9 | Huntingdon | 74436 | Derry Run Bridge Seg 20 | 305 | 12B | Bridge Replacement | CON | 185 | 2025-01-16 | 2025-01-16 | 2408945.55 | 50000.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2458945.95
S. Alleghenies | 9 | Huntingdon | 74468 | SR 3029 over Hares Valley Creek | 3029 | 03B | Bridge Restoration | PE | 185 | 2030-11-07 |  | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 74468 | SR 3029 over Hares Valley Creek | 3029 | 03B | Bridge Restoration | ROW | 185 | 2030-11-07 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 74468 | SR 3029 over Hares Valley Creek | 3029 | 03B | Bridge Restoration | UTL | 185 | 2030-11-07 |  | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Huntingdon | 74468 | SR 3029 over Hares Valley Creek | 3029 | 03B | Bridge Restoration | CON | BRIP | 2030-11-07 |  | 0 | 0 | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 1800000
S. Alleghenies | 9 | Huntingdon | 88145 | PA 35 Trough Spring Bridge | 35 | 04B | Bridge Replacement | FD | 185 | 2026-11-05 |  | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
S. Alleghenies | 9 | Huntingdon | 88145 | PA 35 Trough Spring Bridge | 35 | 04B | Bridge Replacement | ROW | 185 | 2026-11-05 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Huntingdon | 88145 | PA 35 Trough Spring Bridge | 35 | 04B | Bridge Replacement | UTL | 185 | 2026-11-05 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Huntingdon | 88145 | PA 35 Trough Spring Bridge | 35 | 04B | Bridge Replacement | CON | 185 | 2026-11-05 |  | 0 | 0 | 459273 | 1135882 | 0 | 0 | 0 | 0 | 0 | 1595155
S. Alleghenies | 9 | Huntingdon | 88146 | PA 655 over Tributary to Sidling Hill Creek | 655 | 000 | Bridge Restoration | PE | 185 | 2031-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000
S. Alleghenies | 9 | Huntingdon | 88146 | PA 655 over Tributary to Sidling Hill Creek | 655 | 000 | Bridge Restoration | FD | 185 | 2031-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 90000
S. Alleghenies | 9 | Huntingdon | 88146 | PA 655 over Tributary to Sidling Hill Creek | 655 | 000 | Bridge Restoration | ROW | 185 | 2031-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Huntingdon | 88146 | PA 655 over Tributary to Sidling Hill Creek | 655 | 000 | Bridge Restoration | UTL | 185 | 2031-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Huntingdon | 88146 | PA 655 over Tributary to Sidling Hill Creek | 655 | 000 | Bridge Restoration | CON | 185 | 2031-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Huntingdon | 88152 | Elliot's Run Bridge #2 | 2005 | 03B | Bridge Restoration | FD | 185 | 2027-11-04 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 88152 | Elliot's Run Bridge #2 | 2005 | 03B | Bridge Restoration | ROW | 185 | 2027-11-04 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Huntingdon | 88152 | Elliot's Run Bridge #2 | 2005 | 03B | Bridge Restoration | UTL | 185 | 2027-11-04 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Huntingdon | 88152 | Elliot's Run Bridge #2 | 2005 | 03B | Bridge Restoration | CON | 185 | 2027-11-04 |  | 0 | 0 | 0 | 200000 | 445000 | 0 | 0 | 0 | 0 | 645000
S. Alleghenies | 9 | Huntingdon | 91441 | PA 913 Sugar Camp Run | 913 | 08B | Bridge Replacement | ROW | 185 | 2026-08-13 |  | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
S. Alleghenies | 9 | Huntingdon | 91441 | PA 913 Sugar Camp Run | 913 | 08B | Bridge Replacement | UTL | 185 | 2026-08-13 |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
S. Alleghenies | 9 | Huntingdon | 91441 | PA 913 Sugar Camp Run | 913 | 08B | Bridge Replacement | CON | 185 | 2026-08-13 |  | 0 | 310506 | 200000 | 139494 | 0 | 0 | 0 | 0 | 0 | 650000
S. Alleghenies | 9 | Huntingdon | 91663 | Bedford Co. Line-Mtn Rd | 26 | 035 | Highway Restoration | ROW | 581 | 2026-08-27 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Huntingdon | 91663 | Bedford Co. Line-Mtn Rd | 26 | 035 | Highway Restoration | UTL | 581 | 2026-08-27 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Huntingdon | 91663 | Bedford Co. Line-Mtn Rd | 26 | 035 | Highway Restoration | CON | 581 | 2026-08-27 |  | 2505000 | 4683750 | 1740000 | 0 | 0 | 0 | 0 | 0 | 0 | 8928750
S. Alleghenies | 9 | Huntingdon | 92714 | PA45 Spruce Creek Bridge | 45 | 02B | Bridge Restoration | ROW | BRIP | 2029-10-18 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Huntingdon | 92714 | PA45 Spruce Creek Bridge | 45 | 02B | Bridge Restoration | UTL | BRIP | 2029-10-18 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 92714 | PA45 Spruce Creek Bridge | 45 | 02B | Bridge Restoration | CON | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 980000 | 1000000 | 624000 | 0 | 0 | 0 | 2604000
S. Alleghenies | 9 | Huntingdon | 92732 | PA655 Trb Mill Crk Bridge | 655 | 01B | Bridge Restoration | FD | 185 | 2026-01-15 | 2026-01-15 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
S. Alleghenies | 9 | Huntingdon | 92732 | PA655 Trb Mill Crk Bridge | 655 | 01B | Bridge Restoration | ROW | 185 | 2026-01-15 | 2026-01-15 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 92732 | PA655 Trb Mill Crk Bridge | 655 | 01B | Bridge Restoration | UTL | 185 | 2026-01-15 | 2026-01-15 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Huntingdon | 92732 | PA655 Trb Mill Crk Bridge | 655 | 01B | Bridge Restoration | CON | 185 | 2026-01-15 | 2026-01-15 | 0 | 427440 | 1174764 | 0 | 0 | 0 | 0 | 0 | 0 | 1602204
S. Alleghenies | 9 | Huntingdon | 96568 | US 22 to Mtn Road | 26 | 036 | Highway Restoration | PE | 581 | 2029-12-13 |  | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
S. Alleghenies | 9 | Huntingdon | 96568 | US 22 to Mtn Road | 26 | 036 | Highway Restoration | ROW | 581 | 2029-12-13 |  | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 35000
S. Alleghenies | 9 | Huntingdon | 96568 | US 22 to Mtn Road | 26 | 036 | Highway Restoration | UTL | 581 | 2029-12-13 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Huntingdon | 96568 | US 22 to Mtn Road | 26 | 036 | Highway Restoration | CON | 581 | 2029-12-13 |  | 0 | 0 | 0 | 0 | 3257995 | 4966911 | 1510000 | 2405094 | 0 | 12140000
S. Alleghenies | 9 | Huntingdon | 96573 | PA 453 - SR 1017 to Blair Co Line | 453 | 004 | Highway Restoration | FD | 581 | 2027-04-08 |  | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
S. Alleghenies | 9 | Huntingdon | 96573 | PA 453 - SR 1017 to Blair Co Line | 453 | 004 | Highway Restoration | ROW | 581 | 2027-04-08 |  | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000
S. Alleghenies | 9 | Huntingdon | 96573 | PA 453 - SR 1017 to Blair Co Line | 453 | 004 | Highway Restoration | UTL | 581 | 2027-04-08 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Huntingdon | 96573 | PA 453 - SR 1017 to Blair Co Line | 453 | 004 | Highway Restoration | CON | 581 | 2027-04-08 |  | 0 | 0 | 1204000 | 1196000 | 0 | 0 | 0 | 0 | 0 | 2400000
S. Alleghenies | 9 | Huntingdon | 96587 | SR 26 - Turkey Farm Rd | 3011 | 002 | Highway Restoration | PE | 581 | 2027-03-11 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 96587 | SR 26 - Turkey Farm Rd | 3011 | 002 | Highway Restoration | CON | 581 | 2027-03-11 |  | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
S. Alleghenies | 9 | Huntingdon | 105999 | PA 350 over Tributary to Warriors Mark Run | 350 | 01B | Bridge Restoration | PE | BRIP | 2028-10-05 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
S. Alleghenies | 9 | Huntingdon | 105999 | PA 350 over Tributary to Warriors Mark Run | 350 | 01B | Bridge Restoration | ROW | BRIP | 2028-10-05 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 105999 | PA 350 over Tributary to Warriors Mark Run | 350 | 01B | Bridge Restoration | UTL | BRIP | 2028-10-05 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 105999 | PA 350 over Tributary to Warriors Mark Run | 350 | 01B | Bridge Restoration | CON | BRIP | 2028-10-05 |  | 0 | 0 | 0 | 400000 | 700000 | 0 | 0 | 0 | 0 | 1100000
S. Alleghenies | 9 | Huntingdon | 108316 | US 522 - Keystone Rd to Mifflin County Line | 522 | 013 | Highway Restoration | CON | 581 | 2022-12-08 | 2022-12-08 | 75222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75222
S. Alleghenies | 9 | Huntingdon | 109604 | US 522 - Orbisonia to PA 35 | 522 | 015 | Highway Restoration | PE | 581 | 2031-06-05 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 109604 | US 522 - Orbisonia to PA 35 | 522 | 015 | Highway Restoration | CON | NHPP | 2031-06-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600000 | 3000000 | 5600000
S. Alleghenies | 9 | Huntingdon | 110431 | Entriken SR 3005 Coffee Run Bridge | 3005 | 01B | Bridge Restoration | ROW | 185 | 2029-12-06 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Huntingdon | 110431 | Entriken SR 3005 Coffee Run Bridge | 3005 | 01B | Bridge Restoration | UTL | 185 | 2029-12-06 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Huntingdon | 110431 | Entriken SR 3005 Coffee Run Bridge | 3005 | 01B | Bridge Restoration | CON | BRIP | 2029-12-06 |  | 0 | 0 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 390000
S. Alleghenies | 9 | Huntingdon | 111993 | Hawns Bridge Road Culvert | 3051 | 01B | Bridge Restoration | PE | 185 | 2027-12-09 |  | 20000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 111993 | Hawns Bridge Road Culvert | 3051 | 01B | Bridge Restoration | ROW | 185 | 2027-12-09 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Huntingdon | 111993 | Hawns Bridge Road Culvert | 3051 | 01B | Bridge Restoration | UTL | 185 | 2027-12-09 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Huntingdon | 111993 | Hawns Bridge Road Culvert | 3051 | 01B | Bridge Restoration | CON | 185 | 2027-12-09 |  | 0 | 0 | 0 | 410000 | 0 | 0 | 0 | 0 | 0 | 410000
S. Alleghenies | 9 | Huntingdon | 116919 | SR 3035 - PA 26 to PA 26 | 3035 | 002 | Highway Restoration | PE | 581 | 2027-06-10 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 116919 | SR 3035 - PA 26 to PA 26 | 3035 | 002 | Highway Restoration | CON | 581 | 2027-06-10 |  | 0 | 0 | 1171440 | 628560 | 0 | 0 | 0 | 0 | 0 | 1800000
S. Alleghenies | 9 | Huntingdon | 116939 | PA 994 - SR 3031 to SR 3017 | 994 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 116939 | PA 994 - SR 3031 to SR 3017 | 994 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000
S. Alleghenies | 9 | Huntingdon | 116941 | PA 994 - PA 26 to SR 3031 | 994 | 0 | Highway Restoration | PE | 581 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 116941 | PA 994 - PA 26 to SR 3031 | 994 | 0 | Highway Restoration | CON | 581 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500000 | 5500000
S. Alleghenies | 9 | Huntingdon | 116943 | PA 994 - PA 747 to US 522 | 994 | 0 | Highway Restoration | PE | 581 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 116943 | PA 994 - PA 747 to US 522 | 994 | 0 | Highway Restoration | CON | 581 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3900000
S. Alleghenies | 9 | Huntingdon | 116947 | US 522 - Fulton County Line to PA 35 | 522 | 014 | Highway Restoration | PE | 581 | 2032-07-29 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 116947 | US 522 - Fulton County Line to PA 35 | 522 | 014 | Highway Restoration | CON | NHPP | 2032-07-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513000 | 4200000 | 5713000
S. Alleghenies | 9 | Huntingdon | 116952 | PA 641 - US 522 to Franklin County Line | 641 | 004 | Highway Restoration | PE | 581 | 2031-08-07 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 116952 | PA 641 - US 522 to Franklin County Line | 641 | 004 | Highway Restoration | CON | STP | 2031-08-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1057500 | 2981406 | 0 | 4038906
S. Alleghenies | 9 | Huntingdon | 116959 | PA 305 - SR 1029 to PA 26 | 305 | 016 | Highway Restoration | PE | 581 | 2029-05-10 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
S. Alleghenies | 9 | Huntingdon | 116959 | PA 305 - SR 1029 to PA 26 | 305 | 016 | Highway Restoration | CON | 581 | 2029-05-10 |  | 0 | 0 | 0 | 0 | 1280000 | 3520000 | 0 | 0 | 0 | 4800000
S. Alleghenies | 9 | Huntingdon | 117085 | T-316 Appleby Rd Shade Creek Bridge | 7207 | 316 | Bridge Replacement | ROW | BOF | 2024-08-22 | 2024-08-22 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
S. Alleghenies | 9 | Huntingdon | 117085 | T-316 Appleby Rd Shade Creek Bridge | 7207 | 316 | Bridge Replacement | ROW | 183 | 2024-08-22 | 2024-08-22 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
S. Alleghenies | 9 | Huntingdon | 117085 | T-316 Appleby Rd Shade Creek Bridge | 7207 | 316 | Bridge Replacement | ROW | LOC | 2024-08-22 | 2024-08-22 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
S. Alleghenies | 9 | Huntingdon | 117085 | T-316 Appleby Rd Shade Creek Bridge | 7207 | 316 | Bridge Replacement | UTL | BOF | 2024-08-22 | 2024-08-22 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
S. Alleghenies | 9 | Huntingdon | 117085 | T-316 Appleby Rd Shade Creek Bridge | 7207 | 316 | Bridge Replacement | UTL | 183 | 2024-08-22 | 2024-08-22 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
S. Alleghenies | 9 | Huntingdon | 117085 | T-316 Appleby Rd Shade Creek Bridge | 7207 | 316 | Bridge Replacement | UTL | LOC | 2024-08-22 | 2024-08-22 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
S. Alleghenies | 9 | Huntingdon | 117085 | T-316 Appleby Rd Shade Creek Bridge | 7207 | 316 | Bridge Replacement | CON | BOF | 2024-08-22 | 2024-08-22 | 486840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486840
S. Alleghenies | 9 | Huntingdon | 117085 | T-316 Appleby Rd Shade Creek Bridge | 7207 | 316 | Bridge Replacement | CON | 183 | 2024-08-22 | 2024-08-22 | 91283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91283
S. Alleghenies | 9 | Huntingdon | 117085 | T-316 Appleby Rd Shade Creek Bridge | 7207 | 316 | Bridge Replacement | CON | LOC | 2024-08-22 | 2024-08-22 | 30732.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30732.4
S. Alleghenies | 9 | Huntingdon | 120022 | PA 305 - US 22 to SR 4005 | 305 | 006 | Highway Restoration | CON | 581 | 2025-01-16 | 2025-01-16 | 340000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340000
S. Alleghenies | 9 | Huntingdon | 120356 | SR 26 - Boro Line to SR 1009 | 26 | 0 | Highway Restoration | PE | 581 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 120356 | SR 26 - Boro Line to SR 1009 | 26 | 0 | Highway Restoration | CON | 581 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000
S. Alleghenies | 9 | Huntingdon | 120357 | SR 305 - SR 4009 to SR 1029 | 305 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
S. Alleghenies | 9 | Huntingdon | 120357 | SR 305 - SR 4009 to SR 1029 | 305 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000000 | 7000000
S. Alleghenies | 9 | Huntingdon | 120383 | T-354 over Shoups Run | 7203 | 354 | Bridge Replacement | PE | BOF | 2028-10-05 |  | 328000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328000
S. Alleghenies | 9 | Huntingdon | 120383 | T-354 over Shoups Run | 7203 | 354 | Bridge Replacement | PE | 183 | 2028-10-05 |  | 61500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61500
S. Alleghenies | 9 | Huntingdon | 120383 | T-354 over Shoups Run | 7203 | 354 | Bridge Replacement | PE | LOC | 2028-10-05 |  | 20500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20500
S. Alleghenies | 9 | Huntingdon | 120383 | T-354 over Shoups Run | 7203 | 354 | Bridge Replacement | FD | BOF | 2028-10-05 |  | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
S. Alleghenies | 9 | Huntingdon | 120383 | T-354 over Shoups Run | 7203 | 354 | Bridge Replacement | FD | 183 | 2028-10-05 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Huntingdon | 120383 | T-354 over Shoups Run | 7203 | 354 | Bridge Replacement | ROW | BOF | 2028-10-05 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Huntingdon | 120383 | T-354 over Shoups Run | 7203 | 354 | Bridge Replacement | ROW | 183 | 2028-10-05 |  | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750
S. Alleghenies | 9 | Huntingdon | 120383 | T-354 over Shoups Run | 7203 | 354 | Bridge Replacement | UTL | BOF | 2028-10-05 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Huntingdon | 120383 | T-354 over Shoups Run | 7203 | 354 | Bridge Replacement | UTL | 183 | 2028-10-05 |  | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750
S. Alleghenies | 9 | Huntingdon | 120383 | T-354 over Shoups Run | 7203 | 354 | Bridge Replacement | CON | BOF | 2028-10-05 |  | 0 | 0 | 0 | 560000 | 0 | 0 | 0 | 0 | 0 | 560000
S. Alleghenies | 9 | Huntingdon | 120383 | T-354 over Shoups Run | 7203 | 354 | Bridge Replacement | CON | 183 | 2028-10-05 |  | 0 | 0 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 105000
S. Alleghenies | 9 | Huntingdon | 120459 | SR 4019 over Arch Spring Run | 4019 | 03B | Bridge Restoration | PE | 185 | 2032-01-15 |  | 0 | 0 | 0 | 40000 | 200000 | 0 | 0 | 0 | 0 | 240000
S. Alleghenies | 9 | Huntingdon | 120459 | SR 4019 over Arch Spring Run | 4019 | 03B | Bridge Restoration | FD | 185 | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 175000 | 0 | 0 | 0 | 175000
S. Alleghenies | 9 | Huntingdon | 120459 | SR 4019 over Arch Spring Run | 4019 | 03B | Bridge Restoration | ROW | 185 | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 120459 | SR 4019 over Arch Spring Run | 4019 | 03B | Bridge Restoration | UTL | 185 | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Huntingdon | 120459 | SR 4019 over Arch Spring Run | 4019 | 03B | Bridge Restoration | CON | BOF | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 548000 | 0 | 1048000
S. Alleghenies | 9 | Huntingdon | 120477 | Shade Gap Intersection Safety Improvements | 522 | 01S | Safety Improvement | PE | 581 | 2030-01-17 |  | 362000 | 318000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680000
S. Alleghenies | 9 | Huntingdon | 120477 | Shade Gap Intersection Safety Improvements | 522 | 01S | Safety Improvement | FD | HSIP | 2030-01-17 |  | 0 | 0 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
S. Alleghenies | 9 | Huntingdon | 120477 | Shade Gap Intersection Safety Improvements | 522 | 01S | Safety Improvement | ROW | HSIP | 2030-01-17 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
S. Alleghenies | 9 | Huntingdon | 120477 | Shade Gap Intersection Safety Improvements | 522 | 01S | Safety Improvement | UTL | HSIP | 2030-01-17 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
S. Alleghenies | 9 | Huntingdon | 120477 | Shade Gap Intersection Safety Improvements | 522 | 01S | Safety Improvement | CON | HSIP | 2030-01-17 |  | 0 | 0 | 0 | 0 | 0 | 752000 | 1584000 | 1584000 | 1600000 | 5520000
S. Alleghenies | 9 | Huntingdon | 120513 | US 22 over SR 3035 | 22 | 0 | Bridge Restoration | PE | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615000 | 615000
S. Alleghenies | 9 | Huntingdon | 120513 | US 22 over SR 3035 | 22 | 0 | Bridge Restoration | FD | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 160000
S. Alleghenies | 9 | Huntingdon | 120513 | US 22 over SR 3035 | 22 | 0 | Bridge Restoration | ROW | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
S. Alleghenies | 9 | Huntingdon | 120513 | US 22 over SR 3035 | 22 | 0 | Bridge Restoration | UTL | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
S. Alleghenies | 9 | Huntingdon | 120513 | US 22 over SR 3035 | 22 | 0 | Bridge Restoration | CON | BRIP | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7800000 | 7800000
S. Alleghenies | 9 | Huntingdon | 120878 | SR 0305 Seg 0170 D/B Under 8ft Clvt | 305 | 015 | Stormwater Management | ROW | 581 | 2025-08-21 | 2025-08-21 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Huntingdon | 120878 | SR 0305 Seg 0170 D/B Under 8ft Clvt | 305 | 015 | Stormwater Management | CON | STP | 2025-08-21 | 2025-08-21 | 279520 | 52116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 331636
S. Alleghenies | 9 | Huntingdon | 120879 | SR 3001 Seg 0110 D/B Under 8ft Clvt | 3001 | 004 | Stormwater Management | CON | STP | 2025-08-21 | 2025-08-21 | 128800 | 184877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313677
S. Alleghenies | 9 | Huntingdon | 121562 | Reconnecting Neighborhoods Through Active Mobility |  | RNM | Transportation Enhancement | CON | TAP | 2027-09-30 |  | 0 | 0 | 998000 | 0 | 0 | 0 | 0 | 0 | 0 | 998000
S. Alleghenies | 9 | Huntingdon | 121563 | Traffic Calming Stage #1 |  | TC1 | Transportation Enhancement | CON | TAP | 2026-06-18 |  | 0 | 0 | 1022897 | 0 | 0 | 0 | 0 | 0 | 0 | 1022897
S. Alleghenies | 9 | Huntingdon | 122527 | T-518 Harper Hill Rd over Shaver Creek (Br No 17) | 7229 | 000 | Bridge Restoration | CON | LOC |  |  | 840000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840000
S. Alleghenies | 9 | Huntingdon | 123353 | US 522 - Palmer Street to Cromwell Street | 522 | 016 | Highway Restoration | CON | NHPP | 2026-06-04 |  | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
S. Alleghenies | 9 | Huntingdon | 123800 | Shirley Township Paving Project |  |  | MultiModal | CON | 411 |  |  | 0 | 127600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127600
S. Alleghenies | 9 | Somerset | 23402 | PA 56 over Clear Shade Creek | 56 | 000 | Bridge Restoration | PE | 185 | 2031-01-09 |  | 0 | 0 | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 375000
S. Alleghenies | 9 | Somerset | 23402 | PA 56 over Clear Shade Creek | 56 | 000 | Bridge Restoration | ROW | 185 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Somerset | 23402 | PA 56 over Clear Shade Creek | 56 | 000 | Bridge Restoration | UTL | 185 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Somerset | 23402 | PA 56 over Clear Shade Creek | 56 | 000 | Bridge Restoration | CON | BRIP | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2383000 | 650000 | 0 | 3033000
S. Alleghenies | 9 | Somerset | 23405 | SR 3010 over Middle Creek | 3010 | 01B | Bridge Restoration | PE | 185 | 2030-08-08 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 23405 | SR 3010 over Middle Creek | 3010 | 01B | Bridge Restoration | ROW | 185 | 2030-08-08 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 23405 | SR 3010 over Middle Creek | 3010 | 01B | Bridge Restoration | UTL | 185 | 2030-08-08 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 23405 | SR 3010 over Middle Creek | 3010 | 01B | Bridge Restoration | CON | BOF | 2030-08-08 |  | 0 | 0 | 0 | 0 | 451000 | 0 | 0 | 0 | 0 | 451000
S. Alleghenies | 9 | Somerset | 23416 | SR 2022 over Brush Creek | 2022 | 03B | Bridge Restoration | PE | BOF | 2029-01-25 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 23416 | SR 2022 over Brush Creek | 2022 | 03B | Bridge Restoration | ROW | BOF | 2029-01-25 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 23416 | SR 2022 over Brush Creek | 2022 | 03B | Bridge Restoration | UTL | BOF | 2029-01-25 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 23416 | SR 2022 over Brush Creek | 2022 | 03B | Bridge Restoration | CON | BOF | 2029-01-25 |  | 0 | 0 | 0 | 0 | 1100000 | 0 | 0 | 0 | 0 | 1100000
S. Alleghenies | 9 | Somerset | 23453 | SR 985 over South Fork Bens Creek | 985 | 0 | Bridge Restoration | PE | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 310000 | 0 | 0 | 310000
S. Alleghenies | 9 | Somerset | 23453 | SR 985 over South Fork Bens Creek | 985 | 0 | Bridge Restoration | FD | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 230000 | 0 | 0 | 230000
S. Alleghenies | 9 | Somerset | 23453 | SR 985 over South Fork Bens Creek | 985 | 0 | Bridge Restoration | ROW | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 23453 | SR 985 over South Fork Bens Creek | 985 | 0 | Bridge Restoration | UTL | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 23453 | SR 985 over South Fork Bens Creek | 985 | 0 | Bridge Restoration | CON | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 2000000
S. Alleghenies | 9 | Somerset | 23458 | Middle Creek Bridge | 3029 | 04B | Bridge Replacement | FD | 185 | 2025-12-04 | 2025-12-04 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
S. Alleghenies | 9 | Somerset | 23458 | Middle Creek Bridge | 3029 | 04B | Bridge Replacement | ROW | 185 | 2025-12-04 | 2025-12-04 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 23458 | Middle Creek Bridge | 3029 | 04B | Bridge Replacement | UTL | 185 | 2025-12-04 | 2025-12-04 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 23458 | Middle Creek Bridge | 3029 | 04B | Bridge Replacement | CON | BRIP | 2025-12-04 | 2025-12-04 | 0 | 1456000 | 66919 | 0 | 0 | 0 | 0 | 0 | 0 | 1522919
S. Alleghenies | 9 | Somerset | 23460 | T-364 Gardner Bridge | 7209 | 364 | Bridge Replacement | PE | BOF | 2026-01-29 | 2026-01-29 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
S. Alleghenies | 9 | Somerset | 23460 | T-364 Gardner Bridge | 7209 | 364 | Bridge Replacement | PE | 183 | 2026-01-29 | 2026-01-29 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
S. Alleghenies | 9 | Somerset | 23460 | T-364 Gardner Bridge | 7209 | 364 | Bridge Replacement | PE | LOC | 2026-01-29 | 2026-01-29 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
S. Alleghenies | 9 | Somerset | 23460 | T-364 Gardner Bridge | 7209 | 364 | Bridge Replacement | FD | BOF | 2026-01-29 | 2026-01-29 | 168000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168000
S. Alleghenies | 9 | Somerset | 23460 | T-364 Gardner Bridge | 7209 | 364 | Bridge Replacement | FD | 183 | 2026-01-29 | 2026-01-29 | 31500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31500
S. Alleghenies | 9 | Somerset | 23460 | T-364 Gardner Bridge | 7209 | 364 | Bridge Replacement | FD | LOC | 2026-01-29 | 2026-01-29 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500
S. Alleghenies | 9 | Somerset | 23460 | T-364 Gardner Bridge | 7209 | 364 | Bridge Replacement | ROW | BOF | 2026-01-29 | 2026-01-29 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Somerset | 23460 | T-364 Gardner Bridge | 7209 | 364 | Bridge Replacement | ROW | 183 | 2026-01-29 | 2026-01-29 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
S. Alleghenies | 9 | Somerset | 23460 | T-364 Gardner Bridge | 7209 | 364 | Bridge Replacement | UTL | BOF | 2026-01-29 | 2026-01-29 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Somerset | 23460 | T-364 Gardner Bridge | 7209 | 364 | Bridge Replacement | UTL | 183 | 2026-01-29 | 2026-01-29 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
S. Alleghenies | 9 | Somerset | 23460 | T-364 Gardner Bridge | 7209 | 364 | Bridge Replacement | CON | BOF | 2026-01-29 | 2026-01-29 | 838428 | 312357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150785
S. Alleghenies | 9 | Somerset | 23460 | T-364 Gardner Bridge | 7209 | 364 | Bridge Replacement | CON | 183 | 2026-01-29 | 2026-01-29 | 200906 | 14867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215773
S. Alleghenies | 9 | Somerset | 23460 | T-364 Gardner Bridge | 7209 | 364 | Bridge Replacement | CON | LOC | 2026-01-29 | 2026-01-29 | 52402 | 19522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71924
S. Alleghenies | 9 | Somerset | 23462 | PA653 Laurel Hill Crk Brg | 653 | 09B | Bridge Restoration | FD | 185 | 2026-12-10 |  | 0 | 406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406000
S. Alleghenies | 9 | Somerset | 23462 | PA653 Laurel Hill Crk Brg | 653 | 09B | Bridge Restoration | ROW | 185 | 2026-12-10 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 23462 | PA653 Laurel Hill Crk Brg | 653 | 09B | Bridge Restoration | UTL | 185 | 2026-12-10 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 23462 | PA653 Laurel Hill Crk Brg | 653 | 09B | Bridge Restoration | CON | 185 | 2026-12-10 |  | 0 | 0 | 373000 | 862748 | 1950000 | 0 | 0 | 0 | 0 | 3185748
S. Alleghenies | 9 | Somerset | 23478 | US 30 to N Somerset | 219 | 047 | Highway Restoration | CON | SXF | 2024-07-11 | 2024-06-13 | 97644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97644
S. Alleghenies | 9 | Somerset | 23478 | US 30 to N Somerset | 219 | 047 | Highway Restoration | CON | 581 | 2024-07-11 | 2024-06-13 | 480612 | 1265000 | 715000 | 0 | 0 | 0 | 0 | 0 | 0 | 2460612
S. Alleghenies | 9 | Somerset | 23482 | SR 3003 over Laurel Hill Creek | 3003 | 0 | Bridge Restoration | PE | 185 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 237250 | 150000 | 422750 | 0 | 810000
S. Alleghenies | 9 | Somerset | 23482 | SR 3003 over Laurel Hill Creek | 3003 | 0 | Bridge Restoration | FD | 185 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 600000
S. Alleghenies | 9 | Somerset | 23482 | SR 3003 over Laurel Hill Creek | 3003 | 0 | Bridge Restoration | ROW | 185 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 23482 | SR 3003 over Laurel Hill Creek | 3003 | 0 | Bridge Restoration | UTL | 185 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 23482 | SR 3003 over Laurel Hill Creek | 3003 | 0 | Bridge Restoration | CON | BRIP | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3538000 | 2150000 | 5688000
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | PE | BOF | 2026-08-27 |  | 204000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204000
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | PE | 183 | 2026-08-27 |  | 38250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38250
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | PE | LOC | 2026-08-27 |  | 12750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12750
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | FD | BOF | 2026-08-27 |  | 0 | 208000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208000
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | FD | 183 | 2026-08-27 |  | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | FD | LOC | 2026-08-27 |  | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | ROW | BOF | 2026-08-27 |  | 0 | 22400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22400
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | ROW | 183 | 2026-08-27 |  | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | ROW | LOC | 2026-08-27 |  | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | UTL | BOF | 2026-08-27 |  | 0 | 22400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22400
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | UTL | 183 | 2026-08-27 |  | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | UTL | LOC | 2026-08-27 |  | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | CON | BOF | 2026-08-27 |  | 0 | 429363 | 849037 | 0 | 0 | 0 | 0 | 0 | 0 | 1278400
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | CON | 183 | 2026-08-27 |  | 0 | 80506 | 159194 | 0 | 0 | 0 | 0 | 0 | 0 | 239700
S. Alleghenies | 9 | Somerset | 23508 | T-719 Over Brush Creek | 7216 | 719 | Bridge Replacement | CON | LOC | 2026-08-27 |  | 0 | 26835 | 53065 | 0 | 0 | 0 | 0 | 0 | 0 | 79900
S. Alleghenies | 9 | Somerset | 23532 | 24th Street Bridge | 7422 | 24S | Bridge Replacement | CON | BOF | 2024-12-12 | 2024-12-12 | 1091328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1091328
S. Alleghenies | 9 | Somerset | 23532 | 24th Street Bridge | 7422 | 24S | Bridge Replacement | CON | 183 | 2024-12-12 | 2024-12-12 | 204624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204624
S. Alleghenies | 9 | Somerset | 23532 | 24th Street Bridge | 7422 | 24S | Bridge Replacement | CON | LOC | 2024-12-12 | 2024-12-12 | 68208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68208
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | PE | BOF | 2026-08-27 |  | 127200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127200
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | PE | 183 | 2026-08-27 |  | 23850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23850
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | PE | LOC | 2026-08-27 |  | 7950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7950
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | FD | BOF | 2026-08-27 |  | 0 | 123142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123142
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | FD | 183 | 2026-08-27 |  | 0 | 23089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23089
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | FD | LOC | 2026-08-27 |  | 0 | 7696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7696
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | ROW | BOF | 2026-08-27 |  | 0 | 23200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23200
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | ROW | 183 | 2026-08-27 |  | 0 | 4350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4350
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | ROW | LOC | 2026-08-27 |  | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | UTL | BOF | 2026-08-27 |  | 0 | 23200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23200
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | UTL | 183 | 2026-08-27 |  | 0 | 4350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4350
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | UTL | LOC | 2026-08-27 |  | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | CON | BOF | 2026-08-27 |  | 0 | 440000 | 88000 | 0 | 0 | 0 | 0 | 0 | 0 | 528000
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | CON | 183 | 2026-08-27 |  | 0 | 82500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 99000
S. Alleghenies | 9 | Somerset | 23534 | S. 22nd Street Brdg | 7422 | 22S | Bridge Restoration | CON | LOC | 2026-08-27 |  | 0 | 27500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 33000
S. Alleghenies | 9 | Somerset | 23551 | Stony Creek Trib Br | 4041 | 07B | Bridge Replacement | ROW | 185 | 2025-11-06 | 2025-11-06 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
S. Alleghenies | 9 | Somerset | 23551 | Stony Creek Trib Br | 4041 | 07B | Bridge Replacement | UTL | 185 | 2025-11-06 | 2025-11-06 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
S. Alleghenies | 9 | Somerset | 23551 | Stony Creek Trib Br | 4041 | 07B | Bridge Replacement | CON | BRIP | 2025-11-06 | 2025-11-06 | 0 | 1082000 | 68240 | 0 | 0 | 0 | 0 | 0 | 0 | 1150240
S. Alleghenies | 9 | Somerset | 23590 | Breastwork Run Br #1 | 1017 | 01B | Bridge Replacement | CON | BRIP | 2027-08-12 |  | 0 | 0 | 973205 | 1150000 | 0 | 0 | 0 | 0 | 0 | 2123205
S. Alleghenies | 9 | Somerset | 23591 | Breastwork Run Br #2 | 1017 | 02B | Bridge Replacement | CON | BRIP | 2027-08-12 |  | 0 | 0 | 1142766 | 1150000 | 0 | 0 | 0 | 0 | 0 | 2292766
S. Alleghenies | 9 | Somerset | 23595 | SR 2021 over Shaffers Run | 2021 | 03B | Bridge Restoration | PE | 185 | 2031-10-23 |  | 0 | 0 | 0 | 0 | 165000 | 0 | 0 | 0 | 0 | 165000
S. Alleghenies | 9 | Somerset | 23595 | SR 2021 over Shaffers Run | 2021 | 03B | Bridge Restoration | FD | 185 | 2031-10-23 |  | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 120000
S. Alleghenies | 9 | Somerset | 23595 | SR 2021 over Shaffers Run | 2021 | 03B | Bridge Restoration | ROW | 185 | 2031-10-23 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 23595 | SR 2021 over Shaffers Run | 2021 | 03B | Bridge Restoration | UTL | 185 | 2031-10-23 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 23595 | SR 2021 over Shaffers Run | 2021 | 03B | Bridge Restoration | CON | 185 | 2031-10-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 696000 | 250000 | 0 | 946000
S. Alleghenies | 9 | Somerset | 23596 | Blue Lick Ck Trib Br | 2026 | 01B | Bridge Replacement | PE | BOF | 2026-01-08 | 2026-01-08 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
S. Alleghenies | 9 | Somerset | 23596 | Blue Lick Ck Trib Br | 2026 | 01B | Bridge Replacement | ROW | BOF | 2026-01-08 | 2026-01-08 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Somerset | 23596 | Blue Lick Ck Trib Br | 2026 | 01B | Bridge Replacement | UTL | BOF | 2026-01-08 | 2026-01-08 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 23596 | Blue Lick Ck Trib Br | 2026 | 01B | Bridge Replacement | CON | BRIP | 2026-01-08 | 2026-01-08 | 0 | 959200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959200
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | PE | BOF | 2027-07-15 |  | 248226.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248226.4
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | PE | 183 | 2027-07-15 |  | 46542.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46542.45
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | PE | LOC | 2027-07-15 |  | 11927 | 3587.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15514.15
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | FD | BOF | 2027-07-15 |  | 0 | 100000 | 104000 | 0 | 0 | 0 | 0 | 0 | 0 | 204000
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | FD | 183 | 2027-07-15 |  | 0 | 18750 | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 38250
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | FD | LOC | 2027-07-15 |  | 0 | 6250 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 12750
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | ROW | BOF | 2027-07-15 |  | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | ROW | 183 | 2027-07-15 |  | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | ROW | LOC | 2027-07-15 |  | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | UTL | BOF | 2027-07-15 |  | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | UTL | 183 | 2027-07-15 |  | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | UTL | LOC | 2027-07-15 |  | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | CON | BOF | 2027-07-15 |  | 0 | 0 | 1432000 | 28000 | 900000 | 0 | 0 | 0 | 0 | 2360000
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | CON | 183 | 2027-07-15 |  | 0 | 0 | 268500 | 1750 | 168750 | 0 | 0 | 0 | 0 | 439000
S. Alleghenies | 9 | Somerset | 72477 | T-712 Rockingham Bridge | 7220 | 712 | Bridge Replacement | CON | LOC | 2027-07-15 |  | 0 | 0 | 89500 | 5250 | 56250 | 0 | 0 | 0 | 0 | 151000
S. Alleghenies | 9 | Somerset | 74460 | Miller Run BR | 1021 | 01B | Bridge Replacement | FD | 185 | 2026-01-08 | 2026-01-08 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000
S. Alleghenies | 9 | Somerset | 74460 | Miller Run BR | 1021 | 01B | Bridge Replacement | ROW | 185 | 2026-01-08 | 2026-01-08 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
S. Alleghenies | 9 | Somerset | 74460 | Miller Run BR | 1021 | 01B | Bridge Replacement | UTL | 185 | 2026-01-08 | 2026-01-08 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Somerset | 74460 | Miller Run BR | 1021 | 01B | Bridge Replacement | CON | 185 | 2026-01-08 | 2026-01-08 | 0 | 734811 | 173682 | 0 | 0 | 0 | 0 | 0 | 0 | 908493
S. Alleghenies | 9 | Somerset | 74469 | Little Piney Run BR | 2010 | 02B | Bridge Replacement | ROW | 185 | 2026-04-23 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Somerset | 74469 | Little Piney Run BR | 2010 | 02B | Bridge Replacement | UTL | 185 | 2026-04-23 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Somerset | 74469 | Little Piney Run BR | 2010 | 02B | Bridge Replacement | CON | 185 | 2026-04-23 |  | 0 | 250000 | 530000 | 150000 | 0 | 0 | 0 | 0 | 0 | 930000
S. Alleghenies | 9 | Somerset | 74470 | Gladdens Run BR | 2013 | 04B | Bridge Replacement | FD | BOF | 2026-08-13 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
S. Alleghenies | 9 | Somerset | 74470 | Gladdens Run BR | 2013 | 04B | Bridge Replacement | ROW | BOF | 2026-08-13 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Somerset | 74470 | Gladdens Run BR | 2013 | 04B | Bridge Replacement | UTL | BOF | 2026-08-13 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Somerset | 74470 | Gladdens Run BR | 2013 | 04B | Bridge Replacement | CON | BOF | 2026-08-13 |  | 0 | 523000 | 312000 | 400000 | 0 | 0 | 0 | 0 | 0 | 1235000
S. Alleghenies | 9 | Somerset | 74481 | Poorbaugh Run BR | 2020 | 02B | Bridge Replacement | FD | BRIP | 2027-08-12 |  | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275000
S. Alleghenies | 9 | Somerset | 74481 | Poorbaugh Run BR | 2020 | 02B | Bridge Replacement | ROW | STP | 2027-08-12 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 74481 | Poorbaugh Run BR | 2020 | 02B | Bridge Replacement | UTL | STP | 2027-08-12 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 74481 | Poorbaugh Run BR | 2020 | 02B | Bridge Replacement | CON | BRIP | 2027-08-12 |  | 0 | 0 | 515000 | 515000 | 0 | 0 | 0 | 0 | 0 | 1030000
S. Alleghenies | 9 | Somerset | 74487 | Smith Run Br | 3007 | 03B | Bridge Replacement | CON | BRIP | 2025-01-09 | 2025-01-09 | 884152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884152
S. Alleghenies | 9 | Somerset | 74497 | SR 4029 over North Fork Bens Creek | 4029 | 01B | Bridge Restoration | PE | BOF | 2030-01-17 |  | 0 | 0 | 0 | 630000 | 0 | 0 | 0 | 0 | 0 | 630000
S. Alleghenies | 9 | Somerset | 74497 | SR 4029 over North Fork Bens Creek | 4029 | 01B | Bridge Restoration | FD | BRIP | 2030-01-17 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
S. Alleghenies | 9 | Somerset | 74497 | SR 4029 over North Fork Bens Creek | 4029 | 01B | Bridge Restoration | ROW | BRIP | 2030-01-17 |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000
S. Alleghenies | 9 | Somerset | 74497 | SR 4029 over North Fork Bens Creek | 4029 | 01B | Bridge Restoration | UTL | BRIP | 2030-01-17 |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000
S. Alleghenies | 9 | Somerset | 74497 | SR 4029 over North Fork Bens Creek | 4029 | 01B | Bridge Restoration | CON | BOF | 2030-01-17 |  | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 1600000
S. Alleghenies | 9 | Somerset | 88159 | SR2001 Laurel Crk Bridge | 2001 | 01B | Bridge Replacement | FD | 185 | 2025-12-11 | 2025-12-11 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
S. Alleghenies | 9 | Somerset | 88159 | SR2001 Laurel Crk Bridge | 2001 | 01B | Bridge Replacement | ROW | 185 | 2025-12-11 | 2025-12-11 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 88159 | SR2001 Laurel Crk Bridge | 2001 | 01B | Bridge Replacement | UTL | 185 | 2025-12-11 | 2025-12-11 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 88159 | SR2001 Laurel Crk Bridge | 2001 | 01B | Bridge Replacement | CON | 185 | 2025-12-11 | 2025-12-11 | 0 | 1146651 | 353778 | 0 | 0 | 0 | 0 | 0 | 0 | 1500429
S. Alleghenies | 9 | Somerset | 88162 | Hillegas Run Bridge | 2017 | 04B | Bridge Replacement | FD | BRIP | 2027-08-12 |  | 0 | 223000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223000
S. Alleghenies | 9 | Somerset | 88162 | Hillegas Run Bridge | 2017 | 04B | Bridge Replacement | ROW | BRIP | 2027-08-12 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 88162 | Hillegas Run Bridge | 2017 | 04B | Bridge Replacement | UTL | BRIP | 2027-08-12 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 88162 | Hillegas Run Bridge | 2017 | 04B | Bridge Replacement | CON | BRIP | 2027-08-12 |  | 0 | 0 | 500000 | 600000 | 0 | 0 | 0 | 0 | 0 | 1100000
S. Alleghenies | 9 | Somerset | 88166 | SR 4013 over Spruce Run | 4013 | 000 | Bridge Restoration | PE | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 250000
S. Alleghenies | 9 | Somerset | 88166 | SR 4013 over Spruce Run | 4013 | 000 | Bridge Restoration | FD | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 0 | 185000
S. Alleghenies | 9 | Somerset | 88166 | SR 4013 over Spruce Run | 4013 | 000 | Bridge Restoration | ROW | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Somerset | 88166 | SR 4013 over Spruce Run | 4013 | 000 | Bridge Restoration | UTL | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Somerset | 88166 | SR 4013 over Spruce Run | 4013 | 000 | Bridge Restoration | CON | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
S. Alleghenies | 9 | Somerset | 91442 | PA 160 over Branch of Blue Lick Creek | 160 | 30B | Bridge Restoration | PE | 185 | 2028-10-05 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 91442 | PA 160 over Branch of Blue Lick Creek | 160 | 30B | Bridge Restoration | ROW | 185 | 2028-10-05 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 91442 | PA 160 over Branch of Blue Lick Creek | 160 | 30B | Bridge Restoration | UTL | 185 | 2028-10-05 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 91442 | PA 160 over Branch of Blue Lick Creek | 160 | 30B | Bridge Restoration | CON | 185 | 2028-10-05 |  | 0 | 0 | 0 | 0 | 115750 | 200000 | 384250 | 0 | 0 | 700000
S. Alleghenies | 9 | Somerset | 91446 | Humbert Red Run 1 | 3007 | 04B | Bridge Replacement | CON | 185 | 2026-01-29 | 2026-01-29 | 0 | 547300 | 565645 | 0 | 0 | 0 | 0 | 0 | 0 | 1112945
S. Alleghenies | 9 | Somerset | 91448 | Mance Trib Wills Crk | 2017 | 05B | Bridge Replacement | FD | 185 | 2027-08-12 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
S. Alleghenies | 9 | Somerset | 91448 | Mance Trib Wills Crk | 2017 | 05B | Bridge Replacement | ROW | 185 | 2027-08-12 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 91448 | Mance Trib Wills Crk | 2017 | 05B | Bridge Replacement | UTL | 185 | 2027-08-12 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 91448 | Mance Trib Wills Crk | 2017 | 05B | Bridge Replacement | CON | 185 | 2027-08-12 |  | 0 | 0 | 0 | 350000 | 520000 | 0 | 0 | 0 | 0 | 870000
S. Alleghenies | 9 | Somerset | 92720 | PA 31 over West Branch Coxes Creek | 31 | 000 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
S. Alleghenies | 9 | Somerset | 92720 | PA 31 over West Branch Coxes Creek | 31 | 000 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 92720 | PA 31 over West Branch Coxes Creek | 31 | 000 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 92720 | PA 31 over West Branch Coxes Creek | 31 | 000 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Somerset | 93144 | PA 281 - Fayette Co Line to SR 3007 | 281 | 000 | Highway Restoration | PE | 581 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 93144 | PA 281 - Fayette Co Line to SR 3007 | 281 | 000 | Highway Restoration | CON | STP | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10100000 | 10100000
S. Alleghenies | 9 | Somerset | 94341 | SR 4015 over Quemahoning Creek | 4015 | 000 | Bridge Restoration | PE | 185 | 2033-01-06 |  | 0 | 0 | 0 | 100000 | 41250 | 0 | 0 | 0 | 0 | 141250
S. Alleghenies | 9 | Somerset | 94341 | SR 4015 over Quemahoning Creek | 4015 | 000 | Bridge Restoration | FD | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 230000 | 0 | 0 | 0 | 230000
S. Alleghenies | 9 | Somerset | 94341 | SR 4015 over Quemahoning Creek | 4015 | 000 | Bridge Restoration | ROW | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 94341 | SR 4015 over Quemahoning Creek | 4015 | 000 | Bridge Restoration | UTL | 185 | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 94341 | SR 4015 over Quemahoning Creek | 4015 | 000 | Bridge Restoration | CON | BOF | 2033-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 1500000
S. Alleghenies | 9 | Somerset | 96600 | PA 56 - SR 1033 to Bedford Co Line | 56 | 000 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
S. Alleghenies | 9 | Somerset | 96600 | PA 56 - SR 1033 to Bedford Co Line | 56 | 000 | Highway Restoration | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000
S. Alleghenies | 9 | Somerset | 96610 | PA 653 - Fayette Co Line to PA 281 | 653 | 010 | Highway Restoration | PE | 581 | 2031-09-11 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 96610 | PA 653 - Fayette Co Line to PA 281 | 653 | 010 | Highway Restoration | CON | 581 | 2031-09-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 0 | 3500000
S. Alleghenies | 9 | Somerset | 96614 | PA 669 - Md State Line to US 219 | 669 | 000 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
S. Alleghenies | 9 | Somerset | 96614 | PA 669 - Md State Line to US 219 | 669 | 000 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000000 | 7000000
S. Alleghenies | 9 | Somerset | 103035 | CSX Grade Xing Improvemnt |  |  | Rail Highway Grade Crossing | CON | RRX | 2031-12-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 1800000
S. Alleghenies | 9 | Somerset | 105110 | US 219 Salisbury Rockfall | 219 | 035 | Highway Restoration | CON | NHPP | 2022-03-17 | 2022-03-17 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000
S. Alleghenies | 9 | Somerset | 105604 | SR4035 Trib Quemahoning Crk Bridge | 4035 | 02B | Bridge Restoration | PE | 185 | 2028-12-14 |  | 417236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417236
S. Alleghenies | 9 | Somerset | 105604 | SR4035 Trib Quemahoning Crk Bridge | 4035 | 02B | Bridge Restoration | FD | 185 | 2028-12-14 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 105604 | SR4035 Trib Quemahoning Crk Bridge | 4035 | 02B | Bridge Restoration | ROW | 185 | 2028-12-14 |  | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 105604 | SR4035 Trib Quemahoning Crk Bridge | 4035 | 02B | Bridge Restoration | UTL | 185 | 2028-12-14 |  | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 105604 | SR4035 Trib Quemahoning Crk Bridge | 4035 | 02B | Bridge Restoration | CON | 185 | 2028-12-14 |  | 0 | 0 | 0 | 364000 | 550000 | 0 | 0 | 0 | 0 | 914000
S. Alleghenies | 9 | Somerset | 105980 | US 219 - MD line to Meyersdale Bypass | 219 | 041 | Highway Restoration | ROW | 581 | 2026-12-10 |  | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
S. Alleghenies | 9 | Somerset | 105980 | US 219 - MD line to Meyersdale Bypass | 219 | 041 | Highway Restoration | UTL | 581 | 2026-12-10 |  | 61000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61000
S. Alleghenies | 9 | Somerset | 105980 | US 219 - MD line to Meyersdale Bypass | 219 | 041 | Highway Restoration | CON | NHPP | 2026-12-10 |  | 0 | 0 | 1040000 | 2800000 | 1973000 | 1113000 | 0 | 0 | 0 | 6926000
S. Alleghenies | 9 | Somerset | 106261 | Windber Borough 15th St Grade Crossing |  |  | Rail Highway Grade Crossing | CON | RRX | 2028-12-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
S. Alleghenies | 9 | Somerset | 106262 | Somerset Ave Grade Crossing | 1033 | 000 | Rail Highway Grade Crossing | CON | RRX | 2028-12-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
S. Alleghenies | 9 | Somerset | 106263 | Mount Davis Road Grade Crossing | 2004 | 000 | Rail Highway Grade Crossing | CON | RRX | 2031-12-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760000 | 2760000
S. Alleghenies | 9 | Somerset | 110427 | South Berlin PA 160 Buffalo Creek Bridge | 160 | 29B | Bridge Replacement | PE | BRIP | 2027-06-24 |  | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
S. Alleghenies | 9 | Somerset | 110427 | South Berlin PA 160 Buffalo Creek Bridge | 160 | 29B | Bridge Replacement | FD | BRIP | 2027-06-24 |  | 0 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000
S. Alleghenies | 9 | Somerset | 110427 | South Berlin PA 160 Buffalo Creek Bridge | 160 | 29B | Bridge Replacement | ROW | BRIP | 2027-06-24 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 110427 | South Berlin PA 160 Buffalo Creek Bridge | 160 | 29B | Bridge Replacement | UTL | BRIP | 2027-06-24 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 110427 | South Berlin PA 160 Buffalo Creek Bridge | 160 | 29B | Bridge Replacement | CON | BRIP | 2027-06-24 |  | 0 | 0 | 555000 | 425500 | 510000 | 0 | 0 | 0 | 0 | 1490500
S. Alleghenies | 9 | Somerset | 110427 | South Berlin PA 160 Buffalo Creek Bridge | 160 | 29B | Bridge Replacement | CON | STP | 2027-06-24 |  | 0 | 0 | 463845 | 1087360 | 0 | 0 | 0 | 0 | 0 | 1551205
S. Alleghenies | 9 | Somerset | 110428 | PA 601 over Trib to Quemahoning Creek | 601 | 16B | Bridge Restoration | PE | 185 | 2028-12-14 |  | 135000 | 273000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408000
S. Alleghenies | 9 | Somerset | 110428 | PA 601 over Trib to Quemahoning Creek | 601 | 16B | Bridge Restoration | FD | 185 | 2028-12-14 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 110428 | PA 601 over Trib to Quemahoning Creek | 601 | 16B | Bridge Restoration | ROW | 185 | 2028-12-14 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
S. Alleghenies | 9 | Somerset | 110428 | PA 601 over Trib to Quemahoning Creek | 601 | 16B | Bridge Restoration | UTL | 185 | 2028-12-14 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Somerset | 110428 | PA 601 over Trib to Quemahoning Creek | 601 | 16B | Bridge Restoration | CON | 185 | 2028-12-14 |  | 0 | 0 | 0 | 200000 | 500000 | 300000 | 0 | 0 | 0 | 1000000
S. Alleghenies | 9 | Somerset | 110495 | PA 160 - US 30 to State Route 1016 | 160 | 0 | Highway Restoration | PE | 581 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
S. Alleghenies | 9 | Somerset | 110495 | PA 160 - US 30 to State Route 1016 | 160 | 0 | Highway Restoration | CON | STP | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3735000 | 3735000
S. Alleghenies | 9 | Somerset | 113442 | PA 403 - US 219 to PA 985 | 403 | 015 | Highway Reconstruction | CON | PRTCT | 2023-01-12 | 2023-01-12 | 437000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437000
S. Alleghenies | 9 | Somerset | 113442 | PA 403 - US 219 to PA 985 | 403 | 015 | Highway Reconstruction | CON | STP | 2023-01-12 | 2023-01-12 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
S. Alleghenies | 9 | Somerset | 113884 | Meyersdale Bypass to Garrett Curve | 2047 | 009 | Highway Restoration | ROW | 581 | 2026-09-03 |  | 50000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000
S. Alleghenies | 9 | Somerset | 113884 | Meyersdale Bypass to Garrett Curve | 2047 | 009 | Highway Restoration | UTL | 581 | 2026-09-03 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
S. Alleghenies | 9 | Somerset | 113884 | Meyersdale Bypass to Garrett Curve | 2047 | 009 | Highway Restoration | CON | BRIP | 2026-09-03 |  | 0 | 750000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
S. Alleghenies | 9 | Somerset | 113884 | Meyersdale Bypass to Garrett Curve | 2047 | 009 | Highway Restoration | CON | PRTCT | 2026-09-03 |  | 0 | 425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425000
S. Alleghenies | 9 | Somerset | 113884 | Meyersdale Bypass to Garrett Curve | 2047 | 009 | Highway Restoration | CON | STP | 2026-09-03 |  | 0 | 1027644 | 2475149 | 495000 | 0 | 0 | 0 | 0 | 0 | 3997793
S. Alleghenies | 9 | Somerset | 113885 | Garrett Curve to Berlin | 2047 | 010 | Highway Restoration | PE | 581 | 2027-11-04 |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
S. Alleghenies | 9 | Somerset | 113885 | Garrett Curve to Berlin | 2047 | 010 | Highway Restoration | CON | BRIP | 2027-11-04 |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
S. Alleghenies | 9 | Somerset | 113885 | Garrett Curve to Berlin | 2047 | 010 | Highway Restoration | CON | STP | 2027-11-04 |  | 0 | 0 | 0 | 0 | 2300000 | 3000000 | 1756572 | 0 | 0 | 7056572
S. Alleghenies | 9 | Somerset | 115845 | US 219 Meyersdale to Old Salisbury Rd | 219 | 050 | New Alignment | PE | APD | 2030-07-11 |  | 10996797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10996797
S. Alleghenies | 9 | Somerset | 115845 | US 219 Meyersdale to Old Salisbury Rd | 219 | 050 | New Alignment | PE | SXF | 2030-07-11 |  | 2203203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2203203
S. Alleghenies | 9 | Somerset | 115845 | US 219 Meyersdale to Old Salisbury Rd | 219 | 050 | New Alignment | FD | APD | 2030-07-11 |  | 17000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000000
S. Alleghenies | 9 | Somerset | 115845 | US 219 Meyersdale to Old Salisbury Rd | 219 | 050 | New Alignment | ROW | APD | 2030-07-11 |  | 0 | 0 | 25000000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000000
S. Alleghenies | 9 | Somerset | 115845 | US 219 Meyersdale to Old Salisbury Rd | 219 | 050 | New Alignment | UTL | APD | 2030-07-11 |  | 0 | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000000
S. Alleghenies | 9 | Somerset | 115845 | US 219 Meyersdale to Old Salisbury Rd | 219 | 050 | New Alignment | CON | APD | 2030-07-11 |  | 0 | 0 | 0 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 68000000 | 153000000
S. Alleghenies | 9 | Somerset | 116802 | US 219 - Jennerstown to Cambria Co - D/B | 219 | 057 | Highway Restoration | CON | NHPP | 2025-09-11 | 2025-09-11 | 3128632 | 5254360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8382992
S. Alleghenies | 9 | Somerset | 116802 | US 219 - Jennerstown to Cambria Co - D/B | 219 | 057 | Highway Restoration | CON | STP | 2025-09-11 | 2025-09-11 | 8461935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8461935
S. Alleghenies | 9 | Somerset | 116802 | US 219 - Jennerstown to Cambria Co - D/B | 219 | 057 | Highway Restoration | CON | 581 | 2025-09-11 | 2025-09-11 | 3301221 | 910011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4211232
S. Alleghenies | 9 | Somerset | 116929 | PA 31 - PA160 to Bedford County Line | 31 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
S. Alleghenies | 9 | Somerset | 116929 | PA 31 - PA160 to Bedford County Line | 31 | 0 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000
S. Alleghenies | 9 | Somerset | 116930 | US 30 - PA 281 to PA 160 | 30 | 0 | Highway Restoration | PE | 581 | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 116930 | US 30 - PA 281 to PA 160 | 30 | 0 | Highway Restoration | CON | NHPP | 2034-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5253000 | 5253000
S. Alleghenies | 9 | Somerset | 116932 | PA 31 - US 219 Bridge to PA 160 | 31 | 024 | Highway Restoration | PE | 581 | 2030-04-11 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 116932 | PA 31 - US 219 Bridge to PA 160 | 31 | 024 | Highway Restoration | CON | 581 | 2030-04-11 |  | 0 | 0 | 0 | 0 | 0 | 343000 | 4530000 | 0 | 0 | 4873000
S. Alleghenies | 9 | Somerset | 116934 | US 30 - Westmoreland County Line to PA 985 | 30 | 020 | Highway Restoration | PE | 581 | 2030-07-11 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
S. Alleghenies | 9 | Somerset | 116934 | US 30 - Westmoreland County Line to PA 985 | 30 | 020 | Highway Restoration | FD | 581 | 2030-07-11 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 250000
S. Alleghenies | 9 | Somerset | 116934 | US 30 - Westmoreland County Line to PA 985 | 30 | 020 | Highway Restoration | CON | 581 | 2030-07-11 |  | 0 | 0 | 0 | 0 | 0 | 590000 | 3000000 | 0 | 0 | 3590000
S. Alleghenies | 9 | Somerset | 116935 | PA 31 - Westmoreland County Line to SR 3037 | 31 | 023 | Highway Restoration | PE | 581 | 2029-07-12 |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
S. Alleghenies | 9 | Somerset | 116935 | PA 31 - Westmoreland County Line to SR 3037 | 31 | 023 | Highway Restoration | CON | 581 | 2029-07-12 |  | 0 | 0 | 0 | 0 | 250000 | 3000000 | 0 | 0 | 0 | 3250000
S. Alleghenies | 9 | Somerset | 116937 | PA 160 - SR 1016 to SR 1029 | 160 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 116937 | PA 160 - SR 1016 to SR 1029 | 160 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 1195000 | 0 | 2995000
S. Alleghenies | 9 | Somerset | 116940 | PA 601 - US 30 to US 219 | 601 | 015 | Highway Restoration | PE | 581 | 2027-02-25 |  | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000
S. Alleghenies | 9 | Somerset | 116940 | PA 601 - US 30 to US 219 | 601 | 015 | Highway Restoration | FD | 581 | 2027-02-25 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
S. Alleghenies | 9 | Somerset | 116940 | PA 601 - US 30 to US 219 | 601 | 015 | Highway Restoration | CON | 581 | 2027-02-25 |  | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 4000000
S. Alleghenies | 9 | Somerset | 116949 | US 219 - Berlin-Somerset Int to Somerset Tpk Int | 219 | 058 | Highway Restoration | FD | 581 | 2027-12-09 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
S. Alleghenies | 9 | Somerset | 116949 | US 219 - Berlin-Somerset Int to Somerset Tpk Int | 219 | 058 | Highway Restoration | ROW | 581 | 2027-12-09 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 116949 | US 219 - Berlin-Somerset Int to Somerset Tpk Int | 219 | 058 | Highway Restoration | UTL | 581 | 2027-12-09 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 116949 | US 219 - Berlin-Somerset Int to Somerset Tpk Int | 219 | 058 | Highway Restoration | CON | BRIP | 2027-12-09 |  | 0 | 0 | 0 | 500000 | 2200000 | 0 | 0 | 0 | 0 | 2700000
S. Alleghenies | 9 | Somerset | 116949 | US 219 - Berlin-Somerset Int to Somerset Tpk Int | 219 | 058 | Highway Restoration | CON | NHPP | 2027-12-09 |  | 0 | 0 | 0 | 2813000 | 3140000 | 0 | 0 | 0 | 0 | 5953000
S. Alleghenies | 9 | Somerset | 116949 | US 219 - Berlin-Somerset Int to Somerset Tpk Int | 219 | 058 | Highway Restoration | CON | STP | 2027-12-09 |  | 0 | 0 | 0 | 221412 | 1708588 | 0 | 0 | 0 | 0 | 1930000
S. Alleghenies | 9 | Somerset | 116964 | SR 3008 over S Glade Run | 3008 | 02B | Bridge Replacement | FD | BOF | 2028-01-13 |  | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
S. Alleghenies | 9 | Somerset | 116964 | SR 3008 over S Glade Run | 3008 | 02B | Bridge Replacement | ROW | BRIP | 2028-01-13 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 116964 | SR 3008 over S Glade Run | 3008 | 02B | Bridge Replacement | UTL | BRIP | 2028-01-13 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 116964 | SR 3008 over S Glade Run | 3008 | 02B | Bridge Replacement | CON | BRIP | 2028-01-13 |  | 0 | 0 | 0 | 700000 | 550000 | 0 | 0 | 0 | 0 | 1250000
S. Alleghenies | 9 | Somerset | 116999 | SR 1017 Segment 70 Over Breastwork Run | 1017 | 03B | Bridge Restoration | PE | BRIP | 2027-08-12 |  | 0 | 125640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125640
S. Alleghenies | 9 | Somerset | 116999 | SR 1017 Segment 70 Over Breastwork Run | 1017 | 03B | Bridge Restoration | FD | 185 | 2027-08-12 |  | 0 | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000
S. Alleghenies | 9 | Somerset | 116999 | SR 1017 Segment 70 Over Breastwork Run | 1017 | 03B | Bridge Restoration | ROW | 185 | 2027-08-12 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 116999 | SR 1017 Segment 70 Over Breastwork Run | 1017 | 03B | Bridge Restoration | UTL | 185 | 2027-08-12 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Somerset | 116999 | SR 1017 Segment 70 Over Breastwork Run | 1017 | 03B | Bridge Restoration | CON | BRIP | 2027-08-12 |  | 0 | 0 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 850000
S. Alleghenies | 9 | Somerset | 117000 | SR 1017 Segment 80 Over Breastwork Run | 1017 | 04B | Bridge Restoration | PE | BRIP | 2027-08-12 |  | 0 | 12555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12555
S. Alleghenies | 9 | Somerset | 117000 | SR 1017 Segment 80 Over Breastwork Run | 1017 | 04B | Bridge Restoration | FD | 185 | 2027-08-12 |  | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000
S. Alleghenies | 9 | Somerset | 117000 | SR 1017 Segment 80 Over Breastwork Run | 1017 | 04B | Bridge Restoration | ROW | 185 | 2027-08-12 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 117000 | SR 1017 Segment 80 Over Breastwork Run | 1017 | 04B | Bridge Restoration | UTL | 185 | 2027-08-12 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Somerset | 117000 | SR 1017 Segment 80 Over Breastwork Run | 1017 | 04B | Bridge Restoration | CON | BOF | 2027-08-12 |  | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000
S. Alleghenies | 9 | Somerset | 117000 | SR 1017 Segment 80 Over Breastwork Run | 1017 | 04B | Bridge Restoration | CON | BRIP | 2027-08-12 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
S. Alleghenies | 9 | Somerset | 117001 | SR 1017 Segment 50 Over Tributary Breastwork Run | 1017 | 05B | Bridge Restoration | PE | 185 | 2027-08-12 |  | 0 | 82558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82558
S. Alleghenies | 9 | Somerset | 117001 | SR 1017 Segment 50 Over Tributary Breastwork Run | 1017 | 05B | Bridge Restoration | FD | 185 | 2027-08-12 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 117001 | SR 1017 Segment 50 Over Tributary Breastwork Run | 1017 | 05B | Bridge Restoration | ROW | 185 | 2027-08-12 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 117001 | SR 1017 Segment 50 Over Tributary Breastwork Run | 1017 | 05B | Bridge Restoration | UTL | 185 | 2027-08-12 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 117001 | SR 1017 Segment 50 Over Tributary Breastwork Run | 1017 | 05B | Bridge Restoration | CON | 185 | 2027-08-12 |  | 0 | 0 | 0 | 100000 | 380000 | 0 | 0 | 0 | 0 | 480000
S. Alleghenies | 9 | Somerset | 117002 | SR 1017 Over Wills Run | 1017 | 06B | Bridge Replacement | PE | 185 | 2027-08-12 |  | 0 | 91380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91380
S. Alleghenies | 9 | Somerset | 117002 | SR 1017 Over Wills Run | 1017 | 06B | Bridge Replacement | FD | 185 | 2027-08-12 |  | 0 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145000
S. Alleghenies | 9 | Somerset | 117002 | SR 1017 Over Wills Run | 1017 | 06B | Bridge Replacement | ROW | 185 | 2027-08-12 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 117002 | SR 1017 Over Wills Run | 1017 | 06B | Bridge Replacement | UTL | 185 | 2027-08-12 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 117002 | SR 1017 Over Wills Run | 1017 | 06B | Bridge Replacement | CON | 185 | 2027-08-12 |  | 0 | 0 | 675000 | 0 | 0 | 0 | 0 | 0 | 0 | 675000
S. Alleghenies | 9 | Somerset | 117003 | SR 3006 Over South Glade Creek | 3006 | 01B | Bridge Restoration | ROW | 185 | 2027-02-11 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 117003 | SR 3006 Over South Glade Creek | 3006 | 01B | Bridge Restoration | UTL | 185 | 2027-02-11 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 117003 | SR 3006 Over South Glade Creek | 3006 | 01B | Bridge Restoration | CON | BOF | 2027-02-11 |  | 0 | 0 | 0 | 1008000 | 0 | 0 | 0 | 0 | 0 | 1008000
S. Alleghenies | 9 | Somerset | 117015 | PA 601 Barclay Run Bridge | 601 | 15B | Bridge Restoration | ROW | BRIP | 2028-01-13 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 117015 | PA 601 Barclay Run Bridge | 601 | 15B | Bridge Restoration | UTL | BRIP | 2028-01-13 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 117015 | PA 601 Barclay Run Bridge | 601 | 15B | Bridge Restoration | CON | BRIP | 2028-01-13 |  | 0 | 0 | 0 | 242500 | 0 | 0 | 0 | 0 | 0 | 242500
S. Alleghenies | 9 | Somerset | 117769 | 2023 SA Bridge Painting | 219 | 54B | Bridge Restoration | CON | BRIP | 2023-08-10 | 2023-08-10 | 266589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266589
S. Alleghenies | 9 | Somerset | 118338 | Garrett Borough Streetscape Project | 653 | GBS | Bicycle and Pedestrian Facilities Transit | CON | TAP | 2023-11-02 | 2023-12-14 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
S. Alleghenies | 9 | Somerset | 118339 | Rockwood Streetscape Improvements | 653 | RSI | Bicycle Pedestrian Highway | CON | TAP | 2025-08-21 | 2025-08-21 | 1390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1390000
S. Alleghenies | 9 | Somerset | 119696 | September 11th Trail - Garrett to Berlin |  | GTB | Transportation Enhancement | PE | STP |  |  | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
S. Alleghenies | 9 | Somerset | 120360 | PA 31 - Borough Line to US 219 Bridge | 31 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
S. Alleghenies | 9 | Somerset | 120360 | PA 31 - Borough Line to US 219 Bridge | 31 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
S. Alleghenies | 9 | Somerset | 120361 | PA 160 - SR 1029 to Cambria County | 160 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
S. Alleghenies | 9 | Somerset | 120361 | PA 160 - SR 1029 to Cambria County | 160 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000
S. Alleghenies | 9 | Somerset | 120382 | T-706 over Oven Run | 7220 | 706 | Bridge Restoration | PE | BOF | 2027-09-16 |  | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000
S. Alleghenies | 9 | Somerset | 120382 | T-706 over Oven Run | 7220 | 706 | Bridge Restoration | PE | 183 | 2027-09-16 |  | 41250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41250
S. Alleghenies | 9 | Somerset | 120382 | T-706 over Oven Run | 7220 | 706 | Bridge Restoration | PE | LOC | 2027-09-16 |  | 13750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13750
S. Alleghenies | 9 | Somerset | 120382 | T-706 over Oven Run | 7220 | 706 | Bridge Restoration | FD | BOF | 2027-09-16 |  | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
S. Alleghenies | 9 | Somerset | 120382 | T-706 over Oven Run | 7220 | 706 | Bridge Restoration | FD | 183 | 2027-09-16 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
S. Alleghenies | 9 | Somerset | 120382 | T-706 over Oven Run | 7220 | 706 | Bridge Restoration | ROW | BOF | 2027-09-16 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Somerset | 120382 | T-706 over Oven Run | 7220 | 706 | Bridge Restoration | ROW | 183 | 2027-09-16 |  | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
S. Alleghenies | 9 | Somerset | 120382 | T-706 over Oven Run | 7220 | 706 | Bridge Restoration | UTL | BOF | 2027-09-16 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
S. Alleghenies | 9 | Somerset | 120382 | T-706 over Oven Run | 7220 | 706 | Bridge Restoration | UTL | 183 | 2027-09-16 |  | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
S. Alleghenies | 9 | Somerset | 120382 | T-706 over Oven Run | 7220 | 706 | Bridge Restoration | CON | BOF | 2027-09-16 |  | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
S. Alleghenies | 9 | Somerset | 120382 | T-706 over Oven Run | 7220 | 706 | Bridge Restoration | CON | 183 | 2027-09-16 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
S. Alleghenies | 9 | Somerset | 120398 | SR 1003 over Glade Creek | 1003 | 01B | Bridge Restoration | PE | 185 | 2028-12-14 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 120398 | SR 1003 over Glade Creek | 1003 | 01B | Bridge Restoration | ROW | 185 | 2028-12-14 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 120398 | SR 1003 over Glade Creek | 1003 | 01B | Bridge Restoration | UTL | 185 | 2028-12-14 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 120398 | SR 1003 over Glade Creek | 1003 | 01B | Bridge Restoration | CON | 185 | 2028-12-14 |  | 0 | 0 | 0 | 200000 | 950000 | 0 | 0 | 0 | 0 | 1150000
S. Alleghenies | 9 | Somerset | 120458 | SR 1021 over Miller Run | 1021 | 02B | Bridge Restoration | PE | 185 | 2030-01-31 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 120458 | SR 1021 over Miller Run | 1021 | 02B | Bridge Restoration | ROW | 185 | 2030-01-31 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 120458 | SR 1021 over Miller Run | 1021 | 02B | Bridge Restoration | UTL | 185 | 2030-01-31 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 120458 | SR 1021 over Miller Run | 1021 | 02B | Bridge Restoration | CON | 185 | 2030-01-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 600000
S. Alleghenies | 9 | Somerset | 120461 | SR 3014 over Laurel Hill Creek | 3014 | 03B | Bridge Restoration | PE | 185 | 2029-11-08 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 120461 | SR 3014 over Laurel Hill Creek | 3014 | 03B | Bridge Restoration | ROW | 185 | 2029-11-08 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 120461 | SR 3014 over Laurel Hill Creek | 3014 | 03B | Bridge Restoration | UTL | 185 | 2029-11-08 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 120461 | SR 3014 over Laurel Hill Creek | 3014 | 03B | Bridge Restoration | CON | 185 | 2029-11-08 |  | 0 | 0 | 0 | 0 | 0 | 610000 | 0 | 0 | 0 | 610000
S. Alleghenies | 9 | Somerset | 120462 | SR 4004 over Quemahoning Creek | 4004 | 03B | Bridge Restoration | PE | BOF | 2032-01-08 |  | 0 | 0 | 0 | 215000 | 0 | 0 | 0 | 0 | 0 | 215000
S. Alleghenies | 9 | Somerset | 120462 | SR 4004 over Quemahoning Creek | 4004 | 03B | Bridge Restoration | FD | 185 | 2032-01-08 |  | 0 | 0 | 0 | 0 | 0 | 165000 | 0 | 0 | 0 | 165000
S. Alleghenies | 9 | Somerset | 120462 | SR 4004 over Quemahoning Creek | 4004 | 03B | Bridge Restoration | ROW | 185 | 2032-01-08 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 120462 | SR 4004 over Quemahoning Creek | 4004 | 03B | Bridge Restoration | UTL | 185 | 2032-01-08 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 120462 | SR 4004 over Quemahoning Creek | 4004 | 03B | Bridge Restoration | CON | BOF | 2032-01-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1226000 | 274000 | 0 | 1500000
S. Alleghenies | 9 | Somerset | 120463 | SR 4033 over Roaring Run | 4033 | 02B | Bridge Restoration | PE | 185 | 2029-01-18 |  | 0 | 0 | 0 | 590000 | 0 | 0 | 0 | 0 | 0 | 590000
S. Alleghenies | 9 | Somerset | 120463 | SR 4033 over Roaring Run | 4033 | 02B | Bridge Restoration | FD | 185 | 2029-01-18 |  | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0 | 170000
S. Alleghenies | 9 | Somerset | 120463 | SR 4033 over Roaring Run | 4033 | 02B | Bridge Restoration | ROW | 185 | 2029-01-18 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 120463 | SR 4033 over Roaring Run | 4033 | 02B | Bridge Restoration | UTL | 185 | 2029-01-18 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
S. Alleghenies | 9 | Somerset | 120463 | SR 4033 over Roaring Run | 4033 | 02B | Bridge Restoration | CON | BRIP | 2029-01-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000
S. Alleghenies | 9 | Somerset | 120471 | SR 4025 over Two Mile Run | 4025 | 0 | Bridge Restoration | PE | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145000 | 145000
S. Alleghenies | 9 | Somerset | 120471 | SR 4025 over Two Mile Run | 4025 | 0 | Bridge Restoration | FD | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 105000
S. Alleghenies | 9 | Somerset | 120471 | SR 4025 over Two Mile Run | 4025 | 0 | Bridge Restoration | ROW | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 120471 | SR 4025 over Two Mile Run | 4025 | 0 | Bridge Restoration | UTL | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 120471 | SR 4025 over Two Mile Run | 4025 | 0 | Bridge Restoration | CON | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Somerset | 120473 | SR 2004 over Elk Lick Creek | 2004 | 0 | Bridge Restoration | PE | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 105000
S. Alleghenies | 9 | Somerset | 120473 | SR 2004 over Elk Lick Creek | 2004 | 0 | Bridge Restoration | FD | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
S. Alleghenies | 9 | Somerset | 120473 | SR 2004 over Elk Lick Creek | 2004 | 0 | Bridge Restoration | ROW | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 120473 | SR 2004 over Elk Lick Creek | 2004 | 0 | Bridge Restoration | UTL | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 120473 | SR 2004 over Elk Lick Creek | 2004 | 0 | Bridge Restoration | CON | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Somerset | 120475 | SR 4005 over West Branch Coxes Creek | 4005 | 0 | Bridge Restoration | PE | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 70000
S. Alleghenies | 9 | Somerset | 120475 | SR 4005 over West Branch Coxes Creek | 4005 | 0 | Bridge Restoration | FD | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
S. Alleghenies | 9 | Somerset | 120475 | SR 4005 over West Branch Coxes Creek | 4005 | 0 | Bridge Restoration | ROW | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 120475 | SR 4005 over West Branch Coxes Creek | 4005 | 0 | Bridge Restoration | UTL | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 120475 | SR 4005 over West Branch Coxes Creek | 4005 | 0 | Bridge Restoration | CON | 185 | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Somerset | 120478 | SR 3015 over Rice Run | 3015 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
S. Alleghenies | 9 | Somerset | 120478 | SR 3015 over Rice Run | 3015 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 120478 | SR 3015 over Rice Run | 3015 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 120478 | SR 3015 over Rice Run | 3015 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Somerset | 120483 | SR 4021 over Higgins Run | 4021 | 0 | Bridge Restoration | PE | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260000 | 0 | 260000
S. Alleghenies | 9 | Somerset | 120483 | SR 4021 over Higgins Run | 4021 | 0 | Bridge Restoration | FD | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 0 | 190000
S. Alleghenies | 9 | Somerset | 120483 | SR 4021 over Higgins Run | 4021 | 0 | Bridge Restoration | ROW | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Somerset | 120483 | SR 4021 over Higgins Run | 4021 | 0 | Bridge Restoration | UTL | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Somerset | 120483 | SR 4021 over Higgins Run | 4021 | 0 | Bridge Restoration | CON | BOF | 2035-01-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 2200000
S. Alleghenies | 9 | Somerset | 120489 | SR 2021 over Savage Run | 2021 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
S. Alleghenies | 9 | Somerset | 120489 | SR 2021 over Savage Run | 2021 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 120489 | SR 2021 over Savage Run | 2021 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 120489 | SR 2021 over Savage Run | 2021 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Somerset | 120504 | SR 1003 over Wells Creek | 1003 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 175000
S. Alleghenies | 9 | Somerset | 120504 | SR 1003 over Wells Creek | 1003 | 0 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | 130000
S. Alleghenies | 9 | Somerset | 120504 | SR 1003 over Wells Creek | 1003 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 120504 | SR 1003 over Wells Creek | 1003 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 120504 | SR 1003 over Wells Creek | 1003 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
S. Alleghenies | 9 | Somerset | 120519 | SR 2004 over Elk Lick Creek | 2004 | 0 | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
S. Alleghenies | 9 | Somerset | 120519 | SR 2004 over Elk Lick Creek | 2004 | 0 | Bridge Restoration | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119000 | 0 | 119000
S. Alleghenies | 9 | Somerset | 120519 | SR 2004 over Elk Lick Creek | 2004 | 0 | Bridge Restoration | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Somerset | 120519 | SR 2004 over Elk Lick Creek | 2004 | 0 | Bridge Restoration | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
S. Alleghenies | 9 | Somerset | 120519 | SR 2004 over Elk Lick Creek | 2004 | 0 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
S. Alleghenies | 9 | Somerset | 120522 | SR 2004 over Big Spring Run | 2004 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 80000
S. Alleghenies | 9 | Somerset | 120522 | SR 2004 over Big Spring Run | 2004 | 0 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000
S. Alleghenies | 9 | Somerset | 120522 | SR 2004 over Big Spring Run | 2004 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 120522 | SR 2004 over Big Spring Run | 2004 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
S. Alleghenies | 9 | Somerset | 120522 | SR 2004 over Big Spring Run | 2004 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810000 | 810000
S. Alleghenies | 9 | Somerset | 120884 | US 40 Seg 0040 D/B Under 8ft Clvt | 40 | 004 | Stormwater Management | ROW | 581 | 2025-08-21 | 2025-08-21 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Somerset | 120884 | US 40 Seg 0040 D/B Under 8ft Clvt | 40 | 004 | Stormwater Management | CON | STP | 2025-08-21 | 2025-08-21 | 382000 | 293957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675957
S. Alleghenies | 9 | Somerset | 120885 | US 40 Seg 0100 D/B Under 8ft Clvt | 40 | 005 | Stormwater Management | ROW | 581 | 2025-08-21 | 2025-08-21 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Somerset | 120885 | US 40 Seg 0100 D/B Under 8ft Clvt | 40 | 005 | Stormwater Management | CON | STP | 2025-08-21 | 2025-08-21 | 382000 | 166053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548053
S. Alleghenies | 9 | Somerset | 120886 | SR 0985 Seg 0010 D/B Under 8ft Clvt | 985 | 019 | Stormwater Management | ROW | 581 | 2025-08-21 | 2025-08-21 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
S. Alleghenies | 9 | Somerset | 120886 | SR 0985 Seg 0010 D/B Under 8ft Clvt | 985 | 019 | Stormwater Management | CON | STP | 2025-08-21 | 2025-08-21 | 361803 | 438182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799985
S. Alleghenies | 9 | Somerset | 122211 | Somerset County Guiderail | 669 | 000 | 409 Expanded Maintenance | CON | 409 | 2025-06-05 | 2025-06-05 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
S. Alleghenies | 9 | Somerset | 122212 | 2024 County Wide Mill & Fill #1 | 4013 | 005 | 409 Expanded Maintenance | CON | 409 | 2025-01-30 | 2025-01-30 | 4077000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4077000
S. Alleghenies | 9 | Somerset | 122612 | US 219 Boynton Bridge Replacement | 219 | 46E | Bridge Replacement | PE | 185 | 2026-02-26 | 2026-02-26 | 595000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595000
S. Alleghenies | 9 | Somerset | 122612 | US 219 Boynton Bridge Replacement | 219 | 46E | Bridge Replacement | FD | 185 | 2026-02-26 | 2026-02-26 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
S. Alleghenies | 9 | Somerset | 122612 | US 219 Boynton Bridge Replacement | 219 | 46E | Bridge Replacement | UTL | BRIP | 2026-02-26 | 2026-02-26 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 122612 | US 219 Boynton Bridge Replacement | 219 | 46E | Bridge Replacement | CON | BRIP | 2026-02-26 | 2026-02-26 | 0 | 2544640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2544640
S. Alleghenies | 9 | Somerset | 122613 | US 219 Boynton Temporary Bridge | 219 | 47E | Reserve Line Item | ROW | 185 | 2025-05-15 | 2025-05-15 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
S. Alleghenies | 9 | Somerset | 122613 | US 219 Boynton Temporary Bridge | 219 | 47E | Reserve Line Item | CON | 185 | 2025-05-15 | 2025-05-15 | 2220608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2220608
S. Alleghenies | 9 | Somerset | 123167 | US 219 - Meyersdale to Berlin Joints | 219 | 059 | Highway Restoration | CON | NHPP | 2026-04-09 |  | 0 | 1833738 | 1566262 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000
S. Alleghenies | 9 | Somerset | 123389 | PA 601 Corridor Improvements | 601 | 18S | Congestion Reduction | PE | 581 | 2029-05-10 |  | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Scranton/W-B | 4 | Lackawanna | 7764 | West Lackawanna Ave. Bridge over Conrail Railroad | 7302 | WLK | Bridge Replacement | UTL | STU | 2027-01-14 |  | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Scranton/W-B | 4 | Lackawanna | 7764 | West Lackawanna Ave. Bridge over Conrail Railroad | 7302 | WLK | Bridge Replacement | UTL | 183 | 2027-01-14 |  | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
Scranton/W-B | 4 | Lackawanna | 7764 | West Lackawanna Ave. Bridge over Conrail Railroad | 7302 | WLK | Bridge Replacement | UTL | LOC | 2027-01-14 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Scranton/W-B | 4 | Lackawanna | 7764 | West Lackawanna Ave. Bridge over Conrail Railroad | 7302 | WLK | Bridge Replacement | CON | STU | 2027-01-14 |  | 2800000 | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600000
Scranton/W-B | 4 | Lackawanna | 7764 | West Lackawanna Ave. Bridge over Conrail Railroad | 7302 | WLK | Bridge Replacement | CON | 183 | 2027-01-14 |  | 525000 | 525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000
Scranton/W-B | 4 | Lackawanna | 7911 | North Main Avenue Bridge over Leggetts Creek | 7302 | NMA | Bridge Replacement | CON | NHPP | 2024-12-12 | 2024-12-12 | 2751495 | 239177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2990672
Scranton/W-B | 4 | Lackawanna | 7911 | North Main Avenue Bridge over Leggetts Creek | 7302 | NMA | Bridge Replacement | CON | 183 | 2024-12-12 | 2024-12-12 | 65751 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560751
Scranton/W-B | 4 | Lackawanna | 7911 | North Main Avenue Bridge over Leggetts Creek | 7302 | NMA | Bridge Replacement | CON | LOC | 2024-12-12 | 2024-12-12 | 21917 | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186917
Scranton/W-B | 4 | Lackawanna | 8040 | 6th Ave.Bridge,Carbondale | 7301 | BRG | Bridge Replacement | FD | BOF | 2027-01-28 |  | 328000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328000
Scranton/W-B | 4 | Lackawanna | 8040 | 6th Ave.Bridge,Carbondale | 7301 | BRG | Bridge Replacement | FD | 183 | 2027-01-28 |  | 61500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61500
Scranton/W-B | 4 | Lackawanna | 8040 | 6th Ave.Bridge,Carbondale | 7301 | BRG | Bridge Replacement | FD | LOC | 2027-01-28 |  | 20500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20500
Scranton/W-B | 4 | Lackawanna | 8040 | 6th Ave.Bridge,Carbondale | 7301 | BRG | Bridge Replacement | CON | BOF | 2027-01-28 |  | 0 | 520000 | 328000 | 552000 | 0 | 0 | 0 | 0 | 0 | 1400000
Scranton/W-B | 4 | Lackawanna | 8040 | 6th Ave.Bridge,Carbondale | 7301 | BRG | Bridge Replacement | CON | 183 | 2027-01-28 |  | 0 | 97500 | 61500 | 103500 | 0 | 0 | 0 | 0 | 0 | 262500
Scranton/W-B | 4 | Lackawanna | 8040 | 6th Ave.Bridge,Carbondale | 7301 | BRG | Bridge Replacement | CON | LOC | 2027-01-28 |  | 0 | 32500 | 20500 | 34500 | 0 | 0 | 0 | 0 | 0 | 87500
Scranton/W-B | 4 | Lackawanna | 8129 | SR 3013 over Keyser Creek | 3013 | 202 | Bridge Restoration | PE | STP | 2027-10-21 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Lackawanna | 8129 | SR 3013 over Keyser Creek | 3013 | 202 | Bridge Restoration | PE | 185 | 2027-10-21 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Lackawanna | 8129 | SR 3013 over Keyser Creek | 3013 | 202 | Bridge Restoration | FD | STP | 2027-10-21 |  | 0 | 284000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284000
Scranton/W-B | 4 | Lackawanna | 8129 | SR 3013 over Keyser Creek | 3013 | 202 | Bridge Restoration | FD | 185 | 2027-10-21 |  | 0 | 71000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71000
Scranton/W-B | 4 | Lackawanna | 8129 | SR 3013 over Keyser Creek | 3013 | 202 | Bridge Restoration | CON | STP | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Lackawanna | 8129 | SR 3013 over Keyser Creek | 3013 | 202 | Bridge Restoration | CON | 185 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Lackawanna | 8156 | SR 3012 over Keyser Creek | 3012 | D50 | Bridge Replacement | PE | STP | 2027-10-21 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Lackawanna | 8156 | SR 3012 over Keyser Creek | 3012 | D50 | Bridge Replacement | PE | 185 | 2027-10-21 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Lackawanna | 8156 | SR 3012 over Keyser Creek | 3012 | D50 | Bridge Replacement | FD | STU | 2027-10-21 |  | 0 | 336000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336000
Scranton/W-B | 4 | Lackawanna | 8156 | SR 3012 over Keyser Creek | 3012 | D50 | Bridge Replacement | FD | 185 | 2027-10-21 |  | 0 | 84000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84000
Scranton/W-B | 4 | Lackawanna | 8156 | SR 3012 over Keyser Creek | 3012 | D50 | Bridge Replacement | CON | STP | 2027-10-21 |  | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Lackawanna | 8156 | SR 3012 over Keyser Creek | 3012 | D50 | Bridge Replacement | CON | 185 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Lackawanna | 8174 | SR 690 over Van Brunt Creek | 690 | D50 | Bridge Replacement | CON | STU | 2023-12-07 | 2023-12-07 | 530170 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730170
Scranton/W-B | 4 | Lackawanna | 8174 | SR 690 over Van Brunt Creek | 690 | D50 | Bridge Replacement | CON | 185 | 2023-12-07 | 2023-12-07 | 132542 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182542
Scranton/W-B | 4 | Lackawanna | 8182 | SR 3017 over Lackawanna River | 3017 | D50 | Bridge Preservation - State Funded | CON | STP | 2025-12-04 | 2025-12-04 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
Scranton/W-B | 4 | Lackawanna | 8182 | SR 3017 over Lackawanna River | 3017 | D50 | Bridge Preservation - State Funded | CON | 185 | 2025-12-04 | 2025-12-04 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Scranton/W-B | 4 | Lackawanna | 8185 | SR 4032 over Summit Lake Creek | 4032 | 0 | Bridge Restoration | PE | STP | 2032-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Lackawanna | 8185 | SR 4032 over Summit Lake Creek | 4032 | 0 | Bridge Restoration | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Lackawanna | 8185 | SR 4032 over Summit Lake Creek | 4032 | 0 | Bridge Restoration | CON | STP | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Scranton/W-B | 4 | Lackawanna | 8185 | SR 4032 over Summit Lake Creek | 4032 | 0 | Bridge Restoration | CON | 581 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Scranton/W-B | 4 | Lackawanna | 8191 | SR 435 over Lackawanna County Railroad Authority | 435 | 251 | Bridge Replacement | CON | BRIP | 2025-01-16 | 2025-01-16 | 3602000 | 2900000 | 2200000 | 1040980 | 0 | 0 | 0 | 0 | 0 | 9742980
Scranton/W-B | 4 | Lackawanna | 8191 | SR 435 over Lackawanna County Railroad Authority | 435 | 251 | Bridge Replacement | CON | STP | 2025-01-16 | 2025-01-16 | 7794073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7794073
Scranton/W-B | 4 | Lackawanna | 8191 | SR 435 over Lackawanna County Railroad Authority | 435 | 251 | Bridge Replacement | CON | STU | 2025-01-16 | 2025-01-16 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
Scranton/W-B | 4 | Lackawanna | 8191 | SR 435 over Lackawanna County Railroad Authority | 435 | 251 | Bridge Replacement | CON | 581 | 2025-01-16 | 2025-01-16 | 1350500 | 870000 | 800000 | 1551263 | 0 | 0 | 0 | 0 | 0 | 4571763
Scranton/W-B | 4 | Lackawanna | 8230 | SR 3015 over Lackawanna River | 3015 | 270 | Bridge Restoration | FD | STP | 2026-09-17 |  | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475000
Scranton/W-B | 4 | Lackawanna | 8230 | SR 3015 over Lackawanna River | 3015 | 270 | Bridge Restoration | ROW | 185 | 2026-09-17 |  | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
Scranton/W-B | 4 | Lackawanna | 8230 | SR 3015 over Lackawanna River | 3015 | 270 | Bridge Restoration | CON | STP | 2026-09-17 |  | 0 | 0 | 0 | 0 | 1440000 | 0 | 0 | 0 | 0 | 1440000
Scranton/W-B | 4 | Lackawanna | 8230 | SR 3015 over Lackawanna River | 3015 | 270 | Bridge Restoration | CON | STU | 2026-09-17 |  | 0 | 0 | 1200000 | 800000 | 0 | 0 | 0 | 0 | 0 | 2000000
Scranton/W-B | 4 | Lackawanna | 8230 | SR 3015 over Lackawanna River | 3015 | 270 | Bridge Restoration | CON | 185 | 2026-09-17 |  | 0 | 0 | 300000 | 200000 | 360000 | 0 | 0 | 0 | 0 | 860000
Scranton/W-B | 4 | Lackawanna | 8238 | SR 307 over Interstate 380 | 307 | D55 | Bridge Preservation - Federal | CON | STU | 2024-12-12 | 2024-12-12 | 662996 | 2780492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3443488
Scranton/W-B | 4 | Lackawanna | 8238 | SR 307 over Interstate 380 | 307 | D55 | Bridge Preservation - Federal | CON | 185 | 2024-12-12 | 2024-12-12 | 83600 | 700000 | 72272 | 0 | 0 | 0 | 0 | 0 | 0 | 855872
Scranton/W-B | 4 | Lackawanna | 8256 | SR 8001 ramp over Route 11 | 8001 | 250 | Bridge Replacement | PE | NHPP | 2027-12-09 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Lackawanna | 8256 | SR 8001 ramp over Route 11 | 8001 | 250 | Bridge Replacement | PE | 185 | 2027-12-09 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Lackawanna | 8256 | SR 8001 ramp over Route 11 | 8001 | 250 | Bridge Replacement | CON | STP | 2027-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
Scranton/W-B | 4 | Lackawanna | 8256 | SR 8001 ramp over Route 11 | 8001 | 250 | Bridge Replacement | CON | 185 | 2027-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Scranton/W-B | 4 | Lackawanna | 8308 | SR 3006 over Gardner Creek | 3006 | 250 | Bridge Replacement | CON | BOF | 2023-07-27 | 2023-07-27 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Scranton/W-B | 4 | Lackawanna | 8308 | SR 3006 over Gardner Creek | 3006 | 250 | Bridge Replacement | CON | 185 | 2023-07-27 | 2023-07-27 | 6250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6250
Scranton/W-B | 4 | Lackawanna | 8383 | SR 4007 over Ackerly Creek | 4007 | 270 | Bridge Restoration | PE | 581 | 2028-02-17 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Scranton/W-B | 4 | Lackawanna | 8383 | SR 4007 over Ackerly Creek | 4007 | 270 | Bridge Restoration | CON | 581 | 2028-02-17 |  | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000
Scranton/W-B | 4 | Lackawanna | 8384 | SR 3020 over Lackawanna County Rail Authority | 3020 | 250 | Bridge Replacement | FD | STU | 2028-05-11 |  | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Lackawanna | 8384 | SR 3020 over Lackawanna County Rail Authority | 3020 | 250 | Bridge Replacement | FD | 185 | 2028-05-11 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Lackawanna | 8384 | SR 3020 over Lackawanna County Rail Authority | 3020 | 250 | Bridge Replacement | CON | STP | 2028-05-11 |  | 0 | 0 | 0 | 0 | 0 | 6000000 | 2500000 | 3500000 | 0 | 12000000
Scranton/W-B | 4 | Lackawanna | 8384 | SR 3020 over Lackawanna County Rail Authority | 3020 | 250 | Bridge Replacement | CON | 581 | 2028-05-11 |  | 0 | 0 | 0 | 0 | 0 | 1500000 | 625000 | 875000 | 0 | 3000000
Scranton/W-B | 4 | Lackawanna | 67170 | Goers Hill Bridge No. 3 over White Oak Run |  |  | Bridge Replacement | UTL | 183 | 2026-04-23 |  | 0 | 97500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97500
Scranton/W-B | 4 | Lackawanna | 67170 | Goers Hill Bridge No. 3 over White Oak Run |  |  | Bridge Replacement | CON | BOF | 2026-04-23 |  | 0 | 1879625 | 450000 | 870375 | 0 | 0 | 0 | 0 | 0 | 3200000
Scranton/W-B | 4 | Lackawanna | 67170 | Goers Hill Bridge No. 3 over White Oak Run |  |  | Bridge Replacement | CON | 183 | 2026-04-23 |  | 0 | 352430 | 84375 | 163195 | 0 | 0 | 0 | 0 | 0 | 600000
Scranton/W-B | 4 | Lackawanna | 67170 | Goers Hill Bridge No. 3 over White Oak Run |  |  | Bridge Replacement | CON | LOC | 2026-04-23 |  | 0 | 117477 | 28125 | 54398 | 0 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Lackawanna | 67190 | SR 6006 over Racket Brook | 6006 | 000 | Bridge Replacement | PE | NHPP | 2031-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Lackawanna | 67190 | SR 6006 over Racket Brook | 6006 | 000 | Bridge Replacement | PE | 185 | 2031-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Lackawanna | 67190 | SR 6006 over Racket Brook | 6006 | 000 | Bridge Replacement | CON | BRIP | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 1600000
Scranton/W-B | 4 | Lackawanna | 67190 | SR 6006 over Racket Brook | 6006 | 000 | Bridge Replacement | CON | 185 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 400000
Scranton/W-B | 4 | Lackawanna | 67197 | SR 2002 over West Branch of Wallenpaupack Creek | 2002 | 270 | Bridge Restoration | PE | STP | 2027-10-21 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Lackawanna | 67197 | SR 2002 over West Branch of Wallenpaupack Creek | 2002 | 270 | Bridge Restoration | PE | 185 | 2027-10-21 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Lackawanna | 67197 | SR 2002 over West Branch of Wallenpaupack Creek | 2002 | 270 | Bridge Restoration | CON | 581 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 2000000
Scranton/W-B | 4 | Lackawanna | 67199 | SR 3023 over Roaring Brook | 3023 | D50 | Bridge Restoration | CON | BRIP | 2026-04-23 |  | 0 | 1652000 | 1000000 | 2402000 | 0 | 0 | 0 | 0 | 0 | 5054000
Scranton/W-B | 4 | Lackawanna | 67199 | SR 3023 over Roaring Brook | 3023 | D50 | Bridge Restoration | CON | STP | 2026-04-23 |  | 0 | 746000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 746000
Scranton/W-B | 4 | Lackawanna | 67199 | SR 3023 over Roaring Brook | 3023 | D50 | Bridge Restoration | CON | 581 | 2026-04-23 |  | 0 | 599500 | 250000 | 600500 | 0 | 0 | 0 | 0 | 0 | 1450000
Scranton/W-B | 4 | Lackawanna | 67203 | SR 307 over Williams Bridge Reservoir | 307 | D53 | Bridge Replacement | FD | STU | 2026-06-04 |  | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
Scranton/W-B | 4 | Lackawanna | 67203 | SR 307 over Williams Bridge Reservoir | 307 | D53 | Bridge Replacement | FD | 185 | 2026-06-04 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Scranton/W-B | 4 | Lackawanna | 67203 | SR 307 over Williams Bridge Reservoir | 307 | D53 | Bridge Replacement | CON | STU | 2026-06-04 |  | 0 | 0 | 0 | 1900000 | 0 | 0 | 0 | 0 | 0 | 1900000
Scranton/W-B | 4 | Lackawanna | 67203 | SR 307 over Williams Bridge Reservoir | 307 | D53 | Bridge Replacement | CON | 581 | 2026-06-04 |  | 0 | 0 | 0 | 475000 | 0 | 0 | 0 | 0 | 0 | 475000
Scranton/W-B | 4 | Lackawanna | 67220 | SR 4003 over South Branch of Tunkhannock Creek | 4003 | 250 | Bridge Restoration | PE | BOF | 2031-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Lackawanna | 67220 | SR 4003 over South Branch of Tunkhannock Creek | 4003 | 250 | Bridge Restoration | PE | 185 | 2031-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Lackawanna | 67220 | SR 4003 over South Branch of Tunkhannock Creek | 4003 | 250 | Bridge Restoration | CON | BOF | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 2000000
Scranton/W-B | 4 | Lackawanna | 67220 | SR 4003 over South Branch of Tunkhannock Creek | 4003 | 250 | Bridge Restoration | CON | 185 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 500000
Scranton/W-B | 4 | Lackawanna | 67224 | SR 4036 over Falls Creek | 4036 | 250 | Bridge Replacement | FD | BRIP | 2026-05-21 |  | 315000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315000
Scranton/W-B | 4 | Lackawanna | 67224 | SR 4036 over Falls Creek | 4036 | 250 | Bridge Replacement | ROW | 581 | 2026-05-21 |  | 0 | 40500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40500
Scranton/W-B | 4 | Lackawanna | 67224 | SR 4036 over Falls Creek | 4036 | 250 | Bridge Replacement | CON | STP | 2026-05-21 |  | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Lackawanna | 67224 | SR 4036 over Falls Creek | 4036 | 250 | Bridge Replacement | CON | 185 | 2026-05-21 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Lackawanna | 67227 | SR 107 over Branch Tunkhannock Creek | 107 | D50 | Bridge Restoration | PE | STP | 2027-02-11 |  | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
Scranton/W-B | 4 | Lackawanna | 67227 | SR 107 over Branch Tunkhannock Creek | 107 | D50 | Bridge Restoration | PE | STU | 2027-02-11 |  | 244000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244000
Scranton/W-B | 4 | Lackawanna | 67227 | SR 107 over Branch Tunkhannock Creek | 107 | D50 | Bridge Restoration | CON | STP | 2027-02-11 |  | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Scranton/W-B | 4 | Lackawanna | 67227 | SR 107 over Branch Tunkhannock Creek | 107 | D50 | Bridge Restoration | CON | 185 | 2027-02-11 |  | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Scranton/W-B | 4 | Lackawanna | 67231 | SR 3002 over Branch of Saint Johns Creek | 3002 | 250 | Bridge Restoration | PE | STP | 2028-10-05 |  | 330000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000
Scranton/W-B | 4 | Lackawanna | 67231 | SR 3002 over Branch of Saint Johns Creek | 3002 | 250 | Bridge Restoration | PE | 185 | 2028-10-05 |  | 82500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Scranton/W-B | 4 | Lackawanna | 67231 | SR 3002 over Branch of Saint Johns Creek | 3002 | 250 | Bridge Restoration | CON | STP | 2028-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 800000
Scranton/W-B | 4 | Lackawanna | 67231 | SR 3002 over Branch of Saint Johns Creek | 3002 | 250 | Bridge Restoration | CON | 581 | 2028-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Scranton/W-B | 4 | Lackawanna | 67234 | SR 4011 over South Branch Tunkannock Creek | 4011 | D50 | Bridge Replacement | PE | 185 | 2031-01-01 |  | 116006 | 146494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262500
Scranton/W-B | 4 | Lackawanna | 67234 | SR 4011 over South Branch Tunkannock Creek | 4011 | D50 | Bridge Replacement | CON | 185 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000
Scranton/W-B | 4 | Lackawanna | 68824 | SR 438 over South Branch of Tunkhannock Creek | 438 | 274 | Bridge Restoration | PE | 581 | 2028-02-17 |  | 0 | 100000 | 618000 | 0 | 0 | 0 | 0 | 0 | 0 | 718000
Scranton/W-B | 4 | Lackawanna | 68824 | SR 438 over South Branch of Tunkhannock Creek | 438 | 274 | Bridge Restoration | CON | 581 | 2028-02-17 |  | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 2000000
Scranton/W-B | 4 | Lackawanna | 68836 | SR 1015 over I-81 | 1015 | 270 | Bridge Replacement | PE | BOF | 2035-01-01 |  | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 280000
Scranton/W-B | 4 | Lackawanna | 68836 | SR 1015 over I-81 | 1015 | 270 | Bridge Replacement | PE | 185 | 2035-01-01 |  | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
Scranton/W-B | 4 | Lackawanna | 68836 | SR 1015 over I-81 | 1015 | 270 | Bridge Replacement | CON | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
Scranton/W-B | 4 | Lackawanna | 68836 | SR 1015 over I-81 | 1015 | 270 | Bridge Replacement | CON | 581 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Scranton/W-B | 4 | Lackawanna | 69172 | SR 8041 over SR 11 | 8041 | 271 | Bridge Preservation - Federal | FD | NHPP | 2027-12-01 |  | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Lackawanna | 69172 | SR 8041 over SR 11 | 8041 | 271 | Bridge Preservation - Federal | FD | 185 | 2027-12-01 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Lackawanna | 69172 | SR 8041 over SR 11 | 8041 | 271 | Bridge Preservation - Federal | CON | NHPP | 2027-12-01 |  | 0 | 0 | 0 | 0 | 0 | 600000 | 500000 | 500000 | 0 | 1600000
Scranton/W-B | 4 | Lackawanna | 69172 | SR 8041 over SR 11 | 8041 | 271 | Bridge Preservation - Federal | CON | 185 | 2027-12-01 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 125000 | 125000 | 0 | 400000
Scranton/W-B | 4 | Lackawanna | 70194 | FAS-Loc, Lackawanna Co. |  |  | Reserve Line Item | CON | STU |  |  | 0 | 0 | 110912 | 400000 | 0 | 0 | 0 | 0 | 0 | 510912
Scranton/W-B | 4 | Lackawanna | 70194 | FAS-Loc, Lackawanna Co. |  |  | Reserve Line Item | CON | LOC |  |  | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Lackawanna | 72547 | SR 4022 over SR 4017 | 4022 | 250 | Bridge Restoration | PE | 185 | 2028-10-01 |  | 598000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598000
Scranton/W-B | 4 | Lackawanna | 72547 | SR 4022 over SR 4017 | 4022 | 250 | Bridge Restoration | CON | 581 | 2028-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000
Scranton/W-B | 4 | Lackawanna | 73300 | LLTS Highway Reserve |  |  | Reserve Line Item | CON | BOF |  |  | 3714 | 78000 | 125000 | 280625 | 463000 | 703000 | 503000 | 303000 | 2012000 | 4471339
Scranton/W-B | 4 | Lackawanna | 73300 | LLTS Highway Reserve |  |  | Reserve Line Item | CON | BRIP |  |  | 27760 | 7000 | 9000 | 1566020 | 59000 | 0 | 59000 | 1092760 | 1235000 | 4055540
Scranton/W-B | 4 | Lackawanna | 73300 | LLTS Highway Reserve |  |  | Reserve Line Item | CON | CRP |  |  | 49000 | 17000 | 17000 | 17000 | 17000 | 17000 | 517000 | 517000 | 2067000 | 3235000
Scranton/W-B | 4 | Lackawanna | 73300 | LLTS Highway Reserve |  |  | Reserve Line Item | CON | CRPU |  |  | 27000 | 150000 | 25000 | 0 | 150000 | 150000 | 1150000 | 1150000 | 4600000 | 7402000
Scranton/W-B | 4 | Lackawanna | 73300 | LLTS Highway Reserve |  |  | Reserve Line Item | CON | HSIP |  |  | 380090 | 947000 | 1142000 | 342000 | 992000 | 100 | 2492000 | 3992000 | 15970000 | 26257190
Scranton/W-B | 4 | Lackawanna | 73300 | LLTS Highway Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 285102 | 478248 | 434471 | 1186568 | 41000 | 61000 | 1541000 | 948670 | 4976059
Scranton/W-B | 4 | Lackawanna | 73300 | LLTS Highway Reserve |  |  | Reserve Line Item | CON | STP |  |  | 500 | 408375 | 180000 | 2738000 | 3558000 | 38000 | 138000 | 1738000 | 1252000 | 10050875
Scranton/W-B | 4 | Lackawanna | 73300 | LLTS Highway Reserve |  |  | Reserve Line Item | CON | STU |  |  | 38 | 164716 | 3110088 | 6181066 | 171200 | 1011000 | 470000 | 911000 | 1445000 | 13464108
Scranton/W-B | 4 | Lackawanna | 73300 | LLTS Highway Reserve |  |  | Reserve Line Item | CON | TAU |  |  | 788000 | 4000 | 4000 | 804000 | 804000 | 804000 | 804000 | 804000 | 3216000 | 8032000
Scranton/W-B | 4 | Lackawanna | 73300 | LLTS Highway Reserve |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 138126 | 15730 | 19805 | 1152000 | 176175 | 314921 | 534940 | 146000 | 2497697
Scranton/W-B | 4 | Lackawanna | 73300 | LLTS Highway Reserve |  |  | Reserve Line Item | CON | 581 |  |  | 64245 | 373500 | 30100 | 697379 | 87909 | 778250 | 177000 | 166000 | 56000 | 2430383
Scranton/W-B | 4 | Lackawanna | 73359 | Lck Co 'K' Rts Line Item |  |  | Reserve Line Item | CON | STU |  |  | 0 | 12000 | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 172000
Scranton/W-B | 4 | Lackawanna | 73359 | Lck Co 'K' Rts Line Item |  |  | Reserve Line Item | CON | LOC |  |  | 0 | 78000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 278000
Scranton/W-B | 4 | Lackawanna | 74716 | Dunmore Boro 5 Leg |  |  | Highway Restoration | CON | STP | 2025-12-12 |  | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
Scranton/W-B | 4 | Lackawanna | 79521 | SR 2013 over Meadow Brook | 2013 | 251 | Bridge Restoration | CON | BOF | 2023-11-02 | 2023-11-02 | 552000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552000
Scranton/W-B | 4 | Lackawanna | 79521 | SR 2013 over Meadow Brook | 2013 | 251 | Bridge Restoration | CON | 185 | 2023-11-02 | 2023-11-02 | 138000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138000
Scranton/W-B | 4 | Lackawanna | 84388 | LLTS Bridge Review |  |  | Reserve Line Item | CON | 185 |  |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 84388 | LLTS Bridge Review |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Scranton/W-B | 4 | Lackawanna | 85812 | SR 435 ov Van Brunt Ck | 435 | P01 | Bridge Restoration | ROW | 185 | 2025-10-09 | 2025-10-09 | 46500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46500
Scranton/W-B | 4 | Lackawanna | 85812 | SR 435 ov Van Brunt Ck | 435 | P01 | Bridge Restoration | CON | 185 | 2025-10-09 | 2025-10-09 | 0 | 270377 | 259623 | 0 | 0 | 0 | 0 | 0 | 0 | 530000
Scranton/W-B | 4 | Lackawanna | 90260 | SR 6006 over Lackawanna River | 6006 | BRG | Bridge Preservation - Federal | PE | NHPP | 2032-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Lackawanna | 90260 | SR 6006 over Lackawanna River | 6006 | BRG | Bridge Preservation - Federal | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Lackawanna | 90260 | SR 6006 over Lackawanna River | 6006 | BRG | Bridge Preservation - Federal | CON | NHPP | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 2000000 | 0 | 2400000
Scranton/W-B | 4 | Lackawanna | 90260 | SR 6006 over Lackawanna River | 6006 | BRG | Bridge Preservation - Federal | CON | 185 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 500000 | 0 | 600000
Scranton/W-B | 4 | Lackawanna | 92949 | Tigue Street Park N Ride | 8002 | 290 | Congestion Reduction | ROW | CRPU | 2026-06-18 |  | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
Scranton/W-B | 4 | Lackawanna | 92949 | Tigue Street Park N Ride | 8002 | 290 | Congestion Reduction | CON | CRP | 2026-06-18 |  | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Scranton/W-B | 4 | Lackawanna | 92949 | Tigue Street Park N Ride | 8002 | 290 | Congestion Reduction | CON | CRPU | 2026-06-18 |  | 0 | 645000 | 875000 | 975000 | 0 | 0 | 0 | 0 | 0 | 2495000
Scranton/W-B | 4 | Lackawanna | 94567 | SR 348 Intersection Improvement | 348 | IMP | Safety Improvement | CON | HSIP | 2024-10-24 | 2024-10-24 | 1111469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1111469
Scranton/W-B | 4 | Lackawanna | 95454 | US 11 over Railroad | 11 | D50 | Bridge Preservation - Federal | UTL | 581 | 2026-11-05 |  | 0 | 0 | 0 | 495500 | 0 | 0 | 0 | 0 | 0 | 495500
Scranton/W-B | 4 | Lackawanna | 95454 | US 11 over Railroad | 11 | D50 | Bridge Preservation - Federal | CON | NHPP | 2026-11-05 |  | 0 | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 1000000
Scranton/W-B | 4 | Lackawanna | 95454 | US 11 over Railroad | 11 | D50 | Bridge Preservation - Federal | CON | 581 | 2026-11-05 |  | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 250000
Scranton/W-B | 4 | Lackawanna | 95487 | Bridge Preservation |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 200000
Scranton/W-B | 4 | Lackawanna | 95487 | Bridge Preservation |  |  | Reserve Line Item | CON | 185 |  |  | 27000 | 0 | 0 | 0 | 0 | 0 | 1475000 | 0 | 0 | 1502000
Scranton/W-B | 4 | Lackawanna | 95487 | Bridge Preservation |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Scranton/W-B | 4 | Lackawanna | 96719 | SR 632 over Ackerly Creek | 632 | D51 | Bridge Replacement | CON | STU | 2023-04-13 | 2023-04-13 | 124518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124518
Scranton/W-B | 4 | Lackawanna | 96719 | SR 632 over Ackerly Creek | 632 | D51 | Bridge Replacement | CON | 185 | 2023-04-13 | 2023-04-13 | 31130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31130
Scranton/W-B | 4 | Lackawanna | 102061 | SR 11; SR 1005; SR 6006 Paving | 1005 | PAV | Highway Restoration | CON | STU | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000
Scranton/W-B | 4 | Lackawanna | 102061 | SR 11; SR 1005; SR 6006 Paving | 1005 | PAV | Highway Restoration | CON | 581 | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000
Scranton/W-B | 4 | Lackawanna | 106131 | SR 3014 Dalton Street Railroad Lights /Gates | 3014 | RRX | Rail Highway Grade Crossing | CON | RRX | 2023-05-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64688 | 64688
Scranton/W-B | 4 | Lackawanna | 106134 | SR 3017 Main Street Railroad Lights /Gates | 3017 | RRX | Rail Highway Grade Crossing | CON | RRX | 2023-05-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51750 | 51750
Scranton/W-B | 4 | Lackawanna | 106314 | Elm Street Bridge over Lackawanna River | 7302 | ELM | Bridge Replacement | CON | BOF | 2024-03-14 | 2024-03-14 | 4809497 | 746000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5555497
Scranton/W-B | 4 | Lackawanna | 106314 | Elm Street Bridge over Lackawanna River | 7302 | ELM | Bridge Replacement | CON | 183 | 2024-03-14 | 2024-03-14 | 595125 | 446531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1041656
Scranton/W-B | 4 | Lackawanna | 106314 | Elm Street Bridge over Lackawanna River | 7302 | ELM | Bridge Replacement | CON | LOC | 2024-03-14 | 2024-03-14 | 198375 | 148844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347219
Scranton/W-B | 4 | Lackawanna | 106664 | SR 8025 over Roaring Brook and Service Road | 8025 | 250 | Bridge Restoration | FD | NHPP | 2026-10-01 |  | 0 | 152080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152080
Scranton/W-B | 4 | Lackawanna | 106664 | SR 8025 over Roaring Brook and Service Road | 8025 | 250 | Bridge Restoration | FD | 185 | 2026-10-01 |  | 0 | 38020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38020
Scranton/W-B | 4 | Lackawanna | 106664 | SR 8025 over Roaring Brook and Service Road | 8025 | 250 | Bridge Restoration | UTL | 185 | 2026-10-01 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Scranton/W-B | 4 | Lackawanna | 106664 | SR 8025 over Roaring Brook and Service Road | 8025 | 250 | Bridge Restoration | CON | 185 | 2026-10-01 |  | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 2000000
Scranton/W-B | 4 | Lackawanna | 106664 | SR 8025 over Roaring Brook and Service Road | 8025 | 250 | Bridge Restoration | CON | 581 | 2026-10-01 |  | 0 | 0 | 0 | 2144455 | 3255545 | 0 | 0 | 0 | 0 | 5400000
Scranton/W-B | 4 | Lackawanna | 106681 | SR 247 Expand Jessup Borough Park and Ride | 247 | PAR | Congestion Reduction | PE | CRPU | 2032-10-07 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Scranton/W-B | 4 | Lackawanna | 109778 | SR 435 over Roaring Brook | 435 | 253 | Bridge Replacement | CON | BRIP | 2025-01-16 | 2025-01-16 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
Scranton/W-B | 4 | Lackawanna | 109778 | SR 435 over Roaring Brook | 435 | 253 | Bridge Replacement | CON | STP | 2025-01-16 | 2025-01-16 | 2680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2680000
Scranton/W-B | 4 | Lackawanna | 109778 | SR 435 over Roaring Brook | 435 | 253 | Bridge Replacement | CON | 581 | 2025-01-16 | 2025-01-16 | 500000 | 500000 | 250000 | 420000 | 0 | 0 | 0 | 0 | 0 | 1670000
Scranton/W-B | 4 | Lackawanna | 111466 | Keystone College Pedestrian and Trail Connections |  | TAP | Transportation Enhancement | CON | TAP | 2026-04-23 |  | 917815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917815
Scranton/W-B | 4 | Lackawanna | 111472 | Lack River Heritage Trail to Steamtown Ped Bridge |  | FLP | Transportation Enhancement | CON | TAP | 2027-03-25 |  | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
Scranton/W-B | 4 | Lackawanna | 112288 | SR 2107 over I-81 NB & SB | 2107 | BRG | Bridge Restoration | PE | BOF | 2026-05-21 |  | 315000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340000
Scranton/W-B | 4 | Lackawanna | 112288 | SR 2107 over I-81 NB & SB | 2107 | BRG | Bridge Restoration | PE | 185 | 2026-05-21 |  | 78750 | 6250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000
Scranton/W-B | 4 | Lackawanna | 112288 | SR 2107 over I-81 NB & SB | 2107 | BRG | Bridge Restoration | FD | BOF | 2026-05-21 |  | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000
Scranton/W-B | 4 | Lackawanna | 112288 | SR 2107 over I-81 NB & SB | 2107 | BRG | Bridge Restoration | FD | 185 | 2026-05-21 |  | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
Scranton/W-B | 4 | Lackawanna | 112288 | SR 2107 over I-81 NB & SB | 2107 | BRG | Bridge Restoration | ROW | 185 | 2026-05-21 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Lackawanna | 112288 | SR 2107 over I-81 NB & SB | 2107 | BRG | Bridge Restoration | CON | BOF | 2026-05-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 600000 | 0 | 1600000
Scranton/W-B | 4 | Lackawanna | 112288 | SR 2107 over I-81 NB & SB | 2107 | BRG | Bridge Restoration | CON | 185 | 2026-05-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 150000 | 0 | 400000
Scranton/W-B | 4 | Lackawanna | 112495 | Federal Aid Paving 4-20-FP2 | 247 | FP2 | Highway Restoration | CON | STP | 2020-08-20 | 2020-08-20 | 40500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40500
Scranton/W-B | 4 | Lackawanna | 112495 | Federal Aid Paving 4-20-FP2 | 247 | FP2 | Highway Restoration | CON | STU | 2020-08-20 | 2020-08-20 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Lackawanna | 113072 | SR 3006 over Gardner Creek | 3006 | 251 | Bridge Replacement | ROW | 185 | 2026-05-07 |  | 39260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39260
Scranton/W-B | 4 | Lackawanna | 113072 | SR 3006 over Gardner Creek | 3006 | 251 | Bridge Replacement | CON | BOF | 2026-05-07 |  | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
Scranton/W-B | 4 | Lackawanna | 113072 | SR 3006 over Gardner Creek | 3006 | 251 | Bridge Replacement | CON | 185 | 2026-05-07 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Lackawanna | 113272 | Mill Street over D&L Railroad/Roaring Brook | 7407 | BRG | Bridge Restoration | PE | BOF | 2027-10-14 |  | 746000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 746000
Scranton/W-B | 4 | Lackawanna | 113272 | Mill Street over D&L Railroad/Roaring Brook | 7407 | BRG | Bridge Restoration | PE | 183 | 2027-10-14 |  | 139875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139875
Scranton/W-B | 4 | Lackawanna | 113272 | Mill Street over D&L Railroad/Roaring Brook | 7407 | BRG | Bridge Restoration | PE | LOC | 2027-10-14 |  | 46625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46625
Scranton/W-B | 4 | Lackawanna | 113272 | Mill Street over D&L Railroad/Roaring Brook | 7407 | BRG | Bridge Restoration | FD | BOF | 2027-10-14 |  | 0 | 0 | 400000 | 2800000 | 0 | 0 | 0 | 0 | 0 | 3200000
Scranton/W-B | 4 | Lackawanna | 113272 | Mill Street over D&L Railroad/Roaring Brook | 7407 | BRG | Bridge Restoration | FD | 183 | 2027-10-14 |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Scranton/W-B | 4 | Lackawanna | 113272 | Mill Street over D&L Railroad/Roaring Brook | 7407 | BRG | Bridge Restoration | FD | 185 | 2027-10-14 |  | 0 | 0 | 0 | 525000 | 0 | 0 | 0 | 0 | 0 | 525000
Scranton/W-B | 4 | Lackawanna | 113272 | Mill Street over D&L Railroad/Roaring Brook | 7407 | BRG | Bridge Restoration | CON | BOF | 2027-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000000 | 20000000
Scranton/W-B | 4 | Lackawanna | 113272 | Mill Street over D&L Railroad/Roaring Brook | 7407 | BRG | Bridge Restoration | CON | 185 | 2027-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
Scranton/W-B | 4 | Lackawanna | 113723 | Roadway Improvements SR 632 | 632 | 204 | Highway Restoration | UTL | 581 | 2025-04-10 | 2025-04-10 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Lackawanna | 113723 | Roadway Improvements SR 632 | 632 | 204 | Highway Restoration | UTL | 581 | 2025-04-10 | 2025-04-10 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Scranton/W-B | 4 | Lackawanna | 113723 | Roadway Improvements SR 632 | 632 | 204 | Highway Restoration | CON | 581 | 2025-04-10 | 2025-04-10 | 2275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2275000
Scranton/W-B | 4 | Lackawanna | 113723 | Roadway Improvements SR 632 | 632 | 204 | Highway Restoration | CON | 581 | 2025-04-10 | 2025-04-10 | 0 | 64500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64500
Scranton/W-B | 4 | Lackawanna | 113869 | SR 8015 over I-81 Ramp | 8015 | 251 | Bridge Replacement | PE | NHPP | 2034-10-01 |  | 0 | 0 | 0 | 1600000 | 0 | 0 | 280000 | 0 | 0 | 1880000
Scranton/W-B | 4 | Lackawanna | 113869 | SR 8015 over I-81 Ramp | 8015 | 251 | Bridge Replacement | PE | 185 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 70000
Scranton/W-B | 4 | Lackawanna | 113869 | SR 8015 over I-81 Ramp | 8015 | 251 | Bridge Replacement | PE | 581 | 2034-10-01 |  | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Lackawanna | 113869 | SR 8015 over I-81 Ramp | 8015 | 251 | Bridge Replacement | CON | BRIP | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 3500000
Scranton/W-B | 4 | Lackawanna | 113869 | SR 8015 over I-81 Ramp | 8015 | 251 | Bridge Replacement | CON | 581 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Scranton/W-B | 4 | Lackawanna | 113985 | Guiderail Mash Upgrades - LLTS |  |  | Reserve Line Item | CON | STU |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 113985 | Guiderail Mash Upgrades - LLTS |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 114268 | SR 6 Drainage | 6 | 256 | Bridge Replacement | PE | NHPP | 2027-10-01 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Lackawanna | 114268 | SR 6 Drainage | 6 | 256 | Bridge Replacement | PE | 185 | 2027-10-01 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Scranton/W-B | 4 | Lackawanna | 114268 | SR 6 Drainage | 6 | 256 | Bridge Replacement | FD | BRIP | 2027-10-01 |  | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
Scranton/W-B | 4 | Lackawanna | 114268 | SR 6 Drainage | 6 | 256 | Bridge Replacement | FD | 185 | 2027-10-01 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Lackawanna | 114268 | SR 6 Drainage | 6 | 256 | Bridge Replacement | CON | STU | 2027-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9200000 | 9200000
Scranton/W-B | 4 | Lackawanna | 114268 | SR 6 Drainage | 6 | 256 | Bridge Replacement | CON | 581 | 2027-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300000 | 2300000
Scranton/W-B | 4 | Lackawanna | 115573 | SR 307 and Winola Road Safety Improvement | 307 | IMP | Safety Improvement | PE | HSIP | 2027-09-16 |  | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000
Scranton/W-B | 4 | Lackawanna | 115573 | SR 307 and Winola Road Safety Improvement | 307 | IMP | Safety Improvement | FD | HSIP | 2027-09-16 |  | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 350000
Scranton/W-B | 4 | Lackawanna | 115573 | SR 307 and Winola Road Safety Improvement | 307 | IMP | Safety Improvement | CON | HSIP | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 2000000
Scranton/W-B | 4 | Lackawanna | 115580 | SR 247 and SR 106 Safety Improvement | 247 | IMP | Safety Improvement | CON | HSIP | 2027-03-11 |  | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Scranton/W-B | 4 | Lackawanna | 115704 | SR 2004 over White Oak Run | 2004 | P44 | Bridge Restoration | CON | BOF | 2027-01-28 |  | 0 | 800000 | 1560000 | 0 | 0 | 0 | 0 | 0 | 0 | 2360000
Scranton/W-B | 4 | Lackawanna | 115704 | SR 2004 over White Oak Run | 2004 | P44 | Bridge Restoration | CON | 185 | 2027-01-28 |  | 0 | 200000 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 590000
Scranton/W-B | 4 | Lackawanna | 115720 | SR 3020 over Lacka Co Rail Bridge Preservation | 3020 | P50 | Bridge Preservation - Federal | CON | STU | 2025-01-16 | 2025-01-16 | 5783013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5783013
Scranton/W-B | 4 | Lackawanna | 115720 | SR 3020 over Lacka Co Rail Bridge Preservation | 3020 | P50 | Bridge Preservation - Federal | CON | 581 | 2025-01-16 | 2025-01-16 | 659400 | 100000 | 215600 | 470753 | 0 | 0 | 0 | 0 | 0 | 1445753
Scranton/W-B | 4 | Lackawanna | 115883 | SR 3011 Keyser Avenue Wall Replacement | 3011 | 253 | Highway Restoration | CON | 581 | 2024-04-11 | 2024-05-09 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Scranton/W-B | 4 | Lackawanna | 115918 | SR 6006 over Leggetts Creek Bridge Preservation | 6006 | PRS | Bridge Preservation - State Funded | CON | NHPP | 2023-07-27 | 2023-07-27 | 1800000 | 2150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3950000
Scranton/W-B | 4 | Lackawanna | 116484 | SR 347 over Lackawanna River | 347 | PRS | Bridge Preservation - State Funded | PE | NHPP | 2026-01-29 | 2026-01-29 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 116484 | SR 347 over Lackawanna River | 347 | PRS | Bridge Preservation - State Funded | ROW | 185 | 2026-01-29 | 2026-01-29 | 75800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75800
Scranton/W-B | 4 | Lackawanna | 116484 | SR 347 over Lackawanna River | 347 | PRS | Bridge Preservation - State Funded | CON | NHPP | 2026-01-29 | 2026-01-29 | 0 | 1283420 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 1883420
Scranton/W-B | 4 | Lackawanna | 116551 | SR 3013 Main Street Signal Corridor Phase 2 | 3013 | 204 | Congestion Reduction | PE | HVRU | 2026-05-07 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Scranton/W-B | 4 | Lackawanna | 116551 | SR 3013 Main Street Signal Corridor Phase 2 | 3013 | 204 | Congestion Reduction | ROW | HVRU | 2026-05-07 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Lackawanna | 116551 | SR 3013 Main Street Signal Corridor Phase 2 | 3013 | 204 | Congestion Reduction | CON | HVRU | 2026-05-07 |  | 0 | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000
Scranton/W-B | 4 | Lackawanna | 116551 | SR 3013 Main Street Signal Corridor Phase 2 | 3013 | 204 | Congestion Reduction | CON | CRPU | 2026-05-07 |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Lackawanna | 116551 | SR 3013 Main Street Signal Corridor Phase 2 | 3013 | 204 | Congestion Reduction | CON | HSIP | 2026-05-07 |  | 300000 | 795000 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 1945000
Scranton/W-B | 4 | Lackawanna | 116757 | Meredith Street Safety Crossing | 1039 | MTM | MultiModal | CON | 411 | 2026-06-18 |  | 0 | 344693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344693
Scranton/W-B | 4 | Lackawanna | 116759 | SR 11 over SR 6307 Keyser Ave | 11 | 257 | Bridge Restoration | PE | NHPP | 2032-10-01 |  | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 280000
Scranton/W-B | 4 | Lackawanna | 116759 | SR 11 over SR 6307 Keyser Ave | 11 | 257 | Bridge Restoration | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 70000
Scranton/W-B | 4 | Lackawanna | 116759 | SR 11 over SR 6307 Keyser Ave | 11 | 257 | Bridge Restoration | CON | 185 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
Scranton/W-B | 4 | Lackawanna | 116760 | SR 347 over Leggetts Creek | 347 | 252 | Bridge Restoration | PE | 581 | 2027-10-21 |  | 0 | 0 | 790000 | 0 | 0 | 0 | 0 | 0 | 0 | 790000
Scranton/W-B | 4 | Lackawanna | 116760 | SR 347 over Leggetts Creek | 347 | 252 | Bridge Restoration | CON | 581 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
Scranton/W-B | 4 | Lackawanna | 116761 | SR 347 over Kennedy Creek | 347 | 253 | Bridge Replacement | FD | 185 | 2025-03-13 | 2025-03-13 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Scranton/W-B | 4 | Lackawanna | 116761 | SR 347 over Kennedy Creek | 347 | 253 | Bridge Replacement | UTL | 185 | 2025-03-13 | 2025-03-13 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
Scranton/W-B | 4 | Lackawanna | 116761 | SR 347 over Kennedy Creek | 347 | 253 | Bridge Replacement | CON | 581 | 2025-03-13 | 2025-03-13 | 0 | 260200 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1260200
Scranton/W-B | 4 | Lackawanna | 116762 | SR 435 over Van Brunt Creek | 435 | 254 | Bridge Restoration | PE | STP | 2035-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Lackawanna | 116762 | SR 435 over Van Brunt Creek | 435 | 254 | Bridge Restoration | PE | 185 | 2035-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Lackawanna | 116762 | SR 435 over Van Brunt Creek | 435 | 254 | Bridge Restoration | CON | 581 | 2035-10-01 |  | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 1500000
Scranton/W-B | 4 | Lackawanna | 116763 | SR 438 over South Branch of Tunkhannock Creek | 438 | 0 | Bridge Restoration | PE | 185 | 2028-10-01 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 116763 | SR 438 over South Branch of Tunkhannock Creek | 438 | 0 | Bridge Restoration | CON | 185 | 2028-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000
Scranton/W-B | 4 | Lackawanna | 116764 | SR 690 over Roaring Brook | 690 | 253 | Bridge Restoration | PE | STP | 2027-10-21 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Lackawanna | 116764 | SR 690 over Roaring Brook | 690 | 253 | Bridge Restoration | PE | 185 | 2027-10-21 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Lackawanna | 116764 | SR 690 over Roaring Brook | 690 | 253 | Bridge Restoration | CON | STU | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 2400000 | 0 | 0 | 0 | 2400000
Scranton/W-B | 4 | Lackawanna | 116764 | SR 690 over Roaring Brook | 690 | 253 | Bridge Restoration | CON | 185 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 600000
Scranton/W-B | 4 | Lackawanna | 116765 | SR 1009 over Branch of Fall Brook | 1009 | 250 | Bridge Restoration | PE | STP | 2028-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Lackawanna | 116765 | SR 1009 over Branch of Fall Brook | 1009 | 250 | Bridge Restoration | PE | 185 | 2028-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Lackawanna | 116765 | SR 1009 over Branch of Fall Brook | 1009 | 250 | Bridge Restoration | CON | STU | 2028-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 800000
Scranton/W-B | 4 | Lackawanna | 116765 | SR 1009 over Branch of Fall Brook | 1009 | 250 | Bridge Restoration | CON | 185 | 2028-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Scranton/W-B | 4 | Lackawanna | 116766 | SR 2011 over Lehigh River | 2011 | 0 | Bridge Restoration | PE | BOF | 2030-10-01 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Lackawanna | 116766 | SR 2011 over Lehigh River | 2011 | 0 | Bridge Restoration | PE | 185 | 2030-10-01 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Lackawanna | 116766 | SR 2011 over Lehigh River | 2011 | 0 | Bridge Restoration | CON | BOF | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 1600000
Scranton/W-B | 4 | Lackawanna | 116766 | SR 2011 over Lehigh River | 2011 | 0 | Bridge Restoration | CON | 185 | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 400000
Scranton/W-B | 4 | Lackawanna | 116767 | SR 2018 over SR 380 | 2018 | 250 | Bridge Restoration | PE | BOF | 2029-10-01 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Lackawanna | 116767 | SR 2018 over SR 380 | 2018 | 250 | Bridge Restoration | PE | 185 | 2029-10-01 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Lackawanna | 116767 | SR 2018 over SR 380 | 2018 | 250 | Bridge Restoration | CON | BRIP | 2029-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 3500000
Scranton/W-B | 4 | Lackawanna | 116767 | SR 2018 over SR 380 | 2018 | 250 | Bridge Restoration | CON | 581 | 2029-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Scranton/W-B | 4 | Lackawanna | 116768 | SR 3011 over Saint Johns Creek | 3011 | 250 | Bridge Replacement | PE | STP | 2027-10-21 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Lackawanna | 116768 | SR 3011 over Saint Johns Creek | 3011 | 250 | Bridge Replacement | PE | 185 | 2027-10-21 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Lackawanna | 116768 | SR 3011 over Saint Johns Creek | 3011 | 250 | Bridge Replacement | FD | STU | 2027-10-21 |  | 0 | 388000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388000
Scranton/W-B | 4 | Lackawanna | 116768 | SR 3011 over Saint Johns Creek | 3011 | 250 | Bridge Replacement | FD | 185 | 2027-10-21 |  | 0 | 97000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97000
Scranton/W-B | 4 | Lackawanna | 116768 | SR 3011 over Saint Johns Creek | 3011 | 250 | Bridge Replacement | CON | STU | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 1200000
Scranton/W-B | 4 | Lackawanna | 116768 | SR 3011 over Saint Johns Creek | 3011 | 250 | Bridge Replacement | CON | 185 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 300000
Scranton/W-B | 4 | Lackawanna | 116797 | SR 8041 Ramps E & F over Branch of Leggetts Creek | 8041 | 250 | Bridge Restoration | PE | NHPP | 2031-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Lackawanna | 116797 | SR 8041 Ramps E & F over Branch of Leggetts Creek | 8041 | 250 | Bridge Restoration | PE | 185 | 2031-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Lackawanna | 116797 | SR 8041 Ramps E & F over Branch of Leggetts Creek | 8041 | 250 | Bridge Restoration | CON | NHPP | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 800000
Scranton/W-B | 4 | Lackawanna | 116797 | SR 8041 Ramps E & F over Branch of Leggetts Creek | 8041 | 250 | Bridge Restoration | CON | 185 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Scranton/W-B | 4 | Lackawanna | 117289 | Asset Management 1 | 11 | AST | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 540000 | 0 | 0 | 540000
Scranton/W-B | 4 | Lackawanna | 117290 | Asset Management 2 | 106 | AST | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000
Scranton/W-B | 4 | Lackawanna | 117290 | Asset Management 2 | 106 | AST | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 500000 | 7000000 | 7560000
Scranton/W-B | 4 | Lackawanna | 117890 | SR 11 over North Main Avenue | 11 | P01 | Bridge Preservation - State Funded | CON | BRIP | 2026-06-04 |  | 1140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1140000
Scranton/W-B | 4 | Lackawanna | 117890 | SR 11 over North Main Avenue | 11 | P01 | Bridge Preservation - State Funded | CON | NHPP | 2026-06-04 |  | 0 | 1200000 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 1460000
Scranton/W-B | 4 | Lackawanna | 117890 | SR 11 over North Main Avenue | 11 | P01 | Bridge Preservation - State Funded | CON | 185 | 2026-06-04 |  | 285000 | 300000 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
Scranton/W-B | 4 | Lackawanna | 117891 | SR 11 over Court Street | 11 | P02 | Bridge Preservation - State Funded | PE | 581 | 2026-06-04 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 117891 | SR 11 over Court Street | 11 | P02 | Bridge Preservation - State Funded | CON | STP | 2026-06-04 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 117891 | SR 11 over Court Street | 11 | P02 | Bridge Preservation - State Funded | CON | 581 | 2026-06-04 |  | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
Scranton/W-B | 4 | Lackawanna | 117892 | SR 11 over Theodore Street | 11 | P03 | Bridge Preservation - State Funded | PE | 581 | 2026-06-04 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 117892 | SR 11 over Theodore Street | 11 | P03 | Bridge Preservation - State Funded | CON | STP | 2026-06-04 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 117892 | SR 11 over Theodore Street | 11 | P03 | Bridge Preservation - State Funded | CON | 581 | 2026-06-04 |  | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
Scranton/W-B | 4 | Lackawanna | 117893 | SR 11 over Leach Creek | 11 | P04 | Bridge Preservation - State Funded | PE | 581 | 2026-06-04 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 117893 | SR 11 over Leach Creek | 11 | P04 | Bridge Preservation - State Funded | CON | STP | 2026-06-04 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 117893 | SR 11 over Leach Creek | 11 | P04 | Bridge Preservation - State Funded | CON | 581 | 2026-06-04 |  | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 600000
Scranton/W-B | 4 | Lackawanna | 117894 | SR 11 over SR 6307 | 11 | P05 | Bridge Preservation - State Funded | PE | 581 | 2026-06-04 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 117894 | SR 11 over SR 6307 | 11 | P05 | Bridge Preservation - State Funded | CON | 185 | 2026-06-04 |  | 0 | 1530000 | 1470000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
Scranton/W-B | 4 | Lackawanna | 117895 | SR 8029 On Ramp SB SR 11 | 8029 | P01 | Bridge Preservation - State Funded | PE | 581 | 2026-06-04 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 117895 | SR 8029 On Ramp SB SR 11 | 8029 | P01 | Bridge Preservation - State Funded | CON | 581 | 2026-06-04 |  | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 1500000
Scranton/W-B | 4 | Lackawanna | 117896 | SR 8029 Ramp from Main Ave. | 8029 | P02 | Bridge Preservation - State Funded | PE | 581 | 2026-06-04 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 117896 | SR 8029 Ramp from Main Ave. | 8029 | P02 | Bridge Preservation - State Funded | CON | 581 | 2026-06-04 |  | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000
Scranton/W-B | 4 | Lackawanna | 118208 | 2025 Federal Aid Paving - FP3 | 6 | FPP | Highway Restoration | CON | NHPP | 2027-03-11 |  | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Scranton/W-B | 4 | Lackawanna | 118208 | 2025 Federal Aid Paving - FP3 | 6 | FPP | Highway Restoration | CON | 581 | 2027-03-11 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Lackawanna | 118209 | 2025 Federal Aid Paving - FP4 | 84 | FPP | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 1750000
Scranton/W-B | 4 | Lackawanna | 118217 | City of Scranton Corridor Crossing | 3018 | RRX | Rail Highway Grade Crossing | CON | RRX | 2024-03-01 |  | 0 | 0 | 475000 | 500000 | 370000 | 951261 | 0 | 0 | 0 | 2296261
Scranton/W-B | 4 | Lackawanna | 118282 | SR 8001 over SR 11 NB | 8001 | P01 | Bridge Preservation - State Funded | PE | 185 | 2026-10-22 |  | 39960 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239960
Scranton/W-B | 4 | Lackawanna | 118428 | Archbald Borough Pedestrian Safety TASA |  | TAS | Transportation Enhancement | CON | TAP | 2026-04-23 |  | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455000
Scranton/W-B | 4 | Lackawanna | 118429 | Dickson City Boro Multimodal Revitilization TASA |  | TAS | Transportation Enhancement | CON | TAP | 2025-08-21 | 2025-08-21 | 2000449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000449
Scranton/W-B | 4 | Lackawanna | 118429 | Dickson City Boro Multimodal Revitilization TASA |  | TAS | Transportation Enhancement | CON | TAU | 2025-08-21 | 2025-08-21 | 101000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101000
Scranton/W-B | 4 | Lackawanna | 118430 | LHVA Pedestrian Enhancements TASA |  | TAP | Transportation Enhancement | CON | TAP | 2026-05-21 |  | 430000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430000
Scranton/W-B | 4 | Lackawanna | 118738 | T-718 over Roaring Brook | 7206 | LC5 | Bridge Restoration | CON | STP | 2025-04-17 | 2025-04-17 | 1630793 | 369207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Scranton/W-B | 4 | Lackawanna | 118738 | T-718 over Roaring Brook | 7206 | LC5 | Bridge Restoration | CON | STP | 2025-04-17 | 2025-04-17 | 316062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316062
Scranton/W-B | 4 | Lackawanna | 118738 | T-718 over Roaring Brook | 7206 | LC5 | Bridge Restoration | CON | STU | 2025-04-17 | 2025-04-17 | 46488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46488
Scranton/W-B | 4 | Lackawanna | 118738 | T-718 over Roaring Brook | 7206 | LC5 | Bridge Restoration | CON | LOC | 2025-04-17 | 2025-04-17 | 1637450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1637450
Scranton/W-B | 4 | Lackawanna | 118777 | SR 590 over I-84 EB/WB | 590 | P01 | Bridge Preservation - State Funded | CON | 581 | 2023-12-14 | 2023-12-14 | 47384 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322384
Scranton/W-B | 4 | Lackawanna | 119277 | LLTS Carbon Reduction Reserve Line Item |  |  | Reserve Line Item | CON | CRPU |  |  | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
Scranton/W-B | 4 | Lackawanna | 119601 | SR 6 over Norfolk Southern RR | 6 | P01 | Bridge Restoration | ROW | 185 | 2025-06-26 | 2025-06-26 | 27680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27680
Scranton/W-B | 4 | Lackawanna | 119601 | SR 6 over Norfolk Southern RR | 6 | P01 | Bridge Restoration | CON | NHPP | 2025-06-26 | 2025-06-26 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
Scranton/W-B | 4 | Lackawanna | 119601 | SR 6 over Norfolk Southern RR | 6 | P01 | Bridge Restoration | CON | 581 | 2025-06-26 | 2025-06-26 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Scranton/W-B | 4 | Lackawanna | 120529 | SR 11 Rain Event Repairs 3 | 11 | 2R3 | Disaster Permanent Repair | CON | NHPP | 2023-05-25 | 2023-05-25 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Scranton/W-B | 4 | Lackawanna | 120529 | SR 11 Rain Event Repairs 3 | 11 | 2R3 | Disaster Permanent Repair | CON | 581 | 2023-05-25 | 2023-05-25 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Lackawanna | 120592 | I-81 Rain Event Repairs | 81 | R23 | Disaster Permanent Repair | CON | NHPP | 2022-05-26 | 2022-05-26 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000
Scranton/W-B | 4 | Lackawanna | 120813 | SR 6011 Market Street Culvert | 6011 | 252 | Highway Restoration | ROW | 185 | 2026-07-02 |  | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
Scranton/W-B | 4 | Lackawanna | 120819 | SR 632 over Ackerly Creek II | 632 | 250 | Bridge Replacement | FD | 581 | 2025-10-23 | 2025-10-23 | 215000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215000
Scranton/W-B | 4 | Lackawanna | 120819 | SR 632 over Ackerly Creek II | 632 | 250 | Bridge Replacement | ROW | 581 | 2025-10-23 | 2025-10-23 | 33050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33050
Scranton/W-B | 4 | Lackawanna | 120819 | SR 632 over Ackerly Creek II | 632 | 250 | Bridge Replacement | CON | 185 | 2025-10-23 | 2025-10-23 | 975000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975000
Scranton/W-B | 4 | Lackawanna | 120845 | SR 590 Main Street Pipes | 590 | 252 | Bridge Replacement | PE | 581 |  |  | 0 | 310000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310000
Scranton/W-B | 4 | Lackawanna | 121385 | Gordon Avenue K-194 |  |  | Highway Restoration | CON | STU | 2026-02-12 | 2026-02-12 | 0 | 788000 | 512000 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000
Scranton/W-B | 4 | Lackawanna | 121525 | Blakely Borough -Valley View SD Sidewalks | 247 | TAS | Transportation Enhancement | CON | SRTSF | 2027-02-11 |  | 0 | 1009827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1009827
Scranton/W-B | 4 | Lackawanna | 121526 | Jessup Borough Hill ST SR 1014 Sidewalks | 1014 | TAS | Transportation Enhancement | CON | TAP | 2027-02-11 |  | 1277655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1277655
Scranton/W-B | 4 | Lackawanna | 121527 | Dickson City Streetscape Phase IV |  | TAS | Transportation Enhancement | CON | TAP | 2027-03-25 |  | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Scranton/W-B | 4 | Lackawanna | 121528 | LHVA Olyphant Trail Project |  | TAS | Transportation Enhancement | CON | TAP | 2026-06-18 |  | 600335 | 701500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1301835
Scranton/W-B | 4 | Lackawanna | 121528 | LHVA Olyphant Trail Project |  | TAS | Transportation Enhancement | CON | TAU | 2026-06-18 |  | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Lackawanna | 121531 | Mayfield School Safety Sidewalks |  | TAS | Transportation Enhancement | UTL | TAP | 2026-03-26 |  | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
Scranton/W-B | 4 | Lackawanna | 121531 | Mayfield School Safety Sidewalks |  | TAS | Transportation Enhancement | CON | TAP | 2026-03-26 |  | 388114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388114
Scranton/W-B | 4 | Lackawanna | 122225 | Beech Road Resurfacing |  | MTM | MultiModal | CON | 411 | 2026-04-15 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Lackawanna | 122225 | Beech Road Resurfacing |  | MTM | MultiModal | CON | LOC | 2026-04-15 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Scranton/W-B | 4 | Lackawanna | 122250 | LHVA Carbondale Trail Crossing Safety Project | 1039 | MTM | MultiModal | CON | 411 |  |  | 0 | 292914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292914
Scranton/W-B | 4 | Lackawanna | 122493 | ROW Claims Assitance - LLTS |  |  | Reserve Line Item | ROW | 581 |  |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Scranton/W-B | 4 | Lackawanna | 122520 | SR 1029 over Hulls Creek | 1029 | PRS | Bridge Preservation - State Funded | PE | 185 | 2027-04-08 |  | 445000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445000
Scranton/W-B | 4 | Lackawanna | 122573 | Dunmore Borough Keystone Industrial Park Road |  | ARC | Highway Reconstruction | PE | APL | 2026-09-10 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Lackawanna | 122573 | Dunmore Borough Keystone Industrial Park Road |  | ARC | Highway Reconstruction | FD | APL | 2026-09-10 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Lackawanna | 122573 | Dunmore Borough Keystone Industrial Park Road |  | ARC | Highway Reconstruction | CON | APL | 2026-09-10 |  | 1424325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1424325
Scranton/W-B | 4 | Lackawanna | 122573 | Dunmore Borough Keystone Industrial Park Road |  | ARC | Highway Reconstruction | CON | LOC | 2026-09-10 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 8464 | SR 3011 over Wapwallopen Creek | 3011 | 10S | Bridge Restoration | PE | BRIP | 2028-10-05 |  | 460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460000
Scranton/W-B | 4 | Luzerne | 8464 | SR 3011 over Wapwallopen Creek | 3011 | 10S | Bridge Restoration | PE | 185 | 2028-10-05 |  | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000
Scranton/W-B | 4 | Luzerne | 8464 | SR 3011 over Wapwallopen Creek | 3011 | 10S | Bridge Restoration | CON | BOF | 2028-10-05 |  | 0 | 0 | 0 | 0 | 2400000 | 0 | 0 | 0 | 0 | 2400000
Scranton/W-B | 4 | Luzerne | 8464 | SR 3011 over Wapwallopen Creek | 3011 | 10S | Bridge Restoration | CON | 185 | 2028-10-05 |  | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 600000
Scranton/W-B | 4 | Luzerne | 8741 | SR 2035 Suscon Road over Bear Creek | 2035 | 353 | Bridge Replacement | CON | BOF | 2023-12-14 | 2023-12-14 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 8741 | SR 2035 Suscon Road over Bear Creek | 2035 | 353 | Bridge Replacement | CON | 185 | 2023-12-14 | 2023-12-14 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 8757 | T-482 over Huntington Creek | 7217 | BRG | Bridge Replacement | PE | BOF | 2035-10-04 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 8757 | T-482 over Huntington Creek | 7217 | BRG | Bridge Replacement | PE | 185 | 2035-10-04 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 8758 | T-338 over Little Nescopeck Creek | 7230 | BRG | Bridge Replacement | PE | BOF | 2035-10-04 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 8758 | T-338 over Little Nescopeck Creek | 7230 | BRG | Bridge Replacement | PE | 183 | 2035-10-04 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 8759 | SR 7204 over Nescopeck Creek | 7204 | BRG | Bridge Replacement | FD | BOF | 2028-10-19 |  | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Scranton/W-B | 4 | Luzerne | 8759 | SR 7204 over Nescopeck Creek | 7204 | BRG | Bridge Replacement | FD | 183 | 2028-10-19 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Scranton/W-B | 4 | Luzerne | 8759 | SR 7204 over Nescopeck Creek | 7204 | BRG | Bridge Replacement | CON | BOF | 2028-10-19 |  | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 1600000
Scranton/W-B | 4 | Luzerne | 8759 | SR 7204 over Nescopeck Creek | 7204 | BRG | Bridge Replacement | CON | 183 | 2028-10-19 |  | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 300000
Scranton/W-B | 4 | Luzerne | 8765 | T-392 over Wapwallopen Creek Bridge | 7215 | BRG | Bridge Replacement | PE | STP | 2031-10-23 |  | 0 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Scranton/W-B | 4 | Luzerne | 8765 | T-392 over Wapwallopen Creek Bridge | 7215 | BRG | Bridge Replacement | FD | STP | 2031-10-23 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Luzerne | 8765 | T-392 over Wapwallopen Creek Bridge | 7215 | BRG | Bridge Replacement | CON | STP | 2031-10-23 |  | 0 | 0 | 600000 | 600000 | 0 | 0 | 0 | 0 | 0 | 1200000
Scranton/W-B | 4 | Luzerne | 8766 | T 451 Huntington Bridge 3 | 7217 | BRG | Bridge Replacement | PE | BOF | 2035-10-04 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 8766 | T 451 Huntington Bridge 3 | 7217 | BRG | Bridge Replacement | PE | 183 | 2035-10-04 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 8767 | T-472 over Huntington Creek | 7217 | BRG | Bridge Replacement | PE | BOF | 2035-10-04 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 8767 | T-472 over Huntington Creek | 7217 | BRG | Bridge Replacement | PE | 183 | 2035-10-04 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 8868 | SR 3014 over Nescopeck Creek | 3014 | 370 | Bridge Replacement | CON | BOF | 2022-03-31 | 2022-03-31 | 85976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85976
Scranton/W-B | 4 | Luzerne | 8868 | SR 3014 over Nescopeck Creek | 3014 | 370 | Bridge Replacement | CON | 185 | 2022-03-31 | 2022-03-31 | 21494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21494
Scranton/W-B | 4 | Luzerne | 8999 | SR 2005 over Bowman Spring Run | 2005 | 351 | Bridge Preservation - Federal | PE | 185 | 2028-01-27 |  | 545500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545500
Scranton/W-B | 4 | Luzerne | 8999 | SR 2005 over Bowman Spring Run | 2005 | 351 | Bridge Preservation - Federal | CON | NHPP | 2028-01-27 |  | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Luzerne | 8999 | SR 2005 over Bowman Spring Run | 2005 | 351 | Bridge Preservation - Federal | CON | 581 | 2028-01-27 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Luzerne | 9000 | SR 2008 over Nanticoke Creek | 2008 | 353 | Bridge Restoration | PE | STP | 2031-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 9000 | SR 2008 over Nanticoke Creek | 2008 | 353 | Bridge Restoration | PE | 185 | 2031-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 9000 | SR 2008 over Nanticoke Creek | 2008 | 353 | Bridge Restoration | CON | 581 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 1500000
Scranton/W-B | 4 | Luzerne | 9024 | SR 1036 over Leonards Creek | 1036 | D50 | Bridge Preservation - Federal | CON | 185 | 2026-04-09 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Scranton/W-B | 4 | Luzerne | 9025 | SR 4004 over Shickshinny Creek | 4004 | 350 | Bridge Replacement | CON | 581 | 2027-01-14 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Scranton/W-B | 4 | Luzerne | 9084 | SR 924 over SR 81 | 924 | 351 | Bridge Preservation - Federal | PE | NHPP | 2029-10-01 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Luzerne | 9084 | SR 924 over SR 81 | 924 | 351 | Bridge Preservation - Federal | CON | STP | 2029-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
Scranton/W-B | 4 | Luzerne | 9084 | SR 924 over SR 81 | 924 | 351 | Bridge Preservation - Federal | CON | 185 | 2029-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Scranton/W-B | 4 | Luzerne | 9128 | SR 115 over I-81 | 115 | 303 | Highway Reconstruction | CON | NHPP | 2024-06-06 | 2024-06-06 | 2880000 | 7049328 | 4467201 | 0 | 0 | 0 | 0 | 0 | 0 | 14396529
Scranton/W-B | 4 | Luzerne | 9128 | SR 115 over I-81 | 115 | 303 | Highway Reconstruction | CON | STP | 2024-06-06 | 2024-06-06 | 1385000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1385000
Scranton/W-B | 4 | Luzerne | 9128 | SR 115 over I-81 | 115 | 303 | Highway Reconstruction | CON | STU | 2024-06-06 | 2024-06-06 | 1063000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063000
Scranton/W-B | 4 | Luzerne | 9174 | SR 309 over Branch of Toby Creek | 309 | D56 | Bridge Restoration | CON | NHPP | 2023-01-26 | 2023-01-26 | 140722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140722
Scranton/W-B | 4 | Luzerne | 9180 | SR 115 over Ten Mile Run | 115 | 354 | Bridge Restoration | PE | STP | 2031-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 9180 | SR 115 over Ten Mile Run | 115 | 354 | Bridge Restoration | PE | 185 | 2031-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 9180 | SR 115 over Ten Mile Run | 115 | 354 | Bridge Restoration | CON | 581 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 56623 | SR 309 over Toby Creek | 309 | 364 | Bridge Replacement | CON | 185 | 2026-10-22 |  | 0 | 0 | 0 | 850000 | 2750000 | 2389825 | 269829 | 0 | 0 | 6259654
Scranton/W-B | 4 | Luzerne | 56623 | SR 309 over Toby Creek | 309 | 364 | Bridge Replacement | CON | 581 | 2026-10-22 |  | 0 | 0 | 0 | 150000 | 2790346 | 0 | 0 | 0 | 0 | 2940346
Scranton/W-B | 4 | Luzerne | 64481 | Butler Twp. Park & Ride | 309 | 393 | Congestion Reduction | PE | CRPU |  |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Scranton/W-B | 4 | Luzerne | 67254 | Broadway Street over Susquehanna River | 7302 | 350 | Bridge Replacement | CON | OTH-F | 2030-11-07 |  | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 5000000
Scranton/W-B | 4 | Luzerne | 67254 | Broadway Street over Susquehanna River | 7302 | 350 | Bridge Replacement | CON | STP | 2030-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 5000000
Scranton/W-B | 4 | Luzerne | 67254 | Broadway Street over Susquehanna River | 7302 | 350 | Bridge Replacement | CON | LOC | 2030-11-07 |  | 0 | 0 | 0 | 0 | 32500000 | 0 | 32500000 | 0 | 0 | 65000000
Scranton/W-B | 4 | Luzerne | 67255 | SR 7303 over Susquehanna River and Railroad | 7303 | 350 | Bridge Replacement | FD | STU | 2026-12-03 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 67255 | SR 7303 over Susquehanna River and Railroad | 7303 | 350 | Bridge Replacement | FD | 185 | 2026-12-03 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 67255 | SR 7303 over Susquehanna River and Railroad | 7303 | 350 | Bridge Replacement | CON | STU | 2026-12-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 4000000 | 8000000
Scranton/W-B | 4 | Luzerne | 67255 | SR 7303 over Susquehanna River and Railroad | 7303 | 350 | Bridge Replacement | CON | 185 | 2026-12-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | 2000000
Scranton/W-B | 4 | Luzerne | 67280 | SR 2036 over Red Run | 2036 | D52 | Bridge Replacement | PE | 185 | 2030-10-01 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Scranton/W-B | 4 | Luzerne | 67280 | SR 2036 over Red Run | 2036 | D52 | Bridge Replacement | CON | 581 | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Scranton/W-B | 4 | Luzerne | 67284 | SR 437 over Little Nescopeck Creek | 437 | 000 | Bridge Restoration | PE | STP | 2032-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 67284 | SR 437 over Little Nescopeck Creek | 437 | 000 | Bridge Restoration | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 67284 | SR 437 over Little Nescopeck Creek | 437 | 000 | Bridge Restoration | CON | 185 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 67291 | SR 1415 over Tributary Harvey's Lake Creek | 1415 | D01 | Bridge Replacement | PE | 185 | 2032-10-01 |  | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Scranton/W-B | 4 | Luzerne | 67291 | SR 1415 over Tributary Harvey's Lake Creek | 1415 | D01 | Bridge Replacement | CON | 581 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 67295 | SR 4016 over Hunlock Creek | 4016 | 353 | Bridge Restoration | PE | STP | 2027-10-21 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 67295 | SR 4016 over Hunlock Creek | 4016 | 353 | Bridge Restoration | PE | 185 | 2027-10-21 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 67295 | SR 4016 over Hunlock Creek | 4016 | 353 | Bridge Restoration | CON | 581 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 3000000
Scranton/W-B | 4 | Luzerne | 67296 | SR 11 over Hunlock Creek | 11 | 357 | Bridge Restoration | CON | STP | 2024-12-12 | 2024-12-12 | 800000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960000
Scranton/W-B | 4 | Luzerne | 67296 | SR 11 over Hunlock Creek | 11 | 357 | Bridge Restoration | CON | STU | 2024-12-12 | 2024-12-12 | 990000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1740000
Scranton/W-B | 4 | Luzerne | 67296 | SR 11 over Hunlock Creek | 11 | 357 | Bridge Restoration | CON | 185 | 2024-12-12 | 2024-12-12 | 447500 | 227500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675000
Scranton/W-B | 4 | Luzerne | 67299 | SR 29 over Harveys Creek | 29 | 350 | Bridge Restoration | CON | 581 | 2016-09-29 | 2016-09-29 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Scranton/W-B | 4 | Luzerne | 67333 | SR 3040 over Tributary Nescopeck Creek | 3040 | D51 | Bridge Replacement | CON | STU | 2024-02-29 | 2024-02-29 | 0 | 387792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387792
Scranton/W-B | 4 | Luzerne | 67333 | SR 3040 over Tributary Nescopeck Creek | 3040 | D51 | Bridge Replacement | CON | 185 | 2024-02-29 | 2024-02-29 | 0 | 96948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96948
Scranton/W-B | 4 | Luzerne | 67388 | SR 29 over Harveys Creek | 29 | 357 | Bridge Restoration | PE | STP | 2032-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 67388 | SR 29 over Harveys Creek | 29 | 357 | Bridge Restoration | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 67388 | SR 29 over Harveys Creek | 29 | 357 | Bridge Restoration | CON | STU | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 4000000
Scranton/W-B | 4 | Luzerne | 67388 | SR 29 over Harveys Creek | 29 | 357 | Bridge Restoration | CON | 185 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 67391 | SR 29 over Pikes Creek | 29 | 358 | Bridge Restoration | PE | 581 | 2027-10-21 |  | 0 | 412230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412230
Scranton/W-B | 4 | Luzerne | 67391 | SR 29 over Pikes Creek | 29 | 358 | Bridge Restoration | CON | 581 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 67395 | SR 2008 over Espy Run | 2008 | 350 | Bridge Restoration | FD | 581 | 2026-10-01 |  | 0 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325000
Scranton/W-B | 4 | Luzerne | 67395 | SR 2008 over Espy Run | 2008 | 350 | Bridge Restoration | ROW | 581 | 2026-10-01 |  | 0 | 0 | 64900 | 0 | 0 | 0 | 0 | 0 | 0 | 64900
Scranton/W-B | 4 | Luzerne | 67395 | SR 2008 over Espy Run | 2008 | 350 | Bridge Restoration | CON | STP | 2026-10-01 |  | 0 | 440000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 67395 | SR 2008 over Espy Run | 2008 | 350 | Bridge Restoration | CON | 185 | 2026-10-01 |  | 0 | 110000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 67410 | SR 6309 over Luzerne County Rail Authority | 6309 | D50 | Bridge Replacement | PE | NHPP | 2028-09-14 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 67410 | SR 6309 over Luzerne County Rail Authority | 6309 | D50 | Bridge Replacement | PE | 581 | 2028-09-14 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 67410 | SR 6309 over Luzerne County Rail Authority | 6309 | D50 | Bridge Replacement | CON | STP | 2028-09-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
Scranton/W-B | 4 | Luzerne | 67410 | SR 6309 over Luzerne County Rail Authority | 6309 | D50 | Bridge Replacement | CON | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Scranton/W-B | 4 | Luzerne | 67442 | SR 309 over Wapwallopen Creek | 309 | 379 | Bridge Restoration | PE | STP | 2032-10-01 |  | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 280000
Scranton/W-B | 4 | Luzerne | 67442 | SR 309 over Wapwallopen Creek | 309 | 379 | Bridge Restoration | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 70000
Scranton/W-B | 4 | Luzerne | 67442 | SR 309 over Wapwallopen Creek | 309 | 379 | Bridge Restoration | CON | 581 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 67450 | SR 3004 over Turtle Run Creek | 3004 | D01 | Bridge Replacement | PE | STP | 2031-10-01 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Scranton/W-B | 4 | Luzerne | 67450 | SR 3004 over Turtle Run Creek | 3004 | D01 | Bridge Replacement | CON | 185 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Scranton/W-B | 4 | Luzerne | 67456 | SR 924 Over Conrail, Hazle | 924 | 350 | Bridge Replacement | CON | BRIP | 2026-12-10 |  | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
Scranton/W-B | 4 | Luzerne | 67456 | SR 924 Over Conrail, Hazle | 924 | 350 | Bridge Replacement | CON | NHPP | 2026-12-10 |  | 0 | 247920 | 952080 | 400000 | 1400000 | 1400000 | 0 | 0 | 0 | 4400000
Scranton/W-B | 4 | Luzerne | 67456 | SR 924 Over Conrail, Hazle | 924 | 350 | Bridge Replacement | CON | 185 | 2026-12-10 |  | 0 | 0 | 200000 | 500000 | 350000 | 350000 | 0 | 0 | 0 | 1400000
Scranton/W-B | 4 | Luzerne | 67457 | SR 2048 over Pond Creek | 2048 | 370 | Bridge Replacement | PE | 581 | 2026-12-03 |  | 0 | 282000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282000
Scranton/W-B | 4 | Luzerne | 67457 | SR 2048 over Pond Creek | 2048 | 370 | Bridge Replacement | FD | 185 | 2026-12-03 |  | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
Scranton/W-B | 4 | Luzerne | 67457 | SR 2048 over Pond Creek | 2048 | 370 | Bridge Replacement | ROW | 581 | 2026-12-03 |  | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 70000
Scranton/W-B | 4 | Luzerne | 67457 | SR 2048 over Pond Creek | 2048 | 370 | Bridge Replacement | CON | 581 | 2026-12-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000
Scranton/W-B | 4 | Luzerne | 67460 | SR 3040 over Tributary Nescopeck Creek | 3040 | D50 | Bridge Replacement | FD | STP | 2026-11-05 |  | 40000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Scranton/W-B | 4 | Luzerne | 67460 | SR 3040 over Tributary Nescopeck Creek | 3040 | D50 | Bridge Replacement | ROW | 185 | 2026-11-05 |  | 0 | 85192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85192
Scranton/W-B | 4 | Luzerne | 67460 | SR 3040 over Tributary Nescopeck Creek | 3040 | D50 | Bridge Replacement | CON | STP | 2026-11-05 |  | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 67460 | SR 3040 over Tributary Nescopeck Creek | 3040 | D50 | Bridge Replacement | CON | 185 | 2026-11-05 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 67468 | SR 1021 over Abrahams Creek | 1021 | 000 | Bridge Restoration | PE | STP | 2032-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 67468 | SR 1021 over Abrahams Creek | 1021 | 000 | Bridge Restoration | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 67468 | SR 1021 over Abrahams Creek | 1021 | 000 | Bridge Restoration | CON | 581 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 2000000
Scranton/W-B | 4 | Luzerne | 67482 | SR 3004 over Espy Run | 3004 | D53 | Bridge Replacement | PE | STU | 2031-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Luzerne | 67482 | SR 3004 over Espy Run | 3004 | D53 | Bridge Replacement | PE | 185 | 2031-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 67482 | SR 3004 over Espy Run | 3004 | D53 | Bridge Replacement | CON | BRIP | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 4000000
Scranton/W-B | 4 | Luzerne | 67482 | SR 3004 over Espy Run | 3004 | D53 | Bridge Replacement | CON | 581 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 67491 | SR 315 over Reading Blue Mt and Northern Railroad | 315 | D53 | Bridge Preservation - Federal | PE | STP | 2030-10-01 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Luzerne | 67491 | SR 315 over Reading Blue Mt and Northern Railroad | 315 | D53 | Bridge Preservation - Federal | CON | STP | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
Scranton/W-B | 4 | Luzerne | 67491 | SR 315 over Reading Blue Mt and Northern Railroad | 315 | D53 | Bridge Preservation - Federal | CON | 581 | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Scranton/W-B | 4 | Luzerne | 68943 | SR 309 over Toby Creek #2 | 309 | 373 | Bridge Restoration | PE | NHPP | 2031-10-01 |  | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 280000
Scranton/W-B | 4 | Luzerne | 68943 | SR 309 over Toby Creek #2 | 309 | 373 | Bridge Restoration | PE | 185 | 2031-10-01 |  | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 18000
Scranton/W-B | 4 | Luzerne | 68943 | SR 309 over Toby Creek #2 | 309 | 373 | Bridge Restoration | CON | NHPP | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200000 | 0 | 3200000
Scranton/W-B | 4 | Luzerne | 68943 | SR 309 over Toby Creek #2 | 309 | 373 | Bridge Restoration | CON | 185 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 68947 | SR 309 over Toby Creek #3 | 309 | 374 | Bridge Restoration | PE | NHPP | 2031-10-01 |  | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 280000
Scranton/W-B | 4 | Luzerne | 68947 | SR 309 over Toby Creek #3 | 309 | 374 | Bridge Restoration | PE | 185 | 2031-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 68947 | SR 309 over Toby Creek #3 | 309 | 374 | Bridge Restoration | CON | NHPP | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200000 | 0 | 3200000
Scranton/W-B | 4 | Luzerne | 68947 | SR 309 over Toby Creek #3 | 309 | 374 | Bridge Restoration | CON | 185 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 68963 | SR 415 over Huntsville Creek | 415 | 370 | Bridge Restoration | PE | 581 | 2027-10-21 |  | 0 | 353100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353100
Scranton/W-B | 4 | Luzerne | 68963 | SR 415 over Huntsville Creek | 415 | 370 | Bridge Restoration | CON | 185 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 68977 | SR 1014 Overbrook over SR 309 | 1014 | 370 | Bridge Replacement | PE | STP | 2026-07-02 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 68977 | SR 1014 Overbrook over SR 309 | 1014 | 370 | Bridge Replacement | PE | 581 | 2026-07-02 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
Scranton/W-B | 4 | Luzerne | 68977 | SR 1014 Overbrook over SR 309 | 1014 | 370 | Bridge Replacement | FD | STP | 2026-07-02 |  | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56000
Scranton/W-B | 4 | Luzerne | 68977 | SR 1014 Overbrook over SR 309 | 1014 | 370 | Bridge Replacement | FD | 185 | 2026-07-02 |  | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000
Scranton/W-B | 4 | Luzerne | 68977 | SR 1014 Overbrook over SR 309 | 1014 | 370 | Bridge Replacement | ROW | STP | 2026-07-02 |  | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000
Scranton/W-B | 4 | Luzerne | 68977 | SR 1014 Overbrook over SR 309 | 1014 | 370 | Bridge Replacement | ROW | 185 | 2026-07-02 |  | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Scranton/W-B | 4 | Luzerne | 68977 | SR 1014 Overbrook over SR 309 | 1014 | 370 | Bridge Replacement | UTL | 185 | 2026-07-02 |  | 26108 | 4495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30603
Scranton/W-B | 4 | Luzerne | 68977 | SR 1014 Overbrook over SR 309 | 1014 | 370 | Bridge Replacement | UTL | OTH | 2026-07-02 |  | 26108 | 4495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30603
Scranton/W-B | 4 | Luzerne | 68977 | SR 1014 Overbrook over SR 309 | 1014 | 370 | Bridge Replacement | CON | STP | 2026-07-02 |  | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
Scranton/W-B | 4 | Luzerne | 68977 | SR 1014 Overbrook over SR 309 | 1014 | 370 | Bridge Replacement | CON | 185 | 2026-07-02 |  | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 68996 | SR 1061 over Branch of Harveys Creek | 1061 | 370 | Bridge Restoration | FD | 581 | 2026-10-01 |  | 0 | 365000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365000
Scranton/W-B | 4 | Luzerne | 68996 | SR 1061 over Branch of Harveys Creek | 1061 | 370 | Bridge Restoration | ROW | 185 | 2026-10-01 |  | 0 | 67674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67674
Scranton/W-B | 4 | Luzerne | 68996 | SR 1061 over Branch of Harveys Creek | 1061 | 370 | Bridge Restoration | CON | 185 | 2026-10-01 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Scranton/W-B | 4 | Luzerne | 69001 | SR 2019 over Interstate 81 | 2019 | 370 | Bridge Preservation - Federal | PE | STP | 2032-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Luzerne | 69001 | SR 2019 over Interstate 81 | 2019 | 370 | Bridge Preservation - Federal | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 69001 | SR 2019 over Interstate 81 | 2019 | 370 | Bridge Preservation - Federal | CON | STU | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
Scranton/W-B | 4 | Luzerne | 69001 | SR 2019 over Interstate 81 | 2019 | 370 | Bridge Preservation - Federal | CON | 581 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Scranton/W-B | 4 | Luzerne | 69228 | SR 29 over New Commerce Boulevard | 29 | 371 | Bridge Restoration | PE | NHPP | 2032-10-07 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Luzerne | 69228 | SR 29 over New Commerce Boulevard | 29 | 371 | Bridge Restoration | PE | 185 | 2032-10-07 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 69228 | SR 29 over New Commerce Boulevard | 29 | 371 | Bridge Restoration | CON | STP | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
Scranton/W-B | 4 | Luzerne | 69228 | SR 29 over New Commerce Boulevard | 29 | 371 | Bridge Restoration | CON | 185 | 2032-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Scranton/W-B | 4 | Luzerne | 73756 | Rogers Avenue over Solomon Creek | 7401 | RGS | Bridge Replacement | PE | BOF | 2031-01-16 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Luzerne | 73756 | Rogers Avenue over Solomon Creek | 7401 | RGS | Bridge Replacement | PE | 185 | 2031-01-16 |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Scranton/W-B | 4 | Luzerne | 73756 | Rogers Avenue over Solomon Creek | 7401 | RGS | Bridge Replacement | PE | LOC | 2031-01-16 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Scranton/W-B | 4 | Luzerne | 73756 | Rogers Avenue over Solomon Creek | 7401 | RGS | Bridge Replacement | CON | BOF | 2031-01-16 |  | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 1200000
Scranton/W-B | 4 | Luzerne | 73756 | Rogers Avenue over Solomon Creek | 7401 | RGS | Bridge Replacement | CON | 185 | 2031-01-16 |  | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000
Scranton/W-B | 4 | Luzerne | 73757 | Carey Street over Solomon Creek | 7401 | CRY | Bridge Restoration | PE | BOF | 2031-01-16 |  | 0 | 0 | 320000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Luzerne | 73757 | Carey Street over Solomon Creek | 7401 | CRY | Bridge Restoration | PE | 183 | 2031-01-16 |  | 0 | 0 | 60000 | 15000 | 0 | 0 | 0 | 0 | 0 | 75000
Scranton/W-B | 4 | Luzerne | 73757 | Carey Street over Solomon Creek | 7401 | CRY | Bridge Restoration | PE | LOC | 2031-01-16 |  | 0 | 0 | 20000 | 5000 | 0 | 0 | 0 | 0 | 0 | 25000
Scranton/W-B | 4 | Luzerne | 73757 | Carey Street over Solomon Creek | 7401 | CRY | Bridge Restoration | CON | BOF | 2031-01-16 |  | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 1200000
Scranton/W-B | 4 | Luzerne | 73757 | Carey Street over Solomon Creek | 7401 | CRY | Bridge Restoration | CON | 185 | 2031-01-16 |  | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000
Scranton/W-B | 4 | Luzerne | 79531 | SR 2010 over Sugar Notch Run Creek | 2010 | 350 | Bridge Restoration | PE | STP | 2028-02-17 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 79531 | SR 2010 over Sugar Notch Run Creek | 2010 | 350 | Bridge Restoration | PE | 185 | 2028-02-17 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 79531 | SR 2010 over Sugar Notch Run Creek | 2010 | 350 | Bridge Restoration | CON | STU | 2028-02-17 |  | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 1600000
Scranton/W-B | 4 | Luzerne | 79531 | SR 2010 over Sugar Notch Run Creek | 2010 | 350 | Bridge Restoration | CON | 185 | 2028-02-17 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Luzerne | 79532 | SR 2041 over Bear Creek | 2041 | 350 | Bridge Replacement | CON | STP | 2023-10-19 | 2023-11-02 | 2350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2350000
Scranton/W-B | 4 | Luzerne | 79532 | SR 2041 over Bear Creek | 2041 | 350 | Bridge Replacement | CON | STU | 2023-10-19 | 2023-11-02 | 200000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000
Scranton/W-B | 4 | Luzerne | 79532 | SR 2041 over Bear Creek | 2041 | 350 | Bridge Replacement | CON | 185 | 2023-10-19 | 2023-11-02 | 637500 | 47500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685000
Scranton/W-B | 4 | Luzerne | 79540 | SR 4014 over Pine Creek | 4014 | 351 | Bridge Restoration | PE | BOF | 2030-10-01 |  | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000
Scranton/W-B | 4 | Luzerne | 79540 | SR 4014 over Pine Creek | 4014 | 351 | Bridge Restoration | PE | 185 | 2030-10-01 |  | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
Scranton/W-B | 4 | Luzerne | 79540 | SR 4014 over Pine Creek | 4014 | 351 | Bridge Restoration | CON | BOF | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 3200000 | 0 | 0 | 0 | 3200000
Scranton/W-B | 4 | Luzerne | 79540 | SR 4014 over Pine Creek | 4014 | 351 | Bridge Restoration | CON | 581 | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 82906 | FAS-Loc, Luzerne Co. |  |  | Reserve Line Item | CON | STU |  |  | 0 | 400000 | 400000 | 129934 | 0 | 0 | 0 | 0 | 0 | 929934
Scranton/W-B | 4 | Luzerne | 82906 | FAS-Loc, Luzerne Co. |  |  | Reserve Line Item | CON | LOC |  |  | 0 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 300000
Scranton/W-B | 4 | Luzerne | 84301 | SR 11 over Abraham's Ck | 11 | 356 | Bridge Restoration | PE | 185 | 2034-10-01 |  | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Scranton/W-B | 4 | Luzerne | 84301 | SR 11 over Abraham's Ck | 11 | 356 | Bridge Restoration | CON | 185 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 2000000
Scranton/W-B | 4 | Luzerne | 92444 | Cooks Store Intersection | 118 | 392 | Safety Improvement | CON | HSIP | 2027-03-25 |  | 0 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000
Scranton/W-B | 4 | Luzerne | 93036 | SR 3010 over Branch Wapwallopen Creek | 3010 | 350 | Bridge Restoration | PE | STU | 2027-01-14 |  | 104795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104795
Scranton/W-B | 4 | Luzerne | 93036 | SR 3010 over Branch Wapwallopen Creek | 3010 | 350 | Bridge Restoration | FD | STP | 2027-01-14 |  | 0 | 50000 | 5000 | 170000 | 0 | 0 | 0 | 0 | 0 | 225000
Scranton/W-B | 4 | Luzerne | 93036 | SR 3010 over Branch Wapwallopen Creek | 3010 | 350 | Bridge Restoration | ROW | 581 | 2027-01-14 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Scranton/W-B | 4 | Luzerne | 93036 | SR 3010 over Branch Wapwallopen Creek | 3010 | 350 | Bridge Restoration | CON | STU | 2027-01-14 |  | 0 | 0 | 1280000 | 0 | 0 | 0 | 0 | 0 | 0 | 1280000
Scranton/W-B | 4 | Luzerne | 93036 | SR 3010 over Branch Wapwallopen Creek | 3010 | 350 | Bridge Restoration | CON | 185 | 2027-01-14 |  | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
Scranton/W-B | 4 | Luzerne | 93038 | Union St @ 309 Park-N-Ride | 309 | UST | Congestion Reduction | PE | CRPU | 2028-01-13 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Luzerne | 93931 | SR 11 over SR 2037, Susquehanna River and Railroad | 11 | 350 | Bridge Replacement | FD | BRIP | 2026-12-03 |  | 500000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 93931 | SR 11 over SR 2037, Susquehanna River and Railroad | 11 | 350 | Bridge Replacement | FD | NHPP | 2026-12-03 |  | 5490000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5790000
Scranton/W-B | 4 | Luzerne | 93931 | SR 11 over SR 2037, Susquehanna River and Railroad | 11 | 350 | Bridge Replacement | ROW | NHPP | 2026-12-03 |  | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300000
Scranton/W-B | 4 | Luzerne | 93931 | SR 11 over SR 2037, Susquehanna River and Railroad | 11 | 350 | Bridge Replacement | UTL | NHPP | 2026-12-03 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Scranton/W-B | 4 | Luzerne | 93931 | SR 11 over SR 2037, Susquehanna River and Railroad | 11 | 350 | Bridge Replacement | CON | BRIP | 2026-12-03 |  | 0 | 0 | 0 | 0 | 700000 | 4059000 | 9000000 | 316240 | 0 | 14075240
Scranton/W-B | 4 | Luzerne | 93931 | SR 11 over SR 2037, Susquehanna River and Railroad | 11 | 350 | Bridge Replacement | CON | NHPP | 2026-12-03 |  | 0 | 0 | 0 | 0 | 1903760 | 0 | 0 | 0 | 11000000 | 12903760
Scranton/W-B | 4 | Luzerne | 93931 | SR 11 over SR 2037, Susquehanna River and Railroad | 11 | 350 | Bridge Replacement | CON | RAISE | 2026-12-03 |  | 0 | 0 | 0 | 19000000 | 0 | 0 | 0 | 0 | 0 | 19000000
Scranton/W-B | 4 | Luzerne | 93931 | SR 11 over SR 2037, Susquehanna River and Railroad | 11 | 350 | Bridge Replacement | CON | STP | 2026-12-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Scranton/W-B | 4 | Luzerne | 93931 | SR 11 over SR 2037, Susquehanna River and Railroad | 11 | 350 | Bridge Replacement | CON | STU | 2026-12-03 |  | 0 | 0 | 0 | 0 | 3000000 | 0 | 4141000 | 0 | 0 | 7141000
Scranton/W-B | 4 | Luzerne | 93931 | SR 11 over SR 2037, Susquehanna River and Railroad | 11 | 350 | Bridge Replacement | CON | 185 | 2026-12-03 |  | 0 | 0 | 0 | 2750000 | 2120000 | 0 | 3285250 | 79060 | 2800940 | 11035250
Scranton/W-B | 4 | Luzerne | 93931 | SR 11 over SR 2037, Susquehanna River and Railroad | 11 | 350 | Bridge Replacement | CON | 581 | 2026-12-03 |  | 0 | 0 | 0 | 0 | 0 | 964750 | 0 | 0 | 0 | 964750
Scranton/W-B | 4 | Luzerne | 94303 | SR 2040 over Kendall Creek | 2040 | D50 | Bridge Replacement | PE | 185 | 2034-10-01 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Scranton/W-B | 4 | Luzerne | 94303 | SR 2040 over Kendall Creek | 2040 | D50 | Bridge Replacement | CON | 581 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 95494 | K-Route Luzerne County |  |  | Reserve Line Item | CON | STU |  |  | 0 | 400000 | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 1200000
Scranton/W-B | 4 | Luzerne | 95494 | K-Route Luzerne County |  |  | Reserve Line Item | CON | LOC |  |  | 0 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 300000
Scranton/W-B | 4 | Luzerne | 96722 | SR 1044 over Abraham's Creek | 1044 | D50 | Bridge Replacement | CON | STU | 2023-04-27 | 2023-04-27 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
Scranton/W-B | 4 | Luzerne | 96722 | SR 1044 over Abraham's Creek | 1044 | D50 | Bridge Replacement | CON | 185 | 2023-04-27 | 2023-04-27 | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17500
Scranton/W-B | 4 | Luzerne | 96724 | SR 2042 over Little Wapwallopen Creek | 2042 | D50 | Bridge Replacement | PE | 185 | 2035-10-01 |  | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Scranton/W-B | 4 | Luzerne | 96724 | SR 2042 over Little Wapwallopen Creek | 2042 | D50 | Bridge Replacement | CON | 581 | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 97941 | SR 309 over SR 8039 Ramp A | 309 | 365 | Bridge Removal | FD | NHPP | 2026-10-22 |  | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
Scranton/W-B | 4 | Luzerne | 97941 | SR 309 over SR 8039 Ramp A | 309 | 365 | Bridge Removal | CON | BRIP | 2026-10-22 |  | 0 | 0 | 0 | 0 | 6000000 | 5000000 | 0 | 1250000 | 0 | 12250000
Scranton/W-B | 4 | Luzerne | 97941 | SR 309 over SR 8039 Ramp A | 309 | 365 | Bridge Removal | CON | STP | 2026-10-22 |  | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 450000
Scranton/W-B | 4 | Luzerne | 97941 | SR 309 over SR 8039 Ramp A | 309 | 365 | Bridge Removal | CON | STU | 2026-10-22 |  | 0 | 0 | 0 | 0 | 1839800 | 0 | 0 | 0 | 0 | 1839800
Scranton/W-B | 4 | Luzerne | 97941 | SR 309 over SR 8039 Ramp A | 309 | 365 | Bridge Removal | CON | 185 | 2026-10-22 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 97941 | SR 309 over SR 8039 Ramp A | 309 | 365 | Bridge Removal | CON | 581 | 2026-10-22 |  | 0 | 0 | 0 | 200000 | 760200 | 0 | 3500000 | 0 | 0 | 4460200
Scranton/W-B | 4 | Luzerne | 97942 | SR 309 over Toby Creek 1 | 309 | 357 | Bridge Replacement | FD | NHPP | 2026-10-22 |  | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63000
Scranton/W-B | 4 | Luzerne | 97942 | SR 309 over Toby Creek 1 | 309 | 357 | Bridge Replacement | CON | BRIP | 2026-10-22 |  | 0 | 0 | 1550000 | 1350000 | 2300000 | 0 | 0 | 0 | 0 | 5200000
Scranton/W-B | 4 | Luzerne | 97942 | SR 309 over Toby Creek 1 | 309 | 357 | Bridge Replacement | CON | 185 | 2026-10-22 |  | 0 | 0 | 387500 | 337500 | 2075000 | 0 | 0 | 0 | 0 | 2800000
Scranton/W-B | 4 | Luzerne | 97943 | SR 309 over Toby Creek 2 | 309 | 358 | Bridge Restoration | FD | NHPP | 2026-10-22 |  | 73500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73500
Scranton/W-B | 4 | Luzerne | 97943 | SR 309 over Toby Creek 2 | 309 | 358 | Bridge Restoration | CON | BRIP | 2026-10-22 |  | 0 | 1000000 | 2700000 | 2700000 | 0 | 0 | 0 | 0 | 0 | 6400000
Scranton/W-B | 4 | Luzerne | 97943 | SR 309 over Toby Creek 2 | 309 | 358 | Bridge Restoration | CON | 185 | 2026-10-22 |  | 0 | 250000 | 675000 | 675000 | 0 | 0 | 0 | 0 | 0 | 1600000
Scranton/W-B | 4 | Luzerne | 100508 | SR 1005 over Becker's Creek | 1005 | D50 | Bridge Replacement | CON | STU | 2024-07-11 | 2024-07-11 | 387000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387000
Scranton/W-B | 4 | Luzerne | 100508 | SR 1005 over Becker's Creek | 1005 | D50 | Bridge Replacement | CON | 185 | 2024-07-11 | 2024-07-11 | 96750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96750
Scranton/W-B | 4 | Luzerne | 101388 | SR 1036 over Abrahams Creek | 1036 | D52 | Bridge Preservation - State Funded | PE | 581 | 2026-04-09 |  | 0 | 0 | 172000 | 0 | 0 | 0 | 0 | 0 | 0 | 172000
Scranton/W-B | 4 | Luzerne | 101388 | SR 1036 over Abrahams Creek | 1036 | D52 | Bridge Preservation - State Funded | FD | 581 | 2026-04-09 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 101388 | SR 1036 over Abrahams Creek | 1036 | D52 | Bridge Preservation - State Funded | CON | STP | 2026-04-09 |  | 0 | 1040000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1040000
Scranton/W-B | 4 | Luzerne | 101388 | SR 1036 over Abrahams Creek | 1036 | D52 | Bridge Preservation - State Funded | CON | 185 | 2026-04-09 |  | 0 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260000
Scranton/W-B | 4 | Luzerne | 101479 | SR 115 Pipe Replacement | 115 | D53 | Highway Restoration | CON | NHPP | 2027-01-14 |  | 0 | 0 | 400000 | 400000 | 1200000 | 400000 | 0 | 0 | 0 | 2400000
Scranton/W-B | 4 | Luzerne | 101479 | SR 115 Pipe Replacement | 115 | D53 | Highway Restoration | CON | STP | 2027-01-14 |  | 0 | 0 | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 101479 | SR 115 Pipe Replacement | 115 | D53 | Highway Restoration | CON | 581 | 2027-01-14 |  | 0 | 0 | 200000 | 200000 | 300000 | 100000 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 101925 | SR 4035 over Pine Creek | 4035 | 350 | Bridge Restoration | PE | BOF | 2026-10-22 |  | 0 | 124375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124375
Scranton/W-B | 4 | Luzerne | 101925 | SR 4035 over Pine Creek | 4035 | 350 | Bridge Restoration | FD | BOF | 2026-10-22 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Scranton/W-B | 4 | Luzerne | 101925 | SR 4035 over Pine Creek | 4035 | 350 | Bridge Restoration | ROW | 581 | 2026-10-22 |  | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
Scranton/W-B | 4 | Luzerne | 101925 | SR 4035 over Pine Creek | 4035 | 350 | Bridge Restoration | CON | BOF | 2026-10-22 |  | 0 | 0 | 0 | 560000 | 240000 | 0 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 101925 | SR 4035 over Pine Creek | 4035 | 350 | Bridge Restoration | CON | 185 | 2026-10-22 |  | 0 | 0 | 0 | 140000 | 60000 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 101927 | SR 437 over Railroad | 437 | 351 | Bridge Preservation - Federal | PE | BRIP | 2027-12-09 |  | 464240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464240
Scranton/W-B | 4 | Luzerne | 101927 | SR 437 over Railroad | 437 | 351 | Bridge Preservation - Federal | PE | 185 | 2027-12-09 |  | 116060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116060
Scranton/W-B | 4 | Luzerne | 101927 | SR 437 over Railroad | 437 | 351 | Bridge Preservation - Federal | CON | STP | 2027-12-09 |  | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 101927 | SR 437 over Railroad | 437 | 351 | Bridge Preservation - Federal | CON | 185 | 2027-12-09 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 102000 | SR 1036 Bridge Preservation | 1036 | D51 | Bridge Preservation - State Funded | CON | 185 | 2026-04-09 |  | 560000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | FD | NHPP | 2028-01-27 |  | 5760000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5760000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | FD | 581 | 2028-01-27 |  | 1440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | ROW | NHPP | 2028-01-27 |  | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | ROW | 581 | 2028-01-27 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | UTL | NHPP | 2028-01-27 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | UTL | 581 | 2028-01-27 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | CON | HVRU | 2028-01-27 |  | 0 | 0 | 1500000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 4500000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | CON | CRP | 2028-01-27 |  | 0 | 0 | 0 | 0 | 500000 | 500000 | 0 | 0 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | CON | CRPU | 2028-01-27 |  | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 2000000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | CON | HSIP | 2028-01-27 |  | 0 | 0 | 0 | 3000000 | 3000000 | 0 | 0 | 0 | 0 | 6000000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | CON | NHPP | 2028-01-27 |  | 0 | 0 | 0 | 1000000 | 5550672 | 800000 | 8460000 | 0 | 2189328 | 18000000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | CON | STP | 2028-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | CON | STU | 2028-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7800000 | 7800000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | CON | 185 | 2028-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
Scranton/W-B | 4 | Luzerne | 102030 | SR 2002 (San Souci Parkway) Reconstruction | 2002 | D50 | Highway Reconstruction | CON | 581 | 2028-01-27 |  | 0 | 0 | 0 | 820000 | 0 | 0 | 2280000 | 3500000 | 12400000 | 19000000
Scranton/W-B | 4 | Luzerne | 102116 | SR 2005 Reconstruction | 2005 | 370 | Highway Restoration | PE | 581 | 2029-10-01 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Luzerne | 102116 | SR 2005 Reconstruction | 2005 | 370 | Highway Restoration | CON | 581 | 2029-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000
Scranton/W-B | 4 | Luzerne | 103196 | CP Pittston / Dupont Corridor | 2017 | RRX | Rail Highway Grade Crossing | CON | RRX | 2024-08-16 |  | 577505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577505
Scranton/W-B | 4 | Luzerne | 103454 | N Washington St. over Luzerne/Susquehanna Railroad | 7304 | BRG | Bridge Replacement | PE | BOF | 2027-04-29 |  | 48580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48580
Scranton/W-B | 4 | Luzerne | 103454 | N Washington St. over Luzerne/Susquehanna Railroad | 7304 | BRG | Bridge Replacement | PE | 183 | 2027-04-29 |  | 9109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9109
Scranton/W-B | 4 | Luzerne | 103454 | N Washington St. over Luzerne/Susquehanna Railroad | 7304 | BRG | Bridge Replacement | PE | LOC | 2027-04-29 |  | 3036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3036
Scranton/W-B | 4 | Luzerne | 103454 | N Washington St. over Luzerne/Susquehanna Railroad | 7304 | BRG | Bridge Replacement | FD | BOF | 2027-04-29 |  | 252000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324000
Scranton/W-B | 4 | Luzerne | 103454 | N Washington St. over Luzerne/Susquehanna Railroad | 7304 | BRG | Bridge Replacement | FD | 183 | 2027-04-29 |  | 47250 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60750
Scranton/W-B | 4 | Luzerne | 103454 | N Washington St. over Luzerne/Susquehanna Railroad | 7304 | BRG | Bridge Replacement | FD | LOC | 2027-04-29 |  | 15750 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20250
Scranton/W-B | 4 | Luzerne | 103454 | N Washington St. over Luzerne/Susquehanna Railroad | 7304 | BRG | Bridge Replacement | ROW | BOF | 2027-04-29 |  | 0 | 128000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 168000
Scranton/W-B | 4 | Luzerne | 103454 | N Washington St. over Luzerne/Susquehanna Railroad | 7304 | BRG | Bridge Replacement | ROW | 183 | 2027-04-29 |  | 0 | 42000 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 49500
Scranton/W-B | 4 | Luzerne | 103454 | N Washington St. over Luzerne/Susquehanna Railroad | 7304 | BRG | Bridge Replacement | ROW | LOC | 2027-04-29 |  | 0 | 14000 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 16500
Scranton/W-B | 4 | Luzerne | 103454 | N Washington St. over Luzerne/Susquehanna Railroad | 7304 | BRG | Bridge Replacement | CON | BOF | 2027-04-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2800000 | 1200000 | 0 | 4000000
Scranton/W-B | 4 | Luzerne | 103454 | N Washington St. over Luzerne/Susquehanna Railroad | 7304 | BRG | Bridge Replacement | CON | 183 | 2027-04-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 225000 | 0 | 750000
Scranton/W-B | 4 | Luzerne | 103454 | N Washington St. over Luzerne/Susquehanna Railroad | 7304 | BRG | Bridge Replacement | CON | LOC | 2027-04-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 75000 | 0 | 250000
Scranton/W-B | 4 | Luzerne | 105050 | Nanticoke Streetscaping | 2002 | STR | Transportation Enhancement | CON | SXF | 2023-04-27 | 2023-04-27 | 230285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230285
Scranton/W-B | 4 | Luzerne | 105164 | SR 239 Safety Improvements | 239 | ERS | Safety Improvement | CON | HSIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 1500000
Scranton/W-B | 4 | Luzerne | 106127 | SR 2027 McAlpine Street over Mill Creek | 2027 | WAR | Rail Highway Grade Crossing | CON | RRX | 2023-05-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86250 | 86250
Scranton/W-B | 4 | Luzerne | 106324 | Commerce Boulevard Crossing |  | RRX | Rail Highway Grade Crossing | CON | RRX | 2022-06-01 |  | 523924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 523924
Scranton/W-B | 4 | Luzerne | 108017 | Greater Hazleton Rails to Trails (GHRT) PH III |  |  | Transportation Enhancement | CON | STP | 2019-09-27 | 2019-09-12 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Scranton/W-B | 4 | Luzerne | 110085 | SR 239 over Pine Creek | 239 | 351 | Bridge Replacement | CON | STP | 2024-08-08 | 2024-08-08 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
Scranton/W-B | 4 | Luzerne | 110085 | SR 239 over Pine Creek | 239 | 351 | Bridge Replacement | CON | 185 | 2024-08-08 | 2024-08-08 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Scranton/W-B | 4 | Luzerne | 110327 | SR 309 Signal Corridor | 309 | 394 | Safety Improvement | CON | HSIP | 2022-08-25 | 2022-08-25 | 1550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550000
Scranton/W-B | 4 | Luzerne | 111134 | C and H Corridor |  | RRX | Rail Highway Grade Crossing | CON | RRX | 2024-10-01 |  | 0 | 602002 | 0 | 517500 | 111725 | 48500 | 58615 | 0 | 0 | 1338342
Scranton/W-B | 4 | Luzerne | 112133 | Bridge Preservation 2025 | 1006 | PRS | Bridge Preservation - State Funded | PE | 185 |  |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 112837 | SR 29 over Susq River and RR Bridge Preservation | 29 | P22 | Bridge Preservation - Federal | CON | NHPP | 2022-03-31 | 2022-03-31 | 189176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189176
Scranton/W-B | 4 | Luzerne | 112874 | PA 309-Mundy Crossroads Improvement Partnership | 315 | MTM | Highway Reconstruction | CON | SXF | 2026-07-02 |  | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
Scranton/W-B | 4 | Luzerne | 112874 | PA 309-Mundy Crossroads Improvement Partnership | 315 | MTM | Highway Reconstruction | CON | 411 | 2026-07-02 |  | 6914554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6914554
Scranton/W-B | 4 | Luzerne | 112874 | PA 309-Mundy Crossroads Improvement Partnership | 315 | MTM | Highway Reconstruction | CON | PRIV | 2026-07-02 |  | 11085446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11085446
Scranton/W-B | 4 | Luzerne | 113368 | Exeter Borough Restore and Improve SR 1025 MTM | 1025 | MTM | MultiModal | CON | 411 | 2026-01-09 |  | 572293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 572293
Scranton/W-B | 4 | Luzerne | 113368 | Exeter Borough Restore and Improve SR 1025 MTM | 1025 | MTM | MultiModal | CON | LOC | 2026-01-09 |  | 245269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245269
Scranton/W-B | 4 | Luzerne | 113369 | Lehman Twsp Old Route 115 Base Repair and Pave MTM |  | MTM | MultiModal | CON | 411 | 2020-09-03 |  | 572293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 572293
Scranton/W-B | 4 | Luzerne | 113369 | Lehman Twsp Old Route 115 Base Repair and Pave MTM |  | MTM | MultiModal | CON | LOC | 2020-09-03 |  | 245269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245269
Scranton/W-B | 4 | Luzerne | 113521 | Hillside Road over Tobys Creek | 7220 | BRG | Bridge Replacement | PE | STP | 2027-05-13 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Scranton/W-B | 4 | Luzerne | 113521 | Hillside Road over Tobys Creek | 7220 | BRG | Bridge Replacement | FD | STP | 2027-05-13 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Scranton/W-B | 4 | Luzerne | 113521 | Hillside Road over Tobys Creek | 7220 | BRG | Bridge Replacement | CON | STP | 2027-05-13 |  | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Scranton/W-B | 4 | Luzerne | 113521 | Hillside Road over Tobys Creek | 7220 | BRG | Bridge Replacement | CON | STP | 2027-05-13 |  | 0 | 2202780 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 3202780
Scranton/W-B | 4 | Luzerne | 113521 | Hillside Road over Tobys Creek | 7220 | BRG | Bridge Replacement | CON | 185 | 2027-05-13 |  | 0 | 550695 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 800695
Scranton/W-B | 4 | Luzerne | 113623 | Hanover Industrial Estates Multimodal Improvements |  |  | Safety Improvement | CON | APL | 2025-07-18 |  | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260000
Scranton/W-B | 4 | Luzerne | 113853 | SR 1035 over Cider Run Creek | 1035 | 350 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 327500 | 137500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465000
Scranton/W-B | 4 | Luzerne | 113853 | SR 1035 over Cider Run Creek | 1035 | 350 | Bridge Restoration | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 114269 | SR 415 over Toby Creek | 415 | 351 | Bridge Replacement | CON | STP | 2027-07-15 |  | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
Scranton/W-B | 4 | Luzerne | 114269 | SR 415 over Toby Creek | 415 | 351 | Bridge Replacement | CON | 185 | 2027-07-15 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Luzerne | 114271 | SR 309 over Susquehanna River | 309 | 370 | Bridge Restoration | FD | NHPP | 2027-06-10 |  | 0 | 0 | 800000 | 1600000 | 0 | 0 | 0 | 0 | 0 | 2400000
Scranton/W-B | 4 | Luzerne | 114271 | SR 309 over Susquehanna River | 309 | 370 | Bridge Restoration | FD | 185 | 2027-06-10 |  | 0 | 0 | 200000 | 400000 | 0 | 0 | 0 | 0 | 0 | 600000
Scranton/W-B | 4 | Luzerne | 114271 | SR 309 over Susquehanna River | 309 | 370 | Bridge Restoration | CON | BRIP | 2027-06-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000000 | 24000000
Scranton/W-B | 4 | Luzerne | 114271 | SR 309 over Susquehanna River | 309 | 370 | Bridge Restoration | CON | NHPP | 2027-06-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28810762 | 28810762
Scranton/W-B | 4 | Luzerne | 114271 | SR 309 over Susquehanna River | 309 | 370 | Bridge Restoration | CON | STP | 2027-06-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
Scranton/W-B | 4 | Luzerne | 114271 | SR 309 over Susquehanna River | 309 | 370 | Bridge Restoration | CON | 185 | 2027-06-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 15000000
Scranton/W-B | 4 | Luzerne | 114275 | SR 2005 over Susquehanna River | 2005 | 352 | Bridge Restoration | PE | NHPP | 2030-10-01 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Luzerne | 114275 | SR 2005 over Susquehanna River | 2005 | 352 | Bridge Restoration | CON | STU | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000000 | 8000000
Scranton/W-B | 4 | Luzerne | 114275 | SR 2005 over Susquehanna River | 2005 | 352 | Bridge Restoration | CON | 185 | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Scranton/W-B | 4 | Luzerne | 114276 | SR 2007 over Railroad and Local Streets | 2007 | 351 | Bridge Removal | STUDY | STP |  |  | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
Scranton/W-B | 4 | Luzerne | 114276 | SR 2007 over Railroad and Local Streets | 2007 | 351 | Bridge Removal | STUDY | 185 |  |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
Scranton/W-B | 4 | Luzerne | 114277 | SR 2010 over Pocono Northeast Railroad | 2010 | 352 | Bridge Replacement | PE | 581 | 2027-02-25 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Scranton/W-B | 4 | Luzerne | 114277 | SR 2010 over Pocono Northeast Railroad | 2010 | 352 | Bridge Replacement | CON | STU | 2027-02-25 |  | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 114277 | SR 2010 over Pocono Northeast Railroad | 2010 | 352 | Bridge Replacement | CON | 581 | 2027-02-25 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 115571 | SR 309 and SR 2045 Safety Improvement | 309 | IMP | Safety Improvement | PE | HSIP | 2027-04-08 |  | 205000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205000
Scranton/W-B | 4 | Luzerne | 115571 | SR 309 and SR 2045 Safety Improvement | 309 | IMP | Safety Improvement | FD | HSIP | 2027-04-08 |  | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000
Scranton/W-B | 4 | Luzerne | 115571 | SR 309 and SR 2045 Safety Improvement | 309 | IMP | Safety Improvement | CON | HSIP | 2027-04-08 |  | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 2000000
Scranton/W-B | 4 | Luzerne | 115728 | SR 118 over Fades Creek Bridge Replacement | 118 | P56 | Bridge Replacement | PE | 185 | 2026-12-03 |  | 460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460000
Scranton/W-B | 4 | Luzerne | 115728 | SR 118 over Fades Creek Bridge Replacement | 118 | P56 | Bridge Replacement | ROW | 581 | 2026-12-03 |  | 22155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22155
Scranton/W-B | 4 | Luzerne | 115728 | SR 118 over Fades Creek Bridge Replacement | 118 | P56 | Bridge Replacement | CON | 581 | 2026-12-03 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Luzerne | 115731 | SR 315 over RBM&N Rail Bridge Preservation | 315 | P59 | Bridge Preservation - State Funded | CON | 581 | 2025-11-06 | 2025-11-06 | 0 | 539800 | 2700000 | 63605 | 0 | 0 | 0 | 0 | 0 | 3303405
Scranton/W-B | 4 | Luzerne | 115733 | SR 1013 over Tobys Creek Bridge Preservation | 1013 | P61 | Bridge Preservation - State Funded | CON | BRIP | 2025-04-10 | 2025-07-24 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
Scranton/W-B | 4 | Luzerne | 115733 | SR 1013 over Tobys Creek Bridge Preservation | 1013 | P61 | Bridge Preservation - State Funded | CON | STP | 2025-04-10 | 2025-07-24 | 0 | 265220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265220
Scranton/W-B | 4 | Luzerne | 115733 | SR 1013 over Tobys Creek Bridge Preservation | 1013 | P61 | Bridge Preservation - State Funded | CON | STU | 2025-04-10 | 2025-07-24 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Scranton/W-B | 4 | Luzerne | 115733 | SR 1013 over Tobys Creek Bridge Preservation | 1013 | P61 | Bridge Preservation - State Funded | CON | 185 | 2025-04-10 | 2025-07-24 | 177500 | 66305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243805
Scranton/W-B | 4 | Luzerne | 115734 | SR 1030 over Harveys Creek | 1030 | P62 | Bridge Replacement | CON | 581 | 2026-12-10 |  | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 115819 | SR 1009 Market Street over Susquehanna River | 1009 | PRS | Bridge Preservation - Federal | FD | NHPP | 2027-03-25 |  | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 480000
Scranton/W-B | 4 | Luzerne | 115819 | SR 1009 Market Street over Susquehanna River | 1009 | PRS | Bridge Preservation - Federal | FD | 185 | 2027-03-25 |  | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Scranton/W-B | 4 | Luzerne | 115819 | SR 1009 Market Street over Susquehanna River | 1009 | PRS | Bridge Preservation - Federal | CON | NHPP | 2027-03-25 |  | 0 | 0 | 0 | 0 | 0 | 8000000 | 0 | 0 | 0 | 8000000
Scranton/W-B | 4 | Luzerne | 115819 | SR 1009 Market Street over Susquehanna River | 1009 | PRS | Bridge Preservation - Federal | CON | 185 | 2027-03-25 |  | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 2000000
Scranton/W-B | 4 | Luzerne | 115919 | SR 309 over Township Rd T-462 Bridge | 309 | 380 | Bridge Restoration | CON | STP | 2025-10-09 | 2025-10-09 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Luzerne | 115919 | SR 309 over Township Rd T-462 Bridge | 309 | 380 | Bridge Restoration | CON | STU | 2025-10-09 | 2025-10-09 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Scranton/W-B | 4 | Luzerne | 115919 | SR 309 over Township Rd T-462 Bridge | 309 | 380 | Bridge Restoration | CON | 185 | 2025-10-09 | 2025-10-09 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Scranton/W-B | 4 | Luzerne | 116423 | SR 2005 over Luzerne County Rail Authority | 2005 | PRS | Bridge Restoration | CON | NHPP | 2027-08-26 |  | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
Scranton/W-B | 4 | Luzerne | 116423 | SR 2005 over Luzerne County Rail Authority | 2005 | PRS | Bridge Restoration | CON | 185 | 2027-08-26 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Luzerne | 116817 | SR 118 over Fades Creek | 118 | 352 | Bridge Restoration | PE | STP |  |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Luzerne | 116817 | SR 118 over Fades Creek | 118 | 352 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 116818 | SR 437 over Branch of Little Nescopeck Creek | 437 | 354 | Bridge Restoration | PE | STP | 2033-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Luzerne | 116818 | SR 437 over Branch of Little Nescopeck Creek | 437 | 354 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 116819 | SR 1034 over Branch of Harveys Creek | 1034 | 350 | Bridge Restoration | PE | 185 | 2028-02-17 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Luzerne | 116819 | SR 1034 over Branch of Harveys Creek | 1034 | 350 | Bridge Restoration | CON | 581 | 2028-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 116820 | SR 2001 over Solomon Creek | 2001 | 350 | Bridge Restoration | PE | STP | 2027-10-21 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Scranton/W-B | 4 | Luzerne | 116820 | SR 2001 over Solomon Creek | 2001 | 350 | Bridge Restoration | PE | 185 | 2027-10-21 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Scranton/W-B | 4 | Luzerne | 116820 | SR 2001 over Solomon Creek | 2001 | 350 | Bridge Restoration | CON | STU | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 1600000
Scranton/W-B | 4 | Luzerne | 116820 | SR 2001 over Solomon Creek | 2001 | 350 | Bridge Restoration | CON | 185 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Luzerne | 116821 | SR 2001 over Sugar Notch Creek | 2001 | 351 | Bridge Restoration | PE | STP | 2027-10-21 |  | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 280000
Scranton/W-B | 4 | Luzerne | 116821 | SR 2001 over Sugar Notch Creek | 2001 | 351 | Bridge Restoration | PE | 185 | 2027-10-21 |  | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 70000
Scranton/W-B | 4 | Luzerne | 116821 | SR 2001 over Sugar Notch Creek | 2001 | 351 | Bridge Restoration | CON | STU | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 116821 | SR 2001 over Sugar Notch Creek | 2001 | 351 | Bridge Restoration | CON | 185 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 116822 | SR 2007 over Rail Road and Local Streets | 2007 | 352 | Bridge Restoration | PE | STP | 2030-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Luzerne | 116822 | SR 2007 over Rail Road and Local Streets | 2007 | 352 | Bridge Restoration | PE | 185 | 2030-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 116824 | SR 2033 over Run Off | 2033 | 350 | Bridge Restoration | PE | STP | 2033-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Luzerne | 116824 | SR 2033 over Run Off | 2033 | 350 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 116824 | SR 2033 over Run Off | 2033 | 350 | Bridge Restoration | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 116825 | SR 2047 over Big Wapwallopen Creek | 2047 | 352 | Bridge Restoration | PE | BOF | 2030-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Luzerne | 116825 | SR 2047 over Big Wapwallopen Creek | 2047 | 352 | Bridge Restoration | PE | 185 | 2030-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 116825 | SR 2047 over Big Wapwallopen Creek | 2047 | 352 | Bridge Restoration | CON | BOF | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 116825 | SR 2047 over Big Wapwallopen Creek | 2047 | 352 | Bridge Restoration | CON | 581 | 2030-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 116826 | SR 2047 over Branch of Big Wapwallopen Creek | 2047 | 353 | Bridge Restoration | PE | STP | 2034-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Luzerne | 116826 | SR 2047 over Branch of Big Wapwallopen Creek | 2047 | 353 | Bridge Restoration | PE | 185 | 2034-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 116826 | SR 2047 over Branch of Big Wapwallopen Creek | 2047 | 353 | Bridge Restoration | CON | STP | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 116826 | SR 2047 over Branch of Big Wapwallopen Creek | 2047 | 353 | Bridge Restoration | CON | 581 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 116827 | SR 3006 over Branch of Pond Creek | 3006 | 351 | Bridge Restoration | PE | BOF | 2031-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Luzerne | 116827 | SR 3006 over Branch of Pond Creek | 3006 | 351 | Bridge Restoration | PE | 185 | 2031-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 116827 | SR 3006 over Branch of Pond Creek | 3006 | 351 | Bridge Restoration | CON | BRIP | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 116827 | SR 3006 over Branch of Pond Creek | 3006 | 351 | Bridge Restoration | CON | 581 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 116828 | SR 3010 over Wapwallopen Creek | 3010 | 351 | Bridge Restoration | PE | STP | 2032-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Luzerne | 116828 | SR 3010 over Wapwallopen Creek | 3010 | 351 | Bridge Restoration | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 116828 | SR 3010 over Wapwallopen Creek | 3010 | 351 | Bridge Restoration | CON | STU | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000 | 0 | 2400000
Scranton/W-B | 4 | Luzerne | 116828 | SR 3010 over Wapwallopen Creek | 3010 | 351 | Bridge Restoration | CON | 581 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 600000
Scranton/W-B | 4 | Luzerne | 116829 | SR 3018 over Tributary to Nescopeck Creek | 3018 | 352 | Bridge Restoration | FD | 581 | 2026-11-05 |  | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000
Scranton/W-B | 4 | Luzerne | 116829 | SR 3018 over Tributary to Nescopeck Creek | 3018 | 352 | Bridge Restoration | ROW | 185 | 2026-11-05 |  | 0 | 116963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116963
Scranton/W-B | 4 | Luzerne | 116829 | SR 3018 over Tributary to Nescopeck Creek | 3018 | 352 | Bridge Restoration | CON | STP | 2026-11-05 |  | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 116829 | SR 3018 over Tributary to Nescopeck Creek | 3018 | 352 | Bridge Restoration | CON | 185 | 2026-11-05 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 116830 | SR 4026 over Branch of Hunlock Creek | 4026 | 352 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Luzerne | 116830 | SR 4026 over Branch of Hunlock Creek | 4026 | 352 | Bridge Restoration | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000
Scranton/W-B | 4 | Luzerne | 116835 | SR 309 over Toby Creek #1 | 309 | 381 | Bridge Restoration | PE | NHPP | 2031-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Luzerne | 116835 | SR 309 over Toby Creek #1 | 309 | 381 | Bridge Restoration | PE | 185 | 2031-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 116835 | SR 309 over Toby Creek #1 | 309 | 381 | Bridge Restoration | CON | 581 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 4000000
Scranton/W-B | 4 | Luzerne | 117042 | SR 3016 Slide | 3016 | SLD | Highway Restoration | FD | 581 | 2026-02-26 | 2026-02-26 | 0 | 0 | 0 | 245000 | 0 | 0 | 0 | 0 | 0 | 245000
Scranton/W-B | 4 | Luzerne | 117042 | SR 3016 Slide | 3016 | SLD | Highway Restoration | ROW | 581 | 2026-02-26 | 2026-02-26 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
Scranton/W-B | 4 | Luzerne | 117042 | SR 3016 Slide | 3016 | SLD | Highway Restoration | CON | 581 | 2026-02-26 | 2026-02-26 | 0 | 0 | 0 | 3255545 | 0 | 0 | 0 | 0 | 0 | 3255545
Scranton/W-B | 4 | Luzerne | 117107 | SR 115 Retaining Wall Replacement | 115 | 355 | Highway Restoration | PE | NHPP | 2035-10-01 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Luzerne | 117107 | SR 115 Retaining Wall Replacement | 115 | 355 | Highway Restoration | CON | 581 | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000000 | 18000000
Scranton/W-B | 4 | Luzerne | 117110 | SR 2041 over Branch of Pine Creek | 2041 | 352 | Bridge Replacement | PE | STP | 2033-10-01 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Scranton/W-B | 4 | Luzerne | 117110 | SR 2041 over Branch of Pine Creek | 2041 | 352 | Bridge Replacement | PE | 185 | 2033-10-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Scranton/W-B | 4 | Luzerne | 117110 | SR 2041 over Branch of Pine Creek | 2041 | 352 | Bridge Replacement | CON | STP | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 117110 | SR 2041 over Branch of Pine Creek | 2041 | 352 | Bridge Replacement | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 117111 | SR 1010 over Drainage | 1010 | 351 | Bridge Replacement | PE | 581 |  |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Luzerne | 117976 | Federal Aid Paving 4-23-FP1 | 309 | FPP | Highway Restoration | CON | NHPP | 2023-03-02 | 2023-03-02 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
Scranton/W-B | 4 | Luzerne | 117979 | SR 115 Resurfacing | 115 | M23 | Highway Restoration | CON | STP | 2028-03-02 |  | 0 | 0 | 215000 | 40000 | 40000 | 0 | 0 | 0 | 0 | 295000
Scranton/W-B | 4 | Luzerne | 117979 | SR 115 Resurfacing | 115 | M23 | Highway Restoration | CON | STU | 2028-03-02 |  | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Luzerne | 117981 | SR 309 Federal Aid Paving 2026 | 309 | M26 | Highway Restoration | CON | NHPP | 2026-05-21 |  | 0 | 0 | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 117981 | SR 309 Federal Aid Paving 2026 | 309 | M26 | Highway Restoration | CON | 581 | 2026-05-21 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Luzerne | 117982 | SR 11 Federal Aid Paving 2026 | 11 | S04 | Highway Restoration | CON | NHPP | 2026-04-23 |  | 0 | 0 | 1823471 | 2926529 | 0 | 0 | 0 | 0 | 0 | 4750000
Scranton/W-B | 4 | Luzerne | 118219 | Jaycee Drive RR Crossing |  | RRX | Rail Highway Grade Crossing | CON | RRX | 2026-03-01 |  | 0 | 0 | 0 | 67500 | 0 | 0 | 0 | 0 | 0 | 67500
Scranton/W-B | 4 | Luzerne | 118281 | SR 239 over Big Wapwallopen Creek | 239 | P01 | Bridge Preservation - State Funded | ROW | 581 | 2025-12-04 | 2025-12-04 | 30050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30050
Scranton/W-B | 4 | Luzerne | 118281 | SR 239 over Big Wapwallopen Creek | 239 | P01 | Bridge Preservation - State Funded | CON | STP | 2025-12-04 | 2025-12-04 | 0 | 800000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
Scranton/W-B | 4 | Luzerne | 118281 | SR 239 over Big Wapwallopen Creek | 239 | P01 | Bridge Preservation - State Funded | CON | STU | 2025-12-04 | 2025-12-04 | 0 | 0 | 718000 | 0 | 0 | 0 | 0 | 0 | 0 | 718000
Scranton/W-B | 4 | Luzerne | 118281 | SR 239 over Big Wapwallopen Creek | 239 | P01 | Bridge Preservation - State Funded | CON | 185 | 2025-12-04 | 2025-12-04 | 0 | 200000 | 279500 | 0 | 0 | 0 | 0 | 0 | 0 | 479500
Scranton/W-B | 4 | Luzerne | 118283 | LCRA Corridor 2 | 1009 | RRX | Rail Highway Grade Crossing | CON | RRX | 2026-05-14 |  | 0 | 759411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759411
Scranton/W-B | 4 | Luzerne | 118418 | Exeter Borough MTM Resurfacing |  |  | MultiModal | CON | 411 | 2027-02-11 |  | 55153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55153
Scranton/W-B | 4 | Luzerne | 118418 | Exeter Borough MTM Resurfacing |  |  | MultiModal | CON | LOC | 2027-02-11 |  | 16546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16546
Scranton/W-B | 4 | Luzerne | 118431 | Riverfront Trail Pedestrian Enhancements TASA |  | TAS | Transportation Enhancement | CON | TAP | 2027-02-11 |  | 0 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000
Scranton/W-B | 4 | Luzerne | 118432 | Hanover Township Transportation Enhancements TASA |  | TAS | Transportation Enhancement | CON | TAP | 2026-01-29 | 2026-01-29 | 826000 | 1282750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2108750
Scranton/W-B | 4 | Luzerne | 118530 | SR 424 Corridor Improvements - TIIF | 424 | INT | Safety Improvement | CON | 581 | 2027-02-11 |  | 0 | 4500000 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 9000000
Scranton/W-B | 4 | Luzerne | 118538 | Hazleton Creek Corridor Improvements - TIIF |  |  | Safety Improvement | PE | 581 | 2027-03-05 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Scranton/W-B | 4 | Luzerne | 118538 | Hazleton Creek Corridor Improvements - TIIF |  |  | Safety Improvement | ROW | 581 | 2027-03-05 |  | 2042380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2042380
Scranton/W-B | 4 | Luzerne | 118538 | Hazleton Creek Corridor Improvements - TIIF |  |  | Safety Improvement | CON | 581 | 2027-03-05 |  | 0 | 2857620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2857620
Scranton/W-B | 4 | Luzerne | 118538 | Hazleton Creek Corridor Improvements - TIIF |  |  | Safety Improvement | CON | PRIV | 2027-03-05 |  | 0 | 9237965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9237965
Scranton/W-B | 4 | Luzerne | 118778 | SR 4018 over Pine Creek | 4018 | P01 | Bridge Restoration | CON | 581 | 2025-01-30 | 2025-01-30 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
Scranton/W-B | 4 | Luzerne | 118849 | Rotary Drive Local Access |  |  | New Alignment | CON | APL | 2025-08-08 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Scranton/W-B | 4 | Luzerne | 118849 | Rotary Drive Local Access |  |  | New Alignment | CON | LOC | 2025-08-08 |  | 1147500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1147500
Scranton/W-B | 4 | Luzerne | 119492 | South River Street Streetscape | 2004 | TIF | Transportation Enhancement | CON | 581 | 2026-03-26 | 2026-03-26 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Scranton/W-B | 4 | Luzerne | 119725 | Sweet Valley Road Improvements |  | SVR | Highway Restoration | CON | SXF | 2025-07-18 |  | 1550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550000
Scranton/W-B | 4 | Luzerne | 120104 | SR 93 and I-80 Off Ramp | 93 | RLN | Safety Improvement | CON | HSIP | 2026-07-30 |  | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Scranton/W-B | 4 | Luzerne | 120804 | West Union Street Scape Project |  | MTM | MultiModal | CON | 411 |  |  | 0 | 873000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 873000
Scranton/W-B | 4 | Luzerne | 120804 | West Union Street Scape Project |  | MTM | MultiModal | CON | LOC |  |  | 0 | 873820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 873820
Scranton/W-B | 4 | Luzerne | 120806 | Dale Drive over Big Wapwallopen Creek |  | MTM | MultiModal | CON | 411 |  |  | 545446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545446
Scranton/W-B | 4 | Luzerne | 120807 | East Mountain Blvd Street Improvements |  | MTM | MultiModal | CON | 411 |  |  | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Scranton/W-B | 4 | Luzerne | 120807 | East Mountain Blvd Street Improvements |  | MTM | MultiModal | CON | LOC |  |  | 0 | 467203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467203
Scranton/W-B | 4 | Luzerne | 121029 | SR 11 over SR 2037, Susquehanna River/RXR Preserv | 11 | PRS | Bridge Preservation - State Funded | UTL | 581 | 2025-01-09 | 2025-01-09 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Scranton/W-B | 4 | Luzerne | 121029 | SR 11 over SR 2037, Susquehanna River/RXR Preserv | 11 | PRS | Bridge Preservation - State Funded | CON | 581 | 2025-01-09 | 2025-01-09 | 2343216 | 1992670 | 1084400 | 0 | 0 | 0 | 0 | 0 | 0 | 5420286
Scranton/W-B | 4 | Luzerne | 121030 | SR 2007 over Railroad Preservation | 2007 | PRS | Bridge Preservation - State Funded | CON | 581 | 2025-05-22 | 2025-05-22 | 2000000 | 2500000 | 3435000 | 0 | 0 | 0 | 0 | 0 | 0 | 7935000
Scranton/W-B | 4 | Luzerne | 121051 | Asset Management 3 | 11 | AST | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2016240 | 2016240
Scranton/W-B | 4 | Luzerne | 121051 | Asset Management 3 | 11 | AST | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199060 | 1199060
Scranton/W-B | 4 | Luzerne | 121052 | Asset Management 4 | 11 | AST | Reserve Line Item | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Scranton/W-B | 4 | Luzerne | 121052 | Asset Management 4 | 11 | AST | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000
Scranton/W-B | 4 | Luzerne | 121083 | CenterPoint South Commerce & Trade Park Impr. | 2004 | MTM | MultiModal | CON | 411 | 2025-09-11 | 2025-09-11 | 1885311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1885311
Scranton/W-B | 4 | Luzerne | 121083 | CenterPoint South Commerce & Trade Park Impr. | 2004 | MTM | MultiModal | CON | PRIV | 2025-09-11 | 2025-09-11 | 1013172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1013172
Scranton/W-B | 4 | Luzerne | 121532 | Edwardsville Creekside Trail Connection | 11 | TAS | Transportation Enhancement | PE | CRPU | 2027-02-11 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Scranton/W-B | 4 | Luzerne | 121532 | Edwardsville Creekside Trail Connection | 11 | TAS | Transportation Enhancement | CON | TAP | 2027-02-11 |  | 0 | 1001011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1001011
Scranton/W-B | 4 | Luzerne | 121539 | Riverfront Trail Extension Phase 2 |  | TAS | Transportation Enhancement | CON | TAP | 2027-02-11 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Scranton/W-B | 4 | Luzerne | 121539 | Riverfront Trail Extension Phase 2 |  | TAS | Transportation Enhancement | CON | TAU | 2027-02-11 |  | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Scranton/W-B | 4 | Luzerne | 122223 | Hanover Green School Safe Streets |  |  | MultiModal | FD | 411 |  |  | 0 | 48200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48200
Scranton/W-B | 4 | Luzerne | 122223 | Hanover Green School Safe Streets |  |  | MultiModal | CON | 411 |  |  | 0 | 434925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434925
Scranton/W-B | 4 | Luzerne | 122248 | Wilkes-Barre City Streetscapes |  | MTM | MultiModal | CON | 411 | 2026-04-15 |  | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
Scranton/W-B | 4 | Luzerne | 122249 | City of Hazleton Street Improvements |  | MTM | MultiModal | CON | 411 |  |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Scranton/W-B | 4 | Luzerne | 122253 | Centerpointe Boulevard Resurfacing MTM |  | MTM | MultiModal | CON | 411 | 2026-04-23 |  | 300915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300915
Scranton/W-B | 4 | Luzerne | 122445 | Crestwood Drive K-Route Paving |  | RSF | Highway Restoration | CON | STP | 2026-12-03 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Scranton/W-B | 4 | Luzerne | 122593 | Commerce Drive Roadway Improvements MTM |  | MTM | MultiModal | CON | 411 |  |  | 0 | 610171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610171
Scranton/W-B | 4 | Luzerne | 122736 | SR 11 & SR 92 Intersection Improvement | 11 | INT | Congestion Reduction | CON | NHPP | 2026-07-30 |  | 0 | 380000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380000
Scranton/W-B | 4 | Luzerne | 123106 | SR 2061 Mundy Street Reconstruction | 2061 | MDY | Highway Restoration | PE | 581 | 2027-05-13 |  | 30000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SEDA-COG | 2 | Clinton | 3763 | T-537 over Fishing Creek Bridge | 7215 | REM | Bridge Removal | PE | 581 | 2026-06-18 |  | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
SEDA-COG | 2 | Clinton | 3763 | T-537 over Fishing Creek Bridge | 7215 | REM | Bridge Removal | ROW | 581 | 2026-06-18 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SEDA-COG | 2 | Clinton | 3763 | T-537 over Fishing Creek Bridge | 7215 | REM | Bridge Removal | UTL | 581 | 2026-06-18 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SEDA-COG | 2 | Clinton | 3763 | T-537 over Fishing Creek Bridge | 7215 | REM | Bridge Removal | CON | 581 | 2026-06-18 |  | 0 | 0 | 0 | 316000 | 0 | 0 | 0 | 0 | 0 | 316000
SEDA-COG | 2 | Clinton | 3770 | SR 2022 ov LtBr Sugar Run | 2022 | A03 | Bridge Replacement | PE | 185 | 2029-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 532043 | 0 | 0 | 532043
SEDA-COG | 2 | Clinton | 3770 | SR 2022 ov LtBr Sugar Run | 2022 | A03 | Bridge Replacement | FD | 185 | 2029-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391432 | 0 | 391432
SEDA-COG | 2 | Clinton | 3770 | SR 2022 ov LtBr Sugar Run | 2022 | A03 | Bridge Replacement | ROW | 185 | 2029-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65239 | 0 | 65239
SEDA-COG | 2 | Clinton | 3770 | SR 2022 ov LtBr Sugar Run | 2022 | A03 | Bridge Replacement | UTL | 185 | 2029-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65239 | 0 | 65239
SEDA-COG | 2 | Clinton | 3770 | SR 2022 ov LtBr Sugar Run | 2022 | A03 | Bridge Replacement | CON | 185 | 2029-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1304773 | 0 | 1304773
SEDA-COG | 2 | Clinton | 3793 | PA 120/North Smith Run | 120 | A15 | Bridge Restoration | PE | 185 | 2029-03-29 |  | 0 | 323553 | 145578 | 0 | 0 | 0 | 0 | 0 | 0 | 469131
SEDA-COG | 2 | Clinton | 3793 | PA 120/North Smith Run | 120 | A15 | Bridge Restoration | FD | 185 | 2029-03-29 |  | 0 | 0 | 0 | 347782 | 0 | 0 | 0 | 0 | 0 | 347782
SEDA-COG | 2 | Clinton | 3793 | PA 120/North Smith Run | 120 | A15 | Bridge Restoration | ROW | 185 | 2029-03-29 |  | 0 | 0 | 0 | 86946 | 0 | 0 | 0 | 0 | 0 | 86946
SEDA-COG | 2 | Clinton | 3793 | PA 120/North Smith Run | 120 | A15 | Bridge Restoration | UTL | 185 | 2029-03-29 |  | 0 | 0 | 0 | 86946 | 0 | 0 | 0 | 0 | 0 | 86946
SEDA-COG | 2 | Clinton | 3793 | PA 120/North Smith Run | 120 | A15 | Bridge Restoration | CON | 185 | 2029-03-29 |  | 0 | 0 | 0 | 0 | 974057 | 0 | 0 | 0 | 0 | 974057
SEDA-COG | 2 | Clinton | 3840 | Rauchtown Bridge | 2010 | A01 | Bridge Restoration | PE | BOF | 2026-11-05 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SEDA-COG | 2 | Clinton | 3840 | Rauchtown Bridge | 2010 | A01 | Bridge Restoration | FD | BOF | 2026-11-05 |  | 0 | 319538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319538
SEDA-COG | 2 | Clinton | 3840 | Rauchtown Bridge | 2010 | A01 | Bridge Restoration | ROW | BOF | 2026-11-05 |  | 0 | 56228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56228
SEDA-COG | 2 | Clinton | 3840 | Rauchtown Bridge | 2010 | A01 | Bridge Restoration | UTL | BOF | 2026-11-05 |  | 0 | 56228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56228
SEDA-COG | 2 | Clinton | 3840 | Rauchtown Bridge | 2010 | A01 | Bridge Restoration | CON | BOF | 2026-11-05 |  | 0 | 0 | 200000 | 757136 | 0 | 0 | 0 | 0 | 0 | 957136
SEDA-COG | 2 | Clinton | 3850 | SR 1001 Improvements | 1001 | C01 | Highway Reconstruction | CON | STP | 2022-05-12 | 2022-05-12 | 170000 | 5950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175950
SEDA-COG | 2 | Clinton | 3850 | SR 1001 Improvements | 1001 | C01 | Highway Reconstruction | CON | 581 | 2022-05-12 | 2022-05-12 | 0 | 1488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1488
SEDA-COG | 2 | Clinton | 3859 | PA 44/Pine Creek Br. | 44 | A01 | Bridge Restoration | PE | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677118 | 677118
SEDA-COG | 2 | Clinton | 3859 | PA 44/Pine Creek Br. | 44 | A01 | Bridge Restoration | FD | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553694 | 553694
SEDA-COG | 2 | Clinton | 3859 | PA 44/Pine Creek Br. | 44 | A01 | Bridge Restoration | ROW | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138423 | 138423
SEDA-COG | 2 | Clinton | 3859 | PA 44/Pine Creek Br. | 44 | A01 | Bridge Restoration | CON | 185 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12263141 | 12263141
SEDA-COG | 2 | Clinton | 3859 | PA 44/Pine Creek Br. | 44 | A01 | Bridge Restoration | CON | 581 | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579198 | 1579198
SEDA-COG | 2 | Clinton | 3861 | Laurel Run Bridge | 150 | A06 | Bridge Restoration | PE | BRIP | 2029-04-26 |  | 0 | 0 | 472714 | 0 | 0 | 0 | 0 | 0 | 0 | 472714
SEDA-COG | 2 | Clinton | 3861 | Laurel Run Bridge | 150 | A06 | Bridge Restoration | FD | BRIP | 2029-04-26 |  | 0 | 0 | 0 | 347782 | 0 | 0 | 0 | 0 | 0 | 347782
SEDA-COG | 2 | Clinton | 3861 | Laurel Run Bridge | 150 | A06 | Bridge Restoration | ROW | BRIP | 2029-04-26 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Clinton | 3861 | Laurel Run Bridge | 150 | A06 | Bridge Restoration | UTL | BRIP | 2029-04-26 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Clinton | 3861 | Laurel Run Bridge | 150 | A06 | Bridge Restoration | CON | 581 | 2029-04-26 |  | 0 | 0 | 0 | 0 | 1195539 | 0 | 0 | 0 | 0 | 1195539
SEDA-COG | 2 | Clinton | 68128 | Reserve Betterment/Safety Line Item |  | 000 | Reserve Line Item | CON | BRIP |  |  | 0 | 179925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179925
SEDA-COG | 2 | Clinton | 68128 | Reserve Betterment/Safety Line Item |  | 000 | Reserve Line Item | CON | HSIP |  |  | 0 | 548935 | 931200 | 931200 | 649200 | 649200 | 649200 | 649200 | 2596000 | 7604135
SEDA-COG | 2 | Clinton | 68128 | Reserve Betterment/Safety Line Item |  | 000 | Reserve Line Item | CON | NHPP |  |  | 0 | 560867 | 504424 | 0 | 0 | 0 | 0 | 0 | 0 | 1065291
SEDA-COG | 2 | Clinton | 68128 | Reserve Betterment/Safety Line Item |  | 000 | Reserve Line Item | CON | STP |  |  | 0 | 533956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 533956
SEDA-COG | 2 | Clinton | 68128 | Reserve Betterment/Safety Line Item |  | 000 | Reserve Line Item | CON | 185 |  |  | 0 | 451064 | 0 | 31675 | 0 | 0 | 0 | 0 | 0 | 482739
SEDA-COG | 2 | Clinton | 69038 | Bridge over Laurel Run | 2019 | A02 | Bridge Replacement | CON | BOF | 2024-02-29 | 2024-02-29 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SEDA-COG | 2 | Clinton | 83139 | Retro Local Bridge |  | LOC | Reserve Line Item | CON | 183 |  |  | 0 | 600000 | 0 | 519804 | 0 | 0 | 0 | 0 | 0 | 1119804
SEDA-COG | 2 | Clinton | 83139 | Retro Local Bridge |  | LOC | Reserve Line Item | CON | LOC |  |  | 0 | 150000 | 0 | 129951 | 0 | 0 | 0 | 0 | 0 | 279951
SEDA-COG | 2 | Clinton | 85149 | SR 0880 Rauchtown Cr II | 880 | A03 | Bridge Restoration | CON | BRIP | 2023-12-14 | 2023-12-14 | 200000 | 67137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267137
SEDA-COG | 2 | Clinton | 85149 | SR 0880 Rauchtown Cr II | 880 | A03 | Bridge Restoration | CON | STP | 2023-12-14 | 2023-12-14 | 352907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352907
SEDA-COG | 2 | Clinton | 85149 | SR 0880 Rauchtown Cr II | 880 | A03 | Bridge Restoration | CON | 185 | 2023-12-14 | 2023-12-14 | 60209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60209
SEDA-COG | 2 | Clinton | 88178 | Bridge ovNorfolk Southern | 220 | P58 | Bridge Replacement | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671958 | 671958
SEDA-COG | 2 | Clinton | 88178 | Bridge ovNorfolk Southern | 220 | P58 | Bridge Replacement | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3023812 | 3023812
SEDA-COG | 2 | Clinton | 91546 | SR 120 Upper Stimpson Run | 120 | A16 | Bridge Restoration | PE | 581 | 2029-02-22 |  | 0 | 393928 | 75203 | 0 | 0 | 0 | 0 | 0 | 0 | 469131
SEDA-COG | 2 | Clinton | 91546 | SR 120 Upper Stimpson Run | 120 | A16 | Bridge Restoration | FD | 185 | 2029-02-22 |  | 0 | 0 | 0 | 347782 | 0 | 0 | 0 | 0 | 0 | 347782
SEDA-COG | 2 | Clinton | 91546 | SR 120 Upper Stimpson Run | 120 | A16 | Bridge Restoration | ROW | 185 | 2029-02-22 |  | 0 | 0 | 0 | 86946 | 0 | 0 | 0 | 0 | 0 | 86946
SEDA-COG | 2 | Clinton | 91546 | SR 120 Upper Stimpson Run | 120 | A16 | Bridge Restoration | UTL | 185 | 2029-02-22 |  | 0 | 0 | 0 | 86946 | 0 | 0 | 0 | 0 | 0 | 86946
SEDA-COG | 2 | Clinton | 91546 | SR 120 Upper Stimpson Run | 120 | A16 | Bridge Restoration | CON | 185 | 2029-02-22 |  | 0 | 0 | 0 | 0 | 955242 | 0 | 0 | 0 | 0 | 955242
SEDA-COG | 2 | Clinton | 92421 | SC Bridge Plank/Channel Program |  |  | General Maintenance | CON | 185 |  | 2020-08-20 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SEDA-COG | 2 | Clinton | 93317 | Norfolk Southern Bridge | 120 | A17 | Bridge Restoration | PE | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657511 | 657511
SEDA-COG | 2 | Clinton | 93317 | Norfolk Southern Bridge | 120 | A17 | Bridge Restoration | FD | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449876 | 449876
SEDA-COG | 2 | Clinton | 93317 | Norfolk Southern Bridge | 120 | A17 | Bridge Restoration | ROW | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138424 | 138424
SEDA-COG | 2 | Clinton | 93317 | Norfolk Southern Bridge | 120 | A17 | Bridge Restoration | UTL | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138424 | 138424
SEDA-COG | 2 | Clinton | 93317 | Norfolk Southern Bridge | 120 | A17 | Bridge Restoration | CON | 185 | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10589389 | 10589389
SEDA-COG | 2 | Clinton | 93318 | SR 1002 W.Br. Susq Rvr | 1002 | A02 | Bridge Restoration | PE | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 622905 | 622905
SEDA-COG | 2 | Clinton | 93318 | SR 1002 W.Br. Susq Rvr | 1002 | A02 | Bridge Restoration | FD | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449876 | 449876
SEDA-COG | 2 | Clinton | 93318 | SR 1002 W.Br. Susq Rvr | 1002 | A02 | Bridge Restoration | ROW | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138424 | 138424
SEDA-COG | 2 | Clinton | 93318 | SR 1002 W.Br. Susq Rvr | 1002 | A02 | Bridge Restoration | UTL | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138424 | 138424
SEDA-COG | 2 | Clinton | 93318 | SR 1002 W.Br. Susq Rvr | 1002 | A02 | Bridge Restoration | CON | BOF | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6460371 | 6460371
SEDA-COG | 2 | Clinton | 93318 | SR 1002 W.Br. Susq Rvr | 1002 | A02 | Bridge Restoration | CON | STP | 2033-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8419701 | 8419701
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | PE | BOF | 2028-03-30 |  | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | PE | 183 | 2028-03-30 |  | 67500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | PE | LOC | 2028-03-30 |  | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | FD | BOF | 2028-03-30 |  | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | FD | 183 | 2028-03-30 |  | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | FD | LOC | 2028-03-30 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | ROW | BOF | 2028-03-30 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | ROW | 183 | 2028-03-30 |  | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | ROW | LOC | 2028-03-30 |  | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | UTL | BOF | 2028-03-30 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | UTL | 183 | 2028-03-30 |  | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | UTL | LOC | 2028-03-30 |  | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | CON | BRIP | 2028-03-30 |  | 0 | 0 | 0 | 1224000 | 0 | 0 | 0 | 0 | 0 | 1224000
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | CON | 183 | 2028-03-30 |  | 0 | 0 | 0 | 229500 | 0 | 0 | 0 | 0 | 0 | 229500
SEDA-COG | 2 | Clinton | 95903 | T-349 over Fishing Creek | 7215 | LOC | Bridge Replacement | CON | LOC | 2028-03-30 |  | 0 | 0 | 0 | 76500 | 0 | 0 | 0 | 0 | 0 | 76500
SEDA-COG | 2 | Clinton | 99956 | SR 144 Resurfacing | 144 | 326 | Highway Restoration | PE | 581 | 2032-04-01 |  | 0 | 0 | 0 | 0 | 0 | 553444 | 0 | 0 | 0 | 553444
SEDA-COG | 2 | Clinton | 99956 | SR 144 Resurfacing | 144 | 326 | Highway Restoration | CON | 581 | 2032-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 666948 | 5856918 | 0 | 6523866
SEDA-COG | 2 | Clinton | 101535 | Bridge over Long Run | 477 | A08 | Bridge Replacement | FD | BRIP | 2025-04-17 | 2025-04-17 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SEDA-COG | 2 | Clinton | 101535 | Bridge over Long Run | 477 | A08 | Bridge Replacement | CON | BRIP | 2025-04-17 | 2025-04-17 | 1485260 | 0 | 393928 | 0 | 0 | 0 | 0 | 0 | 0 | 1879188
SEDA-COG | 2 | Clinton | 110355 | 2022 Bridge Preservation | 150 | P37 | Bridge Restoration | CON | BRIP | 2022-05-12 | 2022-05-12 | 0 | 36600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36600
SEDA-COG | 2 | Clinton | 110355 | 2022 Bridge Preservation | 150 | P37 | Bridge Restoration | CON | STP | 2022-05-12 | 2022-05-12 | 37000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37000
SEDA-COG | 2 | Clinton | 110355 | 2022 Bridge Preservation | 150 | P37 | Bridge Restoration | CON | 185 | 2022-05-12 | 2022-05-12 | 9150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9150
SEDA-COG | 2 | Clinton | 112317 | I-80 ICM (Exit 173 to 185) | 80 | I03 | Congestion Reduction | PE | CRP | 2026-03-12 | 2026-03-12 | 115200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115200
SEDA-COG | 2 | Clinton | 112317 | I-80 ICM (Exit 173 to 185) | 80 | I03 | Congestion Reduction | PE | CRP | 2026-03-12 | 2026-03-12 | 184800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184800
SEDA-COG | 2 | Clinton | 112317 | I-80 ICM (Exit 173 to 185) | 80 | I03 | Congestion Reduction | PE | 581 | 2026-03-12 | 2026-03-12 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SEDA-COG | 2 | Clinton | 112317 | I-80 ICM (Exit 173 to 185) | 80 | I03 | Congestion Reduction | CON | CRP | 2026-03-12 | 2026-03-12 | 960000 | 59800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1019800
SEDA-COG | 2 | Clinton | 112317 | I-80 ICM (Exit 173 to 185) | 80 | I03 | Congestion Reduction | CON | CRP | 2026-03-12 | 2026-03-12 | 290200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290200
SEDA-COG | 2 | Clinton | 113133 | SR 120 over Dry Run | 120 | A19 | Bridge Restoration | PE | 581 | 2026-08-13 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 2 | Clinton | 113133 | SR 120 over Dry Run | 120 | A19 | Bridge Restoration | FD | 185 | 2026-08-13 |  | 0 | 293110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 293110
SEDA-COG | 2 | Clinton | 113133 | SR 120 over Dry Run | 120 | A19 | Bridge Restoration | ROW | 185 | 2026-08-13 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SEDA-COG | 2 | Clinton | 113133 | SR 120 over Dry Run | 120 | A19 | Bridge Restoration | UTL | 185 | 2026-08-13 |  | 79568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79568
SEDA-COG | 2 | Clinton | 113133 | SR 120 over Dry Run | 120 | A19 | Bridge Restoration | CON | 185 | 2026-08-13 |  | 0 | 811272 | 552043 | 0 | 0 | 0 | 0 | 0 | 0 | 1363315
SEDA-COG | 2 | Clinton | 114298 | SR 120 West Port Fill Slide | 120 | 324 | Highway Restoration | FD | STP | 2026-02-26 | 2026-02-26 | 347800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347800
SEDA-COG | 2 | Clinton | 114298 | SR 120 West Port Fill Slide | 120 | 324 | Highway Restoration | ROW | STP | 2026-02-26 | 2026-02-26 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 2 | Clinton | 114298 | SR 120 West Port Fill Slide | 120 | 324 | Highway Restoration | UTL | STP | 2026-02-26 | 2026-02-26 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SEDA-COG | 2 | Clinton | 114298 | SR 120 West Port Fill Slide | 120 | 324 | Highway Restoration | CON | PRTCT | 2026-02-26 | 2026-02-26 | 0 | 925000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 925000
SEDA-COG | 2 | Clinton | 114298 | SR 120 West Port Fill Slide | 120 | 324 | Highway Restoration | CON | 581 | 2026-02-26 | 2026-02-26 | 1375383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1375383
SEDA-COG | 2 | Clinton | 117043 | SEDA-COG Bridge Preservation 1 | 220 | P57 | Bridge Restoration | PE | NHPP | 2033-03-31 |  | 0 | 0 | 0 | 405746 | 0 | 0 | 0 | 0 | 0 | 405746
SEDA-COG | 2 | Clinton | 117043 | SEDA-COG Bridge Preservation 1 | 220 | P57 | Bridge Restoration | ROW | NHPP | 2033-03-31 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Clinton | 117043 | SEDA-COG Bridge Preservation 1 | 220 | P57 | Bridge Restoration | UTL | NHPP | 2033-03-31 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Clinton | 117043 | SEDA-COG Bridge Preservation 1 | 220 | P57 | Bridge Restoration | CON | NHPP | 2033-03-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6557000 | 6557000
SEDA-COG | 2 | Clinton | 117043 | SEDA-COG Bridge Preservation 1 | 220 | P57 | Bridge Restoration | CON | STP | 2033-03-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 968932 | 968932
SEDA-COG | 2 | Clinton | 117043 | SEDA-COG Bridge Preservation 1 | 220 | P57 | Bridge Restoration | CON | 581 | 2033-03-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1813233 | 1813233
SEDA-COG | 2 | Clinton | 117921 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 1900000 | 1900000 | 1900000 | 1900000 | 7596000 | 15196000
SEDA-COG | 2 | Clinton | 117921 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 0 | 1865553 | 5539000 | 5539000 | 5539000 | 5539000 | 22155000 | 46176553
SEDA-COG | 2 | Clinton | 117921 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 488000 | 488000 | 488000 | 488000 | 488000 | 488000 | 488000 | 1950000 | 5366000
SEDA-COG | 2 | Clinton | 117921 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 0 | 0 | 0 | 282000 | 282000 | 282000 | 282000 | 1128000 | 2256000
SEDA-COG | 2 | Clinton | 117921 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 4278000 | 4278000 | 4278000 | 4278000 | 17116000 | 34228000
SEDA-COG | 2 | Clinton | 117921 | Infrastructure Investment Reserve Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 0 | 0 | 0 | 510000 | 510000 | 510000 | 510000 | 2036000 | 4076000
SEDA-COG | 2 | Clinton | 119232 | SEDACOG Concrete Preservation | 220 | 327 | Preventive Maintenance | CON | NHPP | 2024-06-13 | 2024-06-13 | 270300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270300
SEDA-COG | 2 | Clinton | 119411 | SR 220 Youngdale Bridges | 220 | P64 | Bridge Restoration | CON | BRIP | 2025-01-09 | 2025-01-09 | 1916825 | 669233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586058
SEDA-COG | 2 | Clinton | 119926 | SR 120 Bridge Preservations | 120 | P60 | Bridge Restoration | PE | 185 | 2032-03-25 |  | 0 | 0 | 0 | 472714 | 0 | 0 | 0 | 0 | 0 | 472714
SEDA-COG | 2 | Clinton | 119926 | SR 120 Bridge Preservations | 120 | P60 | Bridge Restoration | ROW | 185 | 2032-03-25 |  | 0 | 0 | 0 | 86946 | 0 | 0 | 0 | 0 | 0 | 86946
SEDA-COG | 2 | Clinton | 119926 | SR 120 Bridge Preservations | 120 | P60 | Bridge Restoration | UTL | 185 | 2032-03-25 |  | 0 | 0 | 0 | 86946 | 0 | 0 | 0 | 0 | 0 | 86946
SEDA-COG | 2 | Clinton | 119926 | SR 120 Bridge Preservations | 120 | P60 | Bridge Restoration | CON | 581 | 2032-03-25 |  | 0 | 0 | 0 | 0 | 1176430 | 0 | 0 | 0 | 0 | 1176430
SEDA-COG | 2 | Clinton | 119928 | SR 150 Bridge Preservations | 150 | P68 | Bridge Restoration | PE | BRIP | 2028-11-02 |  | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000
SEDA-COG | 2 | Clinton | 119928 | SR 150 Bridge Preservations | 150 | P68 | Bridge Restoration | PE | STP | 2028-11-02 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 2 | Clinton | 119928 | SR 150 Bridge Preservations | 150 | P68 | Bridge Restoration | ROW | STP | 2028-11-02 |  | 0 | 0 | 0 | 0 | 130484 | 0 | 0 | 0 | 0 | 130484
SEDA-COG | 2 | Clinton | 119928 | SR 150 Bridge Preservations | 150 | P68 | Bridge Restoration | UTL | STP | 2028-11-02 |  | 0 | 0 | 0 | 0 | 130472 | 0 | 0 | 0 | 0 | 130472
SEDA-COG | 2 | Clinton | 119928 | SR 150 Bridge Preservations | 150 | P68 | Bridge Restoration | CON | 185 | 2028-11-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1565728 | 0 | 0 | 1565728
SEDA-COG | 2 | Clinton | 119935 | SR 220 over Private Drive | 220 | A05 | Bridge Restoration | PE | NHPP | 2030-02-28 |  | 0 | 0 | 150000 | 243928 | 0 | 0 | 0 | 0 | 0 | 393928
SEDA-COG | 2 | Clinton | 119935 | SR 220 over Private Drive | 220 | A05 | Bridge Restoration | ROW | STP | 2030-02-28 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Clinton | 119935 | SR 220 over Private Drive | 220 | A05 | Bridge Restoration | UTL | STP | 2030-02-28 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Clinton | 119935 | SR 220 over Private Drive | 220 | A05 | Bridge Restoration | CON | 185 | 2030-02-28 |  | 0 | 0 | 0 | 0 | 0 | 3690622 | 0 | 1000 | 0 | 3691622
SEDA-COG | 2 | Clinton | 119939 | SR 220 over Bald Eagle Creek | 220 | A07 | Bridge Replacement | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 293361 | 293361
SEDA-COG | 2 | Clinton | 119939 | SR 220 over Bald Eagle Creek | 220 | A07 | Bridge Replacement | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378597 | 378597
SEDA-COG | 2 | Clinton | 119939 | SR 220 over Bald Eagle Creek | 220 | A07 | Bridge Replacement | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8063498 | 8063498
SEDA-COG | 2 | Clinton | 119953 | SR 220 over Lower Creek Rd | 220 | A01 | Bridge Preservation - Federal | CON | NHPP | 2024-03-14 | 2024-03-14 | 82305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82305
SEDA-COG | 2 | Clinton | 119955 | SR 220 over SR 150 | 220 | 0 | Bridge Replacement | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671958 | 671958
SEDA-COG | 2 | Clinton | 119955 | SR 220 over SR 150 | 220 | 0 | Bridge Replacement | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 816681 | 816681
SEDA-COG | 2 | Clinton | 119955 | SR 220 over SR 150 | 220 | 0 | Bridge Replacement | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1349266 | 1349266
SEDA-COG | 2 | Clinton | 120111 | SR 880 HFST Project | 880 | HFS | General Maintenance | CON | 581 | 2024-06-13 | 2024-06-13 | 58000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58000
SEDA-COG | 2 | Clinton | 120759 | SR 64 Concrete Preservation | 64 | 330 | Highway Restoration | PE | STP | 2028-09-30 |  | 0 | 200000 | 272714 | 0 | 0 | 0 | 0 | 0 | 0 | 472714
SEDA-COG | 2 | Clinton | 120759 | SR 64 Concrete Preservation | 64 | 330 | Highway Restoration | ROW | STP | 2028-09-30 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Clinton | 120759 | SR 64 Concrete Preservation | 64 | 330 | Highway Restoration | UTL | STP | 2028-09-30 |  | 0 | 0 | 0 | 115927 | 0 | 0 | 0 | 0 | 0 | 115927
SEDA-COG | 2 | Clinton | 120759 | SR 64 Concrete Preservation | 64 | 330 | Highway Restoration | CON | 581 | 2028-09-30 |  | 0 | 0 | 0 | 2500000 | 2603049 | 0 | 0 | 0 | 0 | 5103049
SEDA-COG | 2 | Clinton | 120760 | Hogan Blvd Drainage | 150 | 329 | Highway Restoration | PE | 581 | 2027-05-30 |  | 318270 | 162530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480800
SEDA-COG | 2 | Clinton | 120760 | Hogan Blvd Drainage | 150 | 329 | Highway Restoration | CON | STP | 2027-05-30 |  | 0 | 0 | 1125509 | 0 | 0 | 0 | 0 | 0 | 0 | 1125509
SEDA-COG | 2 | Clinton | 120760 | Hogan Blvd Drainage | 150 | 329 | Highway Restoration | CON | 581 | 2027-05-30 |  | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 750000
SEDA-COG | 2 | Clinton | 120761 | Flemington Canal Brdg | 150 | A07 | Bridge Restoration | PE | BRIP | 2030-02-28 |  | 0 | 0 | 472714 | 0 | 0 | 0 | 0 | 0 | 0 | 472714
SEDA-COG | 2 | Clinton | 120761 | Flemington Canal Brdg | 150 | A07 | Bridge Restoration | FD | STP | 2030-02-28 |  | 0 | 0 | 0 | 348782 | 0 | 0 | 0 | 0 | 0 | 348782
SEDA-COG | 2 | Clinton | 120761 | Flemington Canal Brdg | 150 | A07 | Bridge Restoration | ROW | STP | 2030-02-28 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Clinton | 120761 | Flemington Canal Brdg | 150 | A07 | Bridge Restoration | UTL | STP | 2030-02-28 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Clinton | 120761 | Flemington Canal Brdg | 150 | A07 | Bridge Restoration | CON | 185 | 2030-02-28 |  | 0 | 0 | 0 | 0 | 0 | 1475849 | 0 | 0 | 0 | 1475849
SEDA-COG | 2 | Clinton | 120763 | SR 220 Concrete Preservation | 220 | 331 | Highway Restoration | PE | NHPP | 2027-09-30 |  | 0 | 302200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302200
SEDA-COG | 2 | Clinton | 120763 | SR 220 Concrete Preservation | 220 | 331 | Highway Restoration | PE | STP | 2027-09-30 |  | 141824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141824
SEDA-COG | 2 | Clinton | 120763 | SR 220 Concrete Preservation | 220 | 331 | Highway Restoration | CON | NHPP | 2027-09-30 |  | 0 | 0 | 1753084 | 0 | 0 | 0 | 0 | 0 | 0 | 1753084
SEDA-COG | 2 | Clinton | 120763 | SR 220 Concrete Preservation | 220 | 331 | Highway Restoration | CON | 581 | 2027-09-30 |  | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 750000
SEDA-COG | 2 | Clinton | 120805 | Maintenance/Betterment Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 3130677 | 2343554 | 2000000 | 0 | 0 | 0 | 0 | 0 | 7474231
SEDA-COG | 2 | Clinton | 121465 | SR 880 Pipe | 880 | A04 | Highway Restoration | PE | 581 | 2027-10-07 |  | 250000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340000
SEDA-COG | 2 | Clinton | 121645 | US 220 Bridge Epoxy Project | 220 | P65 | Bridge Preservation - State Funded | PE | STP | 2026-03-26 | 2026-03-26 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 2 | Clinton | 121645 | US 220 Bridge Epoxy Project | 220 | P65 | Bridge Preservation - State Funded | CON | NHPP | 2026-03-26 | 2026-03-26 | 0 | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000
SEDA-COG | 2 | Clinton | 121673 | SR 1016 Avis Bridge Hit RAR | 1016 | RAR | Bridge Restoration | CON | 581 | 2025-04-10 | 2025-04-10 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000
SEDA-COG | 2 | Clinton | 122200 | 2025 SEDA-COG Bridge Epoxy | 880 | EPX | Bridge Preservation - State Funded | CON | 581 | 2025-04-17 | 2025-04-17 | 290791 | 111709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402500
SEDA-COG | 2 | Clinton | 122205 | SR 477 Salona Bridge Hit RAR | 477 | RAR | Bridge Restoration | PE | 581 | 2025-06-26 | 2025-06-26 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SEDA-COG | 2 | Clinton | 122205 | SR 477 Salona Bridge Hit RAR | 477 | RAR | Bridge Restoration | CON | 581 | 2025-06-26 | 2025-06-26 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
SEDA-COG | 2 | Clinton | 122475 | SR 120 Fill Slopes | 120 | 0 | Highway Restoration | PE | PRTCT | 2026-10-01 |  | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
SEDA-COG | 2 | Clinton | 122475 | SR 120 Fill Slopes | 120 | 0 | Highway Restoration | PE | 581 | 2026-10-01 |  | 90000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000
SEDA-COG | 2 | Clinton | 122475 | SR 120 Fill Slopes | 120 | 0 | Highway Restoration | CON | PRTCT | 2026-10-01 |  | 0 | 1640000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1640000
SEDA-COG | 2 | Clinton | 122632 | 2026 Clinton HFST-Lane Departures | 120 | HFS | Safety Improvement | CON | HSIP | 2026-04-23 |  | 268886 | 382265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 651151
SEDA-COG | 2 | Clinton | 122632 | 2026 Clinton HFST-Lane Departures | 120 | HFS | Safety Improvement | CON | STP | 2026-04-23 |  | 0 | 185475 | 196790 | 0 | 0 | 0 | 0 | 0 | 0 | 382265
SEDA-COG | 2 | Clinton | 123265 | SR 220 Corridor Hwy Restoration | 220 | 335 | Highway Restoration | PE | NHPP | 2029-03-01 |  | 0 | 100000 | 345576 | 0 | 0 | 0 | 0 | 0 | 0 | 445576
SEDA-COG | 2 | Clinton | 123508 | Clinton Co SR 220 Brdg Rehab | 220 | P66 | Bridge Restoration | PE | NHPP | 2026-04-23 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SEDA-COG | 2 | Clinton | 123508 | Clinton Co SR 220 Brdg Rehab | 220 | P66 | Bridge Restoration | CON | NHPP | 2026-04-23 |  | 0 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000
SEDA-COG | 2 | Juniata | 4096 | Mahantango Creek Bridge | 2019 | A02 | Bridge Replacement | FD | BOF | 2025-12-11 | 2025-12-11 | 26106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26106
SEDA-COG | 2 | Juniata | 4096 | Mahantango Creek Bridge | 2019 | A02 | Bridge Replacement | ROW | BOF | 2025-12-11 | 2025-12-11 | 86947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86947
SEDA-COG | 2 | Juniata | 4096 | Mahantango Creek Bridge | 2019 | A02 | Bridge Replacement | UTL | BOF | 2025-12-11 | 2025-12-11 | 86947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86947
SEDA-COG | 2 | Juniata | 4096 | Mahantango Creek Bridge | 2019 | A02 | Bridge Replacement | CON | BOF | 2025-12-11 | 2025-12-11 | 0 | 1224854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1224854
SEDA-COG | 2 | Juniata | 4096 | Mahantango Creek Bridge | 2019 | A02 | Bridge Replacement | CON | STP | 2025-12-11 | 2025-12-11 | 0 | 387230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387230
SEDA-COG | 2 | Juniata | 4096 | Mahantango Creek Bridge | 2019 | A02 | Bridge Replacement | CON | 185 | 2025-12-11 | 2025-12-11 | 0 | 403021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403021
SEDA-COG | 2 | Juniata | 4160 | Stoney Run Bridge | 235 | A02 | Bridge Replacement | PE | STP | 2026-03-26 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 2 | Juniata | 4160 | Stoney Run Bridge | 235 | A02 | Bridge Replacement | FD | BRIP | 2026-03-26 |  | 0 | 240400 | 59600 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SEDA-COG | 2 | Juniata | 4160 | Stoney Run Bridge | 235 | A02 | Bridge Replacement | ROW | STP | 2026-03-26 |  | 0 | 57963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57963
SEDA-COG | 2 | Juniata | 4160 | Stoney Run Bridge | 235 | A02 | Bridge Replacement | UTL | STP | 2026-03-26 |  | 0 | 56963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56963
SEDA-COG | 2 | Juniata | 4160 | Stoney Run Bridge | 235 | A02 | Bridge Replacement | CON | BRIP | 2026-03-26 |  | 0 | 35360 | 1291011 | 0 | 0 | 0 | 0 | 0 | 0 | 1326371
SEDA-COG | 2 | Juniata | 4160 | Stoney Run Bridge | 235 | A02 | Bridge Replacement | CON | 185 | 2026-03-26 |  | 0 | 0 | 337653 | 0 | 0 | 0 | 0 | 0 | 0 | 337653
SEDA-COG | 2 | Juniata | 4190 | Bridge over NS Railroad | 75 | A03 | Bridge Replacement | FD | NHPP | 2022-05-12 | 2022-05-12 | 0 | 24704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24704
SEDA-COG | 2 | Juniata | 69423 | 2023 SEDACOG Bridge Preservation | 22 | P41 | Bridge Restoration | CON | BRIP | 2023-04-13 | 2023-04-13 | 139652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139652
SEDA-COG | 2 | Juniata | 69511 | SR 0074 over Hunters Crk | 74 | A01 | Bridge Replacement | PE | BRIP | 2032-03-30 |  | 0 | 0 | 0 | 486895 | 0 | 0 | 0 | 0 | 0 | 486895
SEDA-COG | 2 | Juniata | 69511 | SR 0074 over Hunters Crk | 74 | A01 | Bridge Replacement | FD | 581 | 2032-03-30 |  | 0 | 0 | 0 | 0 | 384486 | 0 | 0 | 0 | 0 | 384486
SEDA-COG | 2 | Juniata | 69511 | SR 0074 over Hunters Crk | 74 | A01 | Bridge Replacement | ROW | STP | 2032-03-30 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Juniata | 69511 | SR 0074 over Hunters Crk | 74 | A01 | Bridge Replacement | UTL | STP | 2032-03-30 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Juniata | 69511 | SR 0074 over Hunters Crk | 74 | A01 | Bridge Replacement | CON | BRIP | 2032-03-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 445000 | 445000 | 0 | 890000
SEDA-COG | 2 | Juniata | 69511 | SR 0074 over Hunters Crk | 74 | A01 | Bridge Replacement | CON | STP | 2032-03-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 252354 | 122416 | 0 | 374770
SEDA-COG | 2 | Juniata | 69512 | SR 0850 Little Laurel Run | 850 | A08 | Bridge Replacement | FD | BRIP | 2025-12-04 | 2025-12-04 | 50000 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000
SEDA-COG | 2 | Juniata | 69512 | SR 0850 Little Laurel Run | 850 | A08 | Bridge Replacement | ROW | STP | 2025-12-04 | 2025-12-04 | 42436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42436
SEDA-COG | 2 | Juniata | 69512 | SR 0850 Little Laurel Run | 850 | A08 | Bridge Replacement | UTL | STP | 2025-12-04 | 2025-12-04 | 63654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63654
SEDA-COG | 2 | Juniata | 69512 | SR 0850 Little Laurel Run | 850 | A08 | Bridge Replacement | CON | 185 | 2025-12-04 | 2025-12-04 | 352825 | 1031612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1384437
SEDA-COG | 2 | Juniata | 81406 | SR 35 Trib Cocolamus Crk | 35 | A17 | Bridge Restoration | PE | NHPP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 312543 | 0 | 0 | 312543
SEDA-COG | 2 | Juniata | 81406 | SR 35 Trib Cocolamus Crk | 35 | A17 | Bridge Restoration | PE | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221043 | 0 | 221043
SEDA-COG | 2 | Juniata | 81406 | SR 35 Trib Cocolamus Crk | 35 | A17 | Bridge Restoration | FD | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391432 | 0 | 391432
SEDA-COG | 2 | Juniata | 81406 | SR 35 Trib Cocolamus Crk | 35 | A17 | Bridge Restoration | ROW | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130477 | 0 | 130477
SEDA-COG | 2 | Juniata | 81406 | SR 35 Trib Cocolamus Crk | 35 | A17 | Bridge Restoration | UTL | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130477 | 0 | 130477
SEDA-COG | 2 | Juniata | 81406 | SR 35 Trib Cocolamus Crk | 35 | A17 | Bridge Restoration | CON | STP | 2033-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920518 | 0 | 1920518
SEDA-COG | 2 | Juniata | 85170 | SR 0850 over Trib. Tuscar | 850 | A10 | Bridge Replacement | FD | 185 | 2025-12-04 | 2025-12-04 | 112000 | 138000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SEDA-COG | 2 | Juniata | 85170 | SR 0850 over Trib. Tuscar | 850 | A10 | Bridge Replacement | ROW | 185 | 2025-12-04 | 2025-12-04 | 59703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Juniata | 85170 | SR 0850 over Trib. Tuscar | 850 | A10 | Bridge Replacement | UTL | 185 | 2025-12-04 | 2025-12-04 | 59703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Juniata | 85170 | SR 0850 over Trib. Tuscar | 850 | A10 | Bridge Replacement | CON | 185 | 2025-12-04 | 2025-12-04 | 350000 | 243102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 593102
SEDA-COG | 2 | Juniata | 85176 | SR 0075 over Trib Tuscarora | 75 | A14 | Bridge Restoration | PE | 185 | 2027-01-28 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 2 | Juniata | 85176 | SR 0075 over Trib Tuscarora | 75 | A14 | Bridge Restoration | FD | 185 | 2027-01-28 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SEDA-COG | 2 | Juniata | 85176 | SR 0075 over Trib Tuscarora | 75 | A14 | Bridge Restoration | ROW | 185 | 2027-01-28 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 2 | Juniata | 85176 | SR 0075 over Trib Tuscarora | 75 | A14 | Bridge Restoration | UTL | 185 | 2027-01-28 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 2 | Juniata | 85176 | SR 0075 over Trib Tuscarora | 75 | A14 | Bridge Restoration | CON | 185 | 2027-01-28 |  | 0 | 0 | 444171 | 0 | 0 | 0 | 0 | 0 | 0 | 444171
SEDA-COG | 2 | Juniata | 85178 | SR 0075 over Trib Tuscaro | 75 | A09 | Bridge Restoration | PE | 185 | 2027-01-28 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 2 | Juniata | 85178 | SR 0075 over Trib Tuscaro | 75 | A09 | Bridge Restoration | FD | 185 | 2027-01-28 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SEDA-COG | 2 | Juniata | 85178 | SR 0075 over Trib Tuscaro | 75 | A09 | Bridge Restoration | ROW | 185 | 2027-01-28 |  | 0 | 79568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79568
SEDA-COG | 2 | Juniata | 85178 | SR 0075 over Trib Tuscaro | 75 | A09 | Bridge Restoration | UTL | 185 | 2027-01-28 |  | 0 | 79568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79568
SEDA-COG | 2 | Juniata | 85178 | SR 0075 over Trib Tuscaro | 75 | A09 | Bridge Restoration | CON | 581 | 2027-01-28 |  | 0 | 0 | 592727 | 0 | 0 | 0 | 0 | 0 | 0 | 592727
SEDA-COG | 2 | Juniata | 85183 | SR 0333 over Trib Juniata BOX | 333 | A10 | Bridge Restoration | CON | 185 | 2024-10-10 | 2024-10-10 | 568649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568649
SEDA-COG | 2 | Juniata | 85188 | SR 2007 over Doe Run | 2007 | A02 | Bridge Replacement | PE | BOF | 2026-12-10 |  | 245578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245578
SEDA-COG | 2 | Juniata | 85188 | SR 2007 over Doe Run | 2007 | A02 | Bridge Replacement | FD | BOF | 2026-12-10 |  | 0 | 327818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327818
SEDA-COG | 2 | Juniata | 85188 | SR 2007 over Doe Run | 2007 | A02 | Bridge Replacement | ROW | BOF | 2026-12-10 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
SEDA-COG | 2 | Juniata | 85188 | SR 2007 over Doe Run | 2007 | A02 | Bridge Replacement | UTL | BOF | 2026-12-10 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
SEDA-COG | 2 | Juniata | 85188 | SR 2007 over Doe Run | 2007 | A02 | Bridge Replacement | CON | BOF | 2026-12-10 |  | 0 | 0 | 545132 | 300000 | 0 | 0 | 0 | 0 | 0 | 845132
SEDA-COG | 2 | Juniata | 91516 | SR 3014 Doyle Run Bridge | 3014 | A02 | Bridge Restoration | PE | BOF | 2030-03-28 |  | 0 | 0 | 472714 | 173892 | 0 | 0 | 0 | 0 | 0 | 646606
SEDA-COG | 2 | Juniata | 91516 | SR 3014 Doyle Run Bridge | 3014 | A02 | Bridge Restoration | FD | 185 | 2030-03-28 |  | 0 | 0 | 0 | 0 | 358216 | 0 | 0 | 0 | 0 | 358216
SEDA-COG | 2 | Juniata | 91516 | SR 3014 Doyle Run Bridge | 3014 | A02 | Bridge Restoration | ROW | 185 | 2030-03-28 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Juniata | 91516 | SR 3014 Doyle Run Bridge | 3014 | A02 | Bridge Restoration | UTL | 185 | 2030-03-28 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Juniata | 91516 | SR 3014 Doyle Run Bridge | 3014 | A02 | Bridge Restoration | CON | BOF | 2030-03-28 |  | 0 | 0 | 0 | 0 | 0 | 1228874 | 0 | 0 | 0 | 1228874
SEDA-COG | 2 | Juniata | 93942 | SR 235 Cranes Run Bridge | 235 | A05 | Bridge Replacement | PE | BRIP | 2029-04-30 |  | 0 | 0 | 472714 | 0 | 0 | 0 | 0 | 0 | 0 | 472714
SEDA-COG | 2 | Juniata | 93942 | SR 235 Cranes Run Bridge | 235 | A05 | Bridge Replacement | FD | BRIP | 2029-04-30 |  | 0 | 0 | 0 | 347782 | 0 | 0 | 0 | 0 | 0 | 347782
SEDA-COG | 2 | Juniata | 93942 | SR 235 Cranes Run Bridge | 235 | A05 | Bridge Replacement | ROW | BRIP | 2029-04-30 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Juniata | 93942 | SR 235 Cranes Run Bridge | 235 | A05 | Bridge Replacement | UTL | BRIP | 2029-04-30 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Juniata | 93942 | SR 235 Cranes Run Bridge | 235 | A05 | Bridge Replacement | CON | STP | 2029-04-30 |  | 0 | 0 | 0 | 0 | 1509988 | 0 | 0 | 0 | 0 | 1509988
SEDA-COG | 2 | Juniata | 100370 | Smith Rd to Snyder Co. | 35 | 913 | Highway Restoration | CON | 581 | 2031-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7613286 | 7613286
SEDA-COG | 2 | Juniata | 108876 | Group 2-25-ST9 | 35 | 0 | General Maintenance | CON | 581 | 2025-03-27 | 2025-03-27 | 376356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376356
SEDA-COG | 2 | Juniata | 109717 | SR 2003 over Doe Run II | 2003 | A03 | Bridge Restoration | PE | BOF | 2027-01-28 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SEDA-COG | 2 | Juniata | 109717 | SR 2003 over Doe Run II | 2003 | A03 | Bridge Restoration | FD | BOF | 2027-01-28 |  | 340890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340890
SEDA-COG | 2 | Juniata | 109717 | SR 2003 over Doe Run II | 2003 | A03 | Bridge Restoration | ROW | BOF | 2027-01-28 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 2 | Juniata | 109717 | SR 2003 over Doe Run II | 2003 | A03 | Bridge Restoration | UTL | BOF | 2027-01-28 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 2 | Juniata | 109717 | SR 2003 over Doe Run II | 2003 | A03 | Bridge Restoration | CON | BOF | 2027-01-28 |  | 0 | 0 | 625509 | 778108 | 0 | 0 | 0 | 0 | 0 | 1403617
SEDA-COG | 2 | Juniata | 112751 | Trib Cocolamus Creek BOX | 2010 | A03 | Bridge Restoration | PE | 185 | 2025-11-06 | 2025-11-06 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 2 | Juniata | 112751 | Trib Cocolamus Creek BOX | 2010 | A03 | Bridge Restoration | ROW | 185 | 2025-11-06 | 2025-11-06 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SEDA-COG | 2 | Juniata | 112751 | Trib Cocolamus Creek BOX | 2010 | A03 | Bridge Restoration | CON | 185 | 2025-11-06 | 2025-11-06 | 0 | 510038 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 710038
SEDA-COG | 2 | Juniata | 112752 | Trib Stony Run BOX | 2017 | A03 | Bridge Restoration | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 443370 | 0 | 0 | 443370
SEDA-COG | 2 | Juniata | 112752 | Trib Stony Run BOX | 2017 | A03 | Bridge Restoration | ROW | 185 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65239 | 0 | 65239
SEDA-COG | 2 | Juniata | 112752 | Trib Stony Run BOX | 2017 | A03 | Bridge Restoration | UTL | 185 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65239 | 0 | 65239
SEDA-COG | 2 | Juniata | 112752 | Trib Stony Run BOX | 2017 | A03 | Bridge Restoration | CON | 185 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 978580 | 0 | 978580
SEDA-COG | 2 | Juniata | 113143 | SR 3008 over Trib Tuscarora Creek | 3008 | A03 | Bridge Restoration | CON | 185 | 2024-03-28 | 2024-03-28 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SEDA-COG | 2 | Juniata | 113146 | SR 3019 over Doyle Run BOX | 3019 | A01 | Bridge Restoration | PE | 185 | 2026-10-01 |  | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000
SEDA-COG | 2 | Juniata | 113146 | SR 3019 over Doyle Run BOX | 3019 | A01 | Bridge Restoration | ROW | 185 | 2026-10-01 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
SEDA-COG | 2 | Juniata | 113146 | SR 3019 over Doyle Run BOX | 3019 | A01 | Bridge Restoration | UTL | 185 | 2026-10-01 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
SEDA-COG | 2 | Juniata | 113146 | SR 3019 over Doyle Run BOX | 3019 | A01 | Bridge Restoration | CON | 185 | 2026-10-01 |  | 0 | 0 | 944132 | 0 | 0 | 0 | 0 | 0 | 0 | 944132
SEDA-COG | 2 | Juniata | 114302 | 2024 SEDA-COG Bridge Preservation | 2006 | P44 | Bridge Restoration | CON | BOF | 2024-10-10 | 2024-10-10 | 1487522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1487522
SEDA-COG | 2 | Juniata | 114302 | 2024 SEDA-COG Bridge Preservation | 2006 | P44 | Bridge Restoration | CON | 185 | 2024-10-10 | 2024-10-10 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 2 | Juniata | 116804 | SR 333 over Delaware Creek | 333 | A11 | Bridge Restoration | PE | 581 | 2030-04-25 |  | 0 | 0 | 472713 | 0 | 0 | 0 | 0 | 0 | 0 | 472713
SEDA-COG | 2 | Juniata | 116804 | SR 333 over Delaware Creek | 333 | A11 | Bridge Restoration | FD | STP | 2030-04-25 |  | 0 | 0 | 0 | 0 | 358216 | 0 | 0 | 0 | 0 | 358216
SEDA-COG | 2 | Juniata | 116804 | SR 333 over Delaware Creek | 333 | A11 | Bridge Restoration | ROW | STP | 2030-04-25 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Juniata | 116804 | SR 333 over Delaware Creek | 333 | A11 | Bridge Restoration | UTL | STP | 2030-04-25 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Juniata | 116804 | SR 333 over Delaware Creek | 333 | A11 | Bridge Restoration | CON | BRIP | 2030-04-25 |  | 0 | 0 | 0 | 0 | 0 | 445000 | 0 | 0 | 0 | 445000
SEDA-COG | 2 | Juniata | 116804 | SR 333 over Delaware Creek | 333 | A11 | Bridge Restoration | CON | STP | 2030-04-25 |  | 0 | 0 | 0 | 0 | 0 | 1520189 | 0 | 0 | 0 | 1520189
SEDA-COG | 2 | Juniata | 116805 | SR 333 over Delaware Creek II | 333 | A12 | Bridge Restoration | PE | 185 | 2030-04-25 |  | 0 | 0 | 0 | 407040 | 0 | 0 | 0 | 0 | 0 | 407040
SEDA-COG | 2 | Juniata | 116805 | SR 333 over Delaware Creek II | 333 | A12 | Bridge Restoration | FD | STP | 2030-04-25 |  | 0 | 0 | 0 | 0 | 358216 | 0 | 0 | 0 | 0 | 358216
SEDA-COG | 2 | Juniata | 116805 | SR 333 over Delaware Creek II | 333 | A12 | Bridge Restoration | ROW | STP | 2030-04-25 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Juniata | 116805 | SR 333 over Delaware Creek II | 333 | A12 | Bridge Restoration | UTL | STP | 2030-04-25 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Juniata | 116805 | SR 333 over Delaware Creek II | 333 | A12 | Bridge Restoration | CON | STP | 2030-04-25 |  | 0 | 0 | 0 | 0 | 0 | 1844811 | 0 | 0 | 0 | 1844811
SEDA-COG | 2 | Juniata | 116886 | 2025 SEDA-COG Bridge Preservation (II) | 22 | P54 | Bridge Restoration | PE | NHPP | 2025-11-06 | 2025-11-06 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
SEDA-COG | 2 | Juniata | 116886 | 2025 SEDA-COG Bridge Preservation (II) | 22 | P54 | Bridge Restoration | CON | NHPP | 2025-11-06 | 2025-11-06 | 2420082 | 3010356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5430438
SEDA-COG | 2 | Juniata | 116886 | 2025 SEDA-COG Bridge Preservation (II) | 22 | P54 | Bridge Restoration | CON | 185 | 2025-11-06 | 2025-11-06 | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000
SEDA-COG | 2 | Juniata | 116886 | 2025 SEDA-COG Bridge Preservation (II) | 22 | P54 | Bridge Restoration | CON | 581 | 2025-11-06 | 2025-11-06 | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18750
SEDA-COG | 2 | Juniata | 116994 | Trib Tuscarora Creek BOX | 3008 | A04 | Bridge Restoration | PE | 185 | 2030-03-28 |  | 0 | 0 | 0 | 347782 | 0 | 0 | 0 | 0 | 0 | 347782
SEDA-COG | 2 | Juniata | 116994 | Trib Tuscarora Creek BOX | 3008 | A04 | Bridge Restoration | ROW | 185 | 2030-03-28 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Juniata | 116994 | Trib Tuscarora Creek BOX | 3008 | A04 | Bridge Restoration | UTL | 185 | 2030-03-28 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Juniata | 116994 | Trib Tuscarora Creek BOX | 3008 | A04 | Bridge Restoration | CON | 581 | 2030-03-28 |  | 0 | 0 | 0 | 0 | 0 | 922405 | 0 | 0 | 0 | 922405
SEDA-COG | 2 | Juniata | 116997 | Doe Run BOX | 2007 | A03 | Bridge Restoration | PE | BOF | 2031-10-30 |  | 0 | 0 | 0 | 0 | 475178 | 0 | 0 | 0 | 0 | 475178
SEDA-COG | 2 | Juniata | 116997 | Doe Run BOX | 2007 | A03 | Bridge Restoration | ROW | BOF | 2031-10-30 |  | 0 | 0 | 0 | 0 | 0 | 65239 | 0 | 0 | 0 | 65239
SEDA-COG | 2 | Juniata | 116997 | Doe Run BOX | 2007 | A03 | Bridge Restoration | UTL | BOF | 2031-10-30 |  | 0 | 0 | 0 | 0 | 0 | 65239 | 0 | 0 | 0 | 65239
SEDA-COG | 2 | Juniata | 116997 | Doe Run BOX | 2007 | A03 | Bridge Restoration | CON | BOF | 2031-10-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1346291 | 0 | 0 | 1346291
SEDA-COG | 2 | Juniata | 119410 | SR 22 Thompsontown Bridges | 22 | P63 | Bridge Restoration | FD | STP | 2024-11-07 | 2024-10-24 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
SEDA-COG | 2 | Juniata | 119410 | SR 22 Thompsontown Bridges | 22 | P63 | Bridge Restoration | CON | BRIP | 2024-11-07 | 2024-10-24 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 2 | Juniata | 119410 | SR 22 Thompsontown Bridges | 22 | P63 | Bridge Restoration | CON | STP | 2024-11-07 | 2024-10-24 | 4821961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4821961
SEDA-COG | 2 | Juniata | 119410 | SR 22 Thompsontown Bridges | 22 | P63 | Bridge Restoration | CON | 581 | 2024-11-07 | 2024-10-24 | 31250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31250
SEDA-COG | 2 | Juniata | 119418 | SR 333 HFST | 333 | HFS | Safety Improvement | CON | HSIP | 2024-06-13 | 2024-06-13 | 45395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395
SEDA-COG | 2 | Juniata | 119418 | SR 333 HFST | 333 | HFS | Safety Improvement | CON | 581 | 2024-06-13 | 2024-06-13 | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000
SEDA-COG | 2 | Juniata | 119959 | SR 22 over Lost Creek | 22 | P02 | Bridge Restoration | PE | BRIP | 2030-02-28 |  | 0 | 0 | 472714 | 0 | 0 | 0 | 0 | 0 | 0 | 472714
SEDA-COG | 2 | Juniata | 119959 | SR 22 over Lost Creek | 22 | P02 | Bridge Restoration | ROW | STP | 2030-02-28 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Juniata | 119959 | SR 22 over Lost Creek | 22 | P02 | Bridge Restoration | UTL | STP | 2030-02-28 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Juniata | 119959 | SR 22 over Lost Creek | 22 | P02 | Bridge Restoration | CON | 581 | 2030-02-28 |  | 0 | 0 | 0 | 0 | 0 | 4006718 | 1000000 | 0 | 0 | 5006718
SEDA-COG | 2 | Juniata | 119962 | SR 22 over Wagner Rd | 22 | A05 | Bridge Restoration | PE | BRIP | 2032-02-19 |  | 0 | 0 | 214385 | 258329 | 0 | 0 | 0 | 0 | 0 | 472714
SEDA-COG | 2 | Juniata | 119962 | SR 22 over Wagner Rd | 22 | A05 | Bridge Restoration | ROW | STP | 2032-02-19 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Juniata | 119962 | SR 22 over Wagner Rd | 22 | A05 | Bridge Restoration | UTL | STP | 2032-02-19 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Juniata | 119962 | SR 22 over Wagner Rd | 22 | A05 | Bridge Restoration | CON | 581 | 2032-02-19 |  | 0 | 0 | 0 | 0 | 1194052 | 0 | 0 | 0 | 0 | 1194052
SEDA-COG | 2 | Juniata | 119967 | SR 22 over T-554 Pfoutz Valley Rd | 22 | P03 | Bridge Restoration | PE | BRIP | 2028-09-30 |  | 0 | 0 | 472714 | 0 | 0 | 0 | 0 | 0 | 0 | 472714
SEDA-COG | 2 | Juniata | 119967 | SR 22 over T-554 Pfoutz Valley Rd | 22 | P03 | Bridge Restoration | ROW | STP | 2028-09-30 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Juniata | 119967 | SR 22 over T-554 Pfoutz Valley Rd | 22 | P03 | Bridge Restoration | UTL | STP | 2028-09-30 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Juniata | 119967 | SR 22 over T-554 Pfoutz Valley Rd | 22 | P03 | Bridge Restoration | CON | STP | 2028-09-30 |  | 0 | 0 | 0 | 2285792 | 0 | 0 | 0 | 0 | 0 | 2285792
SEDA-COG | 2 | Juniata | 119978 | SR 850 over Woodward Run | 850 | A11 | Bridge Replacement | PE | STP | 2030-04-25 |  | 0 | 0 | 0 | 486895 | 0 | 0 | 0 | 0 | 0 | 486895
SEDA-COG | 2 | Juniata | 119978 | SR 850 over Woodward Run | 850 | A11 | Bridge Replacement | FD | BRIP | 2030-04-25 |  | 0 | 0 | 0 | 0 | 445000 | 0 | 0 | 0 | 0 | 445000
SEDA-COG | 2 | Juniata | 119978 | SR 850 over Woodward Run | 850 | A11 | Bridge Replacement | ROW | STP | 2030-04-25 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Juniata | 119978 | SR 850 over Woodward Run | 850 | A11 | Bridge Replacement | UTL | STP | 2030-04-25 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Juniata | 119978 | SR 850 over Woodward Run | 850 | A11 | Bridge Replacement | CON | 581 | 2030-04-25 |  | 0 | 0 | 0 | 0 | 0 | 1106886 | 522203 | 0 | 0 | 1629089
SEDA-COG | 2 | Juniata | 119981 | SR 2016 Bridge Preservation | 2016 | P69 | Bridge Restoration | PE | BRIP | 2028-11-02 |  | 0 | 0 | 0 | 281718 | 0 | 0 | 0 | 0 | 0 | 281718
SEDA-COG | 2 | Juniata | 119981 | SR 2016 Bridge Preservation | 2016 | P69 | Bridge Restoration | PE | STP | 2028-11-02 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 2 | Juniata | 119981 | SR 2016 Bridge Preservation | 2016 | P69 | Bridge Restoration | FD | BOF | 2028-11-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 479031 | 0 | 0 | 479031
SEDA-COG | 2 | Juniata | 119981 | SR 2016 Bridge Preservation | 2016 | P69 | Bridge Restoration | ROW | BOF | 2028-11-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 63339 | 0 | 0 | 63339
SEDA-COG | 2 | Juniata | 119981 | SR 2016 Bridge Preservation | 2016 | P69 | Bridge Restoration | UTL | BOF | 2028-11-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 63339 | 0 | 0 | 63339
SEDA-COG | 2 | Juniata | 119981 | SR 2016 Bridge Preservation | 2016 | P69 | Bridge Restoration | CON | BOF | 2028-11-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1952000 | 0 | 1952000
SEDA-COG | 2 | Juniata | 119981 | SR 2016 Bridge Preservation | 2016 | P69 | Bridge Restoration | CON | 185 | 2028-11-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1565728 | 0 | 0 | 1565728
SEDA-COG | 2 | Juniata | 119983 | SR's 3030 & 3019 over Tuscarora Crk | 3030 | A01 | Bridge Restoration | PE | BOF | 2028-05-30 |  | 0 | 458945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458945
SEDA-COG | 2 | Juniata | 119983 | SR's 3030 & 3019 over Tuscarora Crk | 3030 | A01 | Bridge Restoration | PE | BRIP | 2028-05-30 |  | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
SEDA-COG | 2 | Juniata | 119983 | SR's 3030 & 3019 over Tuscarora Crk | 3030 | A01 | Bridge Restoration | ROW | BOF | 2028-05-30 |  | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 0 | 56275
SEDA-COG | 2 | Juniata | 119983 | SR's 3030 & 3019 over Tuscarora Crk | 3030 | A01 | Bridge Restoration | UTL | BOF | 2028-05-30 |  | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 0 | 56275
SEDA-COG | 2 | Juniata | 119983 | SR's 3030 & 3019 over Tuscarora Crk | 3030 | A01 | Bridge Restoration | CON | BOF | 2028-05-30 |  | 0 | 0 | 0 | 1243864 | 1476822 | 592648 | 0 | 0 | 0 | 3313334
SEDA-COG | 2 | Juniata | 120112 | SR 235 HFST | 235 | HFS | Safety Improvement | PE | HSIP | 2027-04-29 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SEDA-COG | 2 | Juniata | 120112 | SR 235 HFST | 235 | HFS | Safety Improvement | CON | HSIP | 2027-04-29 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 2 | Juniata | 120113 | SR 235 High Friction Surface Treatment | 235 | HFS | Safety Improvement | CON | HSIP | 2024-06-13 | 2024-06-13 | 31800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31800
SEDA-COG | 2 | Juniata | 120137 | SR 35 HFST | 35 | HFS | Safety Improvement | CON | HSIP | 2024-06-13 | 2024-06-13 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SEDA-COG | 2 | Juniata | 120682 | SR 0022 HTCMB | 22 | CMB | Safety Improvement | CON | HSIP | 2024-10-10 | 2024-10-10 | 827080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827080
SEDA-COG | 2 | Juniata | 121035 | SR 22 Juniata Resurfacing | 22 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671958 | 671958
SEDA-COG | 2 | Juniata | 121035 | SR 22 Juniata Resurfacing | 22 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7316561 | 7316561
SEDA-COG | 2 | Juniata | 121382 | US 22 Concrete Restoration (ST92) | 22 | ST9 | Highway Restoration | CON | 581 | 2024-08-08 | 2024-08-08 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
SEDA-COG | 2 | Mifflin | 4551 | SR 1002 over Honey Creek | 1002 | A01 | Bridge Replacement | FD | BRIP | 2026-12-10 |  | 0 | 300512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300512
SEDA-COG | 2 | Mifflin | 4551 | SR 1002 over Honey Creek | 1002 | A01 | Bridge Replacement | ROW | BRIP | 2026-12-10 |  | 0 | 173891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173891
SEDA-COG | 2 | Mifflin | 4551 | SR 1002 over Honey Creek | 1002 | A01 | Bridge Replacement | UTL | BRIP | 2026-12-10 |  | 0 | 86945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86945
SEDA-COG | 2 | Mifflin | 4551 | SR 1002 over Honey Creek | 1002 | A01 | Bridge Replacement | CON | 185 | 2026-12-10 |  | 0 | 0 | 1450611 | 0 | 0 | 0 | 0 | 0 | 0 | 1450611
SEDA-COG | 2 | Mifflin | 4582 | Lewistown Narrows Rehab | 22 | C05 | Highway Restoration | CON | NHPP | 2025-03-27 | 2025-03-27 | 4216800 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4416800
SEDA-COG | 2 | Mifflin | 4582 | Lewistown Narrows Rehab | 22 | C05 | Highway Restoration | CON | STP | 2025-03-27 | 2025-03-27 | 985200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985200
SEDA-COG | 2 | Mifflin | 4582 | Lewistown Narrows Rehab | 22 | C05 | Highway Restoration | CON | 581 | 2025-03-27 | 2025-03-27 | 1054200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054200
SEDA-COG | 2 | Mifflin | 69387 | Long Hollow Run Bridge | 22 | A15 | Bridge Restoration | PE | NHPP | 2024-06-13 | 2024-06-13 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490
SEDA-COG | 2 | Mifflin | 69387 | Long Hollow Run Bridge | 22 | A15 | Bridge Restoration | CON | STP | 2024-06-13 | 2024-06-13 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
SEDA-COG | 2 | Mifflin | 72767 | Lewistown to Co. Line Betterment | 522 | 719 | Highway Restoration | ROW | NHPP | 2026-05-07 |  | 0 | 109273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109273
SEDA-COG | 2 | Mifflin | 72767 | Lewistown to Co. Line Betterment | 522 | 719 | Highway Restoration | UTL | NHPP | 2026-05-07 |  | 0 | 109273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109273
SEDA-COG | 2 | Mifflin | 72767 | Lewistown to Co. Line Betterment | 522 | 719 | Highway Restoration | CON | NHPP | 2026-05-07 |  | 0 | 1840269 | 955673 | 0 | 0 | 0 | 0 | 0 | 0 | 2795942
SEDA-COG | 2 | Mifflin | 72767 | Lewistown to Co. Line Betterment | 522 | 719 | Highway Restoration | CON | 581 | 2026-05-07 |  | 0 | 775182 | 2361235 | 0 | 0 | 0 | 0 | 0 | 0 | 3136417
SEDA-COG | 2 | Mifflin | 81491 | Co. Line to Belleville | 655 | 725 | Highway Restoration | PE | 581 | 2029-09-27 |  | 0 | 0 | 0 | 477621 | 0 | 0 | 0 | 0 | 0 | 477621
SEDA-COG | 2 | Mifflin | 81491 | Co. Line to Belleville | 655 | 725 | Highway Restoration | FD | 581 | 2029-09-27 |  | 0 | 0 | 0 | 0 | 368962 | 0 | 0 | 0 | 0 | 368962
SEDA-COG | 2 | Mifflin | 81491 | Co. Line to Belleville | 655 | 725 | Highway Restoration | ROW | 581 | 2029-09-27 |  | 0 | 0 | 0 | 0 | 92241 | 0 | 0 | 0 | 0 | 92241
SEDA-COG | 2 | Mifflin | 81491 | Co. Line to Belleville | 655 | 725 | Highway Restoration | UTL | 581 | 2029-09-27 |  | 0 | 0 | 0 | 0 | 92241 | 0 | 0 | 0 | 0 | 92241
SEDA-COG | 2 | Mifflin | 81491 | Co. Line to Belleville | 655 | 725 | Highway Restoration | CON | STP | 2029-09-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3112646 | 0 | 0 | 3112646
SEDA-COG | 2 | Mifflin | 81491 | Co. Line to Belleville | 655 | 725 | Highway Restoration | CON | 581 | 2029-09-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4915849 | 0 | 0 | 4915849
SEDA-COG | 2 | Mifflin | 81528 | SR 2005 Br. Kish Creek | 2005 | A01 | Bridge Restoration | PE | 185 | 2028-01-27 |  | 318270 | 181730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SEDA-COG | 2 | Mifflin | 81528 | SR 2005 Br. Kish Creek | 2005 | A01 | Bridge Restoration | ROW | 185 | 2028-01-27 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
SEDA-COG | 2 | Mifflin | 81528 | SR 2005 Br. Kish Creek | 2005 | A01 | Bridge Restoration | UTL | 185 | 2028-01-27 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
SEDA-COG | 2 | Mifflin | 81528 | SR 2005 Br. Kish Creek | 2005 | A01 | Bridge Restoration | CON | 185 | 2028-01-27 |  | 0 | 0 | 944132 | 0 | 0 | 0 | 0 | 0 | 0 | 944132
SEDA-COG | 2 | Mifflin | 85290 | SR 0522 over Jacks Creek | 522 | A04 | Bridge Restoration | ROW | BRIP | 2024-10-24 | 2024-10-24 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
SEDA-COG | 2 | Mifflin | 85290 | SR 0522 over Jacks Creek | 522 | A04 | Bridge Restoration | UTL | BRIP | 2024-10-24 | 2024-10-24 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
SEDA-COG | 2 | Mifflin | 85290 | SR 0522 over Jacks Creek | 522 | A04 | Bridge Restoration | CON | BRIP | 2024-10-24 | 2024-10-24 | 1275740 | 841975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2117715
SEDA-COG | 2 | Mifflin | 85290 | SR 0522 over Jacks Creek | 522 | A04 | Bridge Restoration | CON | NHPP | 2024-10-24 | 2024-10-24 | 727348 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 887348
SEDA-COG | 2 | Mifflin | 85290 | SR 0522 over Jacks Creek | 522 | A04 | Bridge Restoration | CON | STP | 2024-10-24 | 2024-10-24 | 0 | 277837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277837
SEDA-COG | 2 | Mifflin | 85299 | Lewistown Bridges | 3006 | A01 | Bridge Restoration | PE | BRIP | 2027-10-21 |  | 0 | 154581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154581
SEDA-COG | 2 | Mifflin | 85299 | Lewistown Bridges | 3006 | A01 | Bridge Restoration | PE | NHPP | 2027-10-21 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SEDA-COG | 2 | Mifflin | 85299 | Lewistown Bridges | 3006 | A01 | Bridge Restoration | FD | NHPP | 2027-10-21 |  | 0 | 347782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347782
SEDA-COG | 2 | Mifflin | 85299 | Lewistown Bridges | 3006 | A01 | Bridge Restoration | ROW | NHPP | 2027-10-21 |  | 0 | 50000 | 65927 | 0 | 0 | 0 | 0 | 0 | 0 | 115927
SEDA-COG | 2 | Mifflin | 85299 | Lewistown Bridges | 3006 | A01 | Bridge Restoration | UTL | NHPP | 2027-10-21 |  | 0 | 50000 | 123891 | 0 | 0 | 0 | 0 | 0 | 0 | 173891
SEDA-COG | 2 | Mifflin | 85299 | Lewistown Bridges | 3006 | A01 | Bridge Restoration | CON | NHPP | 2027-10-21 |  | 0 | 0 | 1250000 | 1570384 | 0 | 0 | 0 | 0 | 0 | 2820384
SEDA-COG | 2 | Mifflin | 85299 | Lewistown Bridges | 3006 | A01 | Bridge Restoration | CON | 185 | 2027-10-21 |  | 0 | 0 | 504171 | 261175 | 0 | 0 | 0 | 0 | 0 | 765346
SEDA-COG | 2 | Mifflin | 85300 | Lewistown Bridge II | 3006 | A02 | Bridge Restoration | CON | NHPP | 2027-10-21 |  | 0 | 0 | 250000 | 1326456 | 0 | 0 | 0 | 0 | 0 | 1576456
SEDA-COG | 2 | Mifflin | 88202 | Kishacoquillas Creek | 3006 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 532044 | 0 | 0 | 532044
SEDA-COG | 2 | Mifflin | 88202 | Kishacoquillas Creek | 3006 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65239 | 0 | 65239
SEDA-COG | 2 | Mifflin | 88202 | Kishacoquillas Creek | 3006 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65239 | 0 | 65239
SEDA-COG | 2 | Mifflin | 88202 | Kishacoquillas Creek | 3006 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2608546 | 0 | 2608546
SEDA-COG | 2 | Mifflin | 91608 | SR 1012 Laurel Run Br | 1012 | A02 | Bridge Restoration | CON | NHPP | 2023-11-02 | 2023-11-02 | 509000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 509000
SEDA-COG | 2 | Mifflin | 95962 | T-350 over Kishacoquillas | 7209 | 0 | Bridge Replacement | CON | 183 |  |  | 350879 | 80196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431075
SEDA-COG | 2 | Mifflin | 95962 | T-350 over Kishacoquillas | 7209 | 0 | Bridge Replacement | CON | LOC |  |  | 87720 | 20049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107769
SEDA-COG | 2 | Mifflin | 95971 | T-439 ov Kishacoquillas | 7203 | BR | Bridge Replacement | ROW | BOF | 2025-12-11 | 2025-12-11 | 76800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76800
SEDA-COG | 2 | Mifflin | 95971 | T-439 ov Kishacoquillas | 7203 | BR | Bridge Replacement | ROW | LOC | 2025-12-11 | 2025-12-11 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200
SEDA-COG | 2 | Mifflin | 95971 | T-439 ov Kishacoquillas | 7203 | BR | Bridge Replacement | UTL | BOF | 2025-12-11 | 2025-12-11 | 340000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340000
SEDA-COG | 2 | Mifflin | 95971 | T-439 ov Kishacoquillas | 7203 | BR | Bridge Replacement | CON | STP | 2025-12-11 | 2025-12-11 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
SEDA-COG | 2 | Mifflin | 95971 | T-439 ov Kishacoquillas | 7203 | BR | Bridge Replacement | CON | BOF | 2025-12-11 | 2025-12-11 | 58619 | 4822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63441
SEDA-COG | 2 | Mifflin | 95971 | T-439 ov Kishacoquillas | 7203 | BR | Bridge Replacement | CON | STP | 2025-12-11 | 2025-12-11 | 288559 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 688559
SEDA-COG | 2 | Mifflin | 110175 | T-422 over Kish Creek | 7205 | REM | Bridge Removal | PE | 581 | 2028-02-17 |  | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000
SEDA-COG | 2 | Mifflin | 110175 | T-422 over Kish Creek | 7205 | REM | Bridge Removal | CON | 581 | 2028-02-17 |  | 0 | 0 | 0 | 0 | 620000 | 0 | 0 | 0 | 0 | 620000
SEDA-COG | 2 | Mifflin | 113151 | SR 2008 over Br Jacks Creek | 2008 | A02 | Bridge Restoration | FD | BOF | 2025-12-11 | 2025-12-11 | 358216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358216
SEDA-COG | 2 | Mifflin | 113151 | SR 2008 over Br Jacks Creek | 2008 | A02 | Bridge Restoration | ROW | BOF | 2025-12-11 | 2025-12-11 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SEDA-COG | 2 | Mifflin | 113151 | SR 2008 over Br Jacks Creek | 2008 | A02 | Bridge Restoration | UTL | BOF | 2025-12-11 | 2025-12-11 | 103375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103375
SEDA-COG | 2 | Mifflin | 113151 | SR 2008 over Br Jacks Creek | 2008 | A02 | Bridge Restoration | CON | BOF | 2025-12-11 | 2025-12-11 | 0 | 1294295 | 207455 | 0 | 0 | 0 | 0 | 0 | 0 | 1501750
SEDA-COG | 2 | Mifflin | 113151 | SR 2008 over Br Jacks Creek | 2008 | A02 | Bridge Restoration | CON | BRIP | 2025-12-11 | 2025-12-11 | 0 | 0 | 0 | 110447 | 0 | 0 | 0 | 0 | 0 | 110447
SEDA-COG | 2 | Mifflin | 113152 | SR 2002 over Hungry Run | 2002 | A05 | Bridge Replacement | PE | 185 | 2032-04-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 380031 | 0 | 0 | 380031
SEDA-COG | 2 | Mifflin | 113152 | SR 2002 over Hungry Run | 2002 | A05 | Bridge Replacement | CON | 185 | 2032-04-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 576538 | 728235 | 0 | 1304773
SEDA-COG | 2 | Mifflin | 113153 | SR 22 over Abandoned RR | 22 | A19 | Bridge Restoration | PE | 185 | 2030-03-30 |  | 0 | 0 | 0 | 486895 | 0 | 0 | 0 | 0 | 0 | 486895
SEDA-COG | 2 | Mifflin | 113153 | SR 22 over Abandoned RR | 22 | A19 | Bridge Restoration | FD | 185 | 2030-03-30 |  | 0 | 0 | 0 | 0 | 358216 | 0 | 0 | 0 | 0 | 358216
SEDA-COG | 2 | Mifflin | 113153 | SR 22 over Abandoned RR | 22 | A19 | Bridge Restoration | ROW | 185 | 2030-03-30 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Mifflin | 113153 | SR 22 over Abandoned RR | 22 | A19 | Bridge Restoration | UTL | 185 | 2030-03-30 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Mifflin | 113153 | SR 22 over Abandoned RR | 22 | A19 | Bridge Restoration | CON | NHPP | 2030-03-30 |  | 0 | 0 | 0 | 0 | 0 | 730874 | 500000 | 0 | 0 | 1230874
SEDA-COG | 2 | Mifflin | 113155 | SR 3017 over Trib Juniata River | 3017 | A04 | Bridge Restoration | PE | 185 | 2028-03-30 |  | 0 | 0 | 0 | 407039 | 0 | 0 | 0 | 0 | 0 | 407039
SEDA-COG | 2 | Mifflin | 113155 | SR 3017 over Trib Juniata River | 3017 | A04 | Bridge Restoration | FD | 185 | 2028-03-30 |  | 0 | 0 | 0 | 0 | 358216 | 0 | 0 | 0 | 0 | 358216
SEDA-COG | 2 | Mifflin | 113155 | SR 3017 over Trib Juniata River | 3017 | A04 | Bridge Restoration | ROW | 185 | 2028-03-30 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Mifflin | 113155 | SR 3017 over Trib Juniata River | 3017 | A04 | Bridge Restoration | UTL | 185 | 2028-03-30 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Mifflin | 113155 | SR 3017 over Trib Juniata River | 3017 | A04 | Bridge Restoration | CON | 185 | 2028-03-30 |  | 0 | 0 | 0 | 0 | 0 | 1239529 | 0 | 0 | 0 | 1239529
SEDA-COG | 2 | Mifflin | 114010 | SR 522 Betterment | 522 | 723 | Highway Restoration | CON | NHPP | 2023-12-14 | 2023-12-14 | 11452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11452
SEDA-COG | 2 | Mifflin | 114010 | SR 522 Betterment | 522 | 723 | Highway Restoration | CON | STP | 2023-12-14 | 2023-12-14 | 242948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242948
SEDA-COG | 2 | Mifflin | 114048 | Kish Pike RR Device Install | 2007 | R21 | Rail Highway Grade Crossing | CON | RRX | 2024-03-05 | 2024-03-05 | 625000 | 463000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088000
SEDA-COG | 2 | Mifflin | 114303 | 2025 SEDA-COG Bridge Preservation | 2004 | P45 | Bridge Restoration | PE | BRIP | 2026-09-17 |  | 510578 | 48422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 559000
SEDA-COG | 2 | Mifflin | 114303 | 2025 SEDA-COG Bridge Preservation | 2004 | P45 | Bridge Restoration | PE | STP | 2026-09-17 |  | 152422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152422
SEDA-COG | 2 | Mifflin | 114303 | 2025 SEDA-COG Bridge Preservation | 2004 | P45 | Bridge Restoration | FD | BRIP | 2026-09-17 |  | 0 | 553000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553000
SEDA-COG | 2 | Mifflin | 114303 | 2025 SEDA-COG Bridge Preservation | 2004 | P45 | Bridge Restoration | ROW | BRIP | 2026-09-17 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
SEDA-COG | 2 | Mifflin | 114303 | 2025 SEDA-COG Bridge Preservation | 2004 | P45 | Bridge Restoration | UTL | BRIP | 2026-09-17 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
SEDA-COG | 2 | Mifflin | 114303 | 2025 SEDA-COG Bridge Preservation | 2004 | P45 | Bridge Restoration | CON | BRIP | 2026-09-17 |  | 0 | 1246724 | 716078 | 0 | 0 | 0 | 0 | 0 | 0 | 1962802
SEDA-COG | 2 | Mifflin | 114303 | 2025 SEDA-COG Bridge Preservation | 2004 | P45 | Bridge Restoration | CON | STP | 2026-09-17 |  | 0 | 950618 | 286580 | 0 | 0 | 0 | 0 | 0 | 0 | 1237198
SEDA-COG | 2 | Mifflin | 114303 | 2025 SEDA-COG Bridge Preservation | 2004 | P45 | Bridge Restoration | CON | 581 | 2026-09-17 |  | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SEDA-COG | 2 | Mifflin | 116799 | SR 22 over Wakefield Run | 22 | A20 | Bridge Restoration | PE | 185 | 2030-02-28 |  | 0 | 0 | 0 | 405746 | 0 | 0 | 0 | 0 | 0 | 405746
SEDA-COG | 2 | Mifflin | 116799 | SR 22 over Wakefield Run | 22 | A20 | Bridge Restoration | ROW | 185 | 2030-02-28 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Mifflin | 116799 | SR 22 over Wakefield Run | 22 | A20 | Bridge Restoration | UTL | 185 | 2030-02-28 |  | 0 | 0 | 0 | 0 | 59703 | 0 | 0 | 0 | 0 | 59703
SEDA-COG | 2 | Mifflin | 116799 | SR 22 over Wakefield Run | 22 | A20 | Bridge Restoration | CON | NHPP | 2030-02-28 |  | 0 | 0 | 0 | 0 | 0 | 909126 | 320748 | 0 | 0 | 1229874
SEDA-COG | 2 | Mifflin | 116889 | 2027 SEDA-COG Bridge Preservation | 4013 | P56 | Bridge Restoration | PE | BOF | 2028-02-17 |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
SEDA-COG | 2 | Mifflin | 116889 | 2027 SEDA-COG Bridge Preservation | 4013 | P56 | Bridge Restoration | CON | BOF | 2028-02-17 |  | 0 | 0 | 1368640 | 599000 | 0 | 0 | 0 | 0 | 0 | 1967640
SEDA-COG | 2 | Mifflin | 116986 | Tributary Jacks Creek BOX | 2004 | A04 | Bridge Restoration | CON | 185 | 2024-10-24 | 2024-10-24 | 718544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 718544
SEDA-COG | 2 | Mifflin | 117782 | Walnut St RR Device Install | 522 | R27 | Rail Highway Grade Crossing | CON | RRX | 2024-03-05 | 2024-03-05 | 0 | 157000 | 183000 | 0 | 0 | 0 | 0 | 0 | 0 | 340000
SEDA-COG | 2 | Mifflin | 118529 | SR 322 Twin Bridges HFST | 322 | HFS | Safety Improvement | CON | NHPP | 2023-04-27 | 2023-04-27 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SEDA-COG | 2 | Mifflin | 119464 | Delaware Ave RR Warning Device | 103 | R27 | Rail Highway Grade Crossing | CON | RRX | 2024-03-05 | 2024-03-05 | 0 | 70000 | 117000 | 179000 | 0 | 0 | 0 | 0 | 0 | 366000
SEDA-COG | 2 | Mifflin | 119778 | SR 1002 Honey Creek Rd Slide Restoration | 1002 | 726 | Highway Restoration | FD | PRTCT | 2027-02-11 |  | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SEDA-COG | 2 | Mifflin | 119778 | SR 1002 Honey Creek Rd Slide Restoration | 1002 | 726 | Highway Restoration | ROW | STR | 2027-02-11 |  | 0 | 82400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82400
SEDA-COG | 2 | Mifflin | 119778 | SR 1002 Honey Creek Rd Slide Restoration | 1002 | 726 | Highway Restoration | UTL | STR | 2027-02-11 |  | 0 | 82400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82400
SEDA-COG | 2 | Mifflin | 119778 | SR 1002 Honey Creek Rd Slide Restoration | 1002 | 726 | Highway Restoration | CON | PRTCT | 2027-02-11 |  | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
SEDA-COG | 2 | Mifflin | 119778 | SR 1002 Honey Creek Rd Slide Restoration | 1002 | 726 | Highway Restoration | CON | STR | 2027-02-11 |  | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SEDA-COG | 2 | Mifflin | 119985 | SR 22 over Carters Run II | 22 | A21 | Bridge Replacement | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 516547 | 0 | 0 | 0 | 516547
SEDA-COG | 2 | Mifflin | 119985 | SR 22 over Carters Run II | 22 | A21 | Bridge Replacement | FD | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 380031 | 0 | 0 | 380031
SEDA-COG | 2 | Mifflin | 119985 | SR 22 over Carters Run II | 22 | A21 | Bridge Replacement | ROW | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 63339 | 0 | 0 | 63339
SEDA-COG | 2 | Mifflin | 119985 | SR 22 over Carters Run II | 22 | A21 | Bridge Replacement | UTL | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 63339 | 0 | 0 | 63339
SEDA-COG | 2 | Mifflin | 119985 | SR 22 over Carters Run II | 22 | A21 | Bridge Replacement | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1640000 | 0 | 1640000
SEDA-COG | 2 | Mifflin | 119985 | SR 22 over Carters Run II | 22 | A21 | Bridge Replacement | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448637 | 0 | 448637
SEDA-COG | 2 | Mifflin | 119987 | SR 22 over Beaver Dam Run | 22 | A06 | Bridge Replacement | PE | BRIP | 2029-04-26 |  | 0 | 0 | 472714 | 0 | 0 | 0 | 0 | 0 | 0 | 472714
SEDA-COG | 2 | Mifflin | 119987 | SR 22 over Beaver Dam Run | 22 | A06 | Bridge Replacement | FD | NHPP | 2029-04-26 |  | 0 | 0 | 0 | 371486 | 0 | 0 | 0 | 0 | 0 | 371486
SEDA-COG | 2 | Mifflin | 119987 | SR 22 over Beaver Dam Run | 22 | A06 | Bridge Replacement | ROW | BRIP | 2029-04-26 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Mifflin | 119987 | SR 22 over Beaver Dam Run | 22 | A06 | Bridge Replacement | UTL | BRIP | 2029-04-26 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Mifflin | 119987 | SR 22 over Beaver Dam Run | 22 | A06 | Bridge Replacement | CON | 185 | 2029-04-26 |  | 0 | 0 | 0 | 254812 | 1910484 | 0 | 0 | 0 | 0 | 2165296
SEDA-COG | 2 | Mifflin | 119993 | SR 322 EB over Branch Laurel Creek | 322 | A06 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 380031 | 0 | 0 | 380031
SEDA-COG | 2 | Mifflin | 119993 | SR 322 EB over Branch Laurel Creek | 322 | A06 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 429487 | 0 | 0 | 429487
SEDA-COG | 2 | Mifflin | 119993 | SR 322 EB over Branch Laurel Creek | 322 | A06 | Bridge Replacement | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1247082 | 0 | 1247082
SEDA-COG | 2 | Mifflin | 119994 | SR 655 over Kishacoquillas Crk | 655 | A07 | Bridge Replacement | PE | 185 | 2029-03-29 |  | 0 | 0 | 337653 | 0 | 0 | 0 | 0 | 0 | 0 | 337653
SEDA-COG | 2 | Mifflin | 119994 | SR 655 over Kishacoquillas Crk | 655 | A07 | Bridge Replacement | ROW | 185 | 2029-03-29 |  | 0 | 0 | 0 | 57963 | 0 | 0 | 0 | 0 | 0 | 57963
SEDA-COG | 2 | Mifflin | 119994 | SR 655 over Kishacoquillas Crk | 655 | A07 | Bridge Replacement | UTL | 185 | 2029-03-29 |  | 0 | 0 | 0 | 57963 | 0 | 0 | 0 | 0 | 0 | 57963
SEDA-COG | 2 | Mifflin | 119994 | SR 655 over Kishacoquillas Crk | 655 | A07 | Bridge Replacement | CON | 185 | 2029-03-29 |  | 0 | 0 | 0 | 0 | 895539 | 0 | 0 | 0 | 0 | 895539
SEDA-COG | 2 | Mifflin | 119996 | SR 3006 over Jacks Creek | 3006 | A03 | Bridge Restoration | PE | BRIP | 2027-06-24 |  | 393945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393945
SEDA-COG | 2 | Mifflin | 119996 | SR 3006 over Jacks Creek | 3006 | A03 | Bridge Restoration | FD | NHPP | 2027-06-24 |  | 0 | 347782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347782
SEDA-COG | 2 | Mifflin | 119996 | SR 3006 over Jacks Creek | 3006 | A03 | Bridge Restoration | ROW | NHPP | 2027-06-24 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
SEDA-COG | 2 | Mifflin | 119996 | SR 3006 over Jacks Creek | 3006 | A03 | Bridge Restoration | UTL | NHPP | 2027-06-24 |  | 0 | 54636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54636
SEDA-COG | 2 | Mifflin | 119996 | SR 3006 over Jacks Creek | 3006 | A03 | Bridge Restoration | CON | NHPP | 2027-06-24 |  | 0 | 0 | 1151425 | 2000000 | 0 | 0 | 0 | 0 | 0 | 3151425
SEDA-COG | 2 | Mifflin | 119996 | SR 3006 over Jacks Creek | 3006 | A03 | Bridge Restoration | CON | 185 | 2027-06-24 |  | 0 | 0 | 487856 | 300000 | 0 | 0 | 0 | 0 | 0 | 787856
SEDA-COG | 2 | Mifflin | 120767 | SR 2008 over Brower Run BOX | 2008 | A03 | Bridge Restoration | PE | 185 | 2026-10-01 |  | 0 | 327818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327818
SEDA-COG | 2 | Mifflin | 120767 | SR 2008 over Brower Run BOX | 2008 | A03 | Bridge Restoration | ROW | 581 | 2026-10-01 |  | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 0 | 56275
SEDA-COG | 2 | Mifflin | 120767 | SR 2008 over Brower Run BOX | 2008 | A03 | Bridge Restoration | UTL | 581 | 2026-10-01 |  | 0 | 0 | 56275 | 0 | 0 | 0 | 0 | 0 | 0 | 56275
SEDA-COG | 2 | Mifflin | 120767 | SR 2008 over Brower Run BOX | 2008 | A03 | Bridge Restoration | CON | 185 | 2026-10-01 |  | 0 | 0 | 0 | 869456 | 0 | 0 | 0 | 0 | 0 | 869456
SEDA-COG | 2 | Mifflin | 120795 | SR 22 over Musser Run | 22 | A07 | Bridge Restoration | PE | BRIP | 2030-04-25 |  | 0 | 0 | 472714 | 0 | 0 | 0 | 0 | 0 | 0 | 472714
SEDA-COG | 2 | Mifflin | 120795 | SR 22 over Musser Run | 22 | A07 | Bridge Restoration | FD | BRIP | 2030-04-25 |  | 0 | 0 | 0 | 347782 | 0 | 0 | 0 | 0 | 0 | 347782
SEDA-COG | 2 | Mifflin | 120795 | SR 22 over Musser Run | 22 | A07 | Bridge Restoration | ROW | BRIP | 2030-04-25 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Mifflin | 120795 | SR 22 over Musser Run | 22 | A07 | Bridge Restoration | UTL | BRIP | 2030-04-25 |  | 0 | 0 | 0 | 57964 | 0 | 0 | 0 | 0 | 0 | 57964
SEDA-COG | 2 | Mifflin | 120795 | SR 22 over Musser Run | 22 | A07 | Bridge Restoration | CON | NHPP | 2030-04-25 |  | 0 | 0 | 0 | 0 | 1520594 | 0 | 0 | 0 | 0 | 1520594
SEDA-COG | 2 | Mifflin | 121033 | SR 3002/Bus 22 Resurfacing | 3002 | 728 | Highway Restoration | CON | STP | 2031-03-13 |  | 0 | 0 | 1794407 | 0 | 0 | 0 | 0 | 0 | 0 | 1794407
SEDA-COG | 2 | Mifflin | 121033 | SR 3002/Bus 22 Resurfacing | 3002 | 728 | Highway Restoration | CON | 581 | 2031-03-13 |  | 0 | 0 | 526018 | 629379 | 0 | 0 | 0 | 0 | 0 | 1155397
SEDA-COG | 2 | Mifflin | 122303 | Group 2-25-ST72 | 8008 | ST7 | Highway Restoration | PE | 581 | 2025-06-05 | 2025-06-05 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 2 | Mifflin | 122303 | Group 2-25-ST72 | 8008 | ST7 | Highway Restoration | CON | 581 | 2025-06-05 | 2025-06-05 | 500000 | 28486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 528486
SEDA-COG | 2 | Mifflin | 122474 | Mann's Narrows Wall/Rock Slide | 322 | 727 | Highway Restoration | PE | PRTCT | 2026-10-01 |  | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
SEDA-COG | 2 | Mifflin | 122474 | Mann's Narrows Wall/Rock Slide | 322 | 727 | Highway Restoration | PE | STP | 2026-10-01 |  | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000
SEDA-COG | 2 | Mifflin | 122474 | Mann's Narrows Wall/Rock Slide | 322 | 727 | Highway Restoration | PE | 581 | 2026-10-01 |  | 102000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102000
SEDA-COG | 2 | Mifflin | 122474 | Mann's Narrows Wall/Rock Slide | 322 | 727 | Highway Restoration | ROW | PRTCT | 2026-10-01 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SEDA-COG | 2 | Mifflin | 122474 | Mann's Narrows Wall/Rock Slide | 322 | 727 | Highway Restoration | CON | PRTCT | 2026-10-01 |  | 0 | 2770000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2770000
SEDA-COG | 3 | Columbia | 5375 | T-373 over Roaring Creek Co Br #11 |  | LBR | Bridge Restoration | FD | BOF | 2027-03-11 |  | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
SEDA-COG | 3 | Columbia | 5375 | T-373 over Roaring Creek Co Br #11 |  | LBR | Bridge Restoration | FD | 183 | 2027-03-11 |  | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Columbia | 5375 | T-373 over Roaring Creek Co Br #11 |  | LBR | Bridge Restoration | FD | LOC | 2027-03-11 |  | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SEDA-COG | 3 | Columbia | 5375 | T-373 over Roaring Creek Co Br #11 |  | LBR | Bridge Restoration | ROW | BOF | 2027-03-11 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SEDA-COG | 3 | Columbia | 5375 | T-373 over Roaring Creek Co Br #11 |  | LBR | Bridge Restoration | ROW | 183 | 2027-03-11 |  | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
SEDA-COG | 3 | Columbia | 5375 | T-373 over Roaring Creek Co Br #11 |  | LBR | Bridge Restoration | ROW | LOC | 2027-03-11 |  | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250
SEDA-COG | 3 | Columbia | 5375 | T-373 over Roaring Creek Co Br #11 |  | LBR | Bridge Restoration | UTL | BOF | 2027-03-11 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
SEDA-COG | 3 | Columbia | 5375 | T-373 over Roaring Creek Co Br #11 |  | LBR | Bridge Restoration | UTL | 183 | 2027-03-11 |  | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
SEDA-COG | 3 | Columbia | 5375 | T-373 over Roaring Creek Co Br #11 |  | LBR | Bridge Restoration | UTL | LOC | 2027-03-11 |  | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
SEDA-COG | 3 | Columbia | 5375 | T-373 over Roaring Creek Co Br #11 |  | LBR | Bridge Restoration | CON | BOF | 2027-03-11 |  | 0 | 0 | 560000 | 1440000 | 0 | 0 | 0 | 0 | 0 | 2000000
SEDA-COG | 3 | Columbia | 5375 | T-373 over Roaring Creek Co Br #11 |  | LBR | Bridge Restoration | CON | 183 | 2027-03-11 |  | 0 | 0 | 105000 | 270000 | 0 | 0 | 0 | 0 | 0 | 375000
SEDA-COG | 3 | Columbia | 5375 | T-373 over Roaring Creek Co Br #11 |  | LBR | Bridge Restoration | CON | LOC | 2027-03-11 |  | 0 | 0 | 35000 | 90000 | 0 | 0 | 0 | 0 | 0 | 125000
SEDA-COG | 3 | Columbia | 5382 | SR 1004 over Kinney Run | 1004 | 012 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 110000 | 110000 | 0 | 0 | 0 | 220000
SEDA-COG | 3 | Columbia | 5382 | SR 1004 over Kinney Run | 1004 | 012 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | 0 | 0 | 130000
SEDA-COG | 3 | Columbia | 5382 | SR 1004 over Kinney Run | 1004 | 012 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 40000
SEDA-COG | 3 | Columbia | 5382 | SR 1004 over Kinney Run | 1004 | 012 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 250000
SEDA-COG | 3 | Columbia | 5382 | SR 1004 over Kinney Run | 1004 | 012 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 500000
SEDA-COG | 3 | Columbia | 5569 | T-367 over Catawissa Creek |  | LBR | Bridge Replacement | STUDY | BOF | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 120000
SEDA-COG | 3 | Columbia | 5569 | T-367 over Catawissa Creek |  | LBR | Bridge Replacement | STUDY | 183 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 22500 | 0 | 0 | 0 | 22500
SEDA-COG | 3 | Columbia | 5569 | T-367 over Catawissa Creek |  | LBR | Bridge Replacement | PE | BOF | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 0 | 400000
SEDA-COG | 3 | Columbia | 5569 | T-367 over Catawissa Creek |  | LBR | Bridge Replacement | PE | 183 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 75000
SEDA-COG | 3 | Columbia | 5569 | T-367 over Catawissa Creek |  | LBR | Bridge Replacement | FD | BOF | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 280000
SEDA-COG | 3 | Columbia | 5569 | T-367 over Catawissa Creek |  | LBR | Bridge Replacement | FD | 183 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52500 | 52500
SEDA-COG | 3 | Columbia | 5569 | T-367 over Catawissa Creek |  | LBR | Bridge Replacement | ROW | BOF | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Columbia | 5569 | T-367 over Catawissa Creek |  | LBR | Bridge Replacement | ROW | 183 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500
SEDA-COG | 3 | Columbia | 5569 | T-367 over Catawissa Creek |  | LBR | Bridge Replacement | UTL | BOF | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Columbia | 5569 | T-367 over Catawissa Creek |  | LBR | Bridge Replacement | UTL | 183 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500
SEDA-COG | 3 | Columbia | 5569 | T-367 over Catawissa Creek |  | LBR | Bridge Replacement | CON | BOF | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 2200000
SEDA-COG | 3 | Columbia | 5569 | T-367 over Catawissa Creek |  | LBR | Bridge Replacement | CON | 183 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412500 | 412500
SEDA-COG | 3 | Columbia | 5571 | T-628 over Scotch Run |  | LBR | Bridge Replacement | PE | BOF | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SEDA-COG | 3 | Columbia | 5571 | T-628 over Scotch Run |  | LBR | Bridge Replacement | PE | 183 | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
SEDA-COG | 3 | Columbia | 5571 | T-628 over Scotch Run |  | LBR | Bridge Replacement | FD | BOF | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 280000
SEDA-COG | 3 | Columbia | 5571 | T-628 over Scotch Run |  | LBR | Bridge Replacement | FD | 183 | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52500 | 52500
SEDA-COG | 3 | Columbia | 5571 | T-628 over Scotch Run |  | LBR | Bridge Replacement | ROW | BOF | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Columbia | 5571 | T-628 over Scotch Run |  | LBR | Bridge Replacement | ROW | 183 | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500
SEDA-COG | 3 | Columbia | 5571 | T-628 over Scotch Run |  | LBR | Bridge Replacement | UTL | BOF | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Columbia | 5571 | T-628 over Scotch Run |  | LBR | Bridge Replacement | UTL | 183 | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500
SEDA-COG | 3 | Columbia | 5571 | T-628 over Scotch Run |  | LBR | Bridge Replacement | CON | BOF | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 1056000
SEDA-COG | 3 | Columbia | 5571 | T-628 over Scotch Run |  | LBR | Bridge Replacement | CON | 183 | 2035-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198000 | 198000
SEDA-COG | 3 | Columbia | 5584 | SR 2009 over Tributary to Catawissa Creek | 2009 | 001 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 200000 | 500000
SEDA-COG | 3 | Columbia | 5584 | SR 2009 over Tributary to Catawissa Creek | 2009 | 001 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 375000
SEDA-COG | 3 | Columbia | 5584 | SR 2009 over Tributary to Catawissa Creek | 2009 | 001 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000
SEDA-COG | 3 | Columbia | 5584 | SR 2009 over Tributary to Catawissa Creek | 2009 | 001 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000
SEDA-COG | 3 | Columbia | 5584 | SR 2009 over Tributary to Catawissa Creek | 2009 | 001 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1930000 | 1930000
SEDA-COG | 3 | Columbia | 5621 | SR 1022 ov Fishing Creek | 1022 | 027 | Bridge Restoration | PE | STP | 2031-09-01 |  | 0 | 0 | 0 | 0 | 140000 | 120000 | 0 | 0 | 0 | 260000
SEDA-COG | 3 | Columbia | 5621 | SR 1022 ov Fishing Creek | 1022 | 027 | Bridge Restoration | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 250000
SEDA-COG | 3 | Columbia | 5621 | SR 1022 ov Fishing Creek | 1022 | 027 | Bridge Restoration | ROW | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 35000
SEDA-COG | 3 | Columbia | 5621 | SR 1022 ov Fishing Creek | 1022 | 027 | Bridge Restoration | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SEDA-COG | 3 | Columbia | 5621 | SR 1022 ov Fishing Creek | 1022 | 027 | Bridge Restoration | CON | STP | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 350000 | 1750000
SEDA-COG | 3 | Columbia | 5622 | SR 1022 over Old Channel | 1022 | 012 | Bridge Restoration | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 310000 | 0 | 0 | 0 | 0 | 310000
SEDA-COG | 3 | Columbia | 5622 | SR 1022 over Old Channel | 1022 | 012 | Bridge Restoration | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 250000
SEDA-COG | 3 | Columbia | 5622 | SR 1022 over Old Channel | 1022 | 012 | Bridge Restoration | ROW | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 35000
SEDA-COG | 3 | Columbia | 5622 | SR 1022 over Old Channel | 1022 | 012 | Bridge Restoration | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SEDA-COG | 3 | Columbia | 5622 | SR 1022 over Old Channel | 1022 | 012 | Bridge Restoration | CON | STP | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 950000 | 1900000
SEDA-COG | 3 | Columbia | 68016 | 3-0 SEDA-COG Line Item |  | 000 | Reserve Line Item | CON | BOF |  |  | 0 | 40000 | 153493 | 1176000 | 3000000 | 3000000 | 3000000 | 3000000 | 12115000 | 25484493
SEDA-COG | 3 | Columbia | 68016 | 3-0 SEDA-COG Line Item |  | 000 | Reserve Line Item | CON | BRIP |  |  | 0 | 40500 | 36000 | 6204000 | 8114000 | 8114000 | 8114000 | 8114000 | 32456000 | 71192500
SEDA-COG | 3 | Columbia | 68016 | 3-0 SEDA-COG Line Item |  | 000 | Reserve Line Item | CON | CRP |  |  | 0 | 24000 | 1095000 | 1095000 | 1095000 | 1095000 | 1095000 | 1095000 | 4381000 | 10975000
SEDA-COG | 3 | Columbia | 68016 | 3-0 SEDA-COG Line Item |  | 000 | Reserve Line Item | CON | HSIP |  |  | 0 | 0 | 5800 | 5800 | 201800 | 1396800 | 1396800 | 1396800 | 5586000 | 9989800
SEDA-COG | 3 | Columbia | 68016 | 3-0 SEDA-COG Line Item |  | 000 | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 702000 | 928500 | 0 | 0 | 0 | 1462000 | 1996000 | 5088500
SEDA-COG | 3 | Columbia | 68016 | 3-0 SEDA-COG Line Item |  | 000 | Reserve Line Item | CON | STP |  |  | 0 | 833000 | 157000 | 500 | 0 | 0 | 0 | 0 | 0 | 990500
SEDA-COG | 3 | Columbia | 68016 | 3-0 SEDA-COG Line Item |  | 000 | Reserve Line Item | CON | 185 |  |  | 0 | 250 | 540000 | 10000 | 0 | 0 | 0 | 0 | 684250 | 1234500
SEDA-COG | 3 | Columbia | 68016 | 3-0 SEDA-COG Line Item |  | 000 | Reserve Line Item | CON | 581 |  |  | 0 | 779000 | 698253 | 576012 | 0 | 0 | 0 | 0 | 1550000 | 3603265
SEDA-COG | 3 | Columbia | 82774 | SR 1020 over Pine Creek | 1020 | 006 | Bridge Restoration | FD | 185 | 2025-10-23 | 2025-10-23 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
SEDA-COG | 3 | Columbia | 82774 | SR 1020 over Pine Creek | 1020 | 006 | Bridge Restoration | ROW | 185 | 2025-10-23 | 2025-10-23 | 37150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37150
SEDA-COG | 3 | Columbia | 82774 | SR 1020 over Pine Creek | 1020 | 006 | Bridge Restoration | CON | BOF | 2025-10-23 | 2025-10-23 | 1742000 | 0 | 233000 | 0 | 0 | 0 | 0 | 0 | 0 | 1975000
SEDA-COG | 3 | Columbia | 88034 | SR 2005 over Roaring Creek | 2005 | 005 | Bridge Restoration | PE | BRIP | 2028-09-01 |  | 0 | 288000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288000
SEDA-COG | 3 | Columbia | 88034 | SR 2005 over Roaring Creek | 2005 | 005 | Bridge Restoration | FD | 185 | 2028-09-01 |  | 0 | 0 | 200000 | 75000 | 0 | 0 | 0 | 0 | 0 | 275000
SEDA-COG | 3 | Columbia | 88034 | SR 2005 over Roaring Creek | 2005 | 005 | Bridge Restoration | ROW | 185 | 2028-09-01 |  | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
SEDA-COG | 3 | Columbia | 88034 | SR 2005 over Roaring Creek | 2005 | 005 | Bridge Restoration | UTL | 185 | 2028-09-01 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Columbia | 88034 | SR 2005 over Roaring Creek | 2005 | 005 | Bridge Restoration | CON | 185 | 2028-09-01 |  | 0 | 0 | 0 | 1565000 | 585000 | 0 | 0 | 0 | 0 | 2150000
SEDA-COG | 3 | Columbia | 88051 | SR 1020 over Fishing Creek | 1020 | 008 | Bridge Restoration | CON | 185 | 2024-09-12 | 2024-09-12 | 1885000 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
SEDA-COG | 3 | Columbia | 88777 | SR 4008 ov Tb Fishing Crk | 4008 | 006 | Bridge Replacement | PE | 185 | 2028-09-14 |  | 0 | 75000 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SEDA-COG | 3 | Columbia | 88777 | SR 4008 ov Tb Fishing Crk | 4008 | 006 | Bridge Replacement | FD | 185 | 2028-09-14 |  | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Columbia | 88777 | SR 4008 ov Tb Fishing Crk | 4008 | 006 | Bridge Replacement | ROW | 185 | 2028-09-14 |  | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 35000
SEDA-COG | 3 | Columbia | 88777 | SR 4008 ov Tb Fishing Crk | 4008 | 006 | Bridge Replacement | UTL | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SEDA-COG | 3 | Columbia | 88777 | SR 4008 ov Tb Fishing Crk | 4008 | 006 | Bridge Replacement | CON | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 375000 | 125000 | 0 | 0 | 0 | 500000
SEDA-COG | 3 | Columbia | 93643 | SR 1001 over Tributary to Susquehanna River | 1001 | 012 | Bridge Replacement | PE | 185 | 2027-09-16 |  | 50000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SEDA-COG | 3 | Columbia | 93643 | SR 1001 over Tributary to Susquehanna River | 1001 | 012 | Bridge Replacement | FD | 185 | 2027-09-16 |  | 0 | 75000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
SEDA-COG | 3 | Columbia | 93643 | SR 1001 over Tributary to Susquehanna River | 1001 | 012 | Bridge Replacement | ROW | 185 | 2027-09-16 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Columbia | 93643 | SR 1001 over Tributary to Susquehanna River | 1001 | 012 | Bridge Replacement | UTL | 185 | 2027-09-16 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SEDA-COG | 3 | Columbia | 93643 | SR 1001 over Tributary to Susquehanna River | 1001 | 012 | Bridge Replacement | CON | 185 | 2027-09-16 |  | 0 | 0 | 0 | 475000 | 75000 | 0 | 0 | 0 | 0 | 550000
SEDA-COG | 3 | Columbia | 94321 | SR 239 over West Branch of West Creek | 239 | 020 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 250000 | 200000 | 0 | 0 | 0 | 450000
SEDA-COG | 3 | Columbia | 94321 | SR 239 over West Branch of West Creek | 239 | 020 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 500000
SEDA-COG | 3 | Columbia | 94321 | SR 239 over West Branch of West Creek | 239 | 020 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000
SEDA-COG | 3 | Columbia | 94321 | SR 239 over West Branch of West Creek | 239 | 020 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
SEDA-COG | 3 | Columbia | 94321 | SR 239 over West Branch of West Creek | 239 | 020 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 1800000
SEDA-COG | 3 | Columbia | 97553 | I-80 WB Montour Co to Millville Rd (SR 4009) | 80 | 128 | Highway Restoration | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000
SEDA-COG | 3 | Columbia | 97553 | I-80 WB Montour Co to Millville Rd (SR 4009) | 80 | 128 | Highway Restoration | CON | NHPP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000
SEDA-COG | 3 | Columbia | 97622 | SR 118 over East and West Branch Fishing Creek | 118 | 018 | Bridge Restoration | PE | 185 | 2032-09-01 |  | 0 | 0 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
SEDA-COG | 3 | Columbia | 97622 | SR 118 over East and West Branch Fishing Creek | 118 | 018 | Bridge Restoration | FD | STP | 2032-09-01 |  | 0 | 0 | 0 | 100000 | 400000 | 0 | 0 | 0 | 0 | 500000
SEDA-COG | 3 | Columbia | 97622 | SR 118 over East and West Branch Fishing Creek | 118 | 018 | Bridge Restoration | ROW | STP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 80000
SEDA-COG | 3 | Columbia | 97622 | SR 118 over East and West Branch Fishing Creek | 118 | 018 | Bridge Restoration | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
SEDA-COG | 3 | Columbia | 97622 | SR 118 over East and West Branch Fishing Creek | 118 | 018 | Bridge Restoration | CON | STP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 350000 | 1600000 | 0 | 0 | 1950000
SEDA-COG | 3 | Columbia | 97622 | SR 118 over East and West Branch Fishing Creek | 118 | 018 | Bridge Restoration | CON | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 1300000 | 2250000 | 2217250 | 280750 | 6048000
SEDA-COG | 3 | Columbia | 97648 | US 11 Signals Berwick Boro | 11 | 116 | Safety Improvement | PE | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 0 | 0 | 400000
SEDA-COG | 3 | Columbia | 97648 | US 11 Signals Berwick Boro | 11 | 116 | Safety Improvement | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 143000 | 107000 | 0 | 250000
SEDA-COG | 3 | Columbia | 97648 | US 11 Signals Berwick Boro | 11 | 116 | Safety Improvement | CON | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 2600000 | 3600000
SEDA-COG | 3 | Columbia | 97738 | West Creek to PA 118 | 239 | 025 | Highway Restoration | CON | 581 | 2027-01-01 |  | 0 | 0 | 100000 | 510000 | 0 | 0 | 0 | 0 | 0 | 610000
SEDA-COG | 3 | Columbia | 98400 | SR 1014 over Kashinka Hollow | 1014 | 013 | Bridge Replacement | ROW | 185 | 2025-09-11 | 2025-09-11 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000
SEDA-COG | 3 | Columbia | 98400 | SR 1014 over Kashinka Hollow | 1014 | 013 | Bridge Replacement | CON | 185 | 2025-09-11 | 2025-09-11 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SEDA-COG | 3 | Columbia | 98506 | SR 42 to Airport Rd | 487 | 111 | Highway Restoration | CON | 581 | 2028-07-01 |  | 0 | 0 | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 1000000
SEDA-COG | 3 | Columbia | 98513 | SR 11 TO SR 1037 | 1015 | 015 | Highway Restoration | CON | 581 | 2029-07-01 |  | 0 | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 240000
SEDA-COG | 3 | Columbia | 98941 | SR 254 over Tributary Fishing Creek | 254 | 054 | Bridge Replacement | PE | 185 | 2027-09-16 |  | 150000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340000
SEDA-COG | 3 | Columbia | 98941 | SR 254 over Tributary Fishing Creek | 254 | 054 | Bridge Replacement | FD | 185 | 2027-09-16 |  | 0 | 150000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SEDA-COG | 3 | Columbia | 98941 | SR 254 over Tributary Fishing Creek | 254 | 054 | Bridge Replacement | ROW | 185 | 2027-09-16 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Columbia | 98941 | SR 254 over Tributary Fishing Creek | 254 | 054 | Bridge Replacement | UTL | 185 | 2027-09-16 |  | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Columbia | 98941 | SR 254 over Tributary Fishing Creek | 254 | 054 | Bridge Replacement | CON | STP | 2027-09-16 |  | 0 | 0 | 0 | 700000 | 700000 | 0 | 0 | 0 | 0 | 1400000
SEDA-COG | 3 | Columbia | 99147 | SR 2009 Soil Slide Repair | 2009 | 009 | Highway Restoration | PE | 581 | 2030-01-01 |  | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Columbia | 99147 | SR 2009 Soil Slide Repair | 2009 | 009 | Highway Restoration | FD | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000
SEDA-COG | 3 | Columbia | 99147 | SR 2009 Soil Slide Repair | 2009 | 009 | Highway Restoration | CON | STP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1150000 | 500000 | 0 | 0 | 1650000
SEDA-COG | 3 | Columbia | 99283 | I-80 Major Guide Signs |  |  | Interstate Maintenance Program | FD | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
SEDA-COG | 3 | Columbia | 99283 | I-80 Major Guide Signs |  |  | Interstate Maintenance Program | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 150000 | 125000 | 0 | 0 | 0 | 275000
SEDA-COG | 3 | Columbia | 100443 | Roaring Cr to Southern Dr | 42 | 089 | Highway Restoration | CON | STP | 2026-02-12 | 2026-02-12 | 0 | 542419 | 290000 | 0 | 0 | 0 | 0 | 0 | 0 | 832419
SEDA-COG | 3 | Columbia | 103011 | SR 487 over Abandoned RR | 487 | 103 | Bridge Removal | FD | STP | 2026-08-27 |  | 240000 | 365000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605000
SEDA-COG | 3 | Columbia | 103011 | SR 487 over Abandoned RR | 487 | 103 | Bridge Removal | ROW | STP | 2026-08-27 |  | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
SEDA-COG | 3 | Columbia | 103011 | SR 487 over Abandoned RR | 487 | 103 | Bridge Removal | CON | STP | 2026-08-27 |  | 0 | 1082000 | 2403000 | 150000 | 0 | 0 | 0 | 0 | 0 | 3635000
SEDA-COG | 3 | Columbia | 103833 | T-557 over Little Fishing Creek |  | LBR | Bridge Restoration | PE | BOF | 2028-09-28 |  | 280000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SEDA-COG | 3 | Columbia | 103833 | T-557 over Little Fishing Creek |  | LBR | Bridge Restoration | PE | 183 | 2028-09-28 |  | 52500 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56500
SEDA-COG | 3 | Columbia | 103833 | T-557 over Little Fishing Creek |  | LBR | Bridge Restoration | FD | BOF | 2028-09-28 |  | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
SEDA-COG | 3 | Columbia | 103833 | T-557 over Little Fishing Creek |  | LBR | Bridge Restoration | FD | 183 | 2028-09-28 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Columbia | 103833 | T-557 over Little Fishing Creek |  | LBR | Bridge Restoration | ROW | BOF | 2028-09-28 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SEDA-COG | 3 | Columbia | 103833 | T-557 over Little Fishing Creek |  | LBR | Bridge Restoration | ROW | 183 | 2028-09-28 |  | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
SEDA-COG | 3 | Columbia | 103833 | T-557 over Little Fishing Creek |  | LBR | Bridge Restoration | UTL | BOF | 2028-09-28 |  | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
SEDA-COG | 3 | Columbia | 103833 | T-557 over Little Fishing Creek |  | LBR | Bridge Restoration | UTL | 183 | 2028-09-28 |  | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
SEDA-COG | 3 | Columbia | 103833 | T-557 over Little Fishing Creek |  | LBR | Bridge Restoration | CON | BOF | 2028-09-28 |  | 0 | 0 | 0 | 440000 | 400000 | 0 | 0 | 0 | 0 | 840000
SEDA-COG | 3 | Columbia | 103833 | T-557 over Little Fishing Creek |  | LBR | Bridge Restoration | CON | 183 | 2028-09-28 |  | 0 | 0 | 0 | 82500 | 75000 | 0 | 0 | 0 | 0 | 157500
SEDA-COG | 3 | Columbia | 103836 | T-356 over Montour Run |  | RBR | Bridge Replacement | PE | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 0 | 0 | 400000
SEDA-COG | 3 | Columbia | 103836 | T-356 over Montour Run |  | RBR | Bridge Replacement | PE | 183 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 0 | 75000
SEDA-COG | 3 | Columbia | 103836 | T-356 over Montour Run |  | RBR | Bridge Replacement | FD | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 0 | 280000
SEDA-COG | 3 | Columbia | 103836 | T-356 over Montour Run |  | RBR | Bridge Replacement | FD | 183 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52500 | 0 | 52500
SEDA-COG | 3 | Columbia | 103836 | T-356 over Montour Run |  | RBR | Bridge Replacement | ROW | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 40000
SEDA-COG | 3 | Columbia | 103836 | T-356 over Montour Run |  | RBR | Bridge Replacement | ROW | 183 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500
SEDA-COG | 3 | Columbia | 103836 | T-356 over Montour Run |  | RBR | Bridge Replacement | UTL | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Columbia | 103836 | T-356 over Montour Run |  | RBR | Bridge Replacement | UTL | 183 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500
SEDA-COG | 3 | Columbia | 103836 | T-356 over Montour Run |  | RBR | Bridge Replacement | CON | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
SEDA-COG | 3 | Columbia | 103836 | T-356 over Montour Run |  | RBR | Bridge Replacement | CON | 183 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 375000
SEDA-COG | 3 | Columbia | 105529 | I-80EB Hetlerville Rd (SR 2028) to Luzerne Co Line | 80 | 162 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Columbia | 105529 | I-80EB Hetlerville Rd (SR 2028) to Luzerne Co Line | 80 | 162 | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 950000
SEDA-COG | 3 | Columbia | 106181 | SR 239 over Fishing Creek | 239 | 024 | Bridge Restoration | PE | 185 | 2025-10-09 | 2025-10-09 | 33905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33905
SEDA-COG | 3 | Columbia | 106181 | SR 239 over Fishing Creek | 239 | 024 | Bridge Restoration | FD | 185 | 2025-10-09 | 2025-10-09 | 470000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470000
SEDA-COG | 3 | Columbia | 106181 | SR 239 over Fishing Creek | 239 | 024 | Bridge Restoration | ROW | 185 | 2025-10-09 | 2025-10-09 | 25850 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57850
SEDA-COG | 3 | Columbia | 106181 | SR 239 over Fishing Creek | 239 | 024 | Bridge Restoration | CON | 185 | 2025-10-09 | 2025-10-09 | 1325500 | 2604500 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 4430000
SEDA-COG | 3 | Columbia | 106733 | SR 93 to Briar Ln | 1025 | 014 | Highway Restoration | FD | 581 | 2025-05-08 | 2025-05-08 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SEDA-COG | 3 | Columbia | 106733 | SR 93 to Briar Ln | 1025 | 014 | Highway Restoration | CON | 581 | 2025-05-08 | 2025-05-08 | 673000 | 914000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1587000
SEDA-COG | 3 | Columbia | 107019 | Adjacent Box Beam Bridge Bundle |  | LBR | Bridge Restoration | PE | BOF | 2026-10-22 |  | 0 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000
SEDA-COG | 3 | Columbia | 107019 | Adjacent Box Beam Bridge Bundle |  | LBR | Bridge Restoration | FD | BOF | 2026-10-22 |  | 300000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000
SEDA-COG | 3 | Columbia | 107019 | Adjacent Box Beam Bridge Bundle |  | LBR | Bridge Restoration | ROW | BOF | 2026-10-22 |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
SEDA-COG | 3 | Columbia | 107019 | Adjacent Box Beam Bridge Bundle |  | LBR | Bridge Restoration | UTL | BOF | 2026-10-22 |  | 43000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43000
SEDA-COG | 3 | Columbia | 107019 | Adjacent Box Beam Bridge Bundle |  | LBR | Bridge Restoration | CON | BOF | 2026-10-22 |  | 0 | 2202493 | 465507 | 0 | 0 | 0 | 0 | 0 | 0 | 2668000
SEDA-COG | 3 | Columbia | 107019 | Adjacent Box Beam Bridge Bundle |  | LBR | Bridge Restoration | CON | BRIP | 2026-10-22 |  | 0 | 446000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 446000
SEDA-COG | 3 | Columbia | 107103 | McGuire Dr to SR 2028 | 1004 | 033 | Highway Restoration | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SEDA-COG | 3 | Columbia | 107103 | McGuire Dr to SR 2028 | 1004 | 033 | Highway Restoration | CON | STP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1790000 | 2000000 | 0 | 3790000
SEDA-COG | 3 | Columbia | 107111 | Reagans Alley to SR 11 | 93 | 012 | Highway Restoration | FD | 581 | 2025-05-08 | 2025-05-08 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SEDA-COG | 3 | Columbia | 107111 | Reagans Alley to SR 11 | 93 | 012 | Highway Restoration | CON | 581 | 2025-05-08 | 2025-05-08 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Columbia | 107113 | Montour Co to White Hall Rd | 254 | 051 | Highway Restoration | CON | 581 | 2025-07-01 |  | 0 | 361000 | 90800 | 0 | 0 | 0 | 0 | 0 | 0 | 451800
SEDA-COG | 3 | Columbia | 107116 | Hilltop Rd to SR 1025 | 1014 | 015 | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SEDA-COG | 3 | Columbia | 107116 | Hilltop Rd to SR 1025 | 1014 | 015 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1720000 | 1720000
SEDA-COG | 3 | Columbia | 109377 | SR 11 to SR 2028 (Hetlerville Rd) EB | 80 | 169 | Highway Restoration | PE | NHPP | 2028-03-02 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SEDA-COG | 3 | Columbia | 109377 | SR 11 to SR 2028 (Hetlerville Rd) EB | 80 | 169 | Highway Restoration | FD | NHPP | 2028-03-02 |  | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Columbia | 109377 | SR 11 to SR 2028 (Hetlerville Rd) EB | 80 | 169 | Highway Restoration | CON | NHPP | 2028-03-02 |  | 0 | 0 | 0 | 1650000 | 1100000 | 0 | 0 | 0 | 0 | 2750000
SEDA-COG | 3 | Columbia | 109378 | SR 11 to SR 2028 (Hetlerville Rd) WB | 80 | 170 | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Columbia | 109378 | SR 11 to SR 2028 (Hetlerville Rd) WB | 80 | 170 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 425000 | 0 | 0 | 0 | 425000
SEDA-COG | 3 | Columbia | 109380 | Rest Area to the Luzerne Co line | 80 | 171 | Highway Restoration | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 10000
SEDA-COG | 3 | Columbia | 109380 | Rest Area to the Luzerne Co line | 80 | 171 | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 0 | 275000
SEDA-COG | 3 | Columbia | 110221 | Hetlerville Rd to Rest Area WB | 80 | 174 | Highway Restoration | PE | 581 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
SEDA-COG | 3 | Columbia | 110221 | Hetlerville Rd to Rest Area WB | 80 | 174 | Highway Restoration | FD | 581 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
SEDA-COG | 3 | Columbia | 110221 | Hetlerville Rd to Rest Area WB | 80 | 174 | Highway Restoration | CON | NHPP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000 | 1100000
SEDA-COG | 3 | Columbia | 113590 | Environmental Remdiation & SCM Monitoring SEDACOG |  |  | Stormwater Management | STUDY | 581 |  |  | 120000 | 320000 | 320000 | 120000 | 0 | 0 | 0 | 0 | 0 | 880000
SEDA-COG | 3 | Columbia | 114141 | SR 4032 over Little Briar Run | 4032 | 001 | Bridge Replacement | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 60000 | 170000 | 0 | 0 | 230000
SEDA-COG | 3 | Columbia | 114141 | SR 4032 over Little Briar Run | 4032 | 001 | Bridge Replacement | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | 0 | 130000
SEDA-COG | 3 | Columbia | 114141 | SR 4032 over Little Briar Run | 4032 | 001 | Bridge Replacement | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000
SEDA-COG | 3 | Columbia | 114141 | SR 4032 over Little Briar Run | 4032 | 001 | Bridge Replacement | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SEDA-COG | 3 | Columbia | 114141 | SR 4032 over Little Briar Run | 4032 | 001 | Bridge Replacement | CON | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
SEDA-COG | 3 | Columbia | 114157 | SR 1027 over Tributary of Susquehanna River | 1027 | 006 | Bridge Replacement | PE | 185 | 2029-09-01 |  | 0 | 0 | 165000 | 100000 | 0 | 0 | 0 | 0 | 0 | 265000
SEDA-COG | 3 | Columbia | 114157 | SR 1027 over Tributary of Susquehanna River | 1027 | 006 | Bridge Replacement | FD | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 110000
SEDA-COG | 3 | Columbia | 114157 | SR 1027 over Tributary of Susquehanna River | 1027 | 006 | Bridge Replacement | ROW | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 35000
SEDA-COG | 3 | Columbia | 114157 | SR 1027 over Tributary of Susquehanna River | 1027 | 006 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Columbia | 114157 | SR 1027 over Tributary of Susquehanna River | 1027 | 006 | Bridge Replacement | CON | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 325000 | 0 | 0 | 475000
SEDA-COG | 3 | Columbia | 114231 | SR 4016 over Black Run | 4016 | 011 | Bridge Replacement | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 200000 | 25000 | 0 | 0 | 0 | 0 | 225000
SEDA-COG | 3 | Columbia | 114231 | SR 4016 over Black Run | 4016 | 011 | Bridge Replacement | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 122000 | 0 | 0 | 0 | 122000
SEDA-COG | 3 | Columbia | 114231 | SR 4016 over Black Run | 4016 | 011 | Bridge Replacement | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 35000
SEDA-COG | 3 | Columbia | 114231 | SR 4016 over Black Run | 4016 | 011 | Bridge Replacement | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 30000
SEDA-COG | 3 | Columbia | 114231 | SR 4016 over Black Run | 4016 | 011 | Bridge Replacement | CON | BOF | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 0 | 400000
SEDA-COG | 3 | Columbia | 114231 | SR 4016 over Black Run | 4016 | 011 | Bridge Replacement | CON | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 100000
SEDA-COG | 3 | Columbia | 115536 | Park St to Shaffer Rd | 11 | 152 | Highway Restoration | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000
SEDA-COG | 3 | Columbia | 115536 | Park St to Shaffer Rd | 11 | 152 | Highway Restoration | CON | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 500000 | 1100000
SEDA-COG | 3 | Columbia | 115538 | Catawissa Cr to SR 11 | 42 | 115 | Highway Restoration | PE | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SEDA-COG | 3 | Columbia | 115538 | Catawissa Cr to SR 11 | 42 | 115 | Highway Restoration | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
SEDA-COG | 3 | Columbia | 115538 | Catawissa Cr to SR 11 | 42 | 115 | Highway Restoration | CON | STP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750000 | 3750000
SEDA-COG | 3 | Columbia | 115539 | Schoolhouse Rd to 1/4mile N of SR 4009 | 42 | 116 | Highway Restoration | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000
SEDA-COG | 3 | Columbia | 115539 | Schoolhouse Rd to 1/4mile N of SR 4009 | 42 | 116 | Highway Restoration | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 600000
SEDA-COG | 3 | Columbia | 115540 | 1/4mile N of SR 4009 to Millville | 42 | 117 | Highway Restoration | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 150000
SEDA-COG | 3 | Columbia | 115540 | 1/4mile N of SR 4009 to Millville | 42 | 117 | Highway Restoration | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 5500000 | 7000000
SEDA-COG | 3 | Columbia | 115541 | SR 11 to Frosty Valley Rd | 42 | 118 | Highway Restoration | PE | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SEDA-COG | 3 | Columbia | 115541 | SR 11 to Frosty Valley Rd | 42 | 118 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
SEDA-COG | 3 | Columbia | 115541 | SR 11 to Frosty Valley Rd | 42 | 118 | Highway Restoration | CON | STP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
SEDA-COG | 3 | Columbia | 115542 | Frosty Valley Rd to Schoolhouse Rd | 42 | 119 | Highway Restoration | PE | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SEDA-COG | 3 | Columbia | 115542 | Frosty Valley Rd to Schoolhouse Rd | 42 | 119 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
SEDA-COG | 3 | Columbia | 115542 | Frosty Valley Rd to Schoolhouse Rd | 42 | 119 | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
SEDA-COG | 3 | Columbia | 115543 | Valley Rd to SR 487 | 11 | 153 | Highway Restoration | PE | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000
SEDA-COG | 3 | Columbia | 115543 | Valley Rd to SR 487 | 11 | 153 | Highway Restoration | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000
SEDA-COG | 3 | Columbia | 115543 | Valley Rd to SR 487 | 11 | 153 | Highway Restoration | CON | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100000 | 3100000
SEDA-COG | 3 | Columbia | 115593 | Columbia Co 2025 Crack Seal |  |  | General Maintenance | FD | 581 | 2025-06-26 | 2025-06-26 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SEDA-COG | 3 | Columbia | 115994 | SR 93 to Briar Ln | 1025 | 018 | Highway Restoration | FD | 581 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Columbia | 115994 | SR 93 to Briar Ln | 1025 | 018 | Highway Restoration | CON | 581 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 550000
SEDA-COG | 3 | Columbia | 116203 | Park Blvd to Luzerne Co | 11 | 162 | Highway Restoration | CON | NHPP | 2025-06-26 | 2025-06-26 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
SEDA-COG | 3 | Columbia | 116203 | Park Blvd to Luzerne Co | 11 | 162 | Highway Restoration | CON | STP | 2025-06-26 | 2025-06-26 | 395000 | 228000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623000
SEDA-COG | 3 | Columbia | 116203 | Park Blvd to Luzerne Co | 11 | 162 | Highway Restoration | CON | 581 | 2025-06-26 | 2025-06-26 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
SEDA-COG | 3 | Columbia | 116356 | Park St to Shaffer Rd (SR 1001) | 11 | 165 | Highway Restoration | CON | NHPP | 2025-06-26 | 2025-06-26 | 400000 | 214000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 614000
SEDA-COG | 3 | Columbia | 116356 | Park St to Shaffer Rd (SR 1001) | 11 | 165 | Highway Restoration | CON | STP | 2025-06-26 | 2025-06-26 | 300000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332000
SEDA-COG | 3 | Columbia | 117137 | Poor House Rd to White Church Rd | 42 | 127 | Highway Restoration | CON | 581 |  |  | 200000 | 495341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695341
SEDA-COG | 3 | Columbia | 117139 | Gaswell Rd to Roaring Cr | 42 | 128 | Highway Restoration | CON | 581 |  |  | 202000 | 457697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 659697
SEDA-COG | 3 | Columbia | 117504 | SR 2028 over Trib to Nescopeck Creek | 2028 | 020 | Bridge Replacement | PE | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 90000 | 0 | 210000
SEDA-COG | 3 | Columbia | 117504 | SR 2028 over Trib to Nescopeck Creek | 2028 | 020 | Bridge Replacement | FD | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SEDA-COG | 3 | Columbia | 117504 | SR 2028 over Trib to Nescopeck Creek | 2028 | 020 | Bridge Replacement | ROW | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000
SEDA-COG | 3 | Columbia | 117504 | SR 2028 over Trib to Nescopeck Creek | 2028 | 020 | Bridge Replacement | UTL | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SEDA-COG | 3 | Columbia | 117504 | SR 2028 over Trib to Nescopeck Creek | 2028 | 020 | Bridge Replacement | CON | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
SEDA-COG | 3 | Columbia | 117576 | SR 4020 over Green Creek | 4020 | 015 | Bridge Restoration | CON | BOF | 2024-10-24 | 2024-10-24 | 1250000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1370000
SEDA-COG | 3 | Columbia | 117577 | SR 2001 over Roaring Creek | 2001 | 022 | Bridge Restoration | PE | BOF | 2026-01-15 | 2026-01-15 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
SEDA-COG | 3 | Columbia | 117577 | SR 2001 over Roaring Creek | 2001 | 022 | Bridge Restoration | PE | 185 | 2026-01-15 | 2026-01-15 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
SEDA-COG | 3 | Columbia | 117577 | SR 2001 over Roaring Creek | 2001 | 022 | Bridge Restoration | FD | 185 | 2026-01-15 | 2026-01-15 | 125000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Columbia | 117577 | SR 2001 over Roaring Creek | 2001 | 022 | Bridge Restoration | ROW | 185 | 2026-01-15 | 2026-01-15 | 18600 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38600
SEDA-COG | 3 | Columbia | 117577 | SR 2001 over Roaring Creek | 2001 | 022 | Bridge Restoration | CON | BOF | 2026-01-15 | 2026-01-15 | 0 | 950000 | 184000 | 0 | 0 | 0 | 0 | 0 | 0 | 1134000
SEDA-COG | 3 | Columbia | 117758 | 24-25 RPM Contract SEDA-COG |  |  | Safety Improvement | CON | 581 | 2025-06-26 | 2025-06-26 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
SEDA-COG | 3 | Columbia | 117759 | 25-26 RPM Contract SEDA-COG |  |  | Safety Improvement | CON | 581 | 2026-06-18 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SEDA-COG | 3 | Columbia | 118286 | SR 487 to Mendenhall Lane | 239 | 027 | Highway Restoration | FD | 581 | 2025-10-09 | 2025-10-09 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SEDA-COG | 3 | Columbia | 118286 | SR 487 to Mendenhall Lane | 239 | 027 | Highway Restoration | CON | 581 | 2025-10-09 | 2025-10-09 | 100000 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
SEDA-COG | 3 | Columbia | 119665 | Southern RAR 2025 |  |  | General Maintenance | PE | 581 | 2025-04-17 | 2025-04-17 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SEDA-COG | 3 | Columbia | 120083 | D3 SEDA-COG Bridge Lighting Upgrades to LED | 42 | 133 | Bridge Restoration | PE | CRP | 2026-07-16 |  | 171000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171000
SEDA-COG | 3 | Columbia | 120083 | D3 SEDA-COG Bridge Lighting Upgrades to LED | 42 | 133 | Bridge Restoration | FD | CRP | 2026-07-16 |  | 255000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000
SEDA-COG | 3 | Columbia | 120083 | D3 SEDA-COG Bridge Lighting Upgrades to LED | 42 | 133 | Bridge Restoration | CON | CRP | 2026-07-16 |  | 642000 | 1071000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1713000
SEDA-COG | 3 | Columbia | 120888 | Multiple br ov Fishing & Ltl Fishing Crks | 254 | 060 | Bridge Preservation - Federal | PE | 185 | 2026-09-03 |  | 0 | 100000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SEDA-COG | 3 | Columbia | 120888 | Multiple br ov Fishing & Ltl Fishing Crks | 254 | 060 | Bridge Preservation - Federal | FD | 185 | 2026-09-03 |  | 0 | 150000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SEDA-COG | 3 | Columbia | 120888 | Multiple br ov Fishing & Ltl Fishing Crks | 254 | 060 | Bridge Preservation - Federal | CON | 185 | 2026-09-03 |  | 0 | 0 | 1762000 | 1763000 | 0 | 0 | 0 | 0 | 0 | 3525000
SEDA-COG | 3 | Columbia | 120889 | Multiple br in Col, North & Snyder Cos. | 487 | 127 | Bridge Preservation - State Funded | PE | 185 | 2028-09-01 |  | 0 | 210000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 460000
SEDA-COG | 3 | Columbia | 120889 | Multiple br in Col, North & Snyder Cos. | 487 | 127 | Bridge Preservation - State Funded | FD | 185 | 2028-09-01 |  | 0 | 0 | 200000 | 75000 | 0 | 0 | 0 | 0 | 0 | 275000
SEDA-COG | 3 | Columbia | 120889 | Multiple br in Col, North & Snyder Cos. | 487 | 127 | Bridge Preservation - State Funded | CON | 185 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 2700000 | 1615000 | 185000 | 0 | 0 | 4500000
SEDA-COG | 3 | Columbia | 120928 | 26-27 RPM Contract SEDA-COG |  |  | Safety Improvement | CON | 581 | 2027-06-24 |  | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SEDA-COG | 3 | Columbia | 120929 | 27-28 RPM Contract SEDA-COG |  |  | Safety Improvement | CON | 581 | 2028-06-01 |  | 0 | 0 | 0 | 81000 | 0 | 0 | 0 | 0 | 0 | 81000
SEDA-COG | 3 | Columbia | 121000 | Columbia Co 2026 Crack Seal |  |  | General Maintenance | FD | 581 | 2026-06-18 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SEDA-COG | 3 | Columbia | 121001 | Columbia Co 2027 Crack Seal |  |  | General Maintenance | FD | 581 | 2027-06-24 |  | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SEDA-COG | 3 | Columbia | 121002 | Columbia Co 2028 Crack Seal |  |  | General Maintenance | FD | 581 | 2028-06-01 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
SEDA-COG | 3 | Columbia | 121004 | Southern RAR 2026 |  |  | General Maintenance | FD | 581 | 2026-05-07 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SEDA-COG | 3 | Columbia | 121005 | Southern RAR 2027 |  |  | General Maintenance | FD | 581 | 2027-04-29 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SEDA-COG | 3 | Columbia | 121008 | Southern RAR 2028 |  |  | General Maintenance | FD | 581 | 2028-06-01 |  | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SEDA-COG | 3 | Columbia | 121013 | Southern RAR 2029 |  |  | General Maintenance | FD | 581 | 2029-06-01 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
SEDA-COG | 3 | Columbia | 121659 | SR 442 to SR 4024 | 42 | 135 | Highway Restoration | STUDY | 581 |  |  | 0 | 50000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Columbia | 122761 | SR 2021 over I-80 (Emergency Repair) | 2021 | 006 | Disaster (Initial Reponse/Non Cap Budg) | PE | 185 |  |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SEDA-COG | 3 | Columbia | 123013 | SEDA-COG T&E Reserve D3 |  |  | Reserve Line Item | STUDY | 185 |  |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
SEDA-COG | 3 | Columbia | 123059 | SR 2021 over I-80 (Emergency Repair) | 2021 | 007 | Bridge Restoration | FD | 185 | 2025-08-14 | 2025-08-25 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SEDA-COG | 3 | Columbia | 123062 | SR 4049 ov W Br Fishing Crk (Fld Follow-Up 2025) | 4049 | 024 | Disaster (Initial Reponse/Non Cap Budg) | FD | 185 |  |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Montour | 6303 | T-396 over E Branch Chillisquaque Ck Cnty Br#12 |  | LBR | Bridge Replacement | CON | BOF | 2024-12-12 | 2024-12-12 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SEDA-COG | 3 | Montour | 6303 | T-396 over E Branch Chillisquaque Ck Cnty Br#12 |  | LBR | Bridge Replacement | CON | 183 | 2024-12-12 | 2024-12-12 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Montour | 6303 | T-396 over E Branch Chillisquaque Ck Cnty Br#12 |  | LBR | Bridge Replacement | CON | LOC | 2024-12-12 | 2024-12-12 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Montour | 6369 | T-318 over Beaver Run |  | LBR | Bridge Replacement | PE | BOF |  |  | 0 | 0 | 0 | 0 | 320000 | 80000 | 0 | 0 | 0 | 400000
SEDA-COG | 3 | Montour | 6369 | T-318 over Beaver Run |  | LBR | Bridge Replacement | PE | 183 |  |  | 0 | 0 | 0 | 0 | 60000 | 15000 | 0 | 0 | 0 | 75000
SEDA-COG | 3 | Montour | 6369 | T-318 over Beaver Run |  | LBR | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 0 | 0 | 280000
SEDA-COG | 3 | Montour | 6369 | T-318 over Beaver Run |  | LBR | Bridge Replacement | FD | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 52500 | 0 | 0 | 52500
SEDA-COG | 3 | Montour | 6369 | T-318 over Beaver Run |  | LBR | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 40000
SEDA-COG | 3 | Montour | 6369 | T-318 over Beaver Run |  | LBR | Bridge Replacement | ROW | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 7500
SEDA-COG | 3 | Montour | 6369 | T-318 over Beaver Run |  | LBR | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 40000
SEDA-COG | 3 | Montour | 6369 | T-318 over Beaver Run |  | LBR | Bridge Replacement | UTL | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500
SEDA-COG | 3 | Montour | 6369 | T-318 over Beaver Run |  | LBR | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820000 | 220000 | 1040000
SEDA-COG | 3 | Montour | 6369 | T-318 over Beaver Run |  | LBR | Bridge Replacement | CON | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153750 | 41250 | 195000
SEDA-COG | 3 | Montour | 87898 | SR 642 from Northumberland County to SR 45 | 642 | 16M | Highway Restoration | CON | 581 | 2026-07-01 |  | 0 | 219000 | 402000 | 0 | 0 | 0 | 0 | 0 | 0 | 621000
SEDA-COG | 3 | Montour | 88800 | SR 254 over Mud Creek and Chillisquaque Creek | 254 | 053 | Bridge Restoration | PE | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 350000 | 400000 | 0 | 0 | 750000
SEDA-COG | 3 | Montour | 88800 | SR 254 over Mud Creek and Chillisquaque Creek | 254 | 053 | Bridge Restoration | FD | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 250000 | 550000
SEDA-COG | 3 | Montour | 88800 | SR 254 over Mud Creek and Chillisquaque Creek | 254 | 053 | Bridge Restoration | ROW | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 200000
SEDA-COG | 3 | Montour | 88800 | SR 254 over Mud Creek and Chillisquaque Creek | 254 | 053 | Bridge Restoration | UTL | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
SEDA-COG | 3 | Montour | 88800 | SR 254 over Mud Creek and Chillisquaque Creek | 254 | 053 | Bridge Restoration | CON | STP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
SEDA-COG | 3 | Montour | 88800 | SR 254 over Mud Creek and Chillisquaque Creek | 254 | 053 | Bridge Restoration | CON | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6100000 | 6100000
SEDA-COG | 3 | Montour | 93524 | SR 54 over Stony Brook | 54 | 076 | Bridge Replacement | CON | BRIP | 2024-07-11 | 2024-07-11 | 0 | 0 | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 475000
SEDA-COG | 3 | Montour | 98507 | SR 642 over Mauses Creek | 642 | 026 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
SEDA-COG | 3 | Montour | 98507 | SR 642 over Mauses Creek | 642 | 026 | Bridge Replacement | CON | 185 | 2029-09-01 |  | 0 | 0 | 0 | 290000 | 0 | 0 | 0 | 0 | 0 | 290000
SEDA-COG | 3 | Montour | 99123 | North'd Co Line to PA 642 | 45 | 030 | Highway Restoration | CON | 581 |  |  | 0 | 701605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 701605
SEDA-COG | 3 | Montour | 100451 | Byrd Ave to Grovania Drv | 2008 | 009 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 55000
SEDA-COG | 3 | Montour | 100483 | SR 54 from SR 254 to SR 3008 | 54 | 087 | Highway Restoration | CON | 581 | 2024-07-11 | 2024-07-11 | 0 | 462053 | 137947 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SEDA-COG | 3 | Montour | 103841 | T-314 over Beaver Run |  | BRB | Bridge Removal | UTL | 581 | 2028-03-02 |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SEDA-COG | 3 | Montour | 103841 | T-314 over Beaver Run |  | BRB | Bridge Removal | CON | 581 | 2028-03-02 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Montour | 103853 | SR 54 Corridor Safety Improvement | 54 | 090 | Safety Improvement | CON | BRIP | 2024-12-12 | 2024-12-12 | 1596000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1596000
SEDA-COG | 3 | Montour | 103853 | SR 54 Corridor Safety Improvement | 54 | 090 | Safety Improvement | CON | HSIP | 2024-12-12 | 2024-12-12 | 1213200 | 1263800 | 669000 | 0 | 0 | 0 | 0 | 0 | 0 | 3146000
SEDA-COG | 3 | Montour | 103853 | SR 54 Corridor Safety Improvement | 54 | 090 | Safety Improvement | CON | NHPP | 2024-12-12 | 2024-12-12 | 2402035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402035
SEDA-COG | 3 | Montour | 103853 | SR 54 Corridor Safety Improvement | 54 | 090 | Safety Improvement | CON | STP | 2024-12-12 | 2024-12-12 | 6740596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6740596
SEDA-COG | 3 | Montour | 103853 | SR 54 Corridor Safety Improvement | 54 | 090 | Safety Improvement | CON | 581 | 2024-12-12 | 2024-12-12 | 3465000 | 1635000 | 2011000 | 2265000 | 0 | 0 | 0 | 0 | 0 | 9376000
SEDA-COG | 3 | Montour | 105520 | I-80 EB Mexico Rd (SR 3013) to Trib to Mauses Crk | 80 | 156 | Highway Restoration | FD | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Montour | 105520 | I-80 EB Mexico Rd (SR 3013) to Trib to Mauses Crk | 80 | 156 | Highway Restoration | CON | NHPP | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550000 | 1550000
SEDA-COG | 3 | Montour | 105521 | I-80 WB Montour Co Line to Mexico Rd (SR 3013) | 80 | 157 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
SEDA-COG | 3 | Montour | 105521 | I-80 WB Montour Co Line to Mexico Rd (SR 3013) | 80 | 157 | Highway Restoration | CON | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SEDA-COG | 3 | Montour | 105524 | I-80 from Mexico Rd to Stump Rd | 80 | 158 | Highway Restoration | FD | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Montour | 105524 | I-80 from Mexico Rd to Stump Rd | 80 | 158 | Highway Restoration | CON | NHPP | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 900000
SEDA-COG | 3 | Montour | 106671 | T-392 over Mud Run |  | BRB | Bridge Removal | CON | 581 | 2028-03-02 |  | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000
SEDA-COG | 3 | Montour | 107128 | SR 54 under Market Street | 54 | 095 | Bridge Restoration | PE | STP | 2026-11-05 |  | 328000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328000
SEDA-COG | 3 | Montour | 107128 | SR 54 under Market Street | 54 | 095 | Bridge Restoration | FD | 185 | 2026-11-05 |  | 300000 | 73000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373000
SEDA-COG | 3 | Montour | 107128 | SR 54 under Market Street | 54 | 095 | Bridge Restoration | ROW | 185 | 2026-11-05 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SEDA-COG | 3 | Montour | 107128 | SR 54 under Market Street | 54 | 095 | Bridge Restoration | UTL | 185 | 2026-11-05 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SEDA-COG | 3 | Montour | 107128 | SR 54 under Market Street | 54 | 095 | Bridge Restoration | CON | BRIP | 2026-11-05 |  | 0 | 0 | 600000 | 890000 | 0 | 0 | 0 | 0 | 0 | 1490000
SEDA-COG | 3 | Montour | 107128 | SR 54 under Market Street | 54 | 095 | Bridge Restoration | CON | STP | 2026-11-05 |  | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
SEDA-COG | 3 | Montour | 109375 | SR 54 to Columbia Co EB | 80 | 168 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Montour | 109375 | SR 54 to Columbia Co EB | 80 | 168 | Highway Restoration | CON | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 1050000
SEDA-COG | 3 | Montour | 111599 | North Branch Canal Trail LeveeTrail |  | 63E | Transportation Enhancement | CON | TAP | 2026-12-03 |  | 0 | 0 | 620629 | 0 | 0 | 0 | 0 | 0 | 0 | 620629
SEDA-COG | 3 | Montour | 113972 | Chillisquaque Cr to SR 254 | 54 | 107 | Highway Restoration | FD | 581 | 2029-01-01 |  | 0 | 0 | 0 | 70000 | 80000 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Montour | 113972 | Chillisquaque Cr to SR 254 | 54 | 107 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 30000 | 0 | 750000 | 4250000 | 0 | 0 | 0 | 5030000
SEDA-COG | 3 | Montour | 114031 | SR 54 to North'd Co Line | 44 | 087 | Highway Restoration | FD | 581 | 2029-01-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
SEDA-COG | 3 | Montour | 114031 | SR 54 to North'd Co Line | 44 | 087 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 700000
SEDA-COG | 3 | Montour | 115544 | 1500ft W of Montour St to Clinic Rd | 11 | 154 | Highway Restoration | FD | 581 | 2026-02-26 | 2026-02-26 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Montour | 115544 | 1500ft W of Montour St to Clinic Rd | 11 | 154 | Highway Restoration | CON | NHPP | 2026-02-26 | 2026-02-26 | 0 | 900000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
SEDA-COG | 3 | Montour | 115545 | Mahoning Twp Line to SR 11 | 54 | 113 | Highway Restoration | PE | 581 | 2030-01-01 |  | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 125000
SEDA-COG | 3 | Montour | 115545 | Mahoning Twp Line to SR 11 | 54 | 113 | Highway Restoration | FD | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 225000
SEDA-COG | 3 | Montour | 115545 | Mahoning Twp Line to SR 11 | 54 | 113 | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1400000 | 3400000 | 0 | 0 | 4800000
SEDA-COG | 3 | Montour | 115548 | 1500ft W of Montour St to Clinic Rd | 11 | 156 | Highway Restoration | FD | 581 | 2036-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Montour | 115548 | 1500ft W of Montour St to Clinic Rd | 11 | 156 | Highway Restoration | CON | NHPP | 2036-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
SEDA-COG | 3 | Montour | 115577 | SR 45 to Mauses Cr | 642 | 035 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 1000000 | 1450000
SEDA-COG | 3 | Montour | 116227 | Ferry St to Cherry St | 2010 | 023 | Highway Restoration | CON | 581 | 2026-02-26 | 2026-02-26 | 0 | 100000 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 370000
SEDA-COG | 3 | Montour | 116308 | Sechler Run to Columbia Co | 11 | 164 | Highway Restoration | FD | 581 | 2028-01-01 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Montour | 116308 | Sechler Run to Columbia Co | 11 | 164 | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 750000
SEDA-COG | 3 | Montour | 116808 | Trib to Mauses Cr to Columbia Co | 80 | 193 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Montour | 116808 | Trib to Mauses Cr to Columbia Co | 80 | 193 | Highway Restoration | CON | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1125000 | 1125000
SEDA-COG | 3 | Montour | 117506 | T-412 over Sechler Run |  | LBR | Bridge Replacement | PE | BOF | 2028-09-01 |  | 0 | 240000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 272000
SEDA-COG | 3 | Montour | 117506 | T-412 over Sechler Run |  | LBR | Bridge Replacement | PE | 183 | 2028-09-01 |  | 0 | 45000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 51000
SEDA-COG | 3 | Montour | 117506 | T-412 over Sechler Run |  | LBR | Bridge Replacement | FD | BOF | 2028-09-01 |  | 0 | 0 | 0 | 112000 | 80000 | 0 | 0 | 0 | 0 | 192000
SEDA-COG | 3 | Montour | 117506 | T-412 over Sechler Run |  | LBR | Bridge Replacement | FD | 183 | 2028-09-01 |  | 0 | 0 | 0 | 21000 | 15000 | 0 | 0 | 0 | 0 | 36000
SEDA-COG | 3 | Montour | 117506 | T-412 over Sechler Run |  | LBR | Bridge Replacement | ROW | BOF | 2028-09-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
SEDA-COG | 3 | Montour | 117506 | T-412 over Sechler Run |  | LBR | Bridge Replacement | ROW | 183 | 2028-09-01 |  | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750
SEDA-COG | 3 | Montour | 117506 | T-412 over Sechler Run |  | LBR | Bridge Replacement | UTL | BOF | 2028-09-01 |  | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 40000
SEDA-COG | 3 | Montour | 117506 | T-412 over Sechler Run |  | LBR | Bridge Replacement | UTL | 183 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 7500
SEDA-COG | 3 | Montour | 117506 | T-412 over Sechler Run |  | LBR | Bridge Replacement | CON | BOF | 2028-09-01 |  | 0 | 0 | 0 | 0 | 840000 | 0 | 0 | 0 | 0 | 840000
SEDA-COG | 3 | Montour | 117506 | T-412 over Sechler Run |  | LBR | Bridge Replacement | CON | 183 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 157500 | 0 | 0 | 0 | 0 | 157500
SEDA-COG | 3 | Montour | 117510 | T-422 over Limestone Run |  | LBR | Bridge Replacement | PE | BOF | 2029-09-01 |  | 0 | 0 | 208000 | 80000 | 0 | 0 | 0 | 0 | 0 | 288000
SEDA-COG | 3 | Montour | 117510 | T-422 over Limestone Run |  | LBR | Bridge Replacement | PE | 183 | 2029-09-01 |  | 0 | 0 | 39000 | 15000 | 0 | 0 | 0 | 0 | 0 | 54000
SEDA-COG | 3 | Montour | 117510 | T-422 over Limestone Run |  | LBR | Bridge Replacement | FD | BOF | 2029-09-01 |  | 0 | 0 | 0 | 120000 | 80000 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Montour | 117510 | T-422 over Limestone Run |  | LBR | Bridge Replacement | FD | 183 | 2029-09-01 |  | 0 | 0 | 0 | 22500 | 15000 | 0 | 0 | 0 | 0 | 37500
SEDA-COG | 3 | Montour | 117510 | T-422 over Limestone Run |  | LBR | Bridge Replacement | ROW | BOF | 2029-09-01 |  | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 28000
SEDA-COG | 3 | Montour | 117510 | T-422 over Limestone Run |  | LBR | Bridge Replacement | ROW | 183 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 5250 | 0 | 0 | 0 | 0 | 5250
SEDA-COG | 3 | Montour | 117510 | T-422 over Limestone Run |  | LBR | Bridge Replacement | UTL | BOF | 2029-09-01 |  | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 40000
SEDA-COG | 3 | Montour | 117510 | T-422 over Limestone Run |  | LBR | Bridge Replacement | UTL | 183 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 7500
SEDA-COG | 3 | Montour | 117510 | T-422 over Limestone Run |  | LBR | Bridge Replacement | CON | BOF | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 1600000
SEDA-COG | 3 | Montour | 117510 | T-422 over Limestone Run |  | LBR | Bridge Replacement | CON | 183 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 300000
SEDA-COG | 3 | Montour | 117513 | T-362 over Mauses Creek, County Bridge #18 |  | LBR | Bridge Replacement | PE | BOF | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 160000 | 160000 | 0 | 0 | 320000
SEDA-COG | 3 | Montour | 117513 | T-362 over Mauses Creek, County Bridge #18 |  | LBR | Bridge Replacement | PE | 183 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 60000
SEDA-COG | 3 | Montour | 117513 | T-362 over Mauses Creek, County Bridge #18 |  | LBR | Bridge Replacement | FD | BOF | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 80000 | 0 | 200000
SEDA-COG | 3 | Montour | 117513 | T-362 over Mauses Creek, County Bridge #18 |  | LBR | Bridge Replacement | FD | 183 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 22500 | 15000 | 0 | 37500
SEDA-COG | 3 | Montour | 117513 | T-362 over Mauses Creek, County Bridge #18 |  | LBR | Bridge Replacement | ROW | BOF | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 28000
SEDA-COG | 3 | Montour | 117513 | T-362 over Mauses Creek, County Bridge #18 |  | LBR | Bridge Replacement | ROW | 183 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250 | 0 | 5250
SEDA-COG | 3 | Montour | 117513 | T-362 over Mauses Creek, County Bridge #18 |  | LBR | Bridge Replacement | UTL | BOF | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
SEDA-COG | 3 | Montour | 117513 | T-362 over Mauses Creek, County Bridge #18 |  | LBR | Bridge Replacement | UTL | 183 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750 | 0 | 3750
SEDA-COG | 3 | Montour | 117513 | T-362 over Mauses Creek, County Bridge #18 |  | LBR | Bridge Replacement | CON | BOF | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1760000 | 1760000
SEDA-COG | 3 | Montour | 117513 | T-362 over Mauses Creek, County Bridge #18 |  | LBR | Bridge Replacement | CON | 183 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330000 | 330000
SEDA-COG | 3 | Montour | 117527 | SR 54 over Mud Creek | 54 | 117 | Bridge Replacement | PE | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 300000 | 250000 | 0 | 0 | 550000
SEDA-COG | 3 | Montour | 117527 | SR 54 over Mud Creek | 54 | 117 | Bridge Replacement | FD | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 200000 | 425000
SEDA-COG | 3 | Montour | 117527 | SR 54 over Mud Creek | 54 | 117 | Bridge Replacement | ROW | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 40000
SEDA-COG | 3 | Montour | 117527 | SR 54 over Mud Creek | 54 | 117 | Bridge Replacement | UTL | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
SEDA-COG | 3 | Montour | 117527 | SR 54 over Mud Creek | 54 | 117 | Bridge Replacement | CON | STP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1278000 | 1278000
SEDA-COG | 3 | Montour | 117527 | SR 54 over Mud Creek | 54 | 117 | Bridge Replacement | CON | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2722000 | 2722000
SEDA-COG | 3 | Montour | 118107 | North'd Co to High Rd | 54 | 118 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Montour | 118107 | North'd Co to High Rd | 54 | 118 | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
SEDA-COG | 3 | Montour | 118333 | Montour 2006 Slide | 2006 | 030 | General Maintenance | CON | 581 | 2024-07-01 |  | 153000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153000
SEDA-COG | 3 | Montour | 118583 | Bloom Rd Intersection | 2005 | 028 | Highway Restoration | CON | 581 | 2026-02-26 | 2026-02-26 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Montour | 119289 | SR 2008 - Right of Way | 2008 | 017 | Planning/Research/Administration | ROW | 581 |  |  | 700000 | 271500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 971500
SEDA-COG | 3 | Montour | 120377 | Railroad St to Clinic Rd | 11 | 180 | Highway Restoration | FD | 581 | 2027-01-01 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Montour | 120377 | Railroad St to Clinic Rd | 11 | 180 | Highway Restoration | CON | NHPP | 2027-01-01 |  | 0 | 0 | 70000 | 160000 | 0 | 0 | 0 | 0 | 0 | 230000
SEDA-COG | 3 | Montour | 121682 | SR 54 & SR 254 Intersection | 254 | 063 | Highway Restoration | STUDY | 581 |  |  | 0 | 143500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143500
SEDA-COG | 3 | Northumberland | 6615 | SR 4020 over Little Shamokin Creek | 4020 | 001 | Bridge Preservation - Federal | PE | BOF | 2026-10-22 |  | 37000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37000
SEDA-COG | 3 | Northumberland | 6615 | SR 4020 over Little Shamokin Creek | 4020 | 001 | Bridge Preservation - Federal | FD | BOF | 2026-10-22 |  | 145000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Northumberland | 6615 | SR 4020 over Little Shamokin Creek | 4020 | 001 | Bridge Preservation - Federal | ROW | 185 | 2026-10-22 |  | 0 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000
SEDA-COG | 3 | Northumberland | 6615 | SR 4020 over Little Shamokin Creek | 4020 | 001 | Bridge Preservation - Federal | CON | BOF | 2026-10-22 |  | 0 | 375000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SEDA-COG | 3 | Northumberland | 6667 | SR 4018 over Unnamed Tributary Susquehanna River | 4018 | 013 | Bridge Replacement | CON | 185 | 2025-01-09 | 2025-01-09 | 650000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SEDA-COG | 3 | Northumberland | 6700 | SR 4022 over Boile Run | 4022 | 019 | Bridge Restoration | PE | 185 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 110000 | 70000 | 0 | 0 | 0 | 180000
SEDA-COG | 3 | Northumberland | 6700 | SR 4022 over Boile Run | 4022 | 019 | Bridge Restoration | FD | 185 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 120000
SEDA-COG | 3 | Northumberland | 6700 | SR 4022 over Boile Run | 4022 | 019 | Bridge Restoration | ROW | 185 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 30000
SEDA-COG | 3 | Northumberland | 6700 | SR 4022 over Boile Run | 4022 | 019 | Bridge Restoration | UTL | 185 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
SEDA-COG | 3 | Northumberland | 6700 | SR 4022 over Boile Run | 4022 | 019 | Bridge Restoration | CON | 185 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 150000 | 400000
SEDA-COG | 3 | Northumberland | 6725 | SR 901 over SEDA-COG Railroad | 901 | 025 | Bridge Restoration | PE | 185 | 2026-01-08 | 2026-01-08 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SEDA-COG | 3 | Northumberland | 6725 | SR 901 over SEDA-COG Railroad | 901 | 025 | Bridge Restoration | FD | 185 | 2026-01-08 | 2026-01-08 | 250000 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315000
SEDA-COG | 3 | Northumberland | 6725 | SR 901 over SEDA-COG Railroad | 901 | 025 | Bridge Restoration | ROW | 185 | 2026-01-08 | 2026-01-08 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000
SEDA-COG | 3 | Northumberland | 6725 | SR 901 over SEDA-COG Railroad | 901 | 025 | Bridge Restoration | UTL | 185 | 2026-01-08 | 2026-01-08 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Northumberland | 6725 | SR 901 over SEDA-COG Railroad | 901 | 025 | Bridge Restoration | CON | BRIP | 2026-01-08 | 2026-01-08 | 0 | 1785000 | 1611000 | 0 | 0 | 0 | 0 | 0 | 0 | 3396000
SEDA-COG | 3 | Northumberland | 6725 | SR 901 over SEDA-COG Railroad | 901 | 025 | Bridge Restoration | CON | 185 | 2026-01-08 | 2026-01-08 | 0 | 44000 | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SEDA-COG | 3 | Northumberland | 6736 | SR 2016 over Millers Run | 2016 | 031 | Bridge Replacement | PE | BOF | 2028-09-01 |  | 0 | 229000 | 321000 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
SEDA-COG | 3 | Northumberland | 6736 | SR 2016 over Millers Run | 2016 | 031 | Bridge Replacement | FD | 185 | 2028-09-01 |  | 0 | 0 | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 375000
SEDA-COG | 3 | Northumberland | 6736 | SR 2016 over Millers Run | 2016 | 031 | Bridge Replacement | ROW | 185 | 2028-09-01 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Northumberland | 6736 | SR 2016 over Millers Run | 2016 | 031 | Bridge Replacement | UTL | 185 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Northumberland | 6736 | SR 2016 over Millers Run | 2016 | 031 | Bridge Replacement | CON | 185 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 765000 | 1435000 | 0 | 0 | 0 | 2200000
SEDA-COG | 3 | Northumberland | 78935 | SR 225 over Mahantango Creek | 225 | 003 | Bridge Restoration | FD | BRIP | 2025-12-04 | 2025-12-04 | 80000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SEDA-COG | 3 | Northumberland | 78935 | SR 225 over Mahantango Creek | 225 | 003 | Bridge Restoration | ROW | BRIP | 2025-12-04 | 2025-12-04 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Northumberland | 78935 | SR 225 over Mahantango Creek | 225 | 003 | Bridge Restoration | CON | BRIP | 2025-12-04 | 2025-12-04 | 0 | 3200000 | 1170000 | 0 | 0 | 0 | 0 | 0 | 0 | 4370000
SEDA-COG | 3 | Northumberland | 79049 | SR 3018 over Mahantango Creek | 3018 | 002 | Bridge Restoration | PE | 185 | 2030-09-01 |  | 0 | 0 | 175000 | 175000 | 0 | 0 | 0 | 0 | 0 | 350000
SEDA-COG | 3 | Northumberland | 79049 | SR 3018 over Mahantango Creek | 3018 | 002 | Bridge Restoration | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 100000 | 150000 | 0 | 0 | 0 | 250000
SEDA-COG | 3 | Northumberland | 79049 | SR 3018 over Mahantango Creek | 3018 | 002 | Bridge Restoration | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 35000
SEDA-COG | 3 | Northumberland | 79049 | SR 3018 over Mahantango Creek | 3018 | 002 | Bridge Restoration | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 35000
SEDA-COG | 3 | Northumberland | 79049 | SR 3018 over Mahantango Creek | 3018 | 002 | Bridge Restoration | CON | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1115000 | 535000 | 0 | 1650000
SEDA-COG | 3 | Northumberland | 88778 | SR 54 over Unnamed Tributary to Shamokin Creek | 54 | 074 | Bridge Replacement | CON | STP | 2023-10-19 | 2023-10-19 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SEDA-COG | 3 | Northumberland | 88798 | Substructure Contract | 890 | 007 | Bridge Preservation - Federal | FD | 185 | 2027-01-14 |  | 0 | 135000 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Northumberland | 88798 | Substructure Contract | 890 | 007 | Bridge Preservation - Federal | ROW | 185 | 2027-01-14 |  | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000
SEDA-COG | 3 | Northumberland | 88798 | Substructure Contract | 890 | 007 | Bridge Preservation - Federal | UTL | 185 | 2027-01-14 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SEDA-COG | 3 | Northumberland | 88798 | Substructure Contract | 890 | 007 | Bridge Preservation - Federal | CON | STP | 2027-01-14 |  | 0 | 0 | 600000 | 1100000 | 0 | 0 | 0 | 0 | 0 | 1700000
SEDA-COG | 3 | Northumberland | 91430 | SR 125 over Carbon Run | 125 | 018 | Bridge Replacement | PE | STP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 0 | 0 | 400000
SEDA-COG | 3 | Northumberland | 91430 | SR 125 over Carbon Run | 125 | 018 | Bridge Replacement | FD | STP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 100000 | 0 | 250000
SEDA-COG | 3 | Northumberland | 91430 | SR 125 over Carbon Run | 125 | 018 | Bridge Replacement | ROW | STP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 35000
SEDA-COG | 3 | Northumberland | 91430 | SR 125 over Carbon Run | 125 | 018 | Bridge Replacement | UTL | STP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000
SEDA-COG | 3 | Northumberland | 91430 | SR 125 over Carbon Run | 125 | 018 | Bridge Replacement | CON | STP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550000 | 1550000
SEDA-COG | 3 | Northumberland | 97564 | I-80 East Bound Lane from SR 405 to Montour County | 80 | 133 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Northumberland | 97564 | I-80 East Bound Lane from SR 405 to Montour County | 80 | 133 | Highway Restoration | CON | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000 | 1300000
SEDA-COG | 3 | Northumberland | 97593 | Locust Gap to Locust Summit | 54 | 085 | Highway Restoration | FD | 581 | 2027-03-25 |  | 0 | 0 | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 51000
SEDA-COG | 3 | Northumberland | 97593 | Locust Gap to Locust Summit | 54 | 085 | Highway Restoration | CON | STP | 2027-03-25 |  | 0 | 0 | 432000 | 848000 | 0 | 0 | 0 | 0 | 0 | 1280000
SEDA-COG | 3 | Northumberland | 97655 | SR 54 to SR 4025 (Stein Rd) | 901 | 023 | Highway Reconstruction | PE | STP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000
SEDA-COG | 3 | Northumberland | 97655 | SR 54 to SR 4025 (Stein Rd) | 901 | 023 | Highway Reconstruction | FD | STP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
SEDA-COG | 3 | Northumberland | 97655 | SR 54 to SR 4025 (Stein Rd) | 901 | 023 | Highway Reconstruction | ROW | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000
SEDA-COG | 3 | Northumberland | 97655 | SR 54 to SR 4025 (Stein Rd) | 901 | 023 | Highway Reconstruction | UTL | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000
SEDA-COG | 3 | Northumberland | 97655 | SR 54 to SR 4025 (Stein Rd) | 901 | 023 | Highway Reconstruction | CON | STP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
SEDA-COG | 3 | Northumberland | 98531 | SR 1007 over Tributary of Warrior Run Creek | 1007 | 011 | Bridge Replacement | CON | 185 | 2024-01-11 | 2024-01-11 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SEDA-COG | 3 | Northumberland | 98674 | Acorn Drive to North of Housels Run Road | 405 | 095 | Highway Restoration | PE | STP | 2029-01-01 |  | 0 | 65000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
SEDA-COG | 3 | Northumberland | 98674 | Acorn Drive to North of Housels Run Road | 405 | 095 | Highway Restoration | FD | STP | 2029-01-01 |  | 0 | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
SEDA-COG | 3 | Northumberland | 98674 | Acorn Drive to North of Housels Run Road | 405 | 095 | Highway Restoration | ROW | STP | 2029-01-01 |  | 0 | 0 | 197000 | 6000 | 0 | 0 | 0 | 0 | 0 | 203000
SEDA-COG | 3 | Northumberland | 98674 | Acorn Drive to North of Housels Run Road | 405 | 095 | Highway Restoration | UTL | 581 | 2029-01-01 |  | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Northumberland | 98674 | Acorn Drive to North of Housels Run Road | 405 | 095 | Highway Restoration | CON | STP | 2029-01-01 |  | 0 | 0 | 0 | 502000 | 3648000 | 1250000 | 0 | 0 | 0 | 5400000
SEDA-COG | 3 | Northumberland | 99001 | SR 44 over Tb Chill Creek | 44 | 080 | Bridge Replacement | PE | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 125000 | 275000
SEDA-COG | 3 | Northumberland | 99001 | SR 44 over Tb Chill Creek | 44 | 080 | Bridge Replacement | FD | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000
SEDA-COG | 3 | Northumberland | 99001 | SR 44 over Tb Chill Creek | 44 | 080 | Bridge Replacement | ROW | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000
SEDA-COG | 3 | Northumberland | 99001 | SR 44 over Tb Chill Creek | 44 | 080 | Bridge Replacement | UTL | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 80000
SEDA-COG | 3 | Northumberland | 99001 | SR 44 over Tb Chill Creek | 44 | 080 | Bridge Replacement | CON | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 1800000
SEDA-COG | 3 | Northumberland | 99006 | SR 61 over Dark Run | 61 | 123 | Bridge Restoration | PE | NHPP | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 120000 | 320000
SEDA-COG | 3 | Northumberland | 99006 | SR 61 over Dark Run | 61 | 123 | Bridge Restoration | FD | NHPP | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275000 | 275000
SEDA-COG | 3 | Northumberland | 99006 | SR 61 over Dark Run | 61 | 123 | Bridge Restoration | ROW | NHPP | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Northumberland | 99006 | SR 61 over Dark Run | 61 | 123 | Bridge Restoration | UTL | NHPP | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Northumberland | 99006 | SR 61 over Dark Run | 61 | 123 | Bridge Restoration | CON | NHPP | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
SEDA-COG | 3 | Northumberland | 99009 | SR 61 over SR 2026 & 901 | 61 | 122 | Bridge Restoration | PE | 185 | 2031-09-01 |  | 0 | 0 | 144000 | 256000 | 0 | 0 | 0 | 0 | 0 | 400000
SEDA-COG | 3 | Northumberland | 99009 | SR 61 over SR 2026 & 901 | 61 | 122 | Bridge Restoration | FD | NHPP | 2031-09-01 |  | 0 | 0 | 0 | 175000 | 125000 | 0 | 0 | 0 | 0 | 300000
SEDA-COG | 3 | Northumberland | 99009 | SR 61 over SR 2026 & 901 | 61 | 122 | Bridge Restoration | ROW | NHPP | 2031-09-01 |  | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 40000
SEDA-COG | 3 | Northumberland | 99009 | SR 61 over SR 2026 & 901 | 61 | 122 | Bridge Restoration | UTL | NHPP | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 40000
SEDA-COG | 3 | Northumberland | 99009 | SR 61 over SR 2026 & 901 | 61 | 122 | Bridge Restoration | CON | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1095000 | 1538000 | 1200000 | 3833000
SEDA-COG | 3 | Northumberland | 99177 | Ridge Rd (SR 1024) to Montour County Line | 11 | 118 | Highway Restoration | FD | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Northumberland | 99177 | Ridge Rd (SR 1024) to Montour County Line | 11 | 118 | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 2250000 | 1000000 | 1250000 | 5500000
SEDA-COG | 3 | Northumberland | 99238 | SR 54 Soil Slide Repair | 54 | 086 | Highway Reconstruction | PE | 581 | 2032-01-01 |  | 0 | 0 | 0 | 100000 | 50000 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Northumberland | 99238 | SR 54 Soil Slide Repair | 54 | 086 | Highway Reconstruction | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 225000 | 0 | 0 | 275000
SEDA-COG | 3 | Northumberland | 99238 | SR 54 Soil Slide Repair | 54 | 086 | Highway Reconstruction | ROW | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 100000
SEDA-COG | 3 | Northumberland | 99238 | SR 54 Soil Slide Repair | 54 | 086 | Highway Reconstruction | UTL | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
SEDA-COG | 3 | Northumberland | 99238 | SR 54 Soil Slide Repair | 54 | 086 | Highway Reconstruction | CON | STP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 4300000 | 4500000
SEDA-COG | 3 | Northumberland | 99243 | SR 44 & SR 1006 ; SR 44 & SR 1014 Intersections | 44 | 044 | Safety Improvement | PE | 581 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 550000
SEDA-COG | 3 | Northumberland | 99243 | SR 44 & SR 1006 ; SR 44 & SR 1014 Intersections | 44 | 044 | Safety Improvement | FD | 581 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 550000
SEDA-COG | 3 | Northumberland | 99243 | SR 44 & SR 1006 ; SR 44 & SR 1014 Intersections | 44 | 044 | Safety Improvement | CON | 581 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500000 | 7500000
SEDA-COG | 3 | Northumberland | 99317 | PA 147 Major Guide Sign | 147 | 146 | Highway Restoration | FD | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 10000
SEDA-COG | 3 | Northumberland | 99317 | PA 147 Major Guide Sign | 147 | 146 | Highway Restoration | CON | NHPP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 0 | 600000
SEDA-COG | 3 | Northumberland | 99327 | 16th St to 4th St | 61 | 118 | Highway Reconstruction | PE | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 100000 | 738000 | 0 | 0 | 0 | 0 | 838000
SEDA-COG | 3 | Northumberland | 99327 | 16th St to 4th St | 61 | 118 | Highway Reconstruction | PE | STP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 409000 | 0 | 0 | 0 | 0 | 409000
SEDA-COG | 3 | Northumberland | 99327 | 16th St to 4th St | 61 | 118 | Highway Reconstruction | FD | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 750000 | 150000 | 0 | 0 | 900000
SEDA-COG | 3 | Northumberland | 99327 | 16th St to 4th St | 61 | 118 | Highway Reconstruction | FD | STP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Northumberland | 99327 | 16th St to 4th St | 61 | 118 | Highway Reconstruction | ROW | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 650000 | 350000 | 0 | 0 | 1000000
SEDA-COG | 3 | Northumberland | 99327 | 16th St to 4th St | 61 | 118 | Highway Reconstruction | ROW | STP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 250000
SEDA-COG | 3 | Northumberland | 99327 | 16th St to 4th St | 61 | 118 | Highway Reconstruction | UTL | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 700000 | 150000 | 1100000
SEDA-COG | 3 | Northumberland | 99327 | 16th St to 4th St | 61 | 118 | Highway Reconstruction | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 3250000 | 4485000 | 10235000
SEDA-COG | 3 | Northumberland | 99329 | Shamokin Creek to 4 Lane | 61 | 117 | Highway Reconstruction | PE | NHPP | 2036-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450000 | 1450000
SEDA-COG | 3 | Northumberland | 99329 | Shamokin Creek to 4 Lane | 61 | 117 | Highway Reconstruction | FD | STP | 2036-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1072000 | 1072000
SEDA-COG | 3 | Northumberland | 99390 | I-180 to PA 44 | 54 | 097 | Highway Restoration | FD | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
SEDA-COG | 3 | Northumberland | 99390 | I-180 to PA 44 | 54 | 097 | Highway Restoration | CON | STP | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 700000 | 2250000 | 1300000 | 0 | 4250000
SEDA-COG | 3 | Northumberland | 99391 | Kulpmont to Lancaster Switch | 61 | 124 | Highway Restoration | CON | NHPP | 2026-07-02 |  | 0 | 2557778 | 1485000 | 0 | 0 | 0 | 0 | 0 | 0 | 4042778
SEDA-COG | 3 | Northumberland | 99391 | Kulpmont to Lancaster Switch | 61 | 124 | Highway Restoration | CON | STP | 2026-07-02 |  | 0 | 7222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7222
SEDA-COG | 3 | Northumberland | 102810 | CSVT to SR 11 | 1024 | 88H | Highway Restoration | PE | 581 | 2027-12-09 |  | 3010000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3010000
SEDA-COG | 3 | Northumberland | 102810 | CSVT to SR 11 | 1024 | 88H | Highway Restoration | FD | 581 | 2027-12-09 |  | 750000 | 1835309 | 414691 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SEDA-COG | 3 | Northumberland | 102810 | CSVT to SR 11 | 1024 | 88H | Highway Restoration | ROW | 581 | 2027-12-09 |  | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SEDA-COG | 3 | Northumberland | 102810 | CSVT to SR 11 | 1024 | 88H | Highway Restoration | UTL | 581 | 2027-12-09 |  | 0 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000
SEDA-COG | 3 | Northumberland | 102810 | CSVT to SR 11 | 1024 | 88H | Highway Restoration | CON | 581 | 2027-12-09 |  | 0 | 12000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 17000000
SEDA-COG | 3 | Northumberland | 103917 | T-696 over Plum Creek |  | LBR | Bridge Replacement | FD | BOF | 2027-01-16 |  | 0 | 112000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112000
SEDA-COG | 3 | Northumberland | 103917 | T-696 over Plum Creek |  | LBR | Bridge Replacement | FD | 183 | 2027-01-16 |  | 0 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000
SEDA-COG | 3 | Northumberland | 103917 | T-696 over Plum Creek |  | LBR | Bridge Replacement | FD | LOC | 2027-01-16 |  | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000
SEDA-COG | 3 | Northumberland | 103917 | T-696 over Plum Creek |  | LBR | Bridge Replacement | ROW | BOF | 2027-01-16 |  | 0 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
SEDA-COG | 3 | Northumberland | 103917 | T-696 over Plum Creek |  | LBR | Bridge Replacement | ROW | 183 | 2027-01-16 |  | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
SEDA-COG | 3 | Northumberland | 103917 | T-696 over Plum Creek |  | LBR | Bridge Replacement | ROW | LOC | 2027-01-16 |  | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
SEDA-COG | 3 | Northumberland | 103917 | T-696 over Plum Creek |  | LBR | Bridge Replacement | UTL | BOF | 2027-01-16 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
SEDA-COG | 3 | Northumberland | 103917 | T-696 over Plum Creek |  | LBR | Bridge Replacement | UTL | 183 | 2027-01-16 |  | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
SEDA-COG | 3 | Northumberland | 103917 | T-696 over Plum Creek |  | LBR | Bridge Replacement | UTL | LOC | 2027-01-16 |  | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
SEDA-COG | 3 | Northumberland | 103917 | T-696 over Plum Creek |  | LBR | Bridge Replacement | CON | BOF | 2027-01-16 |  | 0 | 0 | 816000 | 384000 | 0 | 0 | 0 | 0 | 0 | 1200000
SEDA-COG | 3 | Northumberland | 103917 | T-696 over Plum Creek |  | LBR | Bridge Replacement | CON | 183 | 2027-01-16 |  | 0 | 0 | 153000 | 72000 | 0 | 0 | 0 | 0 | 0 | 225000
SEDA-COG | 3 | Northumberland | 103917 | T-696 over Plum Creek |  | LBR | Bridge Replacement | CON | LOC | 2027-01-16 |  | 0 | 0 | 51000 | 24000 | 0 | 0 | 0 | 0 | 0 | 75000
SEDA-COG | 3 | Northumberland | 103928 | 8th St over Shamokin Crk |  | LBR | Bridge Restoration | PE | BOF | 2026-08-13 |  | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56000
SEDA-COG | 3 | Northumberland | 103928 | 8th St over Shamokin Crk |  | LBR | Bridge Restoration | PE | 183 | 2026-08-13 |  | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250
SEDA-COG | 3 | Northumberland | 103928 | 8th St over Shamokin Crk |  | LBR | Bridge Restoration | PE | ACT13 | 2026-08-13 |  | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750
SEDA-COG | 3 | Northumberland | 103928 | 8th St over Shamokin Crk |  | LBR | Bridge Restoration | FD | BOF | 2026-08-13 |  | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
SEDA-COG | 3 | Northumberland | 103928 | 8th St over Shamokin Crk |  | LBR | Bridge Restoration | FD | 183 | 2026-08-13 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Northumberland | 103928 | 8th St over Shamokin Crk |  | LBR | Bridge Restoration | ROW | BOF | 2026-08-13 |  | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
SEDA-COG | 3 | Northumberland | 103928 | 8th St over Shamokin Crk |  | LBR | Bridge Restoration | ROW | 183 | 2026-08-13 |  | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
SEDA-COG | 3 | Northumberland | 103928 | 8th St over Shamokin Crk |  | LBR | Bridge Restoration | UTL | BOF | 2026-08-13 |  | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
SEDA-COG | 3 | Northumberland | 103928 | 8th St over Shamokin Crk |  | LBR | Bridge Restoration | UTL | 183 | 2026-08-13 |  | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
SEDA-COG | 3 | Northumberland | 103928 | 8th St over Shamokin Crk |  | LBR | Bridge Restoration | CON | BOF | 2026-08-13 |  | 0 | 1600000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000
SEDA-COG | 3 | Northumberland | 103928 | 8th St over Shamokin Crk |  | LBR | Bridge Restoration | CON | 183 | 2026-08-13 |  | 0 | 300000 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 337500
SEDA-COG | 3 | Northumberland | 103928 | 8th St over Shamokin Crk |  | LBR | Bridge Restoration | CON | LOC | 2026-08-13 |  | 0 | 100000 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 112500
SEDA-COG | 3 | Northumberland | 105519 | I-80 West Bound Lane from Union Co to Montour Co | 80 | 155 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Northumberland | 105519 | I-80 West Bound Lane from Union Co to Montour Co | 80 | 155 | Highway Restoration | CON | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000 | 1300000
SEDA-COG | 3 | Northumberland | 108431 | Miles Rd to Hollow Rd (SR 4015) | 61 | 126 | Highway Restoration | FD | 581 | 2029-01-01 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Northumberland | 108431 | Miles Rd to Hollow Rd (SR 4015) | 61 | 126 | Highway Restoration | CON | STP | 2029-01-01 |  | 0 | 0 | 0 | 200000 | 480000 | 0 | 0 | 0 | 0 | 680000
SEDA-COG | 3 | Northumberland | 109360 | SR 54 to I-80 WB | 180 | 135 | Highway Restoration | FD | 581 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Northumberland | 109360 | SR 54 to I-80 WB | 180 | 135 | Highway Restoration | CON | NHPP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
SEDA-COG | 3 | Northumberland | 109577 | I-80 over SR 254 & Limestone Run | 80 | 172 | Bridge Restoration | FD | BRIP | 2026-09-17 |  | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
SEDA-COG | 3 | Northumberland | 109577 | I-80 over SR 254 & Limestone Run | 80 | 172 | Bridge Restoration | CON | NHPP | 2026-09-17 |  | 0 | 1202000 | 2040000 | 0 | 0 | 0 | 0 | 0 | 0 | 3242000
SEDA-COG | 3 | Northumberland | 109833 | SR 405 (CSVT Gap) from Eighth St to Acorn Drive | 405 | 110 | Highway Restoration | CON | NHPP | 2025-07-24 | 2025-07-24 | 2314529 | 822000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3136529
SEDA-COG | 3 | Northumberland | 110224 | 5th St to Dark Run | 61 | 131 | Highway Restoration | CON | NHPP | 2026-07-02 |  | 0 | 1788000 | 323000 | 0 | 0 | 0 | 0 | 0 | 0 | 2111000
SEDA-COG | 3 | Northumberland | 110829 | SR 61 - Paxinos Drainage | 61 | 132 | Highway Restoration | FD | 581 | 2025-05-22 | 2025-05-22 | 30000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
SEDA-COG | 3 | Northumberland | 110829 | SR 61 - Paxinos Drainage | 61 | 132 | Highway Restoration | CON | 581 | 2025-05-22 | 2025-05-22 | 675000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775000
SEDA-COG | 3 | Northumberland | 111352 | SVRR RRX Northumberland County | 487 | 14R | Rail Highway Grade Crossing | CON | RRX | 2023-04-01 | 2023-04-01 | 2221018 | 115374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2336392
SEDA-COG | 3 | Northumberland | 111760 | SR 44 to River Rd | 405 | 097 | General Maintenance | CON | 581 | 2024-12-12 | 2024-12-12 | 2710000 | 490000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200000
SEDA-COG | 3 | Northumberland | 114134 | SR 1016 over Muddy Run | 1016 | 009 | Bridge Replacement | FD | 185 | 2025-12-11 | 2025-12-11 | 75000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
SEDA-COG | 3 | Northumberland | 114134 | SR 1016 over Muddy Run | 1016 | 009 | Bridge Replacement | ROW | 185 | 2025-12-11 | 2025-12-11 | 20000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
SEDA-COG | 3 | Northumberland | 114134 | SR 1016 over Muddy Run | 1016 | 009 | Bridge Replacement | UTL | 185 | 2025-12-11 | 2025-12-11 | 0 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Northumberland | 114134 | SR 1016 over Muddy Run | 1016 | 009 | Bridge Replacement | CON | 185 | 2025-12-11 | 2025-12-11 | 0 | 365000 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SEDA-COG | 3 | Northumberland | 114142 | SR 3003 over Mouse Creek | 3003 | 027 | Bridge Replacement | FD | 185 | 2027-09-16 |  | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Northumberland | 114142 | SR 3003 over Mouse Creek | 3003 | 027 | Bridge Replacement | ROW | 185 | 2027-09-16 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SEDA-COG | 3 | Northumberland | 114142 | SR 3003 over Mouse Creek | 3003 | 027 | Bridge Replacement | UTL | 185 | 2027-09-16 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SEDA-COG | 3 | Northumberland | 114142 | SR 3003 over Mouse Creek | 3003 | 027 | Bridge Replacement | CON | 185 | 2027-09-16 |  | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000
SEDA-COG | 3 | Northumberland | 114158 | SR 4012 over UNT to Shamokin Creek | 4012 | 040 | Bridge Replacement | PE | 185 | 2028-09-14 |  | 0 | 175000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
SEDA-COG | 3 | Northumberland | 114158 | SR 4012 over UNT to Shamokin Creek | 4012 | 040 | Bridge Replacement | FD | 185 | 2028-09-14 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Northumberland | 114158 | SR 4012 over UNT to Shamokin Creek | 4012 | 040 | Bridge Replacement | ROW | 185 | 2028-09-14 |  | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Northumberland | 114158 | SR 4012 over UNT to Shamokin Creek | 4012 | 040 | Bridge Replacement | UTL | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Northumberland | 114158 | SR 4012 over UNT to Shamokin Creek | 4012 | 040 | Bridge Replacement | CON | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 300000 | 200000 | 0 | 0 | 0 | 500000
SEDA-COG | 3 | Northumberland | 114175 | SR 4004 over Tributary of Susquehanna River | 4004 | 018 | Bridge Replacement | PE | 185 | 2029-09-01 |  | 0 | 0 | 150000 | 125000 | 0 | 0 | 0 | 0 | 0 | 275000
SEDA-COG | 3 | Northumberland | 114175 | SR 4004 over Tributary of Susquehanna River | 4004 | 018 | Bridge Replacement | FD | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Northumberland | 114175 | SR 4004 over Tributary of Susquehanna River | 4004 | 018 | Bridge Replacement | ROW | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 35000
SEDA-COG | 3 | Northumberland | 114175 | SR 4004 over Tributary of Susquehanna River | 4004 | 018 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Northumberland | 114175 | SR 4004 over Tributary of Susquehanna River | 4004 | 018 | Bridge Replacement | CON | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 260000 | 240000 | 0 | 0 | 500000
SEDA-COG | 3 | Northumberland | 115506 | Natalie to SR 487 | 54 | 111 | Highway Restoration | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 100000 | 0 | 150000
SEDA-COG | 3 | Northumberland | 115506 | Natalie to SR 487 | 54 | 111 | Highway Restoration | CON | STP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600000 | 5600000
SEDA-COG | 3 | Northumberland | 115506 | Natalie to SR 487 | 54 | 111 | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 1400000
SEDA-COG | 3 | Northumberland | 115507 | Water St to SR 147 | 45 | 038 | Highway Restoration | FD | 581 | 2029-01-01 |  | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
SEDA-COG | 3 | Northumberland | 115507 | Water St to SR 147 | 45 | 038 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
SEDA-COG | 3 | Northumberland | 115508 | SR 487 to Logan Run | 54 | 112 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Northumberland | 115508 | SR 487 to Logan Run | 54 | 112 | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
SEDA-COG | 3 | Northumberland | 115509 | Pine St to Montour Co | 44 | 089 | Highway Restoration | CON | STP | 2026-02-26 | 2026-02-26 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Northumberland | 115579 | North'd SR 254 Grind & Patch | 254 | 058 | Highway Restoration | PE | 581 | 2027-04-29 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Northumberland | 115579 | North'd SR 254 Grind & Patch | 254 | 058 | Highway Restoration | FD | 581 | 2027-04-29 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Northumberland | 115581 | PA 45 to Muddy Run | 147 | 131 | 409 Expanded Maintenance | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000
SEDA-COG | 3 | Northumberland | 115582 | Muddy Run to I-80 | 147 | 132 | 409 Expanded Maintenance | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000
SEDA-COG | 3 | Northumberland | 115584 | Church St to Shikellamy Ave | 405 | 109 | Highway Restoration | PE | NHPP | 2026-01-29 | 2026-01-29 | 334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334
SEDA-COG | 3 | Northumberland | 115584 | Church St to Shikellamy Ave | 405 | 109 | Highway Restoration | FD | 581 | 2026-01-29 | 2026-01-29 | 112000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212000
SEDA-COG | 3 | Northumberland | 115584 | Church St to Shikellamy Ave | 405 | 109 | Highway Restoration | CON | BRIP | 2026-01-29 | 2026-01-29 | 0 | 562000 | 560000 | 200000 | 0 | 0 | 0 | 0 | 0 | 1322000
SEDA-COG | 3 | Northumberland | 115584 | Church St to Shikellamy Ave | 405 | 109 | Highway Restoration | CON | NHPP | 2026-01-29 | 2026-01-29 | 0 | 414000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 439000
SEDA-COG | 3 | Northumberland | 115584 | Church St to Shikellamy Ave | 405 | 109 | Highway Restoration | CON | STP | 2026-01-29 | 2026-01-29 | 0 | 1141604 | 750000 | 600000 | 0 | 0 | 0 | 0 | 0 | 2491604
SEDA-COG | 3 | Northumberland | 116005 | SR 61 to Ash St | 2026 | 006 | Highway Restoration | CON | 581 | 2026-07-02 |  | 0 | 100000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SEDA-COG | 3 | Northumberland | 117540 | SR 1011 over Branch of Warrior Run | 1011 | 033 | Bridge Replacement | PE | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 110000 | 110000 | 0 | 0 | 220000
SEDA-COG | 3 | Northumberland | 117540 | SR 1011 over Branch of Warrior Run | 1011 | 033 | Bridge Replacement | FD | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 120000
SEDA-COG | 3 | Northumberland | 117540 | SR 1011 over Branch of Warrior Run | 1011 | 033 | Bridge Replacement | ROW | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 35000
SEDA-COG | 3 | Northumberland | 117540 | SR 1011 over Branch of Warrior Run | 1011 | 033 | Bridge Replacement | UTL | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000
SEDA-COG | 3 | Northumberland | 117540 | SR 1011 over Branch of Warrior Run | 1011 | 033 | Bridge Replacement | CON | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
SEDA-COG | 3 | Northumberland | 117608 | SR 3018 over Mahantango Creek | 3018 | 014 | Bridge Restoration | FD | BRIP | 2025-12-04 | 2025-12-04 | 175000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
SEDA-COG | 3 | Northumberland | 117608 | SR 3018 over Mahantango Creek | 3018 | 014 | Bridge Restoration | ROW | 185 | 2025-12-04 | 2025-12-04 | 11245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11245
SEDA-COG | 3 | Northumberland | 117608 | SR 3018 over Mahantango Creek | 3018 | 014 | Bridge Restoration | CON | BRIP | 2025-12-04 | 2025-12-04 | 0 | 1238000 | 1162000 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000
SEDA-COG | 3 | Northumberland | 117615 | SR 11 over W Branch Susquehanna River | 11 | 170 | Bridge Restoration | PE | 185 | 2027-01-14 |  | 16250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16250
SEDA-COG | 3 | Northumberland | 117615 | SR 11 over W Branch Susquehanna River | 11 | 170 | Bridge Restoration | FD | BRIP | 2027-01-14 |  | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
SEDA-COG | 3 | Northumberland | 117615 | SR 11 over W Branch Susquehanna River | 11 | 170 | Bridge Restoration | ROW | BRIP | 2027-01-14 |  | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500
SEDA-COG | 3 | Northumberland | 117615 | SR 11 over W Branch Susquehanna River | 11 | 170 | Bridge Restoration | CON | BRIP | 2027-01-14 |  | 0 | 0 | 2500000 | 820000 | 0 | 0 | 0 | 0 | 0 | 3320000
SEDA-COG | 3 | Northumberland | 117615 | SR 11 over W Branch Susquehanna River | 11 | 170 | Bridge Restoration | CON | NHPP | 2027-01-14 |  | 0 | 0 | 0 | 2250000 | 1500000 | 0 | 0 | 0 | 0 | 3750000
SEDA-COG | 3 | Northumberland | 117615 | SR 11 over W Branch Susquehanna River | 11 | 170 | Bridge Restoration | CON | STP | 2027-01-14 |  | 0 | 0 | 0 | 530000 | 0 | 0 | 0 | 0 | 0 | 530000
SEDA-COG | 3 | Northumberland | 117764 | Lycoming County to SR 54 WB | 180 | 148 | Highway Restoration | FD | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Northumberland | 117764 | Lycoming County to SR 54 WB | 180 | 148 | Highway Restoration | CON | NHPP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 600000 | 400000 | 0 | 0 | 0 | 1000000
SEDA-COG | 3 | Northumberland | 117772 | Lycoming County to SR 54 EB | 180 | 149 | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Northumberland | 117772 | Lycoming County to SR 54 EB | 180 | 149 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 400000 | 600000 | 0 | 0 | 0 | 1000000
SEDA-COG | 3 | Northumberland | 118290 | Lycoming Co Line to River Rd | 54 | 119 | Highway Restoration | CON | 581 | 2024-12-12 | 2024-12-12 | 0 | 150000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SEDA-COG | 3 | Northumberland | 118341 | 10th St. to 11th St. | 61 | 01E | Transportation Enhancement | CON | TAP | 2026-12-10 |  | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SEDA-COG | 3 | Northumberland | 119249 | Columbia Co to 5th St | 61 | 138 | Highway Restoration | FD | 581 | 2028-01-01 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Northumberland | 119249 | Columbia Co to 5th St | 61 | 138 | Highway Restoration | CON | NHPP | 2028-01-01 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Northumberland | 119249 | Columbia Co to 5th St | 61 | 138 | Highway Restoration | CON | STP | 2028-01-01 |  | 0 | 0 | 0 | 870000 | 0 | 0 | 0 | 0 | 0 | 870000
SEDA-COG | 3 | Northumberland | 119490 | Market St to Shamokin St |  | EM1 | Transportation Enhancement | FD | SXF | 2025-11-06 | 2025-11-06 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SEDA-COG | 3 | Northumberland | 119490 | Market St to Shamokin St |  | EM1 | Transportation Enhancement | CON | SXF | 2025-11-06 | 2025-11-06 | 1793000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1793000
SEDA-COG | 3 | Northumberland | 119833 | SR 54 Park and Ride Pipe Replacement | 54 | 121 | Highway Restoration | CON | 581 | 2024-12-12 | 2024-12-12 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
SEDA-COG | 3 | Northumberland | 119893 | Northumberland Co 2025 Bridge Flushing |  |  | Bridge Preservation - State Funded | CON | 185 | 2025-05-08 | 2025-05-08 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Northumberland | 120602 | I-180 & SR 147 HTCMB Northumberland County | 180 | 153 | Safety Improvement | CON | HSIP | 2025-03-27 | 2025-03-27 | 2787890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2787890
SEDA-COG | 3 | Northumberland | 120757 | Acess Rd Montandon | 45 | MTF | MultiModal | FD | 411 |  |  | 11100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11100
SEDA-COG | 3 | Northumberland | 120757 | Acess Rd Montandon | 45 | MTF | MultiModal | FD | LOC |  |  | 135299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135299
SEDA-COG | 3 | Northumberland | 120757 | Acess Rd Montandon | 45 | MTF | MultiModal | CON | 411 |  |  | 563430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563430
SEDA-COG | 3 | Northumberland | 120913 | Willow Street over Shamokin Creek |  | LBR | Bridge Replacement | PE | BOF | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 0 | 400000
SEDA-COG | 3 | Northumberland | 120913 | Willow Street over Shamokin Creek |  | LBR | Bridge Replacement | PE | 183 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 75000
SEDA-COG | 3 | Northumberland | 120913 | Willow Street over Shamokin Creek |  | LBR | Bridge Replacement | FD | BOF | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 280000
SEDA-COG | 3 | Northumberland | 120913 | Willow Street over Shamokin Creek |  | LBR | Bridge Replacement | FD | 183 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52500 | 52500
SEDA-COG | 3 | Northumberland | 120913 | Willow Street over Shamokin Creek |  | LBR | Bridge Replacement | ROW | BOF | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Northumberland | 120913 | Willow Street over Shamokin Creek |  | LBR | Bridge Replacement | ROW | 183 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500
SEDA-COG | 3 | Northumberland | 120913 | Willow Street over Shamokin Creek |  | LBR | Bridge Replacement | UTL | BOF | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Northumberland | 120913 | Willow Street over Shamokin Creek |  | LBR | Bridge Replacement | UTL | 183 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500
SEDA-COG | 3 | Northumberland | 120913 | Willow Street over Shamokin Creek |  | LBR | Bridge Replacement | CON | BOF | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 2200000
SEDA-COG | 3 | Northumberland | 120913 | Willow Street over Shamokin Creek |  | LBR | Bridge Replacement | CON | 183 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412500 | 412500
SEDA-COG | 3 | Northumberland | 120917 | Bridge Road over Chillisquaque Creek |  | LBR | Bridge Restoration | PE | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 320000 | 80000 | 0 | 0 | 0 | 400000
SEDA-COG | 3 | Northumberland | 120917 | Bridge Road over Chillisquaque Creek |  | LBR | Bridge Restoration | PE | 183 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 60000 | 15000 | 0 | 0 | 0 | 75000
SEDA-COG | 3 | Northumberland | 120917 | Bridge Road over Chillisquaque Creek |  | LBR | Bridge Restoration | FD | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 0 | 0 | 280000
SEDA-COG | 3 | Northumberland | 120917 | Bridge Road over Chillisquaque Creek |  | LBR | Bridge Restoration | FD | 183 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 52500 | 0 | 0 | 52500
SEDA-COG | 3 | Northumberland | 120917 | Bridge Road over Chillisquaque Creek |  | LBR | Bridge Restoration | ROW | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 40000
SEDA-COG | 3 | Northumberland | 120917 | Bridge Road over Chillisquaque Creek |  | LBR | Bridge Restoration | ROW | 183 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 7500
SEDA-COG | 3 | Northumberland | 120917 | Bridge Road over Chillisquaque Creek |  | LBR | Bridge Restoration | UTL | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 40000
SEDA-COG | 3 | Northumberland | 120917 | Bridge Road over Chillisquaque Creek |  | LBR | Bridge Restoration | UTL | 183 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500
SEDA-COG | 3 | Northumberland | 120917 | Bridge Road over Chillisquaque Creek |  | LBR | Bridge Restoration | CON | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720000 | 720000 | 1440000
SEDA-COG | 3 | Northumberland | 120917 | Bridge Road over Chillisquaque Creek |  | LBR | Bridge Restoration | CON | 183 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 135000 | 270000
SEDA-COG | 3 | Northumberland | 120918 | SR 2010 over Shamokin Creek | 2010 | 025 | Bridge Restoration | PE | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000
SEDA-COG | 3 | Northumberland | 120918 | SR 2010 over Shamokin Creek | 2010 | 025 | Bridge Restoration | FD | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
SEDA-COG | 3 | Northumberland | 120918 | SR 2010 over Shamokin Creek | 2010 | 025 | Bridge Restoration | ROW | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 55000
SEDA-COG | 3 | Northumberland | 120918 | SR 2010 over Shamokin Creek | 2010 | 025 | Bridge Restoration | UTL | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 55000
SEDA-COG | 3 | Northumberland | 120918 | SR 2010 over Shamokin Creek | 2010 | 025 | Bridge Restoration | CON | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 1400000
SEDA-COG | 3 | Northumberland | 121022 | West of Shamokin Creek | 2013 | 009 | Highway Restoration | STUDY | 581 |  |  | 0 | 50000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Northumberland | 121036 | T-630 over Delaware Run |  | LBR | Bridge Restoration | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000
SEDA-COG | 3 | Northumberland | 121036 | T-630 over Delaware Run |  | LBR | Bridge Restoration | PE | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000
SEDA-COG | 3 | Northumberland | 121036 | T-630 over Delaware Run |  | LBR | Bridge Restoration | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 280000
SEDA-COG | 3 | Northumberland | 121036 | T-630 over Delaware Run |  | LBR | Bridge Restoration | FD | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52500 | 52500
SEDA-COG | 3 | Northumberland | 121036 | T-630 over Delaware Run |  | LBR | Bridge Restoration | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Northumberland | 121036 | T-630 over Delaware Run |  | LBR | Bridge Restoration | ROW | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500
SEDA-COG | 3 | Northumberland | 121036 | T-630 over Delaware Run |  | LBR | Bridge Restoration | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Northumberland | 121036 | T-630 over Delaware Run |  | LBR | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500
SEDA-COG | 3 | Northumberland | 121036 | T-630 over Delaware Run |  | LBR | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 1600000
SEDA-COG | 3 | Northumberland | 121036 | T-630 over Delaware Run |  | LBR | Bridge Restoration | CON | 183 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
SEDA-COG | 3 | Northumberland | 121501 | Race Street to Packer Street | 405 | 115 | Transportation Enhancement | CON | TAP | 2028-01-01 |  | 0 | 0 | 1429865 | 0 | 0 | 0 | 0 | 0 | 0 | 1429865
SEDA-COG | 3 | Northumberland | 121660 | Hamilton Underpass | 61 | 139 | Highway Restoration | STUDY | 581 |  |  | 0 | 86000 | 114000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Northumberland | 121840 | 2nd St. and Front St. |  | 07L | Highway Restoration | CON | STP | 2025-04-17 | 2025-04-17 | 1330000 | 207000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1537000
SEDA-COG | 3 | Northumberland | 122180 | SR 405 Handrail and Sidewalk | 405 | 116 | Bicycle Pedestrian Highway | CON | STP | 2025-04-17 | 2025-04-17 | 447000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447000
SEDA-COG | 3 | Northumberland | 122336 | SR 225 over Mahanoy Creek (Emergency Repair) | 225 | 054 | General Maintenance | CON | 185 | 2025-01-20 | 2025-02-12 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Northumberland | 122584 | Montandon SCM Sink Hole | 45 | 047 | Stormwater Management | STUDY | 581 |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Northumberland | 123336 | SEDA-COG Lane Departure Safety Improvement | 54 | 133 | Safety Improvement | PE | HSIP | 2028-01-01 |  | 0 | 133000 | 359000 | 0 | 0 | 0 | 0 | 0 | 0 | 492000
SEDA-COG | 3 | Northumberland | 123336 | SEDA-COG Lane Departure Safety Improvement | 54 | 133 | Safety Improvement | FD | HSIP | 2028-01-01 |  | 0 | 0 | 363000 | 128000 | 0 | 0 | 0 | 0 | 0 | 491000
SEDA-COG | 3 | Northumberland | 123336 | SEDA-COG Lane Departure Safety Improvement | 54 | 133 | Safety Improvement | CON | HSIP | 2028-01-01 |  | 0 | 0 | 0 | 1263000 | 1195000 | 0 | 0 | 0 | 0 | 2458000
SEDA-COG | 3 | Snyder | 6797 | SR 3016 over Aline Creek | 3016 | 001 | Bridge Replacement | PE | 185 | 2028-09-14 |  | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
SEDA-COG | 3 | Snyder | 6797 | SR 3016 over Aline Creek | 3016 | 001 | Bridge Replacement | FD | 185 | 2028-09-14 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Snyder | 6797 | SR 3016 over Aline Creek | 3016 | 001 | Bridge Replacement | ROW | 185 | 2028-09-14 |  | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Snyder | 6797 | SR 3016 over Aline Creek | 3016 | 001 | Bridge Replacement | UTL | 185 | 2028-09-14 |  | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Snyder | 6797 | SR 3016 over Aline Creek | 3016 | 001 | Bridge Replacement | CON | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 244000 | 250000 | 0 | 0 | 0 | 494000
SEDA-COG | 3 | Snyder | 6860 | T-481 over Tuscarora Crk |  | LBR | Bridge Replacement | PE | BOF | 2027-01-01 |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
SEDA-COG | 3 | Snyder | 6860 | T-481 over Tuscarora Crk |  | LBR | Bridge Replacement | PE | 183 | 2027-01-01 |  | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250
SEDA-COG | 3 | Snyder | 6860 | T-481 over Tuscarora Crk |  | LBR | Bridge Replacement | PE | LOC | 2027-01-01 |  | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
SEDA-COG | 3 | Snyder | 6860 | T-481 over Tuscarora Crk |  | LBR | Bridge Replacement | FD | BOF | 2027-01-01 |  | 40000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
SEDA-COG | 3 | Snyder | 6860 | T-481 over Tuscarora Crk |  | LBR | Bridge Replacement | FD | 183 | 2027-01-01 |  | 7500 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500
SEDA-COG | 3 | Snyder | 6860 | T-481 over Tuscarora Crk |  | LBR | Bridge Replacement | FD | LOC | 2027-01-01 |  | 2500 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
SEDA-COG | 3 | Snyder | 6860 | T-481 over Tuscarora Crk |  | LBR | Bridge Replacement | ROW | BOF | 2027-01-01 |  | 0 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
SEDA-COG | 3 | Snyder | 6860 | T-481 over Tuscarora Crk |  | LBR | Bridge Replacement | ROW | 183 | 2027-01-01 |  | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
SEDA-COG | 3 | Snyder | 6860 | T-481 over Tuscarora Crk |  | LBR | Bridge Replacement | ROW | LOC | 2027-01-01 |  | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
SEDA-COG | 3 | Snyder | 6860 | T-481 over Tuscarora Crk |  | LBR | Bridge Replacement | UTL | BOF | 2027-01-01 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
SEDA-COG | 3 | Snyder | 6860 | T-481 over Tuscarora Crk |  | LBR | Bridge Replacement | UTL | 183 | 2027-01-01 |  | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
SEDA-COG | 3 | Snyder | 6860 | T-481 over Tuscarora Crk |  | LBR | Bridge Replacement | UTL | LOC | 2027-01-01 |  | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
SEDA-COG | 3 | Snyder | 6860 | T-481 over Tuscarora Crk |  | LBR | Bridge Replacement | CON | BOF | 2027-01-01 |  | 0 | 600000 | 680000 | 0 | 0 | 0 | 0 | 0 | 0 | 1280000
SEDA-COG | 3 | Snyder | 6860 | T-481 over Tuscarora Crk |  | LBR | Bridge Replacement | CON | 183 | 2027-01-01 |  | 0 | 112500 | 127500 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
SEDA-COG | 3 | Snyder | 6899 | SR 522 over Beaver Creek | 522 | 073 | Bridge Replacement | FD | 185 | 2024-10-24 | 2024-10-24 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
SEDA-COG | 3 | Snyder | 6899 | SR 522 over Beaver Creek | 522 | 073 | Bridge Replacement | CON | BRIP | 2024-10-24 | 2024-10-24 | 1492000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1492000
SEDA-COG | 3 | Snyder | 6899 | SR 522 over Beaver Creek | 522 | 073 | Bridge Replacement | CON | NHPP | 2024-10-24 | 2024-10-24 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SEDA-COG | 3 | Snyder | 6902 | SR 522 over Tb Beaver Crk | 522 | 075 | Bridge Replacement | FD | 185 | 2025-03-13 | 2025-03-13 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000
SEDA-COG | 3 | Snyder | 6902 | SR 522 over Tb Beaver Crk | 522 | 075 | Bridge Replacement | ROW | 185 | 2025-03-13 | 2025-03-13 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250
SEDA-COG | 3 | Snyder | 6902 | SR 522 over Tb Beaver Crk | 522 | 075 | Bridge Replacement | UTL | 185 | 2025-03-13 | 2025-03-13 | 70000 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
SEDA-COG | 3 | Snyder | 6902 | SR 522 over Tb Beaver Crk | 522 | 075 | Bridge Replacement | CON | BRIP | 2025-03-13 | 2025-03-13 | 4257000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4257000
SEDA-COG | 3 | Snyder | 6902 | SR 522 over Tb Beaver Crk | 522 | 075 | Bridge Replacement | CON | NHPP | 2025-03-13 | 2025-03-13 | 994000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994000
SEDA-COG | 3 | Snyder | 6907 | SR 522 over Kern Run | 522 | 077 | Bridge Replacement | PE | STP | 2028-09-01 |  | 66254 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85254
SEDA-COG | 3 | Snyder | 6907 | SR 522 over Kern Run | 522 | 077 | Bridge Replacement | FD | NHPP | 2028-09-01 |  | 0 | 0 | 150000 | 215000 | 0 | 0 | 0 | 0 | 0 | 365000
SEDA-COG | 3 | Snyder | 6907 | SR 522 over Kern Run | 522 | 077 | Bridge Replacement | ROW | NHPP | 2028-09-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
SEDA-COG | 3 | Snyder | 6907 | SR 522 over Kern Run | 522 | 077 | Bridge Replacement | UTL | NHPP | 2028-09-01 |  | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 90000
SEDA-COG | 3 | Snyder | 6907 | SR 522 over Kern Run | 522 | 077 | Bridge Replacement | CON | NHPP | 2028-09-01 |  | 0 | 0 | 0 | 0 | 695000 | 805000 | 0 | 0 | 0 | 1500000
SEDA-COG | 3 | Snyder | 6909 | SR 522 ov Luphers Run | 522 | 079 | Bridge Replacement | PE | STP | 2028-09-01 |  | 65000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000
SEDA-COG | 3 | Snyder | 6909 | SR 522 ov Luphers Run | 522 | 079 | Bridge Replacement | FD | NHPP | 2028-09-01 |  | 0 | 0 | 150000 | 215000 | 0 | 0 | 0 | 0 | 0 | 365000
SEDA-COG | 3 | Snyder | 6909 | SR 522 ov Luphers Run | 522 | 079 | Bridge Replacement | ROW | 185 | 2028-09-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
SEDA-COG | 3 | Snyder | 6909 | SR 522 ov Luphers Run | 522 | 079 | Bridge Replacement | UTL | 185 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 80000
SEDA-COG | 3 | Snyder | 6909 | SR 522 ov Luphers Run | 522 | 079 | Bridge Replacement | CON | NHPP | 2028-09-01 |  | 0 | 0 | 0 | 0 | 900000 | 600000 | 0 | 0 | 0 | 1500000
SEDA-COG | 3 | Snyder | 7588 | Cent. Susq. Val. Sty |  |  | New Alignment | ROW | 581 |  | 2015-09-17 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SEDA-COG | 3 | Snyder | 7588 | Cent. Susq. Val. Sty |  |  | New Alignment | UTL | 581 |  | 2015-09-17 | 2000000 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500000
SEDA-COG | 3 | Snyder | 7588 | Cent. Susq. Val. Sty |  |  | New Alignment | CON | 581 |  | 2015-09-17 | 0 | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300000
SEDA-COG | 3 | Snyder | 67736 | Perlinson(T-488) Wolf Run |  | RBR | Bridge Replacement | CON | 183 |  |  | 630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630000
SEDA-COG | 3 | Snyder | 73625 | Wetlands Monitor-SEDA-COG |  | W02 | Highway Reconstruction | CON | 581 |  |  | 0 | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31000
SEDA-COG | 3 | Snyder | 76402 | CSVT Structures South Sec | 6015 | 88E | New Alignment | CON | 581 | 2023-09-14 | 2023-09-14 | 12000000 | 10000000 | 10000000 | 8100000 | 0 | 0 | 0 | 0 | 0 | 40100000
SEDA-COG | 3 | Snyder | 76403 | CSVT Paving South Section | 6015 | 88F | New Alignment | CON | 581 | 2025-09-25 | 2025-09-25 | 273108 | 11000000 | 23400000 | 27993810 | 30624000 | 26251892 | 33000000 | 43806190 | 0 | 196349000
SEDA-COG | 3 | Snyder | 97589 | SR 4006 over Middle Creek | 4006 | 015 | Bridge Replacement | PE | BOF | 2030-09-01 |  | 0 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 320000
SEDA-COG | 3 | Snyder | 97589 | SR 4006 over Middle Creek | 4006 | 015 | Bridge Replacement | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 50000 | 175000 | 0 | 0 | 0 | 225000
SEDA-COG | 3 | Snyder | 97589 | SR 4006 over Middle Creek | 4006 | 015 | Bridge Replacement | ROW | BOF | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 36000
SEDA-COG | 3 | Snyder | 97589 | SR 4006 over Middle Creek | 4006 | 015 | Bridge Replacement | UTL | BOF | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000
SEDA-COG | 3 | Snyder | 97589 | SR 4006 over Middle Creek | 4006 | 015 | Bridge Replacement | CON | BOF | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1155000 | 1345000 | 0 | 2500000
SEDA-COG | 3 | Snyder | 98548 | SR 1011 over Tb Penn's Crk | 1011 | 023 | Bridge Replacement | FD | 185 | 2026-01-15 | 2026-01-15 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Snyder | 98548 | SR 1011 over Tb Penn's Crk | 1011 | 023 | Bridge Replacement | ROW | 185 | 2026-01-15 | 2026-01-15 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SEDA-COG | 3 | Snyder | 98548 | SR 1011 over Tb Penn's Crk | 1011 | 023 | Bridge Replacement | UTL | 185 | 2026-01-15 | 2026-01-15 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
SEDA-COG | 3 | Snyder | 98548 | SR 1011 over Tb Penn's Crk | 1011 | 023 | Bridge Replacement | CON | 185 | 2026-01-15 | 2026-01-15 | 0 | 333000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333000
SEDA-COG | 3 | Snyder | 98578 | SR 3010 over Unnamed Tributary to Middle Creek | 3010 | 017 | Bridge Replacement | CON | 185 | 2024-12-12 | 2024-12-12 | 225000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SEDA-COG | 3 | Snyder | 98885 | SR 204 to SR 11 | 1014 | 014 | Highway Restoration | CON | STP | 2025-09-25 | 2025-09-25 | 0 | 655000 | 1330000 | 15000 | 0 | 0 | 0 | 0 | 0 | 2000000
SEDA-COG | 3 | Snyder | 98887 | SR 1023 to SR 1017 | 1019 | 015 | Highway Restoration | UTL | 581 | 2025-09-25 | 2025-09-25 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
SEDA-COG | 3 | Snyder | 98887 | SR 1023 to SR 1017 | 1019 | 015 | Highway Restoration | CON | 581 | 2025-09-25 | 2025-09-25 | 0 | 900000 | 430000 | 0 | 0 | 0 | 0 | 0 | 0 | 1330000
SEDA-COG | 3 | Snyder | 99143 | SR 522 over Tb Middle Crk | 522 | 080 | Bridge Restoration | PE | NHPP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 200000 | 0 | 0 | 450000
SEDA-COG | 3 | Snyder | 99143 | SR 522 over Tb Middle Crk | 522 | 080 | Bridge Restoration | FD | NHPP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 125000 | 325000
SEDA-COG | 3 | Snyder | 99143 | SR 522 over Tb Middle Crk | 522 | 080 | Bridge Restoration | ROW | NHPP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 40000
SEDA-COG | 3 | Snyder | 99143 | SR 522 over Tb Middle Crk | 522 | 080 | Bridge Restoration | UTL | NHPP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000
SEDA-COG | 3 | Snyder | 99143 | SR 522 over Tb Middle Crk | 522 | 080 | Bridge Restoration | CON | NHPP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1850000 | 1850000
SEDA-COG | 3 | Snyder | 99241 | SR 11 from N. Main St to Penn's Creek | 11 | 131 | Highway Restoration | CON | NHPP | 2025-01-30 | 2025-01-30 | 1050000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000
SEDA-COG | 3 | Snyder | 99241 | SR 11 from N. Main St to Penn's Creek | 11 | 131 | Highway Restoration | CON | 581 | 2025-01-30 | 2025-01-30 | 0 | 126621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126621
SEDA-COG | 3 | Snyder | 102811 | CSVT ITS Phase 1 | 15 | 88I | Intelligent Transportation System | CON | 581 | 2026-07-16 |  | 0 | 8000000 | 5203297 | 0 | 0 | 0 | 0 | 0 | 0 | 13203297
SEDA-COG | 3 | Snyder | 109837 | Dry Run to Union Co | 104 | 027 | Highway Restoration | FD | 581 | 2026-05-07 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SEDA-COG | 3 | Snyder | 109837 | Dry Run to Union Co | 104 | 027 | Highway Restoration | CON | 581 | 2026-05-07 |  | 0 | 421000 | 479000 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
SEDA-COG | 3 | Snyder | 110228 | Penns Cr to SR 522 NB | 11 | 146 | Highway Restoration | PE | 581 | 2029-01-01 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Snyder | 110228 | Penns Cr to SR 522 NB | 11 | 146 | Highway Restoration | FD | 581 | 2029-01-01 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Snyder | 110228 | Penns Cr to SR 522 NB | 11 | 146 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 2600000 | 1500000 | 0 | 0 | 0 | 4100000
SEDA-COG | 3 | Snyder | 110229 | Penns CR to SR 522 SB | 11 | 147 | Highway Restoration | PE | 581 | 2029-01-01 |  | 0 | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
SEDA-COG | 3 | Snyder | 110229 | Penns CR to SR 522 SB | 11 | 147 | Highway Restoration | FD | 581 | 2029-01-01 |  | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 125000
SEDA-COG | 3 | Snyder | 110229 | Penns CR to SR 522 SB | 11 | 147 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 2550000 | 1600000 | 0 | 0 | 0 | 4150000
SEDA-COG | 3 | Snyder | 111618 | Industrial Park Road ARC |  | 05L | Highway Reconstruction | CON | APL | 2025-11-06 | 2025-11-06 | 0 | 1352207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1352207
SEDA-COG | 3 | Snyder | 111618 | Industrial Park Road ARC |  | 05L | Highway Reconstruction | CON | LOC | 2025-11-06 | 2025-11-06 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SEDA-COG | 3 | Snyder | 113787 | Roosevelt Ave to SR 15/11 Split | 11 | 150 | Highway Restoration | PE | 581 | 2025-09-25 | 2025-09-25 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SEDA-COG | 3 | Snyder | 113787 | Roosevelt Ave to SR 15/11 Split | 11 | 150 | Highway Restoration | FD | 581 | 2025-09-25 | 2025-09-25 | 276000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276000
SEDA-COG | 3 | Snyder | 113787 | Roosevelt Ave to SR 15/11 Split | 11 | 150 | Highway Restoration | UTL | 581 | 2025-09-25 | 2025-09-25 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
SEDA-COG | 3 | Snyder | 113787 | Roosevelt Ave to SR 15/11 Split | 11 | 150 | Highway Restoration | CON | 581 | 2025-09-25 | 2025-09-25 | 0 | 500000 | 3920000 | 2950000 | 0 | 0 | 0 | 0 | 0 | 7370000
SEDA-COG | 3 | Snyder | 114143 | SR 3006 over Trib of West Branch of Mahantango Crk | 3006 | 023 | Bridge Replacement | PE | 185 | 2026-10-22 |  | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
SEDA-COG | 3 | Snyder | 114143 | SR 3006 over Trib of West Branch of Mahantango Crk | 3006 | 023 | Bridge Replacement | FD | 185 | 2026-10-22 |  | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000
SEDA-COG | 3 | Snyder | 114143 | SR 3006 over Trib of West Branch of Mahantango Crk | 3006 | 023 | Bridge Replacement | ROW | 185 | 2026-10-22 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SEDA-COG | 3 | Snyder | 114143 | SR 3006 over Trib of West Branch of Mahantango Crk | 3006 | 023 | Bridge Replacement | UTL | 185 | 2026-10-22 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SEDA-COG | 3 | Snyder | 114143 | SR 3006 over Trib of West Branch of Mahantango Crk | 3006 | 023 | Bridge Replacement | CON | 185 | 2026-10-22 |  | 0 | 0 | 200000 | 170000 | 0 | 0 | 0 | 0 | 0 | 370000
SEDA-COG | 3 | Snyder | 114176 | SR 3016 over Tributary of Mahantango Creek | 3016 | 012 | Bridge Replacement | PE | 185 | 2029-09-01 |  | 0 | 0 | 165000 | 100000 | 0 | 0 | 0 | 0 | 0 | 265000
SEDA-COG | 3 | Snyder | 114176 | SR 3016 over Tributary of Mahantango Creek | 3016 | 012 | Bridge Replacement | FD | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 78000 | 72000 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Snyder | 114176 | SR 3016 over Tributary of Mahantango Creek | 3016 | 012 | Bridge Replacement | ROW | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Snyder | 114176 | SR 3016 over Tributary of Mahantango Creek | 3016 | 012 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Snyder | 114176 | SR 3016 over Tributary of Mahantango Creek | 3016 | 012 | Bridge Replacement | CON | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 0 | 500000
SEDA-COG | 3 | Snyder | 114304 | SR 2007 over Branch of Silver Creek | 2007 | 023 | Bridge Replacement | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 130000 | 138000 | 0 | 0 | 0 | 268000
SEDA-COG | 3 | Snyder | 114304 | SR 2007 over Branch of Silver Creek | 2007 | 023 | Bridge Replacement | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 177000 | 0 | 0 | 177000
SEDA-COG | 3 | Snyder | 114304 | SR 2007 over Branch of Silver Creek | 2007 | 023 | Bridge Replacement | ROW | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 35000
SEDA-COG | 3 | Snyder | 114304 | SR 2007 over Branch of Silver Creek | 2007 | 023 | Bridge Replacement | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000
SEDA-COG | 3 | Snyder | 114304 | SR 2007 over Branch of Silver Creek | 2007 | 023 | Bridge Replacement | CON | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 500000
SEDA-COG | 3 | Snyder | 114320 | SR 3006 ov Mahanoy Cr & SR 1007 ov Middle Cr | 1007 | 028 | Bridge Preservation - Federal | PE | BOF | 2026-10-01 |  | 70000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000
SEDA-COG | 3 | Snyder | 114320 | SR 3006 ov Mahanoy Cr & SR 1007 ov Middle Cr | 1007 | 028 | Bridge Preservation - Federal | FD | 185 | 2026-10-01 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Snyder | 114320 | SR 3006 ov Mahanoy Cr & SR 1007 ov Middle Cr | 1007 | 028 | Bridge Preservation - Federal | CON | BOF | 2026-10-01 |  | 0 | 0 | 619000 | 1181000 | 0 | 0 | 0 | 0 | 0 | 1800000
SEDA-COG | 3 | Snyder | 115551 | SR 11 to Union Co | 15 | 230 | Highway Restoration | FD | 581 | 2026-02-26 | 2026-02-26 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Snyder | 115551 | SR 11 to Union Co | 15 | 230 | Highway Restoration | CON | NHPP | 2026-02-26 | 2026-02-26 | 0 | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64000
SEDA-COG | 3 | Snyder | 115551 | SR 11 to Union Co | 15 | 230 | Highway Restoration | CON | STP | 2026-02-26 | 2026-02-26 | 0 | 686000 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 1136000
SEDA-COG | 3 | Snyder | 115553 | Brosius Hill Rd to Sunny Hill Rd | 35 | 015 | Highway Restoration | FD | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SEDA-COG | 3 | Snyder | 115553 | Brosius Hill Rd to Sunny Hill Rd | 35 | 015 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 1750000 | 500000 | 0 | 0 | 0 | 2250000
SEDA-COG | 3 | Snyder | 115557 | Martin Brothers Rd (SR 2006) to Heister Valley Rd | 104 | 035 | Highway Restoration | FD | 581 | 2029-01-01 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
SEDA-COG | 3 | Snyder | 115557 | Martin Brothers Rd (SR 2006) to Heister Valley Rd | 104 | 035 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 100000 | 1250000 | 0 | 0 | 0 | 0 | 1350000
SEDA-COG | 3 | Snyder | 115558 | Juniata County line to Troup Valley Road (SR 3004) | 104 | 036 | 409 Expanded Maintenance | CON | 581 | 2029-07-01 |  | 0 | 0 | 0 | 0 | 600000 | 600000 | 0 | 0 | 0 | 1200000
SEDA-COG | 3 | Snyder | 115560 | SR 11 to Union Co NB & SB | 15 | 231 | Highway Restoration | PE | 581 | 2031-01-01 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Snyder | 115560 | SR 11 to Union Co NB & SB | 15 | 231 | Highway Restoration | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000
SEDA-COG | 3 | Snyder | 115560 | SR 11 to Union Co NB & SB | 15 | 231 | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 2500000 | 2000000 | 1500000 | 6500000
SEDA-COG | 3 | Snyder | 115561 | Sugar Maple St to SR 11 | 522 | 087 | Highway Restoration | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Snyder | 115561 | Sugar Maple St to SR 11 | 522 | 087 | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 310000 | 0 | 0 | 0 | 0 | 310000
SEDA-COG | 3 | Snyder | 116340 | Gregor Hill Ln to Spring Alley | 522 | 088 | Highway Restoration | FD | 581 | 2030-01-01 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SEDA-COG | 3 | Snyder | 116340 | Gregor Hill Ln to Spring Alley | 522 | 088 | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
SEDA-COG | 3 | Snyder | 116341 | Smalsh Barrick Rd to Mountain Dr | 522 | 089 | Highway Restoration | FD | 581 | 2027-03-25 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Snyder | 116341 | Smalsh Barrick Rd to Mountain Dr | 522 | 089 | Highway Restoration | CON | 581 | 2027-03-25 |  | 0 | 0 | 250000 | 500000 | 0 | 0 | 0 | 0 | 0 | 750000
SEDA-COG | 3 | Snyder | 116547 | Old Trail Rd to Fisher Rd | 1017 | 026 | Highway Restoration | FD | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SEDA-COG | 3 | Snyder | 116549 | Granger Hollow Rd to Union Co | 11 | 166 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Snyder | 116549 | Granger Hollow Rd to Union Co | 11 | 166 | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1250000
SEDA-COG | 3 | Snyder | 116550 | SR 522 to Peach Tree Rd | 204 | 009 | Highway Restoration | FD | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Snyder | 116550 | SR 522 to Peach Tree Rd | 204 | 009 | Highway Restoration | CON | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000 | 850000
SEDA-COG | 3 | Snyder | 117552 | SR 4005 over Tributary Middle Creek | 4005 | 015 | Bridge Replacement | PE | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 150000 | 240000
SEDA-COG | 3 | Snyder | 117552 | SR 4005 over Tributary Middle Creek | 4005 | 015 | Bridge Replacement | FD | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SEDA-COG | 3 | Snyder | 117552 | SR 4005 over Tributary Middle Creek | 4005 | 015 | Bridge Replacement | ROW | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Snyder | 117552 | SR 4005 over Tributary Middle Creek | 4005 | 015 | Bridge Replacement | UTL | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000
SEDA-COG | 3 | Snyder | 117552 | SR 4005 over Tributary Middle Creek | 4005 | 015 | Bridge Replacement | CON | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
SEDA-COG | 3 | Snyder | 117579 | SR 4016 over N Branch Middle Creek | 4016 | 013 | Bridge Restoration | CON | BOF | 2025-01-30 | 2025-01-30 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000
SEDA-COG | 3 | Snyder | 117579 | SR 4016 over N Branch Middle Creek | 4016 | 013 | Bridge Restoration | CON | BRIP | 2025-01-30 | 2025-01-30 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Snyder | 119246 | Snyder County RRX Improvements | 2017 | 27R | Rail Highway Grade Crossing | CON | RRX | 2026-04-01 |  | 800000 | 1827489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2627489
SEDA-COG | 3 | Snyder | 119432 | SR 11 & 1019 Royal Farms Intersection Improvement | 11 | 177 | Safety Improvement | CON | 581 |  |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SEDA-COG | 3 | Snyder | 120369 | Ulsh Rd to N. Main St | 11 | 179 | Highway Restoration | FD | 581 | 2034-01-01 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Snyder | 120369 | Ulsh Rd to N. Main St | 11 | 179 | Highway Restoration | CON | 581 | 2034-01-01 |  | 0 | 0 | 500000 | 1250000 | 0 | 0 | 0 | 0 | 0 | 1750000
SEDA-COG | 3 | Snyder | 120631 | Juniata Co to McKee Half Falls (NB & SB) | 11 | 181 | Highway Restoration | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
SEDA-COG | 3 | Snyder | 120631 | Juniata Co to McKee Half Falls (NB & SB) | 11 | 181 | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450000 | 1450000
SEDA-COG | 3 | Snyder | 120882 | T-356 over N Branch Mahantango Creek |  | LBR | Bridge Replacement | PE | BOF |  |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Snyder | 120882 | T-356 over N Branch Mahantango Creek |  | LBR | Bridge Replacement | PE | 183 |  |  | 0 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 37500
SEDA-COG | 3 | Snyder | 120882 | T-356 over N Branch Mahantango Creek |  | LBR | Bridge Replacement | PE | LOC |  |  | 0 | 0 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 12500
SEDA-COG | 3 | Snyder | 120882 | T-356 over N Branch Mahantango Creek |  | LBR | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 280000
SEDA-COG | 3 | Snyder | 120882 | T-356 over N Branch Mahantango Creek |  | LBR | Bridge Replacement | FD | 183 |  |  | 0 | 0 | 0 | 52500 | 0 | 0 | 0 | 0 | 0 | 52500
SEDA-COG | 3 | Snyder | 120882 | T-356 over N Branch Mahantango Creek |  | LBR | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
SEDA-COG | 3 | Snyder | 120882 | T-356 over N Branch Mahantango Creek |  | LBR | Bridge Replacement | ROW | 183 |  |  | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 7500
SEDA-COG | 3 | Snyder | 120882 | T-356 over N Branch Mahantango Creek |  | LBR | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 40000
SEDA-COG | 3 | Snyder | 120882 | T-356 over N Branch Mahantango Creek |  | LBR | Bridge Replacement | UTL | 183 |  |  | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 7500
SEDA-COG | 3 | Snyder | 120882 | T-356 over N Branch Mahantango Creek |  | LBR | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 1080000 | 0 | 0 | 0 | 0 | 1080000
SEDA-COG | 3 | Snyder | 120882 | T-356 over N Branch Mahantango Creek |  | LBR | Bridge Replacement | CON | 183 |  |  | 0 | 0 | 0 | 0 | 202500 | 0 | 0 | 0 | 0 | 202500
SEDA-COG | 3 | Snyder | 120883 | T-399 over Trib to Middle Creek |  | RBR | Bridge Replacement | CON | 183 | 2029-01-01 |  | 0 | 0 | 350000 | 320000 | 0 | 0 | 0 | 0 | 0 | 670000
SEDA-COG | 3 | Snyder | 120920 | T-458 over Trib to Middle Creek |  | RBR | Bridge Replacement | CON | 183 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 320000 | 670000
SEDA-COG | 3 | Snyder | 120923 | SR 522 and SR 487 bridge painting | 522 | 127 | Bridge Preservation - Federal | PE | STP | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
SEDA-COG | 3 | Snyder | 120923 | SR 522 and SR 487 bridge painting | 522 | 127 | Bridge Preservation - Federal | FD | STP | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
SEDA-COG | 3 | Snyder | 120923 | SR 522 and SR 487 bridge painting | 522 | 127 | Bridge Preservation - Federal | CON | STP | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2228000 | 2228000
SEDA-COG | 3 | Snyder | 120923 | SR 522 and SR 487 bridge painting | 522 | 127 | Bridge Preservation - Federal | CON | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2480000 | 2480000
SEDA-COG | 3 | Snyder | 120926 | SR 1013 over Penns Creek | 1013 | 019 | Bridge Restoration | STUDY | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SEDA-COG | 3 | Snyder | 120926 | SR 1013 over Penns Creek | 1013 | 019 | Bridge Restoration | PE | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 400000
SEDA-COG | 3 | Snyder | 120926 | SR 1013 over Penns Creek | 1013 | 019 | Bridge Restoration | FD | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SEDA-COG | 3 | Snyder | 120926 | SR 1013 over Penns Creek | 1013 | 019 | Bridge Restoration | ROW | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Snyder | 120926 | SR 1013 over Penns Creek | 1013 | 019 | Bridge Restoration | UTL | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
SEDA-COG | 3 | Snyder | 120926 | SR 1013 over Penns Creek | 1013 | 019 | Bridge Restoration | CON | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2330000 | 2330000
SEDA-COG | 3 | Snyder | 121658 | Juniata Co to Dollar General | 35 | 032 | Highway Restoration | STUDY | 581 |  |  | 0 | 50000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SEDA-COG | 3 | Snyder | 123141 | SR 522 to SR 204 | 1009 | 012 | Highway Restoration | CON | 581 | 2025-07-01 |  | 0 | 154636 | 330000 | 0 | 0 | 0 | 0 | 0 | 0 | 484636
SEDA-COG | 3 | Snyder | 123356 | SR 15 Intersection | 1021 | 008 | Highway Restoration | CON | 581 | 2026-02-26 | 2026-02-26 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SEDA-COG | 3 | Union | 7547 | T-428 over Spruce Run |  | LBR | Bridge Replacement | PE | BOF | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
SEDA-COG | 3 | Union | 7547 | T-428 over Spruce Run |  | LBR | Bridge Replacement | PE | 183 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56250 | 56250
SEDA-COG | 3 | Union | 7547 | T-428 over Spruce Run |  | LBR | Bridge Replacement | FD | BOF | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 240000
SEDA-COG | 3 | Union | 7547 | T-428 over Spruce Run |  | LBR | Bridge Replacement | FD | 183 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 45000
SEDA-COG | 3 | Union | 7547 | T-428 over Spruce Run |  | LBR | Bridge Replacement | ROW | BOF | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Union | 7547 | T-428 over Spruce Run |  | LBR | Bridge Replacement | ROW | 183 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500
SEDA-COG | 3 | Union | 7547 | T-428 over Spruce Run |  | LBR | Bridge Replacement | UTL | BOF | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
SEDA-COG | 3 | Union | 7547 | T-428 over Spruce Run |  | LBR | Bridge Replacement | UTL | 183 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500
SEDA-COG | 3 | Union | 7547 | T-428 over Spruce Run |  | LBR | Bridge Replacement | CON | BOF | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360000 | 1360000
SEDA-COG | 3 | Union | 7547 | T-428 over Spruce Run |  | LBR | Bridge Replacement | CON | 183 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 255000
SEDA-COG | 3 | Union | 72352 | T-421 over White Deer Hole Creek, County Br#2 |  | LBR | Bridge Replacement | PE | BOF | 2028-01-01 |  | 252000 | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
SEDA-COG | 3 | Union | 72352 | T-421 over White Deer Hole Creek, County Br#2 |  | LBR | Bridge Replacement | PE | 183 | 2028-01-01 |  | 47250 | 12750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
SEDA-COG | 3 | Union | 72352 | T-421 over White Deer Hole Creek, County Br#2 |  | LBR | Bridge Replacement | FD | BOF | 2028-01-01 |  | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 180000
SEDA-COG | 3 | Union | 72352 | T-421 over White Deer Hole Creek, County Br#2 |  | LBR | Bridge Replacement | FD | 183 | 2028-01-01 |  | 0 | 0 | 33750 | 0 | 0 | 0 | 0 | 0 | 0 | 33750
SEDA-COG | 3 | Union | 72352 | T-421 over White Deer Hole Creek, County Br#2 |  | LBR | Bridge Replacement | ROW | BOF | 2028-01-01 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SEDA-COG | 3 | Union | 72352 | T-421 over White Deer Hole Creek, County Br#2 |  | LBR | Bridge Replacement | ROW | 183 | 2028-01-01 |  | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
SEDA-COG | 3 | Union | 72352 | T-421 over White Deer Hole Creek, County Br#2 |  | LBR | Bridge Replacement | CON | BOF | 2028-01-01 |  | 0 | 0 | 0 | 1220000 | 380000 | 0 | 0 | 0 | 0 | 1600000
SEDA-COG | 3 | Union | 72352 | T-421 over White Deer Hole Creek, County Br#2 |  | LBR | Bridge Replacement | CON | 183 | 2028-01-01 |  | 0 | 0 | 0 | 228750 | 71250 | 0 | 0 | 0 | 0 | 300000
SEDA-COG | 3 | Union | 74042 | SR 2001 over Buffalo Crk | 2001 | 013 | Bridge Restoration | PE | 185 | 2029-09-01 |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SEDA-COG | 3 | Union | 74042 | SR 2001 over Buffalo Crk | 2001 | 013 | Bridge Restoration | FD | BOF | 2029-09-01 |  | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 320000
SEDA-COG | 3 | Union | 74042 | SR 2001 over Buffalo Crk | 2001 | 013 | Bridge Restoration | ROW | BOF | 2029-09-01 |  | 0 | 0 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 45000
SEDA-COG | 3 | Union | 74042 | SR 2001 over Buffalo Crk | 2001 | 013 | Bridge Restoration | UTL | BOF | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SEDA-COG | 3 | Union | 74042 | SR 2001 over Buffalo Crk | 2001 | 013 | Bridge Restoration | CON | BOF | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 1712000 | 1088000 | 0 | 0 | 2800000
SEDA-COG | 3 | Union | 74042 | SR 2001 over Buffalo Crk | 2001 | 013 | Bridge Restoration | CON | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 428000 | 272000 | 0 | 0 | 700000
SEDA-COG | 3 | Union | 78979 | SR 1011 over White Deer Creek | 1011 | 022 | Bridge Restoration | PE | STP | 2021-12-09 | 2021-12-09 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
SEDA-COG | 3 | Union | 87994 | Multiple bridges in Sny, North & Union Cos | 15 | 308 | Bridge Preservation - Federal | PE | 185 | 2027-12-09 |  | 125000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000
SEDA-COG | 3 | Union | 87994 | Multiple bridges in Sny, North & Union Cos | 15 | 308 | Bridge Preservation - Federal | FD | 185 | 2027-12-09 |  | 0 | 0 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 190000
SEDA-COG | 3 | Union | 87994 | Multiple bridges in Sny, North & Union Cos | 15 | 308 | Bridge Preservation - Federal | ROW | 185 | 2027-12-09 |  | 0 | 0 | 45000 | 35000 | 0 | 0 | 0 | 0 | 0 | 80000
SEDA-COG | 3 | Union | 87994 | Multiple bridges in Sny, North & Union Cos | 15 | 308 | Bridge Preservation - Federal | UTL | 185 | 2027-12-09 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
SEDA-COG | 3 | Union | 87994 | Multiple bridges in Sny, North & Union Cos | 15 | 308 | Bridge Preservation - Federal | CON | 185 | 2027-12-09 |  | 0 | 0 | 0 | 335000 | 900000 | 0 | 0 | 0 | 0 | 1235000
SEDA-COG | 3 | Union | 97633 | US 15 over Winfield Creek | 15 | 207 | Bridge Restoration | PE | NHPP | 2030-09-01 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SEDA-COG | 3 | Union | 97633 | US 15 over Winfield Creek | 15 | 207 | Bridge Restoration | PE | STP | 2030-09-01 |  | 135000 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SEDA-COG | 3 | Union | 97633 | US 15 over Winfield Creek | 15 | 207 | Bridge Restoration | FD | NHPP | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 450000
SEDA-COG | 3 | Union | 97633 | US 15 over Winfield Creek | 15 | 207 | Bridge Restoration | ROW | NHPP | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 35000
SEDA-COG | 3 | Union | 97633 | US 15 over Winfield Creek | 15 | 207 | Bridge Restoration | UTL | NHPP | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 120000
SEDA-COG | 3 | Union | 97633 | US 15 over Winfield Creek | 15 | 207 | Bridge Restoration | CON | NHPP | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 1750000 | 750000 | 4400000
SEDA-COG | 3 | Union | 97720 | Forest Hill Rd (SR 3007) to Buffalo Cr | 45 | 032 | Highway Restoration | FD | 581 | 2029-01-01 |  | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
SEDA-COG | 3 | Union | 97720 | Forest Hill Rd (SR 3007) to Buffalo Cr | 45 | 032 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 100000 | 200000 | 0 | 0 | 0 | 0 | 300000
SEDA-COG | 3 | Union | 97746 | JPM Rd to Col John Kelly | 1005 | 036 | Highway Restoration | CON | 581 | 2026-07-01 |  | 0 | 50000 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 375000
SEDA-COG | 3 | Union | 98772 | SR 1003 over Tributary to Little Buffalo Creek | 1003 | 033 | Bridge Replacement | FD | 185 | 2025-12-04 | 2025-12-04 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Union | 98772 | SR 1003 over Tributary to Little Buffalo Creek | 1003 | 033 | Bridge Replacement | CON | 185 | 2025-12-04 | 2025-12-04 | 794500 | 405500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
SEDA-COG | 3 | Union | 98777 | SR 1014 over South Creek | 1014 | 012 | Bridge Replacement | PE | 185 | 2028-09-14 |  | 0 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000
SEDA-COG | 3 | Union | 98777 | SR 1014 over South Creek | 1014 | 012 | Bridge Replacement | FD | 185 | 2028-09-14 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SEDA-COG | 3 | Union | 98777 | SR 1014 over South Creek | 1014 | 012 | Bridge Replacement | ROW | 185 | 2028-09-14 |  | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 35000
SEDA-COG | 3 | Union | 98777 | SR 1014 over South Creek | 1014 | 012 | Bridge Replacement | UTL | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 80000
SEDA-COG | 3 | Union | 98777 | SR 1014 over South Creek | 1014 | 012 | Bridge Replacement | CON | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 225000 | 225000 | 0 | 0 | 0 | 450000
SEDA-COG | 3 | Union | 98786 | SR 2003 over Tributary to Buffalo Creek | 2003 | 012 | Bridge Replacement | CON | 185 | 2023-12-07 | 2023-12-14 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Union | 98826 | SR 3006 over Cold Run | 3006 | 019 | Bridge Replacement | PE | 185 | 2026-10-22 |  | 30000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
SEDA-COG | 3 | Union | 98826 | SR 3006 over Cold Run | 3006 | 019 | Bridge Replacement | FD | 185 | 2026-10-22 |  | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
SEDA-COG | 3 | Union | 98826 | SR 3006 over Cold Run | 3006 | 019 | Bridge Replacement | ROW | 185 | 2026-10-22 |  | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000
SEDA-COG | 3 | Union | 98826 | SR 3006 over Cold Run | 3006 | 019 | Bridge Replacement | UTL | 185 | 2026-10-22 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SEDA-COG | 3 | Union | 98826 | SR 3006 over Cold Run | 3006 | 019 | Bridge Replacement | CON | 185 | 2026-10-22 |  | 0 | 0 | 275000 | 225000 | 0 | 0 | 0 | 0 | 0 | 500000
SEDA-COG | 3 | Union | 98828 | SR 3014 over Turkey Run | 3014 | 007 | Bridge Replacement | FD | 185 | 2025-12-04 | 2025-12-04 | 165000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Union | 98828 | SR 3014 over Turkey Run | 3014 | 007 | Bridge Replacement | ROW | 185 | 2025-12-04 | 2025-12-04 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000
SEDA-COG | 3 | Union | 98828 | SR 3014 over Turkey Run | 3014 | 007 | Bridge Replacement | UTL | 185 | 2025-12-04 | 2025-12-04 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SEDA-COG | 3 | Union | 98828 | SR 3014 over Turkey Run | 3014 | 007 | Bridge Replacement | CON | 185 | 2025-12-04 | 2025-12-04 | 225000 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SEDA-COG | 3 | Union | 98945 | PA 45 to PA 192 | 3007 | 022 | General Maintenance | CON | 581 |  |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Union | 99137 | SR1011 over Tb Susq River | 1011 | 026 | Bridge Replacement | PE | STP | 2031-09-01 |  | 0 | 0 | 0 | 0 | 340000 | 0 | 0 | 0 | 0 | 340000
SEDA-COG | 3 | Union | 99137 | SR1011 over Tb Susq River | 1011 | 026 | Bridge Replacement | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 85000 | 0 | 0 | 0 | 0 | 85000
SEDA-COG | 3 | Union | 99137 | SR1011 over Tb Susq River | 1011 | 026 | Bridge Replacement | FD | STP | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 0 | 0 | 190000
SEDA-COG | 3 | Union | 99137 | SR1011 over Tb Susq River | 1011 | 026 | Bridge Replacement | ROW | STP | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 75000
SEDA-COG | 3 | Union | 99137 | SR1011 over Tb Susq River | 1011 | 026 | Bridge Replacement | UTL | STP | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000
SEDA-COG | 3 | Union | 99137 | SR1011 over Tb Susq River | 1011 | 026 | Bridge Replacement | CON | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 1400000 | 2000000
SEDA-COG | 3 | Union | 99141 | SR 1011 over Tributary to Susquehanna River | 1011 | 021 | Bridge Replacement | PE | STP | 2029-09-01 |  | 0 | 137000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 237000
SEDA-COG | 3 | Union | 99141 | SR 1011 over Tributary to Susquehanna River | 1011 | 021 | Bridge Replacement | FD | STP | 2029-09-01 |  | 0 | 0 | 0 | 80000 | 120000 | 0 | 0 | 0 | 0 | 200000
SEDA-COG | 3 | Union | 99141 | SR 1011 over Tributary to Susquehanna River | 1011 | 021 | Bridge Replacement | FD | 185 | 2029-09-01 |  | 0 | 0 | 0 | 20000 | 30000 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Union | 99141 | SR 1011 over Tributary to Susquehanna River | 1011 | 021 | Bridge Replacement | ROW | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 25000 | 15000 | 0 | 0 | 0 | 40000
SEDA-COG | 3 | Union | 99141 | SR 1011 over Tributary to Susquehanna River | 1011 | 021 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Union | 99141 | SR 1011 over Tributary to Susquehanna River | 1011 | 021 | Bridge Replacement | CON | STP | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 1500000
SEDA-COG | 3 | Union | 99242 | North Bound at North Hill Rd | 15 | 158 | Highway Restoration | PE | PRTCT | 2029-01-01 |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SEDA-COG | 3 | Union | 99242 | North Bound at North Hill Rd | 15 | 158 | Highway Restoration | PE | 581 | 2029-01-01 |  | 100000 | 150000 | 100000 | 125000 | 0 | 0 | 0 | 0 | 0 | 475000
SEDA-COG | 3 | Union | 99242 | North Bound at North Hill Rd | 15 | 158 | Highway Restoration | FD | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 100000 | 125000 | 0 | 0 | 0 | 225000
SEDA-COG | 3 | Union | 99242 | North Bound at North Hill Rd | 15 | 158 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 0 | 750000 | 250000 | 0 | 0 | 1000000
SEDA-COG | 3 | Union | 99249 | High St to SR 1010 | 1011 | 020 | Highway Restoration | CON | 581 |  |  | 0 | 100000 | 275000 | 373988 | 0 | 0 | 0 | 0 | 0 | 748988
SEDA-COG | 3 | Union | 99273 | White Deer Township - Joe Road to SR 44 | 15 | 199 | Highway Restoration | FD | 581 | 2028-01-01 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Union | 99273 | White Deer Township - Joe Road to SR 44 | 15 | 199 | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 0 | 800000 | 200000 | 0 | 0 | 0 | 0 | 1000000
SEDA-COG | 3 | Union | 105516 | Mile Run to Clinton County | 80 | 153 | Highway Restoration | PE | NHPP | 2028-03-26 |  | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
SEDA-COG | 3 | Union | 105516 | Mile Run to Clinton County | 80 | 153 | Highway Restoration | CON | NHPP | 2028-03-26 |  | 0 | 0 | 0 | 0 | 708000 | 1992000 | 1812000 | 488000 | 0 | 5000000
SEDA-COG | 3 | Union | 108425 | Joe Rd to SR 1010 | 15 | 197 | Highway Restoration | FD | 581 | 2028-01-01 |  | 0 | 0 | 59000 | 0 | 0 | 0 | 0 | 0 | 0 | 59000
SEDA-COG | 3 | Union | 108425 | Joe Rd to SR 1010 | 15 | 197 | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 0 | 600000 | 1400000 | 0 | 0 | 0 | 0 | 2000000
SEDA-COG | 3 | Union | 109365 | Clinton Co to SR 4001 EB | 80 | 167 | Highway Restoration | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Union | 109365 | Clinton Co to SR 4001 EB | 80 | 167 | Highway Restoration | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 355000 | 545000 | 0 | 0 | 0 | 900000
SEDA-COG | 3 | Union | 110231 | Mile Run to SR 1010 EB | 80 | 177 | Highway Restoration | PE | NHPP | 2027-03-25 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SEDA-COG | 3 | Union | 110231 | Mile Run to SR 1010 EB | 80 | 177 | Highway Restoration | FD | NHPP | 2027-03-25 |  | 0 | 0 | 0 | 200000 | 125000 | 0 | 0 | 0 | 0 | 325000
SEDA-COG | 3 | Union | 110231 | Mile Run to SR 1010 EB | 80 | 177 | Highway Restoration | CON | NHPP | 2027-03-25 |  | 0 | 0 | 0 | 0 | 0 | 1360000 | 1000000 | 1242000 | 1273000 | 4875000
SEDA-COG | 3 | Union | 110231 | Mile Run to SR 1010 EB | 80 | 177 | Highway Restoration | CON | STP | 2027-03-25 |  | 0 | 0 | 0 | 0 | 0 | 1315000 | 670000 | 140000 | 2000000 | 4125000
SEDA-COG | 3 | Union | 110337 | T-357 ov N Branch of Buffalo Creek |  | BRB | Bridge Removal | UTL | 581 | 2028-03-02 |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SEDA-COG | 3 | Union | 110337 | T-357 ov N Branch of Buffalo Creek |  | BRB | Bridge Removal | CON | 581 | 2028-03-02 |  | 235000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235000
SEDA-COG | 3 | Union | 113459 | T-319 over Penns Creek (Union Cnty #23) |  | LBR | Bridge Restoration | FD | BOF | 2027-01-28 |  | 100000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
SEDA-COG | 3 | Union | 113459 | T-319 over Penns Creek (Union Cnty #23) |  | LBR | Bridge Restoration | FD | 183 | 2027-01-28 |  | 15000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
SEDA-COG | 3 | Union | 113459 | T-319 over Penns Creek (Union Cnty #23) |  | LBR | Bridge Restoration | FD | LOC | 2027-01-28 |  | 5000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Union | 113459 | T-319 over Penns Creek (Union Cnty #23) |  | LBR | Bridge Restoration | ROW | BOF | 2027-01-28 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SEDA-COG | 3 | Union | 113459 | T-319 over Penns Creek (Union Cnty #23) |  | LBR | Bridge Restoration | ROW | 183 | 2027-01-28 |  | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
SEDA-COG | 3 | Union | 113459 | T-319 over Penns Creek (Union Cnty #23) |  | LBR | Bridge Restoration | ROW | LOC | 2027-01-28 |  | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250
SEDA-COG | 3 | Union | 113459 | T-319 over Penns Creek (Union Cnty #23) |  | LBR | Bridge Restoration | UTL | BOF | 2027-01-28 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
SEDA-COG | 3 | Union | 113459 | T-319 over Penns Creek (Union Cnty #23) |  | LBR | Bridge Restoration | UTL | 183 | 2027-01-28 |  | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
SEDA-COG | 3 | Union | 113459 | T-319 over Penns Creek (Union Cnty #23) |  | LBR | Bridge Restoration | UTL | LOC | 2027-01-28 |  | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
SEDA-COG | 3 | Union | 113459 | T-319 over Penns Creek (Union Cnty #23) |  | LBR | Bridge Restoration | CON | BOF | 2027-01-28 |  | 0 | 0 | 1800000 | 200000 | 0 | 0 | 0 | 0 | 0 | 2000000
SEDA-COG | 3 | Union | 113459 | T-319 over Penns Creek (Union Cnty #23) |  | LBR | Bridge Restoration | CON | 183 | 2027-01-28 |  | 0 | 0 | 337500 | 37500 | 0 | 0 | 0 | 0 | 0 | 375000
SEDA-COG | 3 | Union | 113612 | Mile Run to SR 1010 WB | 80 | 186 | Highway Restoration | PE | 581 | 2026-01-15 | 2026-01-15 | 150000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000
SEDA-COG | 3 | Union | 113612 | Mile Run to SR 1010 WB | 80 | 186 | Highway Restoration | FD | 581 | 2026-01-15 | 2026-01-15 | 0 | 35000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Union | 113612 | Mile Run to SR 1010 WB | 80 | 186 | Highway Restoration | CON | NHPP | 2026-01-15 | 2026-01-15 | 0 | 1127000 | 2495000 | 1223500 | 711000 | 0 | 0 | 0 | 0 | 5556500
SEDA-COG | 3 | Union | 113612 | Mile Run to SR 1010 WB | 80 | 186 | Highway Restoration | CON | STP | 2026-01-15 | 2026-01-15 | 0 | 1224000 | 68000 | 1500 | 0 | 0 | 0 | 0 | 0 | 1293500
SEDA-COG | 3 | Union | 113788 | Bull Run to Northumberland Co | 45 | 037 | Highway Restoration | PE | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 225000 | 0 | 325000
SEDA-COG | 3 | Union | 113788 | Bull Run to Northumberland Co | 45 | 037 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 250000
SEDA-COG | 3 | Union | 113788 | Bull Run to Northumberland Co | 45 | 037 | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750000 | 2750000
SEDA-COG | 3 | Union | 114379 | Snyder Co to SR 304 | 15 | 221 | Highway Restoration | FD | 581 | 2028-01-01 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Union | 114379 | Snyder Co to SR 304 | 15 | 221 | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 0 | 425000 | 150000 | 0 | 0 | 0 | 0 | 575000
SEDA-COG | 3 | Union | 115562 | Winfield to Martin St | 15 | 232 | Highway Restoration | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 125000
SEDA-COG | 3 | Union | 115562 | Winfield to Martin St | 15 | 232 | Highway Restoration | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 2000000 | 3000000
SEDA-COG | 3 | Union | 115563 | Fairview Rd to 7th St | 15 | 233 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000
SEDA-COG | 3 | Union | 115563 | Fairview Rd to 7th St | 15 | 233 | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000 | 0 | 1500000
SEDA-COG | 3 | Union | 115564 | Walter Dr to Deitrich Rd | 15 | 234 | Highway Restoration | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000
SEDA-COG | 3 | Union | 115564 | Walter Dr to Deitrich Rd | 15 | 234 | Highway Restoration | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1600000 | 0 | 2100000
SEDA-COG | 3 | Union | 115565 | SR 44 TO BRYSON RD | 15 | 235 | Highway Restoration | FD | 581 | 2027-04-29 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Union | 115565 | SR 44 TO BRYSON RD | 15 | 235 | Highway Restoration | CON | STP | 2027-04-29 |  | 0 | 0 | 280000 | 1722000 | 748000 | 0 | 0 | 0 | 0 | 2750000
SEDA-COG | 3 | Union | 115566 | Red Barn Ln to Limestone Run | 45 | 039 | Highway Restoration | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Union | 115566 | Red Barn Ln to Limestone Run | 45 | 039 | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 1400000
SEDA-COG | 3 | Union | 115588 | Bull Run Crossing to SR 15 | 192 | 027 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SEDA-COG | 3 | Union | 115588 | Bull Run Crossing to SR 15 | 192 | 027 | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
SEDA-COG | 3 | Union | 116354 | Penn St to Kaiser Run Rd | 45 | 042 | Highway Restoration | FD | 581 | 2027-07-01 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SEDA-COG | 3 | Union | 116354 | Penn St to Kaiser Run Rd | 45 | 042 | Highway Restoration | CON | 581 | 2027-07-01 |  | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 500000
SEDA-COG | 3 | Union | 117418 | SR 15 to Susquehanna River | 44 | 095 | Highway Restoration | CON | 581 | 2027-04-29 |  | 0 | 0 | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 175000
SEDA-COG | 3 | Union | 117420 | JPM RD to 3rd St | 1004 | 040 | Highway Restoration | FD | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SEDA-COG | 3 | Union | 117420 | JPM RD to 3rd St | 1004 | 040 | Highway Restoration | CON | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 1800000
SEDA-COG | 3 | Union | 117421 | Penns Creek to SR 45 | 104 | 040 | Highway Restoration | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000
SEDA-COG | 3 | Union | 117421 | Penns Creek to SR 45 | 104 | 040 | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 325000 | 400000 | 0 | 725000
SEDA-COG | 3 | Union | 117424 | SR 45 to Front St | 304 | 020 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SEDA-COG | 3 | Union | 117424 | SR 45 to Front St | 304 | 020 | Highway Restoration | CON | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
SEDA-COG | 3 | Union | 117794 | SR 304 to SR 45 | 2003 | 029 | Highway Restoration | FD | 581 | 2033-07-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Union | 117794 | SR 304 to SR 45 | 2003 | 029 | Highway Restoration | CON | 581 | 2033-07-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000 | 1100000
SEDA-COG | 3 | Union | 118345 | SR 45 & 2007 Signal and BVRT Crossing Upgrade MTF | 2007 | MTF | MultiModal | FD | 411 |  |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SEDA-COG | 3 | Union | 118345 | SR 45 & 2007 Signal and BVRT Crossing Upgrade MTF | 2007 | MTF | MultiModal | FD | LOC |  |  | 156200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156200
SEDA-COG | 3 | Union | 118345 | SR 45 & 2007 Signal and BVRT Crossing Upgrade MTF | 2007 | MTF | MultiModal | CON | 411 |  |  | 468371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468371
SEDA-COG | 3 | Union | 120141 | SR 304 ROW vacation (New Berlin) | 304 | RWV | Planning/Research/Administration | ROW | 581 |  |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SEDA-COG | 3 | Union | 121040 | Pick Rd to Fairground Rd | 235 | 019 | Highway Restoration | FD | 581 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SEDA-COG | 3 | Union | 121040 | Pick Rd to Fairground Rd | 235 | 019 | Highway Restoration | CON | 581 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935000 | 935000
SEDA-COG | 3 | Union | 121041 | Buffalo Cr to SR 45 | 3003 | 030 | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
SEDA-COG | 3 | Union | 121041 | Buffalo Cr to SR 45 | 3003 | 030 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316000 | 316000
SEDA-COG | 3 | Union | 121502 | 5th St to 6th St | 45 | 044 | Transportation Enhancement | CON | TAP | 2027-01-01 |  | 0 | 0 | 296797 | 0 | 0 | 0 | 0 | 0 | 0 | 296797
SEDA-COG | 3 | Union | 121858 | SR 11 near County Line Rd | 11 | 187 | Safety Improvement | FD | 581 | 2025-04-17 | 2025-04-17 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
SEDA-COG | 3 | Union | 121858 | SR 11 near County Line Rd | 11 | 187 | Safety Improvement | CON | HSIP | 2025-04-17 | 2025-04-17 | 141000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141000
SEDA-COG | 3 | Union | 121858 | SR 11 near County Line Rd | 11 | 187 | Safety Improvement | CON | 581 | 2025-04-17 | 2025-04-17 | 212000 | 103000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315000
SEDA-COG | 3 | Union | 122121 | Local Bridge Bundle | 7204 | MML | MultiModal | CON | 411 |  |  | 2188171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2188171
SEDA-COG | 3 | Union | 122121 | Local Bridge Bundle | 7204 | MML | MultiModal | CON | LOC |  |  | 134451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134451
SEDA-COG | 3 | Union | 123237 | SR 192 - Hidden Valley Campground Duckweed Pipe | 192 | 032 | Highway Restoration | PE | 581 | 2027-04-08 |  | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 72000
SEDA-COG | 3 | Union | 123645 | US 15/PA 44 Traffic Study | 15 | 304 | Study Phase of Project | STUDY | 581 |  |  | 0 | 5000 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 10 | Armstrong | 23833 | T-466 Saint Charles Br. | 7212 | 150 | Bridge Restoration | PE | BOF | 2028-08-10 |  | 0 | 371400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371400
SPC | 10 | Armstrong | 23833 | T-466 Saint Charles Br. | 7212 | 150 | Bridge Restoration | FD | BOF | 2028-08-10 |  | 0 | 0 | 432500 | 0 | 0 | 0 | 0 | 0 | 0 | 432500
SPC | 10 | Armstrong | 23833 | T-466 Saint Charles Br. | 7212 | 150 | Bridge Restoration | ROW | BOF | 2028-08-10 |  | 0 | 0 | 27400 | 0 | 0 | 0 | 0 | 0 | 0 | 27400
SPC | 10 | Armstrong | 23833 | T-466 Saint Charles Br. | 7212 | 150 | Bridge Restoration | UTL | BOF | 2028-08-10 |  | 0 | 0 | 21900 | 0 | 0 | 0 | 0 | 0 | 0 | 21900
SPC | 10 | Armstrong | 23833 | T-466 Saint Charles Br. | 7212 | 150 | Bridge Restoration | CON | BOF | 2028-08-10 |  | 0 | 0 | 0 | 822858 | 870768 | 1060214 | 803160 | 0 | 0 | 3557000
SPC | 10 | Armstrong | 23978 | Graff Bridge Preservation | 422 | 160 | Bridge Preservation - Federal | CON | BRIP | 2025-02-13 | 2025-02-13 | 0 | 0 | 1147900 | 0 | 2468830 | 0 | 0 | 0 | 0 | 3616730
SPC | 10 | Armstrong | 23978 | Graff Bridge Preservation | 422 | 160 | Bridge Preservation - Federal | CON | NHPP | 2025-02-13 | 2025-02-13 | 9315900 | 3849919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13165819
SPC | 10 | Armstrong | 23978 | Graff Bridge Preservation | 422 | 160 | Bridge Preservation - Federal | CON | STP | 2025-02-13 | 2025-02-13 | 1922942 | 284528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2207470
SPC | 10 | Armstrong | 24014 | Elgin Cemetery Bridge | 2005 | 151 | Bridge Replacement | PE | 185 | 2030-10-10 |  | 0 | 0 | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 400000
SPC | 10 | Armstrong | 24014 | Elgin Cemetery Bridge | 2005 | 151 | Bridge Replacement | FD | 185 | 2030-10-10 |  | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 450000
SPC | 10 | Armstrong | 24014 | Elgin Cemetery Bridge | 2005 | 151 | Bridge Replacement | ROW | 185 | 2030-10-10 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
SPC | 10 | Armstrong | 24014 | Elgin Cemetery Bridge | 2005 | 151 | Bridge Replacement | UTL | 185 | 2030-10-10 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
SPC | 10 | Armstrong | 24014 | Elgin Cemetery Bridge | 2005 | 151 | Bridge Replacement | CON | 185 | 2030-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 1500000
SPC | 10 | Armstrong | 24135 | Pyra Road Bridge | 2005 | 154 | Bridge Replacement | FD | BOF | 2026-07-02 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 10 | Armstrong | 24135 | Pyra Road Bridge | 2005 | 154 | Bridge Replacement | ROW | 185 | 2026-07-02 |  | 30000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 10 | Armstrong | 24135 | Pyra Road Bridge | 2005 | 154 | Bridge Replacement | UTL | 185 | 2026-07-02 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 10 | Armstrong | 24135 | Pyra Road Bridge | 2005 | 154 | Bridge Replacement | CON | BOF | 2026-07-02 |  | 0 | 584203 | 1511794 | 296003 | 0 | 0 | 0 | 0 | 0 | 2392000
SPC | 10 | Armstrong | 24136 | Brick Church Bridge #2 | 2005 | 153 | Bridge Replacement | PE | BOF | 2023-10-19 | 2023-10-19 | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 645
SPC | 10 | Armstrong | 24136 | Brick Church Bridge #2 | 2005 | 153 | Bridge Replacement | CON | BOF | 2023-10-19 | 2023-10-19 | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000
SPC | 10 | Armstrong | 24158 | Graff Bridge Rehabilitation | 422 | 0 | Bridge Preservation - Federal | PE | NHPP | 2035-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
SPC | 10 | Armstrong | 24158 | Graff Bridge Rehabilitation | 422 | 0 | Bridge Preservation - Federal | FD | NHPP | 2035-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
SPC | 10 | Armstrong | 74205 | Echo Church Bridge | 1028 | 152 | Bridge Replacement | PE | BOF | 2029-06-07 |  | 0 | 539397 | 155603 | 0 | 0 | 0 | 0 | 0 | 0 | 695000
SPC | 10 | Armstrong | 74205 | Echo Church Bridge | 1028 | 152 | Bridge Replacement | FD | BOF | 2029-06-07 |  | 0 | 0 | 0 | 491800 | 0 | 0 | 0 | 0 | 0 | 491800
SPC | 10 | Armstrong | 74205 | Echo Church Bridge | 1028 | 152 | Bridge Replacement | ROW | BOF | 2029-06-07 |  | 0 | 0 | 0 | 38300 | 0 | 0 | 0 | 0 | 0 | 38300
SPC | 10 | Armstrong | 74205 | Echo Church Bridge | 1028 | 152 | Bridge Replacement | UTL | BOF | 2029-06-07 |  | 0 | 0 | 0 | 27400 | 0 | 0 | 0 | 0 | 0 | 27400
SPC | 10 | Armstrong | 74205 | Echo Church Bridge | 1028 | 152 | Bridge Replacement | CON | BOF | 2029-06-07 |  | 0 | 0 | 0 | 0 | 517037 | 385560 | 385560 | 0 | 0 | 1288157
SPC | 10 | Armstrong | 79843 | SPC D-10 Hwy/Bridge Line |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 97911 | 222549 | 0 | 0 | 0 | 0 | 1375654 | 876146 | 2572260
SPC | 10 | Armstrong | 79843 | SPC D-10 Hwy/Bridge Line |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 5787616 | 0 | 1500340 | 0 | 0 | 7287956
SPC | 10 | Armstrong | 79843 | SPC D-10 Hwy/Bridge Line |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 108505 | 458300 | 2391619 | 1000000 | 155790 | 0 | 0 | 0 | 4114214
SPC | 10 | Armstrong | 79843 | SPC D-10 Hwy/Bridge Line |  |  | Reserve Line Item | CON | STP |  |  | 0 | 469879 | 446224 | 3917403 | 1313279 | 2894974 | 0 | 0 | 0 | 9041759
SPC | 10 | Armstrong | 79843 | SPC D-10 Hwy/Bridge Line |  |  | Reserve Line Item | CON | STU |  |  | 0 | 951347 | 477700 | 0 | 0 | 1721241 | 0 | 0 | 0 | 3150288
SPC | 10 | Armstrong | 79843 | SPC D-10 Hwy/Bridge Line |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 132595 | 218454 | 0 | 42199 | 72670 | 0 | 400000 | 0 | 865918
SPC | 10 | Armstrong | 79843 | SPC D-10 Hwy/Bridge Line |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 759220 | 0 | 0 | 3248286 | 975492 | 733046 | 1944148 | 5986983 | 13647175
SPC | 10 | Armstrong | 83239 | Rayburn Township - North of Kittanning Bridge #2 | 1036 | 150 | Bridge Replacement | PE | BOF | 2030-10-10 |  | 0 | 0 | 0 | 382500 | 0 | 0 | 0 | 0 | 0 | 382500
SPC | 10 | Armstrong | 83239 | Rayburn Township - North of Kittanning Bridge #2 | 1036 | 150 | Bridge Replacement | FD | BOF | 2030-10-10 |  | 0 | 0 | 0 | 407397 | 99103 | 0 | 0 | 0 | 0 | 506500
SPC | 10 | Armstrong | 83239 | Rayburn Township - North of Kittanning Bridge #2 | 1036 | 150 | Bridge Replacement | ROW | BOF | 2030-10-10 |  | 0 | 0 | 0 | 0 | 39400 | 0 | 0 | 0 | 0 | 39400
SPC | 10 | Armstrong | 83239 | Rayburn Township - North of Kittanning Bridge #2 | 1036 | 150 | Bridge Replacement | UTL | BOF | 2030-10-10 |  | 0 | 0 | 0 | 0 | 28200 | 0 | 0 | 0 | 0 | 28200
SPC | 10 | Armstrong | 83239 | Rayburn Township - North of Kittanning Bridge #2 | 1036 | 150 | Bridge Replacement | CON | BOF | 2030-10-10 |  | 0 | 0 | 0 | 0 | 782500 | 740680 | 680680 | 591800 | 0 | 2795660
SPC | 10 | Armstrong | 83239 | Rayburn Township - North of Kittanning Bridge #2 | 1036 | 150 | Bridge Replacement | CON | 185 | 2030-10-10 |  | 0 | 0 | 0 | 0 | 266560 | 266560 | 266560 | 0 | 0 | 799680
SPC | 10 | Armstrong | 83245 | Rural Valley Bridge #4 | 2001 | 151 | Bridge Replacement | UTL | 185 | 2023-11-02 | 2023-11-02 | 24891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24891
SPC | 10 | Armstrong | 91803 | McNees Bridge | 2008 | 151 | Bridge Replacement | PE | BOF | 2027-10-14 |  | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SPC | 10 | Armstrong | 91803 | McNees Bridge | 2008 | 151 | Bridge Replacement | FD | BOF | 2027-10-14 |  | 0 | 0 | 409800 | 0 | 0 | 0 | 0 | 0 | 0 | 409800
SPC | 10 | Armstrong | 91803 | McNees Bridge | 2008 | 151 | Bridge Replacement | ROW | BOF | 2027-10-14 |  | 0 | 0 | 54700 | 0 | 0 | 0 | 0 | 0 | 0 | 54700
SPC | 10 | Armstrong | 91803 | McNees Bridge | 2008 | 151 | Bridge Replacement | UTL | BOF | 2027-10-14 |  | 0 | 0 | 54700 | 0 | 0 | 0 | 0 | 0 | 0 | 54700
SPC | 10 | Armstrong | 91803 | McNees Bridge | 2008 | 151 | Bridge Replacement | CON | BOF | 2027-10-14 |  | 0 | 0 | 0 | 749000 | 593050 | 593050 | 0 | 0 | 0 | 1935100
SPC | 10 | Armstrong | 93990 | Bridge North of Avonmore #2 | 156 | 150 | Bridge Replacement | PE | STP | 2028-10-05 |  | 400000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 10 | Armstrong | 98689 | Dunbar Dip | 422 | 19D | New Alignment | PE | NHPP | 2034-12-07 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 10 | Armstrong | 98689 | Dunbar Dip | 422 | 19D | New Alignment | FD | NHPP | 2034-12-07 |  | 0 | 0 | 0 | 200000 | 600880 | 1000000 | 0 | 0 | 0 | 1800880
SPC | 10 | Armstrong | 98689 | Dunbar Dip | 422 | 19D | New Alignment | FD | 581 | 2034-12-07 |  | 0 | 0 | 0 | 50000 | 150220 | 250000 | 0 | 0 | 0 | 450220
SPC | 10 | Armstrong | 98689 | Dunbar Dip | 422 | 19D | New Alignment | ROW | 581 | 2034-12-07 |  | 0 | 0 | 0 | 0 | 0 | 3342193 | 2157807 | 0 | 0 | 5500000
SPC | 10 | Armstrong | 98689 | Dunbar Dip | 422 | 19D | New Alignment | UTL | NHPP | 2034-12-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 320000
SPC | 10 | Armstrong | 98689 | Dunbar Dip | 422 | 19D | New Alignment | UTL | 581 | 2034-12-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 80000
SPC | 10 | Armstrong | 98689 | Dunbar Dip | 422 | 19D | New Alignment | CON | NHPP | 2034-12-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 22600000 | 28600000
SPC | 10 | Armstrong | 98689 | Dunbar Dip | 422 | 19D | New Alignment | CON | 581 | 2034-12-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 5650000 | 7150000
SPC | 10 | Armstrong | 98896 | East of Rural Valley Br. | 85 | 0 | Bridge Replacement | PE | BRIP | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 240000
SPC | 10 | Armstrong | 98896 | East of Rural Valley Br. | 85 | 0 | Bridge Replacement | PE | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000
SPC | 10 | Armstrong | 98896 | East of Rural Valley Br. | 85 | 0 | Bridge Replacement | FD | BRIP | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 240000
SPC | 10 | Armstrong | 98896 | East of Rural Valley Br. | 85 | 0 | Bridge Replacement | FD | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000
SPC | 10 | Armstrong | 98896 | East of Rural Valley Br. | 85 | 0 | Bridge Replacement | ROW | BRIP | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
SPC | 10 | Armstrong | 98896 | East of Rural Valley Br. | 85 | 0 | Bridge Replacement | UTL | BRIP | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
SPC | 10 | Armstrong | 98896 | East of Rural Valley Br. | 85 | 0 | Bridge Replacement | CON | BRIP | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1827809 | 1827809
SPC | 10 | Armstrong | 98896 | East of Rural Valley Br. | 85 | 0 | Bridge Replacement | CON | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456952 | 456952
SPC | 10 | Armstrong | 99909 | Distant East Resurfacing | 28 | 115 | Preventive Maintenance | CON | NHPP | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032000 | 1032000 | 2064000
SPC | 10 | Armstrong | 99909 | Distant East Resurfacing | 28 | 115 | Preventive Maintenance | CON | 581 | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258000 | 258000 | 516000
SPC | 10 | Armstrong | 99973 | Armstrong GROUP 101-26-SIA | 85 | 111 | General Maintenance | CON | 185 | 2026-04-23 |  | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35200
SPC | 10 | Armstrong | 103146 | PA 56 Apollo Group Bridges | 56 | 156 | Bridge Replacement | UTL | 581 | 2021-02-25 | 2021-03-11 | 78979 | 51500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130479
SPC | 10 | Armstrong | 105894 | PA 28 - Distant South Microsurface | 28 | 106 | 409 Expanded Maintenance | CON | 581 | 2033-01-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4235550 | 4235550
SPC | 10 | Armstrong | 109622 | 1/112th Infantry Bridge/Graff Ramp Rehabilitation | 66 | 158 | Bridge Restoration | CON | BRIP | 2025-02-13 | 2025-02-13 | 946680 | 3953595 | 5492980 | 5622251 | 0 | 0 | 0 | 0 | 0 | 16015506
SPC | 10 | Armstrong | 109622 | 1/112th Infantry Bridge/Graff Ramp Rehabilitation | 66 | 158 | Bridge Restoration | CON | STP | 2025-02-13 | 2025-02-13 | 9983616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9983616
SPC | 10 | Armstrong | 109622 | 1/112th Infantry Bridge/Graff Ramp Rehabilitation | 66 | 158 | Bridge Restoration | CON | STU | 2025-02-13 | 2025-02-13 | 2502749 | 582450 | 2000000 | 219492 | 0 | 0 | 0 | 0 | 0 | 5304691
SPC | 10 | Armstrong | 111826 | Armstrong Co. Department Force Bridge Maintenance | 68 | 0 | Bridge Restoration | CON | 185 | 2028-10-05 |  | 154500 | 212200 | 218600 | 179351 | 225200 | 225200 | 225200 | 225200 | 900800 | 2566251
SPC | 10 | Armstrong | 114936 | US 422 County Line East PM | 422 | 101 | Preventive Maintenance | CON | NHPP | 2024-03-28 | 2024-03-28 | 0 | 136000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136000
SPC | 10 | Armstrong | 114936 | US 422 County Line East PM | 422 | 101 | Preventive Maintenance | CON | STP | 2024-03-28 | 2024-03-28 | 0 | 257096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257096
SPC | 10 | Armstrong | 114936 | US 422 County Line East PM | 422 | 101 | Preventive Maintenance | CON | SXF | 2024-03-28 | 2024-03-28 | 66903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66903
SPC | 10 | Armstrong | 114936 | US 422 County Line East PM | 422 | 101 | Preventive Maintenance | CON | 581 | 2024-03-28 | 2024-03-28 | 1299606 | 64274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1363880
SPC | 10 | Armstrong | 114950 | US 422 Worthington East PM | 422 | 102 | Preventive Maintenance | PE | 581 | 2027-01-14 |  | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000
SPC | 10 | Armstrong | 114950 | US 422 Worthington East PM | 422 | 102 | Preventive Maintenance | ROW | 581 | 2027-01-14 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SPC | 10 | Armstrong | 114950 | US 422 Worthington East PM | 422 | 102 | Preventive Maintenance | CON | 581 | 2027-01-14 |  | 0 | 0 | 370750 | 2389831 | 4300784 | 934328 | 299817 | 245990 | 0 | 8541500
SPC | 10 | Armstrong | 117243 | Armstrong Latex Group Bridges | 28 | 169 | Bridge Preservation - Federal | CON | STP | 2024-01-25 | 2024-01-25 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000
SPC | 10 | Armstrong | 117669 | T-860 Beagle Club Bridge | 7224 | 150 | Bridge Replacement | PE | BOF | 2030-03-07 |  | 0 | 0 | 0 | 394000 | 0 | 0 | 0 | 0 | 0 | 394000
SPC | 10 | Armstrong | 117669 | T-860 Beagle Club Bridge | 7224 | 150 | Bridge Replacement | FD | BOF | 2030-03-07 |  | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000
SPC | 10 | Armstrong | 117669 | T-860 Beagle Club Bridge | 7224 | 150 | Bridge Replacement | ROW | BOF | 2030-03-07 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 10 | Armstrong | 117669 | T-860 Beagle Club Bridge | 7224 | 150 | Bridge Replacement | UTL | BOF | 2030-03-07 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
SPC | 10 | Armstrong | 117669 | T-860 Beagle Club Bridge | 7224 | 150 | Bridge Replacement | CON | BOF | 2030-03-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 950000
SPC | 10 | Armstrong | 117687 | PA 28 Goheenville South PM | 28 | 105 | Preventive Maintenance | CON | NHPP | 2026-03-26 | 2026-03-26 | 0 | 2602707 | 1794438 | 0 | 0 | 0 | 0 | 0 | 0 | 4397145
SPC | 10 | Armstrong | 117687 | PA 28 Goheenville South PM | 28 | 105 | Preventive Maintenance | CON | 581 | 2026-03-26 | 2026-03-26 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 0 | 0 | 85000
SPC | 10 | Armstrong | 119578 | SR 4023 Tarrtown Rd Slides | 4023 | 19B | Highway Reconstruction | FD | STP | 2026-10-22 |  | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000
SPC | 10 | Armstrong | 119578 | SR 4023 Tarrtown Rd Slides | 4023 | 19B | Highway Reconstruction | ROW | 581 | 2026-10-22 |  | 0 | 51500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51500
SPC | 10 | Armstrong | 119578 | SR 4023 Tarrtown Rd Slides | 4023 | 19B | Highway Reconstruction | CON | PRTCT | 2026-10-22 |  | 0 | 4496900 | 3503100 | 0 | 0 | 0 | 0 | 0 | 0 | 8000000
SPC | 10 | Armstrong | 119578 | SR 4023 Tarrtown Rd Slides | 4023 | 19B | Highway Reconstruction | CON | 581 | 2026-10-22 |  | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 3000000
SPC | 10 | Armstrong | 119726 | Armstrong Second. Routes (Group NO. 101-24-SIA) | 2025 | 102 | 409 Expanded Maintenance | CON | PRTCT | 2024-03-28 | 2024-03-28 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 10 | Armstrong | 119814 | US 422 West Kittanning PM | 422 | 103 | Preventive Maintenance | CON | 581 | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2420549 | 3815786 | 6236335
SPC | 10 | Armstrong | 119815 | PA 28 - Distant North Resurfacing | 28 | 107 | Preventive Maintenance | CON | 581 | 2030-03-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157300 | 2157300
SPC | 10 | Armstrong | 120237 | SR 66/SR128 Riverside Light Upgrade | 66 | 193 | Congestion Reduction | CON | CRPU | 2025-05-22 | 2025-05-22 | 164346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164346
SPC | 10 | Armstrong | 120237 | SR 66/SR128 Riverside Light Upgrade | 66 | 193 | Congestion Reduction | CON | 073 | 2025-05-22 | 2025-05-22 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
SPC | 10 | Armstrong | 120237 | SR 66/SR128 Riverside Light Upgrade | 66 | 193 | Congestion Reduction | CON | 582 | 2025-05-22 | 2025-05-22 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 10 | Armstrong | 120768 | East of Templeton 1 and 2 Group Bridges | 1030 | 152 | Bridge Replacement | ROW | 185 | 2028-07-13 |  | 0 | 54700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54700
SPC | 10 | Armstrong | 120768 | East of Templeton 1 and 2 Group Bridges | 1030 | 152 | Bridge Replacement | UTL | 185 | 2028-07-13 |  | 0 | 54700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54700
SPC | 10 | Armstrong | 120768 | East of Templeton 1 and 2 Group Bridges | 1030 | 152 | Bridge Replacement | CON | 185 | 2028-07-13 |  | 0 | 0 | 0 | 0 | 0 | 337668 | 1262332 | 0 | 0 | 1600000
SPC | 10 | Armstrong | 120999 | Avonmore Station Bridge | 156 | 151 | Bridge Replacement | PE | STP | 2035-10-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 344900 | 0 | 0 | 344900
SPC | 10 | Armstrong | 120999 | Avonmore Station Bridge | 156 | 151 | Bridge Replacement | FD | STP | 2035-10-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332800 | 0 | 332800
SPC | 10 | Armstrong | 120999 | Avonmore Station Bridge | 156 | 151 | Bridge Replacement | ROW | STP | 2035-10-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47600 | 0 | 47600
SPC | 10 | Armstrong | 120999 | Avonmore Station Bridge | 156 | 151 | Bridge Replacement | UTL | STP | 2035-10-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47600 | 0 | 47600
SPC | 10 | Armstrong | 121054 | Kittanning Streetscape Project | 1038 | 180 | Transportation Enhancement | PE | STU | 2027-05-27 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
SPC | 10 | Armstrong | 122012 | District 10 HFST SPC 2026 | 28 | ST2 | Safety Improvement | CON | HSIP | 2025-11-06 | 2025-11-06 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 10 | Armstrong | 122324 | Gilpin Township Roadway Safety Initiative MTF |  | 192 | MultiModal | CON | 411 |  |  | 64571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64571
SPC | 10 | Armstrong | 122324 | Gilpin Township Roadway Safety Initiative MTF |  | 192 | MultiModal | CON | LOC |  |  | 27673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27673
SPC | 10 | Armstrong | 122499 | Houser Bridge Rehabilitation MTF | 7202 | 150 | MultiModal | FD | 411 | 2026-10-22 |  | 0 | 57000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57000
SPC | 10 | Armstrong | 122499 | Houser Bridge Rehabilitation MTF | 7202 | 150 | MultiModal | FD | LOC | 2026-10-22 |  | 0 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000
SPC | 10 | Armstrong | 122499 | Houser Bridge Rehabilitation MTF | 7202 | 150 | MultiModal | CON | 411 | 2026-10-22 |  | 0 | 513082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513082
SPC | 10 | Armstrong | 122499 | Houser Bridge Rehabilitation MTF | 7202 | 150 | MultiModal | CON | LOC | 2026-10-22 |  | 0 | 102884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102884
SPC | 10 | Butler | 24241 | PA 528 over Lake Arthur | 528 | 260 | Bridge Restoration | PE | 185 | 2031-10-09 |  | 0 | 0 | 0 | 0 | 654579 | 261885 | 0 | 0 | 0 | 916464
SPC | 10 | Butler | 24241 | PA 528 over Lake Arthur | 528 | 260 | Bridge Restoration | FD | BRIP | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 389200 | 389200 | 0 | 0 | 778400
SPC | 10 | Butler | 24241 | PA 528 over Lake Arthur | 528 | 260 | Bridge Restoration | FD | 185 | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 97300 | 97300 | 0 | 0 | 194600
SPC | 10 | Butler | 24241 | PA 528 over Lake Arthur | 528 | 260 | Bridge Restoration | ROW | BRIP | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 625240 | 625240 | 0 | 0 | 1250480
SPC | 10 | Butler | 24241 | PA 528 over Lake Arthur | 528 | 260 | Bridge Restoration | ROW | 185 | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 156310 | 156310 | 0 | 0 | 312620
SPC | 10 | Butler | 24241 | PA 528 over Lake Arthur | 528 | 260 | Bridge Restoration | UTL | BRIP | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 48800 | 0 | 0 | 48800
SPC | 10 | Butler | 24241 | PA 528 over Lake Arthur | 528 | 260 | Bridge Restoration | UTL | 185 | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 0 | 0 | 12200
SPC | 10 | Butler | 24241 | PA 528 over Lake Arthur | 528 | 260 | Bridge Restoration | CON | BRIP | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2441125 | 11749410 | 14190535
SPC | 10 | Butler | 24241 | PA 528 over Lake Arthur | 528 | 260 | Bridge Restoration | CON | 185 | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610281 | 0 | 610281
SPC | 10 | Butler | 24409 | State Game Lands 95 Br | 268 | 251 | Bridge Replacement | PE | 185 | 2029-10-18 |  | 191800 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221800
SPC | 10 | Butler | 24409 | State Game Lands 95 Br | 268 | 251 | Bridge Replacement | FD | 185 | 2029-10-18 |  | 400000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
SPC | 10 | Butler | 24409 | State Game Lands 95 Br | 268 | 251 | Bridge Replacement | ROW | 185 | 2029-10-18 |  | 0 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87500
SPC | 10 | Butler | 24409 | State Game Lands 95 Br | 268 | 251 | Bridge Replacement | UTL | 185 | 2029-10-18 |  | 0 | 0 | 54700 | 0 | 0 | 0 | 0 | 0 | 0 | 54700
SPC | 10 | Butler | 24409 | State Game Lands 95 Br | 268 | 251 | Bridge Replacement | CON | BRIP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 1866667 | 1816667 | 1906666 | 0 | 5590000
SPC | 10 | Butler | 24409 | State Game Lands 95 Br | 268 | 251 | Bridge Replacement | CON | 185 | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 466667 | 466667 | 476666 | 0 | 1410000
SPC | 10 | Butler | 24471 | CO #24 Kelly Bridge | 7232 | 251 | Bridge Replacement | CON | BOF | 2024-07-25 | 2024-07-25 | 0 | 8876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8876
SPC | 10 | Butler | 24663 | US 422 over PA 356 | 422 | 25D | Bridge Replacement | PE | NHPP | 2029-10-18 |  | 1083500 | 590500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1674000
SPC | 10 | Butler | 24663 | US 422 over PA 356 | 422 | 25D | Bridge Replacement | FD | NHPP | 2029-10-18 |  | 0 | 0 | 632900 | 0 | 0 | 0 | 0 | 0 | 0 | 632900
SPC | 10 | Butler | 24663 | US 422 over PA 356 | 422 | 25D | Bridge Replacement | ROW | NHPP | 2029-10-18 |  | 0 | 0 | 257500 | 0 | 0 | 0 | 0 | 0 | 0 | 257500
SPC | 10 | Butler | 24663 | US 422 over PA 356 | 422 | 25D | Bridge Replacement | UTL | NHPP | 2029-10-18 |  | 0 | 0 | 257500 | 0 | 0 | 0 | 0 | 0 | 0 | 257500
SPC | 10 | Butler | 24663 | US 422 over PA 356 | 422 | 25D | Bridge Replacement | CON | STP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 1276907 | 2627468 | 1500000 | 1500000 | 6904375
SPC | 10 | Butler | 24663 | US 422 over PA 356 | 422 | 25D | Bridge Replacement | CON | STU | 2029-10-18 |  | 0 | 0 | 607885 | 2866093 | 3085585 | 1364344 | 3085585 | 1000000 | 2940733 | 14950225
SPC | 10 | Butler | 24682 | Southwest of Euclid Bridge | 138 | 251 | Bridge Replacement | ROW | 185 | 2024-10-10 | 2024-10-10 | 0 | 49300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49300
SPC | 10 | Butler | 24682 | Southwest of Euclid Bridge | 138 | 251 | Bridge Replacement | CON | 185 | 2024-10-10 | 2024-10-10 | 649582 | 239120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 888702
SPC | 10 | Butler | 24690 | US 422 over SR 4005 Bridge | 422 | 260 | Bridge Replacement | PE | NHPP | 2030-01-17 |  | 412000 | 76055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488055
SPC | 10 | Butler | 24690 | US 422 over SR 4005 Bridge | 422 | 260 | Bridge Replacement | FD | NHPP | 2030-01-17 |  | 0 | 794956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 794956
SPC | 10 | Butler | 24690 | US 422 over SR 4005 Bridge | 422 | 260 | Bridge Replacement | UTL | NHPP | 2030-01-17 |  | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400
SPC | 10 | Butler | 24690 | US 422 over SR 4005 Bridge | 422 | 260 | Bridge Replacement | CON | NHPP | 2030-01-17 |  | 0 | 0 | 2432890 | 2341100 | 2091100 | 2499310 | 2000000 | 0 | 0 | 11364400
SPC | 10 | Butler | 24690 | US 422 over SR 4005 Bridge | 422 | 260 | Bridge Replacement | CON | 581 | 2030-01-17 |  | 0 | 0 | 710275 | 585275 | 552775 | 552775 | 500000 | 0 | 0 | 2901100
SPC | 10 | Butler | 24709 | Branchton Bridge | 4010 | 254 | Bridge Replacement | PE | 185 | 2028-10-19 |  | 500000 | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529000
SPC | 10 | Butler | 24709 | Branchton Bridge | 4010 | 254 | Bridge Replacement | FD | BOF | 2028-10-19 |  | 0 | 0 | 0 | 506500 | 0 | 0 | 0 | 0 | 0 | 506500
SPC | 10 | Butler | 24709 | Branchton Bridge | 4010 | 254 | Bridge Replacement | ROW | BOF | 2028-10-19 |  | 0 | 0 | 0 | 39400 | 0 | 0 | 0 | 0 | 0 | 39400
SPC | 10 | Butler | 24709 | Branchton Bridge | 4010 | 254 | Bridge Replacement | UTL | BOF | 2028-10-19 |  | 0 | 0 | 0 | 28200 | 0 | 0 | 0 | 0 | 0 | 28200
SPC | 10 | Butler | 24709 | Branchton Bridge | 4010 | 254 | Bridge Replacement | CON | BOF | 2028-10-19 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 0 | 0 | 1000000
SPC | 10 | Butler | 24722 | PA 8 over Muddy Creek | 8 | 263 | Bridge Replacement | PE | STP | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 400000
SPC | 10 | Butler | 24722 | PA 8 over Muddy Creek | 8 | 263 | Bridge Replacement | FD | BRIP | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 400000
SPC | 10 | Butler | 24722 | PA 8 over Muddy Creek | 8 | 263 | Bridge Replacement | ROW | BRIP | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67000 | 0 | 67000
SPC | 10 | Butler | 24722 | PA 8 over Muddy Creek | 8 | 263 | Bridge Replacement | UTL | BRIP | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
SPC | 10 | Butler | 24722 | PA 8 over Muddy Creek | 8 | 263 | Bridge Replacement | CON | BRIP | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
SPC | 10 | Butler | 24759 | PA 356 over Tributary to Coal Run | 356 | 253 | Bridge Replacement | CON | 185 | 2023-11-02 | 2023-11-02 | 1340458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1340458
SPC | 10 | Butler | 24814 | Bruin Bridge #5 | 1004 | 252 | Bridge Replacement | FD | BOF | 2026-10-22 |  | 300000 | 144100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 444100
SPC | 10 | Butler | 24814 | Bruin Bridge #5 | 1004 | 252 | Bridge Replacement | ROW | BOF | 2026-10-22 |  | 0 | 31900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31900
SPC | 10 | Butler | 24814 | Bruin Bridge #5 | 1004 | 252 | Bridge Replacement | UTL | BOF | 2026-10-22 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 10 | Butler | 24814 | Bruin Bridge #5 | 1004 | 252 | Bridge Replacement | CON | BOF | 2026-10-22 |  | 0 | 0 | 2018000 | 0 | 0 | 0 | 0 | 0 | 0 | 2018000
SPC | 10 | Butler | 24827 | Renfrew Bridge | 3007 | 251 | Bridge Replacement | PE | 581 | 2029-01-11 |  | 224234 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464234
SPC | 10 | Butler | 24827 | Renfrew Bridge | 3007 | 251 | Bridge Replacement | FD | STP | 2029-01-11 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 10 | Butler | 24827 | Renfrew Bridge | 3007 | 251 | Bridge Replacement | ROW | STP | 2029-01-11 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 10 | Butler | 24827 | Renfrew Bridge | 3007 | 251 | Bridge Replacement | UTL | STP | 2029-01-11 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 10 | Butler | 24827 | Renfrew Bridge | 3007 | 251 | Bridge Replacement | CON | 185 | 2029-01-11 |  | 0 | 0 | 647284 | 1457000 | 1517906 | 1170010 | 0 | 0 | 0 | 4792200
SPC | 10 | Butler | 56592 | T-584 Geibel Road Bridge | 7228 | 251 | Bridge Replacement | CON | BOF | 2025-05-08 | 2025-05-08 | 934269 | 119067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1053336
SPC | 10 | Butler | 67185 | Freedom Rd Turnpike Bridge | 3020 | 250 | Bridge Replacement | ROW | STP | 2018-12-06 | 2018-12-13 | 429915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 429915
SPC | 10 | Butler | 77945 | T-603 Saint Joe Bridge | 7224 | 250 | Bridge Replacement | PE | BOF | 2028-11-09 |  | 0 | 371400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371400
SPC | 10 | Butler | 77945 | T-603 Saint Joe Bridge | 7224 | 250 | Bridge Replacement | FD | BOF | 2028-11-09 |  | 0 | 0 | 409800 | 0 | 0 | 0 | 0 | 0 | 0 | 409800
SPC | 10 | Butler | 77945 | T-603 Saint Joe Bridge | 7224 | 250 | Bridge Replacement | ROW | BOF | 2028-11-09 |  | 0 | 0 | 27400 | 0 | 0 | 0 | 0 | 0 | 0 | 27400
SPC | 10 | Butler | 77945 | T-603 Saint Joe Bridge | 7224 | 250 | Bridge Replacement | UTL | BOF | 2028-11-09 |  | 0 | 0 | 21900 | 0 | 0 | 0 | 0 | 0 | 0 | 21900
SPC | 10 | Butler | 77945 | T-603 Saint Joe Bridge | 7224 | 250 | Bridge Replacement | CON | BOF | 2028-11-09 |  | 0 | 0 | 0 | 654542 | 423258 | 0 | 0 | 0 | 0 | 1077800
SPC | 10 | Butler | 83317 | PA 268 ovTrib.S.Br. Bear Ck | 268 | 253 | Bridge Replacement | PE | 185 | 2028-10-19 |  | 0 | 410783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410783
SPC | 10 | Butler | 83317 | PA 268 ovTrib.S.Br. Bear Ck | 268 | 253 | Bridge Replacement | FD | 185 | 2028-10-19 |  | 0 | 0 | 437100 | 0 | 0 | 0 | 0 | 0 | 0 | 437100
SPC | 10 | Butler | 83317 | PA 268 ovTrib.S.Br. Bear Ck | 268 | 253 | Bridge Replacement | ROW | 185 | 2028-10-19 |  | 0 | 0 | 25046 | 21454 | 0 | 0 | 0 | 0 | 0 | 46500
SPC | 10 | Butler | 83317 | PA 268 ovTrib.S.Br. Bear Ck | 268 | 253 | Bridge Replacement | UTL | 185 | 2028-10-19 |  | 0 | 0 | 0 | 0 | 56300 | 0 | 0 | 0 | 0 | 56300
SPC | 10 | Butler | 83317 | PA 268 ovTrib.S.Br. Bear Ck | 268 | 253 | Bridge Replacement | CON | BRIP | 2028-10-19 |  | 0 | 0 | 0 | 0 | 0 | 998480 | 998480 | 0 | 0 | 1996960
SPC | 10 | Butler | 83317 | PA 268 ovTrib.S.Br. Bear Ck | 268 | 253 | Bridge Replacement | CON | 185 | 2028-10-19 |  | 0 | 0 | 0 | 0 | 0 | 249620 | 249620 | 0 | 0 | 499240
SPC | 10 | Butler | 83323 | PA 528 over Big Run | 528 | 259 | Bridge Replacement | PE | 185 | 2027-10-21 |  | 200000 | 194544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394544
SPC | 10 | Butler | 83323 | PA 528 over Big Run | 528 | 259 | Bridge Replacement | FD | 185 | 2027-10-21 |  | 0 | 437100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437100
SPC | 10 | Butler | 83323 | PA 528 over Big Run | 528 | 259 | Bridge Replacement | ROW | 185 | 2027-10-21 |  | 0 | 21900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21900
SPC | 10 | Butler | 83323 | PA 528 over Big Run | 528 | 259 | Bridge Replacement | CON | 185 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 912500 | 912500 | 0 | 0 | 0 | 1825000
SPC | 10 | Butler | 83336 | SR 3015 over Trib. to Breakneck Creek | 3015 | 255 | Bridge Replacement | CON | STP | 2023-07-13 | 2023-07-13 | 0 | 169222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169222
SPC | 10 | Butler | 83338 | West Liberty Bridge No.2 | 4008 | 000 | Bridge Replacement | PE | BOF | 2031-06-12 |  | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000
SPC | 10 | Butler | 83338 | West Liberty Bridge No.2 | 4008 | 000 | Bridge Replacement | FD | BOF | 2031-06-12 |  | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 350000
SPC | 10 | Butler | 83338 | West Liberty Bridge No.2 | 4008 | 000 | Bridge Replacement | ROW | BOF | 2031-06-12 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
SPC | 10 | Butler | 83338 | West Liberty Bridge No.2 | 4008 | 000 | Bridge Replacement | UTL | BOF | 2031-06-12 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
SPC | 10 | Butler | 83338 | West Liberty Bridge No.2 | 4008 | 000 | Bridge Replacement | CON | BOF | 2031-06-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 600000
SPC | 10 | Butler | 83338 | West Liberty Bridge No.2 | 4008 | 000 | Bridge Replacement | CON | 185 | 2031-06-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SPC | 10 | Butler | 83611 | US 422 Shawood Pipe | 422 | 259 | Bridge Replacement | CON | NHPP | 2027-01-14 |  | 0 | 0 | 0 | 800000 | 2103613 | 2103613 | 2103613 | 1284512 | 587847 | 8983198
SPC | 10 | Butler | 83611 | US 422 Shawood Pipe | 422 | 259 | Bridge Replacement | CON | 581 | 2027-01-14 |  | 0 | 0 | 0 | 200000 | 525887 | 525887 | 525887 | 321128 | 146962 | 2245751
SPC | 10 | Butler | 86105 | Karns Crossing Bridge | 68 | 253 | Bridge Replacement | UTL | STP | 2024-11-07 | 2024-11-07 | 285994 | 34603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320597
SPC | 10 | Butler | 86105 | Karns Crossing Bridge | 68 | 253 | Bridge Replacement | UTL | 185 | 2024-11-07 | 2024-11-07 | 71498 | 8651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80149
SPC | 10 | Butler | 86105 | Karns Crossing Bridge | 68 | 253 | Bridge Replacement | CON | BRIP | 2024-11-07 | 2024-11-07 | 9572320 | 6565405 | 2101376 | 763056 | 2262554 | 0 | 0 | 0 | 0 | 21264711
SPC | 10 | Butler | 86105 | Karns Crossing Bridge | 68 | 253 | Bridge Replacement | CON | NHPP | 2024-11-07 | 2024-11-07 | 500000 | 2560000 | 0 | 0 | 3901580 | 0 | 0 | 0 | 0 | 6961580
SPC | 10 | Butler | 86105 | Karns Crossing Bridge | 68 | 253 | Bridge Replacement | CON | STP | 2024-11-07 | 2024-11-07 | 8406504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8406504
SPC | 10 | Butler | 86105 | Karns Crossing Bridge | 68 | 253 | Bridge Replacement | CON | STU | 2024-11-07 | 2024-11-07 | 1411150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411150
SPC | 10 | Butler | 86105 | Karns Crossing Bridge | 68 | 253 | Bridge Replacement | CON | 185 | 2024-11-07 | 2024-11-07 | 1058610 | 417140 | 2111888 | 6368323 | 2629750 | 0 | 0 | 0 | 0 | 12585711
SPC | 10 | Butler | 90001 | NE of Evans City Bridge | 68 | 257 | Bridge Replacement | PE | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 450000
SPC | 10 | Butler | 90001 | NE of Evans City Bridge | 68 | 257 | Bridge Replacement | FD | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 450000
SPC | 10 | Butler | 90001 | NE of Evans City Bridge | 68 | 257 | Bridge Replacement | ROW | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000
SPC | 10 | Butler | 90001 | NE of Evans City Bridge | 68 | 257 | Bridge Replacement | UTL | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000
SPC | 10 | Butler | 90001 | NE of Evans City Bridge | 68 | 257 | Bridge Replacement | CON | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
SPC | 10 | Butler | 91286 | Three Degree Rd Intersection | 228 | 29B | Highway Restoration | ROW | NHPP | 2022-10-20 | 2022-10-20 | 1060800 | 487200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1548000
SPC | 10 | Butler | 91286 | Three Degree Rd Intersection | 228 | 29B | Highway Restoration | ROW | 581 | 2022-10-20 | 2022-10-20 | 265200 | 121800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387000
SPC | 10 | Butler | 91286 | Three Degree Rd Intersection | 228 | 29B | Highway Restoration | CON | 581 | 2022-10-20 | 2022-10-20 | 10529864 | 2266071 | 2556783 | 4510307 | 0 | 0 | 0 | 0 | 0 | 19863025
SPC | 10 | Butler | 91288 | Balls Bend | 228 | 270 | Highway Reconstruction | ROW | STP | 2021-01-14 | 2021-01-07 | 0 | 235200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235200
SPC | 10 | Butler | 91288 | Balls Bend | 228 | 270 | Highway Reconstruction | ROW | 581 | 2021-01-14 | 2021-01-07 | 0 | 58800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58800
SPC | 10 | Butler | 92908 | Mars RR Bridge West Expansion | 228 | 29D | Additional Lanes | FD | STU | 2030-11-21 |  | 3700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700000
SPC | 10 | Butler | 92908 | Mars RR Bridge West Expansion | 228 | 29D | Additional Lanes | CON | NHPP | 2030-11-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21936153 | 21936153
SPC | 10 | Butler | 92908 | Mars RR Bridge West Expansion | 228 | 29D | Additional Lanes | CON | STP | 2030-11-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26293768 | 26293768
SPC | 10 | Butler | 92908 | Mars RR Bridge West Expansion | 228 | 29D | Additional Lanes | CON | STU | 2030-11-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8256750 | 8256750
SPC | 10 | Butler | 92908 | Mars RR Bridge West Expansion | 228 | 29D | Additional Lanes | CON | 581 | 2030-11-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36173329 | 36173329
SPC | 10 | Butler | 95876 | Victory Bridge | 7209 | 0 | Bridge Replacement | PE | BOF | 2032-02-22 |  | 0 | 0 | 398900 | 0 | 0 | 0 | 0 | 0 | 0 | 398900
SPC | 10 | Butler | 95876 | Victory Bridge | 7209 | 0 | Bridge Replacement | FD | BOF | 2032-02-22 |  | 0 | 0 | 0 | 394000 | 0 | 0 | 0 | 0 | 0 | 394000
SPC | 10 | Butler | 95876 | Victory Bridge | 7209 | 0 | Bridge Replacement | ROW | BOF | 2032-02-22 |  | 0 | 0 | 0 | 37800 | 0 | 0 | 0 | 0 | 0 | 37800
SPC | 10 | Butler | 95876 | Victory Bridge | 7209 | 0 | Bridge Replacement | UTL | BOF | 2032-02-22 |  | 0 | 0 | 0 | 78800 | 0 | 0 | 0 | 0 | 0 | 78800
SPC | 10 | Butler | 95876 | Victory Bridge | 7209 | 0 | Bridge Replacement | CON | BOF | 2032-02-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 185196 | 1300946 | 25858 | 1512000
SPC | 10 | Butler | 95881 | T-841 Courtney Mill Br. | 7221 | 0 | Bridge Replacement | PE | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000
SPC | 10 | Butler | 95881 | T-841 Courtney Mill Br. | 7221 | 0 | Bridge Replacement | FD | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000
SPC | 10 | Butler | 95881 | T-841 Courtney Mill Br. | 7221 | 0 | Bridge Replacement | ROW | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
SPC | 10 | Butler | 95881 | T-841 Courtney Mill Br. | 7221 | 0 | Bridge Replacement | UTL | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
SPC | 10 | Butler | 95881 | T-841 Courtney Mill Br. | 7221 | 0 | Bridge Replacement | CON | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7400000 | 7400000
SPC | 10 | Butler | 98028 | Shearer Bridge Pres. | 422 | 25C | Preventive Maintenance | CON | NHPP | 2025-07-24 | 2025-07-24 | 529756 | 489317 | 408210 | 0 | 0 | 0 | 0 | 0 | 0 | 1427283
SPC | 10 | Butler | 98028 | Shearer Bridge Pres. | 422 | 25C | Preventive Maintenance | CON | SXF | 2025-07-24 | 2025-07-24 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000
SPC | 10 | Butler | 98028 | Shearer Bridge Pres. | 422 | 25C | Preventive Maintenance | CON | 185 | 2025-07-24 | 2025-07-24 | 922329 | 300000 | 259492 | 0 | 0 | 0 | 0 | 0 | 0 | 1481821
SPC | 10 | Butler | 98108 | SR 68 - Butler North Resurfacing | 68 | 294 | 409 Expanded Maintenance | CON | 581 | 2026-02-26 | 2026-02-26 | 0 | 0 | 0 | 1632000 | 1632000 | 0 | 0 | 0 | 0 | 3264000
SPC | 10 | Butler | 98730 | Portersville Bridge | 488 | 250 | Bridge Replacement | CON | STP | 2022-02-17 | 2022-02-17 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275000
SPC | 10 | Butler | 98730 | Portersville Bridge | 488 | 250 | Bridge Replacement | CON | 185 | 2022-02-17 | 2022-02-17 | 68750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68750
SPC | 10 | Butler | 99683 | US 19 over Coal Run | 19 | 255 | Bridge Replacement | PE | BRIP | 2032-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000
SPC | 10 | Butler | 99683 | US 19 over Coal Run | 19 | 255 | Bridge Replacement | PE | 185 | 2032-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 80000
SPC | 10 | Butler | 99683 | US 19 over Coal Run | 19 | 255 | Bridge Replacement | FD | BRIP | 2032-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000
SPC | 10 | Butler | 99683 | US 19 over Coal Run | 19 | 255 | Bridge Replacement | FD | 185 | 2032-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 80000
SPC | 10 | Butler | 99683 | US 19 over Coal Run | 19 | 255 | Bridge Replacement | ROW | BRIP | 2032-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 80000
SPC | 10 | Butler | 99683 | US 19 over Coal Run | 19 | 255 | Bridge Replacement | ROW | 185 | 2032-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
SPC | 10 | Butler | 99683 | US 19 over Coal Run | 19 | 255 | Bridge Replacement | UTL | BRIP | 2032-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 80000
SPC | 10 | Butler | 99683 | US 19 over Coal Run | 19 | 255 | Bridge Replacement | UTL | 185 | 2032-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
SPC | 10 | Butler | 99683 | US 19 over Coal Run | 19 | 255 | Bridge Replacement | CON | BRIP | 2032-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2056000 | 2056000
SPC | 10 | Butler | 105574 | Zelienople Railroad Corridor | 288 | 271 | Rail Highway Grade Crossing | CON | RRX | 2029-01-18 |  | 0 | 0 | 392500 | 392500 | 0 | 0 | 0 | 0 | 0 | 785000
SPC | 10 | Butler | 105900 | Ekastown West 3R | 228 | 204 | Highway Restoration | FD | STP | 2026-03-26 | 2026-03-26 | 560000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560000
SPC | 10 | Butler | 105900 | Ekastown West 3R | 228 | 204 | Highway Restoration | UTL | STP | 2026-03-26 | 2026-03-26 | 0 | 1648000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1648000
SPC | 10 | Butler | 105900 | Ekastown West 3R | 228 | 204 | Highway Restoration | CON | STP | 2026-03-26 | 2026-03-26 | 0 | 3812186 | 5051926 | 3216847 | 0 | 0 | 0 | 0 | 0 | 12080959
SPC | 10 | Butler | 105900 | Ekastown West 3R | 228 | 204 | Highway Restoration | CON | SXF | 2026-03-26 | 2026-03-26 | 0 | 7000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000000
SPC | 10 | Butler | 105900 | Ekastown West 3R | 228 | 204 | Highway Restoration | CON | 581 | 2026-03-26 | 2026-03-26 | 0 | 0 | 836432 | 1190787 | 1784203 | 500001 | 0 | 0 | 0 | 4311423
SPC | 10 | Butler | 106486 | PA 356 Corridor Improvements | 356 | 293 | Congestion Reduction | FD | 581 | 2029-10-18 |  | 120441 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265441
SPC | 10 | Butler | 106486 | PA 356 Corridor Improvements | 356 | 293 | Congestion Reduction | ROW | STU | 2029-10-18 |  | 0 | 2560000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2560000
SPC | 10 | Butler | 106486 | PA 356 Corridor Improvements | 356 | 293 | Congestion Reduction | ROW | 581 | 2029-10-18 |  | 0 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640000
SPC | 10 | Butler | 106486 | PA 356 Corridor Improvements | 356 | 293 | Congestion Reduction | CON | STP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 1000000 | 502669 | 0 | 1752669
SPC | 10 | Butler | 106486 | PA 356 Corridor Improvements | 356 | 293 | Congestion Reduction | CON | 581 | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 5020625 | 9023506 | 5998800 | 0 | 20042931
SPC | 10 | Butler | 109385 | Slippery Rock Group Crossings |  |  | Rail Highway Grade Crossing | CON | RRX | 2032-01-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 550000
SPC | 10 | Butler | 110766 | Maple Avenue Crossing |  | 292 | Rail Highway Grade Crossing | CON | RRX | 2030-03-07 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
SPC | 10 | Butler | 110768 | Evans City Corridor Crossings |  |  | Rail Highway Grade Crossing | CON | RRX | 2030-01-10 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
SPC | 10 | Butler | 110783 | 10-2 SR 3021 Corridor Improvements | 3021 | 271 | Safety Improvement | CON | HSIP | 2023-12-07 | 2023-12-07 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 10 | Butler | 110783 | 10-2 SR 3021 Corridor Improvements | 3021 | 271 | Safety Improvement | CON | 581 | 2023-12-07 | 2023-12-07 | 618000 | 5607007 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 7725007
SPC | 10 | Butler | 111827 | Butler Co. Department Force Bridge Maintenance | 8 | 0 | Bridge Restoration | CON | 185 | 2028-10-05 |  | 154500 | 212200 | 218600 | 179351 | 225200 | 225200 | 225200 | 225200 | 900800 | 2566251
SPC | 10 | Butler | 112418 | Picklegate Bridge Preservation | 3001 | 250 | Bridge Restoration | PE | 185 | 2033-12-15 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 50000 | 0 | 0 | 200000
SPC | 10 | Butler | 112418 | Picklegate Bridge Preservation | 3001 | 250 | Bridge Restoration | FD | BRIP | 2033-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 0 | 280000
SPC | 10 | Butler | 112418 | Picklegate Bridge Preservation | 3001 | 250 | Bridge Restoration | FD | 185 | 2033-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 0 | 70000
SPC | 10 | Butler | 112418 | Picklegate Bridge Preservation | 3001 | 250 | Bridge Restoration | ROW | BRIP | 2033-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 16000
SPC | 10 | Butler | 112418 | Picklegate Bridge Preservation | 3001 | 250 | Bridge Restoration | ROW | 185 | 2033-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000
SPC | 10 | Butler | 112418 | Picklegate Bridge Preservation | 3001 | 250 | Bridge Restoration | UTL | BRIP | 2033-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 16000
SPC | 10 | Butler | 112418 | Picklegate Bridge Preservation | 3001 | 250 | Bridge Restoration | UTL | 185 | 2033-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000
SPC | 10 | Butler | 112418 | Picklegate Bridge Preservation | 3001 | 250 | Bridge Restoration | CON | BRIP | 2033-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200000 | 5200000
SPC | 10 | Butler | 112418 | Picklegate Bridge Preservation | 3001 | 250 | Bridge Restoration | CON | 185 | 2033-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000 | 1300000
SPC | 10 | Butler | 112528 | SR 3020 Haine School Road to Commonwealth Drive | 3020 | 297 | Highway Reconstruction | CON | STU | 2021-01-14 | 2021-01-07 | 9800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9800
SPC | 10 | Butler | 113652 | General Butler Bridge PM | 8 | 262 | Bridge Preservation - Federal | FD | STP | 2027-06-24 |  | 200000 | 85761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285761
SPC | 10 | Butler | 113652 | General Butler Bridge PM | 8 | 262 | Bridge Preservation - Federal | CON | NHPP | 2027-06-24 |  | 0 | 600604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600604
SPC | 10 | Butler | 113652 | General Butler Bridge PM | 8 | 262 | Bridge Preservation - Federal | CON | STP | 2027-06-24 |  | 0 | 0 | 2731850 | 1092750 | 1274495 | 228174 | 2000000 | 425100 | 0 | 7752369
SPC | 10 | Butler | 114789 | SR 8 Butler City to SR 308 | 8 | 202 | Preventive Maintenance | CON | 581 | 2025-10-23 | 2025-10-09 | 0 | 1618924 | 5869207 | 7194063 | 280981 | 0 | 0 | 0 | 0 | 14963175
SPC | 10 | Butler | 115104 | US 422 Lawrence County Line East PM | 422 | 201 | Preventive Maintenance | CON | 581 | 2026-01-29 | 2026-01-29 | 0 | 1825677 | 4163295 | 577366 | 357062 | 0 | 0 | 0 | 0 | 6923400
SPC | 10 | Butler | 115108 | US 422 Prospect PM | 422 | 202 | Preventive Maintenance | CON | 581 | 2030-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3245300 | 3245300 | 0 | 6490600
SPC | 10 | Butler | 115109 | US 422 Bonnie Brook East PM | 422 | 203 | Preventive Maintenance | CON | 581 | 2033-01-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4233270 | 4233270
SPC | 10 | Butler | 116127 | SR 356 Park-and-Ride | 356 | 294 | Congestion Reduction | CON | CAQ | 2029-10-18 |  | 0 | 0 | 0 | 2755518 | 0 | 0 | 0 | 0 | 0 | 2755518
SPC | 10 | Butler | 116127 | SR 356 Park-and-Ride | 356 | 294 | Congestion Reduction | CON | CRP | 2029-10-18 |  | 0 | 0 | 432680 | 0 | 0 | 0 | 0 | 0 | 0 | 432680
SPC | 10 | Butler | 116127 | SR 356 Park-and-Ride | 356 | 294 | Congestion Reduction | CON | 581 | 2029-10-18 |  | 0 | 0 | 0 | 576528 | 0 | 0 | 0 | 0 | 0 | 576528
SPC | 10 | Butler | 116661 | I-79 Seneca Ramps - TSMO | 79 | 295 | Congestion Reduction | CON | STP | 2023-12-07 | 2023-12-07 | 0 | 3148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3148
SPC | 10 | Butler | 117244 | Zelienople Bridge #1 Latex Overlay | 19 | 254 | Bridge Preservation - State Funded | CON | 185 | 2025-04-10 | 2025-04-10 | 1323367 | 780933 | 195700 | 0 | 0 | 0 | 0 | 0 | 0 | 2300000
SPC | 10 | Butler | 117246 | Wayne Street Viaduct Epoxy | 356 | 254 | Bridge Preservation - State Funded | FD | 185 | 2026-08-13 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 10 | Butler | 117246 | Wayne Street Viaduct Epoxy | 356 | 254 | Bridge Preservation - State Funded | CON | 185 | 2026-08-13 |  | 0 | 165500 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 665500
SPC | 10 | Butler | 117264 | Jefferson - Cunningham Streets Signal Improvements | 68 | 296 | Congestion Reduction | ROW | CAQ | 2025-03-27 | 2025-03-27 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
SPC | 10 | Butler | 117264 | Jefferson - Cunningham Streets Signal Improvements | 68 | 296 | Congestion Reduction | CON | CAQ | 2025-03-27 | 2025-03-27 | 2853157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2853157
SPC | 10 | Butler | 117264 | Jefferson - Cunningham Streets Signal Improvements | 68 | 296 | Congestion Reduction | CON | CRP | 2025-03-27 | 2025-03-27 | 615640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615640
SPC | 10 | Butler | 117264 | Jefferson - Cunningham Streets Signal Improvements | 68 | 296 | Congestion Reduction | CON | 581 | 2025-03-27 | 2025-03-27 | 368531 | 498668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 867199
SPC | 10 | Butler | 117334 | US 422 County Line West PM | 422 | 206 | Highway Restoration | CON | NHPP | 2028-01-13 |  | 0 | 0 | 2230722 | 1168232 | 0 | 0 | 0 | 0 | 0 | 3398954
SPC | 10 | Butler | 117334 | US 422 County Line West PM | 422 | 206 | Highway Restoration | CON | 581 | 2028-01-13 |  | 0 | 0 | 0 | 0 | 1684481 | 834420 | 1302707 | 1794438 | 0 | 5616046
SPC | 10 | Butler | 117377 | Butler Latex Group Bridges | 28 | 251 | Bridge Preservation - State Funded | FD | 185 | 2028-04-06 |  | 0 | 61295 | 416205 | 0 | 0 | 0 | 0 | 0 | 0 | 477500
SPC | 10 | Butler | 117377 | Butler Latex Group Bridges | 28 | 251 | Bridge Preservation - State Funded | UTL | 185 | 2028-04-06 |  | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 11000
SPC | 10 | Butler | 117377 | Butler Latex Group Bridges | 28 | 251 | Bridge Preservation - State Funded | CON | BRIP | 2028-04-06 |  | 0 | 0 | 0 | 0 | 0 | 1400000 | 1400000 | 0 | 0 | 2800000
SPC | 10 | Butler | 117377 | Butler Latex Group Bridges | 28 | 251 | Bridge Preservation - State Funded | CON | 185 | 2028-04-06 |  | 0 | 0 | 0 | 0 | 0 | 350000 | 350000 | 0 | 0 | 700000
SPC | 10 | Butler | 117378 | Butler Epoxy Group Bridges | 8 | 263 | Bridge Preservation - State Funded | CON | 185 | 2025-10-23 | 2025-10-23 | 0 | 875800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875800
SPC | 10 | Butler | 117652 | Lardintown Bridge #4 | 2011 | 251 | Bridge Replacement | PE | BOF | 2032-09-16 |  | 0 | 0 | 0 | 0 | 327184 | 0 | 0 | 0 | 0 | 327184
SPC | 10 | Butler | 117652 | Lardintown Bridge #4 | 2011 | 251 | Bridge Replacement | FD | BOF | 2032-09-16 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
SPC | 10 | Butler | 117652 | Lardintown Bridge #4 | 2011 | 251 | Bridge Replacement | ROW | BOF | 2032-09-16 |  | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000
SPC | 10 | Butler | 117652 | Lardintown Bridge #4 | 2011 | 251 | Bridge Replacement | UTL | BOF | 2032-09-16 |  | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000
SPC | 10 | Butler | 117652 | Lardintown Bridge #4 | 2011 | 251 | Bridge Replacement | CON | BOF | 2032-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 760000 | 0 | 0 | 760000
SPC | 10 | Butler | 117652 | Lardintown Bridge #4 | 2011 | 251 | Bridge Replacement | CON | 185 | 2032-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 0 | 0 | 190000
SPC | 10 | Butler | 118362 | Butler-Freeport Community Trail Stream Bank Stabil |  |  | Bicycle and Pedestrian Facilities Transit | CON | TAP | 2025-07-24 | 2025-07-24 | 561476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561476
SPC | 10 | Butler | 119471 | SR 3007 Slide Repair | 3007 | 201 | Safety Improvement | FD | 581 | 2024-02-15 | 2024-02-15 | 8950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8950
SPC | 10 | Butler | 119692 | D10/SPC Carbon Reduction Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 149640 | 0 | 0 | 0 | 0 | 0 | 450240 | 1932000 | 2531880
SPC | 10 | Butler | 119717 | SR 3022 Rochester Road Widening | 3022 | 291 | Highway Reconstruction | STUDY | 581 | 2035-05-17 |  | 0 | 321159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321159
SPC | 10 | Butler | 119717 | SR 3022 Rochester Road Widening | 3022 | 291 | Highway Reconstruction | PE | 581 | 2035-05-17 |  | 0 | 800000 | 827758 | 0 | 0 | 0 | 0 | 0 | 0 | 1627758
SPC | 10 | Butler | 120409 | South Monroe Street Bridge | 7301 | 250 | Bridge Replacement | PE | BOF | 2028-10-19 |  | 0 | 583500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583500
SPC | 10 | Butler | 120409 | South Monroe Street Bridge | 7301 | 250 | Bridge Replacement | FD | BOF | 2028-10-19 |  | 0 | 0 | 260900 | 230900 | 0 | 0 | 0 | 0 | 0 | 491800
SPC | 10 | Butler | 120409 | South Monroe Street Bridge | 7301 | 250 | Bridge Replacement | ROW | BOF | 2028-10-19 |  | 0 | 0 | 0 | 337700 | 0 | 0 | 0 | 0 | 0 | 337700
SPC | 10 | Butler | 120409 | South Monroe Street Bridge | 7301 | 250 | Bridge Replacement | UTL | BOF | 2028-10-19 |  | 0 | 0 | 0 | 168900 | 0 | 0 | 0 | 0 | 0 | 168900
SPC | 10 | Butler | 120409 | South Monroe Street Bridge | 7301 | 250 | Bridge Replacement | CON | BOF | 2028-10-19 |  | 0 | 0 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 550000
SPC | 10 | Butler | 120525 | T-487 Woodland Road Bridge (CO #110 Giles) | 7226 | 0 | Bridge Restoration | PE | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
SPC | 10 | Butler | 120525 | T-487 Woodland Road Bridge (CO #110 Giles) | 7226 | 0 | Bridge Restoration | FD | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 207996 | 42004 | 0 | 0 | 250000
SPC | 10 | Butler | 120525 | T-487 Woodland Road Bridge (CO #110 Giles) | 7226 | 0 | Bridge Restoration | ROW | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 10000
SPC | 10 | Butler | 120525 | T-487 Woodland Road Bridge (CO #110 Giles) | 7226 | 0 | Bridge Restoration | UTL | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 10000
SPC | 10 | Butler | 120525 | T-487 Woodland Road Bridge (CO #110 Giles) | 7226 | 0 | Bridge Restoration | CON | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775000 | 775000
SPC | 10 | Butler | 121003 | Near Hallston Bridge | 1010 | 0 | Bridge Replacement | PE | BOF | 2031-12-11 |  | 0 | 0 | 0 | 0 | 255500 | 0 | 0 | 0 | 0 | 255500
SPC | 10 | Butler | 121003 | Near Hallston Bridge | 1010 | 0 | Bridge Replacement | FD | BOF | 2031-12-11 |  | 0 | 0 | 0 | 0 | 0 | 245000 | 0 | 0 | 0 | 245000
SPC | 10 | Butler | 121003 | Near Hallston Bridge | 1010 | 0 | Bridge Replacement | ROW | BOF | 2031-12-11 |  | 0 | 0 | 0 | 0 | 0 | 33500 | 0 | 0 | 0 | 33500
SPC | 10 | Butler | 121003 | Near Hallston Bridge | 1010 | 0 | Bridge Replacement | UTL | BOF | 2031-12-11 |  | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 35000
SPC | 10 | Butler | 121003 | Near Hallston Bridge | 1010 | 0 | Bridge Replacement | CON | BOF | 2031-12-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 604800 | 604800 | 0 | 1209600
SPC | 10 | Butler | 121003 | Near Hallston Bridge | 1010 | 0 | Bridge Replacement | CON | 185 | 2031-12-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 151200 | 151200 | 0 | 302400
SPC | 10 | Butler | 121007 | NE of Evans City Bridge #1 Preservation | 68 | 257 | Bridge Preservation - Federal | FD | STP | 2033-12-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 400000
SPC | 10 | Butler | 121007 | NE of Evans City Bridge #1 Preservation | 68 | 257 | Bridge Preservation - Federal | UTL | STP | 2033-12-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000
SPC | 10 | Butler | 121007 | NE of Evans City Bridge #1 Preservation | 68 | 257 | Bridge Preservation - Federal | CON | STP | 2033-12-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
SPC | 10 | Butler | 121010 | South of Brownsdale Bridge #1 Preservation | 3007 | 0 | Bridge Preservation - Federal | PE | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
SPC | 10 | Butler | 121010 | South of Brownsdale Bridge #1 Preservation | 3007 | 0 | Bridge Preservation - Federal | FD | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000
SPC | 10 | Butler | 121010 | South of Brownsdale Bridge #1 Preservation | 3007 | 0 | Bridge Preservation - Federal | ROW | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
SPC | 10 | Butler | 121010 | South of Brownsdale Bridge #1 Preservation | 3007 | 0 | Bridge Preservation - Federal | CON | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 950000
SPC | 10 | Butler | 121188 | Butler Main St. Student and Ped Safety Project | 8 | 274 | Congestion Reduction | CON | CAQ | 2027-03-04 |  | 0 | 0 | 1545356 | 0 | 0 | 0 | 0 | 0 | 0 | 1545356
SPC | 10 | Butler | 122284 | Forward Township Guiderail MTF |  | 293 | MultiModal | CON | 411 |  |  | 44076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44076
SPC | 10 | Butler | 122284 | Forward Township Guiderail MTF |  | 293 | MultiModal | CON | LOC |  |  | 18890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18890
SPC | 10 | Butler | 122289 | Clinton Township Road Resurfacing Project MTF |  | 294 | MultiModal | CON | 411 |  |  | 408361.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408361.8
SPC | 10 | Butler | 122289 | Clinton Township Road Resurfacing Project MTF |  | 294 | MultiModal | CON | LOC |  |  | 175012.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175012.2
SPC | 10 | Butler | 122521 | Zelienople Borough Main St/Spring St Crosswalk MTF |  | 296 | MultiModal | CON | 411 |  |  | 72240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72240
SPC | 10 | Butler | 122521 | Zelienople Borough Main St/Spring St Crosswalk MTF |  | 296 | MultiModal | CON | LOC |  |  | 24560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24560
SPC | 10 | Butler | 123978 | Equitable Access to Opportunity in Butler Township |  | 287 | MultiModal | CON | STU | 2026-10-01 |  | 0 | 0 | 481320 | 0 | 0 | 0 | 0 | 0 | 0 | 481320
SPC | 10 | Butler | 123978 | Equitable Access to Opportunity in Butler Township |  | 287 | MultiModal | CON | LOC | 2026-10-01 |  | 0 | 0 | 300825 | 0 | 0 | 0 | 0 | 0 | 0 | 300825
SPC | 10 | Butler | 123980 | Butler County Bridge Bundle MTF | 7226 | 250 | Bridge Restoration | PE | 411 | 2027-03-25 |  | 0 | 86000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86000
SPC | 10 | Butler | 123980 | Butler County Bridge Bundle MTF | 7226 | 250 | Bridge Restoration | PE | LOC | 2027-03-25 |  | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
SPC | 10 | Butler | 123980 | Butler County Bridge Bundle MTF | 7226 | 250 | Bridge Restoration | FD | 411 | 2027-03-25 |  | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000
SPC | 10 | Butler | 123980 | Butler County Bridge Bundle MTF | 7226 | 250 | Bridge Restoration | FD | LOC | 2027-03-25 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 10 | Butler | 123980 | Butler County Bridge Bundle MTF | 7226 | 250 | Bridge Restoration | CON | 411 | 2027-03-25 |  | 0 | 2349200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349200
SPC | 10 | Butler | 123980 | Butler County Bridge Bundle MTF | 7226 | 250 | Bridge Restoration | CON | LOC | 2027-03-25 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 10 | Indiana | 25548 | US 422 over Two Lick Ck. | 422 | 467 | Bridge Restoration | CON | NHPP | 2023-01-12 | 2023-01-12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
SPC | 10 | Indiana | 25587 | Broadhead Run Bridge #2 | 1045 | 453 | Bridge Replacement | CON | BOF | 2025-08-07 | 2025-08-07 | 704542 | 900306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1604848
SPC | 10 | Indiana | 25596 | PA 286 ovTrib to Cherry Rn | 286 | 465 | Bridge Replacement | UTL | 185 | 2025-10-23 | 2025-10-23 | 58365 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233365
SPC | 10 | Indiana | 25596 | PA 286 ovTrib to Cherry Rn | 286 | 465 | Bridge Replacement | CON | 185 | 2025-10-23 | 2025-10-23 | 0 | 1229937 | 1003216 | 0 | 0 | 0 | 0 | 0 | 0 | 2233153
SPC | 10 | Indiana | 25602 | Green Valley Bridge #1 | 3031 | 451 | Bridge Replacement | ROW | 185 | 2025-01-09 | 2025-01-09 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000
SPC | 10 | Indiana | 25602 | Green Valley Bridge #1 | 3031 | 451 | Bridge Replacement | UTL | 185 | 2025-01-09 | 2025-01-09 | 0 | 51500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51500
SPC | 10 | Indiana | 25602 | Green Valley Bridge #1 | 3031 | 451 | Bridge Replacement | CON | 185 | 2025-01-09 | 2025-01-09 | 391686 | 317700 | 375100 | 0 | 0 | 0 | 0 | 0 | 0 | 1084486
SPC | 10 | Indiana | 25616 | US 119 Sullivan NB/SB Bridges | 119 | 46A | Bridge Replacement | PE | 185 | 2034-10-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 25616 | US 119 Sullivan NB/SB Bridges | 119 | 46A | Bridge Replacement | FD | 185 | 2034-10-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 25616 | US 119 Sullivan NB/SB Bridges | 119 | 46A | Bridge Replacement | ROW | 185 | 2034-10-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 25616 | US 119 Sullivan NB/SB Bridges | 119 | 46A | Bridge Replacement | CON | 185 | 2034-10-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4190163 | 4190163
SPC | 10 | Indiana | 25621 | US 119 over SR 8001 (Northbound and Southbound) | 119 | 467 | Bridge Replacement | CON | NHPP | 2030-01-31 |  | 0 | 0 | 0 | 1500000 | 712327 | 4176740 | 1600334 | 1215868 | 0 | 9205269
SPC | 10 | Indiana | 25621 | US 119 over SR 8001 (Northbound and Southbound) | 119 | 467 | Bridge Replacement | CON | STP | 2030-01-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 838266 | 0 | 0 | 838266
SPC | 10 | Indiana | 25621 | US 119 over SR 8001 (Northbound and Southbound) | 119 | 467 | Bridge Replacement | CON | STU | 2030-01-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2085585 | 1144857 | 3230442
SPC | 10 | Indiana | 25621 | US 119 over SR 8001 (Northbound and Southbound) | 119 | 467 | Bridge Replacement | CON | 185 | 2030-01-31 |  | 0 | 0 | 0 | 375000 | 178082 | 1044185 | 857713 | 1075363 | 1021397 | 4551740
SPC | 10 | Indiana | 25777 | McKeages Crossing | 580 | 451 | Bridge Replacement | PE | BOF | 2028-09-28 |  | 386998 | 113002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 10 | Indiana | 25777 | McKeages Crossing | 580 | 451 | Bridge Replacement | FD | BOF | 2028-09-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 25777 | McKeages Crossing | 580 | 451 | Bridge Replacement | ROW | BOF | 2028-09-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
SPC | 10 | Indiana | 25777 | McKeages Crossing | 580 | 451 | Bridge Replacement | UTL | BOF | 2028-09-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000
SPC | 10 | Indiana | 25777 | McKeages Crossing | 580 | 451 | Bridge Replacement | CON | BOF | 2028-09-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1592826 | 1592826
SPC | 10 | Indiana | 25779 | Fulton Run Road Bridge | 954 | 460 | Bridge Replacement | PE | 185 | 2029-10-18 |  | 185300 | 214700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 10 | Indiana | 25779 | Fulton Run Road Bridge | 954 | 460 | Bridge Replacement | FD | 185 | 2029-10-18 |  | 0 | 0 | 316900 | 0 | 0 | 0 | 0 | 0 | 0 | 316900
SPC | 10 | Indiana | 25779 | Fulton Run Road Bridge | 954 | 460 | Bridge Replacement | ROW | 185 | 2029-10-18 |  | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 5500
SPC | 10 | Indiana | 25779 | Fulton Run Road Bridge | 954 | 460 | Bridge Replacement | UTL | 185 | 2029-10-18 |  | 0 | 0 | 54700 | 0 | 0 | 0 | 0 | 0 | 0 | 54700
SPC | 10 | Indiana | 25779 | Fulton Run Road Bridge | 954 | 460 | Bridge Replacement | CON | 185 | 2029-10-18 |  | 0 | 0 | 0 | 0 | 637649 | 637650 | 0 | 0 | 0 | 1275299
SPC | 10 | Indiana | 25793 | Coy Bridge #2 | 2019 | 451 | Bridge Replacement | PE | BOF | 2032-02-12 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
SPC | 10 | Indiana | 25793 | Coy Bridge #2 | 2019 | 451 | Bridge Replacement | FD | BOF | 2032-02-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 400000
SPC | 10 | Indiana | 25793 | Coy Bridge #2 | 2019 | 451 | Bridge Replacement | ROW | BOF | 2032-02-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000
SPC | 10 | Indiana | 25793 | Coy Bridge #2 | 2019 | 451 | Bridge Replacement | UTL | BOF | 2032-02-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000
SPC | 10 | Indiana | 25793 | Coy Bridge #2 | 2019 | 451 | Bridge Replacement | CON | BOF | 2032-02-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448200 | 0 | 448200
SPC | 10 | Indiana | 25795 | Clarksburg Bridge #1 | 3007 | 452 | Bridge Replacement | CON | BOF | 2024-08-22 | 2024-08-22 | 296283 | 155670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451953
SPC | 10 | Indiana | 25798 | Muddy Run Bridge #3 | 3013 | 451 | Bridge Replacement | PE | STP | 2028-03-02 |  | 346808 | 335525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682333
SPC | 10 | Indiana | 25798 | Muddy Run Bridge #3 | 3013 | 451 | Bridge Replacement | FD | BRIP | 2028-03-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 25798 | Muddy Run Bridge #3 | 3013 | 451 | Bridge Replacement | ROW | BRIP | 2028-03-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 10 | Indiana | 25798 | Muddy Run Bridge #3 | 3013 | 451 | Bridge Replacement | UTL | BRIP | 2028-03-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 10 | Indiana | 25798 | Muddy Run Bridge #3 | 3013 | 451 | Bridge Replacement | CON | BRIP | 2028-03-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
SPC | 10 | Indiana | 25802 | Anthony Run Bridge #2 | 3039 | 450 | Bridge Replacement | CON | BOF | 2025-08-07 | 2025-08-07 | 863695 | 910975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1774670
SPC | 10 | Indiana | 25813 | Diamondville Bridge #1 | 1012 | 452 | Bridge Replacement | PE | BOF | 2031-02-08 |  | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000
SPC | 10 | Indiana | 25813 | Diamondville Bridge #1 | 1012 | 452 | Bridge Replacement | FD | BOF | 2031-02-08 |  | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 450000
SPC | 10 | Indiana | 25813 | Diamondville Bridge #1 | 1012 | 452 | Bridge Replacement | ROW | BOF | 2031-02-08 |  | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 35000
SPC | 10 | Indiana | 25813 | Diamondville Bridge #1 | 1012 | 452 | Bridge Replacement | UTL | BOF | 2031-02-08 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 10 | Indiana | 25813 | Diamondville Bridge #1 | 1012 | 452 | Bridge Replacement | CON | BOF | 2031-02-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 752600 | 752600 | 0 | 1505200
SPC | 10 | Indiana | 25813 | Diamondville Bridge #1 | 1012 | 452 | Bridge Replacement | CON | 185 | 2031-02-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 188150 | 188150 | 0 | 376300
SPC | 10 | Indiana | 78101 | Mentch Bridge EB/WB | 422 | 466 | Bridge Replacement | FD | NHPP | 2021-12-16 | 2021-12-16 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264
SPC | 10 | Indiana | 78117 | Rearick Road Bridge #1 | 3010 | 451 | Bridge Replacement | CON | BOF | 2025-08-21 | 2025-08-21 | 383700 | 763100 | 58154 | 0 | 0 | 0 | 0 | 0 | 0 | 1204954
SPC | 10 | Indiana | 78117 | Rearick Road Bridge #1 | 3010 | 451 | Bridge Replacement | CON | 185 | 2025-08-21 | 2025-08-21 | 286424 | 0 | 14815 | 0 | 0 | 0 | 0 | 0 | 0 | 301239
SPC | 10 | Indiana | 78118 | SR 3017 Cherry Run Bridge | 3017 | 450 | Bridge Replacement | PE | 185 | 2027-10-07 |  | 299423 | 201077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500500
SPC | 10 | Indiana | 78118 | SR 3017 Cherry Run Bridge | 3017 | 450 | Bridge Replacement | FD | 185 | 2027-10-07 |  | 0 | 382500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382500
SPC | 10 | Indiana | 78118 | SR 3017 Cherry Run Bridge | 3017 | 450 | Bridge Replacement | ROW | 185 | 2027-10-07 |  | 0 | 54700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54700
SPC | 10 | Indiana | 78118 | SR 3017 Cherry Run Bridge | 3017 | 450 | Bridge Replacement | UTL | 185 | 2027-10-07 |  | 0 | 54700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54700
SPC | 10 | Indiana | 78118 | SR 3017 Cherry Run Bridge | 3017 | 450 | Bridge Replacement | CON | 185 | 2027-10-07 |  | 0 | 0 | 0 | 0 | 985000 | 985000 | 0 | 0 | 0 | 1970000
SPC | 10 | Indiana | 78119 | Davis Bridge #2 | 4006 | 451 | Bridge Replacement | PE | BOF | 2031-02-08 |  | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000
SPC | 10 | Indiana | 78119 | Davis Bridge #2 | 4006 | 451 | Bridge Replacement | FD | BOF | 2031-02-08 |  | 0 | 0 | 0 | 0 | 0 | 360000 | 0 | 0 | 0 | 360000
SPC | 10 | Indiana | 78119 | Davis Bridge #2 | 4006 | 451 | Bridge Replacement | ROW | BOF | 2031-02-08 |  | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 35000
SPC | 10 | Indiana | 78119 | Davis Bridge #2 | 4006 | 451 | Bridge Replacement | UTL | BOF | 2031-02-08 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 10 | Indiana | 78119 | Davis Bridge #2 | 4006 | 451 | Bridge Replacement | CON | BOF | 2031-02-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 552000 | 552000 | 0 | 1104000
SPC | 10 | Indiana | 78119 | Davis Bridge #2 | 4006 | 451 | Bridge Replacement | CON | 185 | 2031-02-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 138000 | 138000 | 0 | 276000
SPC | 10 | Indiana | 83213 | Creekside Bridge #1 | 110 | 453 | Bridge Replacement | PE | BRIP | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
SPC | 10 | Indiana | 83213 | Creekside Bridge #1 | 110 | 453 | Bridge Replacement | FD | BRIP | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 400000
SPC | 10 | Indiana | 83213 | Creekside Bridge #1 | 110 | 453 | Bridge Replacement | ROW | BRIP | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000
SPC | 10 | Indiana | 83213 | Creekside Bridge #1 | 110 | 453 | Bridge Replacement | UTL | BRIP | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000
SPC | 10 | Indiana | 83213 | Creekside Bridge #1 | 110 | 453 | Bridge Replacement | CON | BRIP | 2031-10-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 1750000
SPC | 10 | Indiana | 83227 | US 119 over Pine Run | 119 | 45B | Bridge Replacement | PE | 185 | 2029-10-18 |  | 0 | 63291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63291
SPC | 10 | Indiana | 83227 | US 119 over Pine Run | 119 | 45B | Bridge Replacement | FD | 581 | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 83227 | US 119 over Pine Run | 119 | 45B | Bridge Replacement | ROW | 581 | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
SPC | 10 | Indiana | 83227 | US 119 over Pine Run | 119 | 45B | Bridge Replacement | UTL | 581 | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000
SPC | 10 | Indiana | 83227 | US 119 over Pine Run | 119 | 45B | Bridge Replacement | CON | 581 | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 1750000
SPC | 10 | Indiana | 83255 | Rossmoyne Bridge No. 1 | 210 | 451 | Bridge Replacement | PE | 185 | 2027-06-24 |  | 294761 | 201999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496760
SPC | 10 | Indiana | 83255 | Rossmoyne Bridge No. 1 | 210 | 451 | Bridge Replacement | FD | 185 | 2027-06-24 |  | 0 | 371400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371400
SPC | 10 | Indiana | 83255 | Rossmoyne Bridge No. 1 | 210 | 451 | Bridge Replacement | ROW | 185 | 2027-06-24 |  | 0 | 31900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31900
SPC | 10 | Indiana | 83255 | Rossmoyne Bridge No. 1 | 210 | 451 | Bridge Replacement | UTL | 185 | 2027-06-24 |  | 0 | 53100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53100
SPC | 10 | Indiana | 83255 | Rossmoyne Bridge No. 1 | 210 | 451 | Bridge Replacement | CON | 185 | 2027-06-24 |  | 0 | 0 | 1038100 | 0 | 0 | 0 | 0 | 0 | 0 | 1038100
SPC | 10 | Indiana | 83356 | SR 3024 over McCarthy Run | 3024 | 000 | Bridge Replacement | CON | 185 | 2033-06-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019360 | 2019360
SPC | 10 | Indiana | 83370 | Dilltown Bridge No. 3 | 2012 | 451 | Bridge Replacement | UTL | BOF | 2025-01-09 | 2025-01-09 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000
SPC | 10 | Indiana | 83370 | Dilltown Bridge No. 3 | 2012 | 451 | Bridge Replacement | CON | BOF | 2025-01-09 | 2025-01-09 | 1772432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1772432
SPC | 10 | Indiana | 83382 | SR 3007 over Marshall Run #1 | 3007 | 451 | Bridge Replacement | CON | 185 | 2024-08-22 | 2024-08-22 | 758256 | 258500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016756
SPC | 10 | Indiana | 83387 | Stewart Run Bridge | 3013 | 450 | Bridge Replacement | PE | 185 | 2028-03-02 |  | 0 | 134235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134235
SPC | 10 | Indiana | 83387 | Stewart Run Bridge | 3013 | 450 | Bridge Replacement | ROW | 185 | 2028-03-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 10 | Indiana | 83387 | Stewart Run Bridge | 3013 | 450 | Bridge Replacement | UTL | 185 | 2028-03-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 10 | Indiana | 83387 | Stewart Run Bridge | 3013 | 450 | Bridge Replacement | CON | 185 | 2028-03-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
SPC | 10 | Indiana | 88615 | Indiana US 422 Bypass Repair | 422 | 405 | Highway Restoration | CON | NHPP | 2024-09-12 | 2024-09-12 | 8336119 | 1371378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9707497
SPC | 10 | Indiana | 93991 | Carl E. Keith Memorial Bridge Rehabilitation | 1014 | 0 | Bridge Restoration | PE | BOF | 2033-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000
SPC | 10 | Indiana | 93991 | Carl E. Keith Memorial Bridge Rehabilitation | 1014 | 0 | Bridge Restoration | FD | BOF | 2033-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000
SPC | 10 | Indiana | 93991 | Carl E. Keith Memorial Bridge Rehabilitation | 1014 | 0 | Bridge Restoration | ROW | BOF | 2033-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 10 | Indiana | 93991 | Carl E. Keith Memorial Bridge Rehabilitation | 1014 | 0 | Bridge Restoration | UTL | BOF | 2033-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 10 | Indiana | 93991 | Carl E. Keith Memorial Bridge Rehabilitation | 1014 | 0 | Bridge Restoration | CON | BOF | 2033-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
SPC | 10 | Indiana | 95727 | US 119 Hamill NB/SB Bridges | 119 | 46B | Bridge Replacement | PE | 185 | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 400000
SPC | 10 | Indiana | 95727 | US 119 Hamill NB/SB Bridges | 119 | 46B | Bridge Replacement | CON | 185 | 2034-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250424 | 2449370 | 3316130 | 6015924
SPC | 10 | Indiana | 95728 | Hamill SB Bridge Preserv. | 119 | 0 | Bridge Preservation - State Funded | PE | 185 | 2032-02-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 400000
SPC | 10 | Indiana | 95728 | Hamill SB Bridge Preserv. | 119 | 0 | Bridge Preservation - State Funded | CON | 185 | 2032-02-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250424 | 2449370 | 3316130 | 6015924
SPC | 10 | Indiana | 95850 | Brush Valley Bridge #10 | 2018 | 451 | Bridge Replacement | PE | BOF | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 95850 | Brush Valley Bridge #10 | 2018 | 451 | Bridge Replacement | FD | BOF | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 95850 | Brush Valley Bridge #10 | 2018 | 451 | Bridge Replacement | ROW | BOF | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
SPC | 10 | Indiana | 95850 | Brush Valley Bridge #10 | 2018 | 451 | Bridge Replacement | UTL | BOF | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000
SPC | 10 | Indiana | 95850 | Brush Valley Bridge #10 | 2018 | 451 | Bridge Replacement | CON | BOF | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 1600000
SPC | 10 | Indiana | 95852 | US 119 over Two Lick Ck. | 119 | 468 | Bridge Restoration | FD | NHPP | 2030-02-14 |  | 20000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000
SPC | 10 | Indiana | 95852 | US 119 over Two Lick Ck. | 119 | 468 | Bridge Restoration | CON | NHPP | 2030-02-14 |  | 0 | 0 | 2400000 | 1343640 | 1263140 | 1263140 | 0 | 0 | 0 | 6269920
SPC | 10 | Indiana | 95852 | US 119 over Two Lick Ck. | 119 | 468 | Bridge Restoration | CON | 185 | 2030-02-14 |  | 0 | 0 | 600000 | 335910 | 315785 | 315785 | 0 | 0 | 0 | 1567480
SPC | 10 | Indiana | 98805 | Buena Vista Bridge Preservation | 56 | 458 | Preventive Maintenance | PE | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 350000
SPC | 10 | Indiana | 98805 | Buena Vista Bridge Preservation | 56 | 458 | Preventive Maintenance | FD | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 350000
SPC | 10 | Indiana | 98805 | Buena Vista Bridge Preservation | 56 | 458 | Preventive Maintenance | CON | 185 | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4162100 | 4162100
SPC | 10 | Indiana | 98811 | Bridge to Nowhere EB/WB PM | 422 | 45B | Bridge Restoration | FD | NHPP | 2027-02-25 |  | 750000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000
SPC | 10 | Indiana | 98811 | Bridge to Nowhere EB/WB PM | 422 | 45B | Bridge Restoration | ROW | NHPP | 2027-02-25 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 10 | Indiana | 98811 | Bridge to Nowhere EB/WB PM | 422 | 45B | Bridge Restoration | UTL | NHPP | 2027-02-25 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SPC | 10 | Indiana | 98811 | Bridge to Nowhere EB/WB PM | 422 | 45B | Bridge Restoration | CON | BRIP | 2027-02-25 |  | 0 | 0 | 463700 | 3632937 | 0 | 3961533 | 3082393 | 2972329 | 1500340 | 15613232
SPC | 10 | Indiana | 98811 | Bridge to Nowhere EB/WB PM | 422 | 45B | Bridge Restoration | CON | NHPP | 2027-02-25 |  | 0 | 217692 | 0 | 0 | 0 | 1038047 | 2440858 | 0 | 0 | 3696597
SPC | 10 | Indiana | 98811 | Bridge to Nowhere EB/WB PM | 422 | 45B | Bridge Restoration | CON | STP | 2027-02-25 |  | 0 | 0 | 0 | 0 | 5639226 | 3576945 | 0 | 0 | 0 | 9216171
SPC | 10 | Indiana | 98811 | Bridge to Nowhere EB/WB PM | 422 | 45B | Bridge Restoration | CON | 581 | 2027-02-25 |  | 0 | 0 | 0 | 0 | 0 | 259512 | 610214 | 0 | 0 | 869726
SPC | 10 | Indiana | 101113 | Stoney Run Bridge #1 | 119 | 469 | Bridge Restoration | CON | NHPP | 2030-02-14 |  | 0 | 0 | 1600000 | 961040 | 1048360 | 1048360 | 0 | 0 | 0 | 4657760
SPC | 10 | Indiana | 101113 | Stoney Run Bridge #1 | 119 | 469 | Bridge Restoration | CON | 185 | 2030-02-14 |  | 0 | 0 | 400000 | 240260 | 262090 | 262090 | 0 | 0 | 0 | 1164440
SPC | 10 | Indiana | 105582 | Olson Road Crossing |  |  | Rail Highway Grade Crossing | CON | RRX | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
SPC | 10 | Indiana | 111796 | Indian Springs Road/Rustic Lodge Road Intersection | 4422 | 471 | Additional Lanes | UTL | 581 | 2023-11-02 | 2023-11-02 | 1333 | 63560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64893
SPC | 10 | Indiana | 111829 | Indiana Co. Department Force Bridge Maintenance | 553 | 0 | Bridge Restoration | CON | 185 | 2028-10-05 |  | 154500 | 212200 | 218600 | 179351 | 225200 | 225200 | 225200 | 225200 | 900800 | 2566251
SPC | 10 | Indiana | 112424 | US 22 Penn View PM | 22 | 404 | Preventive Maintenance | CON | NHPP | 2028-01-13 |  | 0 | 0 | 0 | 1141129 | 0 | 0 | 0 | 0 | 0 | 1141129
SPC | 10 | Indiana | 112424 | US 22 Penn View PM | 22 | 404 | Preventive Maintenance | CON | 581 | 2028-01-13 |  | 0 | 0 | 0 | 285283 | 3391321 | 4143767 | 0 | 0 | 0 | 7820371
SPC | 10 | Indiana | 112431 | SR 119 Indiana Bypass Reconstruction | 119 | 0 | Highway Reconstruction | FD | 581 | 2033-10-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 112431 | SR 119 Indiana Bypass Reconstruction | 119 | 0 | Highway Reconstruction | CON | 581 | 2033-10-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11748739 | 11748739
SPC | 10 | Indiana | 112537 | US 119 Sullivan Northbound Bridge | 119 | 0 | Bridge Restoration | PE | 185 | 2033-10-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 112537 | US 119 Sullivan Northbound Bridge | 119 | 0 | Bridge Restoration | FD | 185 | 2033-10-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 112537 | US 119 Sullivan Northbound Bridge | 119 | 0 | Bridge Restoration | ROW | 185 | 2033-10-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 112537 | US 119 Sullivan Northbound Bridge | 119 | 0 | Bridge Restoration | CON | 185 | 2033-10-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4190163 | 4190163
SPC | 10 | Indiana | 112632 | US 119 Lutz School Road NB/SB Bridges | 119 | 46C | Bridge Restoration | PE | 185 | 2033-10-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 112632 | US 119 Lutz School Road NB/SB Bridges | 119 | 46C | Bridge Restoration | FD | 185 | 2033-10-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 112632 | US 119 Lutz School Road NB/SB Bridges | 119 | 46C | Bridge Restoration | ROW | 185 | 2033-10-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
SPC | 10 | Indiana | 112632 | US 119 Lutz School Road NB/SB Bridges | 119 | 46C | Bridge Restoration | UTL | 185 | 2033-10-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
SPC | 10 | Indiana | 112632 | US 119 Lutz School Road NB/SB Bridges | 119 | 46C | Bridge Restoration | CON | STP | 2033-10-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537140 | 537140
SPC | 10 | Indiana | 112632 | US 119 Lutz School Road NB/SB Bridges | 119 | 46C | Bridge Restoration | CON | 185 | 2033-10-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283185 | 283185
SPC | 10 | Indiana | 112661 | US 119 Lutz School Road Southbound Bridge | 119 | 0 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 112661 | US 119 Lutz School Road Southbound Bridge | 119 | 0 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 112661 | US 119 Lutz School Road Southbound Bridge | 119 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
SPC | 10 | Indiana | 112661 | US 119 Lutz School Road Southbound Bridge | 119 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
SPC | 10 | Indiana | 114423 | Jacksonville Bridge #1 | 286 | 466 | Bridge Replacement | UTL | NHPP | 2026-08-27 |  | 216900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216900
SPC | 10 | Indiana | 114423 | Jacksonville Bridge #1 | 286 | 466 | Bridge Replacement | CON | BRIP | 2026-08-27 |  | 0 | 0 | 1313044 | 500756 | 0 | 0 | 0 | 0 | 0 | 1813800
SPC | 10 | Indiana | 114605 | US 422: Armstrong County Line to Indiana Bypass | 422 | 402 | Highway Reconstruction | PE | NHPP | 2030-10-10 |  | 257500 | 842500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000
SPC | 10 | Indiana | 114605 | US 422: Armstrong County Line to Indiana Bypass | 422 | 402 | Highway Reconstruction | FD | NHPP | 2030-10-10 |  | 0 | 0 | 218560 | 218560 | 0 | 0 | 0 | 0 | 0 | 437120
SPC | 10 | Indiana | 114605 | US 422: Armstrong County Line to Indiana Bypass | 422 | 402 | Highway Reconstruction | FD | 581 | 2030-10-10 |  | 0 | 0 | 54640 | 54640 | 0 | 0 | 0 | 0 | 0 | 109280
SPC | 10 | Indiana | 114605 | US 422: Armstrong County Line to Indiana Bypass | 422 | 402 | Highway Reconstruction | ROW | NHPP | 2030-10-10 |  | 0 | 0 | 437120 | 437120 | 0 | 0 | 0 | 0 | 0 | 874240
SPC | 10 | Indiana | 114605 | US 422: Armstrong County Line to Indiana Bypass | 422 | 402 | Highway Reconstruction | ROW | 581 | 2030-10-10 |  | 0 | 0 | 109280 | 109280 | 0 | 0 | 0 | 0 | 0 | 218560
SPC | 10 | Indiana | 114605 | US 422: Armstrong County Line to Indiana Bypass | 422 | 402 | Highway Reconstruction | UTL | NHPP | 2030-10-10 |  | 0 | 0 | 218560 | 218560 | 0 | 0 | 0 | 0 | 0 | 437120
SPC | 10 | Indiana | 114605 | US 422: Armstrong County Line to Indiana Bypass | 422 | 402 | Highway Reconstruction | UTL | 581 | 2030-10-10 |  | 0 | 0 | 54640 | 54640 | 0 | 0 | 0 | 0 | 0 | 109280
SPC | 10 | Indiana | 114605 | US 422: Armstrong County Line to Indiana Bypass | 422 | 402 | Highway Reconstruction | CON | NHPP | 2030-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3342862 | 688858 | 0 | 4031720
SPC | 10 | Indiana | 114605 | US 422: Armstrong County Line to Indiana Bypass | 422 | 402 | Highway Reconstruction | CON | 581 | 2030-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 835716 | 172214 | 0 | 1007930
SPC | 10 | Indiana | 117138 | US 22 Concrete Preservation - Clyde Section | 22 | 408 | Highway Restoration | FD | 581 | 2027-03-11 |  | 0 | 161000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161000
SPC | 10 | Indiana | 117248 | US 119 over Crooked Creek | 119 | 45A | Bridge Replacement | PE | NHPP | 2028-10-05 |  | 1024953 | 329814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1354767
SPC | 10 | Indiana | 117248 | US 119 over Crooked Creek | 119 | 45A | Bridge Replacement | FD | NHPP | 2028-10-05 |  | 0 | 0 | 412000 | 0 | 0 | 0 | 0 | 0 | 0 | 412000
SPC | 10 | Indiana | 117248 | US 119 over Crooked Creek | 119 | 45A | Bridge Replacement | ROW | NHPP | 2028-10-05 |  | 0 | 0 | 257500 | 0 | 0 | 0 | 0 | 0 | 0 | 257500
SPC | 10 | Indiana | 117248 | US 119 over Crooked Creek | 119 | 45A | Bridge Replacement | UTL | NHPP | 2028-10-05 |  | 0 | 0 | 61800 | 0 | 0 | 0 | 0 | 0 | 0 | 61800
SPC | 10 | Indiana | 117248 | US 119 over Crooked Creek | 119 | 45A | Bridge Replacement | CON | BRIP | 2028-10-05 |  | 0 | 0 | 0 | 0 | 0 | 207880 | 107880 | 257880 | 1900574 | 2474214
SPC | 10 | Indiana | 117248 | US 119 over Crooked Creek | 119 | 45A | Bridge Replacement | CON | NHPP | 2028-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 913333 | 2499762 | 1726905 | 5140000
SPC | 10 | Indiana | 117248 | US 119 over Crooked Creek | 119 | 45A | Bridge Replacement | CON | STP | 2028-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1016366 | 2478791 | 1577092 | 5072249
SPC | 10 | Indiana | 117493 | Pleasant Valley Bridge | 2012 | 450 | Bridge Replacement | PE | BOF | 2025-01-09 | 2025-01-09 | 33714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33714
SPC | 10 | Indiana | 117493 | Pleasant Valley Bridge | 2012 | 450 | Bridge Replacement | CON | BOF | 2025-01-09 | 2025-01-09 | 2749389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2749389
SPC | 10 | Indiana | 117682 | Cypress Bridge | 1014 | 0 | Bridge Replacement | PE | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000
SPC | 10 | Indiana | 117682 | Cypress Bridge | 1014 | 0 | Bridge Replacement | FD | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000
SPC | 10 | Indiana | 117682 | Cypress Bridge | 1014 | 0 | Bridge Replacement | ROW | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000
SPC | 10 | Indiana | 117682 | Cypress Bridge | 1014 | 0 | Bridge Replacement | UTL | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 10 | Indiana | 117682 | Cypress Bridge | 1014 | 0 | Bridge Replacement | CON | BOF | 2032-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1982370 | 1982370
SPC | 10 | Indiana | 117685 | First Sergeant Alexander Kelly Memorial Bridge | 286 | 467 | Bridge Replacement | PE | BRIP | 2032-09-23 |  | 0 | 0 | 0 | 0 | 0 | 360000 | 0 | 0 | 0 | 360000
SPC | 10 | Indiana | 117685 | First Sergeant Alexander Kelly Memorial Bridge | 286 | 467 | Bridge Replacement | PE | 185 | 2032-09-23 |  | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 90000
SPC | 10 | Indiana | 117685 | First Sergeant Alexander Kelly Memorial Bridge | 286 | 467 | Bridge Replacement | FD | BRIP | 2032-09-23 |  | 0 | 0 | 0 | 0 | 0 | 310000 | 50000 | 0 | 0 | 360000
SPC | 10 | Indiana | 117685 | First Sergeant Alexander Kelly Memorial Bridge | 286 | 467 | Bridge Replacement | FD | 185 | 2032-09-23 |  | 0 | 0 | 0 | 0 | 0 | 77500 | 12500 | 0 | 0 | 90000
SPC | 10 | Indiana | 117685 | First Sergeant Alexander Kelly Memorial Bridge | 286 | 467 | Bridge Replacement | ROW | BRIP | 2032-09-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 40000
SPC | 10 | Indiana | 117685 | First Sergeant Alexander Kelly Memorial Bridge | 286 | 467 | Bridge Replacement | ROW | 185 | 2032-09-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000
SPC | 10 | Indiana | 117685 | First Sergeant Alexander Kelly Memorial Bridge | 286 | 467 | Bridge Replacement | UTL | BRIP | 2032-09-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 40000
SPC | 10 | Indiana | 117685 | First Sergeant Alexander Kelly Memorial Bridge | 286 | 467 | Bridge Replacement | UTL | 185 | 2032-09-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000
SPC | 10 | Indiana | 117685 | First Sergeant Alexander Kelly Memorial Bridge | 286 | 467 | Bridge Replacement | CON | BRIP | 2032-09-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11111867 | 11111867
SPC | 10 | Indiana | 117685 | First Sergeant Alexander Kelly Memorial Bridge | 286 | 467 | Bridge Replacement | CON | 185 | 2032-09-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3390020 | 3390020
SPC | 10 | Indiana | 119170 | 119 Business Park Access Road - Phase II |  | 491 | New Alignment | CON | APL |  |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 10 | Indiana | 119837 | SR 119 - Home North PM | 119 | 418 | Preventive Maintenance | CON | 581 | 2032-01-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1492433 | 2157807 | 3650240
SPC | 10 | Indiana | 119839 | US 119 Marchand South PM | 119 | 419 | Highway Restoration | CON | STP | 2032-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2442440 | 0 | 2442440
SPC | 10 | Indiana | 119877 | US 422 Penn Run Resurfacing | 422 | 493 | Preventive Maintenance | CON | NHPP | 2032-02-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1201095 | 1201095
SPC | 10 | Indiana | 119877 | US 422 Penn Run Resurfacing | 422 | 493 | Preventive Maintenance | CON | 581 | 2032-02-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300274 | 300274
SPC | 10 | Indiana | 119938 | US 22 - SR 403 Underpass Paving | 22 | 406 | Preventive Maintenance | CON | NHPP | 2025-03-27 | 2025-03-27 | 1275445 | 766000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2041445
SPC | 10 | Indiana | 119938 | US 22 - SR 403 Underpass Paving | 22 | 406 | Preventive Maintenance | CON | 581 | 2025-03-27 | 2025-03-27 | 318862 | 191500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510362
SPC | 10 | Indiana | 120376 | PA 403/US 22 Park and Ride | 403 | 101 | Congestion Reduction | FD | CRP | 2027-10-07 |  | 0 | 206000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206000
SPC | 10 | Indiana | 120376 | PA 403/US 22 Park and Ride | 403 | 101 | Congestion Reduction | FD | 581 | 2027-10-07 |  | 0 | 51500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51500
SPC | 10 | Indiana | 120376 | PA 403/US 22 Park and Ride | 403 | 101 | Congestion Reduction | ROW | CRP | 2027-10-07 |  | 0 | 63680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63680
SPC | 10 | Indiana | 120376 | PA 403/US 22 Park and Ride | 403 | 101 | Congestion Reduction | ROW | 581 | 2027-10-07 |  | 0 | 15920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15920
SPC | 10 | Indiana | 120376 | PA 403/US 22 Park and Ride | 403 | 101 | Congestion Reduction | UTL | CRP | 2027-10-07 |  | 0 | 63680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63680
SPC | 10 | Indiana | 120376 | PA 403/US 22 Park and Ride | 403 | 101 | Congestion Reduction | UTL | 581 | 2027-10-07 |  | 0 | 15920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15920
SPC | 10 | Indiana | 120376 | PA 403/US 22 Park and Ride | 403 | 101 | Congestion Reduction | CON | CRP | 2027-10-07 |  | 0 | 0 | 50320 | 483000 | 483000 | 483000 | 483000 | 32760 | 0 | 2015080
SPC | 10 | Indiana | 120376 | PA 403/US 22 Park and Ride | 403 | 101 | Congestion Reduction | CON | 581 | 2027-10-07 |  | 0 | 0 | 611940 | 0 | 0 | 0 | 0 | 0 | 0 | 611940
SPC | 10 | Indiana | 120541 | T-565 Long Road Bridge | 7208 | 0 | Bridge Restoration | PE | BOF | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 200000
SPC | 10 | Indiana | 120541 | T-565 Long Road Bridge | 7208 | 0 | Bridge Restoration | PE | 185 | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000
SPC | 10 | Indiana | 120541 | T-565 Long Road Bridge | 7208 | 0 | Bridge Restoration | FD | BRIP | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 160000
SPC | 10 | Indiana | 120541 | T-565 Long Road Bridge | 7208 | 0 | Bridge Restoration | FD | 185 | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 40000
SPC | 10 | Indiana | 120541 | T-565 Long Road Bridge | 7208 | 0 | Bridge Restoration | ROW | BRIP | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 12000
SPC | 10 | Indiana | 120541 | T-565 Long Road Bridge | 7208 | 0 | Bridge Restoration | ROW | 185 | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000
SPC | 10 | Indiana | 120541 | T-565 Long Road Bridge | 7208 | 0 | Bridge Restoration | UTL | BRIP | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 60000
SPC | 10 | Indiana | 120541 | T-565 Long Road Bridge | 7208 | 0 | Bridge Restoration | UTL | 185 | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000
SPC | 10 | Indiana | 120541 | T-565 Long Road Bridge | 7208 | 0 | Bridge Restoration | CON | BOF | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
SPC | 10 | Indiana | 120541 | T-565 Long Road Bridge | 7208 | 0 | Bridge Restoration | CON | 185 | 2034-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
SPC | 10 | Indiana | 121829 | Kintersburg Covered Bridge Rehabilitation |  |  | Bridge Restoration | CON | TAP | 2025-07-10 | 2025-07-10 | 928672 | 197000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1125672
SPC | 10 | Indiana | 122386 | Indiana Borough Sidewalk Repair MTF |  | 494 | MultiModal | CON | 411 |  |  | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000
SPC | 10 | Indiana | 122386 | Indiana Borough Sidewalk Repair MTF |  | 494 | MultiModal | CON | LOC |  |  | 144000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144000
SPC | 10 | Indiana | 122629 | Heshbon Truss Repair | 259 | EMG | Bridge Preservation - State Funded | CON | 185 | 2025-05-27 | 2025-01-09 | 0 | 68400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68400
SPC | 11 | Allegheny | 26623 | SR 2040/Buttermilk Hollow Rd - Ceco Dr | 2040 | A22 | Highway Reconstruction | CON | HSIP | 2021-07-22 | 2021-07-22 | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41000
SPC | 11 | Allegheny | 26623 | SR 2040/Buttermilk Hollow Rd - Ceco Dr | 2040 | A22 | Highway Reconstruction | CON | NHPP | 2021-07-22 | 2021-07-22 | 77000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77000
SPC | 11 | Allegheny | 27144 | 28th Street Bridge | 7301 | LOC | Bridge Restoration | FD | BOF | 2027-01-14 |  | 1120000 | 84000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1204000
SPC | 11 | Allegheny | 27144 | 28th Street Bridge | 7301 | LOC | Bridge Restoration | FD | 183 | 2027-01-14 |  | 210000 | 15750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225750
SPC | 11 | Allegheny | 27144 | 28th Street Bridge | 7301 | LOC | Bridge Restoration | FD | LOC | 2027-01-14 |  | 70000 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75250
SPC | 11 | Allegheny | 27144 | 28th Street Bridge | 7301 | LOC | Bridge Restoration | ROW | BOF | 2027-01-14 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 27144 | 28th Street Bridge | 7301 | LOC | Bridge Restoration | ROW | 183 | 2027-01-14 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Allegheny | 27144 | 28th Street Bridge | 7301 | LOC | Bridge Restoration | ROW | LOC | 2027-01-14 |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SPC | 11 | Allegheny | 27144 | 28th Street Bridge | 7301 | LOC | Bridge Restoration | CON | BRIP | 2027-01-14 |  | 0 | 0 | 2000000 | 2000000 | 4000000 | 0 | 0 | 0 | 0 | 8000000
SPC | 11 | Allegheny | 27144 | 28th Street Bridge | 7301 | LOC | Bridge Restoration | CON | 183 | 2027-01-14 |  | 0 | 0 | 375000 | 375000 | 750000 | 0 | 0 | 0 | 0 | 1500000
SPC | 11 | Allegheny | 27144 | 28th Street Bridge | 7301 | LOC | Bridge Restoration | CON | LOC | 2027-01-14 |  | 0 | 0 | 125000 | 125000 | 250000 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 27219 | Campbell's Run Road | 3041 | 0 | Highway Restoration | FD | STU | 2025-11-06 | 2025-11-06 | 116000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116000
SPC | 11 | Allegheny | 27219 | Campbell's Run Road | 3041 | 0 | Highway Restoration | FD | LOC | 2025-11-06 | 2025-11-06 | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
SPC | 11 | Allegheny | 27219 | Campbell's Run Road | 3041 | 0 | Highway Restoration | CON | STP | 2025-11-06 | 2025-11-06 | 0 | 288000 | 1440000 | 0 | 650000 | 0 | 0 | 0 | 0 | 2378000
SPC | 11 | Allegheny | 27219 | Campbell's Run Road | 3041 | 0 | Highway Restoration | CON | STU | 2025-11-06 | 2025-11-06 | 4000000 | 11336315 | 12136315 | 9383370 | 1200000 | 0 | 0 | 0 | 0 | 38056000
SPC | 11 | Allegheny | 27219 | Campbell's Run Road | 3041 | 0 | Highway Restoration | CON | LOC | 2025-11-06 | 2025-11-06 | 1000000 | 5046079 | 3394079 | 2345843 | 462500 | 0 | 0 | 0 | 0 | 12248501
SPC | 11 | Allegheny | 27225 | 2048 Wm Penn Hwy/I-376 Ramp to PA 48 | 2048 | A14 | Highway Restoration | CON | NHPP | 2023-01-12 | 2023-01-12 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000
SPC | 11 | Allegheny | 27316 | Plum Creek Bridge No. 2 (PU02) | 7113 | LOC | Bridge Restoration | FD | STU | 2026-10-01 |  | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640000
SPC | 11 | Allegheny | 27316 | Plum Creek Bridge No. 2 (PU02) | 7113 | LOC | Bridge Restoration | FD | 183 | 2026-10-01 |  | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
SPC | 11 | Allegheny | 27316 | Plum Creek Bridge No. 2 (PU02) | 7113 | LOC | Bridge Restoration | FD | LOC | 2026-10-01 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SPC | 11 | Allegheny | 27316 | Plum Creek Bridge No. 2 (PU02) | 7113 | LOC | Bridge Restoration | CON | BOF | 2026-10-01 |  | 0 | 1360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360000
SPC | 11 | Allegheny | 27316 | Plum Creek Bridge No. 2 (PU02) | 7113 | LOC | Bridge Restoration | CON | 183 | 2026-10-01 |  | 0 | 255000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000
SPC | 11 | Allegheny | 27316 | Plum Creek Bridge No. 2 (PU02) | 7113 | LOC | Bridge Restoration | CON | LOC | 2026-10-01 |  | 0 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000
SPC | 11 | Allegheny | 27322 | Days Run Bridge No. 3 (DY03) | 7104 | LOC | Bridge Replacement | PE | 183 | 2028-02-17 |  | 61285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61285
SPC | 11 | Allegheny | 27322 | Days Run Bridge No. 3 (DY03) | 7104 | LOC | Bridge Replacement | PE | LOC | 2028-02-17 |  | 15321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15321
SPC | 11 | Allegheny | 27322 | Days Run Bridge No. 3 (DY03) | 7104 | LOC | Bridge Replacement | FD | 183 | 2028-02-17 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 27322 | Days Run Bridge No. 3 (DY03) | 7104 | LOC | Bridge Replacement | FD | LOC | 2028-02-17 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 27322 | Days Run Bridge No. 3 (DY03) | 7104 | LOC | Bridge Replacement | ROW | 183 | 2028-02-17 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SPC | 11 | Allegheny | 27322 | Days Run Bridge No. 3 (DY03) | 7104 | LOC | Bridge Replacement | ROW | LOC | 2028-02-17 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SPC | 11 | Allegheny | 27322 | Days Run Bridge No. 3 (DY03) | 7104 | LOC | Bridge Replacement | CON | BOF | 2028-02-17 |  | 0 | 0 | 800000 | 800000 | 0 | 0 | 0 | 0 | 0 | 1600000
SPC | 11 | Allegheny | 27322 | Days Run Bridge No. 3 (DY03) | 7104 | LOC | Bridge Replacement | CON | 183 | 2028-02-17 |  | 0 | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 27322 | Days Run Bridge No. 3 (DY03) | 7104 | LOC | Bridge Replacement | CON | LOC | 2028-02-17 |  | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 27326 | Ravensburg Boulevard Bridges | 7302 | LOC | Bridge Preservation - Federal | PE | BRIP | 2028-10-19 |  | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 11 | Allegheny | 27445 | 22/30 over the Parkway West | 22 | A37 | Bridge Replacement | ROW | BRIP | 2026-02-12 | 2026-02-12 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 27445 | 22/30 over the Parkway West | 22 | A37 | Bridge Replacement | UTL | BRIP | 2026-02-12 | 2026-02-12 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SPC | 11 | Allegheny | 27445 | 22/30 over the Parkway West | 22 | A37 | Bridge Replacement | CON | BRIP | 2026-02-12 | 2026-02-12 | 5744000 | 7564872 | 7528810 | 14364400 | 2812000 | 0 | 0 | 0 | 0 | 38014082
SPC | 11 | Allegheny | 27445 | 22/30 over the Parkway West | 22 | A37 | Bridge Replacement | CON | STU | 2026-02-12 | 2026-02-12 | 0 | 0 | 0 | 0 | 8250000 | 0 | 0 | 0 | 0 | 8250000
SPC | 11 | Allegheny | 27445 | 22/30 over the Parkway West | 22 | A37 | Bridge Replacement | CON | 185 | 2026-02-12 | 2026-02-12 | 6299190 | 5275128 | 160000 | 2732750 | 3208850 | 0 | 0 | 0 | 0 | 17675918
SPC | 11 | Allegheny | 27445 | 22/30 over the Parkway West | 22 | A37 | Bridge Replacement | CON | PRIV | 2026-02-12 | 2026-02-12 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
SPC | 11 | Allegheny | 27481 | Little Deer Cr Br 4 (DL04) | 7209 | LOC | Bridge Preservation - Federal | PE | BOF | 2050-03-15 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 27481 | Little Deer Cr Br 4 (DL04) | 7209 | LOC | Bridge Preservation - Federal | CON | BOF | 2050-03-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
SPC | 11 | Allegheny | 27491 | Beck's Run Road |  |  | Highway Restoration | FD | NHPP | 2028-06-08 |  | 0 | 0 | 0 | 1096000 | 0 | 0 | 0 | 0 | 0 | 1096000
SPC | 11 | Allegheny | 27491 | Beck's Run Road |  |  | Highway Restoration | FD | LOC | 2028-06-08 |  | 0 | 0 | 0 | 274000 | 0 | 0 | 0 | 0 | 0 | 274000
SPC | 11 | Allegheny | 27491 | Beck's Run Road |  |  | Highway Restoration | ROW | NHPP | 2028-06-08 |  | 0 | 0 | 0 | 640000 | 0 | 0 | 0 | 0 | 0 | 640000
SPC | 11 | Allegheny | 27491 | Beck's Run Road |  |  | Highway Restoration | ROW | LOC | 2028-06-08 |  | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 160000
SPC | 11 | Allegheny | 27491 | Beck's Run Road |  |  | Highway Restoration | CON | NHPP | 2028-06-08 |  | 0 | 0 | 0 | 0 | 0 | 7200000 | 0 | 0 | 0 | 7200000
SPC | 11 | Allegheny | 27491 | Beck's Run Road |  |  | Highway Restoration | CON | LOC | 2028-06-08 |  | 0 | 0 | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 1800000
SPC | 11 | Allegheny | 27493 | Smithfield St Reconstruct, Ph 1 |  | LOC | Highway Restoration | FD | STU | 2026-03-12 | 2026-03-26 | 176000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176000
SPC | 11 | Allegheny | 27493 | Smithfield St Reconstruct, Ph 1 |  | LOC | Highway Restoration | FD | LOC | 2026-03-12 | 2026-03-26 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44000
SPC | 11 | Allegheny | 27493 | Smithfield St Reconstruct, Ph 1 |  | LOC | Highway Restoration | CON | STP | 2026-03-12 | 2026-03-26 | 2400000 | 3760000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6160000
SPC | 11 | Allegheny | 27493 | Smithfield St Reconstruct, Ph 1 |  | LOC | Highway Restoration | CON | LOC | 2026-03-12 | 2026-03-26 | 600000 | 940000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1540000
SPC | 11 | Allegheny | 27513 | Thompson Run Road Bridge - TN02 | 7116 | LOC | Bridge Replacement | CON | 183 | 2027-06-10 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 27513 | Thompson Run Road Bridge - TN02 | 7116 | LOC | Bridge Replacement | CON | LOC | 2027-06-10 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 27514 | Thompson Run Road Bridge - TN03 | 7116 | LOC | Bridge Replacement | CON | 183 | 2027-06-10 |  | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 27514 | Thompson Run Road Bridge - TN03 | 7116 | LOC | Bridge Replacement | CON | LOC | 2027-06-10 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 27543 | Kenmawr Bridge over NS RR | 7463 | BRG | Bridge Replacement | CON | NHPP | 2019-11-15 | 2019-11-15 | 163404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163404
SPC | 11 | Allegheny | 27561 | Painter's Run Bridge #8 | 7123 | LOC | Bridge Restoration | PE | BRIP | 2031-04-10 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 27561 | Painter's Run Bridge #8 | 7123 | LOC | Bridge Restoration | CON | BRIP | 2031-04-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 1500000
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | PE | NHPP | 2027-09-30 |  | 0 | 65069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65069
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | PE | 183 | 2027-09-30 |  | 0 | 12200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | PE | LOC | 2027-09-30 |  | 0 | 4067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4067
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | FD | NHPP | 2027-09-30 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | FD | 183 | 2027-09-30 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | FD | LOC | 2027-09-30 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | ROW | NHPP | 2027-09-30 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | ROW | 183 | 2027-09-30 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | ROW | LOC | 2027-09-30 |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | UTL | NHPP | 2027-09-30 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | UTL | 183 | 2027-09-30 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | UTL | LOC | 2027-09-30 |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | CON | BRIP | 2027-09-30 |  | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 1200000
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | CON | 183 | 2027-09-30 |  | 0 | 0 | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 225000
SPC | 11 | Allegheny | 27573 | Grant Avenue Bridge ov Girty's Run | 7445 | LOC | Bridge Replacement | CON | LOC | 2027-09-30 |  | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Allegheny | 27747 | Swinburne Bridge | 7301 | LOC | Bridge Restoration | FD | BOF | 2028-03-16 |  | 0 | 0 | 960000 | 0 | 0 | 0 | 0 | 0 | 0 | 960000
SPC | 11 | Allegheny | 27747 | Swinburne Bridge | 7301 | LOC | Bridge Restoration | FD | 183 | 2028-03-16 |  | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 180000
SPC | 11 | Allegheny | 27747 | Swinburne Bridge | 7301 | LOC | Bridge Restoration | FD | LOC | 2028-03-16 |  | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
SPC | 11 | Allegheny | 27747 | Swinburne Bridge | 7301 | LOC | Bridge Restoration | ROW | BOF | 2028-03-16 |  | 0 | 0 | 565000 | 0 | 0 | 0 | 0 | 0 | 0 | 565000
SPC | 11 | Allegheny | 27747 | Swinburne Bridge | 7301 | LOC | Bridge Restoration | ROW | 183 | 2028-03-16 |  | 0 | 0 | 147500 | 0 | 0 | 0 | 0 | 0 | 0 | 147500
SPC | 11 | Allegheny | 27747 | Swinburne Bridge | 7301 | LOC | Bridge Restoration | ROW | LOC | 2028-03-16 |  | 0 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 37500
SPC | 11 | Allegheny | 27747 | Swinburne Bridge | 7301 | LOC | Bridge Restoration | CON | BOF | 2028-03-16 |  | 0 | 0 | 3185000 | 4996000 | 0 | 0 | 0 | 0 | 5499000 | 13680000
SPC | 11 | Allegheny | 27747 | Swinburne Bridge | 7301 | LOC | Bridge Restoration | CON | 183 | 2028-03-16 |  | 0 | 0 | 597187 | 936750 | 0 | 1031064 | 0 | 0 | 0 | 2565001
SPC | 11 | Allegheny | 27747 | Swinburne Bridge | 7301 | LOC | Bridge Restoration | CON | LOC | 2028-03-16 |  | 0 | 0 | 199062 | 312250 | 0 | 343687 | 0 | 0 | 0 | 854999
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | PE | BOF | 2027-09-30 |  | 40000 | 93218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133218
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | PE | 183 | 2027-09-30 |  | 7500 | 17478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24978
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | PE | LOC | 2027-09-30 |  | 2500 | 5826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8326
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | FD | BOF | 2027-09-30 |  | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | FD | 183 | 2027-09-30 |  | 67500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | FD | LOC | 2027-09-30 |  | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | ROW | BOF | 2027-09-30 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | ROW | 183 | 2027-09-30 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | ROW | LOC | 2027-09-30 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | UTL | BOF | 2027-09-30 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | UTL | 183 | 2027-09-30 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | UTL | LOC | 2027-09-30 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | CON | BOF | 2027-09-30 |  | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 1200000
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | CON | 183 | 2027-09-30 |  | 0 | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 225000
SPC | 11 | Allegheny | 27751 | Lincoln Ave Bridge 13 | 7445 | LOC | Bridge Replacement | CON | LOC | 2027-09-30 |  | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Allegheny | 27806 | Corliss Tunnel |  |  | Safety Improvement | PE | STU | 2029-04-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515000 | 0 | 515000
SPC | 11 | Allegheny | 27806 | Corliss Tunnel |  |  | Safety Improvement | PE | LOC | 2029-04-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
SPC | 11 | Allegheny | 27806 | Corliss Tunnel |  |  | Safety Improvement | CON | STP | 2029-04-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 0 | 0 | 6000000
SPC | 11 | Allegheny | 27806 | Corliss Tunnel |  |  | Safety Improvement | CON | STU | 2029-04-12 |  | 0 | 0 | 0 | 0 | 0 | 6000000 | 0 | 0 | 0 | 6000000
SPC | 11 | Allegheny | 27806 | Corliss Tunnel |  |  | Safety Improvement | CON | 183 | 2029-04-12 |  | 0 | 0 | 0 | 0 | 0 | 1125000 | 1125000 | 0 | 0 | 2250000
SPC | 11 | Allegheny | 27806 | Corliss Tunnel |  |  | Safety Improvement | CON | LOC | 2029-04-12 |  | 0 | 0 | 0 | 0 | 0 | 375000 | 375000 | 0 | 0 | 750000
SPC | 11 | Allegheny | 27939 | Klopfer Street Bridge |  |  | Bridge Replacement | PE | BOF | 2029-04-12 |  | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Allegheny | 28010 | PA 50 -I79-Vanadium | 50 | A26 | Highway Restoration | PE | CAQ | 2022-10-20 | 2022-10-20 | 0 | 680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680000
SPC | 11 | Allegheny | 28010 | PA 50 -I79-Vanadium | 50 | A26 | Highway Restoration | CON | NHPP | 2022-10-20 | 2022-10-20 | 410000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000
SPC | 11 | Allegheny | 28025 | 2040/Ceco Dr to Brownsville Rd | 2040 | A23 | Highway Restoration | CON | 581 | 2024-01-11 | 2024-01-11 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
SPC | 11 | Allegheny | 28025 | 2040/Ceco Dr to Brownsville Rd | 2040 | A23 | Highway Restoration | CON | 581 | 2024-01-11 | 2024-01-11 | 167000 | 158000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325000
SPC | 11 | Allegheny | 28044 | Versailles Avenue Viaduct | 7304 | BR | Bridge Replacement | FD | SXF | 2027-04-08 |  | 0 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000
SPC | 11 | Allegheny | 28044 | Versailles Avenue Viaduct | 7304 | BR | Bridge Replacement | ROW | BRIP | 2027-04-08 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 28044 | Versailles Avenue Viaduct | 7304 | BR | Bridge Replacement | UTL | BRIP | 2027-04-08 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 28044 | Versailles Avenue Viaduct | 7304 | BR | Bridge Replacement | CON | BRIP | 2027-04-08 |  | 0 | 0 | 4000000 | 6400000 | 0 | 0 | 0 | 0 | 0 | 10400000
SPC | 11 | Allegheny | 28044 | Versailles Avenue Viaduct | 7304 | BR | Bridge Replacement | CON | 183 | 2027-04-08 |  | 0 | 0 | 750000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 1950000
SPC | 11 | Allegheny | 28044 | Versailles Avenue Viaduct | 7304 | BR | Bridge Replacement | CON | LOC | 2027-04-08 |  | 0 | 0 | 250000 | 400000 | 0 | 0 | 0 | 0 | 0 | 650000
SPC | 11 | Allegheny | 28250 | WB11 Wible Run #11 | 7118 | LOC | Bridge Replacement | FD | STP | 2027-11-04 |  | 0 | 668000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 668000
SPC | 11 | Allegheny | 28250 | WB11 Wible Run #11 | 7118 | LOC | Bridge Replacement | FD | 183 | 2027-11-04 |  | 0 | 125250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125250
SPC | 11 | Allegheny | 28250 | WB11 Wible Run #11 | 7118 | LOC | Bridge Replacement | FD | LOC | 2027-11-04 |  | 0 | 41750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41750
SPC | 11 | Allegheny | 28250 | WB11 Wible Run #11 | 7118 | LOC | Bridge Replacement | ROW | STP | 2027-11-04 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SPC | 11 | Allegheny | 28250 | WB11 Wible Run #11 | 7118 | LOC | Bridge Replacement | ROW | 183 | 2027-11-04 |  | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
SPC | 11 | Allegheny | 28250 | WB11 Wible Run #11 | 7118 | LOC | Bridge Replacement | ROW | LOC | 2027-11-04 |  | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
SPC | 11 | Allegheny | 28250 | WB11 Wible Run #11 | 7118 | LOC | Bridge Replacement | CON | STP | 2027-11-04 |  | 0 | 0 | 0 | 0 | 0 | 3600000 | 0 | 0 | 0 | 3600000
SPC | 11 | Allegheny | 28250 | WB11 Wible Run #11 | 7118 | LOC | Bridge Replacement | CON | 183 | 2027-11-04 |  | 0 | 0 | 0 | 0 | 0 | 675000 | 0 | 0 | 0 | 675000
SPC | 11 | Allegheny | 28250 | WB11 Wible Run #11 | 7118 | LOC | Bridge Replacement | CON | LOC | 2027-11-04 |  | 0 | 0 | 0 | 0 | 0 | 225000 | 0 | 0 | 0 | 225000
SPC | 11 | Allegheny | 28266 | Painters Run Bridge No 2 (PA02) | 7123 | LOC | Bridge Restoration | CON | BOF | 2027-11-04 |  | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
SPC | 11 | Allegheny | 28266 | Painters Run Bridge No 2 (PA02) | 7123 | LOC | Bridge Restoration | CON | 183 | 2027-11-04 |  | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
SPC | 11 | Allegheny | 28266 | Painters Run Bridge No 2 (PA02) | 7123 | LOC | Bridge Restoration | CON | LOC | 2027-11-04 |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Allegheny | 28273 | ML01 McLaughlin Run #1 | 7414 | LOC | Bridge Replacement | PE | STP | 2028-10-05 |  | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000
SPC | 11 | Allegheny | 28273 | ML01 McLaughlin Run #1 | 7414 | LOC | Bridge Replacement | PE | 183 | 2028-10-05 |  | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000
SPC | 11 | Allegheny | 28273 | ML01 McLaughlin Run #1 | 7414 | LOC | Bridge Replacement | PE | LOC | 2028-10-05 |  | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
SPC | 11 | Allegheny | 28273 | ML01 McLaughlin Run #1 | 7414 | LOC | Bridge Replacement | FD | STP | 2028-10-05 |  | 0 | 0 | 0 | 620000 | 0 | 0 | 0 | 0 | 0 | 620000
SPC | 11 | Allegheny | 28273 | ML01 McLaughlin Run #1 | 7414 | LOC | Bridge Replacement | FD | 183 | 2028-10-05 |  | 0 | 0 | 0 | 116250 | 0 | 0 | 0 | 0 | 0 | 116250
SPC | 11 | Allegheny | 28273 | ML01 McLaughlin Run #1 | 7414 | LOC | Bridge Replacement | FD | LOC | 2028-10-05 |  | 0 | 0 | 0 | 38750 | 0 | 0 | 0 | 0 | 0 | 38750
SPC | 11 | Allegheny | 28273 | ML01 McLaughlin Run #1 | 7414 | LOC | Bridge Replacement | ROW | STP | 2028-10-05 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
SPC | 11 | Allegheny | 28273 | ML01 McLaughlin Run #1 | 7414 | LOC | Bridge Replacement | ROW | 183 | 2028-10-05 |  | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 7500
SPC | 11 | Allegheny | 28273 | ML01 McLaughlin Run #1 | 7414 | LOC | Bridge Replacement | ROW | LOC | 2028-10-05 |  | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500
SPC | 11 | Allegheny | 28273 | ML01 McLaughlin Run #1 | 7414 | LOC | Bridge Replacement | CON | BRIP | 2028-10-05 |  | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 4000000
SPC | 11 | Allegheny | 28273 | ML01 McLaughlin Run #1 | 7414 | LOC | Bridge Replacement | CON | 183 | 2028-10-05 |  | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 750000
SPC | 11 | Allegheny | 28273 | ML01 McLaughlin Run #1 | 7414 | LOC | Bridge Replacement | CON | LOC | 2028-10-05 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 250000
SPC | 11 | Allegheny | 28279 | Mission Street West Bridge |  |  | Bridge Replacement | PE | BOF | 2032-04-15 |  | 0 | 0 | 0 | 0 | 0 | 1008000 | 0 | 0 | 0 | 1008000
SPC | 11 | Allegheny | 28279 | Mission Street West Bridge |  |  | Bridge Replacement | PE | 183 | 2032-04-15 |  | 0 | 0 | 0 | 0 | 0 | 189000 | 0 | 0 | 0 | 189000
SPC | 11 | Allegheny | 28279 | Mission Street West Bridge |  |  | Bridge Replacement | PE | LOC | 2032-04-15 |  | 0 | 0 | 0 | 0 | 0 | 63000 | 0 | 0 | 0 | 63000
SPC | 11 | Allegheny | 28279 | Mission Street West Bridge |  |  | Bridge Replacement | CON | BOF | 2032-04-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000000 | 0 | 9000000
SPC | 11 | Allegheny | 28309 | SR 65 Ramps & SR 279 Ft. Duq | 65 | A57 | Bridge Preservation - Federal | FD | BRIP | 2025-06-05 | 2025-06-05 | 0 | 46000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000
SPC | 11 | Allegheny | 28309 | SR 65 Ramps & SR 279 Ft. Duq | 65 | A57 | Bridge Preservation - Federal | CON | BRIP | 2025-06-05 | 2025-06-05 | 5000000 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5135000
SPC | 11 | Allegheny | 28323 | Trumbull Drive Bridge | 7435 | 0 | Bridge Replacement | FD | BOF | 2026-12-10 |  | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
SPC | 11 | Allegheny | 28323 | Trumbull Drive Bridge | 7435 | 0 | Bridge Replacement | ROW | BOF | 2026-12-10 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 28323 | Trumbull Drive Bridge | 7435 | 0 | Bridge Replacement | CON | BOF | 2026-12-10 |  | 0 | 0 | 4400000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 5600000
SPC | 11 | Allegheny | 28323 | Trumbull Drive Bridge | 7435 | 0 | Bridge Replacement | CON | 183 | 2026-12-10 |  | 0 | 0 | 991250 | 58750 | 0 | 0 | 0 | 0 | 0 | 1050000
SPC | 11 | Allegheny | 28323 | Trumbull Drive Bridge | 7435 | 0 | Bridge Replacement | CON | LOC | 2026-12-10 |  | 0 | 0 | 275000 | 75000 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Allegheny | 28344 | McKees Rocks Bridge Phase 2 | 3104 | A03 | Bridge Preservation - State Funded | CON | 185 | 2022-06-09 | 2022-06-09 | 2408000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2408000
SPC | 11 | Allegheny | 28345 | Jerome Street Bridge | 2094 | A04 | Bridge Restoration | CON | NHPP | 2020-04-30 | 2020-04-30 | 8600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8600
SPC | 11 | Allegheny | 28372 | Unity Trestle Road |  |  | Highway Restoration | PE | STP | 2035-06-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 520000 | 0 | 0 | 520000
SPC | 11 | Allegheny | 28372 | Unity Trestle Road |  |  | Highway Restoration | PE | LOC | 2035-06-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | 0 | 0 | 130000
SPC | 11 | Allegheny | 28372 | Unity Trestle Road |  |  | Highway Restoration | CON | STP | 2035-06-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000 | 2400000
SPC | 11 | Allegheny | 28372 | Unity Trestle Road |  |  | Highway Restoration | CON | LOC | 2035-06-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000
SPC | 11 | Allegheny | 28426 | AL Local BPRS Group 5 | 7420 | BRG | Bridge Preservation - Federal | FD | STP | 2026-08-13 |  | 152000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152000
SPC | 11 | Allegheny | 28426 | AL Local BPRS Group 5 | 7420 | BRG | Bridge Preservation - Federal | FD | 183 | 2026-08-13 |  | 28500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28500
SPC | 11 | Allegheny | 28426 | AL Local BPRS Group 5 | 7420 | BRG | Bridge Preservation - Federal | FD | LOC | 2026-08-13 |  | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500
SPC | 11 | Allegheny | 28426 | AL Local BPRS Group 5 | 7420 | BRG | Bridge Preservation - Federal | CON | STP | 2026-08-13 |  | 0 | 2500000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 7500000
SPC | 11 | Allegheny | 28426 | AL Local BPRS Group 5 | 7420 | BRG | Bridge Preservation - Federal | CON | 183 | 2026-08-13 |  | 468750 | 468750 | 937500 | 0 | 0 | 0 | 0 | 0 | 0 | 1875000
SPC | 11 | Allegheny | 28426 | AL Local BPRS Group 5 | 7420 | BRG | Bridge Preservation - Federal | CON | LOC | 2026-08-13 |  | 156250 | 156250 | 312500 | 0 | 0 | 0 | 0 | 0 | 0 | 625000
SPC | 11 | Allegheny | 29421 | MTF Main/19 Intersection Upgrades & Road Construct | 1001 | 0 | MultiModal | CON | 411 | 2026-03-12 |  | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 11 | Allegheny | 56960 | Rankin Bridge | 7456 | 0 | Bridge Preservation - Federal | PE | BRIP | 2031-05-08 |  | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 800000
SPC | 11 | Allegheny | 56960 | Rankin Bridge | 7456 | 0 | Bridge Preservation - Federal | PE | 183 | 2031-05-08 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 11 | Allegheny | 56960 | Rankin Bridge | 7456 | 0 | Bridge Preservation - Federal | PE | LOC | 2031-05-08 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 56960 | Rankin Bridge | 7456 | 0 | Bridge Preservation - Federal | CON | STU | 2031-05-08 |  | 0 | 0 | 0 | 0 | 0 | 9000000 | 12600000 | 0 | 0 | 21600000
SPC | 11 | Allegheny | 56960 | Rankin Bridge | 7456 | 0 | Bridge Preservation - Federal | CON | 183 | 2031-05-08 |  | 0 | 0 | 0 | 0 | 0 | 1687500 | 2362500 | 0 | 0 | 4050000
SPC | 11 | Allegheny | 56960 | Rankin Bridge | 7456 | 0 | Bridge Preservation - Federal | CON | LOC | 2031-05-08 |  | 0 | 0 | 0 | 0 | 0 | 562500 | 787500 | 0 | 0 | 1350000
SPC | 11 | Allegheny | 57066 | Crawford Run Bridge (CE02) | 7104 | LOC | Bridge Replacement | PE | STP | 2029-03-29 |  | 148000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148000
SPC | 11 | Allegheny | 57066 | Crawford Run Bridge (CE02) | 7104 | LOC | Bridge Replacement | PE | 183 | 2029-03-29 |  | 27750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27750
SPC | 11 | Allegheny | 57066 | Crawford Run Bridge (CE02) | 7104 | LOC | Bridge Replacement | PE | LOC | 2029-03-29 |  | 9250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9250
SPC | 11 | Allegheny | 57066 | Crawford Run Bridge (CE02) | 7104 | LOC | Bridge Replacement | FD | STP | 2029-03-29 |  | 0 | 0 | 310000 | 0 | 310000 | 0 | 0 | 0 | 0 | 620000
SPC | 11 | Allegheny | 57066 | Crawford Run Bridge (CE02) | 7104 | LOC | Bridge Replacement | FD | 183 | 2029-03-29 |  | 0 | 0 | 58125 | 0 | 58125 | 0 | 0 | 0 | 0 | 116250
SPC | 11 | Allegheny | 57066 | Crawford Run Bridge (CE02) | 7104 | LOC | Bridge Replacement | FD | LOC | 2029-03-29 |  | 0 | 0 | 19375 | 0 | 19375 | 0 | 0 | 0 | 0 | 38750
SPC | 11 | Allegheny | 57066 | Crawford Run Bridge (CE02) | 7104 | LOC | Bridge Replacement | ROW | STP | 2029-03-29 |  | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 40000
SPC | 11 | Allegheny | 57066 | Crawford Run Bridge (CE02) | 7104 | LOC | Bridge Replacement | ROW | 183 | 2029-03-29 |  | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 7500
SPC | 11 | Allegheny | 57066 | Crawford Run Bridge (CE02) | 7104 | LOC | Bridge Replacement | ROW | LOC | 2029-03-29 |  | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500
SPC | 11 | Allegheny | 57066 | Crawford Run Bridge (CE02) | 7104 | LOC | Bridge Replacement | CON | STP | 2029-03-29 |  | 0 | 0 | 0 | 0 | 3200000 | 0 | 0 | 0 | 0 | 3200000
SPC | 11 | Allegheny | 57066 | Crawford Run Bridge (CE02) | 7104 | LOC | Bridge Replacement | CON | 183 | 2029-03-29 |  | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 57066 | Crawford Run Bridge (CE02) | 7104 | LOC | Bridge Replacement | CON | LOC | 2029-03-29 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 57074 | Bull Creek Br No 7 (BF07) | 7202 | LOC | Bridge Replacement | PE | 183 | 2023-01-26 | 2023-01-26 | 85120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85120
SPC | 11 | Allegheny | 57074 | Bull Creek Br No 7 (BF07) | 7202 | LOC | Bridge Replacement | PE | LOC | 2023-01-26 | 2023-01-26 | 21280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21280
SPC | 11 | Allegheny | 57074 | Bull Creek Br No 7 (BF07) | 7202 | LOC | Bridge Replacement | FD | 183 | 2023-01-26 | 2023-01-26 | 255016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255016
SPC | 11 | Allegheny | 57074 | Bull Creek Br No 7 (BF07) | 7202 | LOC | Bridge Replacement | FD | LOC | 2023-01-26 | 2023-01-26 | 63754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63754
SPC | 11 | Allegheny | 57074 | Bull Creek Br No 7 (BF07) | 7202 | LOC | Bridge Replacement | ROW | 183 | 2023-01-26 | 2023-01-26 | 1288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288
SPC | 11 | Allegheny | 57074 | Bull Creek Br No 7 (BF07) | 7202 | LOC | Bridge Replacement | ROW | LOC | 2023-01-26 | 2023-01-26 | 322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322
SPC | 11 | Allegheny | 57074 | Bull Creek Br No 7 (BF07) | 7202 | LOC | Bridge Replacement | CON | 183 | 2023-01-26 | 2023-01-26 | 1480064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1480064
SPC | 11 | Allegheny | 57074 | Bull Creek Br No 7 (BF07) | 7202 | LOC | Bridge Replacement | CON | LOC | 2023-01-26 | 2023-01-26 | 370016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370016
SPC | 11 | Allegheny | 62721 | SR 51, Chartiers Avenue ov Chartiers Creek | 51 | 000 | Bridge Preservation - Federal | PE | 185 | 2034-04-06 |  | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 350000
SPC | 11 | Allegheny | 62721 | SR 51, Chartiers Avenue ov Chartiers Creek | 51 | 000 | Bridge Preservation - Federal | CON | 185 | 2034-04-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 2500000
SPC | 11 | Allegheny | 63306 | Tarentum Bridge Ramps A, B, C & D ov Allegheny Riv | 366 | A07 | Bridge Preservation - Federal | CON | BRIP | 2027-03-11 |  | 0 | 0 | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000
SPC | 11 | Allegheny | 63306 | Tarentum Bridge Ramps A, B, C & D ov Allegheny Riv | 366 | A07 | Bridge Preservation - Federal | CON | NHPP | 2027-03-11 |  | 0 | 0 | 0 | 0 | 8000000 | 0 | 0 | 0 | 0 | 8000000
SPC | 11 | Allegheny | 63306 | Tarentum Bridge Ramps A, B, C & D ov Allegheny Riv | 366 | A07 | Bridge Preservation - Federal | CON | 185 | 2027-03-11 |  | 0 | 0 | 0 | 3000000 | 1977000 | 0 | 0 | 0 | 0 | 4977000
SPC | 11 | Allegheny | 63306 | Tarentum Bridge Ramps A, B, C & D ov Allegheny Riv | 366 | A07 | Bridge Preservation - Federal | CON | 581 | 2027-03-11 |  | 0 | 0 | 0 | 2000000 | 123000 | 0 | 0 | 0 | 0 | 2123000
SPC | 11 | Allegheny | 63330 | Bateman Road Bridge | 978 | A16 | Bridge Replacement | FD | 185 | 2027-06-15 |  | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SPC | 11 | Allegheny | 63330 | Bateman Road Bridge | 978 | A16 | Bridge Replacement | ROW | 185 | 2027-06-15 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Allegheny | 63330 | Bateman Road Bridge | 978 | A16 | Bridge Replacement | UTL | 185 | 2027-06-15 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 63330 | Bateman Road Bridge | 978 | A16 | Bridge Replacement | CON | 185 | 2027-06-15 |  | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 2000000
SPC | 11 | Allegheny | 63558 | McLaughlin Run Rd #2 | 3004 | A16 | Bridge Replacement | CON | 185 | 2027-03-25 |  | 0 | 0 | 600000 | 600000 | 700000 | 0 | 0 | 0 | 0 | 1900000
SPC | 11 | Allegheny | 63583 | McKeesport Duquesne Bridge | 2114 | A05 | Bridge Preservation - Federal | FD | BRIP | 2025-10-09 | 2025-10-09 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
SPC | 11 | Allegheny | 63583 | McKeesport Duquesne Bridge | 2114 | A05 | Bridge Preservation - Federal | FD | 185 | 2025-10-09 | 2025-10-09 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Allegheny | 63583 | McKeesport Duquesne Bridge | 2114 | A05 | Bridge Preservation - Federal | CON | BRIP | 2025-10-09 | 2025-10-09 | 5600000 | 0 | 0 | 4800000 | 0 | 0 | 0 | 0 | 0 | 10400000
SPC | 11 | Allegheny | 63583 | McKeesport Duquesne Bridge | 2114 | A05 | Bridge Preservation - Federal | CON | NHPP | 2025-10-09 | 2025-10-09 | 15711000 | 14406000 | 5000000 | 0 | 5339000 | 0 | 0 | 0 | 0 | 40456000
SPC | 11 | Allegheny | 63583 | McKeesport Duquesne Bridge | 2114 | A05 | Bridge Preservation - Federal | CON | STP | 2025-10-09 | 2025-10-09 | 2000000 | 0 | 0 | 0 | 6000000 | 0 | 0 | 0 | 0 | 8000000
SPC | 11 | Allegheny | 63583 | McKeesport Duquesne Bridge | 2114 | A05 | Bridge Preservation - Federal | CON | SXF | 2025-10-09 | 2025-10-09 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000
SPC | 11 | Allegheny | 68252 | Pittsburgh City BPRSF Line Item |  | LOC | Reserve Line Item | CON | BOF |  |  | 0 | 1034000 | 0 | 209000 | 0 | 0 | 0 | 0 | 0 | 1243000
SPC | 11 | Allegheny | 68252 | Pittsburgh City BPRSF Line Item |  | LOC | Reserve Line Item | CON | BRIP |  |  | 0 | 369697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369697
SPC | 11 | Allegheny | 68252 | Pittsburgh City BPRSF Line Item |  | LOC | Reserve Line Item | CON | 183 |  |  | 371250 | 2272188 | 330625 | 174937 | 0 | 0 | 0 | 0 | 0 | 3149000
SPC | 11 | Allegheny | 68252 | Pittsburgh City BPRSF Line Item |  | LOC | Reserve Line Item | CON | LOC |  |  | 606125 | 444563 | 121875 | 58312 | 0 | 0 | 0 | 0 | 0 | 1230875
SPC | 11 | Allegheny | 69055 | 62nd Street Bridge NB Approach | 8 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 69055 | 62nd Street Bridge NB Approach | 8 | 0 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 2000000
SPC | 11 | Allegheny | 69055 | 62nd Street Bridge NB Approach | 8 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000
SPC | 11 | Allegheny | 69839 | Alleg. Co Local Br. (S/L) |  |  | Reserve Line Item | CON | 183 |  |  | 0 | 2520300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520300
SPC | 11 | Allegheny | 69839 | Alleg. Co Local Br. (S/L) |  |  | Reserve Line Item | CON | LOC |  |  | 89704 | 645700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735404
SPC | 11 | Allegheny | 74255 | PA 28 over Yutes Run | 28 | A63 | Bridge Preservation - Federal | FD | 185 | 2027-04-15 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Allegheny | 74255 | PA 28 over Yutes Run | 28 | A63 | Bridge Preservation - Federal | ROW | 185 | 2027-04-15 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 74255 | PA 28 over Yutes Run | 28 | A63 | Bridge Preservation - Federal | UTL | 185 | 2027-04-15 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 74255 | PA 28 over Yutes Run | 28 | A63 | Bridge Preservation - Federal | CON | 185 | 2027-04-15 |  | 0 | 0 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 1350000
SPC | 11 | Allegheny | 74319 | Lovedale Rd Br/Wylie Rn | 2010 | A07 | Safety Improvement | CON | PRTCT | 2027-01-14 |  | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 4000000
SPC | 11 | Allegheny | 74320 | Streets Run Road Culvert | 2046 | 000 | Bridge Replacement | PE | 185 | 2033-02-10 |  | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 74320 | Streets Run Road Culvert | 2046 | 000 | Bridge Replacement | CON | BRIP | 2033-02-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3784000 | 3784000
SPC | 11 | Allegheny | 74320 | Streets Run Road Culvert | 2046 | 000 | Bridge Replacement | CON | 185 | 2033-02-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1716000 | 1716000
SPC | 11 | Allegheny | 75341 | Betterment Reserve Allegheny |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 4031865 | 7136000 | 8079000 | 5000000 | 2000000 | 436722 | 250000 | 0 | 26933587
SPC | 11 | Allegheny | 75341 | Betterment Reserve Allegheny |  |  | Reserve Line Item | CON | STP |  |  | 0 | 1782657 | 170000 | 660000 | 0 | 26000 | 1626000 | 2926000 | 2227780 | 9418437
SPC | 11 | Allegheny | 75341 | Betterment Reserve Allegheny |  |  | Reserve Line Item | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 345695 | 1072695 | 0 | 1418390
SPC | 11 | Allegheny | 75341 | Betterment Reserve Allegheny |  |  | Reserve Line Item | CON | 581 |  |  | 389484 | 5357726 | 2694730 | 547945 | 280650 | 0 | 0 | 3589000 | 1906000 | 14765535
SPC | 11 | Allegheny | 75669 | Slide Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 800000
SPC | 11 | Allegheny | 75669 | Slide Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 76430 | SPC Reg. Safety Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 2312000 | 4195360 | 13291000 | 13291000 | 13291000 | 13291000 | 13291000 | 13291000 | 53163000 | 139416360
SPC | 11 | Allegheny | 76458 | Bridge - Allegheny County |  |  | Reserve Line Item | FD | 185 |  |  | 0 | 0 | 441250 | 0 | 0 | 0 | 0 | 0 | 0 | 441250
SPC | 11 | Allegheny | 76458 | Bridge - Allegheny County |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 1550000 | 0 | 0 | 0 | 3798000 | 5348000
SPC | 11 | Allegheny | 76458 | Bridge - Allegheny County |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 2035528 | 4744790 | 2219600 | 0 | 0 | 0 | 680000 | 1866000 | 11545918
SPC | 11 | Allegheny | 76458 | Bridge - Allegheny County |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
SPC | 11 | Allegheny | 76458 | Bridge - Allegheny County |  |  | Reserve Line Item | CON | 185 |  |  | 260084 | 2060984 | 477713 | 0 | 438024 | 7399750 | 1722000 | 1045000 | 733000 | 14136555
SPC | 11 | Allegheny | 77273 | PRT Bus Procurement |  | PT | Reserve Line Item | CON | CAQ |  |  | 6172000 | 6172000 | 6172000 | 6172000 | 6172000 | 6172000 | 6172000 | 6172000 | 24688000 | 74064000
SPC | 11 | Allegheny | 78152 | Ewing Road over Meek Run | 3070 | A09 | Bridge Replacement | CON | STP | 2024-12-12 | 2024-12-12 | 1029000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1029000
SPC | 11 | Allegheny | 78162 | Noblestown Road Bridge ov Branch Robinson Run | 3048 | A27 | Bridge Replacement | PE | 185 | 2027-01-28 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 78162 | Noblestown Road Bridge ov Branch Robinson Run | 3048 | A27 | Bridge Replacement | FD | 185 | 2027-01-28 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 78162 | Noblestown Road Bridge ov Branch Robinson Run | 3048 | A27 | Bridge Replacement | ROW | 185 | 2027-01-28 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 78162 | Noblestown Road Bridge ov Branch Robinson Run | 3048 | A27 | Bridge Replacement | UTL | 185 | 2027-01-28 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 78162 | Noblestown Road Bridge ov Branch Robinson Run | 3048 | A27 | Bridge Replacement | CON | 185 | 2027-01-28 |  | 0 | 0 | 0 | 378500 | 1121500 | 0 | 0 | 0 | 0 | 1500000
SPC | 11 | Allegheny | 78231 | Indiana Drive Culvert | 2070 | A03 | Bridge Replacement | FD | 185 | 2027-03-11 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Allegheny | 78231 | Indiana Drive Culvert | 2070 | A03 | Bridge Replacement | ROW | 185 | 2027-03-11 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 78231 | Indiana Drive Culvert | 2070 | A03 | Bridge Replacement | UTL | 185 | 2027-03-11 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 78231 | Indiana Drive Culvert | 2070 | A03 | Bridge Replacement | CON | 185 | 2027-03-11 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 11 | Allegheny | 78232 | Electric Ave ov Falls Run | 2112 | A07 | Bridge Replacement | FD | 185 | 2031-04-17 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
SPC | 11 | Allegheny | 78232 | Electric Ave ov Falls Run | 2112 | A07 | Bridge Replacement | ROW | 185 | 2031-04-17 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 78232 | Electric Ave ov Falls Run | 2112 | A07 | Bridge Replacement | UTL | 185 | 2031-04-17 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 78232 | Electric Ave ov Falls Run | 2112 | A07 | Bridge Replacement | CON | STP | 2031-04-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15500000 | 15500000
SPC | 11 | Allegheny | 78232 | Electric Ave ov Falls Run | 2112 | A07 | Bridge Replacement | CON | 185 | 2031-04-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15500000 | 15500000
SPC | 11 | Allegheny | 78234 | Millers Run Road ov Branch of Millers Run | 3001 | A02 | Bridge Replacement | FD | 185 | 2027-01-14 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 78234 | Millers Run Road ov Branch of Millers Run | 3001 | A02 | Bridge Replacement | ROW | 185 | 2027-01-14 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 78234 | Millers Run Road ov Branch of Millers Run | 3001 | A02 | Bridge Replacement | UTL | 185 | 2027-01-14 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 78441 | Eighth Ave ov Homestead Run | 837 | A46 | Bridge Preservation - Federal | CON | 185 | 2025-07-24 | 2025-07-24 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 11 | Allegheny | 79252 | Bull Creek Br No 8 (BF08) | 7202 | LOC | Bridge Replacement | PE | 183 | 2023-01-26 | 2023-01-26 | 79904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79904
SPC | 11 | Allegheny | 79252 | Bull Creek Br No 8 (BF08) | 7202 | LOC | Bridge Replacement | PE | LOC | 2023-01-26 | 2023-01-26 | 19976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19976
SPC | 11 | Allegheny | 79252 | Bull Creek Br No 8 (BF08) | 7202 | LOC | Bridge Replacement | FD | 183 | 2023-01-26 | 2023-01-26 | 249644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249644
SPC | 11 | Allegheny | 79252 | Bull Creek Br No 8 (BF08) | 7202 | LOC | Bridge Replacement | FD | LOC | 2023-01-26 | 2023-01-26 | 62411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62411
SPC | 11 | Allegheny | 79252 | Bull Creek Br No 8 (BF08) | 7202 | LOC | Bridge Replacement | ROW | 183 | 2023-01-26 | 2023-01-26 | 1772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1772
SPC | 11 | Allegheny | 79252 | Bull Creek Br No 8 (BF08) | 7202 | LOC | Bridge Replacement | ROW | LOC | 2023-01-26 | 2023-01-26 | 443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443
SPC | 11 | Allegheny | 79252 | Bull Creek Br No 8 (BF08) | 7202 | LOC | Bridge Replacement | CON | 183 | 2023-01-26 | 2023-01-26 | 1398392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1398392
SPC | 11 | Allegheny | 79252 | Bull Creek Br No 8 (BF08) | 7202 | LOC | Bridge Replacement | CON | LOC | 2023-01-26 | 2023-01-26 | 349598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349598
SPC | 11 | Allegheny | 79448 | PA 65, Ohio River Boulevard | 65 | A61 | Highway Restoration | PE | 581 | 2028-03-09 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 79448 | PA 65, Ohio River Boulevard | 65 | A61 | Highway Restoration | CON | 581 | 2028-03-09 |  | 0 | 0 | 0 | 0 | 2600000 | 0 | 0 | 0 | 0 | 2600000
SPC | 11 | Allegheny | 79894 | MC07 McClarens Run #7 | 7203 | LOC | Bridge Replacement | CON | 183 | 2025-04-10 | 2025-04-10 | 1080000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080000
SPC | 11 | Allegheny | 79894 | MC07 McClarens Run #7 | 7203 | LOC | Bridge Replacement | CON | LOC | 2025-04-10 | 2025-04-10 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000
SPC | 11 | Allegheny | 81700 | SR 19, Gilkeson-Scott Road | 19 | A86 | Highway Restoration | FD | NHPP | 2030-03-15 |  | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 81700 | SR 19, Gilkeson-Scott Road | 19 | A86 | Highway Restoration | UTL | NHPP | 2030-03-15 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Allegheny | 81700 | SR 19, Gilkeson-Scott Road | 19 | A86 | Highway Restoration | CON | NHPP | 2030-03-15 |  | 0 | 0 | 0 | 0 | 560000 | 739000 | 711000 | 3750000 | 0 | 5760000
SPC | 11 | Allegheny | 81700 | SR 19, Gilkeson-Scott Road | 19 | A86 | Highway Restoration | CON | 581 | 2030-03-15 |  | 0 | 0 | 0 | 0 | 1440000 | 0 | 0 | 0 | 0 | 1440000
SPC | 11 | Allegheny | 81708 | FU07 Flaugherty Run Bridge #7 | 7103 | LOC | Bridge Restoration | FD | BOF | 2029-08-09 |  | 0 | 0 | 615000 | 0 | 0 | 0 | 0 | 0 | 0 | 615000
SPC | 11 | Allegheny | 81708 | FU07 Flaugherty Run Bridge #7 | 7103 | LOC | Bridge Restoration | ROW | BOF | 2029-08-09 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 81708 | FU07 Flaugherty Run Bridge #7 | 7103 | LOC | Bridge Restoration | CON | BOF | 2029-08-09 |  | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 1500000
SPC | 11 | Allegheny | 81711 | Pine Creek Bridge #9 (PN09) | 7216 | LOC | Bridge Replacement | FD | BOF | 2029-08-09 |  | 0 | 0 | 615000 | 0 | 0 | 0 | 0 | 0 | 0 | 615000
SPC | 11 | Allegheny | 81711 | Pine Creek Bridge #9 (PN09) | 7216 | LOC | Bridge Replacement | UTL | BOF | 2029-08-09 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 81711 | Pine Creek Bridge #9 (PN09) | 7216 | LOC | Bridge Replacement | CON | BOF | 2029-08-09 |  | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 0 | 0 | 2500000
SPC | 11 | Allegheny | 81714 | Spruce Run Bridge #4 (XP04) | 7405 | LOC | Bridge Replacement | FD | 183 | 2028-12-14 |  | 0 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440000
SPC | 11 | Allegheny | 81714 | Spruce Run Bridge #4 (XP04) | 7405 | LOC | Bridge Replacement | FD | LOC | 2028-12-14 |  | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
SPC | 11 | Allegheny | 81714 | Spruce Run Bridge #4 (XP04) | 7405 | LOC | Bridge Replacement | ROW | 183 | 2028-12-14 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SPC | 11 | Allegheny | 81714 | Spruce Run Bridge #4 (XP04) | 7405 | LOC | Bridge Replacement | ROW | LOC | 2028-12-14 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SPC | 11 | Allegheny | 81714 | Spruce Run Bridge #4 (XP04) | 7405 | LOC | Bridge Replacement | CON | 183 | 2028-12-14 |  | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SPC | 11 | Allegheny | 81714 | Spruce Run Bridge #4 (XP04) | 7405 | LOC | Bridge Replacement | CON | LOC | 2028-12-14 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 81780 | SR 3009/Baptist Rd, Hamilton Rd to Brownsville Rd | 3009 | A24 | Highway Reconstruction | PE | STP | 2026-03-12 | 2026-03-12 | 200000 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244000
SPC | 11 | Allegheny | 81780 | SR 3009/Baptist Rd, Hamilton Rd to Brownsville Rd | 3009 | A24 | Highway Reconstruction | CON | STP | 2026-03-12 | 2026-03-12 | 0 | 1740000 | 800000 | 3500000 | 0 | 0 | 0 | 0 | 0 | 6040000
SPC | 11 | Allegheny | 81780 | SR 3009/Baptist Rd, Hamilton Rd to Brownsville Rd | 3009 | A24 | Highway Reconstruction | CON | STU | 2026-03-12 | 2026-03-12 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 81780 | SR 3009/Baptist Rd, Hamilton Rd to Brownsville Rd | 3009 | A24 | Highway Reconstruction | CON | 581 | 2026-03-12 | 2026-03-12 | 0 | 1436000 | 224000 | 0 | 0 | 0 | 0 | 0 | 0 | 1660000
SPC | 11 | Allegheny | 82241 | SR. 4032, Fern Hollow Slide | 4032 | 000 | Disaster Permanent Repair | ROW | 581 |  | 2022-10-20 | 25000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Allegheny | 82557 | SR 30 Slide Remediation, East Pittsburgh | 30 | A36 | Highway Restoration | UTL | 581 | 2018-04-20 | 2018-04-20 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 11 | Allegheny | 82754 | SPC Region TAU Line Item |  |  | Reserve Line Item | CON | TAU |  |  | 962555 | 1982940 | 2326000 | 3826000 | 3826000 | 3826000 | 3826000 | 3826000 | 15302000 | 39703495
SPC | 11 | Allegheny | 83136 | Penn Ave Reconstruction, Ph 2 |  | LOC | Highway Reconstruction | CON | STU | 2025-10-09 | 2025-10-09 | 3472000 | 4395006 | 1200000 | 16000 | 0 | 0 | 0 | 0 | 0 | 9083006
SPC | 11 | Allegheny | 83136 | Penn Ave Reconstruction, Ph 2 |  | LOC | Highway Reconstruction | CON | LOC | 2025-10-09 | 2025-10-09 | 901750 | 1132501 | 337706 | 0 | 0 | 0 | 0 | 0 | 0 | 2371957
SPC | 11 | Allegheny | 83137 | South Negley Ave. Bridge | 7301 | LOC | Bridge Restoration | CON | STU | 2028-05-11 |  | 0 | 0 | 0 | 2784000 | 2816000 | 0 | 0 | 0 | 0 | 5600000
SPC | 11 | Allegheny | 83137 | South Negley Ave. Bridge | 7301 | LOC | Bridge Restoration | CON | 183 | 2028-05-11 |  | 0 | 0 | 525000 | 525000 | 0 | 0 | 0 | 0 | 0 | 1050000
SPC | 11 | Allegheny | 83137 | South Negley Ave. Bridge | 7301 | LOC | Bridge Restoration | CON | LOC | 2028-05-11 |  | 0 | 0 | 0 | 175000 | 175000 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Allegheny | 84078 | SPC CMAQ Line Item |  |  | Reserve Line Item | CON | CAQ |  |  | 0 | 7267141 | 68249 | 194457 | 1309267 | 23860000 | 23860000 | 23860000 | 95438000 | 175857114
SPC | 11 | Allegheny | 86446 | Geotechnical Review |  |  | Safety Improvement | PE | 581 |  |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 87777 | Allegheny Co Loc Br Pres. |  |  | Reserve Line Item | CON | 183 |  |  | 32500 | 734347 | 112500 | 0 | 0 | 0 | 0 | 0 | 0 | 879347
SPC | 11 | Allegheny | 87777 | Allegheny Co Loc Br Pres. |  |  | Reserve Line Item | CON | LOC |  |  | 7500 | 508782 | 112500 | 80000 | 0 | 0 | 0 | 0 | 0 | 708782
SPC | 11 | Allegheny | 88398 | CM03 - Campbells Run No. 3 | 7415 | LOC | Bridge Restoration | PE | BOF | 2028-03-02 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SPC | 11 | Allegheny | 88398 | CM03 - Campbells Run No. 3 | 7415 | LOC | Bridge Restoration | FD | BOF | 2028-03-02 |  | 775000 | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 816000
SPC | 11 | Allegheny | 88398 | CM03 - Campbells Run No. 3 | 7415 | LOC | Bridge Restoration | ROW | BOF | 2028-03-02 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 88398 | CM03 - Campbells Run No. 3 | 7415 | LOC | Bridge Restoration | CON | BOF | 2028-03-02 |  | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 0 | 0 | 1800000
SPC | 11 | Allegheny | 88398 | CM03 - Campbells Run No. 3 | 7415 | LOC | Bridge Restoration | CON | 183 | 2028-03-02 |  | 0 | 0 | 0 | 337500 | 0 | 0 | 0 | 0 | 0 | 337500
SPC | 11 | Allegheny | 88398 | CM03 - Campbells Run No. 3 | 7415 | LOC | Bridge Restoration | CON | LOC | 2028-03-02 |  | 0 | 0 | 0 | 112500 | 0 | 0 | 0 | 0 | 0 | 112500
SPC | 11 | Allegheny | 88414 | PA03 - Painters Run No. 3 | 7123 | LOC | Bridge Restoration | FD | BRIP | 2027-11-04 |  | 0 | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68000
SPC | 11 | Allegheny | 88414 | PA03 - Painters Run No. 3 | 7123 | LOC | Bridge Restoration | FD | 183 | 2027-11-04 |  | 0 | 12750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12750
SPC | 11 | Allegheny | 88414 | PA03 - Painters Run No. 3 | 7123 | LOC | Bridge Restoration | FD | LOC | 2027-11-04 |  | 0 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4250
SPC | 11 | Allegheny | 88414 | PA03 - Painters Run No. 3 | 7123 | LOC | Bridge Restoration | ROW | BRIP | 2027-11-04 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SPC | 11 | Allegheny | 88414 | PA03 - Painters Run No. 3 | 7123 | LOC | Bridge Restoration | ROW | 183 | 2027-11-04 |  | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
SPC | 11 | Allegheny | 88414 | PA03 - Painters Run No. 3 | 7123 | LOC | Bridge Restoration | ROW | LOC | 2027-11-04 |  | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
SPC | 11 | Allegheny | 88414 | PA03 - Painters Run No. 3 | 7123 | LOC | Bridge Restoration | CON | BRIP | 2027-11-04 |  | 0 | 0 | 3200000 | 0 | 0 | 0 | 0 | 0 | 0 | 3200000
SPC | 11 | Allegheny | 88414 | PA03 - Painters Run No. 3 | 7123 | LOC | Bridge Restoration | CON | 183 | 2027-11-04 |  | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 88414 | PA03 - Painters Run No. 3 | 7123 | LOC | Bridge Restoration | CON | LOC | 2027-11-04 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 88497 | Abers Creek Bridge #3 (AB03) | 7446 | LOC | Bridge Restoration | CON | BOF | 2027-12-16 |  | 0 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260000
SPC | 11 | Allegheny | 88497 | Abers Creek Bridge #3 (AB03) | 7446 | LOC | Bridge Restoration | CON | 183 | 2027-12-16 |  | 0 | 48750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48750
SPC | 11 | Allegheny | 88497 | Abers Creek Bridge #3 (AB03) | 7446 | LOC | Bridge Restoration | CON | LOC | 2027-12-16 |  | 0 | 16250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16250
SPC | 11 | Allegheny | 88498 | Abers Creek No.4 (AB04) | 7446 | LOC | Bridge Preservation - Federal | CON | BOF | 2027-12-16 |  | 0 | 340000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340000
SPC | 11 | Allegheny | 88498 | Abers Creek No.4 (AB04) | 7446 | LOC | Bridge Preservation - Federal | CON | 183 | 2027-12-16 |  | 0 | 63750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63750
SPC | 11 | Allegheny | 88498 | Abers Creek No.4 (AB04) | 7446 | LOC | Bridge Preservation - Federal | CON | LOC | 2027-12-16 |  | 0 | 21250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21250
SPC | 11 | Allegheny | 89046 | McKnight Road ov Babcock Blvd Bridge Replacement | 4003 | A27 | Bridge Replacement | PE | BRIP | 2028-04-20 |  | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 89077 | Verona Road Bridge | 2058 | A12 | Bridge Replacement | FD | 185 | 2027-04-15 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 89077 | Verona Road Bridge | 2058 | A12 | Bridge Replacement | ROW | 185 | 2027-04-15 |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 11 | Allegheny | 89077 | Verona Road Bridge | 2058 | A12 | Bridge Replacement | UTL | 185 | 2027-04-15 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 89077 | Verona Road Bridge | 2058 | A12 | Bridge Replacement | CON | SXF | 2027-04-15 |  | 0 | 0 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 850000
SPC | 11 | Allegheny | 89077 | Verona Road Bridge | 2058 | A12 | Bridge Replacement | CON | 581 | 2027-04-15 |  | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 1150000 | 2350000
SPC | 11 | Allegheny | 89155 | Rochester Road Culvert | 4011 | A21 | Bridge Replacement | UTL | 185 | 2024-11-07 | 2024-11-07 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
SPC | 11 | Allegheny | 89155 | Rochester Road Culvert | 4011 | A21 | Bridge Replacement | CON | 581 | 2024-11-07 | 2024-11-07 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000
SPC | 11 | Allegheny | 91694 | PA 8- Butler Street | 8 | A79 | Highway Restoration | CON | NHPP | 2024-06-06 | 2024-06-06 | 333000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583000
SPC | 11 | Allegheny | 91723 | Steubenville Pike | 60 | 0 | Highway Restoration | PE | 581 | 2031-01-15 |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 91723 | Steubenville Pike | 60 | 0 | Highway Restoration | CON | 581 | 2031-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000
SPC | 11 | Allegheny | 91796 | Streets Run Road Flood Control | 2046 | A16 | Safety Improvement | STUDY | PRTCT | 2030-03-07 |  | 50000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
SPC | 11 | Allegheny | 91796 | Streets Run Road Flood Control | 2046 | A16 | Safety Improvement | STUDY | 581 | 2030-03-07 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Allegheny | 91796 | Streets Run Road Flood Control | 2046 | A16 | Safety Improvement | CON | 581 | 2030-03-07 |  | 0 | 0 | 0 | 6000000 | 6000000 | 8000000 | 0 | 0 | 0 | 20000000
SPC | 11 | Allegheny | 91845 | PA 28/Highland Park Br Interchange | 28 | A56 | Highway Reconstruction | ROW | NHPP | 2020-10-01 | 2020-10-01 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SPC | 11 | Allegheny | 91845 | PA 28/Highland Park Br Interchange | 28 | A56 | Highway Reconstruction | CON | NHPP | 2020-10-01 | 2020-10-01 | 1290607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1290607
SPC | 11 | Allegheny | 91845 | PA 28/Highland Park Br Interchange | 28 | A56 | Highway Reconstruction | CON | 581 | 2020-10-01 | 2020-10-01 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
SPC | 11 | Allegheny | 91881 | SR 4034, Little Sewickley Creek Road | 4034 | 0 | Safety Improvement | CON | 581 | 2028-04-15 |  | 0 | 0 | 0 | 1300000 | 0 | 0 | 0 | 0 | 0 | 1300000
SPC | 11 | Allegheny | 91907 | Charles Anderson Bridge | 7301 | LOC | Bridge Restoration | CON | NHPP | 2024-02-29 | 2024-02-29 | 2720000 | 2532000 | 580000 | 0 | 0 | 0 | 0 | 0 | 0 | 5832000
SPC | 11 | Allegheny | 92274 | PA 28: Highland Park - RIDC | 28 | A58 | Highway Restoration | CON | STP | 2021-07-22 | 2021-07-22 | 195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000
SPC | 11 | Allegheny | 92276 | PA 28: Harmarville-Russelton | 28 | A62 | Highway Restoration | CON | HSIP | 2022-03-03 | 2022-03-03 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SPC | 11 | Allegheny | 93371 | Patton St Bridge (TL13) | 7479 | 0 | Bridge Restoration | FD | STU | 2027-08-12 |  | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000
SPC | 11 | Allegheny | 93371 | Patton St Bridge (TL13) | 7479 | 0 | Bridge Restoration | FD | 183 | 2027-08-12 |  | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
SPC | 11 | Allegheny | 93371 | Patton St Bridge (TL13) | 7479 | 0 | Bridge Restoration | FD | LOC | 2027-08-12 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SPC | 11 | Allegheny | 93371 | Patton St Bridge (TL13) | 7479 | 0 | Bridge Restoration | ROW | STU | 2027-08-12 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SPC | 11 | Allegheny | 93371 | Patton St Bridge (TL13) | 7479 | 0 | Bridge Restoration | ROW | 183 | 2027-08-12 |  | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
SPC | 11 | Allegheny | 93371 | Patton St Bridge (TL13) | 7479 | 0 | Bridge Restoration | ROW | LOC | 2027-08-12 |  | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
SPC | 11 | Allegheny | 93371 | Patton St Bridge (TL13) | 7479 | 0 | Bridge Restoration | CON | STP | 2027-08-12 |  | 0 | 0 | 160000 | 1600000 | 0 | 1600000 | 0 | 0 | 0 | 3360000
SPC | 11 | Allegheny | 93371 | Patton St Bridge (TL13) | 7479 | 0 | Bridge Restoration | CON | STU | 2027-08-12 |  | 0 | 0 | 0 | 4000000 | 1000000 | 3000000 | 0 | 0 | 0 | 8000000
SPC | 11 | Allegheny | 93371 | Patton St Bridge (TL13) | 7479 | 0 | Bridge Restoration | CON | 183 | 2027-08-12 |  | 0 | 0 | 1050000 | 1050000 | 0 | 0 | 0 | 0 | 0 | 2100000
SPC | 11 | Allegheny | 93371 | Patton St Bridge (TL13) | 7479 | 0 | Bridge Restoration | CON | LOC | 2027-08-12 |  | 0 | 0 | 350000 | 350000 | 0 | 0 | 0 | 0 | 0 | 700000
SPC | 11 | Allegheny | 93394 | AL Local BPRS Group 4 | 7301 | LOC | Bridge Preservation - Federal | CON | STU | 2027-04-08 |  | 0 | 0 | 3520000 | 0 | 0 | 0 | 0 | 0 | 0 | 3520000
SPC | 11 | Allegheny | 93394 | AL Local BPRS Group 4 | 7301 | LOC | Bridge Preservation - Federal | CON | 183 | 2027-04-08 |  | 0 | 0 | 660000 | 0 | 0 | 0 | 0 | 0 | 0 | 660000
SPC | 11 | Allegheny | 93394 | AL Local BPRS Group 4 | 7301 | LOC | Bridge Preservation - Federal | CON | LOC | 2027-04-08 |  | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 220000
SPC | 11 | Allegheny | 93419 | MA08 - Glenwood Bridge | 885 | LOC | Bridge Preservation - Federal | CON | BRIP | 2023-08-10 | 2023-08-10 | 2880000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880000
SPC | 11 | Allegheny | 93419 | MA08 - Glenwood Bridge | 885 | LOC | Bridge Preservation - Federal | CON | 183 | 2023-08-10 | 2023-08-10 | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000
SPC | 11 | Allegheny | 93419 | MA08 - Glenwood Bridge | 885 | LOC | Bridge Preservation - Federal | CON | LOC | 2023-08-10 | 2023-08-10 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000
SPC | 11 | Allegheny | 93915 | Talbot Ave Ramp Bridge | 7456 | LOC | Bridge Replacement | PE | BOF | 2027-12-09 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
SPC | 11 | Allegheny | 93915 | Talbot Ave Ramp Bridge | 7456 | LOC | Bridge Replacement | PE | 183 | 2027-12-09 |  | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
SPC | 11 | Allegheny | 93915 | Talbot Ave Ramp Bridge | 7456 | LOC | Bridge Replacement | PE | LOC | 2027-12-09 |  | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
SPC | 11 | Allegheny | 93915 | Talbot Ave Ramp Bridge | 7456 | LOC | Bridge Replacement | FD | BOF | 2027-12-09 |  | 1040000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1040000
SPC | 11 | Allegheny | 93915 | Talbot Ave Ramp Bridge | 7456 | LOC | Bridge Replacement | FD | 183 | 2027-12-09 |  | 195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000
SPC | 11 | Allegheny | 93915 | Talbot Ave Ramp Bridge | 7456 | LOC | Bridge Replacement | FD | LOC | 2027-12-09 |  | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000
SPC | 11 | Allegheny | 93915 | Talbot Ave Ramp Bridge | 7456 | LOC | Bridge Replacement | ROW | BOF | 2027-12-09 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 93915 | Talbot Ave Ramp Bridge | 7456 | LOC | Bridge Replacement | ROW | 183 | 2027-12-09 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Allegheny | 93915 | Talbot Ave Ramp Bridge | 7456 | LOC | Bridge Replacement | ROW | LOC | 2027-12-09 |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SPC | 11 | Allegheny | 93915 | Talbot Ave Ramp Bridge | 7456 | LOC | Bridge Replacement | CON | BOF | 2027-12-09 |  | 0 | 0 | 0 | 1975000 | 3225000 | 2000000 | 0 | 0 | 0 | 7200000
SPC | 11 | Allegheny | 93915 | Talbot Ave Ramp Bridge | 7456 | LOC | Bridge Replacement | CON | 183 | 2027-12-09 |  | 0 | 0 | 0 | 370313 | 604687 | 375000 | 0 | 0 | 0 | 1350000
SPC | 11 | Allegheny | 93915 | Talbot Ave Ramp Bridge | 7456 | LOC | Bridge Replacement | CON | LOC | 2027-12-09 |  | 0 | 0 | 0 | 123437 | 201563 | 125000 | 0 | 0 | 0 | 450000
SPC | 11 | Allegheny | 93917 | Kenmawr Ave Ramp | 7456 | LOC | Bridge Restoration | CON | BOF | 2023-08-10 | 2023-08-10 | 0 | 2120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2120000
SPC | 11 | Allegheny | 93917 | Kenmawr Ave Ramp | 7456 | LOC | Bridge Restoration | CON | 183 | 2023-08-10 | 2023-08-10 | 0 | 397500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397500
SPC | 11 | Allegheny | 93917 | Kenmawr Ave Ramp | 7456 | LOC | Bridge Restoration | CON | LOC | 2023-08-10 | 2023-08-10 | 0 | 132500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132500
SPC | 11 | Allegheny | 94645 | West Liberty Avenue | 3069 | A25 | Highway Restoration | CON | NHPP | 2027-10-21 |  | 0 | 0 | 3600000 | 3600000 | 0 | 0 | 0 | 0 | 0 | 7200000
SPC | 11 | Allegheny | 94651 | I-376/Parkway East A.T.M | 376 | A51 | Safety Improvement | PE | CRP | 2027-09-16 |  | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 11 | Allegheny | 94651 | I-376/Parkway East A.T.M | 376 | A51 | Safety Improvement | PE | CRPU | 2027-09-16 |  | 0 | 770000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770000
SPC | 11 | Allegheny | 94651 | I-376/Parkway East A.T.M | 376 | A51 | Safety Improvement | FD | CRP | 2027-09-16 |  | 1112000 | 153000 | 1153000 | 1153000 | 1153000 | 0 | 0 | 0 | 0 | 4724000
SPC | 11 | Allegheny | 94651 | I-376/Parkway East A.T.M | 376 | A51 | Safety Improvement | CON | CAQ | 2027-09-16 |  | 0 | 0 | 0 | 0 | 8026480 | 0 | 0 | 0 | 0 | 8026480
SPC | 11 | Allegheny | 94651 | I-376/Parkway East A.T.M | 376 | A51 | Safety Improvement | CON | STP | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16243000 | 16243000
SPC | 11 | Allegheny | 94651 | I-376/Parkway East A.T.M | 376 | A51 | Safety Improvement | CON | STU | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 15000000
SPC | 11 | Allegheny | 94651 | I-376/Parkway East A.T.M | 376 | A51 | Safety Improvement | CON | 581 | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33344000 | 33344000
SPC | 11 | Allegheny | 94698 | SPC Smart Tr. Initiative |  |  | Reserve Line Item | CON | STU |  |  | 0 | 53000 | 2518680 | 0 | 3000000 | 3000000 | 3000000 | 3000000 | 12000000 | 26571680
SPC | 11 | Allegheny | 95754 | LN01 - Licks Run North 1 | 7219 | LOC | Bridge Restoration | FD | 183 | 2027-11-04 |  | 0 | 223200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223200
SPC | 11 | Allegheny | 95754 | LN01 - Licks Run North 1 | 7219 | LOC | Bridge Restoration | FD | LOC | 2027-11-04 |  | 0 | 55800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55800
SPC | 11 | Allegheny | 95754 | LN01 - Licks Run North 1 | 7219 | LOC | Bridge Restoration | CON | 183 | 2027-11-04 |  | 0 | 0 | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 480000
SPC | 11 | Allegheny | 95754 | LN01 - Licks Run North 1 | 7219 | LOC | Bridge Restoration | CON | LOC | 2027-11-04 |  | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 120000
SPC | 11 | Allegheny | 97028 | I-376/Banksville Interchange | 376 | A59 | Safety Improvement | FD | CAQ | 2027-05-13 |  | 1329222 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679222
SPC | 11 | Allegheny | 97028 | I-376/Banksville Interchange | 376 | A59 | Safety Improvement | ROW | CAQ | 2027-05-13 |  | 1301464 | 2698536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
SPC | 11 | Allegheny | 97028 | I-376/Banksville Interchange | 376 | A59 | Safety Improvement | UTL | CAQ | 2027-05-13 |  | 527540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 527540
SPC | 11 | Allegheny | 97028 | I-376/Banksville Interchange | 376 | A59 | Safety Improvement | CON | CAQ | 2027-05-13 |  | 0 | 0 | 2000000 | 3400000 | 5600000 | 0 | 0 | 0 | 0 | 11000000
SPC | 11 | Allegheny | 97028 | I-376/Banksville Interchange | 376 | A59 | Safety Improvement | CON | NHPP | 2027-05-13 |  | 0 | 0 | 0 | 0 | 0 | 16000000 | 11241278 | 12139000 | 0 | 39380278
SPC | 11 | Allegheny | 97028 | I-376/Banksville Interchange | 376 | A59 | Safety Improvement | CON | 581 | 2027-05-13 |  | 0 | 0 | 0 | 0 | 10000000 | 4000000 | 11000000 | 10000000 | 0 | 35000000
SPC | 11 | Allegheny | 98085 | PA 837/33rd St to Smithfield | 837 | A42 | Safety Improvement | CON | NHPP | 2019-12-12 | 2019-12-12 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000
SPC | 11 | Allegheny | 98125 | Bates Street Improvement | 885 | A52 | Safety Improvement | FD | 581 | 2033-06-15 |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 11 | Allegheny | 98125 | Bates Street Improvement | 885 | A52 | Safety Improvement | ROW | 581 | 2033-06-15 |  | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
SPC | 11 | Allegheny | 98125 | Bates Street Improvement | 885 | A52 | Safety Improvement | UTL | 581 | 2033-06-15 |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SPC | 11 | Allegheny | 98125 | Bates Street Improvement | 885 | A52 | Safety Improvement | CON | 581 | 2033-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26500000 | 26500000
SPC | 11 | Allegheny | 100624 | Tarentum Bridge Over Allegheny River | 366 | A08 | Bridge Restoration | FD | NHPP | 2027-03-11 |  | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 11 | Allegheny | 100624 | Tarentum Bridge Over Allegheny River | 366 | A08 | Bridge Restoration | CON | NHPP | 2027-03-11 |  | 0 | 0 | 3236000 | 0 | 0 | 0 | 0 | 0 | 0 | 3236000
SPC | 11 | Allegheny | 100624 | Tarentum Bridge Over Allegheny River | 366 | A08 | Bridge Restoration | CON | STU | 2027-03-11 |  | 0 | 0 | 0 | 3000000 | 7000000 | 0 | 5282000 | 0 | 0 | 15282000
SPC | 11 | Allegheny | 100624 | Tarentum Bridge Over Allegheny River | 366 | A08 | Bridge Restoration | CON | 185 | 2027-03-11 |  | 0 | 0 | 0 | 14140000 | 0 | 0 | 15000000 | 0 | 0 | 29140000
SPC | 11 | Allegheny | 100624 | Tarentum Bridge Over Allegheny River | 366 | A08 | Bridge Restoration | CON | 581 | 2027-03-11 |  | 0 | 0 | 0 | 0 | 6000000 | 6342000 | 12000000 | 8000000 | 0 | 32342000
SPC | 11 | Allegheny | 100637 | Clinton Rd ov NB Robinson | 978 | A15 | Bridge Replacement | FD | 185 | 2027-11-04 |  | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SPC | 11 | Allegheny | 100637 | Clinton Rd ov NB Robinson | 978 | A15 | Bridge Replacement | ROW | 185 | 2027-11-04 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Allegheny | 100637 | Clinton Rd ov NB Robinson | 978 | A15 | Bridge Replacement | UTL | 185 | 2027-11-04 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 100637 | Clinton Rd ov NB Robinson | 978 | A15 | Bridge Replacement | CON | STP | 2027-11-04 |  | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 1600000
SPC | 11 | Allegheny | 100637 | Clinton Rd ov NB Robinson | 978 | A15 | Bridge Replacement | CON | 185 | 2027-11-04 |  | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 100701 | McKees Rocks Bridge Phase 3 | 3104 | A04 | Bridge Preservation - Federal | FD | BRIP | 2030-03-15 |  | 0 | 0 | 6500000 | 0 | 0 | 0 | 0 | 0 | 0 | 6500000
SPC | 11 | Allegheny | 100701 | McKees Rocks Bridge Phase 3 | 3104 | A04 | Bridge Preservation - Federal | CON | STP | 2030-03-15 |  | 0 | 0 | 0 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 0 | 25000000
SPC | 11 | Allegheny | 100722 | Shenot Road Bridge | 4050 | A01 | Bridge Replacement | PE | 185 | 2028-07-27 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 100722 | Shenot Road Bridge | 4050 | A01 | Bridge Replacement | CON | 185 | 2028-07-27 |  | 0 | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 0 | 1800000
SPC | 11 | Allegheny | 100723 | Richard Road over Wexford Run | 4053 | A05 | Bridge Replacement | FD | 185 | 2026-12-03 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 11 | Allegheny | 100723 | Richard Road over Wexford Run | 4053 | A05 | Bridge Replacement | ROW | 185 | 2026-12-03 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 100723 | Richard Road over Wexford Run | 4053 | A05 | Bridge Replacement | UTL | 185 | 2026-12-03 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 100723 | Richard Road over Wexford Run | 4053 | A05 | Bridge Replacement | CON | 185 | 2026-12-03 |  | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 1500000
SPC | 11 | Allegheny | 100728 | Boulevard of Allies Ramps | 885 | A46 | Bridge Preservation - Federal | CON | BRIP | 2022-01-13 | 2022-01-13 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 100768 | US Route 22 - Wash County Line to Imperial Int. | 22 | 0 | Highway Reconstruction | PE | 581 | 2033-04-07 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 100768 | US Route 22 - Wash County Line to Imperial Int. | 22 | 0 | Highway Reconstruction | CON | STP | 2033-04-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15256000 | 15256000
SPC | 11 | Allegheny | 100768 | US Route 22 - Wash County Line to Imperial Int. | 22 | 0 | Highway Reconstruction | CON | STU | 2033-04-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 15000000
SPC | 11 | Allegheny | 100769 | US 22 - Imperial Interchange to McKee Road | 22 | A38 | Highway Reconstruction | PE | 581 | 2031-03-13 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 100769 | US 22 - Imperial Interchange to McKee Road | 22 | A38 | Highway Reconstruction | CON | NHPP | 2031-03-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 0 | 11256000 | 26256000
SPC | 11 | Allegheny | 100770 | US 22 - McKee Road to Parkway | 22 | 0 | Highway Reconstruction | PE | 581 | 2033-12-25 |  | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 750000
SPC | 11 | Allegheny | 100770 | US 22 - McKee Road to Parkway | 22 | 0 | Highway Reconstruction | CON | NHPP | 2033-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200000 | 7200000
SPC | 11 | Allegheny | 100770 | US 22 - McKee Road to Parkway | 22 | 0 | Highway Reconstruction | CON | 581 | 2033-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 1800000
SPC | 11 | Allegheny | 100773 | PA 28 / East Ohio Street | 28 | A65 | Highway Restoration | PE | NHPP | 2028-02-17 |  | 250000 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SPC | 11 | Allegheny | 100773 | PA 28 / East Ohio Street | 28 | A65 | Highway Restoration | CON | NHPP | 2028-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800000 | 0 | 4800000
SPC | 11 | Allegheny | 100773 | PA 28 / East Ohio Street | 28 | A65 | Highway Restoration | CON | 581 | 2028-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 1200000
SPC | 11 | Allegheny | 100782 | Mosside Blvd-PA 130 to Haymaker | 48 | A44 | Highway Restoration | PE | NHPP | 2027-07-02 |  | 405216 | 489074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 894290
SPC | 11 | Allegheny | 100782 | Mosside Blvd-PA 130 to Haymaker | 48 | A44 | Highway Restoration | ROW | NHPP | 2027-07-02 |  | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275000
SPC | 11 | Allegheny | 100782 | Mosside Blvd-PA 130 to Haymaker | 48 | A44 | Highway Restoration | UTL | NHPP | 2027-07-02 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 100782 | Mosside Blvd-PA 130 to Haymaker | 48 | A44 | Highway Restoration | CON | NHPP | 2027-07-02 |  | 0 | 0 | 4300000 | 0 | 0 | 0 | 550000 | 0 | 3750000 | 8600000
SPC | 11 | Allegheny | 100789 | Saw Mill Run Blvd: PA 88 to I-376 | 51 | 19A | Highway Reconstruction | PE | 581 | 2050-03-15 |  | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 11 | Allegheny | 100789 | Saw Mill Run Blvd: PA 88 to I-376 | 51 | 19A | Highway Reconstruction | CON | 581 | 2050-03-15 |  | 0 | 0 | 0 | 10000000 | 10000000 | 10000000 | 10000000 | 0 | 0 | 40000000
SPC | 11 | Allegheny | 100797 | PA 65, Sewickley Bridge to Beaver County Line | 65 | 0 | Highway Restoration | CON | NHPP | 2033-04-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3584000 | 3584000
SPC | 11 | Allegheny | 100797 | PA 65, Sewickley Bridge to Beaver County Line | 65 | 0 | Highway Restoration | CON | STP | 2033-04-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319220 | 319220
SPC | 11 | Allegheny | 100797 | PA 65, Sewickley Bridge to Beaver County Line | 65 | 0 | Highway Restoration | CON | STU | 2033-04-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2720780 | 2720780
SPC | 11 | Allegheny | 100797 | PA 65, Sewickley Bridge to Beaver County Line | 65 | 0 | Highway Restoration | CON | 581 | 2033-04-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1656000 | 1656000
SPC | 11 | Allegheny | 100798 | Ohio Rver Blvd-Ped Walkway | 65 | 0 | Highway Restoration | CON | STU | 2033-03-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8160000 | 8160000
SPC | 11 | Allegheny | 100798 | Ohio Rver Blvd-Ped Walkway | 65 | 0 | Highway Restoration | CON | 581 | 2033-03-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040000 | 2040000
SPC | 11 | Allegheny | 100935 | SR 65, Fremont Street Bridge | 65 | 0 | Bridge Restoration | PE | 185 | 2031-05-15 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
SPC | 11 | Allegheny | 100935 | SR 65, Fremont Street Bridge | 65 | 0 | Bridge Restoration | CON | 185 | 2031-05-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000000 | 23000000
SPC | 11 | Allegheny | 100955 | McKeesport-Duquesne Southern Ramps Deck Repl. | 2114 | 0 | Bridge Restoration | PE | NHPP | 2029-05-10 |  | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 11 | Allegheny | 100955 | McKeesport-Duquesne Southern Ramps Deck Repl. | 2114 | 0 | Bridge Restoration | CON | NHPP | 2029-05-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38400000 | 38400000
SPC | 11 | Allegheny | 100955 | McKeesport-Duquesne Southern Ramps Deck Repl. | 2114 | 0 | Bridge Restoration | CON | 185 | 2029-05-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600000 | 9600000
SPC | 11 | Allegheny | 100956 | West End Bridge | 19 | A83 | Bridge Preservation - Federal | FD | 581 | 2028-04-13 |  | 6000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000000
SPC | 11 | Allegheny | 100956 | West End Bridge | 19 | A83 | Bridge Preservation - Federal | ROW | 581 | 2028-04-13 |  | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 11 | Allegheny | 100956 | West End Bridge | 19 | A83 | Bridge Preservation - Federal | UTL | 581 | 2028-04-13 |  | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 11 | Allegheny | 100956 | West End Bridge | 19 | A83 | Bridge Preservation - Federal | CON | 581 | 2028-04-13 |  | 0 | 0 | 0 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 25000000 | 100000000
SPC | 11 | Allegheny | 100958 | 62nd Street Bridge | 8 | A85 | Bridge Restoration | PE | BRIP | 2029-06-14 |  | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
SPC | 11 | Allegheny | 100958 | 62nd Street Bridge | 8 | A85 | Bridge Restoration | CON | BRIP | 2029-06-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000000 | 36000000
SPC | 11 | Allegheny | 100958 | 62nd Street Bridge | 8 | A85 | Bridge Restoration | CON | 185 | 2029-06-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000000 | 9000000
SPC | 11 | Allegheny | 102645 | Smithfield Street Ph 2 - Fort Pitt Blvd to Forbes |  | LOC | Highway Reconstruction | PE | STU | 2033-06-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000
SPC | 11 | Allegheny | 102645 | Smithfield Street Ph 2 - Fort Pitt Blvd to Forbes |  | LOC | Highway Reconstruction | PE | LOC | 2033-06-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 250000
SPC | 11 | Allegheny | 102645 | Smithfield Street Ph 2 - Fort Pitt Blvd to Forbes |  | LOC | Highway Reconstruction | CON | STU | 2033-06-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600000 | 9600000
SPC | 11 | Allegheny | 102645 | Smithfield Street Ph 2 - Fort Pitt Blvd to Forbes |  | LOC | Highway Reconstruction | CON | LOC | 2033-06-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000 | 2400000
SPC | 11 | Allegheny | 103366 | Homestead-Grays Bridge Rehabilitation | 7301 | 0 | Bridge Restoration | CON | BRIP | 2029-09-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25784000 | 28784000 | 17432000 | 72000000
SPC | 11 | Allegheny | 103366 | Homestead-Grays Bridge Rehabilitation | 7301 | 0 | Bridge Restoration | CON | 183 | 2029-09-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4834500 | 6334500 | 2331000 | 13500000
SPC | 11 | Allegheny | 103366 | Homestead-Grays Bridge Rehabilitation | 7301 | 0 | Bridge Restoration | CON | LOC | 2029-09-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1611500 | 2111500 | 777000 | 4500000
SPC | 11 | Allegheny | 104328 | I-79 at PA 910 Interchange | 79 | A65 | Congestion Reduction | PE | NHPP | 2025-06-05 | 2025-06-05 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000
SPC | 11 | Allegheny | 104328 | I-79 at PA 910 Interchange | 79 | A65 | Congestion Reduction | PE | LOC | 2025-06-05 | 2025-06-05 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
SPC | 11 | Allegheny | 104328 | I-79 at PA 910 Interchange | 79 | A65 | Congestion Reduction | UTL | NHPP | 2025-06-05 | 2025-06-05 | 261000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261000
SPC | 11 | Allegheny | 104328 | I-79 at PA 910 Interchange | 79 | A65 | Congestion Reduction | CON | CAQ | 2025-06-05 | 2025-06-05 | 3800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800000
SPC | 11 | Allegheny | 104328 | I-79 at PA 910 Interchange | 79 | A65 | Congestion Reduction | CON | NHPP | 2025-06-05 | 2025-06-05 | 16432616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16432616
SPC | 11 | Allegheny | 104328 | I-79 at PA 910 Interchange | 79 | A65 | Congestion Reduction | CON | STP | 2025-06-05 | 2025-06-05 | 10262227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10262227
SPC | 11 | Allegheny | 104328 | I-79 at PA 910 Interchange | 79 | A65 | Congestion Reduction | CON | STU | 2025-06-05 | 2025-06-05 | 6246415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6246415
SPC | 11 | Allegheny | 104328 | I-79 at PA 910 Interchange | 79 | A65 | Congestion Reduction | CON | 581 | 2025-06-05 | 2025-06-05 | 5164373 | 4170556 | 7629333 | 0 | 0 | 0 | 0 | 0 | 0 | 16964262
SPC | 11 | Allegheny | 105450 | PA 51, Hayden Boulevard, M & O | 51 | 20A | Highway Restoration | PE | NHPP | 2028-03-15 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 105450 | PA 51, Hayden Boulevard, M & O | 51 | 20A | Highway Restoration | CON | 581 | 2028-03-15 |  | 0 | 0 | 0 | 4420000 | 2300000 | 2700000 | 5000000 | 0 | 0 | 14420000
SPC | 11 | Allegheny | 105451 | SR 3015 ov Lick Run Creek | 3015 | A03 | Bridge Replacement | FD | BOF | 2027-10-07 |  | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000
SPC | 11 | Allegheny | 105451 | SR 3015 ov Lick Run Creek | 3015 | A03 | Bridge Replacement | FD | 185 | 2027-10-07 |  | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
SPC | 11 | Allegheny | 105451 | SR 3015 ov Lick Run Creek | 3015 | A03 | Bridge Replacement | ROW | BOF | 2027-10-07 |  | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
SPC | 11 | Allegheny | 105451 | SR 3015 ov Lick Run Creek | 3015 | A03 | Bridge Replacement | ROW | 185 | 2027-10-07 |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
SPC | 11 | Allegheny | 105451 | SR 3015 ov Lick Run Creek | 3015 | A03 | Bridge Replacement | UTL | BOF | 2027-10-07 |  | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
SPC | 11 | Allegheny | 105451 | SR 3015 ov Lick Run Creek | 3015 | A03 | Bridge Replacement | UTL | 185 | 2027-10-07 |  | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
SPC | 11 | Allegheny | 105451 | SR 3015 ov Lick Run Creek | 3015 | A03 | Bridge Replacement | CON | 185 | 2027-10-07 |  | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 11 | Allegheny | 105462 | SR 3048, Noblestown Rd Slide Remediation | 3048 | A20 | Safety Improvement | FD | 581 | 2019-04-11 | 2019-04-11 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 105462 | SR 3048, Noblestown Rd Slide Remediation | 3048 | A20 | Safety Improvement | ROW | 581 | 2019-04-11 | 2019-04-11 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
SPC | 11 | Allegheny | 106080 | Smart Transportation/TAP Admin |  |  | Transportation Enhancement | PE | STU |  |  | 0 | 300000 | 50000 | 250000 | 400000 | 400000 | 400000 | 400000 | 1600000 | 3800000
SPC | 11 | Allegheny | 106269 | Neville Township Traffic Improvement Project |  | LOC | Safety Improvement | STUDY | STP | 2030-12-12 |  | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
SPC | 11 | Allegheny | 106269 | Neville Township Traffic Improvement Project |  | LOC | Safety Improvement | STUDY | STU | 2030-12-12 |  | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
SPC | 11 | Allegheny | 106269 | Neville Township Traffic Improvement Project |  | LOC | Safety Improvement | STUDY | LOC | 2030-12-12 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 106269 | Neville Township Traffic Improvement Project |  | LOC | Safety Improvement | PE | STP | 2030-12-12 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 106269 | Neville Township Traffic Improvement Project |  | LOC | Safety Improvement | PE | LOC | 2030-12-12 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 106269 | Neville Township Traffic Improvement Project |  | LOC | Safety Improvement | CON | STP | 2030-12-12 |  | 0 | 0 | 0 | 0 | 0 | 6400000 | 0 | 0 | 0 | 6400000
SPC | 11 | Allegheny | 106269 | Neville Township Traffic Improvement Project |  | LOC | Safety Improvement | CON | LOC | 2030-12-12 |  | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 1600000
SPC | 11 | Allegheny | 106386 | Larimer Avenue Bridge | 7301 | LOC | Bridge Replacement | FD | BOF | 2029-03-15 |  | 0 | 0 | 1100000 | 500000 | 0 | 0 | 0 | 0 | 0 | 1600000
SPC | 11 | Allegheny | 106386 | Larimer Avenue Bridge | 7301 | LOC | Bridge Replacement | FD | 183 | 2029-03-15 |  | 0 | 0 | 206250 | 93750 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 106386 | Larimer Avenue Bridge | 7301 | LOC | Bridge Replacement | FD | LOC | 2029-03-15 |  | 0 | 0 | 68750 | 31250 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 106386 | Larimer Avenue Bridge | 7301 | LOC | Bridge Replacement | ROW | BOF | 2029-03-15 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 106386 | Larimer Avenue Bridge | 7301 | LOC | Bridge Replacement | ROW | 183 | 2029-03-15 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Allegheny | 106386 | Larimer Avenue Bridge | 7301 | LOC | Bridge Replacement | ROW | LOC | 2029-03-15 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
SPC | 11 | Allegheny | 106386 | Larimer Avenue Bridge | 7301 | LOC | Bridge Replacement | CON | BOF | 2029-03-15 |  | 0 | 0 | 0 | 0 | 10700000 | 3000000 | 0 | 0 | 0 | 13700000
SPC | 11 | Allegheny | 106386 | Larimer Avenue Bridge | 7301 | LOC | Bridge Replacement | CON | BRIP | 2029-03-15 |  | 0 | 0 | 0 | 0 | 0 | 10300000 | 0 | 0 | 0 | 10300000
SPC | 11 | Allegheny | 106386 | Larimer Avenue Bridge | 7301 | LOC | Bridge Replacement | CON | 183 | 2029-03-15 |  | 0 | 0 | 0 | 0 | 2006250 | 2493750 | 0 | 0 | 0 | 4500000
SPC | 11 | Allegheny | 106386 | Larimer Avenue Bridge | 7301 | LOC | Bridge Replacement | CON | LOC | 2029-03-15 |  | 0 | 0 | 0 | 0 | 668750 | 831250 | 0 | 0 | 0 | 1500000
SPC | 11 | Allegheny | 106593 | SPC - Traffic Signal 5 |  |  | Safety Improvement | PE | CAQ | 2027-01-15 |  | 47040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47040
SPC | 11 | Allegheny | 106593 | SPC - Traffic Signal 5 |  |  | Safety Improvement | PE | LOC | 2027-01-15 |  | 11760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11760
SPC | 11 | Allegheny | 106593 | SPC - Traffic Signal 5 |  |  | Safety Improvement | CON | CAQ | 2027-01-15 |  | 0 | 0 | 0 | 0 | 824032 | 0 | 0 | 0 | 0 | 824032
SPC | 11 | Allegheny | 106593 | SPC - Traffic Signal 5 |  |  | Safety Improvement | CON | LOC | 2027-01-15 |  | 0 | 0 | 0 | 0 | 206008 | 0 | 0 | 0 | 0 | 206008
SPC | 11 | Allegheny | 106773 | Liberty Ave |  | LOC | Safety Improvement | ROW | STU | 2026-05-21 |  | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000
SPC | 11 | Allegheny | 106773 | Liberty Ave |  | LOC | Safety Improvement | ROW | LOC | 2026-05-21 |  | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
SPC | 11 | Allegheny | 106773 | Liberty Ave |  | LOC | Safety Improvement | CON | HVRU | 2026-05-21 |  | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000
SPC | 11 | Allegheny | 106773 | Liberty Ave |  | LOC | Safety Improvement | CON | HVRU | 2026-05-21 |  | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 11 | Allegheny | 106773 | Liberty Ave |  | LOC | Safety Improvement | CON | STP | 2026-05-21 |  | 0 | 1068000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1068000
SPC | 11 | Allegheny | 106773 | Liberty Ave |  | LOC | Safety Improvement | CON | STU | 2026-05-21 |  | 1893334 | 515000 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 4008334
SPC | 11 | Allegheny | 106773 | Liberty Ave |  | LOC | Safety Improvement | CON | LOC | 2026-05-21 |  | 1456666 | 395751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1852417
SPC | 11 | Allegheny | 107435 | Traffic Services Support | 3069 | 0 | Planning/Research/Administration | FD | 581 | 2050-12-15 |  | 0 | 350000 | 350000 | 350000 | 0 | 0 | 0 | 0 | 0 | 1050000
SPC | 11 | Allegheny | 107441 | Millvale/Shaler/Etna TRHT Connection |  |  | Transportation Enhancement | FD | STU | 2030-06-13 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SPC | 11 | Allegheny | 107441 | Millvale/Shaler/Etna TRHT Connection |  |  | Transportation Enhancement | FD | LOC | 2030-06-13 |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
SPC | 11 | Allegheny | 107441 | Millvale/Shaler/Etna TRHT Connection |  |  | Transportation Enhancement | ROW | LOC | 2030-06-13 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 107441 | Millvale/Shaler/Etna TRHT Connection |  |  | Transportation Enhancement | UTL | LOC | 2030-06-13 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 107441 | Millvale/Shaler/Etna TRHT Connection |  |  | Transportation Enhancement | CON | LOC | 2030-06-13 |  | 0 | 0 | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | 8000000
SPC | 11 | Allegheny | 108505 | SR 4031, Babcock Boulevard Resurfacing | 4031 | A17 | Highway Restoration | CON | STU | 2024-05-09 | 2024-05-09 | 178044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178044
SPC | 11 | Allegheny | 108528 | SR 48 Mill and Overlay | 48 | A46 | Highway Restoration | CON | NHPP | 2025-03-13 | 2025-03-13 | 9600000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10200000
SPC | 11 | Allegheny | 109349 | PA 65/Emsworth to I-79 | 65 | 0 | Highway Restoration | CON | STU | 2050-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9270000 | 9270000
SPC | 11 | Allegheny | 109383 | Bigelow Boulevard | 400 | A49 | Highway Restoration | FD | 581 | 2027-11-04 |  | 400000 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 11 | Allegheny | 109383 | Bigelow Boulevard | 400 | A49 | Highway Restoration | UTL | 581 | 2027-11-04 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 11 | Allegheny | 109383 | Bigelow Boulevard | 400 | A49 | Highway Restoration | CON | 581 | 2027-11-04 |  | 0 | 0 | 4879800 | 4470000 | 1374000 | 8697000 | 483000 | 460000 | 0 | 20363800
SPC | 11 | Allegheny | 109384 | Stoops Ferry Rd/McGovern Blvd | 51 | 0 | Highway Restoration | PE | 581 | 2050-12-25 |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 109384 | Stoops Ferry Rd/McGovern Blvd | 51 | 0 | Highway Restoration | CON | 581 | 2050-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 4000000
SPC | 11 | Allegheny | 109548 | Presto Sygan Road Bridge | 3028 | A05 | Bridge Replacement | FD | 185 | 2027-04-15 |  | 250000 | 500000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 11 | Allegheny | 109548 | Presto Sygan Road Bridge | 3028 | A05 | Bridge Replacement | ROW | 185 | 2027-04-15 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 109548 | Presto Sygan Road Bridge | 3028 | A05 | Bridge Replacement | UTL | 185 | 2027-04-15 |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 11 | Allegheny | 109548 | Presto Sygan Road Bridge | 3028 | A05 | Bridge Replacement | CON | BRIP | 2027-04-15 |  | 0 | 0 | 560000 | 1040000 | 0 | 0 | 0 | 0 | 0 | 1600000
SPC | 11 | Allegheny | 109548 | Presto Sygan Road Bridge | 3028 | A05 | Bridge Replacement | CON | STU | 2027-04-15 |  | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 11 | Allegheny | 109548 | Presto Sygan Road Bridge | 3028 | A05 | Bridge Replacement | CON | 185 | 2027-04-15 |  | 0 | 0 | 140000 | 760000 | 0 | 0 | 0 | 0 | 0 | 900000
SPC | 11 | Allegheny | 109549 | Highland Park Bridge | 1005 | A06 | Bridge Restoration | FD | 185 | 2027-04-14 |  | 1250000 | 2650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000
SPC | 11 | Allegheny | 109549 | Highland Park Bridge | 1005 | A06 | Bridge Restoration | ROW | 581 | 2027-04-14 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 109549 | Highland Park Bridge | 1005 | A06 | Bridge Restoration | UTL | 581 | 2027-04-14 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 109549 | Highland Park Bridge | 1005 | A06 | Bridge Restoration | CON | NHPP | 2027-04-14 |  | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000 | 10000000 | 35000000 | 65000000
SPC | 11 | Allegheny | 109562 | Stowe Tunnel Rehabilitation | 3092 | A05 | Highway Restoration | PE | 581 | 2029-05-10 |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SPC | 11 | Allegheny | 109562 | Stowe Tunnel Rehabilitation | 3092 | A05 | Highway Restoration | CON | STP | 2029-05-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10600000 | 0 | 10600000
SPC | 11 | Allegheny | 109562 | Stowe Tunnel Rehabilitation | 3092 | A05 | Highway Restoration | CON | STU | 2029-05-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 0 | 10000000
SPC | 11 | Allegheny | 109570 | Glenfield Viaduct Bridge | 4165 | A01 | Bridge Preservation - Federal | PE | BOF | 2027-04-29 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 109570 | Glenfield Viaduct Bridge | 4165 | A01 | Bridge Preservation - Federal | PE | 185 | 2027-04-29 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SPC | 11 | Allegheny | 109570 | Glenfield Viaduct Bridge | 4165 | A01 | Bridge Preservation - Federal | FD | BOF | 2027-04-29 |  | 520000 | 172000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 692000
SPC | 11 | Allegheny | 109570 | Glenfield Viaduct Bridge | 4165 | A01 | Bridge Preservation - Federal | FD | 185 | 2027-04-29 |  | 120000 | 53000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173000
SPC | 11 | Allegheny | 109570 | Glenfield Viaduct Bridge | 4165 | A01 | Bridge Preservation - Federal | ROW | BOF | 2027-04-29 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 109570 | Glenfield Viaduct Bridge | 4165 | A01 | Bridge Preservation - Federal | ROW | 185 | 2027-04-29 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 109570 | Glenfield Viaduct Bridge | 4165 | A01 | Bridge Preservation - Federal | UTL | BOF | 2027-04-29 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 109570 | Glenfield Viaduct Bridge | 4165 | A01 | Bridge Preservation - Federal | UTL | 185 | 2027-04-29 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SPC | 11 | Allegheny | 109570 | Glenfield Viaduct Bridge | 4165 | A01 | Bridge Preservation - Federal | CON | 185 | 2027-04-29 |  | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 11 | Allegheny | 109640 | PA 50: I-79 to Thoms Run | 50 | A32 | Safety Improvement | FD | 581 | 2027-03-14 |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 11 | Allegheny | 109640 | PA 50: I-79 to Thoms Run | 50 | A32 | Safety Improvement | ROW | NHPP | 2027-03-14 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 109640 | PA 50: I-79 to Thoms Run | 50 | A32 | Safety Improvement | ROW | 581 | 2027-03-14 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 109640 | PA 50: I-79 to Thoms Run | 50 | A32 | Safety Improvement | UTL | NHPP | 2027-03-14 |  | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
SPC | 11 | Allegheny | 109640 | PA 50: I-79 to Thoms Run | 50 | A32 | Safety Improvement | UTL | 581 | 2027-03-14 |  | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 109640 | PA 50: I-79 to Thoms Run | 50 | A32 | Safety Improvement | CON | NHPP | 2027-03-14 |  | 0 | 0 | 0 | 0 | 9600000 | 0 | 0 | 0 | 0 | 9600000
SPC | 11 | Allegheny | 109640 | PA 50: I-79 to Thoms Run | 50 | A32 | Safety Improvement | CON | 581 | 2027-03-14 |  | 0 | 0 | 0 | 0 | 2400000 | 0 | 0 | 0 | 0 | 2400000
SPC | 11 | Allegheny | 109691 | Smart PGH (ATCMTD) - Phase 3 |  |  | Safety Improvement | FD | OTH-F | 2027-03-25 |  | 1950000 | 1950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000
SPC | 11 | Allegheny | 109691 | Smart PGH (ATCMTD) - Phase 3 |  |  | Safety Improvement | FD | LOC | 2027-03-25 |  | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 11 | Allegheny | 109691 | Smart PGH (ATCMTD) - Phase 3 |  |  | Safety Improvement | ROW | OTH-F | 2027-03-25 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Allegheny | 109691 | Smart PGH (ATCMTD) - Phase 3 |  |  | Safety Improvement | ROW | LOC | 2027-03-25 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Allegheny | 109691 | Smart PGH (ATCMTD) - Phase 3 |  |  | Safety Improvement | UTL | OTH-F | 2027-03-25 |  | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000
SPC | 11 | Allegheny | 109691 | Smart PGH (ATCMTD) - Phase 3 |  |  | Safety Improvement | UTL | LOC | 2027-03-25 |  | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000
SPC | 11 | Allegheny | 109691 | Smart PGH (ATCMTD) - Phase 3 |  |  | Safety Improvement | CON | OTH-F | 2027-03-25 |  | 0 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
SPC | 11 | Allegheny | 109691 | Smart PGH (ATCMTD) - Phase 3 |  |  | Safety Improvement | CON | 073 | 2027-03-25 |  | 0 | 3200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200000
SPC | 11 | Allegheny | 109691 | Smart PGH (ATCMTD) - Phase 3 |  |  | Safety Improvement | CON | LOC | 2027-03-25 |  | 0 | 3400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000
SPC | 11 | Allegheny | 110316 | Pine Creek Bridge #16 (PI16) | 7118 | LOC | Bridge Preservation - Federal | PE | STU | 2032-03-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 400000
SPC | 11 | Allegheny | 110316 | Pine Creek Bridge #16 (PI16) | 7118 | LOC | Bridge Preservation - Federal | PE | 183 | 2032-03-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 75000
SPC | 11 | Allegheny | 110316 | Pine Creek Bridge #16 (PI16) | 7118 | LOC | Bridge Preservation - Federal | CON | STU | 2032-03-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 1200000
SPC | 11 | Allegheny | 110316 | Pine Creek Bridge #16 (PI16) | 7118 | LOC | Bridge Preservation - Federal | CON | 183 | 2032-03-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 0 | 225000
SPC | 11 | Allegheny | 110352 | East Carson Street Mill and Overlay | 837 | A55 | Highway Restoration | PE | NHPP | 2028-02-10 |  | 100000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 110352 | East Carson Street Mill and Overlay | 837 | A55 | Highway Restoration | ROW | NHPP | 2028-02-10 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 110352 | East Carson Street Mill and Overlay | 837 | A55 | Highway Restoration | UTL | NHPP | 2028-02-10 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 11 | Allegheny | 110352 | East Carson Street Mill and Overlay | 837 | A55 | Highway Restoration | CON | NHPP | 2028-02-10 |  | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 5000000
SPC | 11 | Allegheny | 110353 | SR 4003 - East Street to Babcock Blvd | 4003 | A25 | Highway Restoration | CON | NHPP | 2023-11-02 | 2023-11-02 | 1212000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212000
SPC | 11 | Allegheny | 110369 | PA 51 Clairton Blvd ATSPM | 51 | 12A | Safety Improvement | CON | CAQ | 2024-08-22 | 2024-08-22 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 111571 | SR 51, Clairton Boulevard | 51 | 12A | Highway Restoration | UTL | NHPP | 2024-08-22 | 2024-08-22 | 362000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362000
SPC | 11 | Allegheny | 111571 | SR 51, Clairton Boulevard | 51 | 12A | Highway Restoration | CON | NHPP | 2024-08-22 | 2024-08-22 | 120656 | 787000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 907656
SPC | 11 | Allegheny | 111596 | Cargo Road | 3160 | 0 | Highway Reconstruction | CON | 581 | 2050-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
SPC | 11 | Allegheny | 111838 | SR 1001, Freeport Rd Rockfall Fence and Trail | 1001 | A59 | Safety Improvement | PE | 581 | 2027-06-10 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 11 | Allegheny | 112081 | SMART - Sylvan Ave Multimodal Path |  | LOC | MultiModal | CON | STU | 2023-10-19 | 2023-10-19 | 221600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221600
SPC | 11 | Allegheny | 112081 | SMART - Sylvan Ave Multimodal Path |  | LOC | MultiModal | CON | LOC | 2023-10-19 | 2023-10-19 | 55400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55400
SPC | 11 | Allegheny | 112725 | MTF McKees Rocks Streetscape & Roadway Improvement |  |  | MultiModal | FD | 411 | 2027-04-08 |  | 82013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82013
SPC | 11 | Allegheny | 112725 | MTF McKees Rocks Streetscape & Roadway Improvement |  |  | MultiModal | FD | LOC | 2027-04-08 |  | 82013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82013
SPC | 11 | Allegheny | 112725 | MTF McKees Rocks Streetscape & Roadway Improvement |  |  | MultiModal | CON | 411 | 2027-04-08 |  | 0 | 1721290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1721290
SPC | 11 | Allegheny | 112934 | District Connector Road and Trail (ARC) |  |  | Bicycle Pedestrian Highway | CON | APL | 2027-04-01 |  | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000
SPC | 11 | Allegheny | 112934 | District Connector Road and Trail (ARC) |  |  | Bicycle Pedestrian Highway | CON | OTH-S | 2027-04-01 |  | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000
SPC | 11 | Allegheny | 112934 | District Connector Road and Trail (ARC) |  |  | Bicycle Pedestrian Highway | CON | LOC | 2027-04-01 |  | 83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83333
SPC | 11 | Allegheny | 112934 | District Connector Road and Trail (ARC) |  |  | Bicycle Pedestrian Highway | CON | PRIV | 2027-04-01 |  | 1092857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1092857
SPC | 11 | Allegheny | 112950 | Bridge Wash 2025 | 579 | 0 | Bridge Preservation - Federal | CON | BRIP | 2025-05-08 | 2025-05-08 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
SPC | 11 | Allegheny | 112950 | Bridge Wash 2025 | 579 | 0 | Bridge Preservation - Federal | CON | 185 | 2025-05-08 | 2025-05-08 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 113342 | 2024 ADA Curb Ramp Project | 400 | A53 | Safety Improvement | CON | 581 | 2024-10-10 | 2024-10-10 | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700000
SPC | 11 | Allegheny | 113343 | 2025 ADA Curb Ramp Project | 51 | 0 | Safety Improvement | PE | STP | 2025-09-11 | 2025-09-11 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 113343 | 2025 ADA Curb Ramp Project | 51 | 0 | Safety Improvement | CON | 581 | 2025-09-11 | 2025-09-11 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 11 | Allegheny | 113348 | Bridge Demand Mtc 17, 25 | 3005 | A12 | Bridge Restoration | CON | 185 | 2025-03-13 | 2025-03-13 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Allegheny | 113455 | Environmental Unit Assistance for Permit Activites |  |  | Planning/Research/Administration | PE | 581 |  |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Allegheny | 113508 | Freeway Service Patrol & Traffic Control | 28 | 0 | Intelligent Transportation System | CON | STU |  |  | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
SPC | 11 | Allegheny | 113629 | Babcock Boulevard Culvert | 4031 | A16 | Bridge Replacement | PE | 185 | 2028-04-06 |  | 250000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Allegheny | 113629 | Babcock Boulevard Culvert | 4031 | A16 | Bridge Replacement | FD | 185 | 2028-04-06 |  | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Allegheny | 113629 | Babcock Boulevard Culvert | 4031 | A16 | Bridge Replacement | ROW | 185 | 2028-04-06 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 113629 | Babcock Boulevard Culvert | 4031 | A16 | Bridge Replacement | UTL | 185 | 2028-04-06 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 113629 | Babcock Boulevard Culvert | 4031 | A16 | Bridge Replacement | CON | STP | 2028-04-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 1200000
SPC | 11 | Allegheny | 113629 | Babcock Boulevard Culvert | 4031 | A16 | Bridge Replacement | CON | 185 | 2028-04-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 300000
SPC | 11 | Allegheny | 113631 | Bakerstown Road Bridge | 4068 | A21 | Bridge Restoration | ROW | 185 | 2027-04-15 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 113631 | Bakerstown Road Bridge | 4068 | A21 | Bridge Restoration | UTL | 185 | 2027-04-15 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 113631 | Bakerstown Road Bridge | 4068 | A21 | Bridge Restoration | CON | STU | 2027-04-15 |  | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 1600000
SPC | 11 | Allegheny | 113631 | Bakerstown Road Bridge | 4068 | A21 | Bridge Restoration | CON | 185 | 2027-04-15 |  | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 113632 | West End Bridge Ramps | 8055 | A01 | Bridge Preservation - Federal | FD | NHPP | 2028-04-13 |  | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 11 | Allegheny | 113632 | West End Bridge Ramps | 8055 | A01 | Bridge Preservation - Federal | ROW | NHPP | 2028-04-13 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 113632 | West End Bridge Ramps | 8055 | A01 | Bridge Preservation - Federal | UTL | NHPP | 2028-04-13 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 113632 | West End Bridge Ramps | 8055 | A01 | Bridge Preservation - Federal | CON | NHPP | 2028-04-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000000 | 0 | 7000000
SPC | 11 | Allegheny | 113636 | Center Avenue Bridge | 2001 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 113636 | Center Avenue Bridge | 2001 | 0 | Bridge Replacement | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 2000000
SPC | 11 | Allegheny | 113647 | 62nd Street Bridge SB Approach | 8 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 113647 | 62nd Street Bridge SB Approach | 8 | 0 | Bridge Preservation - Federal | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000
SPC | 11 | Allegheny | 113674 | Verona Road over Tributary to Sandy Creek | 2058 | A18 | Bridge Replacement | FD | 185 | 2027-07-29 |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 11 | Allegheny | 113674 | Verona Road over Tributary to Sandy Creek | 2058 | A18 | Bridge Replacement | ROW | 185 | 2027-07-29 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 113674 | Verona Road over Tributary to Sandy Creek | 2058 | A18 | Bridge Replacement | UTL | 185 | 2027-07-29 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 113674 | Verona Road over Tributary to Sandy Creek | 2058 | A18 | Bridge Replacement | CON | 185 | 2027-07-29 |  | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000
SPC | 11 | Allegheny | 114150 | Swindell Bridge | 7301 | 0 | Bridge Restoration | FD | BRIP | 2027-10-21 |  | 800000 | 1428000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2228000
SPC | 11 | Allegheny | 114150 | Swindell Bridge | 7301 | 0 | Bridge Restoration | FD | 183 | 2027-10-21 |  | 150000 | 267750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417750
SPC | 11 | Allegheny | 114150 | Swindell Bridge | 7301 | 0 | Bridge Restoration | FD | LOC | 2027-10-21 |  | 50000 | 89250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139250
SPC | 11 | Allegheny | 114150 | Swindell Bridge | 7301 | 0 | Bridge Restoration | ROW | BRIP | 2027-10-21 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 114150 | Swindell Bridge | 7301 | 0 | Bridge Restoration | ROW | 183 | 2027-10-21 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Allegheny | 114150 | Swindell Bridge | 7301 | 0 | Bridge Restoration | ROW | LOC | 2027-10-21 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SPC | 11 | Allegheny | 114150 | Swindell Bridge | 7301 | 0 | Bridge Restoration | CON | BRIP | 2027-10-21 |  | 0 | 0 | 0 | 0 | 12000000 | 13600000 | 0 | 0 | 0 | 25600000
SPC | 11 | Allegheny | 114150 | Swindell Bridge | 7301 | 0 | Bridge Restoration | CON | 183 | 2027-10-21 |  | 0 | 0 | 0 | 0 | 2250000 | 2550000 | 0 | 0 | 0 | 4800000
SPC | 11 | Allegheny | 114150 | Swindell Bridge | 7301 | 0 | Bridge Restoration | CON | LOC | 2027-10-21 |  | 0 | 0 | 0 | 0 | 750000 | 850000 | 0 | 0 | 0 | 1600000
SPC | 11 | Allegheny | 114193 | PA 837 Slide Remediation | 837 | A50 | Safety Improvement | ROW | 581 | 2027-01-28 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Allegheny | 114193 | PA 837 Slide Remediation | 837 | A50 | Safety Improvement | CON | NHPP | 2027-01-28 |  | 0 | 0 | 3000000 | 4895000 | 0 | 0 | 0 | 0 | 0 | 7895000
SPC | 11 | Allegheny | 114193 | PA 837 Slide Remediation | 837 | A50 | Safety Improvement | CON | STP | 2027-01-28 |  | 0 | 0 | 0 | 0 | 4105000 | 0 | 0 | 0 | 0 | 4105000
SPC | 11 | Allegheny | 114193 | PA 837 Slide Remediation | 837 | A50 | Safety Improvement | CON | 581 | 2027-01-28 |  | 0 | 0 | 750000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 11 | Allegheny | 114194 | SR 2010, Lovedale Road Wall Remediation | 2010 | A06 | Safety Improvement | FD | 581 | 2027-01-14 |  | 530000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530000
SPC | 11 | Allegheny | 114194 | SR 2010, Lovedale Road Wall Remediation | 2010 | A06 | Safety Improvement | ROW | 581 | 2027-01-14 |  | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520000
SPC | 11 | Allegheny | 114194 | SR 2010, Lovedale Road Wall Remediation | 2010 | A06 | Safety Improvement | CON | PRTCT | 2027-01-14 |  | 0 | 0 | 2500000 | 2500000 | 0 | 0 | 0 | 0 | 0 | 5000000
SPC | 11 | Allegheny | 114194 | SR 2010, Lovedale Road Wall Remediation | 2010 | A06 | Safety Improvement | CON | STP | 2027-01-14 |  | 0 | 0 | 2500000 | 4499000 | 1221000 | 0 | 0 | 0 | 0 | 8220000
SPC | 11 | Allegheny | 114194 | SR 2010, Lovedale Road Wall Remediation | 2010 | A06 | Safety Improvement | CON | 581 | 2027-01-14 |  | 0 | 0 | 625000 | 2300000 | 0 | 0 | 0 | 0 | 0 | 2925000
SPC | 11 | Allegheny | 114195 | SR 3034, Chartiers St Slide Remediation | 3034 | A15 | Safety Improvement | CON | PRTCT | 2027-04-06 |  | 0 | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 11 | Allegheny | 114195 | SR 3034, Chartiers St Slide Remediation | 3034 | A15 | Safety Improvement | CON | STP | 2027-04-06 |  | 0 | 0 | 4360000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 6360000
SPC | 11 | Allegheny | 114195 | SR 3034, Chartiers St Slide Remediation | 3034 | A15 | Safety Improvement | CON | 581 | 2027-04-06 |  | 0 | 0 | 1940000 | 400000 | 0 | 0 | 0 | 0 | 0 | 2340000
SPC | 11 | Allegheny | 114266 | West Carson Street Bridge | 7301 | BRG | Bridge Replacement | FD | BOF | 2027-09-16 |  | 0 | 960000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960000
SPC | 11 | Allegheny | 114266 | West Carson Street Bridge | 7301 | BRG | Bridge Replacement | FD | 183 | 2027-09-16 |  | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000
SPC | 11 | Allegheny | 114266 | West Carson Street Bridge | 7301 | BRG | Bridge Replacement | FD | LOC | 2027-09-16 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
SPC | 11 | Allegheny | 114266 | West Carson Street Bridge | 7301 | BRG | Bridge Replacement | ROW | BOF | 2027-09-16 |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SPC | 11 | Allegheny | 114266 | West Carson Street Bridge | 7301 | BRG | Bridge Replacement | ROW | 183 | 2027-09-16 |  | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
SPC | 11 | Allegheny | 114266 | West Carson Street Bridge | 7301 | BRG | Bridge Replacement | ROW | LOC | 2027-09-16 |  | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
SPC | 11 | Allegheny | 114266 | West Carson Street Bridge | 7301 | BRG | Bridge Replacement | CON | BOF | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000000 | 0 | 8000000
SPC | 11 | Allegheny | 114266 | West Carson Street Bridge | 7301 | BRG | Bridge Replacement | CON | 183 | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 1500000
SPC | 11 | Allegheny | 114266 | West Carson Street Bridge | 7301 | BRG | Bridge Replacement | CON | LOC | 2027-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000
SPC | 11 | Allegheny | 114287 | SR 3003 (Washington Pike) Improvements | 3003 | A11 | Safety Improvement | PE | CAQ | 2027-07-15 |  | 0 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145000
SPC | 11 | Allegheny | 114287 | SR 3003 (Washington Pike) Improvements | 3003 | A11 | Safety Improvement | FD | CAQ | 2027-07-15 |  | 500000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
SPC | 11 | Allegheny | 114287 | SR 3003 (Washington Pike) Improvements | 3003 | A11 | Safety Improvement | ROW | CAQ | 2027-07-15 |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 11 | Allegheny | 114287 | SR 3003 (Washington Pike) Improvements | 3003 | A11 | Safety Improvement | UTL | CAQ | 2027-07-15 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 114287 | SR 3003 (Washington Pike) Improvements | 3003 | A11 | Safety Improvement | CON | CAQ | 2027-07-15 |  | 0 | 0 | 3049200 | 240000 | 1541000 | 0 | 0 | 0 | 0 | 4830200
SPC | 11 | Allegheny | 114288 | Penn Avenue Signal Improvements |  |  | Safety Improvement | FD | CAQ | 2028-09-26 |  | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SPC | 11 | Allegheny | 114288 | Penn Avenue Signal Improvements |  |  | Safety Improvement | FD | LOC | 2028-09-26 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 114288 | Penn Avenue Signal Improvements |  |  | Safety Improvement | ROW | CAQ | 2028-09-26 |  | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 114288 | Penn Avenue Signal Improvements |  |  | Safety Improvement | ROW | LOC | 2028-09-26 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SPC | 11 | Allegheny | 114288 | Penn Avenue Signal Improvements |  |  | Safety Improvement | CON | CAQ | 2028-09-26 |  | 0 | 0 | 0 | 1500000 | 2448592 | 0 | 0 | 0 | 0 | 3948592
SPC | 11 | Allegheny | 114288 | Penn Avenue Signal Improvements |  |  | Safety Improvement | CON | LOC | 2028-09-26 |  | 0 | 0 | 0 | 375000 | 612128 | 0 | 0 | 0 | 0 | 987128
SPC | 11 | Allegheny | 114290 | Allegheny River Green Boulevard |  |  | Safety Improvement | FD | CAQ | 2028-02-03 |  | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
SPC | 11 | Allegheny | 114290 | Allegheny River Green Boulevard |  |  | Safety Improvement | FD | LOC | 2028-02-03 |  | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
SPC | 11 | Allegheny | 114290 | Allegheny River Green Boulevard |  |  | Safety Improvement | ROW | CAQ | 2028-02-03 |  | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 114290 | Allegheny River Green Boulevard |  |  | Safety Improvement | ROW | LOC | 2028-02-03 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SPC | 11 | Allegheny | 114290 | Allegheny River Green Boulevard |  |  | Safety Improvement | CON | CAQ | 2028-02-03 |  | 0 | 0 | 0 | 1360000 | 1456000 | 0 | 0 | 0 | 0 | 2816000
SPC | 11 | Allegheny | 114290 | Allegheny River Green Boulevard |  |  | Safety Improvement | CON | LOC | 2028-02-03 |  | 0 | 0 | 0 | 340000 | 364000 | 0 | 0 | 0 | 0 | 704000
SPC | 11 | Allegheny | 114318 | Tri-Boro Expressway - CPR | 2037 | 0 | Highway Restoration | PE | 581 | 2033-06-09 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 114318 | Tri-Boro Expressway - CPR | 2037 | 0 | Highway Restoration | CON | 581 | 2033-06-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
SPC | 11 | Allegheny | 115070 | SR 2046, Streets Run Road Resurfacing | 2046 | A17 | Highway Restoration | PE | STU | 2027-01-14 |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 11 | Allegheny | 115070 | SR 2046, Streets Run Road Resurfacing | 2046 | A17 | Highway Restoration | ROW | STU | 2027-01-14 |  | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
SPC | 11 | Allegheny | 115070 | SR 2046, Streets Run Road Resurfacing | 2046 | A17 | Highway Restoration | UTL | STU | 2027-01-14 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 115070 | SR 2046, Streets Run Road Resurfacing | 2046 | A17 | Highway Restoration | CON | STU | 2027-01-14 |  | 0 | 0 | 1331380 | 584325 | 684295 | 0 | 0 | 0 | 0 | 2600000
SPC | 11 | Allegheny | 115070 | SR 2046, Streets Run Road Resurfacing | 2046 | A17 | Highway Restoration | CON | SXF | 2027-01-14 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 115070 | SR 2046, Streets Run Road Resurfacing | 2046 | A17 | Highway Restoration | CON | 581 | 2027-01-14 |  | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 4500000
SPC | 11 | Allegheny | 115085 | SR 837, North State Street | 837 | A54 | Highway Reconstruction | PE | NHPP | 2027-01-28 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 115085 | SR 837, North State Street | 837 | A54 | Highway Reconstruction | ROW | 581 | 2027-01-28 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 11 | Allegheny | 115085 | SR 837, North State Street | 837 | A54 | Highway Reconstruction | CON | NHPP | 2027-01-28 |  | 0 | 0 | 0 | 6214000 | 0 | 0 | 0 | 0 | 0 | 6214000
SPC | 11 | Allegheny | 115085 | SR 837, North State Street | 837 | A54 | Highway Reconstruction | CON | 581 | 2027-01-28 |  | 0 | 0 | 0 | 6850000 | 0 | 0 | 0 | 0 | 0 | 6850000
SPC | 11 | Allegheny | 115277 | Western Regional TMC Upgrade |  |  | Safety Improvement | PE | CRPU | 2050-12-25 |  | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 11 | Allegheny | 115476 | Three Rivers Heritage Trail - Brackenridge TAP |  | TAP | Bicycle Pedestrian Highway | CON | TAU | 2024-12-12 | 2024-12-12 | 284445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284445
SPC | 11 | Allegheny | 115555 | MTA Market Place District Improvements Phase 1 | 3072 | A11 | MultiModal | CON | SXF | 2026-02-12 | 2026-02-12 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000
SPC | 11 | Allegheny | 115555 | MTA Market Place District Improvements Phase 1 | 3072 | A11 | MultiModal | CON | 411 | 2026-02-12 | 2026-02-12 | 2315828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2315828
SPC | 11 | Allegheny | 115555 | MTA Market Place District Improvements Phase 1 | 3072 | A11 | MultiModal | CON | 581 | 2026-02-12 | 2026-02-12 | 372000 | 299000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671000
SPC | 11 | Allegheny | 115555 | MTA Market Place District Improvements Phase 1 | 3072 | A11 | MultiModal | CON | LOC | 2026-02-12 | 2026-02-12 | 1705172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1705172
SPC | 11 | Allegheny | 115556 | Thompson Run Rd & Old William Penn Hwy Brdgs | 2065 | A10 | Bridge Restoration | PE | STU | 2027-10-21 |  | 350000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 115556 | Thompson Run Rd & Old William Penn Hwy Brdgs | 2065 | A10 | Bridge Restoration | FD | STU | 2027-10-21 |  | 0 | 200000 | 350000 | 150000 | 0 | 0 | 0 | 0 | 0 | 700000
SPC | 11 | Allegheny | 115556 | Thompson Run Rd & Old William Penn Hwy Brdgs | 2065 | A10 | Bridge Restoration | ROW | STU | 2027-10-21 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 115556 | Thompson Run Rd & Old William Penn Hwy Brdgs | 2065 | A10 | Bridge Restoration | UTL | STU | 2027-10-21 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 11 | Allegheny | 115556 | Thompson Run Rd & Old William Penn Hwy Brdgs | 2065 | A10 | Bridge Restoration | CON | STU | 2027-10-21 |  | 0 | 0 | 2000000 | 2820000 | 0 | 0 | 0 | 0 | 0 | 4820000
SPC | 11 | Allegheny | 116096 | Kittanning St Flood Control | 1003 | A02 | Stormwater Management | PE | STP | 2028-03-15 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 116096 | Kittanning St Flood Control | 1003 | A02 | Stormwater Management | PE | SXF | 2028-03-15 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 116096 | Kittanning St Flood Control | 1003 | A02 | Stormwater Management | PE | 185 | 2028-03-15 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 116096 | Kittanning St Flood Control | 1003 | A02 | Stormwater Management | FD | SXF | 2028-03-15 |  | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
SPC | 11 | Allegheny | 116096 | Kittanning St Flood Control | 1003 | A02 | Stormwater Management | FD | 185 | 2028-03-15 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
SPC | 11 | Allegheny | 116096 | Kittanning St Flood Control | 1003 | A02 | Stormwater Management | ROW | STP | 2028-03-15 |  | 0 | 0 | 1840000 | 0 | 0 | 0 | 0 | 0 | 0 | 1840000
SPC | 11 | Allegheny | 116096 | Kittanning St Flood Control | 1003 | A02 | Stormwater Management | ROW | SXF | 2028-03-15 |  | 0 | 460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460000
SPC | 11 | Allegheny | 116096 | Kittanning St Flood Control | 1003 | A02 | Stormwater Management | ROW | 185 | 2028-03-15 |  | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 116096 | Kittanning St Flood Control | 1003 | A02 | Stormwater Management | UTL | STP | 2028-03-15 |  | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
SPC | 11 | Allegheny | 116096 | Kittanning St Flood Control | 1003 | A02 | Stormwater Management | UTL | 185 | 2028-03-15 |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 116096 | Kittanning St Flood Control | 1003 | A02 | Stormwater Management | CON | 185 | 2028-03-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000000 | 21000000
SPC | 11 | Allegheny | 116170 | Homestead-Duquesne Road Betterment 2 |  | LOC | Highway Restoration | CON | STP | 2027-11-04 |  | 0 | 0 | 593000 | 2207000 | 0 | 0 | 0 | 0 | 0 | 2800000
SPC | 11 | Allegheny | 116170 | Homestead-Duquesne Road Betterment 2 |  | LOC | Highway Restoration | CON | LOC | 2027-11-04 |  | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
SPC | 11 | Allegheny | 116300 | Smart PGH - Phase 1 |  |  | Safety Improvement | CON | 073 | 2026-09-17 |  | 3800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800000
SPC | 11 | Allegheny | 116301 | Smart PGH - Phase 2 |  |  | Safety Improvement | CON | OTH-F | 2027-12-09 |  | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 11 | Allegheny | 116301 | Smart PGH - Phase 2 |  |  | Safety Improvement | CON | LOC | 2027-12-09 |  | 0 | 4294000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4294000
SPC | 11 | Allegheny | 116303 | Smart PGH - City of Pittsburgh TMC | 2308 | 0 | Intelligent Transportation System | CON | OTH-F | 2025-08-07 |  | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
SPC | 11 | Allegheny | 116303 | Smart PGH - City of Pittsburgh TMC | 2308 | 0 | Intelligent Transportation System | CON | LOC | 2025-08-07 |  | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
SPC | 11 | Allegheny | 116589 | Miller's Run Road | 50 | 0 | Highway Reconstruction | PE | 581 | 2050-06-15 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 116589 | Miller's Run Road | 50 | 0 | Highway Reconstruction | CON | STU | 2050-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
SPC | 11 | Allegheny | 116655 | SR 30/SR 48 Intersection Improvement w/D12 | 30 | A39 | Safety Improvement | CON | 581 | 2028-12-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19500000 | 19500000
SPC | 11 | Allegheny | 116925 | Connor Road Bridge | 3038 | A09 | Bridge Replacement | PE | NHPP | 2027-09-30 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 116925 | Connor Road Bridge | 3038 | A09 | Bridge Replacement | FD | NHPP | 2027-09-30 |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SPC | 11 | Allegheny | 116925 | Connor Road Bridge | 3038 | A09 | Bridge Replacement | FD | 185 | 2027-09-30 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 116925 | Connor Road Bridge | 3038 | A09 | Bridge Replacement | ROW | NHPP | 2027-09-30 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 116925 | Connor Road Bridge | 3038 | A09 | Bridge Replacement | ROW | 185 | 2027-09-30 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SPC | 11 | Allegheny | 116925 | Connor Road Bridge | 3038 | A09 | Bridge Replacement | UTL | NHPP | 2027-09-30 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 116925 | Connor Road Bridge | 3038 | A09 | Bridge Replacement | UTL | 185 | 2027-09-30 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SPC | 11 | Allegheny | 116925 | Connor Road Bridge | 3038 | A09 | Bridge Replacement | CON | NHPP | 2027-09-30 |  | 0 | 0 | 3600000 | 3600000 | 0 | 0 | 0 | 0 | 0 | 7200000
SPC | 11 | Allegheny | 116925 | Connor Road Bridge | 3038 | A09 | Bridge Replacement | CON | 185 | 2027-09-30 |  | 0 | 0 | 900000 | 900000 | 0 | 0 | 0 | 0 | 0 | 1800000
SPC | 11 | Allegheny | 117269 | PRT Wilkinsburg Transit Center |  |  | Congestion Reduction | CON | CRP |  |  | 67003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67003
SPC | 11 | Allegheny | 117269 | PRT Wilkinsburg Transit Center |  |  | Congestion Reduction | CON | CRPU |  |  | 1713400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1713400
SPC | 11 | Allegheny | 117269 | PRT Wilkinsburg Transit Center |  |  | Congestion Reduction | CON | LOC |  |  | 445101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445101
SPC | 11 | Allegheny | 117270 | PPC- Marine & Landside Equipment Re-Power Progr |  |  | Air Quality | CON | CAQ | 2024-01-13 | 2024-01-18 | 0 | 0 | 5025000 | 0 | 0 | 0 | 0 | 0 | 0 | 5025000
SPC | 11 | Allegheny | 117270 | PPC- Marine & Landside Equipment Re-Power Progr |  |  | Air Quality | CON | LOC | 2024-01-13 | 2024-01-18 | 0 | 0 | 5025000 | 0 | 0 | 0 | 0 | 0 | 0 | 5025000
SPC | 11 | Allegheny | 117271 | SR 50 Signal Upgrades | 50 | A38 | Congestion Reduction | PE | CAQ | 2025-06-05 | 2025-06-05 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 11 | Allegheny | 117271 | SR 50 Signal Upgrades | 50 | A38 | Congestion Reduction | CON | CAQ | 2025-06-05 | 2025-06-05 | 2477791 | 424889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2902680
SPC | 11 | Allegheny | 117272 | Frankstown Avenue Signal Improvement Project |  |  | Congestion Reduction | CON | CAQ | 2027-02-25 |  | 0 | 0 | 1520143 | 1520143 | 0 | 0 | 0 | 0 | 0 | 3040286
SPC | 11 | Allegheny | 117272 | Frankstown Avenue Signal Improvement Project |  |  | Congestion Reduction | CON | LOC | 2027-02-25 |  | 0 | 0 | 380000 | 380000 | 0 | 0 | 0 | 0 | 0 | 760000
SPC | 11 | Allegheny | 117273 | SR 8 Signal Upgrades | 8 | A82 | Congestion Reduction | CON | CAQ | 2025-06-05 | 2025-06-05 | 824910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824910
SPC | 11 | Allegheny | 117274 | SR 286 Signal Upgrades | 286 | A17 | Congestion Reduction | PE | CAQ | 2025-06-05 | 2025-06-05 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Allegheny | 117274 | SR 286 Signal Upgrades | 286 | A17 | Congestion Reduction | CON | CAQ | 2025-06-05 | 2025-06-05 | 1656831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1656831
SPC | 11 | Allegheny | 117275 | PRT Transit Access Improvement Program |  |  | Public Transit | CON | TAU |  |  | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
SPC | 11 | Allegheny | 117275 | PRT Transit Access Improvement Program |  |  | Public Transit | CON | LOC |  |  | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000
SPC | 11 | Allegheny | 117365 | Maple Ave Bridge | 7301 | BR | Bridge Restoration | FD | BOF | 2027-08-26 |  | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 117365 | Maple Ave Bridge | 7301 | BR | Bridge Restoration | ROW | BOF | 2027-08-26 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 117365 | Maple Ave Bridge | 7301 | BR | Bridge Restoration | CON | BOF | 2027-08-26 |  | 0 | 0 | 0 | 0 | 3200000 | 0 | 0 | 0 | 0 | 3200000
SPC | 11 | Allegheny | 117365 | Maple Ave Bridge | 7301 | BR | Bridge Restoration | CON | 183 | 2027-08-26 |  | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 117365 | Maple Ave Bridge | 7301 | BR | Bridge Restoration | CON | LOC | 2027-08-26 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 117366 | Herron Ave Bridge Preservation | 7301 | 0 | Bridge Preservation - Federal | FD | BRIP | 2028-06-29 |  | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 11 | Allegheny | 117366 | Herron Ave Bridge Preservation | 7301 | 0 | Bridge Preservation - Federal | ROW | BRIP | 2028-06-29 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 117366 | Herron Ave Bridge Preservation | 7301 | 0 | Bridge Preservation - Federal | CON | BRIP | 2028-06-29 |  | 0 | 0 | 0 | 0 | 4800000 | 0 | 0 | 0 | 0 | 4800000
SPC | 11 | Allegheny | 117366 | Herron Ave Bridge Preservation | 7301 | 0 | Bridge Preservation - Federal | CON | 183 | 2028-06-29 |  | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 900000
SPC | 11 | Allegheny | 117366 | Herron Ave Bridge Preservation | 7301 | 0 | Bridge Preservation - Federal | CON | LOC | 2028-06-29 |  | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 117367 | Elizabeth St Bridge | 7301 | BR | Bridge Restoration | FD | BOF | 2028-06-29 |  | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
SPC | 11 | Allegheny | 117367 | Elizabeth St Bridge | 7301 | BR | Bridge Restoration | ROW | BOF | 2028-06-29 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 117367 | Elizabeth St Bridge | 7301 | BR | Bridge Restoration | CON | BRIP | 2028-06-29 |  | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 4000000
SPC | 11 | Allegheny | 117367 | Elizabeth St Bridge | 7301 | BR | Bridge Restoration | CON | 183 | 2028-06-29 |  | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 750000
SPC | 11 | Allegheny | 117367 | Elizabeth St Bridge | 7301 | BR | Bridge Restoration | CON | LOC | 2028-06-29 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 250000
SPC | 11 | Allegheny | 117368 | Corley St Bridge | 7301 | BR | Bridge Replacement | FD | BOF | 2027-12-09 |  | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 11 | Allegheny | 117368 | Corley St Bridge | 7301 | BR | Bridge Replacement | ROW | BOF | 2027-12-09 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 117368 | Corley St Bridge | 7301 | BR | Bridge Replacement | CON | BOF | 2027-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000
SPC | 11 | Allegheny | 117368 | Corley St Bridge | 7301 | BR | Bridge Replacement | CON | BRIP | 2027-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 0 | 0 | 3500000
SPC | 11 | Allegheny | 117368 | Corley St Bridge | 7301 | BR | Bridge Replacement | CON | 183 | 2027-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 750000
SPC | 11 | Allegheny | 117368 | Corley St Bridge | 7301 | BR | Bridge Replacement | CON | LOC | 2027-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 250000
SPC | 11 | Allegheny | 117369 | Calera St Bridge Replacement | 7301 | BR | Bridge Replacement | FD | BOF | 2028-08-10 |  | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
SPC | 11 | Allegheny | 117369 | Calera St Bridge Replacement | 7301 | BR | Bridge Replacement | ROW | BOF | 2028-08-10 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 117369 | Calera St Bridge Replacement | 7301 | BR | Bridge Replacement | CON | BOF | 2028-08-10 |  | 0 | 0 | 0 | 0 | 3200000 | 0 | 0 | 0 | 0 | 3200000
SPC | 11 | Allegheny | 117369 | Calera St Bridge Replacement | 7301 | BR | Bridge Replacement | CON | 183 | 2028-08-10 |  | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 117369 | Calera St Bridge Replacement | 7301 | BR | Bridge Replacement | CON | LOC | 2028-08-10 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 117472 | Bridge over Route 51 Near Woodruff Street | 51 | 17A | Bridge Removal | FD | BOF | 2024-04-18 | 2024-04-18 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
SPC | 11 | Allegheny | 117472 | Bridge over Route 51 Near Woodruff Street | 51 | 17A | Bridge Removal | FD | 183 | 2024-04-18 | 2024-04-18 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
SPC | 11 | Allegheny | 117472 | Bridge over Route 51 Near Woodruff Street | 51 | 17A | Bridge Removal | ROW | BOF | 2024-04-18 | 2024-04-18 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 117472 | Bridge over Route 51 Near Woodruff Street | 51 | 17A | Bridge Removal | ROW | 183 | 2024-04-18 | 2024-04-18 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Allegheny | 117472 | Bridge over Route 51 Near Woodruff Street | 51 | 17A | Bridge Removal | CON | BOF | 2024-04-18 | 2024-04-18 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 117472 | Bridge over Route 51 Near Woodruff Street | 51 | 17A | Bridge Removal | CON | 183 | 2024-04-18 | 2024-04-18 | 0 | 0 | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 117472 | Bridge over Route 51 Near Woodruff Street | 51 | 17A | Bridge Removal | CON | LOC | 2024-04-18 | 2024-04-18 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 117473 | Steen Road Bridge | 7102 | BR | Bridge Restoration | FD | BOF | 2027-04-15 |  | 400000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 117473 | Steen Road Bridge | 7102 | BR | Bridge Restoration | CON | BOF | 2027-04-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3200000 | 0 | 0 | 3200000
SPC | 11 | Allegheny | 117473 | Steen Road Bridge | 7102 | BR | Bridge Restoration | CON | 183 | 2027-04-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 600000
SPC | 11 | Allegheny | 117473 | Steen Road Bridge | 7102 | BR | Bridge Restoration | CON | LOC | 2027-04-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 200000
SPC | 11 | Allegheny | 117776 | Jacks Run Br 1 (JA01) Bridge Preservation | 7301 | 0 | Bridge Preservation - Federal | CON | BRIP | 2034-07-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8240000 | 8240000
SPC | 11 | Allegheny | 117776 | Jacks Run Br 1 (JA01) Bridge Preservation | 7301 | 0 | Bridge Preservation - Federal | CON | 183 | 2034-07-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1545000 | 1545000
SPC | 11 | Allegheny | 117776 | Jacks Run Br 1 (JA01) Bridge Preservation | 7301 | 0 | Bridge Preservation - Federal | CON | LOC | 2034-07-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515000 | 515000
SPC | 11 | Allegheny | 117889 | California Avenue Bridge | 7301 | LOC | Bridge Restoration | FD | BOF | 2027-11-04 |  | 0 | 1000000 | 450000 | 550000 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 11 | Allegheny | 117889 | California Avenue Bridge | 7301 | LOC | Bridge Restoration | ROW | BOF | 2027-11-04 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 117889 | California Avenue Bridge | 7301 | LOC | Bridge Restoration | CON | BOF | 2027-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18400000 | 18400000
SPC | 11 | Allegheny | 117889 | California Avenue Bridge | 7301 | LOC | Bridge Restoration | CON | 183 | 2027-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3450000 | 3450000
SPC | 11 | Allegheny | 117889 | California Avenue Bridge | 7301 | LOC | Bridge Restoration | CON | LOC | 2027-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000 | 1150000
SPC | 11 | Allegheny | 117911 | Wrong Way Detection System | 28 | A64 | Safety Improvement | CON | HSIP | 2024-05-23 | 2024-05-23 | 3150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3150000
SPC | 11 | Allegheny | 117911 | Wrong Way Detection System | 28 | A64 | Safety Improvement | CON | HSIP | 2024-05-23 | 2024-05-23 | 370000 | 507000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 877000
SPC | 11 | Allegheny | 118099 | Big Sewickley Creek No. 7 | 7212 | LOC | Bridge Replacement | FD | 183 | 2028-12-07 |  | 0 | 0 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 440000
SPC | 11 | Allegheny | 118099 | Big Sewickley Creek No. 7 | 7212 | LOC | Bridge Replacement | FD | LOC | 2028-12-07 |  | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
SPC | 11 | Allegheny | 118099 | Big Sewickley Creek No. 7 | 7212 | LOC | Bridge Replacement | ROW | 183 | 2028-12-07 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
SPC | 11 | Allegheny | 118099 | Big Sewickley Creek No. 7 | 7212 | LOC | Bridge Replacement | ROW | LOC | 2028-12-07 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
SPC | 11 | Allegheny | 118099 | Big Sewickley Creek No. 7 | 7212 | LOC | Bridge Replacement | CON | 183 | 2028-12-07 |  | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 1600000
SPC | 11 | Allegheny | 118099 | Big Sewickley Creek No. 7 | 7212 | LOC | Bridge Replacement | CON | LOC | 2028-12-07 |  | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 118315 | Summit Park Drive Bridge | 7214 | LOC | Bridge Restoration | FD | BOF | 2027-05-27 |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 11 | Allegheny | 118315 | Summit Park Drive Bridge | 7214 | LOC | Bridge Restoration | ROW | BOF | 2027-05-27 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 118315 | Summit Park Drive Bridge | 7214 | LOC | Bridge Restoration | UTL | BOF | 2027-05-27 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 118315 | Summit Park Drive Bridge | 7214 | LOC | Bridge Restoration | CON | BOF | 2027-05-27 |  | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 4000000
SPC | 11 | Allegheny | 118315 | Summit Park Drive Bridge | 7214 | LOC | Bridge Restoration | CON | 183 | 2027-05-27 |  | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 11 | Allegheny | 118315 | Summit Park Drive Bridge | 7214 | LOC | Bridge Restoration | CON | LOC | 2027-05-27 |  | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 11 | Allegheny | 118361 | MTF Sylvan Avenue Trail |  | LOC | MultiModal | CON | 411 | 2027-03-25 |  | 0 | 1763824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1763824
SPC | 11 | Allegheny | 118361 | MTF Sylvan Avenue Trail |  | LOC | MultiModal | CON | LOC | 2027-03-25 |  | 0 | 529147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529147
SPC | 11 | Allegheny | 118444 | SR 4012 (Highland) @ SR 4014 (Gass) Roundabout | 4012 | A14 | Safety Improvement | PE | HSIP | 2027-07-15 |  | 611100 | 38900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
SPC | 11 | Allegheny | 118444 | SR 4012 (Highland) @ SR 4014 (Gass) Roundabout | 4012 | A14 | Safety Improvement | PE | HSIP | 2027-07-15 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 11 | Allegheny | 118444 | SR 4012 (Highland) @ SR 4014 (Gass) Roundabout | 4012 | A14 | Safety Improvement | CON | HSIP | 2027-07-15 |  | 0 | 0 | 1211100 | 0 | 0 | 0 | 0 | 0 | 0 | 1211100
SPC | 11 | Allegheny | 118508 | Route 837 Transit Improvements |  |  | Public Transit | CON | TAP | 2050-01-01 |  | 960000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960000
SPC | 11 | Allegheny | 118570 | Skyline Drive Slide | 2042 | A07 | Safety Improvement | FD | STP | 2026-11-05 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 118570 | Skyline Drive Slide | 2042 | A07 | Safety Improvement | ROW | STP | 2026-11-05 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 118570 | Skyline Drive Slide | 2042 | A07 | Safety Improvement | UTL | STP | 2026-11-05 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 118570 | Skyline Drive Slide | 2042 | A07 | Safety Improvement | CON | 581 | 2026-11-05 |  | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 11 | Allegheny | 118571 | Ewings Mill Rd Slide | 3074 | A11 | Safety Improvement | FD | 581 | 2027-02-25 |  | 365005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365005
SPC | 11 | Allegheny | 118579 | AWPM 2025 | 8 | 0 | Safety Improvement | CON | 581 | 2025-02-13 | 2025-02-13 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 118708 | Beaver Avenue Esplanade (Two-Way Conversion) |  |  | Study Phase of Project | STUDY | STU | 2031-03-13 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Allegheny | 118708 | Beaver Avenue Esplanade (Two-Way Conversion) |  |  | Study Phase of Project | CON | STU | 2031-03-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8250000 | 8250000
SPC | 11 | Allegheny | 118768 | New Pathways to Equity - RAISE Grant |  |  | Transportation Enhancement | FD | RAISE | 2026-10-22 |  | 1040000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1040000
SPC | 11 | Allegheny | 118768 | New Pathways to Equity - RAISE Grant |  |  | Transportation Enhancement | CON | RAISE | 2026-10-22 |  | 0 | 9320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9320000
SPC | 11 | Allegheny | 118768 | New Pathways to Equity - RAISE Grant |  |  | Transportation Enhancement | CON | LOC | 2026-10-22 |  | 0 | 2330000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2330000
SPC | 11 | Allegheny | 118781 | Utilities Inspection |  |  | Planning/Research/Administration | UTL | 581 |  |  | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 118872 | 16th Street Bridge (AL05) | 7301 | 0 | Bridge Restoration | PE | NHPP | 2030-05-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720000 | 720000
SPC | 11 | Allegheny | 118872 | 16th Street Bridge (AL05) | 7301 | 0 | Bridge Restoration | PE | LOC | 2030-05-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000
SPC | 11 | Allegheny | 118872 | 16th Street Bridge (AL05) | 7301 | 0 | Bridge Restoration | CON | NHPP | 2030-05-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000000 | 16000000
SPC | 11 | Allegheny | 118872 | 16th Street Bridge (AL05) | 7301 | 0 | Bridge Restoration | CON | LOC | 2030-05-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
SPC | 11 | Allegheny | 118882 | Painters Run Road |  |  | Highway Reconstruction | CON | STU | 2033-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17350000 | 17350000
SPC | 11 | Allegheny | 118882 | Painters Run Road |  |  | Highway Reconstruction | CON | LOC | 2033-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400000 | 6400000
SPC | 11 | Allegheny | 118971 | Bridge Wash 2026 | 279 | 0 | Bridge Preservation - Federal | CON | 185 | 2026-04-09 |  | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 11 | Allegheny | 119169 | Smithfield Street Bridge Deck Replacement | 3027 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 5000000
SPC | 11 | Allegheny | 119183 | Route 8 at Wildwood | 8 | A81 | Congestion Reduction | CON | STP | 2027-07-22 |  | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000
SPC | 11 | Allegheny | 119187 | SR 4011 (Rochester) @ SR 4021 (Lowries) Roundabout | 4011 | A23 | Safety Improvement | PE | HSIP | 2027-07-15 |  | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
SPC | 11 | Allegheny | 119187 | SR 4011 (Rochester) @ SR 4021 (Lowries) Roundabout | 4011 | A23 | Safety Improvement | PE | HSIP | 2027-07-15 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 11 | Allegheny | 119187 | SR 4011 (Rochester) @ SR 4021 (Lowries) Roundabout | 4011 | A23 | Safety Improvement | ROW | HSIP | 2027-07-15 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 119187 | SR 4011 (Rochester) @ SR 4021 (Lowries) Roundabout | 4011 | A23 | Safety Improvement | CON | HSIP | 2027-07-15 |  | 0 | 0 | 1650000 | 0 | 0 | 0 | 0 | 0 | 0 | 1650000
SPC | 11 | Allegheny | 119262 | Fifth Ave Reconstruction |  | LOC | Highway Reconstruction | PE | STP | 2029-11-01 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 119262 | Fifth Ave Reconstruction |  | LOC | Highway Reconstruction | PE | LOC | 2029-11-01 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 119262 | Fifth Ave Reconstruction |  | LOC | Highway Reconstruction | FD | STP | 2029-11-01 |  | 0 | 0 | 0 | 720000 | 0 | 0 | 0 | 0 | 0 | 720000
SPC | 11 | Allegheny | 119262 | Fifth Ave Reconstruction |  | LOC | Highway Reconstruction | FD | LOC | 2029-11-01 |  | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000
SPC | 11 | Allegheny | 119262 | Fifth Ave Reconstruction |  | LOC | Highway Reconstruction | ROW | STP | 2029-11-01 |  | 0 | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 480000
SPC | 11 | Allegheny | 119262 | Fifth Ave Reconstruction |  | LOC | Highway Reconstruction | ROW | LOC | 2029-11-01 |  | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000
SPC | 11 | Allegheny | 119262 | Fifth Ave Reconstruction |  | LOC | Highway Reconstruction | CON | STP | 2029-11-01 |  | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 4000000
SPC | 11 | Allegheny | 119262 | Fifth Ave Reconstruction |  | LOC | Highway Reconstruction | CON | LOC | 2029-11-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
SPC | 11 | Allegheny | 119280 | D11 Carbon Reduction Program Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 0 | 0 | 0 | 0 | 1153000 | 1153000 | 1153000 | 4613000 | 8072000
SPC | 11 | Allegheny | 119281 | SPC Regional CRP/CRPU Line Item |  |  | Reserve Line Item | CON | CRPU |  |  | 155654 | 50000 | 3526000 | 4806000 | 4806000 | 4806000 | 4806000 | 4806000 | 19222000 | 46983654
SPC | 11 | Allegheny | 119343 | Banksville Road Resurfacing | 19 | A87 | Highway Restoration | PE | 581 | 2028-05-18 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 119343 | Banksville Road Resurfacing | 19 | A87 | Highway Restoration | CON | 581 | 2028-05-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16735000 | 16735000
SPC | 11 | Allegheny | 119359 | Grand Avenue/Neville Road |  |  | Highway Reconstruction | PE | STP | 2029-07-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 640000 | 0 | 0 | 640000
SPC | 11 | Allegheny | 119359 | Grand Avenue/Neville Road |  |  | Highway Reconstruction | PE | LOC | 2029-07-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 0 | 160000
SPC | 11 | Allegheny | 119359 | Grand Avenue/Neville Road |  |  | Highway Reconstruction | CON | STP | 2029-07-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5960000 | 5960000
SPC | 11 | Allegheny | 119359 | Grand Avenue/Neville Road |  |  | Highway Reconstruction | CON | LOC | 2029-07-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1490000 | 1490000
SPC | 11 | Allegheny | 119364 | Mission Street East Bridge | 7301 | BR | Bridge Restoration | PE | BOF | 413159 |  | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 119364 | Mission Street East Bridge | 7301 | BR | Bridge Restoration | CON | BOF | 413159 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4400000 | 0 | 0 | 4400000
SPC | 11 | Allegheny | 119364 | Mission Street East Bridge | 7301 | BR | Bridge Restoration | CON | 183 | 413159 |  | 0 | 0 | 0 | 0 | 0 | 0 | 825000 | 0 | 0 | 825000
SPC | 11 | Allegheny | 119364 | Mission Street East Bridge | 7301 | BR | Bridge Restoration | CON | LOC | 413159 |  | 0 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 0 | 275000
SPC | 11 | Allegheny | 119365 | Bloomfield Bridge | 7301 | 0 | Bridge Restoration | PE | BRIP | 2029-01-11 |  | 100000 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 900000
SPC | 11 | Allegheny | 119365 | Bloomfield Bridge | 7301 | 0 | Bridge Restoration | CON | BRIP | 2029-01-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6300000 | 6300000
SPC | 11 | Allegheny | 119367 | Hot Metal Bridge - Pittsburgh | 7301 | 0 | Bridge Restoration | CON | BOF | 2032-11-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17120000 | 17120000
SPC | 11 | Allegheny | 119367 | Hot Metal Bridge - Pittsburgh | 7301 | 0 | Bridge Restoration | CON | 183 | 2032-11-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3210000 | 3210000
SPC | 11 | Allegheny | 119367 | Hot Metal Bridge - Pittsburgh | 7301 | 0 | Bridge Restoration | CON | LOC | 2032-11-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1070000 | 1070000
SPC | 11 | Allegheny | 119371 | Universal Road Bridge over Union Railroad (BI01) | 7113 | BR | Bridge Restoration | CON | BRIP | 2029-12-13 |  | 0 | 0 | 0 | 0 | 3200000 | 0 | 0 | 0 | 0 | 3200000
SPC | 11 | Allegheny | 119371 | Universal Road Bridge over Union Railroad (BI01) | 7113 | BR | Bridge Restoration | CON | 183 | 2029-12-13 |  | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 119371 | Universal Road Bridge over Union Railroad (BI01) | 7113 | BR | Bridge Restoration | CON | LOC | 2029-12-13 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 119375 | PJ McArdle Roadway Over Sycamore | 7301 | BR | Bridge Restoration | CON | BRIP | 2028-07-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
SPC | 11 | Allegheny | 119375 | PJ McArdle Roadway Over Sycamore | 7301 | BR | Bridge Restoration | CON | 183 | 2028-07-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000
SPC | 11 | Allegheny | 119375 | PJ McArdle Roadway Over Sycamore | 7301 | BR | Bridge Restoration | CON | LOC | 2028-07-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
SPC | 11 | Allegheny | 119376 | PJ McArdle Roadway Over Hillside | 7301 | BR | Bridge Restoration | CON | BRIP | 2028-07-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3440000 | 3440000
SPC | 11 | Allegheny | 119376 | PJ McArdle Roadway Over Hillside | 7301 | BR | Bridge Restoration | CON | 183 | 2028-07-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 645000 | 645000
SPC | 11 | Allegheny | 119376 | PJ McArdle Roadway Over Hillside | 7301 | BR | Bridge Restoration | CON | LOC | 2028-07-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215000 | 215000
SPC | 11 | Allegheny | 119377 | Broad St Reconstruction - Euclid Ave to Centre Ave |  | LOC | Highway Reconstruction | PE | STU | 2030-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 800000
SPC | 11 | Allegheny | 119377 | Broad St Reconstruction - Euclid Ave to Centre Ave |  | LOC | Highway Reconstruction | CON | STU | 2030-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200000 | 7200000
SPC | 11 | Allegheny | 119399 | Grant Street Reconstruction, Ph. 1 |  |  | Highway Reconstruction | PE | STU | 2030-12-05 |  | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 1200000
SPC | 11 | Allegheny | 119399 | Grant Street Reconstruction, Ph. 1 |  |  | Highway Reconstruction | PE | LOC | 2030-12-05 |  | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 119399 | Grant Street Reconstruction, Ph. 1 |  |  | Highway Reconstruction | CON | STU | 2030-12-05 |  | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000 | 0 | 0 | 12000000
SPC | 11 | Allegheny | 119399 | Grant Street Reconstruction, Ph. 1 |  |  | Highway Reconstruction | CON | LOC | 2030-12-05 |  | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 0 | 0 | 3000000
SPC | 11 | Allegheny | 119400 | Smithfield Street Reconstruction, Ph. 2 |  |  | Highway Reconstruction | PE | STU |  |  | 0 | 0 | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 480000
SPC | 11 | Allegheny | 119400 | Smithfield Street Reconstruction, Ph. 2 |  |  | Highway Reconstruction | PE | LOC |  |  | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 120000
SPC | 11 | Allegheny | 119433 | Penn Avenue Reconstruction Phase 3 |  |  | Highway Reconstruction | PE | STU | 2030-12-25 |  | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 800000
SPC | 11 | Allegheny | 119433 | Penn Avenue Reconstruction Phase 3 |  |  | Highway Reconstruction | PE | LOC | 2030-12-25 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 119433 | Penn Avenue Reconstruction Phase 3 |  |  | Highway Reconstruction | CON | STP | 2030-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8240000 | 0 | 0 | 8240000
SPC | 11 | Allegheny | 119433 | Penn Avenue Reconstruction Phase 3 |  |  | Highway Reconstruction | CON | LOC | 2030-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2060000 | 0 | 0 | 2060000
SPC | 11 | Allegheny | 119440 | Pittsburgh SRTS Infrastructure Project |  | LOC | Bicycle and Pedestrian Facilities Transit | CON | TAP | 2024-12-12 | 2024-12-12 | 295000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000
SPC | 11 | Allegheny | 119486 | Pittsburgh City Steps - Potomac Avenue |  |  | Bicycle and Pedestrian Facilities Transit | PE | SXF | 2026-10-22 |  | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000
SPC | 11 | Allegheny | 119486 | Pittsburgh City Steps - Potomac Avenue |  |  | Bicycle and Pedestrian Facilities Transit | PE | LOC | 2026-10-22 |  | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000
SPC | 11 | Allegheny | 119486 | Pittsburgh City Steps - Potomac Avenue |  |  | Bicycle and Pedestrian Facilities Transit | FD | SXF | 2026-10-22 |  | 0 | 776000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776000
SPC | 11 | Allegheny | 119486 | Pittsburgh City Steps - Potomac Avenue |  |  | Bicycle and Pedestrian Facilities Transit | FD | LOC | 2026-10-22 |  | 0 | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194000
SPC | 11 | Allegheny | 119486 | Pittsburgh City Steps - Potomac Avenue |  |  | Bicycle and Pedestrian Facilities Transit | CON | SXF | 2026-10-22 |  | 140000 | 2064000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2204000
SPC | 11 | Allegheny | 119486 | Pittsburgh City Steps - Potomac Avenue |  |  | Bicycle and Pedestrian Facilities Transit | CON | TAU | 2026-10-22 |  | 0 | 896000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 896000
SPC | 11 | Allegheny | 119486 | Pittsburgh City Steps - Potomac Avenue |  |  | Bicycle and Pedestrian Facilities Transit | CON | LOC | 2026-10-22 |  | 35000 | 740000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775000
SPC | 11 | Allegheny | 119491 | Rodi Road Streetscape Phase 1 |  |  | Bicycle Pedestrian Highway | CON | SXF | 2026-09-17 |  | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SPC | 11 | Allegheny | 119491 | Rodi Road Streetscape Phase 1 |  |  | Bicycle Pedestrian Highway | CON | LOC | 2026-09-17 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | PE | BOF | 2027-09-30 |  | 80000 | 29200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109200
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | PE | 183 | 2027-09-30 |  | 15000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20475
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | PE | LOC | 2027-09-30 |  | 5000 | 1825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6825
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | FD | BOF | 2027-09-30 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | FD | 183 | 2027-09-30 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | FD | LOC | 2027-09-30 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | ROW | BOF | 2027-09-30 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | ROW | 183 | 2027-09-30 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | ROW | LOC | 2027-09-30 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | UTL | BOF | 2027-09-30 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | UTL | 183 | 2027-09-30 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | UTL | LOC | 2027-09-30 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | CON | BOF | 2027-09-30 |  | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | CON | 183 | 2027-09-30 |  | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
SPC | 11 | Allegheny | 119502 | Lincoln Avenue Bridge #7 Replacement | 7445 | LOC | Bridge Replacement | CON | LOC | 2027-09-30 |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Allegheny | 119595 | SR 4003 - Nelson Run to Perrymont Signal Project | 4003 | A26 | Safety Improvement | CON | CRP | 2026-07-02 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 119595 | SR 4003 - Nelson Run to Perrymont Signal Project | 4003 | A26 | Safety Improvement | CON | STP | 2026-07-02 |  | 0 | 2699104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2699104
SPC | 11 | Allegheny | 119595 | SR 4003 - Nelson Run to Perrymont Signal Project | 4003 | A26 | Safety Improvement | CON | STU | 2026-07-02 |  | 0 | 2675000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2675000
SPC | 11 | Allegheny | 119595 | SR 4003 - Nelson Run to Perrymont Signal Project | 4003 | A26 | Safety Improvement | CON | 581 | 2026-07-02 |  | 0 | 1343526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1343526
SPC | 11 | Allegheny | 119603 | McKeesport Bridge Ramp #1 | 2027 | 0 | Bridge Replacement | PE | BOF | 2028-04-15 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 119603 | McKeesport Bridge Ramp #1 | 2027 | 0 | Bridge Replacement | CON | BRIP | 2028-04-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000
SPC | 11 | Allegheny | 119607 | Tenth Street Bypass Road Reconstruction | 2128 | 0 | Highway Reconstruction | PE | 581 | 2032-09-13 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 119607 | Tenth Street Bypass Road Reconstruction | 2128 | 0 | Highway Reconstruction | CON | STP | 2032-09-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200000 | 3200000
SPC | 11 | Allegheny | 119607 | Tenth Street Bypass Road Reconstruction | 2128 | 0 | Highway Reconstruction | CON | STU | 2032-09-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200000 | 3200000
SPC | 11 | Allegheny | 119607 | Tenth Street Bypass Road Reconstruction | 2128 | 0 | Highway Reconstruction | CON | 581 | 2032-09-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 1600000
SPC | 11 | Allegheny | 119847 | Bocktown Road ov Shouse Run | 3094 | 0 | Bridge Replacement | PE | 185 | 2031-06-19 |  | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Allegheny | 119847 | Bocktown Road ov Shouse Run | 3094 | 0 | Bridge Replacement | CON | 185 | 2031-06-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
SPC | 11 | Allegheny | 119924 | I-279 Southbound Off-Ramp to East Street | 8099 | A01 | Safety Improvement | PE | CAQ | 2027-02-11 |  | 0 | 198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198000
SPC | 11 | Allegheny | 119924 | I-279 Southbound Off-Ramp to East Street | 8099 | A01 | Safety Improvement | PE | 581 | 2027-02-11 |  | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000
SPC | 11 | Allegheny | 119924 | I-279 Southbound Off-Ramp to East Street | 8099 | A01 | Safety Improvement | CON | CAQ | 2027-02-11 |  | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 280000
SPC | 11 | Allegheny | 119924 | I-279 Southbound Off-Ramp to East Street | 8099 | A01 | Safety Improvement | CON | 581 | 2027-02-11 |  | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
SPC | 11 | Allegheny | 119931 | Babcock Blvd Betterment-Rochester to Three Degree |  |  | Highway Restoration | PE | STU | 2030-12-05 |  | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 119931 | Babcock Blvd Betterment-Rochester to Three Degree |  |  | Highway Restoration | PE | LOC | 2030-12-05 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 11 | Allegheny | 119931 | Babcock Blvd Betterment-Rochester to Three Degree |  |  | Highway Restoration | CON | STU | 2030-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000000 | 0 | 12000000
SPC | 11 | Allegheny | 119931 | Babcock Blvd Betterment-Rochester to Three Degree |  |  | Highway Restoration | CON | LOC | 2030-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 3000000
SPC | 11 | Allegheny | 119941 | SR 8 and Sandy Hill Road Widening Project | 8 | A83 | Congestion Reduction | PE | CRPU | 2027-12-09 |  | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000
SPC | 11 | Allegheny | 119941 | SR 8 and Sandy Hill Road Widening Project | 8 | A83 | Congestion Reduction | PE | 581 | 2027-12-09 |  | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
SPC | 11 | Allegheny | 119941 | SR 8 and Sandy Hill Road Widening Project | 8 | A83 | Congestion Reduction | ROW | CRPU | 2027-12-09 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 119941 | SR 8 and Sandy Hill Road Widening Project | 8 | A83 | Congestion Reduction | ROW | 581 | 2027-12-09 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 11 | Allegheny | 119941 | SR 8 and Sandy Hill Road Widening Project | 8 | A83 | Congestion Reduction | UTL | CRPU | 2027-12-09 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Allegheny | 119941 | SR 8 and Sandy Hill Road Widening Project | 8 | A83 | Congestion Reduction | UTL | 581 | 2027-12-09 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 11 | Allegheny | 119941 | SR 8 and Sandy Hill Road Widening Project | 8 | A83 | Congestion Reduction | CON | CRPU | 2027-12-09 |  | 0 | 0 | 1280000 | 0 | 0 | 0 | 0 | 0 | 0 | 1280000
SPC | 11 | Allegheny | 119941 | SR 8 and Sandy Hill Road Widening Project | 8 | A83 | Congestion Reduction | CON | 581 | 2027-12-09 |  | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
SPC | 11 | Allegheny | 119945 | SR 3010 @ Patterson Road Roundabout | 3010 | A03 | Safety Improvement | PE | HSIP | 2028-05-18 |  | 513591 | 136409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
SPC | 11 | Allegheny | 119945 | SR 3010 @ Patterson Road Roundabout | 3010 | A03 | Safety Improvement | CON | HSIP | 2028-05-18 |  | 0 | 0 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 1350000
SPC | 11 | Allegheny | 119950 | Centre Avenue, Avenues of Hope |  |  | Bicycle Pedestrian Highway | PE | STU | 2030-12-25 |  | 0 | 0 | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 480000
SPC | 11 | Allegheny | 119950 | Centre Avenue, Avenues of Hope |  |  | Bicycle Pedestrian Highway | CON | STP | 2030-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800000 | 0 | 4800000
SPC | 11 | Allegheny | 119951 | Irvine Street Reconstruction | 885 | 0 | Bicycle Pedestrian Highway | PE | STU | 2030-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 360000 | 0 | 0 | 360000
SPC | 11 | Allegheny | 119951 | Irvine Street Reconstruction | 885 | 0 | Bicycle Pedestrian Highway | CON | STU | 2030-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000 | 2400000
SPC | 11 | Allegheny | 119986 | CC03 Chartiers Creek Br #3 | 7421 | 0 | Bridge Restoration | PE | BOF | 2030-05-16 |  | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 480000
SPC | 11 | Allegheny | 119986 | CC03 Chartiers Creek Br #3 | 7421 | 0 | Bridge Restoration | PE | 183 | 2030-05-16 |  | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
SPC | 11 | Allegheny | 119986 | CC03 Chartiers Creek Br #3 | 7421 | 0 | Bridge Restoration | PE | LOC | 2030-05-16 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SPC | 11 | Allegheny | 119986 | CC03 Chartiers Creek Br #3 | 7421 | 0 | Bridge Restoration | CON | BOF | 2030-05-16 |  | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 2000000
SPC | 11 | Allegheny | 120039 | Bridge Demand Mtc 18, 26 | 28 | 0 | General Maintenance | CON | 185 | 2026-03-12 | 2026-03-12 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Allegheny | 120079 | Old William Penn Highway Landslide |  |  | Safety Improvement | CON | SXF | 2027-08-12 |  | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SPC | 11 | Allegheny | 120079 | Old William Penn Highway Landslide |  |  | Safety Improvement | CON | LOC | 2027-08-12 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 120080 | Camp Meeting Road FSRTS |  |  | Federal Safe Routes to Schools | PE | LOC | 2027-01-14 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 120080 | Camp Meeting Road FSRTS |  |  | Federal Safe Routes to Schools | CON | SXF | 2027-01-14 |  | 0 | 0 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 850000
SPC | 11 | Allegheny | 120080 | Camp Meeting Road FSRTS |  |  | Federal Safe Routes to Schools | CON | LOC | 2027-01-14 |  | 0 | 0 | 212500 | 0 | 0 | 0 | 0 | 0 | 0 | 212500
SPC | 11 | Allegheny | 120128 | 2026 ADA Curb Ramp Project |  |  | Safety Improvement | PE | 581 | 2026-09-03 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 120128 | 2026 ADA Curb Ramp Project |  |  | Safety Improvement | CON | STP | 2026-09-03 |  | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 11 | Allegheny | 120212 | Consultant Services for Local Project Management |  |  | Planning/Research/Administration | PE | 581 | 2050-12-25 |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 11 | Allegheny | 120370 | TMA TDM Programming & Outreach 25-26 |  |  | Planning/Research/Administration | PRA | CAQ |  |  | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 120370 | TMA TDM Programming & Outreach 25-26 |  |  | Planning/Research/Administration | PRA | LOC |  |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 11 | Allegheny | 120371 | MTF Logan Street Improvement |  | MTF | MultiModal | CON | 411 | 2028-06-22 |  | 0 | 623150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623150
SPC | 11 | Allegheny | 120371 | MTF Logan Street Improvement |  | MTF | MultiModal | CON | LOC | 2028-06-22 |  | 0 | 186945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186945
SPC | 11 | Allegheny | 120892 | POGOH Expansion Phase 3 |  |  | Bicycle Pedestrian Highway | PE | CAQ | 2050-12-25 |  | 0 | 3200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200000
SPC | 11 | Allegheny | 120892 | POGOH Expansion Phase 3 |  |  | Bicycle Pedestrian Highway | PE | PRIV | 2050-12-25 |  | 0 | 1995000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995000
SPC | 11 | Allegheny | 120898 | University Line Oakland to Squirrel Hill BRT |  |  | Public Transit | CON | CAQ | 2050-12-25 |  | 0 | 0 | 0 | 7418300 | 0 | 0 | 0 | 0 | 0 | 7418300
SPC | 11 | Allegheny | 120898 | University Line Oakland to Squirrel Hill BRT |  |  | Public Transit | CON | LOC | 2050-12-25 |  | 0 | 0 | 0 | 132378 | 0 | 0 | 0 | 0 | 0 | 132378
SPC | 11 | Allegheny | 120899 | Brownsville Road Safety Improvement |  |  | Safety Improvement | PE | CAQ | 2029-04-12 |  | 0 | 388866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388866
SPC | 11 | Allegheny | 120899 | Brownsville Road Safety Improvement |  |  | Safety Improvement | PE | LOC | 2029-04-12 |  | 0 | 97216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97216
SPC | 11 | Allegheny | 120899 | Brownsville Road Safety Improvement |  |  | Safety Improvement | FD | CAQ | 2029-04-12 |  | 0 | 0 | 560000 | 0 | 0 | 0 | 0 | 0 | 0 | 560000
SPC | 11 | Allegheny | 120899 | Brownsville Road Safety Improvement |  |  | Safety Improvement | FD | LOC | 2029-04-12 |  | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
SPC | 11 | Allegheny | 120899 | Brownsville Road Safety Improvement |  |  | Safety Improvement | CON | CAQ | 2029-04-12 |  | 0 | 0 | 0 | 0 | 2654629 | 0 | 0 | 0 | 0 | 2654629
SPC | 11 | Allegheny | 120899 | Brownsville Road Safety Improvement |  |  | Safety Improvement | CON | 244 | 2029-04-12 |  | 0 | 0 | 0 | 0 | 545267 | 0 | 0 | 0 | 0 | 545267
SPC | 11 | Allegheny | 120899 | Brownsville Road Safety Improvement |  |  | Safety Improvement | CON | LOC | 2029-04-12 |  | 0 | 0 | 0 | 118390 | 0 | 0 | 0 | 0 | 0 | 118390
SPC | 11 | Allegheny | 120901 | East Liberty - Negley Avenue Implementation |  | TAP | Safety Improvement | CON | TAP | 2027-01-08 |  | 0 | 0 | 1071661 | 0 | 0 | 0 | 0 | 0 | 0 | 1071661
SPC | 11 | Allegheny | 120901 | East Liberty - Negley Avenue Implementation |  | TAP | Safety Improvement | CON | TAU | 2027-01-08 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 11 | Allegheny | 120905 | Microtransit Pilot Project |  |  | Public Transit | CON | CAQ | 2027-02-11 |  | 0 | 0 | 0 | 3971582 | 0 | 0 | 0 | 0 | 0 | 3971582
SPC | 11 | Allegheny | 120905 | Microtransit Pilot Project |  |  | Public Transit | CON | LOC | 2027-02-11 |  | 0 | 0 | 0 | 614783 | 0 | 0 | 0 | 0 | 0 | 614783
SPC | 11 | Allegheny | 120907 | Fairview Park Trail Network |  |  | Bicycle Pedestrian Highway | CON | TAU | 2026-08-13 |  | 0 | 947060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 947060
SPC | 11 | Allegheny | 120907 | Fairview Park Trail Network |  |  | Bicycle Pedestrian Highway | CON | LOC | 2026-08-13 |  | 0 | 853300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 853300
SPC | 11 | Allegheny | 120987 | Liberty Tunnel Roof Replacement | 3069 | A27 | Highway Restoration | CON | NHPP | 2024-08-22 | 2024-08-22 | 0 | 2139792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2139792
SPC | 11 | Allegheny | 120987 | Liberty Tunnel Roof Replacement | 3069 | A27 | Highway Restoration | CON | 581 | 2024-08-22 | 2024-08-22 | 0 | 507117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 507117
SPC | 11 | Allegheny | 121076 | McKeesport Bridge Ramp #2 | 7304 | 0 | Bridge Replacement | PE | BRIP | 2028-04-15 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Allegheny | 121076 | McKeesport Bridge Ramp #2 | 7304 | 0 | Bridge Replacement | CON | BOF | 2028-04-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000
SPC | 11 | Allegheny | 121099 | Clairton Blvd Flood Control -Century III to Coal V | 51 | 21A | Stormwater Management | STUDY | PRTCT | 2029-05-10 |  | 500000 | 625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1125000
SPC | 11 | Allegheny | 121102 | Lebanon Church Road Flood Control - Lebanon School | 2040 | A29 | Study Phase of Project | STUDY | PRTCT | 2050-12-25 |  | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
SPC | 11 | Allegheny | 121295 | Pittsburgh City Steps- Clairhaven Street |  |  | Bicycle and Pedestrian Facilities Transit | CON | SXF | 2026-10-22 |  | 0 | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520000
SPC | 11 | Allegheny | 121295 | Pittsburgh City Steps- Clairhaven Street |  |  | Bicycle and Pedestrian Facilities Transit | CON | LOC | 2026-10-22 |  | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000
SPC | 11 | Allegheny | 121296 | Pittsburgh City Steps - Dickson Street |  |  | Bicycle and Pedestrian Facilities Transit | CON | SXF | 2026-10-22 |  | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SPC | 11 | Allegheny | 121296 | Pittsburgh City Steps - Dickson Street |  |  | Bicycle and Pedestrian Facilities Transit | CON | LOC | 2026-10-22 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 121297 | Pittsburgh City Steps - Ottawa Street |  |  | Bicycle and Pedestrian Facilities Transit | CON | SXF | 2026-10-22 |  | 0 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440000
SPC | 11 | Allegheny | 121297 | Pittsburgh City Steps - Ottawa Street |  |  | Bicycle and Pedestrian Facilities Transit | CON | LOC | 2026-10-22 |  | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
SPC | 11 | Allegheny | 121298 | Pittsburgh City Steps - 56th Street Connection |  |  | Bicycle and Pedestrian Facilities Transit | CON | SXF | 2026-10-22 |  | 0 | 1720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1720000
SPC | 11 | Allegheny | 121298 | Pittsburgh City Steps - 56th Street Connection |  |  | Bicycle and Pedestrian Facilities Transit | CON | LOC | 2026-10-22 |  | 0 | 430000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430000
SPC | 11 | Allegheny | 121377 | POHC LED Upgrades |  |  | Archaeological Activities | CON | RRX |  |  | 0 | 0 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 95000
SPC | 11 | Allegheny | 121378 | W&LE Corridor |  | RRX | Rail Highway Grade Crossing | CON | RRX | 2027-08-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825390 | 0 | 825390
SPC | 11 | Allegheny | 121379 | URR Penn Ave Ext Crossing |  | RRX | Rail Highway Grade Crossing | CON | RRX | 2029-08-01 |  | 0 | 0 | 0 | 0 | 0 | 161500 | 0 | 0 | 0 | 161500
SPC | 11 | Allegheny | 121415 | Mountain View Road Slide Repair | 1024 | A03 | Safety Improvement | CON | 581 | 2026-09-03 |  | 0 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
SPC | 11 | Allegheny | 121430 | Safety Action Plan for Allegheny County |  |  | Study Phase of Project | STUDY | 581 |  |  | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000
SPC | 11 | Allegheny | 121447 | MLK Jr. East Busway - Hard Shoulder Running MPDG |  |  | Public Transit | STUDY | 581 | 2029-03-01 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 11 | Allegheny | 121452 | Arterial Traffic Management MPDG | 30 | A42 | Safety Improvement | PE | 581 | 2029-01-11 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 121504 | Bike Light/Helmet Give-Away and Education Program |  | TAP | Bicycle and Pedestrian Education (K-8 only) | PRA | SRTSF | 2050-12-25 |  | 38500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44000
SPC | 11 | Allegheny | 121505 | Browns Lane and McKnight Road Sidewalk Connector |  | TAP | Bicycle and Pedestrian Facilities Transit | CON | TAP | 2027-03-25 |  | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 121556 | SR 3081 (Montour Street Extension) Slide | 3081 | A07 | Safety Improvement | CON | STP | 2026-08-13 |  | 0 | 1000000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 1360000
SPC | 11 | Allegheny | 121556 | SR 3081 (Montour Street Extension) Slide | 3081 | A07 | Safety Improvement | CON | 581 | 2026-08-13 |  | 0 | 250000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 340000
SPC | 11 | Allegheny | 121632 | SR 48, Long Run Road Slide | 48 | A47 | Safety Improvement | CON | NHPP | 2026-08-27 |  | 0 | 900000 | 1050000 | 0 | 0 | 0 | 0 | 0 | 0 | 1950000
SPC | 11 | Allegheny | 121742 | Penn Ave Cap Connector Project - RCP |  | LOC | Safety Improvement | STUDY | RCP | 2030-12-12 |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 11 | Allegheny | 121742 | Penn Ave Cap Connector Project - RCP |  | LOC | Safety Improvement | STUDY | LOC | 2030-12-12 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 121743 | Regional Connector and Flyover Bridge (RAISE) |  |  | New Bridge | PE | LOC | 2028-10-05 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 121791 | Allegheny River Blvd. @ Sandy Creek Intersection | 130 | 0 | Safety Improvement | STUDY | 581 | 2030-12-05 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 122137 | Constructability Review for Local Projects |  |  | Planning/Research/Administration | FD | 581 |  |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Allegheny | 122148 | MTF Brentwood Pedestrian and Safety |  | MTF | MultiModal | CON | 411 | 2050-12-25 |  | 591300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591300
SPC | 11 | Allegheny | 122148 | MTF Brentwood Pedestrian and Safety |  | MTF | MultiModal | CON | LOC | 2050-12-25 |  | 191250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250
SPC | 11 | Allegheny | 122149 | MTF - Coraopolis Borough Central Business District |  | MTF | MultiModal | FD | 411 | 2030-12-25 |  | 28370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28370
SPC | 11 | Allegheny | 122149 | MTF - Coraopolis Borough Central Business District |  | MTF | MultiModal | FD | LOC | 2030-12-25 |  | 32500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32500
SPC | 11 | Allegheny | 122149 | MTF - Coraopolis Borough Central Business District |  | MTF | MultiModal | CON | 411 | 2030-12-25 |  | 346630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346630
SPC | 11 | Allegheny | 122149 | MTF - Coraopolis Borough Central Business District |  | MTF | MultiModal | CON | LOC | 2030-12-25 |  | 292500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292500
SPC | 11 | Allegheny | 122150 | MTF - SEA Pittsburgh Sidewalk Repairs |  | MTF | General Maintenance | CON | 411 | 2050-12-25 |  | 260306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260306
SPC | 11 | Allegheny | 122150 | MTF - SEA Pittsburgh Sidewalk Repairs |  | MTF | General Maintenance | CON | OTH | 2050-12-25 |  | 68569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68569
SPC | 11 | Allegheny | 122165 | Equitably Empowering EV Ownership - CFI |  | LOC | Electric Vehicle Charging Infrastructure | CON | CFI | 2050-12-25 |  | 0 | 2396406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2396406
SPC | 11 | Allegheny | 122165 | Equitably Empowering EV Ownership - CFI |  | LOC | Electric Vehicle Charging Infrastructure | CON | LOC | 2050-12-25 |  | 0 | 599102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 599102
SPC | 11 | Allegheny | 122288 | Country Club Dr over SR 19 Rehabilitation | 3002 | A02 | Bridge Restoration | PE | 185 | 2025-09-25 | 2025-09-25 | 725000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 725000
SPC | 11 | Allegheny | 122288 | Country Club Dr over SR 19 Rehabilitation | 3002 | A02 | Bridge Restoration | CON | BOF | 2025-09-25 | 2025-09-25 | 2900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2900000
SPC | 11 | Allegheny | 122514 | Bridge Street Bridge Over Thoms Run | 7119 | BR | Bridge Replacement | PE | BOF | 2028-10-01 |  | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SPC | 11 | Allegheny | 122648 | Connie Drive Landslide Repair | 279 | A91 | Safety Improvement | PE | 581 | 2027-07-01 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 11 | Allegheny | 122648 | Connie Drive Landslide Repair | 279 | A91 | Safety Improvement | ROW | 581 | 2027-07-01 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Allegheny | 122648 | Connie Drive Landslide Repair | 279 | A91 | Safety Improvement | CON | 581 | 2027-07-01 |  | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SPC | 11 | Allegheny | 122851 | (PD03) Jacks Run Road Bridge Replacement | 7116 | BRG | Bridge Replacement | CON | BOF | 2026-07-16 |  | 2521688 | 3478312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000
SPC | 11 | Allegheny | 122903 | VRU HSIP School Zone 2026 | 19 | 0 | Safety Improvement | CON | HVRU | 2026-02-26 | 2026-02-26 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SPC | 11 | Allegheny | 122904 | HSIP Lane Departure and HFST 2026 | 22 | 0 | Safety Improvement | CON | HSIP | 2026-02-26 | 2026-02-26 | 0 | 3462827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3462827
SPC | 11 | Allegheny | 122974 | P.J. McArdle Roadway Reconstruction |  | LOC | Highway Reconstruction | PE | STU | 2028-07-27 |  | 0 | 960000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960000
SPC | 11 | Allegheny | 122974 | P.J. McArdle Roadway Reconstruction |  | LOC | Highway Reconstruction | PE | LOC | 2028-07-27 |  | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
SPC | 11 | Allegheny | 123006 | Scott/Carnegie Flood Mitigation | 50 | A39 | Stormwater Management | PE | PRTCT | 2029-01-18 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Allegheny | 123006 | Scott/Carnegie Flood Mitigation | 50 | A39 | Stormwater Management | FD | PRTCT | 2029-01-18 |  | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 11 | Allegheny | 123006 | Scott/Carnegie Flood Mitigation | 50 | A39 | Stormwater Management | ROW | PRTCT | 2029-01-18 |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 11 | Allegheny | 123006 | Scott/Carnegie Flood Mitigation | 50 | A39 | Stormwater Management | UTL | PRTCT | 2029-01-18 |  | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Allegheny | 123006 | Scott/Carnegie Flood Mitigation | 50 | A39 | Stormwater Management | CON | PRTCT | 2029-01-18 |  | 0 | 0 | 0 | 0 | 3000000 | 3000000 | 0 | 0 | 0 | 6000000
SPC | 11 | Allegheny | 123285 | (PD03) Jacks Run Road Bridge Demolition | 7116 | BRG | Bridge Removal | CON | BOF | 2026-02-26 | 2026-02-26 | 0 | 3735000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3735000
SPC | 11 | Allegheny | 123820 | HSIP 2027 VRU Signal Pedestrian Improvements |  |  | Safety Improvement | FD | HVRU | 2027-01-28 |  | 0 | 525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000
SPC | 11 | Allegheny | 123877 | 2026 NFL Draft Transportation Management Plan |  |  | General Maintenance | PE | 582 |  |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Beaver | 28918 | SR 4042, Old Rochester-Bridgewater Rd Bridge | 4042 | B03 | Bridge Restoration | FD | 185 | 2027-04-15 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Beaver | 28918 | SR 4042, Old Rochester-Bridgewater Rd Bridge | 4042 | B03 | Bridge Restoration | ROW | 185 | 2027-04-15 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Beaver | 28918 | SR 4042, Old Rochester-Bridgewater Rd Bridge | 4042 | B03 | Bridge Restoration | UTL | 185 | 2027-04-15 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Beaver | 28918 | SR 4042, Old Rochester-Bridgewater Rd Bridge | 4042 | B03 | Bridge Restoration | CON | BRIP | 2027-04-15 |  | 0 | 0 | 0 | 0 | 4880000 | 0 | 0 | 0 | 0 | 4880000
SPC | 11 | Beaver | 28918 | SR 4042, Old Rochester-Bridgewater Rd Bridge | 4042 | B03 | Bridge Restoration | CON | 185 | 2027-04-15 |  | 0 | 0 | 0 | 0 | 1220000 | 0 | 0 | 0 | 0 | 1220000
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | PE | BRIP | 2027-04-01 |  | 92000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | PE | 183 | 2027-04-01 |  | 17250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17250
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | PE | LOC | 2027-04-01 |  | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | FD | BRIP | 2027-04-01 |  | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | FD | 183 | 2027-04-01 |  | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | FD | LOC | 2027-04-01 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | ROW | BRIP | 2027-04-01 |  | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | ROW | 183 | 2027-04-01 |  | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | ROW | LOC | 2027-04-01 |  | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | UTL | BRIP | 2027-04-01 |  | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | UTL | 183 | 2027-04-01 |  | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | UTL | LOC | 2027-04-01 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | CON | BRIP | 2027-04-01 |  | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 1200000
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | CON | 183 | 2027-04-01 |  | 0 | 0 | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 225000
SPC | 11 | Beaver | 28974 | Loughheads Bridge (CB #9) | 7201 | LOC | Bridge Replacement | CON | LOC | 2027-04-01 |  | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 75000
SPC | 11 | Beaver | 35156 | PA 65, Country Club Bridge | 65 | B33 | Bridge Replacement | FD | 185 | 2025-12-04 | 2025-12-04 | 110116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110116
SPC | 11 | Beaver | 35156 | PA 65, Country Club Bridge | 65 | B33 | Bridge Replacement | ROW | 185 | 2025-12-04 | 2025-12-04 | 235000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235000
SPC | 11 | Beaver | 35156 | PA 65, Country Club Bridge | 65 | B33 | Bridge Replacement | CON | BRIP | 2025-12-04 | 2025-12-04 | 0 | 6668600 | 1946400 | 0 | 0 | 0 | 0 | 0 | 0 | 8615000
SPC | 11 | Beaver | 35156 | PA 65, Country Club Bridge | 65 | B33 | Bridge Replacement | CON | 185 | 2025-12-04 | 2025-12-04 | 0 | 1667150 | 486600 | 0 | 0 | 0 | 0 | 0 | 0 | 2153750
SPC | 11 | Beaver | 67016 | Freedom Rd Upgrade - Ph C | 2004 | B06 | Highway Reconstruction | CON | STP | 2021-09-30 | 2021-09-30 | 1600000 | 652089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2252089
SPC | 11 | Beaver | 70793 | Georgetown Br over PA 51 | 4053 | B01 | Bridge Restoration | FD | 185 | 2027-03-31 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Beaver | 70793 | Georgetown Br over PA 51 | 4053 | B01 | Bridge Restoration | ROW | 185 | 2027-03-31 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Beaver | 70793 | Georgetown Br over PA 51 | 4053 | B01 | Bridge Restoration | UTL | 185 | 2027-03-31 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Beaver | 70793 | Georgetown Br over PA 51 | 4053 | B01 | Bridge Restoration | CON | BOF | 2027-03-31 |  | 0 | 0 | 0 | 0 | 0 | 2400000 | 0 | 0 | 0 | 2400000
SPC | 11 | Beaver | 70793 | Georgetown Br over PA 51 | 4053 | B01 | Bridge Restoration | CON | 185 | 2027-03-31 |  | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 600000
SPC | 11 | Beaver | 78311 | Shenango Road over Wallace Run | 4017 | 0 | Bridge Replacement | PE | 185 | 2032-12-25 |  | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 300000
SPC | 11 | Beaver | 78311 | Shenango Road over Wallace Run | 4017 | 0 | Bridge Replacement | CON | 185 | 2032-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
SPC | 11 | Beaver | 78326 | Chapel Drive ov Brush Creek | 1005 | B04 | Bridge Replacement | PE | 185 | 2029-06-14 |  | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 450000
SPC | 11 | Beaver | 78326 | Chapel Drive ov Brush Creek | 1005 | B04 | Bridge Replacement | CON | 185 | 2029-06-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5700000 | 0 | 5700000
SPC | 11 | Beaver | 89157 | Reno Street over Dutchmans Run | 1037 | B04 | Bridge Replacement | PE | 185 | 2025-09-11 | 2025-09-11 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Beaver | 89157 | Reno Street over Dutchmans Run | 1037 | B04 | Bridge Replacement | CON | 185 | 2025-09-11 | 2025-09-11 | 0 | 1410000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1410000
SPC | 11 | Beaver | 93770 | Pine Run Road Culvert | 1021 | B02 | Bridge Replacement | ROW | 185 | 2025-10-23 | 2025-10-23 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Beaver | 93770 | Pine Run Road Culvert | 1021 | B02 | Bridge Replacement | CON | 185 | 2025-10-23 | 2025-10-23 | 0 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000
SPC | 11 | Beaver | 93770 | Pine Run Road Culvert | 1021 | B02 | Bridge Replacement | CON | 581 | 2025-10-23 | 2025-10-23 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 11 | Beaver | 99795 | Brush Ck Br/BrBrush Ck | 1019 | B01 | Bridge Replacement | PE | 185 | 2028-05-11 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Beaver | 99795 | Brush Ck Br/BrBrush Ck | 1019 | B01 | Bridge Replacement | FD | 185 | 2028-05-11 |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Beaver | 99795 | Brush Ck Br/BrBrush Ck | 1019 | B01 | Bridge Replacement | CON | 185 | 2028-05-11 |  | 0 | 0 | 0 | 0 | 1100000 | 0 | 0 | 0 | 0 | 1100000
SPC | 11 | Beaver | 101165 | Frankfort Road Bridge | 18 | B61 | Bridge Replacement | CON | BRIP | 2024-11-07 | 2024-11-07 | 9128000 | 4824303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13952303
SPC | 11 | Beaver | 101173 | PA 168 over Jordan Run | 168 | B20 | Bridge Replacement | FD | 185 | 2026-12-03 |  | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SPC | 11 | Beaver | 101173 | PA 168 over Jordan Run | 168 | B20 | Bridge Replacement | ROW | 185 | 2026-12-03 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Beaver | 101173 | PA 168 over Jordan Run | 168 | B20 | Bridge Replacement | UTL | 185 | 2026-12-03 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Beaver | 101173 | PA 168 over Jordan Run | 168 | B20 | Bridge Replacement | CON | 185 | 2026-12-03 |  | 0 | 0 | 2500000 | 0 | 500000 | 0 | 0 | 0 | 0 | 3000000
SPC | 11 | Beaver | 101182 | Brush Creek Road Bridge | 1019 | B02 | Bridge Replacement | PE | 185 | 2030-12-12 |  | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Beaver | 101182 | Brush Creek Road Bridge | 1019 | B02 | Bridge Replacement | CON | 185 | 2030-12-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000 | 0 | 1100000
SPC | 11 | Beaver | 101198 | Shenango Road Bridge | 4021 | B05 | Bridge Replacement | FD | BOF | 2027-04-15 |  | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000
SPC | 11 | Beaver | 101198 | Shenango Road Bridge | 4021 | B05 | Bridge Replacement | FD | 185 | 2027-04-15 |  | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
SPC | 11 | Beaver | 101198 | Shenango Road Bridge | 4021 | B05 | Bridge Replacement | ROW | BOF | 2027-04-15 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Beaver | 101198 | Shenango Road Bridge | 4021 | B05 | Bridge Replacement | ROW | 185 | 2027-04-15 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SPC | 11 | Beaver | 101198 | Shenango Road Bridge | 4021 | B05 | Bridge Replacement | UTL | BOF | 2027-04-15 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 11 | Beaver | 101198 | Shenango Road Bridge | 4021 | B05 | Bridge Replacement | UTL | 185 | 2027-04-15 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SPC | 11 | Beaver | 101198 | Shenango Road Bridge | 4021 | B05 | Bridge Replacement | CON | BOF | 2027-04-15 |  | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 1200000
SPC | 11 | Beaver | 101198 | Shenango Road Bridge | 4021 | B05 | Bridge Replacement | CON | 185 | 2027-04-15 |  | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 300000
SPC | 11 | Beaver | 101200 | West Madison Street Bridge | 4042 | B04 | Bridge Restoration | FD | 185 | 2027-04-15 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 11 | Beaver | 101200 | West Madison Street Bridge | 4042 | B04 | Bridge Restoration | UTL | 185 | 2027-04-15 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Beaver | 101200 | West Madison Street Bridge | 4042 | B04 | Bridge Restoration | CON | BRIP | 2027-04-15 |  | 0 | 0 | 0 | 0 | 1440000 | 0 | 0 | 0 | 0 | 1440000
SPC | 11 | Beaver | 101200 | West Madison Street Bridge | 4042 | B04 | Bridge Restoration | CON | 185 | 2027-04-15 |  | 0 | 0 | 0 | 0 | 360000 | 0 | 0 | 0 | 0 | 360000
SPC | 11 | Beaver | 101201 | Kelly Road over Wolf Run | 4043 | B03 | Bridge Replacement | PE | 185 | 2027-11-04 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Beaver | 101201 | Kelly Road over Wolf Run | 4043 | B03 | Bridge Replacement | FD | 185 | 2027-11-04 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Beaver | 101201 | Kelly Road over Wolf Run | 4043 | B03 | Bridge Replacement | ROW | 185 | 2027-11-04 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Beaver | 101201 | Kelly Road over Wolf Run | 4043 | B03 | Bridge Replacement | UTL | 185 | 2027-11-04 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Beaver | 101201 | Kelly Road over Wolf Run | 4043 | B03 | Bridge Replacement | CON | 185 | 2027-11-04 |  | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 2000000
SPC | 11 | Beaver | 101227 | SR 4042 - SR 8039 to Madison Street | 4042 | 0 | Highway Restoration | PE | 581 | 2031-12-25 |  | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Beaver | 102661 | Aliquippa East End Gateway, Ph 1 TIIF | 51 | B54 | Highway Reconstruction | CON | 581 | 2027-10-07 |  | 0 | 2000000 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000
SPC | 11 | Beaver | 102661 | Aliquippa East End Gateway, Ph 1 TIIF | 51 | B54 | Highway Reconstruction | CON | LOC | 2027-10-07 |  | 0 | 6500000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 10500000
SPC | 11 | Beaver | 105441 | PA 18 Bridge ov Beaver River | 18 | B62 | Bridge Preservation - Federal | CON | BRIP | 2026-07-16 |  | 0 | 6200000 | 104000 | 1920000 | 0 | 0 | 0 | 2176000 | 0 | 10400000
SPC | 11 | Beaver | 105441 | PA 18 Bridge ov Beaver River | 18 | B62 | Bridge Preservation - Federal | CON | 185 | 2026-07-16 |  | 0 | 1550000 | 1050000 | 0 | 0 | 0 | 0 | 0 | 0 | 2600000
SPC | 11 | Beaver | 105453 | SR 3007/Frankfort Rd - Allegheny Co Line | 3007 | B06 | Highway Restoration | CON | STP | 2022-04-14 | 2022-04-14 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SPC | 11 | Beaver | 106078 | NS RR Crossings in Darlington and Big Beaver |  | RRX | Rail Highway Grade Crossing | CON | RRX | 2028-08-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000
SPC | 11 | Beaver | 108522 | SR 551, Wallace Run Rd/Market St Resurfacing | 551 | B06 | Highway Restoration | CON | STP | 2024-03-14 | 2024-03-14 | 0 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000
SPC | 11 | Beaver | 109356 | Midland Beaver Road | 68 | B44 | Highway Restoration | PE | STP | 2026-10-01 |  | 350000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Beaver | 109356 | Midland Beaver Road | 68 | B44 | Highway Restoration | CON | NHPP | 2026-10-01 |  | 0 | 5000000 | 5760000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 12760000
SPC | 11 | Beaver | 109356 | Midland Beaver Road | 68 | B44 | Highway Restoration | CON | STU | 2026-10-01 |  | 0 | 4500000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 8500000
SPC | 11 | Beaver | 109356 | Midland Beaver Road | 68 | B44 | Highway Restoration | CON | 581 | 2026-10-01 |  | 0 | 3250000 | 2440000 | 0 | 0 | 0 | 0 | 0 | 0 | 5690000
SPC | 11 | Beaver | 109391 | Brady Run Road Bridge | 4012 | B11 | Bridge Replacement | PE | 185 | 2028-05-15 |  | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Beaver | 109391 | Brady Run Road Bridge | 4012 | B11 | Bridge Replacement | FD | 185 | 2028-05-15 |  | 0 | 0 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
SPC | 11 | Beaver | 109391 | Brady Run Road Bridge | 4012 | B11 | Bridge Replacement | ROW | 185 | 2028-05-15 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Beaver | 109391 | Brady Run Road Bridge | 4012 | B11 | Bridge Replacement | UTL | 185 | 2028-05-15 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Beaver | 109391 | Brady Run Road Bridge | 4012 | B11 | Bridge Replacement | CON | 185 | 2028-05-15 |  | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 1500000
SPC | 11 | Beaver | 110386 | Moffett Mill Road Upgrade | 3010 | B06 | Safety Improvement | PE | 581 | 2028-05-18 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 11 | Beaver | 111604 | Beaver-Rochester Bridge | 51 | 0 | Bridge Replacement | CON | BRIP | 2036-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000000 | 20000000
SPC | 11 | Beaver | 111604 | Beaver-Rochester Bridge | 51 | 0 | Bridge Replacement | CON | 185 | 2036-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
SPC | 11 | Beaver | 112022 | Monaca Gateway MTF-TIIF-Smart | 51 | B52 | Congestion Reduction | ROW | SXF | 2026-01-15 | 2026-01-15 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Beaver | 112022 | Monaca Gateway MTF-TIIF-Smart | 51 | B52 | Congestion Reduction | UTL | SXF | 2026-01-15 | 2026-01-15 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 11 | Beaver | 112022 | Monaca Gateway MTF-TIIF-Smart | 51 | B52 | Congestion Reduction | CON | STP | 2026-01-15 | 2026-01-15 | 0 | 317700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317700
SPC | 11 | Beaver | 112022 | Monaca Gateway MTF-TIIF-Smart | 51 | B52 | Congestion Reduction | CON | STU | 2026-01-15 | 2026-01-15 | 1000000 | 903612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903612
SPC | 11 | Beaver | 112022 | Monaca Gateway MTF-TIIF-Smart | 51 | B52 | Congestion Reduction | CON | 581 | 2026-01-15 | 2026-01-15 | 1873899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1873899
SPC | 11 | Beaver | 112022 | Monaca Gateway MTF-TIIF-Smart | 51 | B52 | Congestion Reduction | CON | 581 | 2026-01-15 | 2026-01-15 | 0 | 226101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226101
SPC | 11 | Beaver | 112022 | Monaca Gateway MTF-TIIF-Smart | 51 | B52 | Congestion Reduction | CON | LOC | 2026-01-15 | 2026-01-15 | 376101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376101
SPC | 11 | Beaver | 113163 | Valley Road Bridge | 7102 | 0 | Bridge Restoration | PE | BOF | 2033-06-15 |  | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Beaver | 113163 | Valley Road Bridge | 7102 | 0 | Bridge Restoration | CON | BOF | 2033-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
SPC | 11 | Beaver | 113165 | Cemetery Road ov Block House Run | 7215 | LOC | Bridge Restoration | PE | BOF | 2030-06-07 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Beaver | 113630 | Century Farm Road Culvert | 3034 | B02 | Bridge Replacement | ROW | 185 | 2025-07-10 | 2025-07-10 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Beaver | 113630 | Century Farm Road Culvert | 3034 | B02 | Bridge Replacement | CON | 185 | 2025-07-10 | 2025-07-10 | 846325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 846325
SPC | 11 | Beaver | 113650 | Midland Beaver Road ov NS RR | 68 | 0 | Bridge Preservation - State Funded | PE | BRIP | 2032-12-25 |  | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 240000
SPC | 11 | Beaver | 113650 | Midland Beaver Road ov NS RR | 68 | 0 | Bridge Preservation - State Funded | PE | 185 | 2032-12-25 |  | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000
SPC | 11 | Beaver | 113650 | Midland Beaver Road ov NS RR | 68 | 0 | Bridge Preservation - State Funded | FD | BRIP | 2032-12-25 |  | 0 | 0 | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 240000
SPC | 11 | Beaver | 113650 | Midland Beaver Road ov NS RR | 68 | 0 | Bridge Preservation - State Funded | FD | 185 | 2032-12-25 |  | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 60000
SPC | 11 | Beaver | 113650 | Midland Beaver Road ov NS RR | 68 | 0 | Bridge Preservation - State Funded | CON | BRIP | 2032-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100000 | 4100000
SPC | 11 | Beaver | 113669 | Tornado Bridge | 18 | 0 | Bridge Replacement | PE | 185 | 2032-06-15 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
SPC | 11 | Beaver | 113669 | Tornado Bridge | 18 | 0 | Bridge Replacement | CON | 185 | 2032-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050000 | 0 | 6050000
SPC | 11 | Beaver | 115203 | SR 51, Constitution Boulevard - Mill and Overlay | 51 | 0 | Highway Restoration | PE | 581 | 2028-06-15 |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Beaver | 115203 | SR 51, Constitution Boulevard - Mill and Overlay | 51 | 0 | Highway Restoration | CON | NHPP | 2028-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500000 | 5500000
SPC | 11 | Beaver | 116315 | SR 18, Big Beaver Boulevard | 18 | B70 | Highway Restoration | PE | NHPP | 2027-06-15 |  | 605001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605001
SPC | 11 | Beaver | 116315 | SR 18, Big Beaver Boulevard | 18 | B70 | Highway Restoration | CON | NHPP | 2027-06-15 |  | 0 | 0 | 0 | 3200000 | 9440000 | 0 | 0 | 0 | 0 | 12640000
SPC | 11 | Beaver | 116315 | SR 18, Big Beaver Boulevard | 18 | B70 | Highway Restoration | CON | 581 | 2027-06-15 |  | 0 | 0 | 0 | 800000 | 1860000 | 0 | 0 | 0 | 0 | 2660000
SPC | 11 | Beaver | 116559 | SR 68, Virginia Avenue/Adams Street | 68 | B45 | Highway Restoration | CON | STP | 2025-03-13 | 2025-03-13 | 4582234 | 1031088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5613322
SPC | 11 | Beaver | 116559 | SR 68, Virginia Avenue/Adams Street | 68 | B45 | Highway Restoration | CON | STU | 2025-03-13 | 2025-03-13 | 1568766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1568766
SPC | 11 | Beaver | 116559 | SR 68, Virginia Avenue/Adams Street | 68 | B45 | Highway Restoration | CON | SXF | 2025-03-13 | 2025-03-13 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Beaver | 116587 | SR 51, Constitution Boulevard - Aliquippa | 51 | 0 | Highway Reconstruction | PE | 581 | 2035-12-25 |  | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Beaver | 116587 | SR 51, Constitution Boulevard - Aliquippa | 51 | 0 | Highway Reconstruction | CON | NHPP | 2035-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5665000 | 5665000
SPC | 11 | Beaver | 116588 | SR 51, Constitution Boulevard - Darlington | 51 | 0 | Highway Restoration | PE | 581 | 2031-05-15 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
SPC | 11 | Beaver | 116588 | SR 51, Constitution Boulevard - Darlington | 51 | 0 | Highway Restoration | CON | NHPP | 2031-05-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11330000 | 11330000
SPC | 11 | Beaver | 117006 | Glasgow Bridge | 68 | 0 | Bridge Restoration | PE | 185 | 2031-12-25 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
SPC | 11 | Beaver | 117006 | Glasgow Bridge | 68 | 0 | Bridge Restoration | CON | 185 | 2031-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300000 | 0 | 3300000
SPC | 11 | Beaver | 117332 | SR 2004 Freedom Crider Rd at Lovi Road | 2004 | B12 | Congestion Reduction | FD | CAQ | 2027-03-25 |  | 200000 | 201600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401600
SPC | 11 | Beaver | 117332 | SR 2004 Freedom Crider Rd at Lovi Road | 2004 | B12 | Congestion Reduction | FD | 581 | 2027-03-25 |  | 50000 | 50400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100400
SPC | 11 | Beaver | 117332 | SR 2004 Freedom Crider Rd at Lovi Road | 2004 | B12 | Congestion Reduction | ROW | CAQ | 2027-03-25 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Beaver | 117332 | SR 2004 Freedom Crider Rd at Lovi Road | 2004 | B12 | Congestion Reduction | ROW | 581 | 2027-03-25 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Beaver | 117332 | SR 2004 Freedom Crider Rd at Lovi Road | 2004 | B12 | Congestion Reduction | UTL | CAQ | 2027-03-25 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Beaver | 117332 | SR 2004 Freedom Crider Rd at Lovi Road | 2004 | B12 | Congestion Reduction | UTL | 581 | 2027-03-25 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Beaver | 117332 | SR 2004 Freedom Crider Rd at Lovi Road | 2004 | B12 | Congestion Reduction | CON | CAQ | 2027-03-25 |  | 0 | 0 | 1380000 | 0 | 0 | 0 | 0 | 0 | 0 | 1380000
SPC | 11 | Beaver | 117987 | Ambridge-Aliquippa Bridge Replacement | 9102 | 0 | Bridge Replacement | STUDY | BOF | 2033-01-01 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Beaver | 117987 | Ambridge-Aliquippa Bridge Replacement | 9102 | 0 | Bridge Replacement | CON | BOF | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16990000 | 16990000
SPC | 11 | Beaver | 117987 | Ambridge-Aliquippa Bridge Replacement | 9102 | 0 | Bridge Replacement | CON | BRIP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7730000 | 7730000
SPC | 11 | Beaver | 117987 | Ambridge-Aliquippa Bridge Replacement | 9102 | 0 | Bridge Replacement | CON | 183 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4635000 | 4635000
SPC | 11 | Beaver | 117987 | Ambridge-Aliquippa Bridge Replacement | 9102 | 0 | Bridge Replacement | CON | LOC | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1545000 | 1545000
SPC | 11 | Beaver | 118443 | SR 51 @ SR 151 Roundabout | 51 | B55 | Safety Improvement | PE | HSIP | 2027-11-04 |  | 722600 | 7400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730000
SPC | 11 | Beaver | 118443 | SR 51 @ SR 151 Roundabout | 51 | B55 | Safety Improvement | CON | HSIP | 2027-11-04 |  | 0 | 0 | 0 | 2242600 | 0 | 0 | 0 | 0 | 0 | 2242600
SPC | 11 | Beaver | 118568 | Conway-Wallrose Slide | 2005 | B04 | Safety Improvement | CON | 581 | 2025-02-13 | 2025-02-13 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000
SPC | 11 | Beaver | 118580 | AWPM 2026 | 51 | B01 | Safety Improvement | CON | 581 | 2026-03-26 | 2026-03-26 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 11 | Beaver | 119903 | Georgetown Rd over Branch of Mill Creek | 3027 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 300000
SPC | 11 | Beaver | 119903 | Georgetown Rd over Branch of Mill Creek | 3027 | 0 | Bridge Replacement | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 1500000
SPC | 11 | Beaver | 119904 | Blackwoods Rd ov Snake Run Bridge Replacement | 2006 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 300000
SPC | 11 | Beaver | 119904 | Blackwoods Rd ov Snake Run Bridge Replacement | 2006 | 0 | Bridge Replacement | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 2000000
SPC | 11 | Beaver | 119972 | Wildwood Road Landslide | 4033 | B07 | Safety Improvement | PE | 581 | 2028-05-18 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 11 | Beaver | 120269 | I-376 Corridor ITS - Beaver County (Northern Sec) | 376 | B16 | Congestion Reduction | PE | CRP | 2027-01-28 |  | 580000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580000
SPC | 11 | Beaver | 120269 | I-376 Corridor ITS - Beaver County (Northern Sec) | 376 | B16 | Congestion Reduction | PE | 581 | 2027-01-28 |  | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145000
SPC | 11 | Beaver | 120269 | I-376 Corridor ITS - Beaver County (Northern Sec) | 376 | B16 | Congestion Reduction | CON | CRP | 2027-01-28 |  | 0 | 0 | 1937936 | 0 | 0 | 0 | 0 | 0 | 0 | 1937936
SPC | 11 | Beaver | 120269 | I-376 Corridor ITS - Beaver County (Northern Sec) | 376 | B16 | Congestion Reduction | CON | 581 | 2027-01-28 |  | 0 | 0 | 484484 | 0 | 0 | 0 | 0 | 0 | 0 | 484484
SPC | 11 | Beaver | 120839 | VRU Improvements | 2001 | 025 | Safety Improvement | CON | HVRU | 2024-12-12 | 2024-12-12 | 635000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 635000
SPC | 11 | Beaver | 121091 | YSRR - Constitution Blvd |  | RRX | Rail Highway Grade Crossing | CON | RRX | 2050-12-25 |  | 0 | 195000 | 286730 | 0 | 0 | 0 | 0 | 0 | 0 | 481730
SPC | 11 | Beaver | 121380 | BPRR Corridor |  | RRX | Rail Highway Grade Crossing | CON | RRX | 2026-12-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750000 | 2750000
SPC | 11 | Beaver | 121411 | Barclay Hill Slide Repair | 4037 | B02 | Safety Improvement | ROW | 581 | 2027-02-11 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 11 | Beaver | 121414 | Hoenig Road Slide Repair | 2003 | B01 | Safety Improvement | CON | 581 | 2026-09-03 |  | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
SPC | 11 | Beaver | 121483 | Freedom Road Acid Mine Drainage (AMD) Treatment | 2004 | B13 | General Maintenance | ROW | 581 | 2025-03-13 | 2025-03-13 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Beaver | 121483 | Freedom Road Acid Mine Drainage (AMD) Treatment | 2004 | B13 | General Maintenance | CON | 581 | 2025-03-13 | 2025-03-13 | 443000 | 22172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465172
SPC | 11 | Beaver | 121651 | Brodhead - Pleasant Drive Intersection Improvement | 3007 | B07 | Safety Improvement | PE | STU | 2028-06-08 |  | 504000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504000
SPC | 11 | Beaver | 122151 | MTF - Ambridge Borough Eighth Street Improvements |  | MTF | MultiModal | CON | 411 | 2027-12-25 |  | 1893450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1893450
SPC | 11 | Beaver | 122151 | MTF - Ambridge Borough Eighth Street Improvements |  | MTF | MultiModal | CON | LOC | 2027-12-25 |  | 719685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719685
SPC | 11 | Lawrence | 29327 | Wallace Road Bridge T356 | 7203 | LOC | Bridge Restoration | PE | BOF | 2029-06-07 |  | 0 | 112000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112000
SPC | 11 | Lawrence | 29327 | Wallace Road Bridge T356 | 7203 | LOC | Bridge Restoration | PE | 179 | 2029-06-07 |  | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
SPC | 11 | Lawrence | 29327 | Wallace Road Bridge T356 | 7203 | LOC | Bridge Restoration | FD | BOF | 2029-06-07 |  | 228000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228000
SPC | 11 | Lawrence | 29327 | Wallace Road Bridge T356 | 7203 | LOC | Bridge Restoration | FD | 179 | 2029-06-07 |  | 57000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57000
SPC | 11 | Lawrence | 29327 | Wallace Road Bridge T356 | 7203 | LOC | Bridge Restoration | ROW | BOF | 2029-06-07 |  | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
SPC | 11 | Lawrence | 29327 | Wallace Road Bridge T356 | 7203 | LOC | Bridge Restoration | ROW | 179 | 2029-06-07 |  | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
SPC | 11 | Lawrence | 29327 | Wallace Road Bridge T356 | 7203 | LOC | Bridge Restoration | UTL | BOF | 2029-06-07 |  | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
SPC | 11 | Lawrence | 29327 | Wallace Road Bridge T356 | 7203 | LOC | Bridge Restoration | UTL | 179 | 2029-06-07 |  | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
SPC | 11 | Lawrence | 29327 | Wallace Road Bridge T356 | 7203 | LOC | Bridge Restoration | CON | BOF | 2029-06-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 1600000
SPC | 11 | Lawrence | 29327 | Wallace Road Bridge T356 | 7203 | LOC | Bridge Restoration | CON | 179 | 2029-06-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 400000
SPC | 11 | Lawrence | 29343 | Mud Bridge Road (T-306) Bridge | 7203 | LOC | Bridge Replacement | PE | BOF | 2030-05-15 |  | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000
SPC | 11 | Lawrence | 29402 | Rose Point Bridge | 7212 | LOC | Bridge Restoration | PE | BOF | 2030-04-18 |  | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Lawrence | 29402 | Rose Point Bridge | 7212 | LOC | Bridge Restoration | CON | BOF | 2030-04-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3520000 | 0 | 0 | 3520000
SPC | 11 | Lawrence | 29402 | Rose Point Bridge | 7212 | LOC | Bridge Restoration | CON | 183 | 2030-04-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 660000 | 0 | 0 | 660000
SPC | 11 | Lawrence | 29402 | Rose Point Bridge | 7212 | LOC | Bridge Restoration | CON | LOC | 2030-04-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | 0 | 220000
SPC | 11 | Lawrence | 29468 | Moores Conner Rd Culvert | 1015 | L01 | Bridge Replacement | PE | 185 | 2027-03-11 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Lawrence | 29468 | Moores Conner Rd Culvert | 1015 | L01 | Bridge Replacement | FD | 185 | 2027-03-11 |  | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SPC | 11 | Lawrence | 29468 | Moores Conner Rd Culvert | 1015 | L01 | Bridge Replacement | ROW | 185 | 2027-03-11 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Lawrence | 29468 | Moores Conner Rd Culvert | 1015 | L01 | Bridge Replacement | UTL | 185 | 2027-03-11 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Lawrence | 29468 | Moores Conner Rd Culvert | 1015 | L01 | Bridge Replacement | CON | 581 | 2027-03-11 |  | 0 | 0 | 0 | 0 | 0 | 1700000 | 0 | 0 | 0 | 1700000
SPC | 11 | Lawrence | 29528 | Graceland Rd Br T464 | 7205 | LOC | Bridge Replacement | CON | BOF | 2026-07-02 |  | 1200000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360000
SPC | 11 | Lawrence | 29528 | Graceland Rd Br T464 | 7205 | LOC | Bridge Replacement | CON | 183 | 2026-07-02 |  | 225000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000
SPC | 11 | Lawrence | 29528 | Graceland Rd Br T464 | 7205 | LOC | Bridge Replacement | CON | LOC | 2026-07-02 |  | 75000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000
SPC | 11 | Lawrence | 29531 | Mcconnell Mill Road Bridge | 2013 | 000 | Bridge Replacement | CON | 185 | 2035-06-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 1500000
SPC | 11 | Lawrence | 29558 | Van Gorders Mill Road Bridge | 2005 | L03 | Bridge Replacement | PE | 185 | 2032-06-17 |  | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Lawrence | 29558 | Van Gorders Mill Road Bridge | 2005 | L03 | Bridge Replacement | FD | 185 | 2032-06-17 |  | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 300000
SPC | 11 | Lawrence | 29558 | Van Gorders Mill Road Bridge | 2005 | L03 | Bridge Replacement | CON | 185 | 2032-06-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 1800000
SPC | 11 | Lawrence | 78357 | Barkley Road Bridge #3 | 7207 | LOC | Bridge Replacement | FD | BOF | 2027-06-10 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 11 | Lawrence | 78357 | Barkley Road Bridge #3 | 7207 | LOC | Bridge Replacement | ROW | BOF | 2027-06-10 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Lawrence | 78357 | Barkley Road Bridge #3 | 7207 | LOC | Bridge Replacement | UTL | BOF | 2027-06-10 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SPC | 11 | Lawrence | 78357 | Barkley Road Bridge #3 | 7207 | LOC | Bridge Replacement | CON | BOF | 2027-06-10 |  | 0 | 0 | 0 | 0 | 960000 | 0 | 0 | 0 | 0 | 960000
SPC | 11 | Lawrence | 78357 | Barkley Road Bridge #3 | 7207 | LOC | Bridge Replacement | CON | 183 | 2027-06-10 |  | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 180000
SPC | 11 | Lawrence | 78357 | Barkley Road Bridge #3 | 7207 | LOC | Bridge Replacement | CON | LOC | 2027-06-10 |  | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 60000
SPC | 11 | Lawrence | 78361 | Jefferson Street Bridge | 7301 | LOC | Bridge Replacement | PE | BOF | 2031-04-15 |  | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000
SPC | 11 | Lawrence | 78361 | Jefferson Street Bridge | 7301 | LOC | Bridge Replacement | FD | BOF | 2031-04-15 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 11 | Lawrence | 78361 | Jefferson Street Bridge | 7301 | LOC | Bridge Replacement | ROW | BOF | 2031-04-15 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 11 | Lawrence | 78361 | Jefferson Street Bridge | 7301 | LOC | Bridge Replacement | UTL | BOF | 2031-04-15 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Lawrence | 78361 | Jefferson Street Bridge | 7301 | LOC | Bridge Replacement | CON | BOF | 2031-04-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 1600000
SPC | 11 | Lawrence | 78361 | Jefferson Street Bridge | 7301 | LOC | Bridge Replacement | CON | 183 | 2031-04-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 300000
SPC | 11 | Lawrence | 78361 | Jefferson Street Bridge | 7301 | LOC | Bridge Replacement | CON | LOC | 2031-04-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
SPC | 11 | Lawrence | 78396 | PA 18 ov Abandoned Plant Access Rd | 18 | 0 | Bridge Replacement | PE | 185 | 2029-04-12 |  | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Lawrence | 78396 | PA 18 ov Abandoned Plant Access Rd | 18 | 0 | Bridge Replacement | CON | 185 | 2029-04-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 1200000
SPC | 11 | Lawrence | 81639 | Frew Mill Road Bridge | 1012 | L08 | Bridge Replacement | PE | BOF | 2026-08-27 |  | 257000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257000
SPC | 11 | Lawrence | 81639 | Frew Mill Road Bridge | 1012 | L08 | Bridge Replacement | FD | BOF | 2026-08-27 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 11 | Lawrence | 81639 | Frew Mill Road Bridge | 1012 | L08 | Bridge Replacement | ROW | BOF | 2026-08-27 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Lawrence | 81639 | Frew Mill Road Bridge | 1012 | L08 | Bridge Replacement | UTL | BOF | 2026-08-27 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 11 | Lawrence | 81639 | Frew Mill Road Bridge | 1012 | L08 | Bridge Replacement | CON | 185 | 2026-08-27 |  | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 11 | Lawrence | 88284 | SR 18 - Liberty Street to Jefferson Street | 18 | L32 | Highway Restoration | CON | NHPP | 2024-03-28 | 2024-03-28 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Lawrence | 88721 | Hickory View Drive (T-316) Bridge |  | LOC | Bridge Replacement | PE | BOF | 2030-07-15 |  | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
SPC | 11 | Lawrence | 88721 | Hickory View Drive (T-316) Bridge |  | LOC | Bridge Replacement | FD | BOF | 2030-07-15 |  | 0 | 0 | 0 | 135000 | 0 | 0 | 0 | 0 | 0 | 135000
SPC | 11 | Lawrence | 88721 | Hickory View Drive (T-316) Bridge |  | LOC | Bridge Replacement | ROW | BOF | 2030-07-15 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 11 | Lawrence | 88721 | Hickory View Drive (T-316) Bridge |  | LOC | Bridge Replacement | UTL | BOF | 2030-07-15 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
SPC | 11 | Lawrence | 88721 | Hickory View Drive (T-316) Bridge |  | LOC | Bridge Replacement | CON | BOF | 2030-07-15 |  | 0 | 0 | 0 | 0 | 0 | 960000 | 0 | 0 | 0 | 960000
SPC | 11 | Lawrence | 88721 | Hickory View Drive (T-316) Bridge |  | LOC | Bridge Replacement | CON | 183 | 2030-07-15 |  | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 180000
SPC | 11 | Lawrence | 88721 | Hickory View Drive (T-316) Bridge |  | LOC | Bridge Replacement | CON | LOC | 2030-07-15 |  | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 60000
SPC | 11 | Lawrence | 91761 | SR 224 (State Street), I-376 to Wilmington Road | 224 | L15 | Highway Restoration | PE | NHPP | 2029-05-17 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Lawrence | 91768 | PA 65/East Washington Street | 65 | L30 | Highway Restoration | CON | STU | 2022-04-28 | 2022-04-28 | 1238000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1238000
SPC | 11 | Lawrence | 92282 | SR 422, Benjamin Franklin Highway | 422 | L37 | Highway Restoration | CON | NHPP | 2022-12-08 | 2022-12-08 | 209440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209440
SPC | 11 | Lawrence | 93435 | Old Route 422 Bridge | 7212 | LOC | Bridge Replacement | PE | BOF | 2030-05-15 |  | 175000 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 11 | Lawrence | 100743 | East Washington Street Br | 2006 | L03 | Bridge Replacement | CON | NHPP | 2024-04-18 | 2024-04-18 | 679200 | 499200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1178400
SPC | 11 | Lawrence | 100743 | East Washington Street Br | 2006 | L03 | Bridge Replacement | CON | 185 | 2024-04-18 | 2024-04-18 | 169800 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294600
SPC | 11 | Lawrence | 100744 | Camp Run Road Bridge | 2011 | L01 | Bridge Replacement | PE | 185 | 2035-06-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 450000
SPC | 11 | Lawrence | 100744 | Camp Run Road Bridge | 2011 | L01 | Bridge Replacement | CON | 185 | 2035-06-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
SPC | 11 | Lawrence | 100916 | PA 18/Beaver Co- Mahoning River | 18 | 0 | Highway Restoration | PE | STP | 2033-05-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 900000
SPC | 11 | Lawrence | 100916 | PA 18/Beaver Co- Mahoning River | 18 | 0 | Highway Restoration | CON | 581 | 2033-05-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000000 | 9000000
SPC | 11 | Lawrence | 100917 | SR 18, Wilmington Road | 18 | L36 | Highway Restoration | PE | 581 | 2027-03-18 |  | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SPC | 11 | Lawrence | 100917 | SR 18, Wilmington Road | 18 | L36 | Highway Restoration | CON | STP | 2027-03-18 |  | 0 | 0 | 0 | 0 | 2000000 | 3500000 | 0 | 0 | 0 | 5500000
SPC | 11 | Lawrence | 105601 | McCartney Hollow Road Bridge T311 | 7207 | LOC | Bridge Replacement | PE | BOF | 2032-05-15 |  | 0 | 0 | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 175000
SPC | 11 | Lawrence | 105601 | McCartney Hollow Road Bridge T311 | 7207 | LOC | Bridge Replacement | CON | BOF | 2032-05-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 1200000
SPC | 11 | Lawrence | 105601 | McCartney Hollow Road Bridge T311 | 7207 | LOC | Bridge Replacement | CON | 183 | 2032-05-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 0 | 0 | 225000
SPC | 11 | Lawrence | 105601 | McCartney Hollow Road Bridge T311 | 7207 | LOC | Bridge Replacement | CON | LOC | 2032-05-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 75000
SPC | 11 | Lawrence | 109386 | Perry Highway | 19 | 0 | Highway Restoration | PE | 581 | 2029-02-15 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Lawrence | 109386 | Perry Highway | 19 | 0 | Highway Restoration | CON | 581 | 2029-02-15 |  | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 4500000
SPC | 11 | Lawrence | 109389 | Perry Highway 2 | 19 | 0 | Highway Restoration | PE | 581 | 2031-06-19 |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
SPC | 11 | Lawrence | 113185 | Paden Road over Hickory Run | 7206 | 0 | Bridge Restoration | PE | BOF | 2032-05-15 |  | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000
SPC | 11 | Lawrence | 113185 | Paden Road over Hickory Run | 7206 | 0 | Bridge Restoration | FD | BOF | 2032-05-15 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 11 | Lawrence | 113185 | Paden Road over Hickory Run | 7206 | 0 | Bridge Restoration | ROW | BOF | 2032-05-15 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
SPC | 11 | Lawrence | 113185 | Paden Road over Hickory Run | 7206 | 0 | Bridge Restoration | UTL | BOF | 2032-05-15 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
SPC | 11 | Lawrence | 113185 | Paden Road over Hickory Run | 7206 | 0 | Bridge Restoration | CON | BOF | 2032-05-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 1400000
SPC | 11 | Lawrence | 113514 | D11 Traffic Signal Intersection Projects | 1005 | L15 | Intelligent Transportation System | CON | 581 | 2025-06-05 | 2025-06-05 | 688000 | 794402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482402
SPC | 11 | Lawrence | 113676 | Cherry Street Bridge | 2032 | 0 | Bridge Preservation - Federal | PE | 185 | 2032-06-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 300000
SPC | 11 | Lawrence | 113676 | Cherry Street Bridge | 2032 | 0 | Bridge Preservation - Federal | CON | BRIP | 2032-06-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840000 | 0 | 1840000
SPC | 11 | Lawrence | 113676 | Cherry Street Bridge | 2032 | 0 | Bridge Preservation - Federal | CON | 185 | 2032-06-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460000 | 0 | 460000
SPC | 11 | Lawrence | 116560 | SR 422, Bus. 422 to Butler County Line | 422 | L39 | Highway Restoration | PE | NHPP | 2026-06-18 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 11 | Lawrence | 116560 | SR 422, Bus. 422 to Butler County Line | 422 | L39 | Highway Restoration | CON | HSIP | 2026-06-18 |  | 0 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000
SPC | 11 | Lawrence | 116560 | SR 422, Bus. 422 to Butler County Line | 422 | L39 | Highway Restoration | CON | NHPP | 2026-06-18 |  | 0 | 4000000 | 2506000 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 10506000
SPC | 11 | Lawrence | 116560 | SR 422, Bus. 422 to Butler County Line | 422 | L39 | Highway Restoration | CON | STU | 2026-06-18 |  | 0 | 0 | 0 | 0 | 1477400 | 1787695 | 0 | 0 | 0 | 3265095
SPC | 11 | Lawrence | 116560 | SR 422, Bus. 422 to Butler County Line | 422 | L39 | Highway Restoration | CON | SXF | 2026-06-18 |  | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 11 | Lawrence | 116560 | SR 422, Bus. 422 to Butler County Line | 422 | L39 | Highway Restoration | CON | 581 | 2026-06-18 |  | 0 | 1000000 | 876500 | 1588055 | 369350 | 800000 | 0 | 0 | 0 | 4633905
SPC | 11 | Lawrence | 117261 | Union Township TA Project |  | TAU | Safety Improvement | CON | TAP | 2027-01-14 |  | 0 | 0 | 680000 | 0 | 0 | 0 | 0 | 0 | 0 | 680000
SPC | 11 | Lawrence | 117475 | Old Pulaski Road Culvert | 4005 | L05 | Bridge Replacement | PE | BOF | 2026-05-21 |  | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56000
SPC | 11 | Lawrence | 117475 | Old Pulaski Road Culvert | 4005 | L05 | Bridge Replacement | PE | 185 | 2026-05-21 |  | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000
SPC | 11 | Lawrence | 117475 | Old Pulaski Road Culvert | 4005 | L05 | Bridge Replacement | FD | BOF | 2026-05-21 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 11 | Lawrence | 117475 | Old Pulaski Road Culvert | 4005 | L05 | Bridge Replacement | ROW | BOF | 2026-05-21 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Lawrence | 117475 | Old Pulaski Road Culvert | 4005 | L05 | Bridge Replacement | UTL | BOF | 2026-05-21 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Lawrence | 117475 | Old Pulaski Road Culvert | 4005 | L05 | Bridge Replacement | CON | 185 | 2026-05-21 |  | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
SPC | 11 | Lawrence | 118141 | SR 956, Mercer Rd - New Wilm Twp line | 956 | 0 | Safety Improvement | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 800000
SPC | 11 | Lawrence | 118141 | SR 956, Mercer Rd - New Wilm Twp line | 956 | 0 | Safety Improvement | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400000 | 5400000
SPC | 11 | Lawrence | 118141 | SR 956, Mercer Rd - New Wilm Twp line | 956 | 0 | Safety Improvement | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000
SPC | 11 | Lawrence | 119017 | Mahoning Ave. Viaduct | 18 | 0 | Bridge Replacement | CON | BRIP | 2032-05-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17245000 | 17245000
SPC | 11 | Lawrence | 119017 | Mahoning Ave. Viaduct | 18 | 0 | Bridge Replacement | CON | STP | 2032-05-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000
SPC | 11 | Lawrence | 119017 | Mahoning Ave. Viaduct | 18 | 0 | Bridge Replacement | CON | 185 | 2032-05-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000000 | 20000000
SPC | 11 | Lawrence | 119017 | Mahoning Ave. Viaduct | 18 | 0 | Bridge Replacement | CON | 581 | 2032-05-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3726000 | 0 | 3726000
SPC | 11 | Lawrence | 119342 | SR 18: Mahoning Ave to Mitchell Rd - Reconstruct | 18 | 0 | Highway Reconstruction | PE | 581 | 2050-12-25 |  | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 750000
SPC | 11 | Lawrence | 119342 | SR 18: Mahoning Ave to Mitchell Rd - Reconstruct | 18 | 0 | Highway Reconstruction | CON | NHPP | 2050-12-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13350000 | 13350000
SPC | 11 | Lawrence | 119466 | SR 158/North Jefferson Street | 158 | L10 | Highway Restoration | CON | STP | 2025-03-27 | 2025-03-27 | 1767478 | 1213522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2981000
SPC | 11 | Lawrence | 119466 | SR 158/North Jefferson Street | 158 | L10 | Highway Restoration | CON | SXF | 2025-03-27 | 2025-03-27 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
SPC | 11 | Lawrence | 119516 | Balph Avenue Bridge | 7301 | LOC | Bridge Replacement | PE | BOF | 2031-04-15 |  | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000
SPC | 11 | Lawrence | 119516 | Balph Avenue Bridge | 7301 | LOC | Bridge Replacement | FD | BOF | 2031-04-15 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 11 | Lawrence | 119516 | Balph Avenue Bridge | 7301 | LOC | Bridge Replacement | ROW | BOF | 2031-04-15 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Lawrence | 119516 | Balph Avenue Bridge | 7301 | LOC | Bridge Replacement | UTL | BOF | 2031-04-15 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 11 | Lawrence | 119516 | Balph Avenue Bridge | 7301 | LOC | Bridge Replacement | CON | BOF | 2031-04-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 1750000
SPC | 11 | Lawrence | 121948 | SR 18/Stonecrest Business Park TIIF | 18 | L35 | Safety Improvement | CON | 581 |  |  | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 12 | Fayette | 69233 | SR 4040 over Lamb Lick Run-2-DFB | 4040 | 000 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 69233 | SR 4040 over Lamb Lick Run-2-DFB | 4040 | 000 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 69233 | SR 4040 over Lamb Lick Run-2-DFB | 4040 | 000 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Fayette | 74185 | SR 3005 over Grassy Run- DFB | 3005 | A20 | Bridge Replacement | ROW | 185 | 2026-09-17 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 74185 | SR 3005 over Grassy Run- DFB | 3005 | A20 | Bridge Replacement | UTL | 185 | 2026-09-17 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 74185 | SR 3005 over Grassy Run- DFB | 3005 | A20 | Bridge Replacement | CON | 185 | 2026-09-17 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 74192 | SR 4040 over Lamb Lick Run-3-DFB | 4040 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Fayette | 74192 | SR 4040 over Lamb Lick Run-3-DFB | 4040 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Fayette | 74192 | SR 4040 over Lamb Lick Run-3-DFB | 4040 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
SPC | 12 | Fayette | 74342 | PA 711 Crawford Ave Bridge | 711 | 06M | Bridge Restoration | CON | BOF | 2023-05-11 | 2023-05-11 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 12 | Fayette | 74344 | Cast Iron Bridge | 4003 | 03M | Bridge Restoration | CON | STP | 2024-03-14 | 2024-03-14 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Fayette | 75999 | PA 201 over Trib Mon River-DFB | 201 | 000 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Fayette | 75999 | PA 201 over Trib Mon River-DFB | 201 | 000 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Fayette | 75999 | PA 201 over Trib Mon River-DFB | 201 | 000 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SPC | 12 | Fayette | 76000 | PA 201 over Trib Mon River-2-DFB | 201 | 000 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 76000 | PA 201 over Trib Mon River-2-DFB | 201 | 000 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 76000 | PA 201 over Trib Mon River-2-DFB | 201 | 000 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 76001 | PA 201 over Trib to Mon River-3-DFB | 201 | 000 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 76001 | PA 201 over Trib to Mon River-3-DFB | 201 | 000 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 76001 | PA 201 over Trib to Mon River-3-DFB | 201 | 000 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 76005 | PA 381 over Stoney Run-DFB | 381 | 000 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Fayette | 76005 | PA 381 over Stoney Run-DFB | 381 | 000 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Fayette | 76005 | PA 381 over Stoney Run-DFB | 381 | 000 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
SPC | 12 | Fayette | 76006 | PA 819 over Trib Yough River | 819 | 03M | Bridge Replacement | FD | 185 | 2027-03-18 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 76006 | PA 819 over Trib Yough River | 819 | 03M | Bridge Replacement | ROW | 185 | 2027-03-18 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Fayette | 76006 | PA 819 over Trib Yough River | 819 | 03M | Bridge Replacement | UTL | 185 | 2027-03-18 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Fayette | 76006 | PA 819 over Trib Yough River | 819 | 03M | Bridge Replacement | CON | BRIP | 2027-03-18 |  | 0 | 0 | 1850000 | 0 | 0 | 0 | 0 | 0 | 0 | 1850000
SPC | 12 | Fayette | 76017 | SR 4016 over Redstone Ck | 4016 | D10 | Bridge Replacement | FD | BOF | 2027-07-01 |  | 575000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575000
SPC | 12 | Fayette | 76017 | SR 4016 over Redstone Ck | 4016 | D10 | Bridge Replacement | ROW | BOF | 2027-07-01 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Fayette | 76017 | SR 4016 over Redstone Ck | 4016 | D10 | Bridge Replacement | UTL | BOF | 2027-07-01 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Fayette | 76017 | SR 4016 over Redstone Ck | 4016 | D10 | Bridge Replacement | CON | STP | 2027-07-01 |  | 0 | 0 | 0 | 1545000 | 0 | 0 | 0 | 0 | 0 | 1545000
SPC | 12 | Fayette | 76018 | SR 4040 over Lamb Lick Run-DFB | 4040 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 76018 | SR 4040 over Lamb Lick Run-DFB | 4040 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 76018 | SR 4040 over Lamb Lick Run-DFB | 4040 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Fayette | 76137 | Moyer Road Bridges | 7202 | MOY | Bridge Replacement | CON | BRIP | 2023-12-14 | 2023-12-14 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 76508 | Dist12 Hwy/Brdg Line Item |  | RLI | Reserve Line Item | CON | BOF |  |  | 0 | 86888 | 3246900 | 621000 | 21000 | 221000 | 1321000 | 1271000 | 38283000 | 45071788
SPC | 12 | Fayette | 76508 | Dist12 Hwy/Brdg Line Item |  | RLI | Reserve Line Item | CON | BRIP |  |  | 0 | 25020 | 0 | 750000 | 3509630 | 1807669 | 7627355 | 12831000 | 36321000 | 62871674
SPC | 12 | Fayette | 76508 | Dist12 Hwy/Brdg Line Item |  | RLI | Reserve Line Item | CON | CRP |  |  | 0 | 249000 | 48792 | 874000 | 874000 | 874000 | 874000 | 874000 | 3496000 | 8163792
SPC | 12 | Fayette | 76508 | Dist12 Hwy/Brdg Line Item |  | RLI | Reserve Line Item | CON | NHPP |  |  | 0 | 1496480 | 1479280 | 646280 | 431000 | 183000 | 6831000 | 10431000 | 13333453 | 34831493
SPC | 12 | Fayette | 76508 | Dist12 Hwy/Brdg Line Item |  | RLI | Reserve Line Item | CON | STP |  |  | 0 | 128029 | 4855000 | 5203720 | 2148615 | 410000 | 4692960 | 9101200 | 22941000 | 49480524
SPC | 12 | Fayette | 76508 | Dist12 Hwy/Brdg Line Item |  | RLI | Reserve Line Item | CON | STU |  |  | 96791 | 0 | 0 | 0 | 753720 | 1103720 | 6703720 | 8703720 | 25986600 | 43348271
SPC | 12 | Fayette | 76508 | Dist12 Hwy/Brdg Line Item |  | RLI | Reserve Line Item | CON | 185 |  |  | 0 | 33050 | 68630 | 790480 | 2295200 | 3288000 | 480089 | 8816500 | 19271653 | 35043602
SPC | 12 | Fayette | 76508 | Dist12 Hwy/Brdg Line Item |  | RLI | Reserve Line Item | CON | 581 |  |  | 62400 | 550849 | 4046128 | 3097795 | 13080 | 235632 | 3448080 | 12854800 | 101566640 | 125875404
SPC | 12 | Fayette | 79322 | SR 1058 over Champion Creek 2-DFB | 1058 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 79322 | SR 1058 over Champion Creek 2-DFB | 1058 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 79322 | SR 1058 over Champion Creek 2-DFB | 1058 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Fayette | 81192 | Layton Bridge | 4038 | D10 | Bridge Replacement | PE | STU | 2025-10-23 | 2025-10-23 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 81192 | Layton Bridge | 4038 | D10 | Bridge Replacement | ROW | 581 | 2025-10-23 | 2025-10-23 | 0 | 2843126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2843126
SPC | 12 | Fayette | 81192 | Layton Bridge | 4038 | D10 | Bridge Replacement | UTL | 581 | 2025-10-23 | 2025-10-23 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 12 | Fayette | 81192 | Layton Bridge | 4038 | D10 | Bridge Replacement | CON | BRIP | 2025-10-23 | 2025-10-23 | 8251420 | 5000000 | 12773350 | 8081000 | 6571370 | 0 | 0 | 0 | 0 | 40677140
SPC | 12 | Fayette | 81192 | Layton Bridge | 4038 | D10 | Bridge Replacement | CON | STP | 2025-10-23 | 2025-10-23 | 1000000 | 5084856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6084856
SPC | 12 | Fayette | 81192 | Layton Bridge | 4038 | D10 | Bridge Replacement | CON | STU | 2025-10-23 | 2025-10-23 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 12 | Fayette | 81192 | Layton Bridge | 4038 | D10 | Bridge Replacement | CON | 581 | 2025-10-23 | 2025-10-23 | 0 | 0 | 0 | 12205 | 0 | 0 | 0 | 0 | 0 | 12205
SPC | 12 | Fayette | 81229 | D12 Bridge Preservation Design |  |  | Bridge Restoration | FD | 185 |  | 2018-06-07 | 400000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
SPC | 12 | Fayette | 81229 | D12 Bridge Preservation Design |  |  | Bridge Restoration | CON | 185 |  | 2018-06-07 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Fayette | 81951 | SR 1039 over Br Dickerson Run-DFB | 1039 | B10 | Bridge Restoration | ROW | 185 | 2025-09-25 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 81951 | SR 1039 over Br Dickerson Run-DFB | 1039 | B10 | Bridge Restoration | UTL | 185 | 2025-09-25 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 81951 | SR 1039 over Br Dickerson Run-DFB | 1039 | B10 | Bridge Restoration | CON | 185 | 2025-09-25 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 81956 | SR 1051 over Br Opossum Run - DFB | 1051 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 81956 | SR 1051 over Br Opossum Run - DFB | 1051 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 81956 | SR 1051 over Br Opossum Run - DFB | 1051 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 81967 | SR4019 over Br Ltl Redstone Ck- DFB | 4019 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 81967 | SR4019 over Br Ltl Redstone Ck- DFB | 4019 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 81967 | SR4019 over Br Ltl Redstone Ck- DFB | 4019 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 81994 | SR 4011 over Washwater Run - DFB | 4011 | B10 | Bridge Replacement | ROW | 185 | 2025-09-25 | 2025-07-10 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 81994 | SR 4011 over Washwater Run - DFB | 4011 | B10 | Bridge Replacement | UTL | 185 | 2025-09-25 | 2025-07-10 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 81994 | SR 4011 over Washwater Run - DFB | 4011 | B10 | Bridge Replacement | CON | 185 | 2025-09-25 | 2025-07-10 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 90801 | PA 982 over Spruce Run | 982 | B10 | Bridge Replacement | PE | 185 |  |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 90801 | PA 982 over Spruce Run | 982 | B10 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
SPC | 12 | Fayette | 90801 | PA 982 over Spruce Run | 982 | B10 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 250000
SPC | 12 | Fayette | 90801 | PA 982 over Spruce Run | 982 | B10 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 250000
SPC | 12 | Fayette | 90801 | PA 982 over Spruce Run | 982 | B10 | Bridge Replacement | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1850000 | 1850000
SPC | 12 | Fayette | 90962 | SR 2011 ov Little Sandy Ck-DFB | 2011 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Fayette | 90962 | SR 2011 ov Little Sandy Ck-DFB | 2011 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Fayette | 90962 | SR 2011 ov Little Sandy Ck-DFB | 2011 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SPC | 12 | Fayette | 90991 | SR 4003 ov Abandoned CSXT-DFB | 4003 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Fayette | 90991 | SR 4003 ov Abandoned CSXT-DFB | 4003 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Fayette | 90991 | SR 4003 ov Abandoned CSXT-DFB | 4003 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
SPC | 12 | Fayette | 91131 | SR 4008 over Fourmile Run- DFB | 4008 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 91131 | SR 4008 over Fourmile Run- DFB | 4008 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 91131 | SR 4008 over Fourmile Run- DFB | 4008 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 93507 | SR 2040 over Redstone Ck | 2040 | B10 | Bridge Replacement | CON | 581 | 2023-04-13 | 2023-04-13 | 1397693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397693
SPC | 12 | Fayette | 95837 | North Gallatin Ave Bridge | 7302 | NGA | Bridge Restoration | ROW | BOF | 2025-06-26 | 2025-06-26 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 95837 | North Gallatin Ave Bridge | 7302 | NGA | Bridge Restoration | UTL | BOF | 2025-06-26 | 2025-06-26 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 95837 | North Gallatin Ave Bridge | 7302 | NGA | Bridge Restoration | CON | BOF | 2025-06-26 | 2025-06-26 | 0 | 2500000 | 570019 | 0 | 0 | 0 | 0 | 0 | 0 | 3070019
SPC | 12 | Fayette | 96661 | McClure/Kingview Road Interchange | 119 | 20K | Safety Improvement | FD | NHPP | 2025-07-10 | 2025-07-10 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 12 | Fayette | 96661 | McClure/Kingview Road Interchange | 119 | 20K | Safety Improvement | CON | BRIP | 2025-07-10 | 2025-07-10 | 0 | 7478480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7478480
SPC | 12 | Fayette | 96661 | McClure/Kingview Road Interchange | 119 | 20K | Safety Improvement | CON | NHPP | 2025-07-10 | 2025-07-10 | 18726381 | 2413619 | 3493720 | 0 | 0 | 0 | 0 | 0 | 0 | 24633720
SPC | 12 | Fayette | 96661 | McClure/Kingview Road Interchange | 119 | 20K | Safety Improvement | CON | STP | 2025-07-10 | 2025-07-10 | 19915000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19915000
SPC | 12 | Fayette | 96661 | McClure/Kingview Road Interchange | 119 | 20K | Safety Improvement | CON | 185 | 2025-07-10 | 2025-07-10 | 0 | 0 | 0 | 2521520 | 0 | 0 | 0 | 0 | 0 | 2521520
SPC | 12 | Fayette | 96661 | McClure/Kingview Road Interchange | 119 | 20K | Safety Improvement | CON | 581 | 2025-07-10 | 2025-07-10 | 2034000 | 1400000 | 2000000 | 5051280 | 0 | 0 | 0 | 0 | 0 | 10485280
SPC | 12 | Fayette | 98559 | SR 4036 over Little Redstone Ck-DFB | 4036 | 0 | Bridge Restoration | ROW | 185 | 2027-03-04 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 98559 | SR 4036 over Little Redstone Ck-DFB | 4036 | 0 | Bridge Restoration | UTL | 185 | 2027-03-04 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 98559 | SR 4036 over Little Redstone Ck-DFB | 4036 | 0 | Bridge Restoration | CON | 185 | 2027-03-04 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 98615 | SR 3014 ov Muddy Run-DFB | 3014 | 0 | Bridge Restoration | ROW | 185 | 2027-05-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 98615 | SR 3014 ov Muddy Run-DFB | 3014 | 0 | Bridge Restoration | UTL | 185 | 2027-05-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 98615 | SR 3014 ov Muddy Run-DFB | 3014 | 0 | Bridge Restoration | CON | 185 | 2027-05-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Fayette | 98813 | SR 3011 ov Jacobs Crk-DFB | 3011 | 0 | Bridge Replacement | ROW | 185 | 2028-02-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Fayette | 98813 | SR 3011 ov Jacobs Crk-DFB | 3011 | 0 | Bridge Replacement | UTL | 185 | 2028-02-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Fayette | 98813 | SR 3011 ov Jacobs Crk-DFB | 3011 | 0 | Bridge Replacement | CON | 185 | 2028-02-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SPC | 12 | Fayette | 99531 | SR 1034 ov Breakneck Run-DFB | 1034 | 0 | Bridge Restoration | ROW | 185 | 2028-01-06 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 99531 | SR 1034 ov Breakneck Run-DFB | 1034 | 0 | Bridge Restoration | UTL | 185 | 2028-01-06 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 99531 | SR 1034 ov Breakneck Run-DFB | 1034 | 0 | Bridge Restoration | CON | 185 | 2028-01-06 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 101968 | D12 Pvmt Presv Design |  |  | Highway Restoration | PE | 581 |  | 2019-06-06 | 500000 | 250000 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 1250000
SPC | 12 | Fayette | 105387 | SR 1005 over Br Back Ck - DFB | 1005 | 01M | Bridge Replacement | ROW | 185 | 2027-09-30 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 105387 | SR 1005 over Br Back Ck - DFB | 1005 | 01M | Bridge Replacement | UTL | 185 | 2027-09-30 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 105387 | SR 1005 over Br Back Ck - DFB | 1005 | 01M | Bridge Replacement | CON | 185 | 2027-09-30 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 105822 | SR 1002 ov Br Laurel Run - DFB | 1002 | G10 | Bridge Replacement | UTL | 185 | 2024-10-24 | 2024-10-24 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 105858 | Districtwide DFB Line Item |  |  | Reserve Line Item | PE | 185 |  | 2020-08-20 | 250000 | 250000 | 250000 | 500000 | 0 | 0 | 0 | 0 | 5000000 | 6250000
SPC | 12 | Fayette | 105858 | Districtwide DFB Line Item |  |  | Reserve Line Item | FD | 185 |  | 2020-08-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
SPC | 12 | Fayette | 105858 | Districtwide DFB Line Item |  |  | Reserve Line Item | CON | 185 |  | 2020-08-20 | 250000 | 250000 | 250000 | 500000 | 0 | 0 | 0 | 0 | 5000000 | 6250000
SPC | 12 | Fayette | 106060 | Dawson Corridor | 1041 | 0 | Rail Highway Grade Crossing | CON | RRX | 2019-12-05 | 2022-08-03 | 1329174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329174
SPC | 12 | Fayette | 110402 | US 119 Connellsville CMAQ | 119 | SE4 | Congestion Reduction | CON | CAQ | 2023-11-02 | 2023-11-02 | 0 | 235582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235582
SPC | 12 | Fayette | 111776 | Jefferson Street Bridge | 7302 | JSB | Bridge Restoration | PE | BRIP | 2028-12-07 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 111776 | Jefferson Street Bridge | 7302 | JSB | Bridge Restoration | FD | BOF | 2028-12-07 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 12 | Fayette | 111776 | Jefferson Street Bridge | 7302 | JSB | Bridge Restoration | ROW | STP | 2028-12-07 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Fayette | 111776 | Jefferson Street Bridge | 7302 | JSB | Bridge Restoration | UTL | BOF | 2028-12-07 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Fayette | 111776 | Jefferson Street Bridge | 7302 | JSB | Bridge Restoration | CON | STP | 2028-12-07 |  | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 1500000
SPC | 12 | Fayette | 113781 | PA 653 over Indian Creek | 653 | 01M | Bridge Restoration | CON | STU | 2023-07-27 | 2023-07-27 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 12 | Fayette | 114628 | D12 BOF Local Bridge Reserve |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 3000000 | 500000 | 500000 | 0 | 4000000
SPC | 12 | Fayette | 114628 | D12 BOF Local Bridge Reserve |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 15000000
SPC | 12 | Fayette | 116189 | SR 1020 Gallatin Avenue Betterment | 1020 | 06R | Highway Restoration | CON | STP | 2026-12-03 |  | 0 | 0 | 0 | 0 | 1761200 | 4000000 | 0 | 0 | 0 | 5761200
SPC | 12 | Fayette | 116189 | SR 1020 Gallatin Avenue Betterment | 1020 | 06R | Highway Restoration | CON | 581 | 2026-12-03 |  | 0 | 0 | 0 | 1750000 | 0 | 4200000 | 0 | 0 | 0 | 5950000
SPC | 12 | Fayette | 116772 | Fayette County Epoxy Overlay 2025 | 21 | 09R | Bridge Restoration | CON | 581 | 2025-06-05 | 2025-06-05 | 0 | 0 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000
SPC | 12 | Fayette | 116775 | Fayette County Epoxy Overlay 2026 | 51 | 16M | Bridge Restoration | CON | 581 | 2026-06-04 |  | 0 | 0 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000
SPC | 12 | Fayette | 117112 | District 12 Support Services |  |  | Reserve Line Item | PE | 581 |  |  | 400331 | 750000 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 2650331
SPC | 12 | Fayette | 117423 | 2026 Slide Repairs | 381 | 0 | Safety Improvement | CON | PRTCT | 2026-12-03 |  | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
SPC | 12 | Fayette | 117423 | 2026 Slide Repairs | 381 | 0 | Safety Improvement | CON | 581 | 2026-12-03 |  | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 4000000
SPC | 12 | Fayette | 117426 | 2028 Slide Contract | 819 | 0 | Safety Improvement | CON | 581 | 2029-02-08 |  | 0 | 0 | 0 | 0 | 8000000 | 0 | 0 | 0 | 0 | 8000000
SPC | 12 | Fayette | 117427 | 2029 Slide Contract |  |  | Safety Improvement | CON | 581 | 2030-02-07 |  | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 0 | 8000000
SPC | 12 | Fayette | 117428 | 2030 Slide Contract |  |  | Safety Improvement | CON | 581 | 2031-03-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 8000000
SPC | 12 | Fayette | 117429 | 2025 RPM Contract | 40 | RPM | Safety Improvement | CON | 581 | 2025-03-27 | 2025-03-27 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
SPC | 12 | Fayette | 117430 | 2026 RPM Contract | 21 | RPM | Safety Improvement | CON | 581 | 2026-05-21 |  | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 12 | Fayette | 117431 | 2027 RPM Contract |  |  | Safety Improvement | CON | 581 | 2027-03-18 |  | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 12 | Fayette | 117432 | 2028 RPM Contract |  |  | Safety Improvement | CON | 581 | 2028-03-16 |  | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 12 | Fayette | 117530 | D12 Slide Design |  |  | Safety Improvement | PE | 581 |  |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 12 | Fayette | 118000 | PA 201/PA 217 Flashing Beacon 2021 | 201 | B10 | Safety Improvement | CON | HSIP | 2023-08-24 | 2023-08-24 | 21327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21327
SPC | 12 | Fayette | 118278 | Sheepskin Trail - City of Uniontown Connection |  | STU | Bicycle and Pedestrian Facilities Transit | PE | CRP | 2027-06-24 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 118278 | Sheepskin Trail - City of Uniontown Connection |  | STU | Bicycle and Pedestrian Facilities Transit | CON | CAQ | 2027-06-24 |  | 0 | 0 | 1300832 | 0 | 0 | 0 | 0 | 0 | 0 | 1300832
SPC | 12 | Fayette | 118278 | Sheepskin Trail - City of Uniontown Connection |  | STU | Bicycle and Pedestrian Facilities Transit | CON | CRPU | 2027-06-24 |  | 0 | 400000 | 325208 | 0 | 0 | 0 | 0 | 0 | 0 | 725208
SPC | 12 | Fayette | 118886 | PA 857 over Mountain Creek Deck Replacement | 857 | 06M | Bridge Restoration | CON | 185 | 2025-05-08 | 2025-05-08 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000
SPC | 12 | Fayette | 118892 | 2025 D12 Bridge Preservation | 4003 | 04M | Bridge Restoration | CON | 581 | 2025-06-26 | 2025-06-26 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 12 | Fayette | 119655 | US 119: Hopwood to Fairgrounds | 119 | 18M | Highway Restoration | CON | STP | 2024-11-07 | 2024-11-07 | 3261870 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3461870
SPC | 12 | Fayette | 119655 | US 119: Hopwood to Fairgrounds | 119 | 18M | Highway Restoration | CON | STU | 2024-11-07 | 2024-11-07 | 683683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 683683
SPC | 12 | Fayette | 119703 | SR 1009 over Little Champion Creek-DFB | 1009 | 04M | Bridge Replacement | ROW | 185 | 2025-09-25 | 2025-07-10 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 119703 | SR 1009 over Little Champion Creek-DFB | 1009 | 04M | Bridge Replacement | UTL | 185 | 2025-09-25 | 2025-07-10 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 119703 | SR 1009 over Little Champion Creek-DFB | 1009 | 04M | Bridge Replacement | UTL | 581 | 2025-09-25 | 2025-07-10 | 0 | 276250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276250
SPC | 12 | Fayette | 119703 | SR 1009 over Little Champion Creek-DFB | 1009 | 04M | Bridge Replacement | CON | 185 | 2025-09-25 | 2025-07-10 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SPC | 12 | Fayette | 120125 | SR 1051 over Little Champions Creek-DFB | 1051 | X10 | Bridge Replacement | ROW | 185 | 2025-09-25 | 2025-07-10 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 120125 | SR 1051 over Little Champions Creek-DFB | 1051 | X10 | Bridge Replacement | UTL | 185 | 2025-09-25 | 2025-07-10 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 120125 | SR 1051 over Little Champions Creek-DFB | 1051 | X10 | Bridge Replacement | CON | 185 | 2025-09-25 | 2025-07-10 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 120603 | Systemic Curve Improvements | 166 | SCI | Safety Improvement | CON | HSIP | 2025-02-27 | 2025-02-27 | 182264 | 17736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Fayette | 120609 | Municipal Bridge 3 | 7201 | MBP | Reserve Line Item | PE | BOF |  |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 120609 | Municipal Bridge 3 | 7201 | MBP | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 12 | Fayette | 120610 | Municipal Bridge 4 |  |  | Reserve Line Item | PE | BOF |  |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 120611 | Municipal Bridge 5 |  |  | Reserve Line Item | PE | BOF |  |  | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 120611 | Municipal Bridge 5 |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 3000000
SPC | 12 | Fayette | 120612 | Municipal Bridge 6 |  |  | Reserve Line Item | PE | BOF |  |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 120612 | Municipal Bridge 6 |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 3000000
SPC | 12 | Fayette | 120613 | Municipal Bridge 7 |  |  | Reserve Line Item | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 120613 | Municipal Bridge 7 |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 3000000
SPC | 12 | Fayette | 120614 | 2031 Municipal Bridge Program |  |  | Reserve Line Item | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000
SPC | 12 | Fayette | 120614 | 2031 Municipal Bridge Program |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 3000000
SPC | 12 | Fayette | 120615 | 2032 Municipal Bridge Program |  |  | Reserve Line Item | PE | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000
SPC | 12 | Fayette | 120615 | 2032 Municipal Bridge Program |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
SPC | 12 | Fayette | 120619 | SR 3013 over Br Wallace Run- DFB | 3013 | P10 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 120619 | SR 3013 over Br Wallace Run- DFB | 3013 | P10 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 120619 | SR 3013 over Br Wallace Run- DFB | 3013 | P10 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 120659 | SR 1055 over Tucker Run-DFB | 1055 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 120659 | SR 1055 over Tucker Run-DFB | 1055 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 120659 | SR 1055 over Tucker Run-DFB | 1055 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 120669 | SR 1030 over Gist Run-DFB | 1030 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 120669 | SR 1030 over Gist Run-DFB | 1030 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 120669 | SR 1030 over Gist Run-DFB | 1030 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Fayette | 120670 | SR 3015 over York Run-DFB | 3015 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 120670 | SR 3015 over York Run-DFB | 3015 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 120670 | SR 3015 over York Run-DFB | 3015 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Fayette | 120673 | SR 2003 over Chaney Run-DFB | 2003 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 120673 | SR 2003 over Chaney Run-DFB | 2003 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 120673 | SR 2003 over Chaney Run-DFB | 2003 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Fayette | 120674 | SR 4040 over Lamb Lick Run-DFB | 4040 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 120674 | SR 4040 over Lamb Lick Run-DFB | 4040 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Fayette | 120674 | SR 4040 over Lamb Lick Run-DFB | 4040 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Fayette | 120962 | Bridge Deck Cleaning & Sealing-2026 |  |  | Bridge Restoration | CON | 185 | 2026-03-12 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 120963 | Arch & Culvert Preservation - 27 |  |  | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 1500000
SPC | 12 | Fayette | 120965 | Stormwater Management 12-1 |  |  | Stormwater Management | CON | 581 | 2026-06-04 |  | 0 | 1723030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1723030
SPC | 12 | Fayette | 120967 | D12 Substructure Preservation |  |  | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
SPC | 12 | Fayette | 120969 | General Preservation 2028-1 | 3009 | 0 | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 4000000
SPC | 12 | Fayette | 120971 | Pipe and Culvert 1200-1 |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
SPC | 12 | Fayette | 120972 | General Preservation 2027-2 |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
SPC | 12 | Fayette | 120972 | General Preservation 2027-2 |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
SPC | 12 | Fayette | 120982 | Fayette County #3- Braznell Bridge | 7216 | FC3 | Bridge Replacement | PE | BOF | 2028-02-28 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 120982 | Fayette County #3- Braznell Bridge | 7216 | FC3 | Bridge Replacement | FD | BOF | 2028-02-28 |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 120982 | Fayette County #3- Braznell Bridge | 7216 | FC3 | Bridge Replacement | ROW | BOF | 2028-02-28 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Fayette | 120982 | Fayette County #3- Braznell Bridge | 7216 | FC3 | Bridge Replacement | UTL | BOF | 2028-02-28 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Fayette | 120982 | Fayette County #3- Braznell Bridge | 7216 | FC3 | Bridge Replacement | CON | BOF | 2028-02-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 50000 | 0 | 1050000
SPC | 12 | Fayette | 120992 | Fayette County Bridge #2 - Linn Station | 7216 | FC2 | Bridge Replacement | PE | BOF | 2028-02-28 |  | 400000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412000
SPC | 12 | Fayette | 120992 | Fayette County Bridge #2 - Linn Station | 7216 | FC2 | Bridge Replacement | FD | BOF | 2028-02-28 |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 120992 | Fayette County Bridge #2 - Linn Station | 7216 | FC2 | Bridge Replacement | ROW | BOF | 2028-02-28 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Fayette | 120992 | Fayette County Bridge #2 - Linn Station | 7216 | FC2 | Bridge Replacement | UTL | BOF | 2028-02-28 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Fayette | 120992 | Fayette County Bridge #2 - Linn Station | 7216 | FC2 | Bridge Replacement | CON | BOF | 2028-02-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 1500000
SPC | 12 | Fayette | 120994 | Fayette County Bridge # 155 | 7216 | 155 | Bridge Replacement | PE | BOF | 2028-02-28 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 12 | Fayette | 120994 | Fayette County Bridge # 155 | 7216 | 155 | Bridge Replacement | FD | BOF | 2028-02-28 |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 120994 | Fayette County Bridge # 155 | 7216 | 155 | Bridge Replacement | ROW | BOF | 2028-02-28 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Fayette | 120994 | Fayette County Bridge # 155 | 7216 | 155 | Bridge Replacement | UTL | BOF | 2028-02-28 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Fayette | 120994 | Fayette County Bridge # 155 | 7216 | 155 | Bridge Replacement | CON | BOF | 2028-02-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 1500000
SPC | 12 | Fayette | 121014 | SR 3009 over North Branch of Browns Run | 3009 | 0 | Bridge Replacement | PE | 581 |  |  | 0 | 0 | 0 | 695000 | 0 | 0 | 0 | 0 | 0 | 695000
SPC | 12 | Fayette | 121014 | SR 3009 over North Branch of Browns Run | 3009 | 0 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
SPC | 12 | Fayette | 121014 | SR 3009 over North Branch of Browns Run | 3009 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 121014 | SR 3009 over North Branch of Browns Run | 3009 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Fayette | 121014 | SR 3009 over North Branch of Browns Run | 3009 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 2000000
SPC | 12 | Fayette | 121065 | Slide Repairs 12-25-1 (PROTECT) | 381 | 01S | Safety Improvement | PE | 581 | 2026-12-03 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Fayette | 121066 | Slide Repairs 12-24-1 | 4022 | DSR | Safety Improvement | CON | PRTCT | 2025-12-11 | 2025-12-11 | 8362000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8362000
SPC | 12 | Fayette | 121190 | Downtown Uniontown Signal Improvements | 2040 | 0 | Congestion Reduction | PE | CRPU |  |  | 1361597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1361597
SPC | 12 | Fayette | 121190 | Downtown Uniontown Signal Improvements | 2040 | 0 | Congestion Reduction | UTL | CRPU |  |  | 912000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 912000
SPC | 12 | Fayette | 121190 | Downtown Uniontown Signal Improvements | 2040 | 0 | Congestion Reduction | UTL | 581 |  |  | 228000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228000
SPC | 12 | Fayette | 121190 | Downtown Uniontown Signal Improvements | 2040 | 0 | Congestion Reduction | CON | CRPU |  |  | 0 | 2586000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586000
SPC | 12 | Fayette | 121190 | Downtown Uniontown Signal Improvements | 2040 | 0 | Congestion Reduction | CON | 581 |  |  | 0 | 646500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646500
SPC | 12 | Fayette | 121431 | Sheepskin Trail LCSI STLC Project | 2025 | STC | Transportation Enhancement | CON | STU | 2026-04-09 |  | 0 | 187000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187000
SPC | 12 | Fayette | 121812 | 12-25-LCSIP Delineation | 21 | 0 | General Maintenance | CON | HSIP | 2025-06-26 | 2025-06-26 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 12 | Fayette | 122364 | D12 Substructure Preservation Project | 119 | 23M | Bridge Restoration | CON | 581 | 2026-06-18 |  | 0 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000
SPC | 12 | Fayette | 122384 | Sheepskin Trail: SE Nilan Bridge |  | SNB | Bicycle Pedestrian Highway | CON | STU | 2026-06-18 |  | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 12 | Fayette | 122502 | PA 381 over Branch of Meadow Run | 381 | 11M | Bridge Restoration | PE | 581 |  |  | 400000 | 195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595000
SPC | 12 | Fayette | 122624 | SR 1058 over Branch of Indian Creek-DFB | 1058 | G10 | Bridge Replacement | ROW | 185 | 2026-09-17 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 122624 | SR 1058 over Branch of Indian Creek-DFB | 1058 | G10 | Bridge Replacement | UTL | 185 | 2026-09-17 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Fayette | 122624 | SR 1058 over Branch of Indian Creek-DFB | 1058 | G10 | Bridge Replacement | CON | 185 | 2026-09-17 |  | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 12 | Fayette | 123198 | Fayette & Greene Resurfacing | 40 | 0 | Highway Restoration | CON | 581 | 2026-07-30 |  | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
SPC | 12 | Fayette | 123461 | PA 711 Emergency Void Repair | 711 | 0 | General Maintenance | CON | 581 |  | 2025-07-10 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 12 | Greene | 30134 | SR 3001 over Wheeling Ck | 3001 | 01A | Bridge Replacement | FD | STP | 2027-03-25 |  | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 12 | Greene | 30134 | SR 3001 over Wheeling Ck | 3001 | 01A | Bridge Replacement | ROW | 581 | 2027-03-25 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SPC | 12 | Greene | 30134 | SR 3001 over Wheeling Ck | 3001 | 01A | Bridge Replacement | UTL | 581 | 2027-03-25 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SPC | 12 | Greene | 30134 | SR 3001 over Wheeling Ck | 3001 | 01A | Bridge Replacement | CON | BRIP | 2027-03-25 |  | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 3000000
SPC | 12 | Greene | 30196 | SR 2003 over Whiteley Ck-DFB | 2003 | 000 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 30196 | SR 2003 over Whiteley Ck-DFB | 2003 | 000 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 30196 | SR 2003 over Whiteley Ck-DFB | 2003 | 000 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Greene | 30207 | Greene Co Bridge # 35 |  | G35 | Bridge Restoration | PE | BOF | 2028-12-07 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 12 | Greene | 30207 | Greene Co Bridge # 35 |  | G35 | Bridge Restoration | PE | BRIP | 2028-12-07 |  | 0 | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000
SPC | 12 | Greene | 30207 | Greene Co Bridge # 35 |  | G35 | Bridge Restoration | FD | BOF | 2028-12-07 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 30207 | Greene Co Bridge # 35 |  | G35 | Bridge Restoration | ROW | BOF | 2028-12-07 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 30207 | Greene Co Bridge # 35 |  | G35 | Bridge Restoration | UTL | BOF | 2028-12-07 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 30207 | Greene Co Bridge # 35 |  | G35 | Bridge Restoration | CON | BOF | 2028-12-07 |  | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Greene | 30211 | SR 3007 over Job Run- DFB | 3007 | 000 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 30211 | SR 3007 over Job Run- DFB | 3007 | 000 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 30211 | SR 3007 over Job Run- DFB | 3007 | 000 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Greene | 30212 | SR 3007 over Job Creek-2- DFB | 3007 | 000 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 30212 | SR 3007 over Job Creek-2- DFB | 3007 | 000 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 30212 | SR 3007 over Job Creek-2- DFB | 3007 | 000 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Greene | 74220 | SR 3011 over Hargus Creek | 3011 | G10 | Bridge Restoration | FD | BOF | 2026-12-03 |  | 575000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575000
SPC | 12 | Greene | 74220 | SR 3011 over Hargus Creek | 3011 | G10 | Bridge Restoration | ROW | BOF | 2026-12-03 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 74220 | SR 3011 over Hargus Creek | 3011 | G10 | Bridge Restoration | UTL | BOF | 2026-12-03 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 74220 | SR 3011 over Hargus Creek | 3011 | G10 | Bridge Restoration | CON | STP | 2026-12-03 |  | 0 | 0 | 0 | 1545000 | 0 | 0 | 0 | 0 | 0 | 1545000
SPC | 12 | Greene | 76020 | PA 18 over Br McCourtney Run-DFB | 18 | 000 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 76020 | PA 18 over Br McCourtney Run-DFB | 18 | 000 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 76020 | PA 18 over Br McCourtney Run-DFB | 18 | 000 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Greene | 79346 | PA 221 over Boyd Run-DFB | 221 | E10 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Greene | 79346 | PA 221 over Boyd Run-DFB | 221 | E10 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Greene | 79346 | PA 221 over Boyd Run-DFB | 221 | E10 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
SPC | 12 | Greene | 79347 | SR 1009 over Castile Run-DFB | 1009 | D20 | Bridge Restoration | ROW | 185 | 2025-09-25 | 2025-07-10 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 79347 | SR 1009 over Castile Run-DFB | 1009 | D20 | Bridge Restoration | UTL | 185 | 2025-09-25 | 2025-07-10 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 79347 | SR 1009 over Castile Run-DFB | 1009 | D20 | Bridge Restoration | CON | 185 | 2025-09-25 | 2025-07-10 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Greene | 79348 | SR 1014 over Castile Run - DFB | 1014 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Greene | 79348 | SR 1014 over Castile Run - DFB | 1014 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Greene | 79348 | SR 1014 over Castile Run - DFB | 1014 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SPC | 12 | Greene | 79361 | SR 3013 over Stewart Run-DFB | 3013 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 79361 | SR 3013 over Stewart Run-DFB | 3013 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 79361 | SR 3013 over Stewart Run-DFB | 3013 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Greene | 81640 | SR 2001 over Rudolph Run -DFB | 2001 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 81640 | SR 2001 over Rudolph Run -DFB | 2001 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 81640 | SR 2001 over Rudolph Run -DFB | 2001 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Greene | 81798 | SR 4007 over Owens Run - DFB | 4007 | C20 | Bridge Replacement | ROW | 185 | 2025-09-25 | 2025-07-10 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SPC | 12 | Greene | 81842 | SR 1010 over Pumpkin Run | 1010 | B10 | Bridge Restoration | FD | BRIP | 2026-04-23 |  | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000
SPC | 12 | Greene | 81842 | SR 1010 over Pumpkin Run | 1010 | B10 | Bridge Restoration | ROW | STP | 2026-04-23 |  | 77250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77250
SPC | 12 | Greene | 81842 | SR 1010 over Pumpkin Run | 1010 | B10 | Bridge Restoration | UTL | STP | 2026-04-23 |  | 0 | 103000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103000
SPC | 12 | Greene | 81842 | SR 1010 over Pumpkin Run | 1010 | B10 | Bridge Restoration | CON | BOF | 2026-04-23 |  | 0 | 1545000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1545000
SPC | 12 | Greene | 81849 | PA 218 ov Br Smith Ck | 218 | M20 | Bridge Replacement | PE | BRIP | 2028-12-07 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Greene | 81849 | PA 218 ov Br Smith Ck | 218 | M20 | Bridge Replacement | PE | STP | 2028-12-07 |  | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 170000
SPC | 12 | Greene | 81849 | PA 218 ov Br Smith Ck | 218 | M20 | Bridge Replacement | FD | 185 | 2028-12-07 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Greene | 81849 | PA 218 ov Br Smith Ck | 218 | M20 | Bridge Replacement | ROW | 185 | 2028-12-07 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 81849 | PA 218 ov Br Smith Ck | 218 | M20 | Bridge Replacement | UTL | 185 | 2028-12-07 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 81849 | PA 218 ov Br Smith Ck | 218 | M20 | Bridge Replacement | CON | 185 | 2028-12-07 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Greene | 81965 | SR 2003 ov Whiteley Creek-DFB | 2003 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 81965 | SR 2003 ov Whiteley Creek-DFB | 2003 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 81965 | SR 2003 ov Whiteley Creek-DFB | 2003 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Greene | 81977 | SR 4007 over Grays Fork- DFB | 4007 | 0 | Bridge Restoration | ROW | 185 | 2027-06-10 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 81977 | SR 4007 over Grays Fork- DFB | 4007 | 0 | Bridge Restoration | UTL | 185 | 2027-06-10 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 81977 | SR 4007 over Grays Fork- DFB | 4007 | 0 | Bridge Restoration | CON | 185 | 2027-06-10 |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Greene | 81987 | SR 2018 ov Br Whiteley Ck-DFB | 2018 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 81987 | SR 2018 ov Br Whiteley Ck-DFB | 2018 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 81987 | SR 2018 ov Br Whiteley Ck-DFB | 2018 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Greene | 89053 | PA 18 over Laughman Run | 18 | D20 | Bridge Replacement | CON | 185 | 2025-07-10 | 2025-07-10 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Greene | 90765 | SR 1006 over Glade Run-DFB | 1006 | C10 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Greene | 90765 | SR 1006 over Glade Run-DFB | 1006 | C10 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Greene | 90765 | SR 1006 over Glade Run-DFB | 1006 | C10 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SPC | 12 | Greene | 96659 | Sugar Run Road Intersect | 2003 | U20 | Safety Improvement | CON | 581 | 2025-03-13 | 2025-03-13 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000
SPC | 12 | Greene | 98556 | SR 1019 ov Coal Run-DFB | 1019 | 0 | Bridge Restoration | ROW | 185 | 2028-03-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Greene | 98556 | SR 1019 ov Coal Run-DFB | 1019 | 0 | Bridge Restoration | UTL | 185 | 2028-03-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Greene | 98556 | SR 1019 ov Coal Run-DFB | 1019 | 0 | Bridge Restoration | CON | 185 | 2028-03-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
SPC | 12 | Greene | 98812 | SR 3010 ov Herod Run-DFB | 3010 | 0 | Bridge Restoration | ROW | 185 | 2030-06-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 98812 | SR 3010 ov Herod Run-DFB | 3010 | 0 | Bridge Restoration | UTL | 185 | 2030-06-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 98812 | SR 3010 ov Herod Run-DFB | 3010 | 0 | Bridge Restoration | CON | 185 | 2030-06-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Greene | 98856 | SR 2008 ov Dunkard Crk | 2008 | A10 | Bridge Restoration | PE | 581 | 2026-11-05 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 12 | Greene | 98856 | SR 2008 ov Dunkard Crk | 2008 | A10 | Bridge Restoration | FD | 185 | 2026-11-05 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Greene | 98856 | SR 2008 ov Dunkard Crk | 2008 | A10 | Bridge Restoration | ROW | 185 | 2026-11-05 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 98856 | SR 2008 ov Dunkard Crk | 2008 | A10 | Bridge Restoration | UTL | 185 | 2026-11-05 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 98856 | SR 2008 ov Dunkard Crk | 2008 | A10 | Bridge Restoration | CON | BOF | 2026-11-05 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Greene | 98862 | SR 4008 ov Crabtree Crk-DFB | 4008 | 0 | Bridge Restoration | ROW | 185 | 2030-06-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 98862 | SR 4008 ov Crabtree Crk-DFB | 4008 | 0 | Bridge Restoration | UTL | 185 | 2030-06-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 98862 | SR 4008 ov Crabtree Crk-DFB | 4008 | 0 | Bridge Restoration | CON | 185 | 2030-06-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Greene | 105401 | SR 1008 over Neel Run - DFB | 1008 | C10 | Bridge Replacement | ROW | 185 | 2026-09-17 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 105401 | SR 1008 over Neel Run - DFB | 1008 | C10 | Bridge Replacement | UTL | 185 | 2026-09-17 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 105401 | SR 1008 over Neel Run - DFB | 1008 | C10 | Bridge Replacement | CON | 185 | 2026-09-17 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Greene | 106407 | Greene Co Bridge #105 | 7202 | 105 | Bridge Replacement | PE | BOF | 2027-12-09 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 12 | Greene | 106407 | Greene Co Bridge #105 | 7202 | 105 | Bridge Replacement | PE | BRIP | 2027-12-09 |  | 0 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500
SPC | 12 | Greene | 106407 | Greene Co Bridge #105 | 7202 | 105 | Bridge Replacement | FD | BOF | 2027-12-09 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 106407 | Greene Co Bridge #105 | 7202 | 105 | Bridge Replacement | ROW | BOF | 2027-12-09 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 106407 | Greene Co Bridge #105 | 7202 | 105 | Bridge Replacement | UTL | BOF | 2027-12-09 |  | 0 | 199000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199000
SPC | 12 | Greene | 106407 | Greene Co Bridge #105 | 7202 | 105 | Bridge Replacement | CON | BOF | 2027-12-09 |  | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Greene | 106889 | SR 4029 over Pettit Run DFB | 4029 | 0 | Bridge Replacement | ROW | 185 | 2035-08-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 106889 | SR 4029 over Pettit Run DFB | 4029 | 0 | Bridge Replacement | UTL | 185 | 2035-08-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 106889 | SR 4029 over Pettit Run DFB | 4029 | 0 | Bridge Replacement | CON | 185 | 2035-08-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Greene | 112595 | Greene County #73 | 7214 | G73 | Bridge Replacement | CON | STP | 2024-12-12 | 2024-12-12 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000
SPC | 12 | Greene | 112595 | Greene County #73 | 7214 | G73 | Bridge Replacement | CON | STP | 2024-12-12 | 2024-12-12 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000
SPC | 12 | Greene | 113705 | 2022 Slide Repairs | 2018 | E10 | Safety Improvement | CON | 581 | 2023-08-10 | 2023-08-10 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SPC | 12 | Greene | 116469 | SR 4031 over Dillie Run-DFB | 4031 | B10 | Bridge Restoration | ROW | 185 | 2025-09-25 | 2025-07-10 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 116469 | SR 4031 over Dillie Run-DFB | 4031 | B10 | Bridge Restoration | CON | 185 | 2025-09-25 | 2025-07-10 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Greene | 116794 | Greene County Epoxy Overlay 2028 | 79 | 0 | Bridge Restoration | CON | 581 | 2028-02-03 |  | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Greene | 117425 | 2027 Slide Repairs | 21 | 0 | Safety Improvement | CON | 581 | 2028-02-03 |  | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 0 | 0 | 0 | 8000000
SPC | 12 | Greene | 117441 | PA 21 East of Waynesburg | 21 | 19R | Highway Restoration | CON | HSIP | 2023-09-28 | 2023-09-28 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 117441 | PA 21 East of Waynesburg | 21 | 19R | Highway Restoration | CON | STP | 2023-09-28 | 2023-09-28 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
SPC | 12 | Greene | 118003 | PA 18/PA 21 Safety Improvements | 21 | S10 | Safety Improvement | UTL | HSIP | 2025-11-06 | 2025-11-06 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
SPC | 12 | Greene | 118003 | PA 18/PA 21 Safety Improvements | 21 | S10 | Safety Improvement | CON | HSIP | 2025-11-06 | 2025-11-06 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Greene | 118003 | PA 18/PA 21 Safety Improvements | 21 | S10 | Safety Improvement | CON | HSIP | 2025-11-06 | 2025-11-06 | 2932439 | 305813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3238252
SPC | 12 | Greene | 118488 | Districtwide Local Bridge Preservation | 7204 | PSV | Bridge Restoration | CON | BOF | 2024-12-12 | 2024-12-12 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 12 | Greene | 119065 | SR 2001 over Rudolph Run-DFB | 2001 | D20 | Bridge Replacement | ROW | 185 |  | 2024-08-22 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SPC | 12 | Greene | 119065 | SR 2001 over Rudolph Run-DFB | 2001 | D20 | Bridge Replacement | UTL | 185 |  | 2024-08-22 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 119296 | SR 3001 over Coon Creek-DFB | 3001 | M10 | Bridge Replacement | UTL | 185 | 2024-10-10 | 2024-08-22 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 119656 | Greene County Concrete Patching Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 4600000 | 0 | 0 | 0 | 4600000
SPC | 12 | Greene | 119656 | Greene County Concrete Patching Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 1150000 | 0 | 0 | 0 | 1150000
SPC | 12 | Greene | 119761 | SR 3018 over Branch of Blacks Run-DFB | 3018 | B10 | Bridge Replacement | UTL | 185 | 2024-10-10 | 2024-08-22 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 120620 | SR 3001 over Cook Run- DFB | 3001 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 120620 | SR 3001 over Cook Run- DFB | 3001 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 120620 | SR 3001 over Cook Run- DFB | 3001 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Greene | 120621 | SR 4017 over Branch of Browns Creek- DFB | 4017 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 120621 | SR 4017 over Branch of Browns Creek- DFB | 4017 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 120621 | SR 4017 over Branch of Browns Creek- DFB | 4017 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Greene | 120623 | SR 4019 over Br of Browns Creek- DFB | 4019 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 120623 | SR 4019 over Br of Browns Creek- DFB | 4019 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 120623 | SR 4019 over Br of Browns Creek- DFB | 4019 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Greene | 120661 | SR 3013 over Pursley Creek-DFB | 3013 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 120661 | SR 3013 over Pursley Creek-DFB | 3013 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Greene | 120661 | SR 3013 over Pursley Creek-DFB | 3013 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Greene | 120664 | SR 2020 over Branch of Smith Creek-DFB | 2020 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Greene | 120664 | SR 2020 over Branch of Smith Creek-DFB | 2020 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Greene | 120664 | SR 2020 over Branch of Smith Creek-DFB | 2020 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SPC | 12 | Greene | 120668 | PA 218 over Branch of Smith Creek-DFB | 218 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Greene | 120668 | PA 218 over Branch of Smith Creek-DFB | 218 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Greene | 120668 | PA 218 over Branch of Smith Creek-DFB | 218 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
SPC | 12 | Greene | 120671 | SR 18 over Branch of Garner Run-DFB | 18 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 120671 | SR 18 over Branch of Garner Run-DFB | 18 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 120671 | SR 18 over Branch of Garner Run-DFB | 18 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Greene | 120675 | SR 18 over Browns Creek-DFB | 18 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 120675 | SR 18 over Browns Creek-DFB | 18 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Greene | 120675 | SR 18 over Browns Creek-DFB | 18 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Greene | 120996 | Greene County Bridge #76 | 7214 | 0 | Bridge Replacement | PE | BOF |  |  | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Greene | 120996 | Greene County Bridge #76 | 7214 | 0 | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Greene | 120996 | Greene County Bridge #76 | 7214 | 0 | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 120996 | Greene County Bridge #76 | 7214 | 0 | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 120996 | Greene County Bridge #76 | 7214 | 0 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 500000 | 0 | 1500000
SPC | 12 | Greene | 120997 | Greene County Bridge No. 54 | 7207 | 0 | Bridge Replacement | PE | BOF |  |  | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Greene | 120997 | Greene County Bridge No. 54 | 7207 | 0 | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Greene | 120997 | Greene County Bridge No. 54 | 7207 | 0 | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 120997 | Greene County Bridge No. 54 | 7207 | 0 | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Greene | 120997 | Greene County Bridge No. 54 | 7207 | 0 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 500000 | 0 | 1500000
SPC | 12 | Greene | 122506 | PA 88 over Branch of Coal Run | 88 | 13M | Bridge Restoration | PE | 185 |  |  | 0 | 400000 | 0 | 195000 | 0 | 0 | 0 | 0 | 0 | 595000
SPC | 12 | Washington | 30882 | PA 221 ov Br Ten Mile Ck-DFB | 221 | E10 | Bridge Restoration | ROW | 185 | 2024-09-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Washington | 30882 | PA 221 ov Br Ten Mile Ck-DFB | 221 | E10 | Bridge Restoration | UTL | 185 | 2024-09-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Washington | 30882 | PA 221 ov Br Ten Mile Ck-DFB | 221 | E10 | Bridge Restoration | CON | 185 | 2024-09-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SPC | 12 | Washington | 30989 | Gabby Bridge #64 |  | W64 | Bridge Restoration | PE | BRIP | 2026-08-13 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 12 | Washington | 30989 | Gabby Bridge #64 |  | W64 | Bridge Restoration | FD | STU | 2026-08-13 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Washington | 30989 | Gabby Bridge #64 |  | W64 | Bridge Restoration | ROW | STU | 2026-08-13 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 30989 | Gabby Bridge #64 |  | W64 | Bridge Restoration | UTL | STU | 2026-08-13 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 30989 | Gabby Bridge #64 |  | W64 | Bridge Restoration | CON | STU | 2026-08-13 |  | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Washington | 30992 | Ten Mile Creek #40 | 7201 | T40 | Bridge Restoration | PE | BOF | 2027-12-09 |  | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000
SPC | 12 | Washington | 30992 | Ten Mile Creek #40 | 7201 | T40 | Bridge Restoration | FD | STP | 2027-12-09 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Washington | 30992 | Ten Mile Creek #40 | 7201 | T40 | Bridge Restoration | ROW | STP | 2027-12-09 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 12 | Washington | 30992 | Ten Mile Creek #40 | 7201 | T40 | Bridge Restoration | UTL | STP | 2027-12-09 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 12 | Washington | 30992 | Ten Mile Creek #40 | 7201 | T40 | Bridge Restoration | CON | STP | 2027-12-09 |  | 0 | 0 | 0 | 1200000 | 1500000 | 0 | 0 | 0 | 0 | 2700000
SPC | 12 | Washington | 31074 | Raccoon Bridge #23 | 7404 | R23 | Bridge Restoration | FD | STU | 2029-01-25 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Washington | 31074 | Raccoon Bridge #23 | 7404 | R23 | Bridge Restoration | ROW | STU | 2029-01-25 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 31074 | Raccoon Bridge #23 | 7404 | R23 | Bridge Restoration | UTL | STU | 2029-01-25 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 31074 | Raccoon Bridge #23 | 7404 | R23 | Bridge Restoration | CON | BRIP | 2029-01-25 |  | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Washington | 31088 | PA 917 over Branch of Pigeon Creek | 917 | F10 | Bridge Restoration | PE | BOF | 2028-01-13 |  | 0 | 0 | 49100 | 0 | 0 | 0 | 0 | 0 | 0 | 49100
SPC | 12 | Washington | 51404 | Pike Run #1 | 7401 | PR1 | Historic Preservation and Rehab of Historic Transp | PE | STP | 2026-11-05 |  | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
SPC | 12 | Washington | 51404 | Pike Run #1 | 7401 | PR1 | Historic Preservation and Rehab of Historic Transp | FD | STP | 2026-11-05 |  | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SPC | 12 | Washington | 51404 | Pike Run #1 | 7401 | PR1 | Historic Preservation and Rehab of Historic Transp | ROW | STP | 2026-11-05 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 12 | Washington | 51404 | Pike Run #1 | 7401 | PR1 | Historic Preservation and Rehab of Historic Transp | UTL | STP | 2026-11-05 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 51404 | Pike Run #1 | 7401 | PR1 | Historic Preservation and Rehab of Historic Transp | CON | STP | 2026-11-05 |  | 0 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000
SPC | 12 | Washington | 51510 | SR 2011 ov Br Ten Mile Ck-DFB | 2011 | 000 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 51510 | SR 2011 ov Br Ten Mile Ck-DFB | 2011 | 000 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 51510 | SR 2011 ov Br Ten Mile Ck-DFB | 2011 | 000 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Washington | 67721 | SR 2011 over Br Plum Run-DFB | 2011 | PRB | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Washington | 67721 | SR 2011 over Br Plum Run-DFB | 2011 | PRB | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Washington | 67721 | SR 2011 over Br Plum Run-DFB | 2011 | PRB | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
SPC | 12 | Washington | 73058 | PA 88 over Peters Creek | 88 | 06M | Bridge Replacement | PE | STP | 2028-01-20 |  | 250000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 12 | Washington | 73058 | PA 88 over Peters Creek | 88 | 06M | Bridge Replacement | FD | STP | 2028-01-20 |  | 0 | 0 | 500185 | 0 | 0 | 0 | 0 | 0 | 0 | 500185
SPC | 12 | Washington | 73058 | PA 88 over Peters Creek | 88 | 06M | Bridge Replacement | UTL | STP | 2028-01-20 |  | 0 | 0 | 200185 | 0 | 0 | 0 | 0 | 0 | 0 | 200185
SPC | 12 | Washington | 73058 | PA 88 over Peters Creek | 88 | 06M | Bridge Replacement | CON | STP | 2028-01-20 |  | 0 | 0 | 0 | 0 | 3000185 | 0 | 0 | 0 | 0 | 3000185
SPC | 12 | Washington | 74234 | SR 3009 over Buffalo Creek #1 | 3009 | C10 | Bridge Replacement | FD | STP | 2028-06-22 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 74234 | SR 3009 over Buffalo Creek #1 | 3009 | C10 | Bridge Replacement | ROW | STP | 2028-06-22 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 12 | Washington | 74234 | SR 3009 over Buffalo Creek #1 | 3009 | C10 | Bridge Replacement | UTL | STP | 2028-06-22 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 12 | Washington | 74234 | SR 3009 over Buffalo Creek #1 | 3009 | C10 | Bridge Replacement | CON | BOF | 2028-06-22 |  | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 2000000
SPC | 12 | Washington | 76045 | US 40 over Buffalo Creek | 40 | 000 | Bridge Replacement | PE | 185 |  |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Washington | 76045 | US 40 over Buffalo Creek | 40 | 000 | Bridge Replacement | FD | 581 |  |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 12 | Washington | 76045 | US 40 over Buffalo Creek | 40 | 000 | Bridge Replacement | ROW | 581 |  |  | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 12 | Washington | 76045 | US 40 over Buffalo Creek | 40 | 000 | Bridge Replacement | UTL | 581 |  |  | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 12 | Washington | 76045 | US 40 over Buffalo Creek | 40 | 000 | Bridge Replacement | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000000 | 7000000
SPC | 12 | Washington | 76050 | PA 88 over Trib Mon River | 88 | S10 | Bridge Restoration | PE | STU | 2023-04-13 | 2023-04-13 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
SPC | 12 | Washington | 76063 | PA 519 over Br Chartiers Run | 519 | P10 | Bridge Replacement | PE | STP | 2027-03-18 |  | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
SPC | 12 | Washington | 76063 | PA 519 over Br Chartiers Run | 519 | P10 | Bridge Replacement | FD | 185 | 2027-03-18 |  | 0 | 500185 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 600185
SPC | 12 | Washington | 76063 | PA 519 over Br Chartiers Run | 519 | P10 | Bridge Replacement | ROW | 185 | 2027-03-18 |  | 0 | 0 | 200185 | 0 | 0 | 0 | 0 | 0 | 0 | 200185
SPC | 12 | Washington | 76063 | PA 519 over Br Chartiers Run | 519 | P10 | Bridge Replacement | UTL | 185 | 2027-03-18 |  | 0 | 0 | 200185 | 0 | 0 | 0 | 0 | 0 | 0 | 200185
SPC | 12 | Washington | 76063 | PA 519 over Br Chartiers Run | 519 | P10 | Bridge Replacement | CON | STP | 2027-03-18 |  | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
SPC | 12 | Washington | 76063 | PA 519 over Br Chartiers Run | 519 | P10 | Bridge Replacement | CON | 581 | 2027-03-18 |  | 0 | 0 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 2500000
SPC | 12 | Washington | 76068 | SR 1039 over Chartiers Creek | 1039 | B10 | Bridge Replacement | FD | BOF | 2027-06-24 |  | 638420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638420
SPC | 12 | Washington | 76068 | SR 1039 over Chartiers Creek | 1039 | B10 | Bridge Replacement | ROW | BOF | 2027-06-24 |  | 0 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325000
SPC | 12 | Washington | 76068 | SR 1039 over Chartiers Creek | 1039 | B10 | Bridge Replacement | UTL | BOF | 2027-06-24 |  | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
SPC | 12 | Washington | 76068 | SR 1039 over Chartiers Creek | 1039 | B10 | Bridge Replacement | CON | BOF | 2027-06-24 |  | 0 | 0 | 0 | 0 | 1300000 | 0 | 0 | 0 | 0 | 1300000
SPC | 12 | Washington | 77851 | SR 2022 over Barrs Run-DFB | 2022 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 77851 | SR 2022 over Barrs Run-DFB | 2022 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 77851 | SR 2022 over Barrs Run-DFB | 2022 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Washington | 79365 | PA 18 over Chartiers Ck-1 | 18 | 05M | Bridge Restoration | FD | STP | 2028-12-14 |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Washington | 79365 | PA 18 over Chartiers Ck-1 | 18 | 05M | Bridge Restoration | ROW | 185 | 2028-12-14 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 79365 | PA 18 over Chartiers Ck-1 | 18 | 05M | Bridge Restoration | UTL | 185 | 2028-12-14 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 79365 | PA 18 over Chartiers Ck-1 | 18 | 05M | Bridge Restoration | CON | STU | 2028-12-14 |  | 0 | 0 | 0 | 0 | 0 | 3000000 | 2000000 | 0 | 0 | 5000000
SPC | 12 | Washington | 81943 | PA 331 over Br Brush Run #2-DFB | 331 | N10 | Bridge Restoration | ROW | 185 | 2025-10-09 | 2025-07-10 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 81943 | PA 331 over Br Brush Run #2-DFB | 331 | N10 | Bridge Restoration | UTL | 185 | 2025-10-09 | 2025-07-10 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 81943 | PA 331 over Br Brush Run #2-DFB | 331 | N10 | Bridge Restoration | CON | 185 | 2025-10-09 | 2025-07-10 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 81989 | SR 2038 over Ltl Pike Run-DFB | 2038 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 81989 | SR 2038 over Ltl Pike Run-DFB | 2038 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 81989 | SR 2038 over Ltl Pike Run-DFB | 2038 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Washington | 88074 | SR 4029 ov Br North Fk Cross-DFB | 4029 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 88074 | SR 4029 ov Br North Fk Cross-DFB | 4029 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 88074 | SR 4029 ov Br North Fk Cross-DFB | 4029 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Washington | 89047 | SR 2011 over Branch Ten Mile Ck-DFB | 2011 | 0 | Bridge Restoration | ROW | 185 | 2028-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Washington | 89047 | SR 2011 over Branch Ten Mile Ck-DFB | 2011 | 0 | Bridge Restoration | UTL | 185 | 2028-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Washington | 89047 | SR 2011 over Branch Ten Mile Ck-DFB | 2011 | 0 | Bridge Restoration | CON | 185 | 2028-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
SPC | 12 | Washington | 89052 | SR 4057 over Brush Run | 4057 | D10 | Bridge Restoration | CON | STU | 2023-12-14 | 2023-12-14 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Washington | 89054 | SR 3023 ov Br Md Wheel Ck-2-DFB | 3023 | 0 | Bridge Restoration | ROW | 185 | 2028-06-15 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 89054 | SR 3023 ov Br Md Wheel Ck-2-DFB | 3023 | 0 | Bridge Restoration | UTL | 185 | 2028-06-15 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 89054 | SR 3023 ov Br Md Wheel Ck-2-DFB | 3023 | 0 | Bridge Restoration | CON | 185 | 2028-06-15 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 89081 | SR 2053 over Branch of Daniels Run 2-DFB | 2053 | A20 | Bridge Restoration | ROW | 185 | 2026-10-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 89081 | SR 2053 over Branch of Daniels Run 2-DFB | 2053 | A20 | Bridge Restoration | UTL | 185 | 2026-10-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 89081 | SR 2053 over Branch of Daniels Run 2-DFB | 2053 | A20 | Bridge Restoration | CON | 185 | 2026-10-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Washington | 89131 | I-79 over Branch of Chartiers Ck #1 | 79 | 0 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 575000 | 0 | 0 | 0 | 0 | 0 | 575000
SPC | 12 | Washington | 89131 | I-79 over Branch of Chartiers Ck #1 | 79 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 89131 | I-79 over Branch of Chartiers Ck #1 | 79 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 89131 | I-79 over Branch of Chartiers Ck #1 | 79 | 0 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 1577500 | 0 | 0 | 0 | 1577500
SPC | 12 | Washington | 90622 | PA 331 over Br Brush Run- DFB | 331 | L20 | Bridge Replacement | ROW | 185 | 2026-10-22 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 90622 | PA 331 over Br Brush Run- DFB | 331 | L20 | Bridge Replacement | UTL | 185 | 2026-10-22 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 90622 | PA 331 over Br Brush Run- DFB | 331 | L20 | Bridge Replacement | CON | 185 | 2026-10-22 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 90685 | PA 18 over Chartiers Creek-2 | 18 | Q10 | Bridge Replacement | CON | STU | 2024-09-26 | 2024-09-26 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
SPC | 12 | Washington | 90690 | SR 1061 over Froman Run- DFB | 1061 | A10 | Bridge Replacement | CON | 185 | 2023-08-24 | 2023-07-27 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 12 | Washington | 90757 | SR 1006 over Branch Peters Creek - DFB | 1006 | F20 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 90757 | SR 1006 over Branch Peters Creek - DFB | 1006 | F20 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 90757 | SR 1006 over Branch Peters Creek - DFB | 1006 | F20 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 90776 | PA 231 over Br Rocky Run- DFB | 231 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 90776 | PA 231 over Br Rocky Run- DFB | 231 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 90776 | PA 231 over Br Rocky Run- DFB | 231 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 90786 | SR 2011 over Plum Run-DFB | 2011 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 90786 | SR 2011 over Plum Run-DFB | 2011 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 90786 | SR 2011 over Plum Run-DFB | 2011 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 91135 | Old Brownsville Bridge Rehab | 2067 | 0 | Bridge Restoration | CON | STP | 2029-01-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500000 | 5500000
SPC | 12 | Washington | 91135 | Old Brownsville Bridge Rehab | 2067 | 0 | Bridge Restoration | CON | 581 | 2029-01-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1375000 | 1375000
SPC | 12 | Washington | 98803 | SR 4035 ov S Frk Cross Ck-DFB | 4035 | 0 | Bridge Restoration | ROW | 185 | 2016-05-02 | 2016-05-02 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 98803 | SR 4035 ov S Frk Cross Ck-DFB | 4035 | 0 | Bridge Restoration | UTL | 185 | 2016-05-02 | 2016-05-02 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 98803 | SR 4035 ov S Frk Cross Ck-DFB | 4035 | 0 | Bridge Restoration | CON | 185 | 2016-05-02 | 2016-05-02 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 98847 | Lane Bane Bridge Preservation | 40 | 0 | Bridge Restoration | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16261387 | 16261387
SPC | 12 | Washington | 98847 | Lane Bane Bridge Preservation | 40 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4065347 | 4065347
SPC | 12 | Washington | 102154 | D12 Construction Mgt |  |  | Reserve Line Item | CON | 581 |  |  | 400331 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900331
SPC | 12 | Washington | 103061 | SR 4035 ov Br Cross Ck-DFB | 4035 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Washington | 103061 | SR 4035 ov Br Cross Ck-DFB | 4035 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Washington | 103061 | SR 4035 ov Br Cross Ck-DFB | 4035 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SPC | 12 | Washington | 103130 | SR 1011 ov Br Chartiers Ck-DFB | 1011 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 103130 | SR 1011 ov Br Chartiers Ck-DFB | 1011 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 103130 | SR 1011 ov Br Chartiers Ck-DFB | 1011 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Washington | 103142 | SR 4015 over Br Raccoon Creek - DFB | 4015 | 01M | Bridge Replacement | ROW | 185 | 2025-10-09 | 2025-07-10 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 103142 | SR 4015 over Br Raccoon Creek - DFB | 4015 | 01M | Bridge Replacement | UTL | 185 | 2025-10-09 | 2025-07-10 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 103142 | SR 4015 over Br Raccoon Creek - DFB | 4015 | 01M | Bridge Replacement | CON | 185 | 2025-10-09 | 2025-07-10 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 103186 | Dunlevy Corridor |  |  | Rail Highway Grade Crossing | CON | RRX | 2017-07-27 | 2017-03-28 | 2368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2368
SPC | 12 | Washington | 103187 | Besco St. Grade Crossing |  |  | Rail Highway Grade Crossing | CON | RRX | 2020-12-03 |  | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000
SPC | 12 | Washington | 105407 | SR 2013 over Branch of Little Daniels Run - DFB | 2013 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 105407 | SR 2013 over Branch of Little Daniels Run - DFB | 2013 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 105407 | SR 2013 over Branch of Little Daniels Run - DFB | 2013 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 105426 | PA 88 Improvements- Charleroi | 88 | 0 | Highway Restoration | CON | STP | 2026-12-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500000 | 9500000
SPC | 12 | Washington | 105888 | SR 2001/PA 18 Bridges over Catfish Creek | 2001 | F10 | Bridge Replacement | ROW | STP | 2025-08-21 | 2025-08-21 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SPC | 12 | Washington | 105888 | SR 2001/PA 18 Bridges over Catfish Creek | 2001 | F10 | Bridge Replacement | UTL | STU | 2025-08-21 | 2025-08-21 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 12 | Washington | 105888 | SR 2001/PA 18 Bridges over Catfish Creek | 2001 | F10 | Bridge Replacement | CON | 581 | 2025-08-21 | 2025-08-21 | 0 | 1315000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 2315000
SPC | 12 | Washington | 106063 | Elco Corridor |  |  | Rail Highway Grade Crossing | CON | RRX | 2018-12-13 |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Washington | 107432 | US 19 Corridor Signal Upgrade | 19 | SE2 | Congestion Reduction | FD | CAQ | 2027-10-07 |  | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SPC | 12 | Washington | 107432 | US 19 Corridor Signal Upgrade | 19 | SE2 | Congestion Reduction | ROW | CAQ | 2027-10-07 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 12 | Washington | 107432 | US 19 Corridor Signal Upgrade | 19 | SE2 | Congestion Reduction | UTL | CAQ | 2027-10-07 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 12 | Washington | 109025 | Bebout Rd/ E McMurray Rd Intersection | 1002 | F10 | Safety Improvement | ROW | STP | 2023-11-02 | 2023-11-02 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 12 | Washington | 109025 | Bebout Rd/ E McMurray Rd Intersection | 1002 | F10 | Safety Improvement | CON | STP | 2023-11-02 | 2023-11-02 | 0 | 0 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000
SPC | 12 | Washington | 109025 | Bebout Rd/ E McMurray Rd Intersection | 1002 | F10 | Safety Improvement | CON | STU | 2023-11-02 | 2023-11-02 | 0 | 166484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166484
SPC | 12 | Washington | 110399 | PA 88 Charleroi CMAQ | 88 | SE5 | Congestion Reduction | CON | CAQ | 2023-06-08 | 2023-06-08 | 1495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495000
SPC | 12 | Washington | 112286 | Harmon Creek #7 | 7212 | 0 | Bridge Restoration | CON | ACT13 |  |  | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SPC | 12 | Washington | 113597 | SR 2047 over Little Tenmile Creek | 2047 | C10 | Bridge Replacement | PE | BOF | 2027-01-07 |  | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 12 | Washington | 113597 | SR 2047 over Little Tenmile Creek | 2047 | C10 | Bridge Replacement | FD | BOF | 2027-01-07 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Washington | 113597 | SR 2047 over Little Tenmile Creek | 2047 | C10 | Bridge Replacement | ROW | BOF | 2027-01-07 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 113597 | SR 2047 over Little Tenmile Creek | 2047 | C10 | Bridge Replacement | UTL | BOF | 2027-01-07 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 113597 | SR 2047 over Little Tenmile Creek | 2047 | C10 | Bridge Replacement | CON | BRIP | 2027-01-07 |  | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 2000000
SPC | 12 | Washington | 113722 | US 40 over Catfish Creek | 40 | S10 | Bridge Restoration | FD | 185 | 2027-04-08 |  | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
SPC | 12 | Washington | 113722 | US 40 over Catfish Creek | 40 | S10 | Bridge Restoration | ROW | 185 | 2027-04-08 |  | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 113722 | US 40 over Catfish Creek | 40 | S10 | Bridge Restoration | UTL | 185 | 2027-04-08 |  | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 113722 | US 40 over Catfish Creek | 40 | S10 | Bridge Restoration | CON | NHPP | 2027-04-08 |  | 0 | 0 | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 1750000
SPC | 12 | Washington | 114561 | PA 18: Main Street to Third Street | 18 | SE9 | Congestion Reduction | PE | CAQ | 2028-03-09 |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 12 | Washington | 114561 | PA 18: Main Street to Third Street | 18 | SE9 | Congestion Reduction | CON | CAQ | 2028-03-09 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Washington | 114584 | Charleroi Corridor RRX |  |  | General Maintenance | CON | RRX |  |  | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 800000
SPC | 12 | Washington | 116084 | SR 3014 over Chartiers Creek- DFB Group Project | 3014 | 01M | Bridge Restoration | ROW | 185 | 2025-10-09 | 2025-07-10 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 116084 | SR 3014 over Chartiers Creek- DFB Group Project | 3014 | 01M | Bridge Restoration | UTL | 185 | 2025-10-09 | 2025-07-10 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 12 | Washington | 116084 | SR 3014 over Chartiers Creek- DFB Group Project | 3014 | 01M | Bridge Restoration | CON | 185 | 2025-10-09 | 2025-07-10 | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275000
SPC | 12 | Washington | 116238 | 2024 Slide Repairs | 88 | 01S | Safety Improvement | CON | 581 | 2024-12-12 | 2024-12-12 | 3102307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3102307
SPC | 12 | Washington | 116369 | SR 4029 over Burgetts Fork-DFB | 4029 | 01M | Bridge Replacement | ROW | 185 | 2026-10-22 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 116369 | SR 4029 over Burgetts Fork-DFB | 4029 | 01M | Bridge Replacement | UTL | 185 | 2026-10-22 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 116369 | SR 4029 over Burgetts Fork-DFB | 4029 | 01M | Bridge Replacement | CON | 185 | 2026-10-22 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 116370 | SR 2005 over Smith Run-DFB | 2005 | A20 | Bridge Replacement | ROW | 185 | 2027-10-07 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 116370 | SR 2005 over Smith Run-DFB | 2005 | A20 | Bridge Replacement | UTL | 185 | 2027-10-07 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 116370 | SR 2005 over Smith Run-DFB | 2005 | A20 | Bridge Replacement | CON | 185 | 2027-10-07 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 116371 | SR 3023 ov Br Middle Wheeling Ck-DFB | 3023 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 116371 | SR 3023 ov Br Middle Wheeling Ck-DFB | 3023 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 116371 | SR 3023 ov Br Middle Wheeling Ck-DFB | 3023 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Washington | 116372 | SR 2079 over Lilley Run-DFB | 2079 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 116372 | SR 2079 over Lilley Run-DFB | 2079 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 116372 | SR 2079 over Lilley Run-DFB | 2079 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 116608 | SR 4045 over Chartiers Run | 4045 | F10 | Bridge Replacement | ROW | 581 |  |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 12 | Washington | 116608 | SR 4045 over Chartiers Run | 4045 | F10 | Bridge Replacement | UTL | 581 |  |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 12 | Washington | 116608 | SR 4045 over Chartiers Run | 4045 | F10 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 1250000 | 0 | 0 | 0 | 0 | 0 | 1250000
SPC | 12 | Washington | 116850 | Donora-Monessen Bridge (Spot Paint/Joints) | 1077 | 0 | Bridge Restoration | CON | BRIP | 2028-02-03 |  | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 3000000
SPC | 12 | Washington | 116915 | Bridge Scour Mitigation and Preservation | 2047 | 01M | Bridge Restoration | CON | 185 | 2025-01-09 | 2025-01-09 | 807765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 807765
SPC | 12 | Washington | 117314 | Cross Creek #33 | 7208 | W33 | Bridge Restoration | PE | BRIP | 2028-12-07 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Washington | 117314 | Cross Creek #33 | 7208 | W33 | Bridge Restoration | FD | BOF | 2028-12-07 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 12 | Washington | 117314 | Cross Creek #33 | 7208 | W33 | Bridge Restoration | ROW | BRIP | 2028-12-07 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 117314 | Cross Creek #33 | 7208 | W33 | Bridge Restoration | UTL | STP | 2028-12-07 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 117314 | Cross Creek #33 | 7208 | W33 | Bridge Restoration | CON | BRIP | 2028-12-07 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Washington | 117422 | 2025 Slide Repairs | 40 | 22M | Safety Improvement | CON | 581 | 2026-10-22 |  | 4000000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000000
SPC | 12 | Washington | 117444 | US 22 Concrete Repair - Washington | 22 | M20 | Highway Restoration | CON | NHPP | 2026-12-10 |  | 0 | 0 | 7998000 | 6001000 | 0 | 0 | 0 | 0 | 0 | 13999000
SPC | 12 | Washington | 117943 | US 19 Adaptive Signal CMAQ Supplement | 19 | 0 | Congestion Reduction | CON | CAQ |  |  | 0 | 0 | 1881220 | 1500000 | 0 | 0 | 0 | 0 | 0 | 3381220
SPC | 12 | Washington | 117943 | US 19 Adaptive Signal CMAQ Supplement | 19 | 0 | Congestion Reduction | CON | 581 |  |  | 0 | 0 | 470305 | 375000 | 0 | 0 | 0 | 0 | 0 | 845305
SPC | 12 | Washington | 117949 | MMVTA 2022 Bus Replacement |  |  | Public Transit | CON | CAQ | 2027-03-18 |  | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
SPC | 12 | Washington | 118280 | West Brownsville RRX Corridor | 2067 | 0 | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
SPC | 12 | Washington | 118319 | National Pike Tunnel Rehabilitation |  | NPT | Transportation Enhancement | CON | TAP | 2025-06-26 | 2025-06-26 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
SPC | 12 | Washington | 118574 | US 40/SR 3005 Intersection Improvements | 40 | 00A | Safety Improvement | CON | HSIP | 2026-06-04 |  | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Washington | 118898 | 2025 D12 Hyro/Latex Bridge Deck Pres | 2020 | 07M | Bridge Restoration | CON | 581 | 2025-03-13 | 2025-03-13 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 12 | Washington | 118903 | 2027 D12 Bridge Preservation | 2056 | 0 | Bridge Preservation - State Funded | CON | 185 | 2027-03-04 |  | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 3000000
SPC | 12 | Washington | 119428 | D12 I-70 ITS Eastern and Western GAP | 70 | 0 | Intelligent Transportation System | CON | STP |  |  | 0 | 0 | 0 | 0 | 500000 | 500000 | 146224 | 0 | 0 | 1146224
SPC | 12 | Washington | 119627 | SR 1025 Weavertown Rd / 1-79 NB Exit Ramp/ Hook St | 1025 | 0 | Highway Reconstruction | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 7000000 | 0 | 0 | 7000000
SPC | 12 | Washington | 119628 | Washington Road US 19/ Weavertown Road SR 1025 | 1025 | 0 | Highway Reconstruction | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1064800 | 0 | 0 | 1064800
SPC | 12 | Washington | 119628 | Washington Road US 19/ Weavertown Road SR 1025 | 1025 | 0 | Highway Reconstruction | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 266200 | 0 | 0 | 266200
SPC | 12 | Washington | 119630 | PA 136 Reconstruction and Realignment | 136 | 0 | Highway Reconstruction | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6050000 | 6050000 | 0 | 12100000
SPC | 12 | Washington | 119634 | SR 1055: I-70 to Dual Round About | 1055 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 3613750 | 0 | 0 | 0 | 3613750
SPC | 12 | Washington | 119635 | SR 3005 and US 40 Interchange | 3005 | 0 | Highway Reconstruction | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6050000 | 6050000 | 0 | 12100000
SPC | 12 | Washington | 119639 | I-79 Detour Improvement Plan Implementation | 79 | 0 | Highway Reconstruction | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 4861660 | 4861660 | 0 | 0 | 9723320
SPC | 12 | Washington | 119641 | I-70 Detour Improvement Plan Implementation | 70 | 0 | Highway Reconstruction | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000000 | 0 | 8000000
SPC | 12 | Washington | 119641 | I-70 Detour Improvement Plan Implementation | 70 | 0 | Highway Reconstruction | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 2000000
SPC | 12 | Washington | 119658 | Washington County Concrete Patching Line Item |  |  | Reserve Line Item | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 4600000 | 0 | 0 | 0 | 4600000
SPC | 12 | Washington | 119658 | Washington County Concrete Patching Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 1150000 | 0 | 0 | 0 | 1150000
SPC | 12 | Washington | 120072 | Tunnel Ridge Pre Work ON3 | 70 | 0 | General Maintenance | CON | 581 | 2024-05-09 | 2024-05-09 | 2671925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2671925
SPC | 12 | Washington | 120580 | SR 2023 over Branch of Little Pike Run- DFB | 2023 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 120580 | SR 2023 over Branch of Little Pike Run- DFB | 2023 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Washington | 120580 | SR 2023 over Branch of Little Pike Run- DFB | 2023 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 120605 | SR 1010 Flashing Beacon | 1010 | 01B | Safety Improvement | CON | HSIP | 2025-05-22 | 2025-05-22 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Washington | 120665 | SR 1045 over Branch of Chartiers Creek-DFB | 1045 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Washington | 120665 | SR 1045 over Branch of Chartiers Creek-DFB | 1045 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Washington | 120665 | SR 1045 over Branch of Chartiers Creek-DFB | 1045 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SPC | 12 | Washington | 120672 | SR 2051 over Branch of Daniels Run-DFB | 2051 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 120672 | SR 2051 over Branch of Daniels Run-DFB | 2051 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 120672 | SR 2051 over Branch of Daniels Run-DFB | 2051 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Washington | 120676 | SR 3001 over Buffalo Creek-DFB | 3001 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 120676 | SR 3001 over Buffalo Creek-DFB | 3001 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Washington | 120676 | SR 3001 over Buffalo Creek-DFB | 3001 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Washington | 121006 | Chartiers Creek #42- Brevard Bridge | 7207 | C42 | Bridge Replacement | PE | BRIP | 2028-02-17 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Washington | 121006 | Chartiers Creek #42- Brevard Bridge | 7207 | C42 | Bridge Replacement | FD | BOF | 2028-02-17 |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Washington | 121006 | Chartiers Creek #42- Brevard Bridge | 7207 | C42 | Bridge Replacement | ROW | BOF | 2028-02-17 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 121006 | Chartiers Creek #42- Brevard Bridge | 7207 | C42 | Bridge Replacement | UTL | BOF | 2028-02-17 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Washington | 121006 | Chartiers Creek #42- Brevard Bridge | 7207 | C42 | Bridge Replacement | CON | BOF | 2028-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 500000 | 0 | 1500000
SPC | 12 | Washington | 121012 | General Preservation 2025-2 | 19 | 21R | Bridge Restoration | CON | 581 | 2025-07-24 | 2025-07-24 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 12 | Washington | 121325 | I-70 Belle Vernon Bridge | 70 | 34M | Study Phase of Project | STUDY | NHPP | 2049-03-18 |  | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000
SPC | 12 | Washington | 121368 | Fiber Installation 1-79 | 79 | 0 | Intelligent Transportation System | CON | CRP |  |  | 1016304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016304
SPC | 12 | Washington | 121368 | Fiber Installation 1-79 | 79 | 0 | Intelligent Transportation System | CON | 581 |  |  | 254076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254076
SPC | 12 | Washington | 122504 | SR 1059 over Peters Creek | 1059 | 02M | Bridge Replacement | PE | 185 |  |  | 0 | 575000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575000
SPC | 12 | Washington | 122508 | PA 221 over Tenmile Creek | 221 | 07M | Bridge Restoration | PE | 185 |  |  | 0 | 400000 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 675000
SPC | 12 | Washington | 122788 | SR 4035 over South Fork Cross Creek | 4035 | K10 | Bridge Replacement | PE | 185 | 2026-10-22 |  | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 12 | Washington | 122895 | PA 519 over Branch of Westland Run | 519 | U10 | Bridge Restoration | PE | 581 | 2026-12-10 |  | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SPC | 12 | Westmoreland | 31554 | Fourth Street Bridge | 7421 | FSB | Bridge Replacement | CON | BOF | 2026-06-18 |  | 0 | 1000000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
SPC | 12 | Westmoreland | 31554 | Fourth Street Bridge | 7421 | FSB | Bridge Replacement | CON | STP | 2026-06-18 |  | 0 | 1000000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Westmoreland | 31554 | Fourth Street Bridge | 7421 | FSB | Bridge Replacement | CON | SXF | 2026-06-18 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Westmoreland | 31554 | Fourth Street Bridge | 7421 | FSB | Bridge Replacement | CON | LOC | 2026-06-18 |  | 0 | 700000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
SPC | 12 | Westmoreland | 31610 | SR 1029 over Spruce Run-DFB | 1029 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 31610 | SR 1029 over Spruce Run-DFB | 1029 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 31610 | SR 1029 over Spruce Run-DFB | 1029 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Westmoreland | 31634 | SR 1015 over Hypocrite Creek - DFB | 1015 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 31634 | SR 1015 over Hypocrite Creek - DFB | 1015 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 31634 | SR 1015 over Hypocrite Creek - DFB | 1015 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 31637 | SR 3073 over Meadow Run- DFB | 3073 | DFB | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 31637 | SR 3073 over Meadow Run- DFB | 3073 | DFB | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 31637 | SR 3073 over Meadow Run- DFB | 3073 | DFB | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 31669 | Fairwood Manor Bridge |  | FMB | Bridge Replacement | UTL | BRIP | 2023-10-05 | 2023-10-05 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
SPC | 12 | Westmoreland | 31669 | Fairwood Manor Bridge |  | FMB | Bridge Replacement | UTL | 183 | 2023-10-05 | 2023-10-05 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
SPC | 12 | Westmoreland | 31689 | Ladysmith Road T-470 |  | LSR | Bridge Restoration | PE | STP | 2028-02-03 |  | 0 | 414000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414000
SPC | 12 | Westmoreland | 31689 | Ladysmith Road T-470 |  | LSR | Bridge Restoration | FD | BOF | 2028-02-03 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Westmoreland | 31689 | Ladysmith Road T-470 |  | LSR | Bridge Restoration | ROW | BOF | 2028-02-03 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Westmoreland | 31689 | Ladysmith Road T-470 |  | LSR | Bridge Restoration | UTL | BOF | 2028-02-03 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Westmoreland | 31689 | Ladysmith Road T-470 |  | LSR | Bridge Restoration | CON | BRIP | 2028-02-03 |  | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Westmoreland | 31706 | Rocky Mountain Road Bridge |  | RMR | Bridge Restoration | PE | BOF | 2028-02-03 |  | 350000 | 107000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457000
SPC | 12 | Westmoreland | 31706 | Rocky Mountain Road Bridge |  | RMR | Bridge Restoration | FD | BOF | 2028-02-03 |  | 0 | 501000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501000
SPC | 12 | Westmoreland | 31706 | Rocky Mountain Road Bridge |  | RMR | Bridge Restoration | ROW | STP | 2028-02-03 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 31706 | Rocky Mountain Road Bridge |  | RMR | Bridge Restoration | UTL | STP | 2028-02-03 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 31927 | Possum Hollow Road | 7209 | PHR | Bridge Replacement | CON | STP | 2029-12-13 |  | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Westmoreland | 67722 | T-479 Fry Hollow Rd Br | 7209 | FHR | Bridge Restoration | PE | BOF | 2028-12-14 |  | 350000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000
SPC | 12 | Westmoreland | 69248 | PA 136 over Pollock Run | 136 | B10 | Bridge Replacement | CON | BRIP | 2024-07-25 | 2024-07-25 | 1511632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1511632
SPC | 12 | Westmoreland | 73028 | Brewery Street Bridge | 7302 | BSB | Bridge Restoration | PE | BOF | 2028-02-17 |  | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 12 | Westmoreland | 73028 | Brewery Street Bridge | 7302 | BSB | Bridge Restoration | PE | STP | 2028-02-17 |  | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
SPC | 12 | Westmoreland | 73028 | Brewery Street Bridge | 7302 | BSB | Bridge Restoration | FD | BOF | 2028-02-17 |  | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SPC | 12 | Westmoreland | 73028 | Brewery Street Bridge | 7302 | BSB | Bridge Restoration | ROW | BOF | 2028-02-17 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Westmoreland | 73028 | Brewery Street Bridge | 7302 | BSB | Bridge Restoration | UTL | BOF | 2028-02-17 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Westmoreland | 73028 | Brewery Street Bridge | 7302 | BSB | Bridge Restoration | CON | BRIP | 2028-02-17 |  | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 1500000
SPC | 12 | Westmoreland | 74261 | SR 3035 over Barren Run- DFB | 3035 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 74261 | SR 3035 over Barren Run- DFB | 3035 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 74261 | SR 3035 over Barren Run- DFB | 3035 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 76123 | PA 711 ov Br of Tubmill Ck | 711 | 10A | Bridge Replacement | CON | BRIP | 2022-12-15 | 2022-12-15 | 592948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592948
SPC | 12 | Westmoreland | 81747 | Salina Bridge | 1060 | A20 | Bridge Replacement | CON | STP | 2024-01-11 | 2024-01-11 | 8242829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8242829
SPC | 12 | Westmoreland | 81751 | PA 356 over Pine Run | 356 | D10 | Bridge Replacement | CON | NHPP | 2023-01-26 | 2023-01-26 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SPC | 12 | Westmoreland | 81938 | SR 2014 over Slate Creek-DFB | 2014 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 81938 | SR 2014 over Slate Creek-DFB | 2014 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 81938 | SR 2014 over Slate Creek-DFB | 2014 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Westmoreland | 81960 | SR 4012 over Brush Creek | 4012 | A10 | Bridge Replacement | CON | STU | 2023-04-13 | 2023-04-13 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 12 | Westmoreland | 81972 | SR 4067 over Branch of Pine Run-DFB | 4067 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 81972 | SR 4067 over Branch of Pine Run-DFB | 4067 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 81972 | SR 4067 over Branch of Pine Run-DFB | 4067 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 81991 | SR 3016 over Br Sewickley Creek - DFB | 3016 | C20 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 81991 | SR 3016 over Br Sewickley Creek - DFB | 3016 | C20 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 81991 | SR 3016 over Br Sewickley Creek - DFB | 3016 | C20 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 83686 | SR 4073 over PA 56 | 4073 | 02M | Bridge Replacement | FD | STP | 2026-10-22 |  | 575000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575000
SPC | 12 | Westmoreland | 83686 | SR 4073 over PA 56 | 4073 | 02M | Bridge Replacement | ROW | STP | 2026-10-22 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 12 | Westmoreland | 83686 | SR 4073 over PA 56 | 4073 | 02M | Bridge Replacement | UTL | STP | 2026-10-22 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 12 | Westmoreland | 83686 | SR 4073 over PA 56 | 4073 | 02M | Bridge Replacement | CON | 581 | 2026-10-22 |  | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 4000000
SPC | 12 | Westmoreland | 88617 | PA 366 over PA 400/380 | 366 | 0 | Bridge Replacement | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1048800 | 0 | 1048800
SPC | 12 | Westmoreland | 88617 | PA 366 over PA 400/380 | 366 | 0 | Bridge Replacement | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262200 | 0 | 262200
SPC | 12 | Westmoreland | 88617 | PA 366 over PA 400/380 | 366 | 0 | Bridge Replacement | FD | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
SPC | 12 | Westmoreland | 88617 | PA 366 over PA 400/380 | 366 | 0 | Bridge Replacement | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
SPC | 12 | Westmoreland | 88617 | PA 366 over PA 400/380 | 366 | 0 | Bridge Replacement | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17790160 | 17790160
SPC | 12 | Westmoreland | 88617 | PA 366 over PA 400/380 | 366 | 0 | Bridge Replacement | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4447540 | 4447540
SPC | 12 | Westmoreland | 89066 | SR 4019 over Brush Creek | 4019 | C10 | Bridge Restoration | FD | STP | 2026-12-10 |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 12 | Westmoreland | 89066 | SR 4019 over Brush Creek | 4019 | C10 | Bridge Restoration | ROW | 185 | 2026-12-10 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 12 | Westmoreland | 89066 | SR 4019 over Brush Creek | 4019 | C10 | Bridge Restoration | UTL | 185 | 2026-12-10 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 12 | Westmoreland | 89066 | SR 4019 over Brush Creek | 4019 | C10 | Bridge Restoration | CON | STP | 2026-12-10 |  | 0 | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000
SPC | 12 | Westmoreland | 90666 | SR 3021 over Trib of Mon River-DFB | 3021 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Westmoreland | 90666 | SR 3021 over Trib of Mon River-DFB | 3021 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Westmoreland | 90666 | SR 3021 over Trib of Mon River-DFB | 3021 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
SPC | 12 | Westmoreland | 90675 | SR 2001 over Branch Jacobs Creek-DFB | 2001 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Westmoreland | 90675 | SR 2001 over Branch Jacobs Creek-DFB | 2001 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Westmoreland | 90675 | SR 2001 over Branch Jacobs Creek-DFB | 2001 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
SPC | 12 | Westmoreland | 90821 | SR 3005 ov Br Speers Run-DFB | 3005 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 90821 | SR 3005 ov Br Speers Run-DFB | 3005 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 90821 | SR 3005 ov Br Speers Run-DFB | 3005 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Westmoreland | 90833 | SR 4037 over Bull Run- DFB | 4037 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 90833 | SR 4037 over Bull Run- DFB | 4037 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 90833 | SR 4037 over Bull Run- DFB | 4037 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 91121 | SR 3024 over Br Long Run- DFB | 3024 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 91121 | SR 3024 over Br Long Run- DFB | 3024 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 91121 | SR 3024 over Br Long Run- DFB | 3024 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 91136 | PA 906 over Trib Mon River | 906 | 0 | Bridge Restoration | PE | 185 |  |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Westmoreland | 91136 | PA 906 over Trib Mon River | 906 | 0 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 12 | Westmoreland | 91136 | PA 906 over Trib Mon River | 906 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 91136 | PA 906 over Trib Mon River | 906 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 91136 | PA 906 over Trib Mon River | 906 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Westmoreland | 98865 | SR 3044 over Little Sewickley Creek | 3044 | 19M | Bridge Restoration | PE | 581 | 2027-06-10 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Westmoreland | 98865 | SR 3044 over Little Sewickley Creek | 3044 | 19M | Bridge Restoration | FD | 185 | 2027-06-10 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 12 | Westmoreland | 98865 | SR 3044 over Little Sewickley Creek | 3044 | 19M | Bridge Restoration | ROW | 185 | 2027-06-10 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 98865 | SR 3044 over Little Sewickley Creek | 3044 | 19M | Bridge Restoration | UTL | 185 | 2027-06-10 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 98865 | SR 3044 over Little Sewickley Creek | 3044 | 19M | Bridge Restoration | CON | BOF | 2027-06-10 |  | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 800000
SPC | 12 | Westmoreland | 98865 | SR 3044 over Little Sewickley Creek | 3044 | 19M | Bridge Restoration | CON | 185 | 2027-06-10 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Westmoreland | 98869 | West Newton Bridge | 136 | C10 | Reserve Line Item | FD | STP | 2026-05-07 |  | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
SPC | 12 | Westmoreland | 98869 | West Newton Bridge | 136 | C10 | Reserve Line Item | CON | BRIP | 2026-05-07 |  | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000
SPC | 12 | Westmoreland | 98869 | West Newton Bridge | 136 | C10 | Reserve Line Item | CON | RAISE | 2026-05-07 |  | 0 | 17000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000000
SPC | 12 | Westmoreland | 98869 | West Newton Bridge | 136 | C10 | Reserve Line Item | CON | 581 | 2026-05-07 |  | 0 | 500000 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 12 | Westmoreland | 103190 | Vine Street Grade Xing |  |  | Rail Highway Grade Crossing | CON | RRX | 2018-12-13 |  | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000
SPC | 12 | Westmoreland | 105320 | SR 3031 over Smithton Run-DFB | 3031 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 105320 | SR 3031 over Smithton Run-DFB | 3031 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 105320 | SR 3031 over Smithton Run-DFB | 3031 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Westmoreland | 105332 | SR 3017 over Branch Cedar Creek - DFB | 3017 | 0 | Bridge Replacement | ROW | 185 | 2030-06-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 105332 | SR 3017 over Branch Cedar Creek - DFB | 3017 | 0 | Bridge Replacement | UTL | 185 | 2030-06-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 105332 | SR 3017 over Branch Cedar Creek - DFB | 3017 | 0 | Bridge Replacement | CON | 185 | 2030-06-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 105350 | PA 201 Ramp to PA 51 Bridges | 51 | 0 | Safety Improvement | PE | 185 | 2029-10-01 |  | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Westmoreland | 105350 | PA 201 Ramp to PA 51 Bridges | 51 | 0 | Safety Improvement | FD | STP | 2029-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000
SPC | 12 | Westmoreland | 105350 | PA 201 Ramp to PA 51 Bridges | 51 | 0 | Safety Improvement | ROW | STP | 2029-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000
SPC | 12 | Westmoreland | 105350 | PA 201 Ramp to PA 51 Bridges | 51 | 0 | Safety Improvement | UTL | STP | 2029-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000
SPC | 12 | Westmoreland | 105350 | PA 201 Ramp to PA 51 Bridges | 51 | 0 | Safety Improvement | CON | NHPP | 2029-10-01 |  | 0 | 0 | 0 | 0 | 6000000 | 0 | 0 | 0 | 0 | 6000000
SPC | 12 | Westmoreland | 105818 | SR 1049 ov Br Ltl Crabtree Ck-DFB | 1049 | A20 | Bridge Restoration | ROW | 185 | 2025-10-09 | 2025-07-10 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SPC | 12 | Westmoreland | 105818 | SR 1049 ov Br Ltl Crabtree Ck-DFB | 1049 | A20 | Bridge Restoration | UTL | 185 | 2025-10-09 | 2025-07-10 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 105818 | SR 1049 ov Br Ltl Crabtree Ck-DFB | 1049 | A20 | Bridge Restoration | UTL | 581 | 2025-10-09 | 2025-07-10 | 0 | 79245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79245
SPC | 12 | Westmoreland | 105818 | SR 1049 ov Br Ltl Crabtree Ck-DFB | 1049 | A20 | Bridge Restoration | CON | 185 | 2025-10-09 | 2025-07-10 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 105821 | SR 1021 over Br Loyalhanna Ck-DFB | 1021 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 105821 | SR 1021 over Br Loyalhanna Ck-DFB | 1021 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 105821 | SR 1021 over Br Loyalhanna Ck-DFB | 1021 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Westmoreland | 105837 | PA 982 over Sawmill Run | 982 | 0 | Bridge Replacement | PE | 185 |  |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Westmoreland | 105837 | PA 982 over Sawmill Run | 982 | 0 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 12 | Westmoreland | 105837 | PA 982 over Sawmill Run | 982 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 12 | Westmoreland | 105837 | PA 982 over Sawmill Run | 982 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 12 | Westmoreland | 105837 | PA 982 over Sawmill Run | 982 | 0 | Bridge Replacement | CON | STU |  |  | 0 | 0 | 0 | 0 | 1850000 | 0 | 0 | 0 | 0 | 1850000
SPC | 12 | Westmoreland | 106061 | Bridge Street and Eureka Hill Grade Crossings | 981 | RRX | Rail Highway Grade Crossing | CON | RRX | 2021-04-15 | 2021-04-15 | 4075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4075
SPC | 12 | Westmoreland | 106406 | West Co Local Br Preservation | 7204 | PSV | Bridge Preservation - Federal | FD | STU | 2026-06-18 |  | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
SPC | 12 | Westmoreland | 106406 | West Co Local Br Preservation | 7204 | PSV | Bridge Preservation - Federal | CON | STP | 2026-06-18 |  | 0 | 0 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
SPC | 12 | Westmoreland | 106406 | West Co Local Br Preservation | 7204 | PSV | Bridge Preservation - Federal | CON | SXF | 2026-06-18 |  | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
SPC | 12 | Westmoreland | 108010 | LVTIP: Norvelt to Pleasant Unity | 981 | V20 | Highway Reconstruction | FD | 581 | 2028-06-08 |  | 0 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000
SPC | 12 | Westmoreland | 108010 | LVTIP: Norvelt to Pleasant Unity | 981 | V20 | Highway Reconstruction | CON | STP | 2028-06-08 |  | 0 | 0 | 0 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 10000000
SPC | 12 | Westmoreland | 108010 | LVTIP: Norvelt to Pleasant Unity | 981 | V20 | Highway Reconstruction | CON | STU | 2028-06-08 |  | 0 | 0 | 0 | 8703720 | 4600000 | 0 | 0 | 0 | 0 | 13303720
SPC | 12 | Westmoreland | 108010 | LVTIP: Norvelt to Pleasant Unity | 981 | V20 | Highway Reconstruction | CON | 581 | 2028-06-08 |  | 0 | 0 | 3431720 | 3431720 | 14253720 | 0 | 0 | 0 | 0 | 21117160
SPC | 12 | Westmoreland | 108140 | LVTIP: Pleasant Unity to Airport | 981 | Y10 | New Alignment | CON | STP | 2025-10-09 | 2025-10-09 | 40680138 | 519862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41200000
SPC | 12 | Westmoreland | 108140 | LVTIP: Pleasant Unity to Airport | 981 | Y10 | New Alignment | CON | STU | 2025-10-09 | 2025-10-09 | 3000000 | 8726882 | 4600000 | 0 | 0 | 0 | 0 | 0 | 0 | 16326882
SPC | 12 | Westmoreland | 110900 | US 30 Corridor Impvmts - Western Section | 30 | A10 | Congestion Reduction | FD | NHPP | 2028-12-14 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
SPC | 12 | Westmoreland | 110900 | US 30 Corridor Impvmts - Western Section | 30 | A10 | Congestion Reduction | ROW | CAQ | 2028-12-14 |  | 4534032 | 6465968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000000
SPC | 12 | Westmoreland | 110900 | US 30 Corridor Impvmts - Western Section | 30 | A10 | Congestion Reduction | UTL | CAQ | 2028-12-14 |  | 4300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4300000
SPC | 12 | Westmoreland | 110900 | US 30 Corridor Impvmts - Western Section | 30 | A10 | Congestion Reduction | CON | NHPP | 2028-12-14 |  | 0 | 0 | 0 | 4000000 | 8000000 | 10000000 | 7600000 | 4000000 | 0 | 33600000
SPC | 12 | Westmoreland | 110900 | US 30 Corridor Impvmts - Western Section | 30 | A10 | Congestion Reduction | CON | STP | 2028-12-14 |  | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 800000
SPC | 12 | Westmoreland | 110900 | US 30 Corridor Impvmts - Western Section | 30 | A10 | Congestion Reduction | CON | 581 | 2028-12-14 |  | 0 | 0 | 0 | 1000000 | 2200000 | 2000000 | 2200000 | 1000000 | 0 | 8400000
SPC | 12 | Westmoreland | 112391 | Vandergrift Bridge Preservation | 56 | 0 | Bridge Restoration | CON | BRIP | 2031-02-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5203645 | 0 | 0 | 5203645
SPC | 12 | Westmoreland | 112391 | Vandergrift Bridge Preservation | 56 | 0 | Bridge Restoration | CON | 185 | 2031-02-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1300911 | 0 | 0 | 1300911
SPC | 12 | Westmoreland | 112395 | Leechburg Bridge Preservation | 4093 | 0 | Bridge Restoration | CON | 185 | 2029-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600000 | 0 | 4600000
SPC | 12 | Westmoreland | 112554 | SR 4041 over Haymakers Run | 4041 | D10 | Bridge Restoration | CON | BOF | 2022-12-15 | 2022-12-15 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Westmoreland | 112902 | SR 4091 ov Stream to Kiski River | 4091 | 01M | Bridge Replacement | PE | 581 |  |  | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Westmoreland | 112902 | SR 4091 ov Stream to Kiski River | 4091 | 01M | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
SPC | 12 | Westmoreland | 112902 | SR 4091 ov Stream to Kiski River | 4091 | 01M | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 112902 | SR 4091 ov Stream to Kiski River | 4091 | 01M | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 112902 | SR 4091 ov Stream to Kiski River | 4091 | 01M | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 2000000
SPC | 12 | Westmoreland | 112980 | SR 3059 over Hunters Run - DFB | 3059 | C10 | Bridge Replacement | ROW | 185 | 2024-12-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 112980 | SR 3059 over Hunters Run - DFB | 3059 | C10 | Bridge Replacement | UTL | 185 | 2024-12-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 112980 | SR 3059 over Hunters Run - DFB | 3059 | C10 | Bridge Replacement | CON | 185 | 2024-12-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Westmoreland | 113267 | New Kensington Corridor | 4087 | RRX | Rail Highway Grade Crossing | CON | RRX | 2023-04-05 |  | 2926927 | 2327080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5254007
SPC | 12 | Westmoreland | 113784 | US 30 over Loyalhanna Creek | 30 | 18M | Bridge Restoration | CON | 581 | 2024-10-10 | 2024-10-10 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Westmoreland | 113823 | Donohoe Road/Georges Station Intersection | 1026 | A10 | Safety Improvement | FD | STP | 2028-04-06 |  | 0 | 0 | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | 1700000
SPC | 12 | Westmoreland | 113823 | Donohoe Road/Georges Station Intersection | 1026 | A10 | Safety Improvement | ROW | 581 | 2028-04-06 |  | 0 | 0 | 0 | 0 | 1000000 | 750000 | 0 | 0 | 0 | 1750000
SPC | 12 | Westmoreland | 113823 | Donohoe Road/Georges Station Intersection | 1026 | A10 | Safety Improvement | UTL | 581 | 2028-04-06 |  | 0 | 0 | 0 | 0 | 1250000 | 0 | 0 | 0 | 0 | 1250000
SPC | 12 | Westmoreland | 113823 | Donohoe Road/Georges Station Intersection | 1026 | A10 | Safety Improvement | CON | STP | 2028-04-06 |  | 0 | 0 | 2000000 | 3850000 | 0 | 0 | 0 | 0 | 0 | 5850000
SPC | 12 | Westmoreland | 114560 | 119 SW Greensburg CMAQ | 119 | SE8 | Congestion Reduction | PE | CAQ | 2027-01-14 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Westmoreland | 114560 | 119 SW Greensburg CMAQ | 119 | SE8 | Congestion Reduction | CON | CAQ | 2027-01-14 |  | 793108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 793108
SPC | 12 | Westmoreland | 114560 | 119 SW Greensburg CMAQ | 119 | SE8 | Congestion Reduction | CON | CRP | 2027-01-14 |  | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 12 | Westmoreland | 114563 | 30 Hempfield on Corridor 95 | 30 | CQ1 | Congestion Reduction | PE | CRPU | 2027-12-09 |  | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
SPC | 12 | Westmoreland | 115909 | Rostraver Township Pedestrian Bridge | 70 | 01P | Bridge Replacement | CON | STP | 2024-09-26 | 2024-09-26 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 12 | Westmoreland | 115909 | Rostraver Township Pedestrian Bridge | 70 | 01P | Bridge Replacement | CON | STU | 2024-09-26 | 2024-09-26 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SPC | 12 | Westmoreland | 116179 | PA 66 Pavement Preservation | 66 | 12M | General Maintenance | ROW | 581 | 2026-06-04 |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
SPC | 12 | Westmoreland | 116179 | PA 66 Pavement Preservation | 66 | 12M | General Maintenance | CON | HSIP | 2026-06-04 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 116179 | PA 66 Pavement Preservation | 66 | 12M | General Maintenance | CON | HVRU | 2026-06-04 |  | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
SPC | 12 | Westmoreland | 116179 | PA 66 Pavement Preservation | 66 | 12M | General Maintenance | CON | NHPP | 2026-06-04 |  | 0 | 11500000 | 3900000 | 0 | 0 | 0 | 0 | 0 | 0 | 15400000
SPC | 12 | Westmoreland | 116461 | I-70 @ PA 201 Interchange PEL | 70 | PEL | Study Phase of Project | STUDY | HSIP |  |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 12 | Westmoreland | 116461 | I-70 @ PA 201 Interchange PEL | 70 | PEL | Study Phase of Project | STUDY | NHPP |  |  | 2500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 12 | Westmoreland | 116465 | SR 1049 over Br Little Crabtree Creek (Seg 40)-DFB | 1049 | B10 | Bridge Replacement | ROW | 185 | 2027-06-01 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 116465 | SR 1049 over Br Little Crabtree Creek (Seg 40)-DFB | 1049 | B10 | Bridge Replacement | UTL | 185 | 2027-06-01 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 116465 | SR 1049 over Br Little Crabtree Creek (Seg 40)-DFB | 1049 | B10 | Bridge Replacement | CON | 185 | 2027-06-01 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 116467 | SR 1049 over Br Little Crabtree Creek (Seg 20)-DFB | 1049 | A10 | Bridge Restoration | ROW | 185 | 2025-10-09 | 2025-07-10 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 116467 | SR 1049 over Br Little Crabtree Creek (Seg 20)-DFB | 1049 | A10 | Bridge Restoration | UTL | 185 | 2025-10-09 | 2025-07-10 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 116467 | SR 1049 over Br Little Crabtree Creek (Seg 20)-DFB | 1049 | A10 | Bridge Restoration | CON | 185 | 2025-10-09 | 2025-07-10 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 116470 | SR 3063 over Andrews Run-DFB | 3063 | A10 | Bridge Replacement | ROW | 185 | 2026-10-01 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 116470 | SR 3063 over Andrews Run-DFB | 3063 | A10 | Bridge Replacement | UTL | 185 | 2026-10-01 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 116470 | SR 3063 over Andrews Run-DFB | 3063 | A10 | Bridge Replacement | CON | 185 | 2026-10-01 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 116471 | SR 4041 over Br of Brush Run-DFB | 4041 | 02M | Bridge Restoration | ROW | 185 | 2025-10-09 | 2025-07-10 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 116471 | SR 4041 over Br of Brush Run-DFB | 4041 | 02M | Bridge Restoration | UTL | 185 | 2025-10-09 | 2025-07-10 | 25000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
SPC | 12 | Westmoreland | 116471 | SR 4041 over Br of Brush Run-DFB | 4041 | 02M | Bridge Restoration | CON | 185 | 2025-10-09 | 2025-07-10 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 116790 | Freeport Bridge Truss Preservation | 356 | 12M | Bridge Restoration | CON | 185 | 2027-03-11 |  | 0 | 0 | 0 | 1000000 | 3000000 | 0 | 0 | 0 | 0 | 4000000
SPC | 12 | Westmoreland | 116917 | Bridge Bearing Preservation | 30 | 22M | Bridge Restoration | CON | BRIP | 2024-11-07 | 2024-11-07 | 0 | 0 | 0 | 0 | 0 | 1195831 | 0 | 0 | 0 | 1195831
SPC | 12 | Westmoreland | 116917 | Bridge Bearing Preservation | 30 | 22M | Bridge Restoration | CON | 185 | 2024-11-07 | 2024-11-07 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 12 | Westmoreland | 116917 | Bridge Bearing Preservation | 30 | 22M | Bridge Restoration | CON | 581 | 2024-11-07 | 2024-11-07 | 0 | 0 | 0 | 0 | 0 | 298958 | 0 | 0 | 0 | 298958
SPC | 12 | Westmoreland | 117558 | 2026 D12 Expansion Dam | 119 | 21M | Bridge Restoration | CON | 185 | 2026-05-21 |  | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 1500000
SPC | 12 | Westmoreland | 118324 | 2023 On Demand Bridge Contract | 3041 | ODB | Bridge Preservation - State Funded | CON | 185 | 2023-07-27 | 2023-07-27 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
SPC | 12 | Westmoreland | 118713 | Westmoreland County Epoxy Overlay - 2023 | 22 | 05M | Bridge Restoration | CON | 185 | 2024-12-12 | 2024-12-12 | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700000
SPC | 12 | Westmoreland | 118883 | SR 1014 over MaGee Run Preservation | 1014 | 03M | Bridge Preservation - State Funded | CON | 185 | 2024-12-12 | 2024-12-12 | 1986235 | 13765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
SPC | 12 | Westmoreland | 119608 | US 30 over SR 3077 Bridge Preservation | 30 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 4738000 | 4738000 | 0 | 0 | 9476000
SPC | 12 | Westmoreland | 119609 | SR 4002 North Greengate Road & RR Tunnel | 4002 | 01M | Safety Improvement | PE | STP |  |  | 500000 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000
SPC | 12 | Westmoreland | 119609 | SR 4002 North Greengate Road & RR Tunnel | 4002 | 01M | Safety Improvement | PE | 581 |  |  | 125000 | 437500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562500
SPC | 12 | Westmoreland | 119609 | SR 4002 North Greengate Road & RR Tunnel | 4002 | 01M | Safety Improvement | FD | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2207040 | 0 | 0 | 2207040
SPC | 12 | Westmoreland | 119609 | SR 4002 North Greengate Road & RR Tunnel | 4002 | 01M | Safety Improvement | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 551760 | 0 | 0 | 551760
SPC | 12 | Westmoreland | 119609 | SR 4002 North Greengate Road & RR Tunnel | 4002 | 01M | Safety Improvement | ROW | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 72600 | 0 | 0 | 72600
SPC | 12 | Westmoreland | 119609 | SR 4002 North Greengate Road & RR Tunnel | 4002 | 01M | Safety Improvement | ROW | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18150 | 0 | 0 | 18150
SPC | 12 | Westmoreland | 119609 | SR 4002 North Greengate Road & RR Tunnel | 4002 | 01M | Safety Improvement | UTL | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 72600 | 0 | 0 | 72600
SPC | 12 | Westmoreland | 119609 | SR 4002 North Greengate Road & RR Tunnel | 4002 | 01M | Safety Improvement | UTL | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18150 | 0 | 0 | 18150
SPC | 12 | Westmoreland | 119609 | SR 4002 North Greengate Road & RR Tunnel | 4002 | 01M | Safety Improvement | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15748000 | 15748000
SPC | 12 | Westmoreland | 119609 | SR 4002 North Greengate Road & RR Tunnel | 4002 | 01M | Safety Improvement | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3937000 | 3937000
SPC | 12 | Westmoreland | 119610 | US 119 West Tech to PA 66 | 119 | 0 | Bridge Restoration | PE | NHPP | 2029-09-13 |  | 0 | 2000000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000
SPC | 12 | Westmoreland | 119610 | US 119 West Tech to PA 66 | 119 | 0 | Bridge Restoration | CON | NHPP | 2029-09-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4840000 | 4840000
SPC | 12 | Westmoreland | 119610 | US 119 West Tech to PA 66 | 119 | 0 | Bridge Restoration | CON | 185 | 2029-09-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210000 | 1210000
SPC | 12 | Westmoreland | 119625 | US 119 West Tec Drive Preservation | 119 | 0 | Highway Restoration | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 4248000 | 0 | 0 | 0 | 4248000
SPC | 12 | Westmoreland | 119625 | US 119 West Tec Drive Preservation | 119 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 1062000 | 0 | 0 | 0 | 1062000
SPC | 12 | Westmoreland | 119637 | PA 66: US 22 to County Line | 66 | 0 | Highway Reconstruction | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6979280 | 6979280
SPC | 12 | Westmoreland | 119637 | PA 66: US 22 to County Line | 66 | 0 | Highway Reconstruction | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1744820 | 1744820
SPC | 12 | Westmoreland | 119638 | PA 130 Corridor Review & Improvements | 130 | 06M | Highway Reconstruction | PE | 581 |  |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 12 | Westmoreland | 119640 | SR 4032 Recon: 7th Street to Turkey Ridge Road | 4032 | 0 | Highway Reconstruction | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4960000 | 0 | 4960000
SPC | 12 | Westmoreland | 119640 | SR 4032 Recon: 7th Street to Turkey Ridge Road | 4032 | 0 | Highway Reconstruction | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1240000 | 0 | 1240000
SPC | 12 | Westmoreland | 119659 | Westmoreland County Concrete Patching Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 4600000 | 0 | 0 | 0 | 4600000
SPC | 12 | Westmoreland | 119659 | Westmoreland County Concrete Patching Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 1150000 | 0 | 0 | 0 | 1150000
SPC | 12 | Westmoreland | 120011 | SR 1051 over Little Crabtree Creek-DFB | 1051 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Westmoreland | 120011 | SR 1051 over Little Crabtree Creek-DFB | 1051 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
SPC | 12 | Westmoreland | 120011 | SR 1051 over Little Crabtree Creek-DFB | 1051 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
SPC | 12 | Westmoreland | 120056 | SR 3014 over Sewickley Creek | 3014 | 0 | Bridge Replacement | PE | BOF |  |  | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
SPC | 12 | Westmoreland | 120056 | SR 3014 over Sewickley Creek | 3014 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SPC | 12 | Westmoreland | 120056 | SR 3014 over Sewickley Creek | 3014 | 0 | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 400000
SPC | 12 | Westmoreland | 120056 | SR 3014 over Sewickley Creek | 3014 | 0 | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 120056 | SR 3014 over Sewickley Creek | 3014 | 0 | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 120056 | SR 3014 over Sewickley Creek | 3014 | 0 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000
SPC | 12 | Westmoreland | 120608 | Municipal Bridge 25 | 7209 | 0 | Reserve Line Item | PE | BOF |  |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Westmoreland | 120608 | Municipal Bridge 25 | 7209 | 0 | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
SPC | 12 | Westmoreland | 120639 | SR 4006 Flashing Beacon | 4006 | 01B | Safety Improvement | CON | HSIP |  | 2025-05-22 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 120641 | US 30 at Cedar Street Improvements | 30 | 24M | Safety Improvement | CON | HSIP | 2025-06-26 | 2025-07-24 | 247000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247000
SPC | 12 | Westmoreland | 120660 | SR 2031 over Keffer Run-DFB | 2031 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 120660 | SR 2031 over Keffer Run-DFB | 2031 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 120660 | SR 2031 over Keffer Run-DFB | 2031 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 120662 | SR 2025 over Branch of Welty Run-DFB | 2025 | 0 | Bridge Restoration | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 120662 | SR 2025 over Branch of Welty Run-DFB | 2025 | 0 | Bridge Restoration | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 120662 | SR 2025 over Branch of Welty Run-DFB | 2025 | 0 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 120666 | SR 4034 over Chartiers Run-DFB | 4034 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 120666 | SR 4034 over Chartiers Run-DFB | 4034 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 120666 | SR 4034 over Chartiers Run-DFB | 4034 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 120667 | SR 1019 over Branch of Hannas Run-DFB | 1019 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 120667 | SR 1019 over Branch of Hannas Run-DFB | 1019 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
SPC | 12 | Westmoreland | 120667 | SR 1019 over Branch of Hannas Run-DFB | 1019 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 120677 | SR 4023 over Branch of Brush Creek- DFB | 4023 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 120677 | SR 4023 over Branch of Brush Creek- DFB | 4023 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 120677 | SR 4023 over Branch of Brush Creek- DFB | 4023 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Westmoreland | 120678 | SR 1046 over Branch of Loyalhanna Creek- DFB | 1046 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 120678 | SR 1046 over Branch of Loyalhanna Creek- DFB | 1046 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 120678 | SR 1046 over Branch of Loyalhanna Creek- DFB | 1046 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Westmoreland | 120968 | 2026 Bridge Preservation | 30 | 23M | Bridge Restoration | CON | 185 | 2026-06-18 |  | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 4000000
SPC | 12 | Westmoreland | 120978 | SR 1028 ov Br Ltl Crabtree Ck-DFB | 1028 | 0 | Bridge Replacement | ROW | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 120978 | SR 1028 ov Br Ltl Crabtree Ck-DFB | 1028 | 0 | Bridge Replacement | UTL | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SPC | 12 | Westmoreland | 120978 | SR 1028 ov Br Ltl Crabtree Ck-DFB | 1028 | 0 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SPC | 12 | Westmoreland | 121009 | T-880 Bridge #2, Donegal Twp | 7205 | 880 | Bridge Replacement | PE | STU | 2027-10-21 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Westmoreland | 121009 | T-880 Bridge #2, Donegal Twp | 7205 | 880 | Bridge Replacement | FD | BOF | 2027-10-21 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Westmoreland | 121009 | T-880 Bridge #2, Donegal Twp | 7205 | 880 | Bridge Replacement | ROW | STP | 2027-10-21 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 121009 | T-880 Bridge #2, Donegal Twp | 7205 | 880 | Bridge Replacement | UTL | STP | 2027-10-21 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SPC | 12 | Westmoreland | 121009 | T-880 Bridge #2, Donegal Twp | 7205 | 880 | Bridge Replacement | CON | BRIP | 2027-10-21 |  | 0 | 0 | 0 | 0 | 750000 | 750000 | 0 | 0 | 0 | 1500000
SPC | 12 | Westmoreland | 121011 | Bells Mill Bridge | 7215 | 0 | Bridge Replacement | PE | BOF |  |  | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Westmoreland | 121011 | Bells Mill Bridge | 7215 | 0 | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
SPC | 12 | Westmoreland | 121011 | Bells Mill Bridge | 7215 | 0 | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Westmoreland | 121011 | Bells Mill Bridge | 7215 | 0 | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SPC | 12 | Westmoreland | 121011 | Bells Mill Bridge | 7215 | 0 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 500000 | 0 | 1500000
SPC | 12 | Westmoreland | 122507 | SR 1061 over Beaver Run | 1061 | 01M | Bridge Restoration | PE | 185 |  |  | 0 | 800000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000
SPC | 12 | Westmoreland | 123278 | PA 66/ PA 366 Safety Improvement | 66 | 0 | Safety Improvement | PE | HSIP |  |  | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
SPC | 12 | Westmoreland | 123283 | PA 217 at Industrial Blvd Safety Improvement | 217 | 0 | Safety Improvement | PE | HSIP |  |  | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 12 | Westmoreland | 123592 | US 30 at Wimmerton | 30 | 25M | Safety Improvement | CON | HSIP | 2026-04-23 |  | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
SPC | 99 | Central Office | 123600 | City of Pittsburgh Intersection Updates |  |  | General Maintenance | CON | 073 |  | 2024-07-25 | 0 | 545885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545885
SPC | 99 | Central Office | 123600 | City of Pittsburgh Intersection Updates |  |  | General Maintenance | CON | LOC |  | 2024-07-25 | 0 | 136472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136472
SVTS | 1 | Mercer | 1463 | SR 1008 Bridge over Otter Creek | 1008 | B00 | Bridge Preservation - Federal | CON | BOF |  |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SVTS | 1 | Mercer | 1475 | SR 4002 Coal Hill Road Bridge over Big Run | 4002 | B02 | Bridge Restoration | FD | 185 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 75000
SVTS | 1 | Mercer | 1475 | SR 4002 Coal Hill Road Bridge over Big Run | 4002 | B02 | Bridge Restoration | CON | 185 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 500000
SVTS | 1 | Mercer | 1580 | SR 58: Grove City to Butler Cty Line | 58 | 462 | General Maintenance | CON | HSIP | 2026-04-23 |  | 0 | 33118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33118
SVTS | 1 | Mercer | 1665 | Gilmore Rd (T-481) Bridges |  | L00 | Bridge Restoration | ROW | STP | 2024-09-26 | 2024-09-26 | 13216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13216
SVTS | 1 | Mercer | 1665 | Gilmore Rd (T-481) Bridges |  | L00 | Bridge Restoration | CON | BOF | 2024-09-26 | 2024-09-26 | 214305 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264305
SVTS | 1 | Mercer | 1665 | Gilmore Rd (T-481) Bridges |  | L00 | Bridge Restoration | CON | BRIP | 2024-09-26 | 2024-09-26 | 160721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160721
SVTS | 1 | Mercer | 1670 | Old Mercer Rd (T-401) Bridge over Nashannock Creek | 7204 | L00 | Bridge Replacement | PE | BOF | 2025-09-25 | 2025-09-25 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000
SVTS | 1 | Mercer | 1670 | Old Mercer Rd (T-401) Bridge over Nashannock Creek | 7204 | L00 | Bridge Replacement | PE | 185 | 2025-09-25 | 2025-09-25 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000
SVTS | 1 | Mercer | 1670 | Old Mercer Rd (T-401) Bridge over Nashannock Creek | 7204 | L00 | Bridge Replacement | PE | LOC | 2025-09-25 | 2025-09-25 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
SVTS | 1 | Mercer | 1670 | Old Mercer Rd (T-401) Bridge over Nashannock Creek | 7204 | L00 | Bridge Replacement | FD | BOF | 2025-09-25 | 2025-09-25 | 168000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168000
SVTS | 1 | Mercer | 1670 | Old Mercer Rd (T-401) Bridge over Nashannock Creek | 7204 | L00 | Bridge Replacement | FD | 183 | 2025-09-25 | 2025-09-25 | 31500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31500
SVTS | 1 | Mercer | 1670 | Old Mercer Rd (T-401) Bridge over Nashannock Creek | 7204 | L00 | Bridge Replacement | FD | LOC | 2025-09-25 | 2025-09-25 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500
SVTS | 1 | Mercer | 1670 | Old Mercer Rd (T-401) Bridge over Nashannock Creek | 7204 | L00 | Bridge Replacement | ROW | BOF | 2025-09-25 | 2025-09-25 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
SVTS | 1 | Mercer | 1670 | Old Mercer Rd (T-401) Bridge over Nashannock Creek | 7204 | L00 | Bridge Replacement | ROW | 183 | 2025-09-25 | 2025-09-25 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
SVTS | 1 | Mercer | 1670 | Old Mercer Rd (T-401) Bridge over Nashannock Creek | 7204 | L00 | Bridge Replacement | CON | BOF | 2025-09-25 | 2025-09-25 | 38165 | 1395906 | 676208 | 0 | 0 | 0 | 0 | 0 | 0 | 2110279
SVTS | 1 | Mercer | 1670 | Old Mercer Rd (T-401) Bridge over Nashannock Creek | 7204 | L00 | Bridge Replacement | CON | 183 | 2025-09-25 | 2025-09-25 | 395678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395678
SVTS | 1 | Mercer | 1670 | Old Mercer Rd (T-401) Bridge over Nashannock Creek | 7204 | L00 | Bridge Replacement | CON | LOC | 2025-09-25 | 2025-09-25 | 64112 | 39004 | 28777 | 0 | 0 | 0 | 0 | 0 | 0 | 131893
SVTS | 1 | Mercer | 1693 | McKinley Ave Brdg | 7407 | STU | Bridge Replacement | FD | STP | 2027-01-14 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SVTS | 1 | Mercer | 1693 | McKinley Ave Brdg | 7407 | STU | Bridge Replacement | CON | STP | 2027-01-14 |  | 0 | 350000 | 520898 | 0 | 0 | 0 | 0 | 0 | 0 | 870898
SVTS | 1 | Mercer | 1725 | US 19: Hadley Road to Cemetery Road | 19 | 15M | Highway Restoration | PE | STP | 2026-05-07 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SVTS | 1 | Mercer | 1725 | US 19: Hadley Road to Cemetery Road | 19 | 15M | Highway Restoration | PE | 581 | 2026-05-07 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SVTS | 1 | Mercer | 1725 | US 19: Hadley Road to Cemetery Road | 19 | 15M | Highway Restoration | FD | STP | 2026-05-07 |  | 242828 | 301172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 544000
SVTS | 1 | Mercer | 1725 | US 19: Hadley Road to Cemetery Road | 19 | 15M | Highway Restoration | FD | 581 | 2026-05-07 |  | 72941 | 63059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136000
SVTS | 1 | Mercer | 1725 | US 19: Hadley Road to Cemetery Road | 19 | 15M | Highway Restoration | ROW | BRIP | 2026-05-07 |  | 29799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29799
SVTS | 1 | Mercer | 1725 | US 19: Hadley Road to Cemetery Road | 19 | 15M | Highway Restoration | ROW | 185 | 2026-05-07 |  | 7450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7450
SVTS | 1 | Mercer | 1725 | US 19: Hadley Road to Cemetery Road | 19 | 15M | Highway Restoration | CON | HSIP | 2026-05-07 |  | 0 | 36834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36834
SVTS | 1 | Mercer | 1725 | US 19: Hadley Road to Cemetery Road | 19 | 15M | Highway Restoration | CON | BRIP | 2026-05-07 |  | 1898279 | 1179003 | 1223387 | 0 | 0 | 0 | 0 | 0 | 0 | 4300669
SVTS | 1 | Mercer | 1725 | US 19: Hadley Road to Cemetery Road | 19 | 15M | Highway Restoration | CON | HSIP | 2026-05-07 |  | 0 | 24135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24135
SVTS | 1 | Mercer | 1725 | US 19: Hadley Road to Cemetery Road | 19 | 15M | Highway Restoration | CON | STP | 2026-05-07 |  | 366972 | 433028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
SVTS | 1 | Mercer | 1725 | US 19: Hadley Road to Cemetery Road | 19 | 15M | Highway Restoration | CON | 185 | 2026-05-07 |  | 715164 | 3991 | 356012 | 0 | 0 | 0 | 0 | 0 | 0 | 1075167
SVTS | 1 | Mercer | 1725 | US 19: Hadley Road to Cemetery Road | 19 | 15M | Highway Restoration | CON | 581 | 2026-05-07 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
SVTS | 1 | Mercer | 1745 | Ohl Street Bridge |  | L00 | Bridge Removal | FD | BRIP | 2026-06-18 |  | 63643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63643
SVTS | 1 | Mercer | 1745 | Ohl Street Bridge |  | L00 | Bridge Removal | FD | 179 | 2026-06-18 |  | 3978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3978
SVTS | 1 | Mercer | 1745 | Ohl Street Bridge |  | L00 | Bridge Removal | FD | 183 | 2026-06-18 |  | 11933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11933
SVTS | 1 | Mercer | 1745 | Ohl Street Bridge |  | L00 | Bridge Removal | CON | 179 | 2026-06-18 |  | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
SVTS | 1 | Mercer | 1745 | Ohl Street Bridge |  | L00 | Bridge Removal | CON | 183 | 2026-06-18 |  | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000
SVTS | 1 | Mercer | 1816 | SR 158 Brdg over I-80 | 158 | B04 | Bridge Restoration | PE | BRIP | 2028-01-01 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SVTS | 1 | Mercer | 1816 | SR 158 Brdg over I-80 | 158 | B04 | Bridge Restoration | CON | BRIP | 2028-01-01 |  | 0 | 0 | 0 | 356953 | 1778047 | 0 | 0 | 0 | 0 | 2135000
SVTS | 1 | Mercer | 1822 | SR 2014 Brdg 1/Otter Ck | 2014 | B06 | Bridge Restoration | PE | 185 | 2027-12-09 |  | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
SVTS | 1 | Mercer | 1822 | SR 2014 Brdg 1/Otter Ck | 2014 | B06 | Bridge Restoration | FD | BRIP | 2027-12-09 |  | 0 | 0 | 0 | 0 | 76831 | 83169 | 0 | 0 | 0 | 160000
SVTS | 1 | Mercer | 1822 | SR 2014 Brdg 1/Otter Ck | 2014 | B06 | Bridge Restoration | CON | BRIP | 2027-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 731131 | 468869 | 1200000
SVTS | 1 | Mercer | 1861 | SR 2017 Brdg/Cool Sprg Ck | 2017 | B00 | Bridge Replacement | CON | BOF | 2024-06-06 | 2024-06-06 | 204789 | 42776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247565
SVTS | 1 | Mercer | 1865 | SR 4021: Atlantic Rd Brdg | 4021 | B01 | Bridge Replacement | FD | 185 | 2029-01-01 |  | 0 | 104762 | 35238 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
SVTS | 1 | Mercer | 1865 | SR 4021: Atlantic Rd Brdg | 4021 | B01 | Bridge Replacement | CON | BOF | 2029-01-01 |  | 0 | 0 | 0 | 0 | 512912 | 447088 | 0 | 0 | 0 | 960000
SVTS | 1 | Mercer | 1865 | SR 4021: Atlantic Rd Brdg | 4021 | B01 | Bridge Replacement | CON | 185 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 128228 | 111772 | 0 | 0 | 0 | 240000
SVTS | 1 | Mercer | 1884 | Service Avenue Bridge | 7302 | STU | General Maintenance | CON | BRIP | 2025-11-06 | 2025-11-06 | 1305920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1305920
SVTS | 1 | Mercer | 1884 | Service Avenue Bridge | 7302 | STU | General Maintenance | CON | STP | 2025-11-06 | 2025-11-06 | 481059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481059
SVTS | 1 | Mercer | 1925 | Blacktown Road Bridge over I-79 | 2006 | B00 | Bridge Preservation - Federal | PE | BOF | 2025-04-10 | 2025-04-10 | 20167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20167
SVTS | 1 | Mercer | 1925 | Blacktown Road Bridge over I-79 | 2006 | B00 | Bridge Preservation - Federal | PE | 185 | 2025-04-10 | 2025-04-10 | 5042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5042
SVTS | 1 | Mercer | 1925 | Blacktown Road Bridge over I-79 | 2006 | B00 | Bridge Preservation - Federal | CON | BOF | 2025-04-10 | 2025-04-10 | 1276180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1276180
SVTS | 1 | Mercer | 1925 | Blacktown Road Bridge over I-79 | 2006 | B00 | Bridge Preservation - Federal | CON | 185 | 2025-04-10 | 2025-04-10 | 271312 | 47733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319045
SVTS | 1 | Mercer | 1930 | SR 4014: Oniontown Bridge | 4014 | B00 | Bridge Restoration | FD | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 160000
SVTS | 1 | Mercer | 1930 | SR 4014: Oniontown Bridge | 4014 | B00 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052548 | 2052548
SVTS | 1 | Mercer | 32317 | SR 2014 - Market Street | 2014 | 22M | Highway Restoration | PE | PRTCT | 2027-12-09 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SVTS | 1 | Mercer | 32317 | SR 2014 - Market Street | 2014 | 22M | Highway Restoration | CON | PRTCT | 2027-12-09 |  | 0 | 0 | 925000 | 0 | 0 | 0 | 0 | 0 | 0 | 925000
SVTS | 1 | Mercer | 32320 | SR 3017: Indiana Avenue | 3017 | 01M | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
SVTS | 1 | Mercer | 32320 | SR 3017: Indiana Avenue | 3017 | 01M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000
SVTS | 1 | Mercer | 32321 | SR 3023: Seventh Avenue | 3023 | 01M | Highway Restoration | PE | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
SVTS | 1 | Mercer | 32321 | SR 3023: Seventh Avenue | 3023 | 01M | Highway Restoration | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 750000
SVTS | 1 | Mercer | 32322 | SR 3025 | 3025 | 05M | Highway Restoration | PE | 581 | 2028-01-01 |  | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
SVTS | 1 | Mercer | 47282 | SR 18: Lawrence Co. Line to I-376 | 18 | 32M | Highway Restoration | CON | STP | 2030-01-01 |  | 0 | 0 | 0 | 462000 | 2095919 | 921081 | 0 | 0 | 0 | 3479000
SVTS | 1 | Mercer | 51188 | SR 58: US 19 to Campbell Drive | 58 | 06M | Highway Restoration | CON | 581 | 2026-01-15 | 2026-01-15 | 0 | 531963 | 4466993 | 0 | 0 | 0 | 0 | 0 | 0 | 4998956
SVTS | 1 | Mercer | 58003 | SR 58: Main Street Bridge | 58 | B14 | Bridge Restoration | CON | 185 | 2024-04-18 | 2024-04-18 | 59392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59392
SVTS | 1 | Mercer | 58052 | US 62 Bridge over I-79 | 62 | B01 | Bridge Replacement | CON | BRIP | 2029-01-01 |  | 0 | 0 | 321256 | 1620747 | 0 | 0 | 0 | 0 | 0 | 1942003
SVTS | 1 | Mercer | 58053 | SR 62: Pine Run Brdg | 62 | B18 | Bridge Restoration | PE | BRIP | 2031-12-31 |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
SVTS | 1 | Mercer | 58053 | SR 62: Pine Run Brdg | 62 | B18 | Bridge Restoration | CON | BRIP | 2031-12-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 848131 | 1551869 | 0 | 2400000
SVTS | 1 | Mercer | 58070 | SR 173: Black Run Brdg | 173 | 000 | Bridge Replacement | PE | 185 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000
SVTS | 1 | Mercer | 58070 | SR 173: Black Run Brdg | 173 | 000 | Bridge Replacement | CON | 185 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250500 | 1340700 | 1591200
SVTS | 1 | Mercer | 58096 | SR 4021: Morrison Run Bridge | 4021 | B05 | Bridge Restoration | UTL | 185 | 2024-01-11 | 2024-01-11 | 22800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22800
SVTS | 1 | Mercer | 67103 | SVATS BIL/IIJA Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 44109 | 130000 | 200000 | 200000 | 200000 | 200000 | 3047831 | 4021940
SVTS | 1 | Mercer | 67103 | SVATS BIL/IIJA Line Item |  |  | Reserve Line Item | CON | CRP |  |  | 254000 | 478000 | 478000 | 478000 | 478000 | 478000 | 478000 | 478000 | 1914000 | 5514000
SVTS | 1 | Mercer | 72658 | US 62 Bridge over Sandy Creek Trib | 62 | B17 | Bridge Preservation - Federal | PE | 185 |  |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SVTS | 1 | Mercer | 72658 | US 62 Bridge over Sandy Creek Trib | 62 | B17 | Bridge Preservation - Federal | CON | 185 |  |  | 0 | 0 | 154198 | 245802 | 0 | 0 | 0 | 0 | 0 | 400000
SVTS | 1 | Mercer | 74703 | PA 258 Bridge/Magargee Run | 258 | B04 | Bridge Restoration | FD | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
SVTS | 1 | Mercer | 74703 | PA 258 Bridge/Magargee Run | 258 | B04 | Bridge Restoration | CON | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 289300 | 460700 | 0 | 750000
SVTS | 1 | Mercer | 74712 | SR 3012 Brdg/Shenango River | 3012 | B00 | Bridge Restoration | PE | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
SVTS | 1 | Mercer | 74712 | SR 3012 Brdg/Shenango River | 3012 | B00 | Bridge Restoration | FD | 185 | 2033-01-01 |  | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
SVTS | 1 | Mercer | 74712 | SR 3012 Brdg/Shenango River | 3012 | B00 | Bridge Restoration | ROW | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
SVTS | 1 | Mercer | 74712 | SR 3012 Brdg/Shenango River | 3012 | B00 | Bridge Restoration | CON | 185 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 533300 | 866700 | 0 | 0 | 1400000
SVTS | 1 | Mercer | 78937 | SR 2022 Bridge over Wolf Creek | 2022 | B01 | Bridge Restoration | FD | 185 | 2031-01-01 |  | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000
SVTS | 1 | Mercer | 78937 | SR 2022 Bridge over Wolf Creek | 2022 | B01 | Bridge Restoration | CON | BOF | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 512912 | 137088 | 0 | 650000
SVTS | 1 | Mercer | 78944 | SR 3039 ov Lackwnk Ck #1 | 3039 | B01 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
SVTS | 1 | Mercer | 78944 | SR 3039 ov Lackwnk Ck #1 | 3039 | B01 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
SVTS | 1 | Mercer | 79496 | On Demand Bridge Contract Line Item |  | RES | Reserve Line Item | CON | 185 |  |  | 0 | 265699 | 455000 | 400000 | 300000 | 300000 | 300000 | 300000 | 1200000 | 3520699
SVTS | 1 | Mercer | 83021 | US 62 and Bestwick Intersection | 62 | 07S | Safety Improvement | PE | STP |  |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SVTS | 1 | Mercer | 83021 | US 62 and Bestwick Intersection | 62 | 07S | Safety Improvement | FD | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000
SVTS | 1 | Mercer | 83021 | US 62 and Bestwick Intersection | 62 | 07S | Safety Improvement | ROW | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SVTS | 1 | Mercer | 83021 | US 62 and Bestwick Intersection | 62 | 07S | Safety Improvement | UTL | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SVTS | 1 | Mercer | 83021 | US 62 and Bestwick Intersection | 62 | 07S | Safety Improvement | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000 | 1150000
SVTS | 1 | Mercer | 84306 | 2024 Dept. Force Br Item |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 0 | 0 | 120000 | 120000 | 120000 | 120000 | 160000 | 640000
SVTS | 1 | Mercer | 84913 | Mercer County T-Beam Rehab Project | 18 | B05 | Bridge Preservation - Federal | PE | 185 | 2027-01-01 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
SVTS | 1 | Mercer | 84913 | Mercer County T-Beam Rehab Project | 18 | B05 | Bridge Preservation - Federal | FD | 185 | 2027-01-01 |  | 0 | 123893 | 26107 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SVTS | 1 | Mercer | 84913 | Mercer County T-Beam Rehab Project | 18 | B05 | Bridge Preservation - Federal | CON | BRIP | 2027-01-01 |  | 0 | 0 | 134700 | 375300 | 0 | 0 | 0 | 0 | 0 | 510000
SVTS | 1 | Mercer | 84914 | US 19 over Johnston Run | 19 | B07 | Bridge Replacement | CON | BRIP | 2023-12-07 | 2023-12-07 | 219518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219518
SVTS | 1 | Mercer | 84916 | US 19/Lil Shenango River | 19 | B09 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SVTS | 1 | Mercer | 84916 | US 19/Lil Shenango River | 19 | B09 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309300 | 309300
SVTS | 1 | Mercer | 84920 | SR 551/Sheng River Trib | 551 | B00 | Bridge Preservation - State Funded | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 134000 | 0 | 0 | 134000
SVTS | 1 | Mercer | 84920 | SR 551/Sheng River Trib | 551 | B00 | Bridge Preservation - State Funded | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
SVTS | 1 | Mercer | 86060 | SR 19: Cemetery Rd - Crawford Cty Ln | 19 | 17M | Highway Restoration | CON | STP | 2026-05-07 |  | 1216568 | 450891 | 1754691 | 1177850 | 0 | 0 | 0 | 0 | 0 | 4600000
SVTS | 1 | Mercer | 88486 | US 62 Br over Spring Ck | 62 | B07 | Bridge Restoration | PE | 185 | 2029-01-01 |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SVTS | 1 | Mercer | 88486 | US 62 Br over Spring Ck | 62 | B07 | Bridge Restoration | ROW | 185 | 2029-01-01 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
SVTS | 1 | Mercer | 88486 | US 62 Br over Spring Ck | 62 | B07 | Bridge Restoration | CON | 185 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 618872 | 581128 | 0 | 0 | 0 | 1200000
SVTS | 1 | Mercer | 88488 | US 62 Bridge over Fox Run | 62 | B08 | Bridge Restoration | CON | BRIP | 2023-12-14 | 2023-12-14 | 41040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41040
SVTS | 1 | Mercer | 89120 | SR 1004 over Little Shenango River Tributary | 1004 | B02 | Bridge Restoration | CON | 185 | 2030-01-01 |  | 0 | 0 | 260000 | 240000 | 0 | 0 | 0 | 0 | 0 | 500000
SVTS | 1 | Mercer | 89168 | PA 18: Through Greenville | 18 | 31M | Highway Restoration | PE | 581 | 2028-01-01 |  | 100000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SVTS | 1 | Mercer | 89168 | PA 18: Through Greenville | 18 | 31M | Highway Restoration | CON | NHPP | 2028-01-01 |  | 0 | 0 | 228093 | 403907 | 0 | 0 | 0 | 0 | 0 | 632000
SVTS | 1 | Mercer | 89168 | PA 18: Through Greenville | 18 | 31M | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 158000 | 0 | 0 | 0 | 0 | 0 | 0 | 158000
SVTS | 1 | Mercer | 90401 | SVTS Safety Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 500000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 1000000 | 3000000
SVTS | 1 | Mercer | 92512 | SR 358/Sheng. River Trib | 358 | B05 | Bridge Replacement | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 228122 | 0 | 0 | 0 | 0 | 228122
SVTS | 1 | Mercer | 92512 | SR 358/Sheng. River Trib | 358 | B05 | Bridge Replacement | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
SVTS | 1 | Mercer | 97277 | US 19 Bridge over Otter Creek Trib #3 | 19 | B12 | Bridge Restoration | ROW | 185 | 2035-01-01 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
SVTS | 1 | Mercer | 97277 | US 19 Bridge over Otter Creek Trib #3 | 19 | B12 | Bridge Restoration | CON | 185 | 2035-01-01 |  | 0 | 0 | 378476 | 221524 | 0 | 0 | 0 | 0 | 0 | 600000
SVTS | 1 | Mercer | 97292 | SR 3007/W. Brch Nesh Ck | 3007 | B02 | Bridge Restoration | CON | BOF | 2032-01-01 |  | 0 | 0 | 0 | 110026 | 0 | 0 | 0 | 375824 | 0 | 485850
SVTS | 1 | Mercer | 97293 | SR 3032 Bridge/Pine Run | 3032 | B00 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
SVTS | 1 | Mercer | 97293 | SR 3032 Bridge/Pine Run | 3032 | B00 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
SVTS | 1 | Mercer | 97298 | PA 845 Bridge over Sawmill Run | 845 | B02 | Bridge Replacement | PE | 185 | 2028-01-01 |  | 0 | 20000 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
SVTS | 1 | Mercer | 97298 | PA 845 Bridge over Sawmill Run | 845 | B02 | Bridge Replacement | FD | 185 | 2028-01-01 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SVTS | 1 | Mercer | 97298 | PA 845 Bridge over Sawmill Run | 845 | B02 | Bridge Replacement | CON | 185 | 2028-01-01 |  | 0 | 0 | 0 | 530000 | 320000 | 0 | 0 | 0 | 0 | 850000
SVTS | 1 | Mercer | 97300 | Mercer 2025 Bridge Shotcrete Group | 4020 | B21 | Bridge Preservation - State Funded | PE | 185 | 2026-06-04 |  | 89178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89178
SVTS | 1 | Mercer | 97300 | Mercer 2025 Bridge Shotcrete Group | 4020 | B21 | Bridge Preservation - State Funded | CON | 185 | 2026-06-04 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
SVTS | 1 | Mercer | 97302 | PA 358 Brdg/Sankeys Run | 358 | B06 | Bridge Restoration | PE | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000
SVTS | 1 | Mercer | 97302 | PA 358 Brdg/Sankeys Run | 358 | B06 | Bridge Restoration | CON | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
SVTS | 1 | Mercer | 97306 | US 62 Bridge over Lackawannock Creek | 62 | B09 | Bridge Restoration | PE | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 130000 | 0 | 0 | 0 | 130000
SVTS | 1 | Mercer | 97306 | US 62 Bridge over Lackawannock Creek | 62 | B09 | Bridge Restoration | CON | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000 | 0 | 850000
SVTS | 1 | Mercer | 97308 | PA 173 Bridge over Black Run Trib | 173 | B04 | Bridge Replacement | PE | 185 | 2032-01-01 |  | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000
SVTS | 1 | Mercer | 97308 | PA 173 Bridge over Black Run Trib | 173 | B04 | Bridge Replacement | CON | 185 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 641200 | 0 | 0 | 641200
SVTS | 1 | Mercer | 97317 | PA 58 Bridge over Munnel Run | 58 | B12 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
SVTS | 1 | Mercer | 97317 | PA 58 Bridge over Munnel Run | 58 | B12 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000
SVTS | 1 | Mercer | 97319 | PA 965 Bridge over Yellow Creek | 965 | B03 | Bridge Restoration | CON | 185 | 2032-01-01 |  | 0 | 0 | 128624 | 0 | 0 | 0 | 0 | 0 | 0 | 128624
SVTS | 1 | Mercer | 97320 | SR 3039 Bridge over Little Neshannock Creek Trib | 3039 | B03 | Bridge Restoration | FD | 185 | 2030-01-01 |  | 0 | 0 | 27517 | 72483 | 0 | 0 | 0 | 0 | 0 | 100000
SVTS | 1 | Mercer | 97320 | SR 3039 Bridge over Little Neshannock Creek Trib | 3039 | B03 | Bridge Restoration | CON | 185 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
SVTS | 1 | Mercer | 97327 | US 62 Bridge over a Shenango River Tributary | 62 | B11 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 170000
SVTS | 1 | Mercer | 97327 | US 62 Bridge over a Shenango River Tributary | 62 | B11 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215300 | 1215300
SVTS | 1 | Mercer | 97329 | PA 846 Brdg/Shenango Res. | 846 | B03 | Bridge Restoration | PE | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 200000
SVTS | 1 | Mercer | 97329 | PA 846 Brdg/Shenango Res. | 846 | B03 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
SVTS | 1 | Mercer | 97332 | SR 3039 Bridge over Little Neshannock Cr Trib #1 | 3039 | B04 | Bridge Restoration | FD | 185 | 2031-01-01 |  | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
SVTS | 1 | Mercer | 97332 | SR 3039 Bridge over Little Neshannock Cr Trib #1 | 3039 | B04 | Bridge Restoration | ROW | 185 | 2031-01-01 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
SVTS | 1 | Mercer | 97332 | SR 3039 Bridge over Little Neshannock Cr Trib #1 | 3039 | B04 | Bridge Restoration | CON | 185 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000
SVTS | 1 | Mercer | 97912 | US 62: Ohio line to Libery Street | 62 | 20M | Highway Restoration | PE | NHPP | 2026-10-29 |  | 258000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258000
SVTS | 1 | Mercer | 97912 | US 62: Ohio line to Libery Street | 62 | 20M | Highway Restoration | PE | STP | 2026-10-29 |  | 193334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193334
SVTS | 1 | Mercer | 97912 | US 62: Ohio line to Libery Street | 62 | 20M | Highway Restoration | FD | NHPP | 2026-10-29 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
SVTS | 1 | Mercer | 97912 | US 62: Ohio line to Libery Street | 62 | 20M | Highway Restoration | CON | NHPP | 2026-10-29 |  | 591644 | 222093 | 877907 | 0 | 0 | 0 | 0 | 0 | 0 | 1691644
SVTS | 1 | Mercer | 97913 | SR 3011: PA 318-Valley View | 3011 | 01M | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1043797 | 3950270 | 0 | 0 | 4994067
SVTS | 1 | Mercer | 98172 | SR 4022 Bridge over Sankeys Run | 4022 | B00 | Bridge Preservation - Federal | FD | 185 | 2027-01-01 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SVTS | 1 | Mercer | 98172 | SR 4022 Bridge over Sankeys Run | 4022 | B00 | Bridge Preservation - Federal | CON | 185 | 2027-01-01 |  | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000
SVTS | 1 | Mercer | 98261 | Mercer Local Brdg Line |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 0 | 324335 | 1830688 | 1830688 | 1830688 | 1830688 | 1830688 | 7322752 | 16800527
SVTS | 1 | Mercer | 98388 | SR 3020: SR 18 to SR 3011 | 3020 | A00 | Highway Restoration | CON | 581 | 2025-04-10 | 2025-04-10 | 942463 | 1222079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2164542
SVTS | 1 | Mercer | 98390 | SR 3003: Lawrence County Line to SR 718 | 3003 | 01M | Highway Restoration | PE | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
SVTS | 1 | Mercer | 98390 | SR 3003: Lawrence County Line to SR 718 | 3003 | 01M | Highway Restoration | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
SVTS | 1 | Mercer | 98390 | SR 3003: Lawrence County Line to SR 718 | 3003 | 01M | Highway Restoration | CON | STP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2429919 | 1738400 | 4168319
SVTS | 1 | Mercer | 98391 | SR 3026: PA 318 to US 62 | 3026 | 01M | Highway Restoration | PE | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
SVTS | 1 | Mercer | 98391 | SR 3026: PA 318 to US 62 | 3026 | 01M | Highway Restoration | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803396 | 3017900 | 4821296
SVTS | 1 | Mercer | 98399 | SR 2005: PA 208 - SR 2007 | 2005 | 01M | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 2429000 | 0 | 0 | 0 | 2429000
SVTS | 1 | Mercer | 98405 | PA 358: Bean Rd-Carpenter | 358 | 06M | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
SVTS | 1 | Mercer | 98405 | PA 358: Bean Rd-Carpenter | 358 | 06M | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
SVTS | 1 | Mercer | 98511 | SR 1002: SR 4025 - US 19 | 1002 | 01M | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
SVTS | 1 | Mercer | 98511 | SR 1002: SR 4025 - US 19 | 1002 | 01M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1551000 | 1551000
SVTS | 1 | Mercer | 98512 | Brdway Ave: PA 18-Council | 760 | A00 | Highway Reconstruction | PE | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 126730 | 73270 | 0 | 200000
SVTS | 1 | Mercer | 98512 | Brdway Ave: PA 18-Council | 760 | A00 | Highway Reconstruction | CON | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014479 | 400000 | 2414479
SVTS | 1 | Mercer | 99871 | SR 2021: Sandy Lk-SR 965 | 2021 | 01M | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105615 | 0 | 105615
SVTS | 1 | Mercer | 99871 | SR 2021: Sandy Lk-SR 965 | 2021 | 01M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076200 | 7076200
SVTS | 1 | Mercer | 99873 | SR 358: Methodist-Bean | 358 | 07M | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
SVTS | 1 | Mercer | 99873 | SR 358: Methodist-Bean | 358 | 07M | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3729600 | 3729600
SVTS | 1 | Mercer | 99873 | SR 358: Methodist-Bean | 358 | 07M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932400 | 932400
SVTS | 1 | Mercer | 99878 | SR 18: Roman to Wilson | 18 | 25M | Highway Restoration | CON | NHPP | 2024-07-11 | 2024-07-11 | 8516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8516
SVTS | 1 | Mercer | 99927 | PA 518: Sharon to Sharpsville | 518 | 07M | Highway Restoration | CON | STP | 2024-12-12 | 2024-12-12 | 1107085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1107085
SVTS | 1 | Mercer | 99927 | PA 518: Sharon to Sharpsville | 518 | 07M | Highway Restoration | CON | 581 | 2024-12-12 | 2024-12-12 | 272539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272539
SVTS | 1 | Mercer | 99936 | SR 718: Russell-Hartford | 718 | 06M | Highway Restoration | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
SVTS | 1 | Mercer | 99936 | SR 718: Russell-Hartford | 718 | 06M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000
SVTS | 1 | Mercer | 99951 | SR 3035: SR 418-State St | 3035 | 01M | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000 | 0 | 115000
SVTS | 1 | Mercer | 99951 | SR 3035: SR 418-State St | 3035 | 01M | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000 | 2100000
SVTS | 1 | Mercer | 99954 | SR 4006: Williamson Rd-SR 18 | 4006 | 01M | Highway Restoration | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
SVTS | 1 | Mercer | 99954 | SR 4006: Williamson Rd-SR 18 | 4006 | 01M | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 1600000
SVTS | 1 | Mercer | 106281 | Bessemer & Lake Erie RR Corridor | 173 | R00 | Safety Improvement | CON | RRX | 2024-01-01 |  | 0 | 0 | 0 | 0 | 400000 | 600000 | 0 | 0 | 0 | 1000000
SVTS | 1 | Mercer | 106423 | Mercer Highway/Bridge Line Item |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 1009773 | 903457 | 150374 | 260400 | 166224 | 260400 | 260400 | 1041700 | 4052728
SVTS | 1 | Mercer | 106423 | Mercer Highway/Bridge Line Item |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 387719 | 0 | 0 | 0 | 0 | 0 | 0 | 387719
SVTS | 1 | Mercer | 106423 | Mercer Highway/Bridge Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 865535 | 1146000 | 1109000 | 1146000 | 1146000 | 1146000 | 1146000 | 4582000 | 12286535
SVTS | 1 | Mercer | 106423 | Mercer Highway/Bridge Line Item |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 1158907 | 250000 | 100000 | 82693 | 1127500 | 1072500 | 1225000 | 439900 | 5456500
SVTS | 1 | Mercer | 106423 | Mercer Highway/Bridge Line Item |  |  | Reserve Line Item | CON | STP |  |  | 0 | 54815 | 16972 | 5731 | 200000 | 2145919 | 2569500 | 787081 | 800000 | 6580018
SVTS | 1 | Mercer | 106423 | Mercer Highway/Bridge Line Item |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 66172 | 57828 | 21098 | 266900 | 266800 | 266800 | 266800 | 2850000 | 4062398
SVTS | 1 | Mercer | 106423 | Mercer Highway/Bridge Line Item |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 251245 | 378007 | 4434058 | 350000 | 1318145 | 1218000 | 532240 | 2297500 | 10779195
SVTS | 1 | Mercer | 109077 | State St. Pedestrian Improvements | 3008 | A03 | Bicycle Pedestrian Highway | CON | 581 | 2024-03-28 | 2024-03-28 | 25812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25812
SVTS | 1 | Mercer | 109750 | PA 718: Bank Pl - River Rd | 718 | 05M | Highway Restoration | CON | 581 | 2025-04-17 | 2025-04-17 | 1588855 | 1413958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3002813
SVTS | 1 | Mercer | 109773 | SR 18: SR 358 - Mill Hill Rd. | 18 | 23M | Highway Restoration | FD | 581 | 2024-07-11 | 2024-07-11 | 21851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21851
SVTS | 1 | Mercer | 109773 | SR 18: SR 358 - Mill Hill Rd. | 18 | 23M | Highway Restoration | ROW | 581 | 2024-07-11 | 2024-07-11 | 42665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42665
SVTS | 1 | Mercer | 109773 | SR 18: SR 358 - Mill Hill Rd. | 18 | 23M | Highway Restoration | CON | NHPP | 2024-07-11 | 2024-07-11 | 451297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451297
SVTS | 1 | Mercer | 109773 | SR 18: SR 358 - Mill Hill Rd. | 18 | 23M | Highway Restoration | CON | 581 | 2024-07-11 | 2024-07-11 | 308324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308324
SVTS | 1 | Mercer | 110124 | Mercer 2027 RPM |  |  | Safety Improvement | CON | STP | 2027-02-25 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SVTS | 1 | Mercer | 110234 | PA 18/SR 4006 Intersection | 18 | S05 | Safety Improvement | PE | STP | 2024-07-25 | 2024-07-25 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
SVTS | 1 | Mercer | 110234 | PA 18/SR 4006 Intersection | 18 | S05 | Safety Improvement | ROW | STP | 2024-07-25 | 2024-07-25 | 8493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8493
SVTS | 1 | Mercer | 110234 | PA 18/SR 4006 Intersection | 18 | S05 | Safety Improvement | UTL | 581 | 2024-07-25 | 2024-07-25 | 25354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25354
SVTS | 1 | Mercer | 110234 | PA 18/SR 4006 Intersection | 18 | S05 | Safety Improvement | CON | HSIP | 2024-07-25 | 2024-07-25 | 790330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 790330
SVTS | 1 | Mercer | 110764 | SR 18/SR 4005 Intersection | 18 | S04 | Air Quality | CON | CRP | 2024-07-11 | 2024-07-11 | 213000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213000
SVTS | 1 | Mercer | 111157 | SR 518/3025 Intersection | 518 | S01 | Safety Improvement | FD | HSIP | 2026-06-18 |  | 193670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193670
SVTS | 1 | Mercer | 111157 | SR 518/3025 Intersection | 518 | S01 | Safety Improvement | FD | STP | 2026-06-18 |  | 106330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106330
SVTS | 1 | Mercer | 111157 | SR 518/3025 Intersection | 518 | S01 | Safety Improvement | ROW | STP | 2026-06-18 |  | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000
SVTS | 1 | Mercer | 111157 | SR 518/3025 Intersection | 518 | S01 | Safety Improvement | UTL | STP | 2026-06-18 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SVTS | 1 | Mercer | 111157 | SR 518/3025 Intersection | 518 | S01 | Safety Improvement | CON | HSIP | 2026-06-18 |  | 0 | 256330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256330
SVTS | 1 | Mercer | 111157 | SR 518/3025 Intersection | 518 | S01 | Safety Improvement | CON | STP | 2026-06-18 |  | 0 | 1548000 | 695670 | 0 | 0 | 0 | 0 | 0 | 0 | 2243670
SVTS | 1 | Mercer | 111321 | SR 518: SR 18 to SR 3017 | 518 | 08M | Highway Restoration | FD | 581 | 2027-01-14 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
SVTS | 1 | Mercer | 111321 | SR 518: SR 18 to SR 3017 | 518 | 08M | Highway Restoration | ROW | 581 | 2027-01-14 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SVTS | 1 | Mercer | 111321 | SR 518: SR 18 to SR 3017 | 518 | 08M | Highway Restoration | UTL | 581 | 2027-01-14 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
SVTS | 1 | Mercer | 111321 | SR 518: SR 18 to SR 3017 | 518 | 08M | Highway Restoration | CON | STP | 2027-01-14 |  | 0 | 0 | 0 | 783231 | 0 | 0 | 0 | 0 | 0 | 783231
SVTS | 1 | Mercer | 112678 | Hosack Road (T-784) Bridges |  | 784 | Bridge Replacement | CON | BOF | 2025-01-30 | 2025-01-30 | 923679 | 148321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1072000
SVTS | 1 | Mercer | 112678 | Hosack Road (T-784) Bridges |  | 784 | Bridge Replacement | CON | LOC | 2025-01-30 | 2025-01-30 | 64153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64153
SVTS | 1 | Mercer | 113309 | Mercer Shotcrete Group | 1016 | B01 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
SVTS | 1 | Mercer | 113309 | Mercer Shotcrete Group | 1016 | B01 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000
SVTS | 1 | Mercer | 115349 | SR 173: Grove City to I-80 | 173 | 461 | General Maintenance | CON | HSIP | 2026-04-23 |  | 0 | 45261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45261
SVTS | 1 | Mercer | 116195 | Mercer 2025 RPM |  |  | Safety Improvement | CON | STP | 2025-03-13 | 2025-03-13 | 85400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85400
SVTS | 1 | Mercer | 116196 | Mercer 2026 RPM |  |  | Safety Improvement | CON | STP | 2026-03-12 | 2026-03-12 | 0 | 101094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101094
SVTS | 1 | Mercer | 116687 | US 62 and SR 3011 Intersection Improvements | 62 | 02S | Safety Improvement | PE | STP | 2031-01-01 |  | 0 | 0 | 129769 | 175000 | 0 | 0 | 0 | 0 | 0 | 304769
SVTS | 1 | Mercer | 116687 | US 62 and SR 3011 Intersection Improvements | 62 | 02S | Safety Improvement | FD | STP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000
SVTS | 1 | Mercer | 116687 | US 62 and SR 3011 Intersection Improvements | 62 | 02S | Safety Improvement | ROW | STP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SVTS | 1 | Mercer | 116687 | US 62 and SR 3011 Intersection Improvements | 62 | 02S | Safety Improvement | UTL | STP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000
SVTS | 1 | Mercer | 116687 | US 62 and SR 3011 Intersection Improvements | 62 | 02S | Safety Improvement | CON | STP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 597500 | 0 | 0 | 597500
SVTS | 1 | Mercer | 116689 | US 62/Robertson Rd. Intersection Improvements | 62 | S04 | Safety Improvement | PE | NHPP |  |  | 0 | 0 | 0 | 110193 | 289807 | 0 | 0 | 0 | 0 | 400000
SVTS | 1 | Mercer | 116689 | US 62/Robertson Rd. Intersection Improvements | 62 | S04 | Safety Improvement | FD | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 97500 | 152500 | 0 | 0 | 250000
SVTS | 1 | Mercer | 116689 | US 62/Robertson Rd. Intersection Improvements | 62 | S04 | Safety Improvement | ROW | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SVTS | 1 | Mercer | 116689 | US 62/Robertson Rd. Intersection Improvements | 62 | S04 | Safety Improvement | UTL | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
SVTS | 1 | Mercer | 116689 | US 62/Robertson Rd. Intersection Improvements | 62 | S04 | Safety Improvement | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 790000 | 790000
SVTS | 1 | Mercer | 117445 | SR 4003: Wasser Bridge Road | 4003 | 02M | Highway Restoration | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
SVTS | 1 | Mercer | 117445 | SR 4003: Wasser Bridge Road | 4003 | 02M | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
SVTS | 1 | Mercer | 117448 | SR 3008 & SR 518: City of Sharon | 3008 | 04M | Highway Restoration | PE | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
SVTS | 1 | Mercer | 117448 | SR 3008 & SR 518: City of Sharon | 3008 | 04M | Highway Restoration | CON | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3519100 | 3519100
SVTS | 1 | Mercer | 117487 | US 62: SR 3011 to Horvath Farms Rd | 62 | 463 | General Maintenance | PE | NHPP | 2026-03-26 | 2026-03-26 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
SVTS | 1 | Mercer | 117487 | US 62: SR 3011 to Horvath Farms Rd | 62 | 463 | General Maintenance | CON | HSIP | 2026-03-26 | 2026-03-26 | 0 | 34060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34060
SVTS | 1 | Mercer | 117537 | SR 718 over Pine Run | 718 | B06 | Bridge Replacement | FD | 185 | 2025-12-11 | 2025-12-11 | 348382 | 86618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435000
SVTS | 1 | Mercer | 117537 | SR 718 over Pine Run | 718 | B06 | Bridge Replacement | ROW | BRIP | 2025-12-11 | 2025-12-11 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
SVTS | 1 | Mercer | 117537 | SR 718 over Pine Run | 718 | B06 | Bridge Replacement | CON | BRIP | 2025-12-11 | 2025-12-11 | 0 | 1203997 | 371829 | 0 | 0 | 0 | 0 | 0 | 0 | 1575826
SVTS | 1 | Mercer | 117575 | SR 62: SR 19 to I-79 | 62 | 25M | Highway Restoration | PE | 581 | 2029-01-01 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SVTS | 1 | Mercer | 117575 | SR 62: SR 19 to I-79 | 62 | 25M | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 802442 | 4943500 | 604058 | 0 | 0 | 0 | 6350000
SVTS | 1 | Mercer | 117627 | SR 358: SR 18 to SR 4006 | 358 | 27M | Highway Restoration | PE | NHPP | 2029-01-01 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
SVTS | 1 | Mercer | 117627 | SR 358: SR 18 to SR 4006 | 358 | 27M | Highway Restoration | CON | NHPP | 2029-01-01 |  | 0 | 0 | 0 | 460900 | 852500 | 0 | 0 | 0 | 0 | 1313400
SVTS | 1 | Mercer | 117671 | US 62 and SR 3037 Intersection Improvement | 62 | 08S | Safety Improvement | PE | HSIP | 2028-01-01 |  | 137000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137000
SVTS | 1 | Mercer | 117671 | US 62 and SR 3037 Intersection Improvement | 62 | 08S | Safety Improvement | CON | HSIP | 2028-01-01 |  | 0 | 0 | 0 | 37000 | 0 | 0 | 0 | 0 | 0 | 37000
SVTS | 1 | Mercer | 117671 | US 62 and SR 3037 Intersection Improvement | 62 | 08S | Safety Improvement | CON | STP | 2028-01-01 |  | 0 | 0 | 0 | 194269 | 0 | 0 | 0 | 0 | 0 | 194269
SVTS | 1 | Mercer | 118216 | SR 2013 Bridge over Munnel Run | 2013 | B01 | Bridge Restoration | PE | 185 | 2027-10-07 |  | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
SVTS | 1 | Mercer | 118216 | SR 2013 Bridge over Munnel Run | 2013 | B01 | Bridge Restoration | ROW | 185 | 2027-10-07 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SVTS | 1 | Mercer | 118216 | SR 2013 Bridge over Munnel Run | 2013 | B01 | Bridge Restoration | UTL | 185 | 2027-10-07 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
SVTS | 1 | Mercer | 118216 | SR 2013 Bridge over Munnel Run | 2013 | B01 | Bridge Restoration | CON | BOF | 2027-10-07 |  | 0 | 0 | 600000 | 512912 | 0 | 0 | 0 | 0 | 0 | 1112912
SVTS | 1 | Mercer | 119220 | Sharon 2022 STU Grant - E. State Street | 518 | STU | Bicycle Pedestrian Highway | CON | TAP | 2025-01-30 | 2025-01-30 | 1142919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1142919
SVTS | 1 | Mercer | 119711 | Mercer 2028 RPM |  |  | Safety Improvement | CON | STP | 2028-01-01 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
SVTS | 1 | Mercer | 119809 | SR 318: Fair St. to Stefanak Dr. | 318 | 01M | Highway Restoration | PE | 581 | 2030-01-01 |  | 123000 | 15696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138696
SVTS | 1 | Mercer | 119809 | SR 318: Fair St. to Stefanak Dr. | 318 | 01M | Highway Restoration | CON | STP | 2030-01-01 |  | 0 | 0 | 0 | 418919 | 1021081 | 0 | 0 | 0 | 0 | 1440000
SVTS | 1 | Mercer | 119809 | SR 318: Fair St. to Stefanak Dr. | 318 | 01M | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 258500 | 101500 | 0 | 0 | 0 | 0 | 360000
SVTS | 1 | Mercer | 119863 | SR 358 & 8005 Ramp Safety Improvements | 358 | S01 | Safety Improvement | CON | 581 | 2024-05-23 | 2024-05-23 | 271979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271979
SVTS | 1 | Mercer | 120524 | Lorenwood Drive - South Darby Road Trail Project |  | MTF | MultiModal | CON | 411 | 2026-03-26 |  | 318500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318500
SVTS | 1 | Mercer | 120524 | Lorenwood Drive - South Darby Road Trail Project |  | MTF | MultiModal | CON | LOC | 2026-03-26 |  | 136500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136500
SVTS | 1 | Mercer | 120597 | SR 2024 Bridge over Wolf Creek Branch | 2024 | B01 | Bridge Replacement | PE | 185 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 160000
SVTS | 1 | Mercer | 120597 | SR 2024 Bridge over Wolf Creek Branch | 2024 | B01 | Bridge Replacement | CON | BRIP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 1200000
SVTS | 1 | Mercer | 120598 | State Route 19 Bridge over Otter Ck Trib | 19 | B22 | Bridge Replacement | PE | 185 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 130000 | 0 | 0 | 0 | 0 | 130000
SVTS | 1 | Mercer | 120598 | State Route 19 Bridge over Otter Ck Trib | 19 | B22 | Bridge Replacement | CON | BRIP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1034700 | 0 | 0 | 0 | 1034700
SVTS | 1 | Mercer | 120599 | SR 208 Bridge over Johnston Run | 208 | B03 | Bridge Restoration | PE | 185 | 2035-01-01 |  | 0 | 0 | 0 | 153093 | 0 | 0 | 0 | 0 | 0 | 153093
SVTS | 1 | Mercer | 120599 | SR 208 Bridge over Johnston Run | 208 | B03 | Bridge Restoration | CON | BRIP | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1065131 | 134869 | 0 | 0 | 1200000
SVTS | 1 | Mercer | 120600 | State Route 1014 over Long Run | 1014 | B04 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
SVTS | 1 | Mercer | 120600 | State Route 1014 over Long Run | 1014 | B04 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
SVTS | 1 | Mercer | 120713 | On Demand Bridge Repair Contract - 2025 |  |  | Bridge Preservation - State Funded | CON | 185 | 2024-10-24 | 2024-10-24 | 215169 | 419132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634301
SVTS | 1 | Mercer | 121184 | Mercer County Systemic Rumble Strips | 173 | S01 | Safety Improvement | PE | HSIP | 2026-06-18 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
SVTS | 1 | Mercer | 121184 | Mercer County Systemic Rumble Strips | 173 | S01 | Safety Improvement | CON | HSIP | 2026-06-18 |  | 0 | 13169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13169
SVTS | 1 | Mercer | 121311 | I-80 WB Mercer Co ITS Addition at SR 173 - TSMO | 80 | TS4 | Intelligent Transportation System | PE | CRP | 2025-03-27 | 2025-03-27 | 31686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31686
SVTS | 1 | Mercer | 121311 | I-80 WB Mercer Co ITS Addition at SR 173 - TSMO | 80 | TS4 | Intelligent Transportation System | PE | 581 | 2025-03-27 | 2025-03-27 | 7922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7922
SVTS | 1 | Mercer | 121311 | I-80 WB Mercer Co ITS Addition at SR 173 - TSMO | 80 | TS4 | Intelligent Transportation System | CON | CRP | 2025-03-27 | 2025-03-27 | 285181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285181
SVTS | 1 | Mercer | 121311 | I-80 WB Mercer Co ITS Addition at SR 173 - TSMO | 80 | TS4 | Intelligent Transportation System | CON | 581 | 2025-03-27 | 2025-03-27 | 71295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71295
SVTS | 1 | Mercer | 121485 | Keel Ridge Rd - TIIF | 3011 | TIF | Highway Restoration | CON | 581 | 2024-11-07 |  | 730000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730000
SVTS | 1 | Mercer | 121509 | Route 18 (N Hermitage Road) Sidewalk Project | 18 | T01 | Transportation Enhancement | CON | TAP | 2026-03-12 | 2026-03-12 | 0 | 392583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392583
SVTS | 1 | Mercer | 122286 | Lorenwood Drive Multimodal Project |  | MT2 | MultiModal | CON | 407 |  |  | 330052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330052
SVTS | 1 | Mercer | 122286 | Lorenwood Drive Multimodal Project |  | MT2 | MultiModal | CON | LOC |  |  | 141451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141451
SVTS | 1 | Mercer | 122346 | Dept. Force Br Line Item |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 400000
SVTS | 1 | Mercer | 122347 | Dept. Force Br. Mercer |  |  | Bridge Preservation - State Funded | CON | 185 |  |  | 200000 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475000
SVTS | 1 | Mercer | 122371 | SR 318 - Ohio to 2nd Ave | 318 | 02M | Highway Restoration | PE | 581 | 2030-01-01 |  | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
SVTS | 1 | Mercer | 123184 | US 62 over Sandy Creek Trib - Sediment Removal | 62 | BSR | Bridge Preservation - Federal | PE | PRTCT | 2026-06-18 |  | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
SVTS | 1 | Mercer | 123184 | US 62 over Sandy Creek Trib - Sediment Removal | 62 | BSR | Bridge Preservation - Federal | UTL | PRTCT | 2026-06-18 |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
SVTS | 1 | Mercer | 123184 | US 62 over Sandy Creek Trib - Sediment Removal | 62 | BSR | Bridge Preservation - Federal | CON | PRTCT | 2026-06-18 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Wayne | 4 | Wayne | 9834 | SR 4017 over Dyberry Creek | 4017 | 670 | Bridge Replacement | CON | 581 | 2039-10-06 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Wayne | 4 | Wayne | 9849 | T-603 Factory Bridge #5 over Equinunk Creek | 7202 | BR5 | Bridge Replacement | FD | BRIP | 2026-09-17 |  | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Wayne | 4 | Wayne | 9849 | T-603 Factory Bridge #5 over Equinunk Creek | 7202 | BR5 | Bridge Replacement | FD | 183 | 2026-09-17 |  | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
Wayne | 4 | Wayne | 9849 | T-603 Factory Bridge #5 over Equinunk Creek | 7202 | BR5 | Bridge Replacement | CON | BOF | 2026-09-17 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Wayne | 4 | Wayne | 9849 | T-603 Factory Bridge #5 over Equinunk Creek | 7202 | BR5 | Bridge Replacement | CON | BRIP | 2026-09-17 |  | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 640000 | 720000
Wayne | 4 | Wayne | 9849 | T-603 Factory Bridge #5 over Equinunk Creek | 7202 | BR5 | Bridge Replacement | CON | 183 | 2026-09-17 |  | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 120000 | 150000
Wayne | 4 | Wayne | 9877 | SR 1023 over Equinunk Creek | 1023 | 02M | Bridge Replacement | FD | BOF | 2027-01-28 |  | 0 | 345000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 465000
Wayne | 4 | Wayne | 9877 | SR 1023 over Equinunk Creek | 1023 | 02M | Bridge Replacement | ROW | 185 | 2027-01-28 |  | 0 | 0 | 80775 | 50000 | 0 | 0 | 0 | 0 | 0 | 130775
Wayne | 4 | Wayne | 9877 | SR 1023 over Equinunk Creek | 1023 | 02M | Bridge Replacement | CON | BRIP | 2027-01-28 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 2000000
Wayne | 4 | Wayne | 9877 | SR 1023 over Equinunk Creek | 1023 | 02M | Bridge Replacement | CON | 185 | 2027-01-28 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 0 | 500000
Wayne | 4 | Wayne | 9936 | SR 3031 over Middle Creek | 3031 | 650 | Bridge Replacement | FD | BRIP | 2026-12-03 |  | 172000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172000
Wayne | 4 | Wayne | 9936 | SR 3031 over Middle Creek | 3031 | 650 | Bridge Replacement | FD | 581 | 2026-12-03 |  | 43000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43000
Wayne | 4 | Wayne | 9936 | SR 3031 over Middle Creek | 3031 | 650 | Bridge Replacement | CON | BOF | 2026-12-03 |  | 100000 | 0 | 313000 | 308800 | 0 | 0 | 0 | 0 | 0 | 721800
Wayne | 4 | Wayne | 9936 | SR 3031 over Middle Creek | 3031 | 650 | Bridge Replacement | CON | BRIP | 2026-12-03 |  | 458000 | 372800 | 702000 | 656500 | 815182 | 0 | 0 | 0 | 0 | 3004482
Wayne | 4 | Wayne | 9936 | SR 3031 over Middle Creek | 3031 | 650 | Bridge Replacement | CON | 185 | 2026-12-03 |  | 0 | 37000 | 20636 | 63000 | 0 | 0 | 0 | 0 | 0 | 120636
Wayne | 4 | Wayne | 9936 | SR 3031 over Middle Creek | 3031 | 650 | Bridge Replacement | CON | 581 | 2026-12-03 |  | 139500 | 0 | 8314 | 459325 | 203796 | 0 | 0 | 0 | 0 | 810935
Wayne | 4 | Wayne | 9972 | SR 2007 over Carley Brook | 2007 | 650 | Bridge Replacement | PE | BRIP | 2035-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 9972 | SR 2007 over Carley Brook | 2007 | 650 | Bridge Replacement | PE | 185 | 2035-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 9983 | SR 1002 over Delaware River | 1002 | 651 | Bridge Restoration | FD | 581 |  |  | 0 | 0 | 0 | 219000 | 0 | 0 | 0 | 0 | 0 | 219000
Wayne | 4 | Wayne | 9983 | SR 1002 over Delaware River | 1002 | 651 | Bridge Restoration | FD | LOC |  |  | 0 | 0 | 0 | 219000 | 0 | 0 | 0 | 0 | 0 | 219000
Wayne | 4 | Wayne | 9983 | SR 1002 over Delaware River | 1002 | 651 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
Wayne | 4 | Wayne | 9983 | SR 1002 over Delaware River | 1002 | 651 | Bridge Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200000 | 4200000
Wayne | 4 | Wayne | 9983 | SR 1002 over Delaware River | 1002 | 651 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 1800000
Wayne | 4 | Wayne | 10008 | SR 4008 over Johnsons Creek | 4008 | 670 | Bridge Restoration | PE | 581 | 2033-10-01 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Wayne | 4 | Wayne | 10008 | SR 4008 over Johnsons Creek | 4008 | 670 | Bridge Restoration | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 1200000
Wayne | 4 | Wayne | 10018 | SR 191 over Branch Middle Creek | 191 | 654 | Bridge Replacement | CON | STP | 2026-12-03 |  | 0 | 0 | 1280000 | 1280000 | 450000 | 190000 | 0 | 0 | 0 | 3200000
Wayne | 4 | Wayne | 10021 | SR 3018 over Branch Middle Creek | 3018 | 650 | Bridge Replacement | CON | 581 | 2024-07-25 | 2024-07-25 | 441795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441795
Wayne | 4 | Wayne | 10046 | SR 1020 over Delaware River - Calicoon | 1020 | 652 | Bridge Restoration | CON | 581 | 2024-03-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000
Wayne | 4 | Wayne | 10046 | SR 1020 over Delaware River - Calicoon | 1020 | 652 | Bridge Restoration | CON | LOC | 2024-03-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000
Wayne | 4 | Wayne | 67578 | SR 296 over Van Aucken Creek | 296 | D50 | Bridge Replacement | UTL | 185 | 2026-03-12 |  | 0 | 0 | 281000 | 0 | 0 | 0 | 0 | 0 | 0 | 281000
Wayne | 4 | Wayne | 67578 | SR 296 over Van Aucken Creek | 296 | D50 | Bridge Replacement | UTL | LOC | 2026-03-12 |  | 0 | 0 | 281000 | 0 | 0 | 0 | 0 | 0 | 0 | 281000
Wayne | 4 | Wayne | 67578 | SR 296 over Van Aucken Creek | 296 | D50 | Bridge Replacement | CON | STP | 2026-03-12 |  | 335000 | 960000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1295000
Wayne | 4 | Wayne | 67578 | SR 296 over Van Aucken Creek | 296 | D50 | Bridge Replacement | CON | 581 | 2026-03-12 |  | 83750 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 323750
Wayne | 4 | Wayne | 67580 | SR 590 over Jones Creek | 590 | 654 | Bridge Replacement | CON | BRIP | 2024-02-15 | 2024-02-15 | 0 | 252000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252000
Wayne | 4 | Wayne | 67580 | SR 590 over Jones Creek | 590 | 654 | Bridge Replacement | CON | STR | 2024-02-15 | 2024-02-15 | 0 | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64000
Wayne | 4 | Wayne | 67580 | SR 590 over Jones Creek | 590 | 654 | Bridge Replacement | CON | 185 | 2024-02-15 | 2024-02-15 | 0 | 79000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79000
Wayne | 4 | Wayne | 67585 | SR 3008 over Ariel Creek | 3008 | 670 | Bridge Replacement | CON | BOF | 2025-11-06 | 2025-11-06 | 687000 | 650155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1337155
Wayne | 4 | Wayne | 67585 | SR 3008 over Ariel Creek | 3008 | 670 | Bridge Replacement | CON | BRIP | 2025-11-06 | 2025-11-06 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
Wayne | 4 | Wayne | 67585 | SR 3008 over Ariel Creek | 3008 | 670 | Bridge Replacement | CON | STP | 2025-11-06 | 2025-11-06 | 833661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833661
Wayne | 4 | Wayne | 67585 | SR 3008 over Ariel Creek | 3008 | 670 | Bridge Replacement | CON | 581 | 2025-11-06 | 2025-11-06 | 381415 | 162539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 543954
Wayne | 4 | Wayne | 67586 | SR 3018 over Branch of Middle Creek | 3018 | 000 | Bridge Restoration | PE | BOF | 2033-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 67586 | SR 3018 over Branch of Middle Creek | 3018 | 000 | Bridge Restoration | PE | 581 | 2033-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 67586 | SR 3018 over Branch of Middle Creek | 3018 | 000 | Bridge Restoration | FD | BOF | 2033-10-01 |  | 0 | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 240000
Wayne | 4 | Wayne | 67586 | SR 3018 over Branch of Middle Creek | 3018 | 000 | Bridge Restoration | FD | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 60000
Wayne | 4 | Wayne | 67586 | SR 3018 over Branch of Middle Creek | 3018 | 000 | Bridge Restoration | CON | BOF | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 1600000
Wayne | 4 | Wayne | 67586 | SR 3018 over Branch of Middle Creek | 3018 | 000 | Bridge Restoration | CON | 185 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
Wayne | 4 | Wayne | 67587 | SR 3018 over Tributary Middle Creek | 3018 | 671 | Bridge Replacement | FD | 581 | 2024-07-25 | 2024-07-25 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Wayne | 4 | Wayne | 67587 | SR 3018 over Tributary Middle Creek | 3018 | 671 | Bridge Replacement | CON | BOF | 2024-07-25 | 2024-07-25 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 67587 | SR 3018 over Tributary Middle Creek | 3018 | 671 | Bridge Replacement | CON | 581 | 2024-07-25 | 2024-07-25 | 0 | 0 | 2000000 | 600000 | 0 | 0 | 0 | 0 | 0 | 2600000
Wayne | 4 | Wayne | 67589 | SR 3020 over Inlet Lake Quinsigamund | 3020 | 650 | Bridge Replacement | FD | 185 | 2026-05-21 |  | 0 | 100000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
Wayne | 4 | Wayne | 67589 | SR 3020 over Inlet Lake Quinsigamund | 3020 | 650 | Bridge Replacement | ROW | 581 | 2026-05-21 |  | 0 | 0 | 84500 | 0 | 0 | 0 | 0 | 0 | 0 | 84500
Wayne | 4 | Wayne | 67589 | SR 3020 over Inlet Lake Quinsigamund | 3020 | 650 | Bridge Replacement | CON | 185 | 2026-05-21 |  | 0 | 0 | 0 | 0 | 960000 | 40000 | 0 | 0 | 0 | 1000000
Wayne | 4 | Wayne | 67592 | SR 3030 over Van Auken Creek | 3030 | D50 | Bridge Replacement | ROW | 581 | 2026-05-07 |  | 0 | 47545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47545
Wayne | 4 | Wayne | 67592 | SR 3030 over Van Auken Creek | 3030 | D50 | Bridge Replacement | CON | 185 | 2026-05-07 |  | 0 | 0 | 100000 | 400000 | 0 | 0 | 0 | 0 | 0 | 500000
Wayne | 4 | Wayne | 68883 | SR 247 over West Branch Dyberry Creek | 247 | 370 | Bridge Replacement | PE | BRIP | 2034-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 68883 | SR 247 over West Branch Dyberry Creek | 247 | 370 | Bridge Replacement | PE | 185 | 2034-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 68900 | SR 590 over Inlet to Finn Swamp | 590 | 651 | Bridge Replacement | CON | 581 | 2024-11-07 | 2024-11-07 | 0 | 500000 | 480000 | 698500 | 0 | 0 | 0 | 0 | 0 | 1678500
Wayne | 4 | Wayne | 68906 | SR 1004 over Calkins Creek | 1004 | 671 | Bridge Replacement | CON | STP | 2027-06-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 400000
Wayne | 4 | Wayne | 68906 | SR 1004 over Calkins Creek | 1004 | 671 | Bridge Replacement | CON | 185 | 2027-06-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
Wayne | 4 | Wayne | 68921 | SR 1023 over South Branch Equinunk | 1023 | 671 | Bridge Replacement | CON | BOF | 2023-12-14 | 2023-12-14 | 0 | 66228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66228
Wayne | 4 | Wayne | 68921 | SR 1023 over South Branch Equinunk | 1023 | 671 | Bridge Replacement | CON | 581 | 2023-12-14 | 2023-12-14 | 0 | 16557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16557
Wayne | 4 | Wayne | 68945 | SR 3031 over Wangum Brook | 3031 | 670 | Bridge Restoration | PE | BOF | 2034-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 68945 | SR 3031 over Wangum Brook | 3031 | 670 | Bridge Restoration | PE | 581 | 2034-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 68945 | SR 3031 over Wangum Brook | 3031 | 670 | Bridge Restoration | CON | BOF | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 1600000
Wayne | 4 | Wayne | 68945 | SR 3031 over Wangum Brook | 3031 | 670 | Bridge Restoration | CON | 185 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
Wayne | 4 | Wayne | 68948 | SR 3039 over Collins Brook | 3039 | 670 | Bridge Restoration | PE | 185 | 2034-10-01 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Wayne | 4 | Wayne | 68948 | SR 3039 over Collins Brook | 3039 | 670 | Bridge Restoration | CON | 581 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
Wayne | 4 | Wayne | 68953 | SR 4001 over Van Auken Ck | 4001 | 670 | Bridge Replacement | CON | 581 | 2024-10-10 | 2024-10-10 | 732655 | 587500 | 29845 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000
Wayne | 4 | Wayne | 68967 | SR 4004 over Outlet White Oak Pond | 4004 | 670 | Bridge Replacement | CON | 581 | 2024-10-10 |  | 0 | 222450 | 179186 | 396651 | 0 | 0 | 0 | 0 | 0 | 798287
Wayne | 4 | Wayne | 79565 | SR 4041 over Riley Creek | 4041 | 650 | Bridge Restoration | CON | BOF | 2023-07-27 | 2023-07-27 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Wayne | 4 | Wayne | 79565 | SR 4041 over Riley Creek | 4041 | 650 | Bridge Restoration | CON | STP | 2023-07-27 | 2023-07-27 | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68000
Wayne | 4 | Wayne | 79565 | SR 4041 over Riley Creek | 4041 | 650 | Bridge Restoration | CON | 185 | 2023-07-27 | 2023-07-27 | 37000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37000
Wayne | 4 | Wayne | 79591 | SR 6 Ov Middle Creek | 6 | 651 | Bridge Restoration | FD | STP | 2027-06-24 |  | 280000 | 92000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372000
Wayne | 4 | Wayne | 79591 | SR 6 Ov Middle Creek | 6 | 651 | Bridge Restoration | FD | 185 | 2027-06-24 |  | 70000 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93000
Wayne | 4 | Wayne | 79591 | SR 6 Ov Middle Creek | 6 | 651 | Bridge Restoration | ROW | 581 | 2027-06-24 |  | 0 | 0 | 34500 | 0 | 0 | 0 | 0 | 0 | 0 | 34500
Wayne | 4 | Wayne | 79591 | SR 6 Ov Middle Creek | 6 | 651 | Bridge Restoration | CON | STP | 2027-06-24 |  | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
Wayne | 4 | Wayne | 79595 | SR 447 over Branch of Wallenpaupack Creek | 447 | 650 | Bridge Restoration | FD | BOF | 2025-12-04 | 2025-12-04 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Wayne | 4 | Wayne | 79595 | SR 447 over Branch of Wallenpaupack Creek | 447 | 650 | Bridge Restoration | FD | BRIP | 2025-12-04 | 2025-12-04 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Wayne | 4 | Wayne | 79595 | SR 447 over Branch of Wallenpaupack Creek | 447 | 650 | Bridge Restoration | FD | 581 | 2025-12-04 | 2025-12-04 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Wayne | 4 | Wayne | 79595 | SR 447 over Branch of Wallenpaupack Creek | 447 | 650 | Bridge Restoration | ROW | 581 | 2025-12-04 | 2025-12-04 | 0 | 0 | 107700 | 0 | 0 | 0 | 0 | 0 | 0 | 107700
Wayne | 4 | Wayne | 79595 | SR 447 over Branch of Wallenpaupack Creek | 447 | 650 | Bridge Restoration | CON | BOF | 2025-12-04 | 2025-12-04 | 0 | 250000 | 400000 | 200000 | 193200 | 0 | 0 | 0 | 0 | 1043200
Wayne | 4 | Wayne | 79595 | SR 447 over Branch of Wallenpaupack Creek | 447 | 650 | Bridge Restoration | CON | 185 | 2025-12-04 | 2025-12-04 | 0 | 62500 | 100000 | 50000 | 48300 | 0 | 0 | 0 | 0 | 260800
Wayne | 4 | Wayne | 79597 | SR 1005 over Outlet of Bunnells Pond | 1005 | 650 | Bridge Restoration | FD | BOF | 2024-03-28 | 2024-03-28 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Wayne | 4 | Wayne | 79597 | SR 1005 over Outlet of Bunnells Pond | 1005 | 650 | Bridge Restoration | FD | 185 | 2024-03-28 | 2024-03-28 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Wayne | 4 | Wayne | 79599 | SR 1016 over Little Equinunk Creek | 1016 | 652 | Bridge Restoration | PE | STP | 2031-01-30 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 79599 | SR 1016 over Little Equinunk Creek | 1016 | 652 | Bridge Restoration | PE | 185 | 2031-01-30 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 79599 | SR 1016 over Little Equinunk Creek | 1016 | 652 | Bridge Restoration | FD | STP | 2031-01-30 |  | 0 | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 280000
Wayne | 4 | Wayne | 79599 | SR 1016 over Little Equinunk Creek | 1016 | 652 | Bridge Restoration | FD | 581 | 2031-01-30 |  | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 70000
Wayne | 4 | Wayne | 79599 | SR 1016 over Little Equinunk Creek | 1016 | 652 | Bridge Restoration | CON | STP | 2031-01-30 |  | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 1600000
Wayne | 4 | Wayne | 79599 | SR 1016 over Little Equinunk Creek | 1016 | 652 | Bridge Restoration | CON | 581 | 2031-01-30 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
Wayne | 4 | Wayne | 79600 | SR 3011 over West Branch of Wallenpaupack Creek | 3011 | 0 | Bridge Restoration | PE | BOF | 2031-01-30 |  | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
Wayne | 4 | Wayne | 79600 | SR 3011 over West Branch of Wallenpaupack Creek | 3011 | 0 | Bridge Restoration | PE | 581 | 2031-01-30 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Wayne | 4 | Wayne | 79600 | SR 3011 over West Branch of Wallenpaupack Creek | 3011 | 0 | Bridge Restoration | FD | BOF | 2031-01-30 |  | 0 | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 280000
Wayne | 4 | Wayne | 79600 | SR 3011 over West Branch of Wallenpaupack Creek | 3011 | 0 | Bridge Restoration | FD | 581 | 2031-01-30 |  | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 70000
Wayne | 4 | Wayne | 79600 | SR 3011 over West Branch of Wallenpaupack Creek | 3011 | 0 | Bridge Restoration | CON | 581 | 2031-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000 | 2100000
Wayne | 4 | Wayne | 85786 | SR 1002 over South Branch Calkins Creek | 1002 | D52 | Bridge Replacement | FD | 581 | 2027-07-29 |  | 151085 | 89451 | 104464 | 40000 | 0 | 0 | 0 | 0 | 0 | 385000
Wayne | 4 | Wayne | 85786 | SR 1002 over South Branch Calkins Creek | 1002 | D52 | Bridge Replacement | ROW | 581 | 2027-07-29 |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Wayne | 4 | Wayne | 85786 | SR 1002 over South Branch Calkins Creek | 1002 | D52 | Bridge Replacement | CON | STP | 2027-07-29 |  | 0 | 0 | 0 | 400000 | 0 | 0 | 1000000 | 0 | 0 | 1400000
Wayne | 4 | Wayne | 85789 | SR 4035 over East Lackawanna River | 4035 | 650 | Bridge Restoration | PE | BOF | 2031-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 85789 | SR 4035 over East Lackawanna River | 4035 | 650 | Bridge Restoration | PE | 581 | 2031-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 85789 | SR 4035 over East Lackawanna River | 4035 | 650 | Bridge Restoration | CON | 581 | 2031-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
Wayne | 4 | Wayne | 89909 | SR 4010 over Shadigee Creek | 4010 | 650 | Bridge Replacement | ROW | 185 | 2025-11-06 | 2025-11-06 | 0 | 0 | 26189 | 0 | 0 | 0 | 0 | 0 | 0 | 26189
Wayne | 4 | Wayne | 89909 | SR 4010 over Shadigee Creek | 4010 | 650 | Bridge Replacement | CON | 581 | 2025-11-06 | 2025-11-06 | 0 | 920000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920000
Wayne | 4 | Wayne | 96742 | SR 3002 over Butternut Creek | 3002 | D51 | Bridge Restoration | CON | BOF | 2025-12-11 | 2025-12-11 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 96742 | SR 3002 over Butternut Creek | 3002 | D51 | Bridge Restoration | CON | 185 | 2025-12-11 | 2025-12-11 | 0 | 75000 | 289800 | 0 | 0 | 0 | 0 | 0 | 0 | 364800
Wayne | 4 | Wayne | 96817 | SR 652 Slide | 652 | SLD | Highway Restoration | ROW | 581 | 2026-07-30 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 96817 | SR 652 Slide | 652 | SLD | Highway Restoration | CON | 581 | 2026-07-30 |  | 0 | 0 | 250000 | 900000 | 0 | 0 | 0 | 0 | 0 | 1150000
Wayne | 4 | Wayne | 98210 | Wayne County Reserve Line |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 21845 | 188170 | 44780 | 553800 | 1267000 | 567000 | 267000 | 166000 | 3075595
Wayne | 4 | Wayne | 98210 | Wayne County Reserve Line |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 200 | 3000 | 500 | 109818 | 5000 | 5000 | 0 | 180000 | 303518
Wayne | 4 | Wayne | 98210 | Wayne County Reserve Line |  |  | Reserve Line Item | CON | CRP |  |  | 250000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 1027000 | 3076000
Wayne | 4 | Wayne | 98210 | Wayne County Reserve Line |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214000 | 3201000 | 3415000
Wayne | 4 | Wayne | 98210 | Wayne County Reserve Line |  |  | Reserve Line Item | CON | STP |  |  | 0 | 509000 | 20000 | 10000 | 40000 | 60000 | 50000 | 50000 | 399000 | 1138000
Wayne | 4 | Wayne | 98210 | Wayne County Reserve Line |  |  | Reserve Line Item | CON | 185 |  |  | 295000 | 24207 | 33600 | 24000 | 32700 | 266000 | 424850 | 767500 | 1364850 | 3232707
Wayne | 4 | Wayne | 98210 | Wayne County Reserve Line |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 1158 | 3491 | 4524 | 332204 | 105000 | 505000 | 104000 | 313000 | 1368377
Wayne | 4 | Wayne | 102313 | Wayne Co Bridge Review |  |  | Reserve Line Item | CON | 185 |  |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 106033 | Bridge Preservation |  |  | Reserve Line Item | CON | BRIP |  |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 106033 | Bridge Preservation |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000
Wayne | 4 | Wayne | 108014 | Wayne County Project Delivery |  |  | Reserve Line Item | CON | 581 |  |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Wayne | 4 | Wayne | 109884 | SR 590 over Outlet House Pond | 590 | 652 | Bridge Replacement | FD | STP | 2026-10-22 |  | 102000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102000
Wayne | 4 | Wayne | 109884 | SR 590 over Outlet House Pond | 590 | 652 | Bridge Replacement | CON | STP | 2026-10-22 |  | 520000 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Wayne | 4 | Wayne | 109884 | SR 590 over Outlet House Pond | 590 | 652 | Bridge Replacement | CON | 581 | 2026-10-22 |  | 130000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Wayne | 4 | Wayne | 109885 | SR 590 over Inlet to Lake Moc-a-Tec | 590 | 653 | Bridge Replacement | UTL | 581 | 2026-03-12 | 2026-03-12 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000
Wayne | 4 | Wayne | 109885 | SR 590 over Inlet to Lake Moc-a-Tec | 590 | 653 | Bridge Replacement | CON | PRTCT | 2026-03-12 | 2026-03-12 | 2504096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504096
Wayne | 4 | Wayne | 109886 | SR 1007 over Boyd's Creek | 1007 | 650 | Bridge Replacement | CON | BOF | 2026-01-08 | 2026-02-12 | 0 | 0 | 235830 | 343320 | 0 | 0 | 0 | 0 | 0 | 579150
Wayne | 4 | Wayne | 109886 | SR 1007 over Boyd's Creek | 1007 | 650 | Bridge Replacement | CON | BRIP | 2026-01-08 | 2026-02-12 | 0 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Wayne | 4 | Wayne | 111777 | SR 6 and Long Ridge Road | 6 | 690 | Safety Improvement | PE | HSIP | 2027-04-08 |  | 0 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 45000
Wayne | 4 | Wayne | 113847 | SR 2009 over Holbert Creek | 2009 | 650 | Bridge Replacement | PE | BOF | 2034-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 113847 | SR 2009 over Holbert Creek | 2009 | 650 | Bridge Replacement | PE | 581 | 2034-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 113868 | SR 4014 over Hiawatha Creek | 4014 | 651 | Bridge Replacement | CON | 185 | 2025-11-06 | 2025-11-06 | 500000 | 655293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1155293
Wayne | 4 | Wayne | 113894 | SR 191, 3031,3042 Intersection Safety Improvements | 191 | 693 | Safety Improvement | FD | HSIP | 2026-12-03 |  | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000
Wayne | 4 | Wayne | 113894 | SR 191, 3031,3042 Intersection Safety Improvements | 191 | 693 | Safety Improvement | CON | HSIP | 2026-12-03 |  | 104000 | 650000 | 411000 | 180000 | 0 | 0 | 0 | 0 | 0 | 1345000
Wayne | 4 | Wayne | 113988 | Guiderail Mash Upgrades - Wayne |  |  | Reserve Line Item | CON | STP |  |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 114064 | Church Street over Lackawaxen River | 7402 | BRG | Bridge Replacement | PE | BOF | 2029-10-18 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Wayne | 4 | Wayne | 114064 | Church Street over Lackawaxen River | 7402 | BRG | Bridge Replacement | PE | STP | 2029-10-18 |  | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Wayne | 4 | Wayne | 114064 | Church Street over Lackawaxen River | 7402 | BRG | Bridge Replacement | PE | 183 | 2029-10-18 |  | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Wayne | 4 | Wayne | 114064 | Church Street over Lackawaxen River | 7402 | BRG | Bridge Replacement | PE | LOC | 2029-10-18 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 114064 | Church Street over Lackawaxen River | 7402 | BRG | Bridge Replacement | FD | 185 | 2029-10-18 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
Wayne | 4 | Wayne | 114064 | Church Street over Lackawaxen River | 7402 | BRG | Bridge Replacement | CON | BOF | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 1000000 | 700000 | 2400000
Wayne | 4 | Wayne | 114064 | Church Street over Lackawaxen River | 7402 | BRG | Bridge Replacement | CON | 185 | 2029-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 131150 | 187500 | 131150 | 449800
Wayne | 4 | Wayne | 114068 | 2025 Asset Management - Phase 1 | 6 | 601 | Reserve Line Item | CON | STP |  |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 114068 | 2025 Asset Management - Phase 1 | 6 | 601 | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000
Wayne | 4 | Wayne | 114069 | 2025 Asset Management - Phase 2 | 6 | 602 | Reserve Line Item | CON | STP |  |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 114069 | 2025 Asset Management - Phase 2 | 6 | 602 | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Wayne | 4 | Wayne | 115572 | SR 6 and Maple Street Safety Improvement | 6 | IMP | Safety Improvement | FD | HSIP | 2027-02-11 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Wayne | 4 | Wayne | 115572 | SR 6 and Maple Street Safety Improvement | 6 | IMP | Safety Improvement | CON | HSIP | 2027-02-11 |  | 0 | 0 | 109000 | 355000 | 356000 | 180000 | 0 | 0 | 0 | 1000000
Wayne | 4 | Wayne | 115743 | SR 4001 over Van Auken Creek | 4001 | P69 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 250000
Wayne | 4 | Wayne | 115746 | SR 3032 Drainage Improvement | 3032 | DNG | Highway Restoration | ROW | PRTCT | 2025-12-04 | 2025-12-04 | 134790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134790
Wayne | 4 | Wayne | 115746 | SR 3032 Drainage Improvement | 3032 | DNG | Highway Restoration | ROW | 581 | 2025-12-04 | 2025-12-04 | 0 | 139800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139800
Wayne | 4 | Wayne | 115746 | SR 3032 Drainage Improvement | 3032 | DNG | Highway Restoration | CON | PRTCT | 2025-12-04 | 2025-12-04 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000
Wayne | 4 | Wayne | 115746 | SR 3032 Drainage Improvement | 3032 | DNG | Highway Restoration | CON | 582 | 2025-12-04 | 2025-12-04 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Wayne | 4 | Wayne | 115884 | SR 4041 over Equinunk Creek | 4041 | 651 | Bridge Restoration | CON | BOF | 2024-03-28 | 2024-03-28 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000
Wayne | 4 | Wayne | 115946 | SR 3028 Shoulder Widening/ELRS | 3028 | ELR | Safety Improvement | PE | HSIP | 2028-02-17 |  | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000
Wayne | 4 | Wayne | 115946 | SR 3028 Shoulder Widening/ELRS | 3028 | ELR | Safety Improvement | FD | HSIP | 2028-02-17 |  | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Wayne | 4 | Wayne | 115946 | SR 3028 Shoulder Widening/ELRS | 3028 | ELR | Safety Improvement | CON | HSIP | 2028-02-17 |  | 0 | 0 | 100000 | 400000 | 444000 | 556000 | 0 | 0 | 0 | 1500000
Wayne | 4 | Wayne | 116098 | SR 0590/3028 Intersection Safety Improvement | 590 | SAF | Safety Improvement | FD | HSIP | 2027-07-29 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Wayne | 4 | Wayne | 116098 | SR 0590/3028 Intersection Safety Improvement | 590 | SAF | Safety Improvement | CON | HSIP | 2027-07-29 |  | 0 | 0 | 0 | 0 | 0 | 64000 | 800000 | 586000 | 0 | 1450000
Wayne | 4 | Wayne | 116968 | SR 170 over West Branch of Lackawaxen River | 170 | 651 | Bridge Restoration | PE | BRIP | 2033-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 116968 | SR 170 over West Branch of Lackawaxen River | 170 | 651 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 116969 | SR 191 over Wallenpaupack Creek | 191 | 655 | Bridge Restoration | PE | BRIP | 2031-01-30 |  | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000
Wayne | 4 | Wayne | 116969 | SR 191 over Wallenpaupack Creek | 191 | 655 | Bridge Restoration | PE | 581 | 2031-01-30 |  | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000
Wayne | 4 | Wayne | 116969 | SR 191 over Wallenpaupack Creek | 191 | 655 | Bridge Restoration | FD | STP | 2031-01-30 |  | 0 | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 280000
Wayne | 4 | Wayne | 116969 | SR 191 over Wallenpaupack Creek | 191 | 655 | Bridge Restoration | FD | 581 | 2031-01-30 |  | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 70000
Wayne | 4 | Wayne | 116969 | SR 191 over Wallenpaupack Creek | 191 | 655 | Bridge Restoration | CON | STP | 2031-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 1200000
Wayne | 4 | Wayne | 116969 | SR 191 over Wallenpaupack Creek | 191 | 655 | Bridge Restoration | CON | 581 | 2031-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 300000
Wayne | 4 | Wayne | 116970 | SR 191 over Middle Creek and Abandoned Railroad | 191 | 656 | Bridge Restoration | PE | BRIP | 2032-10-01 |  | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000
Wayne | 4 | Wayne | 116970 | SR 191 over Middle Creek and Abandoned Railroad | 191 | 656 | Bridge Restoration | PE | 581 | 2032-10-01 |  | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000
Wayne | 4 | Wayne | 116970 | SR 191 over Middle Creek and Abandoned Railroad | 191 | 656 | Bridge Restoration | CON | STP | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Wayne | 4 | Wayne | 116971 | SR 191 over Little Equinunk Creek | 191 | 657 | Bridge Restoration | PE | BRIP | 2032-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 116971 | SR 191 over Little Equinunk Creek | 191 | 657 | Bridge Restoration | PE | 185 | 2032-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 116971 | SR 191 over Little Equinunk Creek | 191 | 657 | Bridge Restoration | CON | BRIP | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000
Wayne | 4 | Wayne | 116971 | SR 191 over Little Equinunk Creek | 191 | 657 | Bridge Restoration | CON | STP | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Wayne | 4 | Wayne | 116971 | SR 191 over Little Equinunk Creek | 191 | 657 | Bridge Restoration | CON | 581 | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 300000
Wayne | 4 | Wayne | 116972 | SR 191 over Salt River Brook | 191 | 658 | Bridge Restoration | PE | BRIP | 2033-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 116972 | SR 191 over Salt River Brook | 191 | 658 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 116973 | SR 191 over Outlet of Nabbys Lake | 191 | 659 | Bridge Restoration | PE | BRIP | 2033-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 116973 | SR 191 over Outlet of Nabbys Lake | 191 | 659 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 116973 | SR 191 over Outlet of Nabbys Lake | 191 | 659 | Bridge Restoration | CON | STP | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Wayne | 4 | Wayne | 116973 | SR 191 over Outlet of Nabbys Lake | 191 | 659 | Bridge Restoration | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Wayne | 4 | Wayne | 116974 | SR 247 over Kinneyville Creek | 247 | 650 | Bridge Restoration | PE | BRIP | 2034-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 116974 | SR 247 over Kinneyville Creek | 247 | 650 | Bridge Restoration | PE | 185 | 2034-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 116974 | SR 247 over Kinneyville Creek | 247 | 650 | Bridge Restoration | CON | BOF | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Wayne | 4 | Wayne | 116974 | SR 247 over Kinneyville Creek | 247 | 650 | Bridge Restoration | CON | BRIP | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Wayne | 4 | Wayne | 116974 | SR 247 over Kinneyville Creek | 247 | 650 | Bridge Restoration | CON | 581 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000
Wayne | 4 | Wayne | 116975 | SR 371 over Branch of Calkins Creek | 371 | 650 | Bridge Restoration | PE | STP | 2031-01-09 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 116975 | SR 371 over Branch of Calkins Creek | 371 | 650 | Bridge Restoration | PE | 185 | 2031-01-09 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 116975 | SR 371 over Branch of Calkins Creek | 371 | 650 | Bridge Restoration | FD | STP | 2031-01-09 |  | 0 | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 280000
Wayne | 4 | Wayne | 116975 | SR 371 over Branch of Calkins Creek | 371 | 650 | Bridge Restoration | FD | 581 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 70000
Wayne | 4 | Wayne | 116975 | SR 371 over Branch of Calkins Creek | 371 | 650 | Bridge Restoration | CON | STP | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 800000
Wayne | 4 | Wayne | 116975 | SR 371 over Branch of Calkins Creek | 371 | 650 | Bridge Restoration | CON | 581 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 200000
Wayne | 4 | Wayne | 116976 | SR 507 over Tributary to Lehigh River | 507 | 651 | Bridge Restoration | PE | STP | 2031-01-09 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 116976 | SR 507 over Tributary to Lehigh River | 507 | 651 | Bridge Restoration | PE | 185 | 2031-01-09 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 116976 | SR 507 over Tributary to Lehigh River | 507 | 651 | Bridge Restoration | FD | STP | 2031-01-09 |  | 0 | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 280000
Wayne | 4 | Wayne | 116976 | SR 507 over Tributary to Lehigh River | 507 | 651 | Bridge Restoration | FD | 581 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 70000
Wayne | 4 | Wayne | 116976 | SR 507 over Tributary to Lehigh River | 507 | 651 | Bridge Restoration | CON | 581 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 2000000
Wayne | 4 | Wayne | 116977 | SR 652 over Tributary to Delaware River | 652 | 652 | Bridge Restoration | PE | BRIP | 2033-10-01 |  | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000
Wayne | 4 | Wayne | 116977 | SR 652 over Tributary to Delaware River | 652 | 652 | Bridge Restoration | PE | 581 | 2033-10-01 |  | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000
Wayne | 4 | Wayne | 116977 | SR 652 over Tributary to Delaware River | 652 | 652 | Bridge Restoration | FD | BRIP | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 350000
Wayne | 4 | Wayne | 116977 | SR 652 over Tributary to Delaware River | 652 | 652 | Bridge Restoration | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Wayne | 4 | Wayne | 116978 | SR 670 over Cramer Creek | 670 | 652 | Bridge Restoration | PE | BRIP | 2034-10-01 |  | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000
Wayne | 4 | Wayne | 116978 | SR 670 over Cramer Creek | 670 | 652 | Bridge Restoration | PE | 581 | 2034-10-01 |  | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000
Wayne | 4 | Wayne | 116978 | SR 670 over Cramer Creek | 670 | 652 | Bridge Restoration | CON | 581 | 2034-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000
Wayne | 4 | Wayne | 116979 | SR 690 over Wallenpaupack Creek | 690 | 650 | Bridge Restoration | PE | BRIP | 2033-10-01 |  | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 12000
Wayne | 4 | Wayne | 116979 | SR 690 over Wallenpaupack Creek | 690 | 650 | Bridge Restoration | PE | 581 | 2033-10-01 |  | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000
Wayne | 4 | Wayne | 116979 | SR 690 over Wallenpaupack Creek | 690 | 650 | Bridge Restoration | FD | STP | 2033-10-01 |  | 0 | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 240000
Wayne | 4 | Wayne | 116979 | SR 690 over Wallenpaupack Creek | 690 | 650 | Bridge Restoration | FD | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 60000
Wayne | 4 | Wayne | 116979 | SR 690 over Wallenpaupack Creek | 690 | 650 | Bridge Restoration | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Wayne | 4 | Wayne | 116980 | SR 3002 over Webster Creek | 3002 | 651 | Bridge Replacement | PE | 185 | 2031-01-09 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Wayne | 4 | Wayne | 116980 | SR 3002 over Webster Creek | 3002 | 651 | Bridge Replacement | FD | 581 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000
Wayne | 4 | Wayne | 116980 | SR 3002 over Webster Creek | 3002 | 651 | Bridge Replacement | CON | 581 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 2000000
Wayne | 4 | Wayne | 116981 | SR 3004 over Jones Creek | 3004 | 652 | Bridge Restoration | PE | BOF | 2033-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 116981 | SR 3004 over Jones Creek | 3004 | 652 | Bridge Restoration | PE | 581 | 2033-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 116981 | SR 3004 over Jones Creek | 3004 | 652 | Bridge Restoration | CON | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000
Wayne | 4 | Wayne | 116982 | SR 3022 over Outlet at Bronsons Pond | 3022 | 650 | Bridge Restoration | PE | 185 | 2033-10-01 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Wayne | 4 | Wayne | 116983 | SR 3028 over Inlet to Lake Wanaka | 3028 | 650 | Bridge Restoration | PE | 185 | 2031-01-09 |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
Wayne | 4 | Wayne | 116983 | SR 3028 over Inlet to Lake Wanaka | 3028 | 650 | Bridge Restoration | FD | 581 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000
Wayne | 4 | Wayne | 116983 | SR 3028 over Inlet to Lake Wanaka | 3028 | 650 | Bridge Restoration | CON | 581 | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 2000000
Wayne | 4 | Wayne | 116984 | SR 4031 over Johnsons Creek | 4031 | 652 | Bridge Restoration | PE | BRIP | 2034-10-01 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Wayne | 4 | Wayne | 116984 | SR 4031 over Johnsons Creek | 4031 | 652 | Bridge Restoration | PE | 581 | 2034-10-01 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 117298 | 2025 Asset Management - Phase 3 | 6 | AST | Reserve Line Item | CON | STP |  |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 117298 | 2025 Asset Management - Phase 3 | 6 | AST | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000
Wayne | 4 | Wayne | 117299 | 2025 Asset Management - Phase 4 | 170 | AST | Reserve Line Item | CON | STP |  |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 117299 | 2025 Asset Management - Phase 4 | 170 | AST | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000
Wayne | 4 | Wayne | 118121 | SR 1011 over Beach Lake Creek | 1011 | 670 | Bridge Replacement | FD | 185 | 2027-01-28 |  | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Wayne | 4 | Wayne | 118121 | SR 1011 over Beach Lake Creek | 1011 | 670 | Bridge Replacement | CON | 185 | 2027-01-28 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
Wayne | 4 | Wayne | 118294 | PA/NY Bridge #6 Painting - Cochecton | 371 | BPA | Bridge Restoration | CON | 581 | 2022-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 950000
Wayne | 4 | Wayne | 118295 | PA/NY Bridge #10 Painting - Buckingham | 191 | BPA | Bridge Restoration | CON | 581 | 2022-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 950000
Wayne | 4 | Wayne | 119792 | SR 6 High Friction Surface Treatment/Signing | 6 | HFS | Safety Improvement | CON | HSIP | 2024-07-11 | 2024-07-11 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000
Wayne | 4 | Wayne | 121173 | SR 196 & SR 507 Intersection Improvement | 196 | IMP | Safety Improvement | PE | HSIP | 2031-10-09 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Wayne | 4 | Wayne | 121173 | SR 196 & SR 507 Intersection Improvement | 196 | IMP | Safety Improvement | FD | HSIP | 2031-10-09 |  | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000
Wayne | 4 | Wayne | 121173 | SR 196 & SR 507 Intersection Improvement | 196 | IMP | Safety Improvement | CON | HSIP | 2031-10-09 |  | 0 | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000
Wayne | 4 | Wayne | 121293 | I-84 Cameras - Wayne County | 84 | CAM | Highway Restoration | PE | CRP | 2025-10-09 | 2025-10-09 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200
Wayne | 4 | Wayne | 121293 | I-84 Cameras - Wayne County | 84 | CAM | Highway Restoration | PE | CRPU | 2025-10-09 | 2025-10-09 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300
Wayne | 4 | Wayne | 121293 | I-84 Cameras - Wayne County | 84 | CAM | Highway Restoration | FD | CRP | 2025-10-09 | 2025-10-09 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Wayne | 4 | Wayne | 121293 | I-84 Cameras - Wayne County | 84 | CAM | Highway Restoration | FD | CRPU | 2025-10-09 | 2025-10-09 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
Wayne | 4 | Wayne | 121293 | I-84 Cameras - Wayne County | 84 | CAM | Highway Restoration | CON | CRP | 2025-10-09 | 2025-10-09 | 69996 | 43336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113332
Wayne | 4 | Wayne | 121293 | I-84 Cameras - Wayne County | 84 | CAM | Highway Restoration | CON | CRPU | 2025-10-09 | 2025-10-09 | 10834 | 10834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21668
Wayne | 4 | Wayne | 121535 | Honesdale Main Street Streetscape | 6 | TAS | Transportation Enhancement | CON | TAP | 2026-06-18 |  | 1330000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1330000
Wayne | 4 | Wayne | 121631 | SR 3004 and Westridge Road Intersection | 3004 | TIF | Safety Improvement | CON | 581 | 2026-06-12 |  | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
Wayne | 4 | Wayne | 121919 | SR 1002 ov Delaware River Repairs | 1002 | EMG | General Maintenance | PE | 185 |  | 2024-02-15 | 815000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815000
Wayne | 4 | Wayne | 121919 | SR 1002 ov Delaware River Repairs | 1002 | EMG | General Maintenance | CON | 185 |  | 2024-02-15 | 697000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697000
Wayne | 4 | Wayne | 122254 | SR 191, SR 3033 Intersection Improvements MTM | 191 | MTM | MultiModal | CON | 411 |  |  | 0 | 825000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825000
Wayne | 4 | Wayne | 122254 | SR 191, SR 3033 Intersection Improvements MTM | 191 | MTM | MultiModal | CON | LOC |  |  | 0 | 135175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135175
Wayne | 4 | Wayne | 122260 | SR 1002 ov Delaware River 2024 | 1002 | E24 | Bridge Removal | CON | BOF | 2025-01-13 | 2025-02-28 | 9200000 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000
Wayne | 4 | Wayne | 122296 | SR 3028 over Middle Creek Preservation | 3028 | PRS | Bridge Preservation - State Funded | PE | 581 | 2028-02-17 |  | 90800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90800
Wayne | 4 | Wayne | 122496 | ROW Claims Assistance - Wayne |  |  | Reserve Line Item | ROW | 581 |  |  | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
Wayne | 4 | Wayne | 123023 | Interstate 84 Repairs | 84 | M26 | Disaster Permanent Repair | CON | 581 | 2025-08-15 | 2022-05-12 | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000
Wayne | 4 | Wayne | 123637 | Fairmont Road over Merrigan Creek |  | LOC | Bridge Replacement | CON | ACT13 |  |  | 0 | 848450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 848450
Williamsport | 3 | Lycoming | 5755 | SR 1010 over Roaring Branch | 1010 | 001 | Bridge Restoration | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 150000 | 150000 | 0 | 0 | 0 | 300000
Williamsport | 3 | Lycoming | 5755 | SR 1010 over Roaring Branch | 1010 | 001 | Bridge Restoration | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 200000
Williamsport | 3 | Lycoming | 5755 | SR 1010 over Roaring Branch | 1010 | 001 | Bridge Restoration | ROW | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 5755 | SR 1010 over Roaring Branch | 1010 | 001 | Bridge Restoration | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Williamsport | 3 | Lycoming | 5755 | SR 1010 over Roaring Branch | 1010 | 001 | Bridge Restoration | CON | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 2000000
Williamsport | 3 | Lycoming | 5920 | SR 1006 over Trib to Wallis Run | 1006 | 035 | Bridge Replacement | PE | 185 | 2028-09-14 |  | 0 | 200000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Williamsport | 3 | Lycoming | 5920 | SR 1006 over Trib to Wallis Run | 1006 | 035 | Bridge Replacement | FD | 185 | 2028-09-14 |  | 0 | 0 | 0 | 50000 | 25000 | 0 | 0 | 0 | 0 | 75000
Williamsport | 3 | Lycoming | 5920 | SR 1006 over Trib to Wallis Run | 1006 | 035 | Bridge Replacement | ROW | 185 | 2028-09-14 |  | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 5920 | SR 1006 over Trib to Wallis Run | 1006 | 035 | Bridge Replacement | UTL | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Williamsport | 3 | Lycoming | 5920 | SR 1006 over Trib to Wallis Run | 1006 | 035 | Bridge Replacement | CON | BOF | 2028-09-14 |  | 0 | 0 | 0 | 0 | 374000 | 250000 | 0 | 0 | 0 | 624000
Williamsport | 3 | Lycoming | 5928 | T-434 over Mosquito Crk | 7202 | RBR | Bridge Replacement | CON | 183 | 2027-01-07 |  | 0 | 0 | 600000 | 600000 | 0 | 0 | 0 | 0 | 0 | 1200000
Williamsport | 3 | Lycoming | 5939 | SR 284 over Flooks Run | 284 | 012 | Bridge Replacement | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 50000 | 0 | 0 | 150000
Williamsport | 3 | Lycoming | 5939 | SR 284 over Flooks Run | 284 | 012 | Bridge Replacement | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 50000
Williamsport | 3 | Lycoming | 5939 | SR 284 over Flooks Run | 284 | 012 | Bridge Replacement | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000
Williamsport | 3 | Lycoming | 5939 | SR 284 over Flooks Run | 284 | 012 | Bridge Replacement | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Williamsport | 3 | Lycoming | 5939 | SR 284 over Flooks Run | 284 | 012 | Bridge Replacement | CON | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 853000 | 853000
Williamsport | 3 | Lycoming | 5983 | SR 1005 over Plunketts Creek | 1005 | 001 | Bridge Replacement | PE | BRIP | 2028-09-14 |  | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000
Williamsport | 3 | Lycoming | 5983 | SR 1005 over Plunketts Creek | 1005 | 001 | Bridge Replacement | FD | 185 | 2028-09-14 |  | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Williamsport | 3 | Lycoming | 5983 | SR 1005 over Plunketts Creek | 1005 | 001 | Bridge Replacement | ROW | 185 | 2028-09-14 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 5983 | SR 1005 over Plunketts Creek | 1005 | 001 | Bridge Replacement | UTL | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Williamsport | 3 | Lycoming | 5983 | SR 1005 over Plunketts Creek | 1005 | 001 | Bridge Replacement | CON | BOF | 2028-09-14 |  | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 2000000
Williamsport | 3 | Lycoming | 6000 | US 220/4th St Interchange | 220 | 119 | Study Phase of Project | STUDY | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Williamsport | 3 | Lycoming | 6030 | SR 2061 over Beaver Run | 2061 | 012 | Bridge Replacement | PE | 185 | 2027-09-16 |  | 95000 | 205000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Williamsport | 3 | Lycoming | 6030 | SR 2061 over Beaver Run | 2061 | 012 | Bridge Replacement | FD | 185 | 2027-09-16 |  | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 150000
Williamsport | 3 | Lycoming | 6030 | SR 2061 over Beaver Run | 2061 | 012 | Bridge Replacement | ROW | 185 | 2027-09-16 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Williamsport | 3 | Lycoming | 6030 | SR 2061 over Beaver Run | 2061 | 012 | Bridge Replacement | UTL | 185 | 2027-09-16 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Williamsport | 3 | Lycoming | 6030 | SR 2061 over Beaver Run | 2061 | 012 | Bridge Replacement | CON | BOF | 2027-09-16 |  | 0 | 0 | 0 | 288000 | 312000 | 0 | 0 | 0 | 0 | 600000
Williamsport | 3 | Lycoming | 6031 | SR 4010 over Larrys Creek | 4010 | 011 | Bridge Replacement | ROW | 185 | 2026-01-08 | 2026-01-08 | 27605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27605
Williamsport | 3 | Lycoming | 6031 | SR 4010 over Larrys Creek | 4010 | 011 | Bridge Replacement | UTL | 185 | 2026-01-08 | 2026-01-08 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 6031 | SR 4010 over Larrys Creek | 4010 | 011 | Bridge Replacement | CON | BOF | 2026-01-08 | 2026-01-08 | 0 | 937000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 937000
Williamsport | 3 | Lycoming | 6031 | SR 4010 over Larrys Creek | 4010 | 011 | Bridge Replacement | CON | 581 | 2026-01-08 | 2026-01-08 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
Williamsport | 3 | Lycoming | 6082 | T-668 over Sugar Run |  | LBR | Bridge Replacement | FD | BOF | 2027-09-16 |  | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Williamsport | 3 | Lycoming | 6082 | T-668 over Sugar Run |  | LBR | Bridge Replacement | FD | 183 | 2027-09-16 |  | 0 | 11250 | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 22500
Williamsport | 3 | Lycoming | 6082 | T-668 over Sugar Run |  | LBR | Bridge Replacement | ROW | BOF | 2027-09-16 |  | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Williamsport | 3 | Lycoming | 6082 | T-668 over Sugar Run |  | LBR | Bridge Replacement | ROW | 183 | 2027-09-16 |  | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
Williamsport | 3 | Lycoming | 6082 | T-668 over Sugar Run |  | LBR | Bridge Replacement | UTL | BOF | 2027-09-16 |  | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 16000
Williamsport | 3 | Lycoming | 6082 | T-668 over Sugar Run |  | LBR | Bridge Replacement | UTL | 183 | 2027-09-16 |  | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000
Williamsport | 3 | Lycoming | 6082 | T-668 over Sugar Run |  | LBR | Bridge Replacement | CON | BOF | 2027-09-16 |  | 0 | 0 | 0 | 320000 | 320000 | 0 | 0 | 0 | 0 | 640000
Williamsport | 3 | Lycoming | 6082 | T-668 over Sugar Run |  | LBR | Bridge Replacement | CON | 183 | 2027-09-16 |  | 0 | 0 | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 120000
Williamsport | 3 | Lycoming | 6083 | T-665 over German Run |  | LBR | Bridge Replacement | UTL | BOF | 2024-10-24 | 2024-10-24 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
Williamsport | 3 | Lycoming | 6083 | T-665 over German Run |  | LBR | Bridge Replacement | UTL | 183 | 2024-10-24 | 2024-10-24 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250
Williamsport | 3 | Lycoming | 6083 | T-665 over German Run |  | LBR | Bridge Replacement | CON | BOF | 2024-10-24 | 2024-10-24 | 1140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1140000
Williamsport | 3 | Lycoming | 6083 | T-665 over German Run |  | LBR | Bridge Replacement | CON | 183 | 2024-10-24 | 2024-10-24 | 213750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213750
Williamsport | 3 | Lycoming | 6083 | T-665 over German Run |  | LBR | Bridge Replacement | CON | LOC | 2024-10-24 | 2024-10-24 | 71250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71250
Williamsport | 3 | Lycoming | 6085 | T-836 over Trout Run |  | LBR | Bridge Replacement | FD | BOF | 2028-09-28 |  | 0 | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Williamsport | 3 | Lycoming | 6085 | T-836 over Trout Run |  | LBR | Bridge Replacement | FD | 183 | 2028-09-28 |  | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 6085 | T-836 over Trout Run |  | LBR | Bridge Replacement | FD | LOC | 2028-09-28 |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
Williamsport | 3 | Lycoming | 6085 | T-836 over Trout Run |  | LBR | Bridge Replacement | ROW | BOF | 2028-09-28 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
Williamsport | 3 | Lycoming | 6085 | T-836 over Trout Run |  | LBR | Bridge Replacement | ROW | 183 | 2028-09-28 |  | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
Williamsport | 3 | Lycoming | 6085 | T-836 over Trout Run |  | LBR | Bridge Replacement | UTL | BOF | 2028-09-28 |  | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 16000
Williamsport | 3 | Lycoming | 6085 | T-836 over Trout Run |  | LBR | Bridge Replacement | UTL | 183 | 2028-09-28 |  | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000
Williamsport | 3 | Lycoming | 6085 | T-836 over Trout Run |  | LBR | Bridge Replacement | CON | BOF | 2028-09-28 |  | 0 | 0 | 0 | 200000 | 400000 | 0 | 0 | 0 | 0 | 600000
Williamsport | 3 | Lycoming | 6085 | T-836 over Trout Run |  | LBR | Bridge Replacement | CON | 183 | 2028-09-28 |  | 0 | 0 | 0 | 37500 | 75000 | 0 | 0 | 0 | 0 | 112500
Williamsport | 3 | Lycoming | 6128 | SR 14 over Trout Run | 14 | 112 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Williamsport | 3 | Lycoming | 6205 | SR 44 over Susquehanna River | 44 | 079 | Bridge Preservation - Federal | PE | 185 | 2026-01-29 | 2026-01-29 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 6205 | SR 44 over Susquehanna River | 44 | 079 | Bridge Preservation - Federal | FD | 185 | 2026-01-29 | 2026-01-29 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Williamsport | 3 | Lycoming | 6205 | SR 44 over Susquehanna River | 44 | 079 | Bridge Preservation - Federal | CON | BRIP | 2026-01-29 | 2026-01-29 | 1146158 | 1925000 | 403842 | 0 | 0 | 0 | 0 | 0 | 0 | 3475000
Williamsport | 3 | Lycoming | 6206 | SR 414 over Pine Creek | 414 | 018 | Bridge Restoration | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 200000 | 0 | 0 | 250000
Williamsport | 3 | Lycoming | 6206 | SR 414 over Pine Creek | 414 | 018 | Bridge Restoration | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 6206 | SR 414 over Pine Creek | 414 | 018 | Bridge Restoration | CON | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1309000 | 0 | 2309000
Williamsport | 3 | Lycoming | 6209 | SR 4001 ov Lt Pine Creek | 4001 | 020 | Bridge Restoration | PE | STP | 2023-06-08 | 2023-06-08 | 0 | 1543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1543
Williamsport | 3 | Lycoming | 68713 | WATS TIP Reserve |  | 000 | Reserve Line Item | CON | BOF |  |  | 0 | 507000 | 2823000 | 1200000 | 0 | 1651000 | 1851000 | 1151000 | 0 | 9183000
Williamsport | 3 | Lycoming | 68713 | WATS TIP Reserve |  | 000 | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 3650158 | 4054000 | 4054000 | 4054000 | 4054000 | 4054000 | 16216000 | 40136158
Williamsport | 3 | Lycoming | 68713 | WATS TIP Reserve |  | 000 | Reserve Line Item | CON | CRP |  |  | 182000 | 310000 | 13000 | 365000 | 463000 | 463000 | 463000 | 463000 | 1853000 | 4575000
Williamsport | 3 | Lycoming | 68713 | WATS TIP Reserve |  | 000 | Reserve Line Item | CON | CRPU |  |  | 79000 | 0 | 0 | 0 | 152000 | 152000 | 152000 | 152000 | 610000 | 1297000
Williamsport | 3 | Lycoming | 68713 | WATS TIP Reserve |  | 000 | Reserve Line Item | CON | HSIP |  |  | 0 | 0 | 0 | 0 | 952712 | 1064000 | 1064000 | 1064000 | 4256000 | 8400712
Williamsport | 3 | Lycoming | 68713 | WATS TIP Reserve |  | 000 | Reserve Line Item | CON | NHPP |  |  | 0 | 311140 | 250000 | 0 | 0 | 0 | 800000 | 0 | 0 | 1361140
Williamsport | 3 | Lycoming | 68713 | WATS TIP Reserve |  | 000 | Reserve Line Item | CON | STP |  |  | 0 | 1726252 | 1000000 | 0 | 0 | 0 | 1200000 | 0 | 0 | 3926252
Williamsport | 3 | Lycoming | 68713 | WATS TIP Reserve |  | 000 | Reserve Line Item | CON | 185 |  |  | 0 | 410500 | 434500 | 100000 | 0 | 0 | 0 | 0 | 0 | 945000
Williamsport | 3 | Lycoming | 68713 | WATS TIP Reserve |  | 000 | Reserve Line Item | CON | 581 |  |  | 0 | 703000 | 450000 | 0 | 2980000 | 1709000 | 1823000 | 0 | 0 | 7665000
Williamsport | 3 | Lycoming | 74373 | Environmental Mitigation Monitoring WATS |  | W05 | Study Phase of Project | CON | 581 |  |  | 0 | 10000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 20000 | 60000
Williamsport | 3 | Lycoming | 79249 | US 220 over Wolf Run | 220 | 213 | Bridge Replacement | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 0 | 0 | 300000
Williamsport | 3 | Lycoming | 79249 | US 220 over Wolf Run | 220 | 213 | Bridge Replacement | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 200000
Williamsport | 3 | Lycoming | 79249 | US 220 over Wolf Run | 220 | 213 | Bridge Replacement | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
Williamsport | 3 | Lycoming | 79249 | US 220 over Wolf Run | 220 | 213 | Bridge Replacement | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Williamsport | 3 | Lycoming | 79249 | US 220 over Wolf Run | 220 | 213 | Bridge Replacement | CON | NHPP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1250000
Williamsport | 3 | Lycoming | 79249 | US 220 over Wolf Run | 220 | 213 | Bridge Replacement | CON | STP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 2250000
Williamsport | 3 | Lycoming | 87918 | SR 44 over Lawshe Run | 44 | 064 | Bridge Replacement | CON | 185 | 2023-08-10 | 2023-08-10 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Williamsport | 3 | Lycoming | 88743 | SR 4001 over Lt Pine Crk | 4001 | 003 | Bridge Restoration | PE | 185 | 2026-12-03 |  | 113935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113935
Williamsport | 3 | Lycoming | 88743 | SR 4001 over Lt Pine Crk | 4001 | 003 | Bridge Restoration | FD | 185 | 2026-12-03 |  | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
Williamsport | 3 | Lycoming | 88743 | SR 4001 over Lt Pine Crk | 4001 | 003 | Bridge Restoration | ROW | 185 | 2026-12-03 |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Williamsport | 3 | Lycoming | 88743 | SR 4001 over Lt Pine Crk | 4001 | 003 | Bridge Restoration | UTL | 185 | 2026-12-03 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Williamsport | 3 | Lycoming | 88743 | SR 4001 over Lt Pine Crk | 4001 | 003 | Bridge Restoration | CON | 185 | 2026-12-03 |  | 0 | 0 | 2000000 | 2453000 | 0 | 0 | 0 | 0 | 0 | 4453000
Williamsport | 3 | Lycoming | 93732 | PA 287 to West Fourth Street | 220 | 122 | Safety Improvement | ROW | NHPP | 2019-07-25 | 2019-07-25 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Williamsport | 3 | Lycoming | 93732 | PA 287 to West Fourth Street | 220 | 122 | Safety Improvement | UTL | NHPP | 2019-07-25 | 2019-07-25 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
Williamsport | 3 | Lycoming | 97508 | US 15 to Campbell Street | 2014 | 092 | Highway Reconstruction | STUDY | NHPP | 2036-01-01 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 0 | 500000
Williamsport | 3 | Lycoming | 97508 | US 15 to Campbell Street | 2014 | 092 | Highway Reconstruction | PE | NHPP | 2036-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Williamsport | 3 | Lycoming | 97508 | US 15 to Campbell Street | 2014 | 092 | Highway Reconstruction | FD | NHPP | 2036-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Williamsport | 3 | Lycoming | 97508 | US 15 to Campbell Street | 2014 | 092 | Highway Reconstruction | CON | STP | 2036-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8229000 | 8229000
Williamsport | 3 | Lycoming | 97508 | US 15 to Campbell Street | 2014 | 092 | Highway Reconstruction | CON | 581 | 2036-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14516000 | 14516000
Williamsport | 3 | Lycoming | 97609 | PA 44 over Ramsey Run | 44 | 054 | Bridge Restoration | PE | 185 | 2036-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 300000
Williamsport | 3 | Lycoming | 97615 | PA 87 over Little Bear Creek | 87 | 106 | Bridge Replacement | FD | 185 | 2027-11-04 |  | 39500 | 195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234500
Williamsport | 3 | Lycoming | 97615 | PA 87 over Little Bear Creek | 87 | 106 | Bridge Replacement | ROW | 185 | 2027-11-04 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
Williamsport | 3 | Lycoming | 97615 | PA 87 over Little Bear Creek | 87 | 106 | Bridge Replacement | CON | 185 | 2027-11-04 |  | 0 | 0 | 0 | 0 | 750000 | 326000 | 695000 | 0 | 0 | 1771000
Williamsport | 3 | Lycoming | 97617 | PA 284 over Bonnell Run | 284 | 007 | Bridge Restoration | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 0 | 0 | 300000
Williamsport | 3 | Lycoming | 97617 | PA 284 over Bonnell Run | 284 | 007 | Bridge Restoration | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 200000
Williamsport | 3 | Lycoming | 97617 | PA 284 over Bonnell Run | 284 | 007 | Bridge Restoration | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
Williamsport | 3 | Lycoming | 97617 | PA 284 over Bonnell Run | 284 | 007 | Bridge Restoration | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
Williamsport | 3 | Lycoming | 97617 | PA 284 over Bonnell Run | 284 | 007 | Bridge Restoration | CON | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Williamsport | 3 | Lycoming | 97620 | PA 864 over Mill Creek | 864 | 015 | Bridge Restoration | PE | 185 | 2028-08-24 |  | 0 | 150000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Williamsport | 3 | Lycoming | 97620 | PA 864 over Mill Creek | 864 | 015 | Bridge Restoration | FD | 185 | 2028-08-24 |  | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 75000
Williamsport | 3 | Lycoming | 97620 | PA 864 over Mill Creek | 864 | 015 | Bridge Restoration | ROW | 185 | 2028-08-24 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Williamsport | 3 | Lycoming | 97620 | PA 864 over Mill Creek | 864 | 015 | Bridge Restoration | UTL | 185 | 2028-08-24 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Williamsport | 3 | Lycoming | 97620 | PA 864 over Mill Creek | 864 | 015 | Bridge Restoration | CON | 185 | 2028-08-24 |  | 0 | 0 | 0 | 0 | 500000 | 1000000 | 0 | 0 | 0 | 1500000
Williamsport | 3 | Lycoming | 97623 | PA 284 over Blacks Creek | 284 | 008 | Bridge Replacement | FD | BOF | 2025-10-09 | 2025-10-09 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Williamsport | 3 | Lycoming | 97623 | PA 284 over Blacks Creek | 284 | 008 | Bridge Replacement | ROW | 185 | 2025-10-09 | 2025-10-09 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Williamsport | 3 | Lycoming | 97623 | PA 284 over Blacks Creek | 284 | 008 | Bridge Replacement | CON | BOF | 2025-10-09 | 2025-10-09 | 1406000 | 388000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1794000
Williamsport | 3 | Lycoming | 97623 | PA 284 over Blacks Creek | 284 | 008 | Bridge Replacement | CON | BRIP | 2025-10-09 | 2025-10-09 | 2115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2115000
Williamsport | 3 | Lycoming | 97632 | SR 2003 over Spring Creek | 2003 | 010 | Bridge Replacement | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 0 | 0 | 300000
Williamsport | 3 | Lycoming | 97632 | SR 2003 over Spring Creek | 2003 | 010 | Bridge Replacement | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Williamsport | 3 | Lycoming | 97632 | SR 2003 over Spring Creek | 2003 | 010 | Bridge Replacement | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000
Williamsport | 3 | Lycoming | 97632 | SR 2003 over Spring Creek | 2003 | 010 | Bridge Replacement | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Williamsport | 3 | Lycoming | 97632 | SR 2003 over Spring Creek | 2003 | 010 | Bridge Replacement | CON | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Williamsport | 3 | Lycoming | 97639 | PA 118 over Greggs Creek | 118 | 011 | Bridge Restoration | PE | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 0 | 300000
Williamsport | 3 | Lycoming | 97639 | PA 118 over Greggs Creek | 118 | 011 | Bridge Restoration | FD | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Williamsport | 3 | Lycoming | 97639 | PA 118 over Greggs Creek | 118 | 011 | Bridge Restoration | ROW | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
Williamsport | 3 | Lycoming | 97639 | PA 118 over Greggs Creek | 118 | 011 | Bridge Restoration | UTL | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Williamsport | 3 | Lycoming | 97639 | PA 118 over Greggs Creek | 118 | 011 | Bridge Restoration | CON | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000
Williamsport | 3 | Lycoming | 97654 | PA 118 over Sugar Run | 118 | 112 | Bridge Restoration | PE | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 0 | 300000
Williamsport | 3 | Lycoming | 97654 | PA 118 over Sugar Run | 118 | 112 | Bridge Restoration | FD | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Williamsport | 3 | Lycoming | 97654 | PA 118 over Sugar Run | 118 | 112 | Bridge Restoration | ROW | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
Williamsport | 3 | Lycoming | 97654 | PA 118 over Sugar Run | 118 | 112 | Bridge Restoration | UTL | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Williamsport | 3 | Lycoming | 97654 | PA 118 over Sugar Run | 118 | 112 | Bridge Restoration | CON | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000
Williamsport | 3 | Lycoming | 97658 | PA 118 ov Little Muncy Cr | 118 | 113 | Bridge Restoration | PE | 185 | 2036-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Williamsport | 3 | Lycoming | 97661 | PA 405 ov Trib Susq Rvr | 405 | 085 | Bridge Restoration | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 0 | 300000
Williamsport | 3 | Lycoming | 97661 | PA 405 ov Trib Susq Rvr | 405 | 085 | Bridge Restoration | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Williamsport | 3 | Lycoming | 97661 | PA 405 ov Trib Susq Rvr | 405 | 085 | Bridge Restoration | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
Williamsport | 3 | Lycoming | 97661 | PA 405 ov Trib Susq Rvr | 405 | 085 | Bridge Restoration | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Williamsport | 3 | Lycoming | 97661 | PA 405 ov Trib Susq Rvr | 405 | 085 | Bridge Restoration | CON | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Williamsport | 3 | Lycoming | 97662 | SR 2053 over Wolf Run | 2053 | 002 | Bridge Restoration | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 0 | 0 | 300000
Williamsport | 3 | Lycoming | 97662 | SR 2053 over Wolf Run | 2053 | 002 | Bridge Restoration | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Williamsport | 3 | Lycoming | 97662 | SR 2053 over Wolf Run | 2053 | 002 | Bridge Restoration | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000
Williamsport | 3 | Lycoming | 97662 | SR 2053 over Wolf Run | 2053 | 002 | Bridge Restoration | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Williamsport | 3 | Lycoming | 97662 | SR 2053 over Wolf Run | 2053 | 002 | Bridge Restoration | CON | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Williamsport | 3 | Lycoming | 97663 | PA 442 over Dry Run | 442 | 021 | Bridge Replacement | PE | 185 | 2035-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Williamsport | 3 | Lycoming | 98940 | Bennet Run to Odell Road | 2014 | 118 | Highway Restoration | CON | NHPP | 2025-02-27 | 2025-02-27 | 556637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556637
Williamsport | 3 | Lycoming | 98940 | Bennet Run to Odell Road | 2014 | 118 | Highway Restoration | CON | STP | 2025-02-27 | 2025-02-27 | 66323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66323
Williamsport | 3 | Lycoming | 98948 | SR 2014 to SR 2024 | 2029 | 005 | 409 Expanded Maintenance | PE | 581 | 2028-01-01 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Williamsport | 3 | Lycoming | 99003 | Water Street to Steele Lane | 220 | 166 | Highway Restoration | CON | STP | 2024-09-26 | 2024-09-26 | 1019000 | 422000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1441000
Williamsport | 3 | Lycoming | 99008 | PA 54 to School House Rd | 405 | 087 | Highway Reconstruction | STUDY | 581 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
Williamsport | 3 | Lycoming | 99025 | SR 1009 over Trib to Blockhouse Cr | 1009 | 008 | Bridge Replacement | CON | 185 | 2024-12-12 | 2024-12-12 | 350000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425000
Williamsport | 3 | Lycoming | 99034 | Bridge Deck Overlays | 15 | 154 | Bridge Preservation - Federal | FD | 185 | 2027-01-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 150000
Williamsport | 3 | Lycoming | 99034 | Bridge Deck Overlays | 15 | 154 | Bridge Preservation - Federal | CON | NHPP | 2027-01-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1506000 | 2756000
Williamsport | 3 | Lycoming | 99035 | SR 2073 ov Greggs Run | 2073 | 001 | Bridge Replacement | FD | 185 | 2025-10-09 | 2025-10-09 | 60000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Williamsport | 3 | Lycoming | 99035 | SR 2073 ov Greggs Run | 2073 | 001 | Bridge Replacement | ROW | 185 | 2025-10-09 | 2025-10-09 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 99035 | SR 2073 ov Greggs Run | 2073 | 001 | Bridge Replacement | CON | BOF | 2025-10-09 | 2025-10-09 | 0 | 290000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290000
Williamsport | 3 | Lycoming | 99035 | SR 2073 ov Greggs Run | 2073 | 001 | Bridge Replacement | CON | BRIP | 2025-10-09 | 2025-10-09 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Williamsport | 3 | Lycoming | 99036 | SR 3007 over Pine Run | 3007 | 015 | Bridge Replacement | PE | 185 | 2026-05-21 |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Williamsport | 3 | Lycoming | 99036 | SR 3007 over Pine Run | 3007 | 015 | Bridge Replacement | FD | 185 | 2026-05-21 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 99036 | SR 3007 over Pine Run | 3007 | 015 | Bridge Replacement | UTL | 185 | 2026-05-21 |  | 0 | 37000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37000
Williamsport | 3 | Lycoming | 99036 | SR 3007 over Pine Run | 3007 | 015 | Bridge Replacement | CON | 185 | 2026-05-21 |  | 300000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
Williamsport | 3 | Lycoming | 99051 | SR 1017 ov Trout Run | 1017 | 018 | Bridge Restoration | CON | BOF | 2036-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Williamsport | 3 | Lycoming | 99052 | SR 3010 ov Larrys Creek | 3010 | 016 | Bridge Restoration | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 250000 | 100000 | 0 | 0 | 0 | 350000
Williamsport | 3 | Lycoming | 99052 | SR 3010 ov Larrys Creek | 3010 | 016 | Bridge Restoration | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 200000
Williamsport | 3 | Lycoming | 99052 | SR 3010 ov Larrys Creek | 3010 | 016 | Bridge Restoration | ROW | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 99052 | SR 3010 ov Larrys Creek | 3010 | 016 | Bridge Restoration | UTL | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
Williamsport | 3 | Lycoming | 99052 | SR 3010 ov Larrys Creek | 3010 | 016 | Bridge Restoration | CON | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000 | 1150000
Williamsport | 3 | Lycoming | 99061 | SR 4010 ov Larry's Creek | 4010 | 006 | Bridge Replacement | ROW | 185 | 2026-01-08 | 2026-01-08 | 34710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34710
Williamsport | 3 | Lycoming | 99061 | SR 4010 ov Larry's Creek | 4010 | 006 | Bridge Replacement | CON | BOF | 2026-01-08 | 2026-01-08 | 0 | 900000 | 146000 | 0 | 0 | 0 | 0 | 0 | 0 | 1046000
Williamsport | 3 | Lycoming | 99061 | SR 4010 ov Larry's Creek | 4010 | 006 | Bridge Replacement | CON | BRIP | 2026-01-08 | 2026-01-08 | 0 | 304000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304000
Williamsport | 3 | Lycoming | 99061 | SR 4010 ov Larry's Creek | 4010 | 006 | Bridge Replacement | CON | 581 | 2026-01-08 | 2026-01-08 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
Williamsport | 3 | Lycoming | 99226 | Lyc Co Bridge Prsv Grp | 180 | 127 | Bridge Restoration | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 150000
Williamsport | 3 | Lycoming | 99226 | Lyc Co Bridge Prsv Grp | 180 | 127 | Bridge Restoration | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 99226 | Lyc Co Bridge Prsv Grp | 180 | 127 | Bridge Restoration | CON | NHPP | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 646000 | 500000 | 0 | 1146000
Williamsport | 3 | Lycoming | 99226 | Lyc Co Bridge Prsv Grp | 180 | 127 | Bridge Restoration | CON | STP | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1020000 | 1020000 | 0 | 2040000
Williamsport | 3 | Lycoming | 99233 | PA 14 over Red Run | 14 | 098 | Bridge Restoration | PE | 185 | 2028-09-01 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Williamsport | 3 | Lycoming | 99233 | PA 14 over Red Run | 14 | 098 | Bridge Restoration | FD | 185 | 2028-09-01 |  | 0 | 0 | 75000 | 100000 | 0 | 0 | 0 | 0 | 0 | 175000
Williamsport | 3 | Lycoming | 99233 | PA 14 over Red Run | 14 | 098 | Bridge Restoration | ROW | 185 | 2028-09-01 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 99233 | PA 14 over Red Run | 14 | 098 | Bridge Restoration | UTL | 185 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 32000 | 0 | 0 | 0 | 0 | 32000
Williamsport | 3 | Lycoming | 99233 | PA 14 over Red Run | 14 | 098 | Bridge Restoration | CON | 185 | 2028-09-01 |  | 0 | 0 | 0 | 0 | 1500000 | 500000 | 0 | 0 | 0 | 2000000
Williamsport | 3 | Lycoming | 99237 | PA 973 over Mill Creek | 973 | 030 | Bridge Restoration | PE | 185 | 2028-09-14 |  | 270000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Williamsport | 3 | Lycoming | 99237 | PA 973 over Mill Creek | 973 | 030 | Bridge Restoration | FD | 185 | 2028-09-14 |  | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 200000
Williamsport | 3 | Lycoming | 99237 | PA 973 over Mill Creek | 973 | 030 | Bridge Restoration | ROW | 185 | 2028-09-14 |  | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 99237 | PA 973 over Mill Creek | 973 | 030 | Bridge Restoration | UTL | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000
Williamsport | 3 | Lycoming | 99237 | PA 973 over Mill Creek | 973 | 030 | Bridge Restoration | CON | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 500000 | 1000000 | 0 | 0 | 0 | 1500000
Williamsport | 3 | Lycoming | 99290 | I-180 to PA 973 | 87 | 112 | Highway Restoration | CON | 581 | 2024-04-18 | 2024-04-18 | 8242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8242
Williamsport | 3 | Lycoming | 99300 | 3rd St to Lick Run Rd | 2039 | 008 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 99300 | 3rd St to Lick Run Rd | 2039 | 008 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000
Williamsport | 3 | Lycoming | 99337 | SR 2018 over Millers Run | 2018 | 011 | Bridge Restoration | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 0 | 0 | 300000
Williamsport | 3 | Lycoming | 99337 | SR 2018 over Millers Run | 2018 | 011 | Bridge Restoration | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Williamsport | 3 | Lycoming | 99337 | SR 2018 over Millers Run | 2018 | 011 | Bridge Restoration | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
Williamsport | 3 | Lycoming | 99337 | SR 2018 over Millers Run | 2018 | 011 | Bridge Restoration | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
Williamsport | 3 | Lycoming | 99337 | SR 2018 over Millers Run | 2018 | 011 | Bridge Restoration | CON | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Williamsport | 3 | Lycoming | 99348 | PA 44 over Furnace Run | 44 | 055 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 300000
Williamsport | 3 | Lycoming | 99352 | PA 287 ov Trb Larrys Crk | 287 | 140 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 100000 | 300000
Williamsport | 3 | Lycoming | 99354 | PA 405 ov Trib Susq Rvr | 405 | 088 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Williamsport | 3 | Lycoming | 99359 | SR 2014 ov Wolf Run | 2014 | 096 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Williamsport | 3 | Lycoming | 99373 | SR 3013 Slide Repair | 3013 | 07S | Highway Reconstruction | PE | 581 | 2034-01-01 |  | 0 | 0 | 100000 | 75000 | 0 | 0 | 0 | 0 | 0 | 175000
Williamsport | 3 | Lycoming | 99373 | SR 3013 Slide Repair | 3013 | 07S | Highway Reconstruction | FD | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 99373 | SR 3013 Slide Repair | 3013 | 07S | Highway Reconstruction | ROW | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 99373 | SR 3013 Slide Repair | 3013 | 07S | Highway Reconstruction | UTL | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Williamsport | 3 | Lycoming | 99373 | SR 3013 Slide Repair | 3013 | 07S | Highway Reconstruction | CON | 581 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000
Williamsport | 3 | Lycoming | 99374 | US 15 Guide Sign Upgrade | 15 | 256 | Safety Improvement | CON | NHPP | 2023-03-30 | 2023-03-30 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000
Williamsport | 3 | Lycoming | 99383 | PA 14 over Abbots Run | 14 | 099 | Bridge Restoration | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 0 | 300000
Williamsport | 3 | Lycoming | 99383 | PA 14 over Abbots Run | 14 | 099 | Bridge Restoration | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Williamsport | 3 | Lycoming | 99383 | PA 14 over Abbots Run | 14 | 099 | Bridge Restoration | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
Williamsport | 3 | Lycoming | 99383 | PA 14 over Abbots Run | 14 | 099 | Bridge Restoration | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Williamsport | 3 | Lycoming | 99383 | PA 14 over Abbots Run | 14 | 099 | Bridge Restoration | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Williamsport | 3 | Lycoming | 99393 | PA44 ov UpperPineBottomRn | 44 | 056 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 300000
Williamsport | 3 | Lycoming | 99402 | PA 414 over Truman Run | 414 | 056 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Williamsport | 3 | Lycoming | 99408 | SR 2083 over Lake Run | 2083 | 001 | Bridge Replacement | FD | 185 | 2027-09-01 |  | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Williamsport | 3 | Lycoming | 99408 | SR 2083 over Lake Run | 2083 | 001 | Bridge Replacement | ROW | 185 | 2027-09-01 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 99408 | SR 2083 over Lake Run | 2083 | 001 | Bridge Replacement | UTL | 185 | 2027-09-01 |  | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 99408 | SR 2083 over Lake Run | 2083 | 001 | Bridge Replacement | CON | BOF | 2027-09-01 |  | 0 | 0 | 0 | 375000 | 225000 | 0 | 0 | 0 | 0 | 600000
Williamsport | 3 | Lycoming | 102641 | Tivoli to Glen Mawr Curves | 220 | 181 | Safety Improvement | CON | HSIP | 2024-09-26 | 2024-09-26 | 649500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649500
Williamsport | 3 | Lycoming | 103945 | T-506 over Daughertys Run |  | RBR | Bridge Replacement | CON | 185 | 2026-08-01 |  | 450000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Williamsport | 3 | Lycoming | 103952 | T-557 over Gregs Run |  | LBR | Bridge Replacement | UTL | BOF | 2024-12-12 | 2024-12-12 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
Williamsport | 3 | Lycoming | 103952 | T-557 over Gregs Run |  | LBR | Bridge Replacement | UTL | 183 | 2024-12-12 | 2024-12-12 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
Williamsport | 3 | Lycoming | 103952 | T-557 over Gregs Run |  | LBR | Bridge Replacement | CON | STP | 2024-12-12 | 2024-12-12 | 625000 | 625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000
Williamsport | 3 | Lycoming | 103952 | T-557 over Gregs Run |  | LBR | Bridge Replacement | CON | 183 | 2024-12-12 | 2024-12-12 | 112500 | 31500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144000
Williamsport | 3 | Lycoming | 103952 | T-557 over Gregs Run |  | LBR | Bridge Replacement | CON | LOC | 2024-12-12 | 2024-12-12 | 37500 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000
Williamsport | 3 | Lycoming | 107588 | North of Fox Hollow Rd | 2032 | 12S | Highway Restoration | PE | 581 | 2028-01-01 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Williamsport | 3 | Lycoming | 107588 | North of Fox Hollow Rd | 2032 | 12S | Highway Restoration | FD | 581 | 2028-01-01 |  | 0 | 0 | 100000 | 50000 | 0 | 0 | 0 | 0 | 0 | 150000
Williamsport | 3 | Lycoming | 107588 | North of Fox Hollow Rd | 2032 | 12S | Highway Restoration | UTL | 581 | 2028-01-01 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Williamsport | 3 | Lycoming | 107588 | North of Fox Hollow Rd | 2032 | 12S | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 0 | 250000 | 1250000 | 0 | 0 | 0 | 0 | 1500000
Williamsport | 3 | Lycoming | 110162 | SR 15 over Hagermans Run | 15 | 205 | Bridge Restoration | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 0 | 300000
Williamsport | 3 | Lycoming | 110162 | SR 15 over Hagermans Run | 15 | 205 | Bridge Restoration | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Williamsport | 3 | Lycoming | 110162 | SR 15 over Hagermans Run | 15 | 205 | Bridge Restoration | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000
Williamsport | 3 | Lycoming | 110162 | SR 15 over Hagermans Run | 15 | 205 | Bridge Restoration | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Williamsport | 3 | Lycoming | 110162 | SR 15 over Hagermans Run | 15 | 205 | Bridge Restoration | CON | NHPP | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000
Williamsport | 3 | Lycoming | 110167 | SR 54 over Susquehanna River | 54 | 101 | Bridge Restoration | PE | 185 | 2026-01-15 | 2026-01-15 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
Williamsport | 3 | Lycoming | 110167 | SR 54 over Susquehanna River | 54 | 101 | Bridge Restoration | FD | 185 | 2026-01-15 | 2026-01-15 | 125000 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Williamsport | 3 | Lycoming | 110167 | SR 54 over Susquehanna River | 54 | 101 | Bridge Restoration | CON | STP | 2026-01-15 | 2026-01-15 | 1656000 | 381000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2037000
Williamsport | 3 | Lycoming | 110180 | PA 973 over North Fork Tombs Run | 973 | 041 | Bridge Replacement | ROW | 185 | 2025-09-25 | 2025-09-25 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 110180 | PA 973 over North Fork Tombs Run | 973 | 041 | Bridge Replacement | UTL | 185 | 2025-09-25 | 2025-09-25 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 110180 | PA 973 over North Fork Tombs Run | 973 | 041 | Bridge Replacement | CON | 185 | 2025-09-25 | 2025-09-25 | 181750 | 468250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000
Williamsport | 3 | Lycoming | 110181 | SR 2015 over German Run | 2015 | 004 | Bridge Replacement | PE | 185 | 2029-09-01 |  | 0 | 0 | 150000 | 100000 | 0 | 0 | 0 | 0 | 0 | 250000
Williamsport | 3 | Lycoming | 110181 | SR 2015 over German Run | 2015 | 004 | Bridge Replacement | FD | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 110181 | SR 2015 over German Run | 2015 | 004 | Bridge Replacement | ROW | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 110181 | SR 2015 over German Run | 2015 | 004 | Bridge Replacement | UTL | 185 | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 110181 | SR 2015 over German Run | 2015 | 004 | Bridge Replacement | CON | BOF | 2029-09-01 |  | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 0 | 0 | 600000
Williamsport | 3 | Lycoming | 110182 | SR 1006 over Trib to Slacks Run | 1006 | 034 | Bridge Replacement | PE | 185 | 2027-09-30 |  | 125000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Williamsport | 3 | Lycoming | 110182 | SR 1006 over Trib to Slacks Run | 1006 | 034 | Bridge Replacement | FD | 185 | 2027-09-30 |  | 0 | 0 | 100000 | 50000 | 0 | 0 | 0 | 0 | 0 | 150000
Williamsport | 3 | Lycoming | 110182 | SR 1006 over Trib to Slacks Run | 1006 | 034 | Bridge Replacement | ROW | 185 | 2027-09-30 |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 110182 | SR 1006 over Trib to Slacks Run | 1006 | 034 | Bridge Replacement | UTL | 185 | 2027-09-30 |  | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
Williamsport | 3 | Lycoming | 110182 | SR 1006 over Trib to Slacks Run | 1006 | 034 | Bridge Replacement | CON | BOF | 2027-09-30 |  | 0 | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | 500000
Williamsport | 3 | Lycoming | 110190 | SR 2004 over Trib to Spring Cr 2 | 2004 | 011 | Bridge Replacement | PE | 185 | 2030-09-01 |  | 0 | 0 | 150000 | 50000 | 0 | 0 | 0 | 0 | 0 | 200000
Williamsport | 3 | Lycoming | 110190 | SR 2004 over Trib to Spring Cr 2 | 2004 | 011 | Bridge Replacement | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 110190 | SR 2004 over Trib to Spring Cr 2 | 2004 | 011 | Bridge Replacement | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 110190 | SR 2004 over Trib to Spring Cr 2 | 2004 | 011 | Bridge Replacement | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 110190 | SR 2004 over Trib to Spring Cr 2 | 2004 | 011 | Bridge Replacement | CON | BOF | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 500000
Williamsport | 3 | Lycoming | 110204 | SR 2055 over Trib to Muncy Cr | 2055 | 003 | Bridge Replacement | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 150000
Williamsport | 3 | Lycoming | 110204 | SR 2055 over Trib to Muncy Cr | 2055 | 003 | Bridge Replacement | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 75000
Williamsport | 3 | Lycoming | 110204 | SR 2055 over Trib to Muncy Cr | 2055 | 003 | Bridge Replacement | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000
Williamsport | 3 | Lycoming | 110204 | SR 2055 over Trib to Muncy Cr | 2055 | 003 | Bridge Replacement | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000
Williamsport | 3 | Lycoming | 110204 | SR 2055 over Trib to Muncy Cr | 2055 | 003 | Bridge Replacement | CON | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Williamsport | 3 | Lycoming | 110205 | SR 2061 over Little Sugar Run | 2061 | 011 | Bridge Replacement | PE | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 150000 | 100000 | 0 | 0 | 0 | 250000
Williamsport | 3 | Lycoming | 110205 | SR 2061 over Little Sugar Run | 2061 | 011 | Bridge Replacement | FD | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 75000
Williamsport | 3 | Lycoming | 110205 | SR 2061 over Little Sugar Run | 2061 | 011 | Bridge Replacement | ROW | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000
Williamsport | 3 | Lycoming | 110205 | SR 2061 over Little Sugar Run | 2061 | 011 | Bridge Replacement | UTL | 185 | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000
Williamsport | 3 | Lycoming | 110205 | SR 2061 over Little Sugar Run | 2061 | 011 | Bridge Replacement | CON | BOF | 2032-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Williamsport | 3 | Lycoming | 110207 | SR 4001 over Tributary to Little Pine Creek | 4001 | 038 | Bridge Replacement | PE | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 150000
Williamsport | 3 | Lycoming | 110207 | SR 4001 over Tributary to Little Pine Creek | 4001 | 038 | Bridge Replacement | FD | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Williamsport | 3 | Lycoming | 110207 | SR 4001 over Tributary to Little Pine Creek | 4001 | 038 | Bridge Replacement | ROW | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000
Williamsport | 3 | Lycoming | 110207 | SR 4001 over Tributary to Little Pine Creek | 4001 | 038 | Bridge Replacement | UTL | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
Williamsport | 3 | Lycoming | 110207 | SR 4001 over Tributary to Little Pine Creek | 4001 | 038 | Bridge Replacement | CON | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000
Williamsport | 3 | Lycoming | 110208 | SR 4002 over Hughes Run | 4002 | 011 | Bridge Replacement | PE | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 150000
Williamsport | 3 | Lycoming | 110208 | SR 4002 over Hughes Run | 4002 | 011 | Bridge Replacement | FD | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Williamsport | 3 | Lycoming | 110208 | SR 4002 over Hughes Run | 4002 | 011 | Bridge Replacement | ROW | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000
Williamsport | 3 | Lycoming | 110208 | SR 4002 over Hughes Run | 4002 | 011 | Bridge Replacement | UTL | 185 | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
Williamsport | 3 | Lycoming | 110208 | SR 4002 over Hughes Run | 4002 | 011 | Bridge Replacement | CON | BOF | 2034-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Williamsport | 3 | Lycoming | 110772 | Montour Street Airport Connector |  | AIR | New Alignment | ROW | SXF | 2028-01-01 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 110772 | Montour Street Airport Connector |  | AIR | New Alignment | UTL | SXF | 2028-01-01 |  | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Williamsport | 3 | Lycoming | 110772 | Montour Street Airport Connector |  | AIR | New Alignment | CON | SXF | 2028-01-01 |  | 0 | 2983000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2983000
Williamsport | 3 | Lycoming | 110772 | Montour Street Airport Connector |  | AIR | New Alignment | CON | TAP | 2028-01-01 |  | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
Williamsport | 3 | Lycoming | 111628 | Willow Street |  | 67E | Transportation Enhancement | CON | TAP | 2027-01-14 |  | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Williamsport | 3 | Lycoming | 112414 | T-776 over English Run |  | LBR | Bridge Replacement | FD | BOF | 2027-09-16 |  | 0 | 0 | 80000 | 40000 | 0 | 0 | 0 | 0 | 0 | 120000
Williamsport | 3 | Lycoming | 112414 | T-776 over English Run |  | LBR | Bridge Replacement | FD | 183 | 2027-09-16 |  | 0 | 0 | 15000 | 7500 | 0 | 0 | 0 | 0 | 0 | 22500
Williamsport | 3 | Lycoming | 112414 | T-776 over English Run |  | LBR | Bridge Replacement | ROW | BOF | 2027-09-16 |  | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
Williamsport | 3 | Lycoming | 112414 | T-776 over English Run |  | LBR | Bridge Replacement | ROW | 183 | 2027-09-16 |  | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 2250
Williamsport | 3 | Lycoming | 112414 | T-776 over English Run |  | LBR | Bridge Replacement | UTL | BOF | 2027-09-16 |  | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 16000
Williamsport | 3 | Lycoming | 112414 | T-776 over English Run |  | LBR | Bridge Replacement | UTL | 183 | 2027-09-16 |  | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000
Williamsport | 3 | Lycoming | 112414 | T-776 over English Run |  | LBR | Bridge Replacement | CON | BOF | 2027-09-16 |  | 0 | 0 | 0 | 480000 | 320000 | 0 | 0 | 0 | 0 | 800000
Williamsport | 3 | Lycoming | 112414 | T-776 over English Run |  | LBR | Bridge Replacement | CON | 183 | 2027-09-16 |  | 0 | 0 | 0 | 90000 | 60000 | 0 | 0 | 0 | 0 | 150000
Williamsport | 3 | Lycoming | 113591 | SCM Monitoring |  |  | Stormwater Management | STUDY | 581 |  |  | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 120000 | 360000
Williamsport | 3 | Lycoming | 114090 | Edgewood Ave to S Market St | 654 | 030 | Highway Restoration | FD | 581 | 2026-03-12 | 2026-03-12 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000
Williamsport | 3 | Lycoming | 114090 | Edgewood Ave to S Market St | 654 | 030 | Highway Restoration | CON | STP | 2026-03-12 | 2026-03-12 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Williamsport | 3 | Lycoming | 114090 | Edgewood Ave to S Market St | 654 | 030 | Highway Restoration | CON | 581 | 2026-03-12 | 2026-03-12 | 1157000 | 1843000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
Williamsport | 3 | Lycoming | 114095 | Pine Creek to SR 287 | 220 | 237 | Highway Restoration | CON | NHPP | 2024-01-25 | 2024-01-25 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Williamsport | 3 | Lycoming | 114099 | Second St.to Park Drive INTERIM | 405 | 101 | Highway Restoration | UTL | 581 | 2026-03-26 | 2026-03-26 | 5700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5700
Williamsport | 3 | Lycoming | 114099 | Second St.to Park Drive INTERIM | 405 | 101 | Highway Restoration | CON | 581 | 2026-03-26 | 2026-03-26 | 1100000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000
Williamsport | 3 | Lycoming | 114161 | FFY 25 WATS RPM Contract |  |  | Safety Improvement | CON | 581 | 2025-06-26 | 2025-06-26 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
Williamsport | 3 | Lycoming | 114162 | FFY 26 WATS RPM Contract |  |  | Safety Improvement | CON | 581 | 2026-06-18 |  | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000
Williamsport | 3 | Lycoming | 114163 | FFY 27 WATS RPM Contract |  |  | Safety Improvement | CON | 581 | 2027-06-24 |  | 0 | 0 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 85000
Williamsport | 3 | Lycoming | 114165 | FFY 28 WATS RPM Contract |  |  | Safety Improvement | CON | 581 | 2028-06-01 |  | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 90000
Williamsport | 3 | Lycoming | 114265 | SR 2014 to Pond Rd | 2049 | 002 | Highway Restoration | PE | 581 | 2027-01-07 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Williamsport | 3 | Lycoming | 114265 | SR 2014 to Pond Rd | 2049 | 002 | Highway Restoration | CON | 581 | 2027-01-07 |  | 0 | 0 | 450000 | 300000 | 0 | 0 | 0 | 0 | 0 | 750000
Williamsport | 3 | Lycoming | 114310 | US 220 over Pine Creek | 220 | 238 | Bridge Restoration | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Williamsport | 3 | Lycoming | 114313 | SR 1003 over Roaring Run | 1003 | 049 | Bridge Replacement | CON | 185 | 2024-10-24 | 2024-10-24 | 700000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Williamsport | 3 | Lycoming | 114314 | SR 1003 over Joe Gray Run | 1003 | 050 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000
Williamsport | 3 | Lycoming | 114330 | SR 3001 over Trib to Antes Creek | 3001 | 019 | Bridge Replacement | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Williamsport | 3 | Lycoming | 114330 | SR 3001 over Trib to Antes Creek | 3001 | 019 | Bridge Replacement | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Williamsport | 3 | Lycoming | 114330 | SR 3001 over Trib to Antes Creek | 3001 | 019 | Bridge Replacement | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Williamsport | 3 | Lycoming | 114352 | SR 3013 over Quenshukney Run | 3013 | 010 | Bridge Replacement | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Williamsport | 3 | Lycoming | 114352 | SR 3013 over Quenshukney Run | 3013 | 010 | Bridge Replacement | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
Williamsport | 3 | Lycoming | 114352 | SR 3013 over Quenshukney Run | 3013 | 010 | Bridge Replacement | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000
Williamsport | 3 | Lycoming | 114352 | SR 3013 over Quenshukney Run | 3013 | 010 | Bridge Replacement | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Williamsport | 3 | Lycoming | 114352 | SR 3013 over Quenshukney Run | 3013 | 010 | Bridge Replacement | CON | BOF | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Williamsport | 3 | Lycoming | 114353 | SR 3025 over Daughertys Run | 3025 | 001 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Williamsport | 3 | Lycoming | 115026 | Skyline Dr to Old Pike Rd | 15 | 222 | Highway Restoration | PE | NHPP | 2027-01-28 |  | 800000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
Williamsport | 3 | Lycoming | 115026 | Skyline Dr to Old Pike Rd | 15 | 222 | Highway Restoration | FD | NHPP | 2027-01-28 |  | 0 | 325000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 425000
Williamsport | 3 | Lycoming | 115026 | Skyline Dr to Old Pike Rd | 15 | 222 | Highway Restoration | CON | NHPP | 2027-01-28 |  | 0 | 0 | 1357000 | 2215000 | 0 | 0 | 0 | 0 | 0 | 3572000
Williamsport | 3 | Lycoming | 115026 | Skyline Dr to Old Pike Rd | 15 | 222 | Highway Restoration | CON | STP | 2027-01-28 |  | 0 | 0 | 1271000 | 2850000 | 0 | 0 | 0 | 0 | 0 | 4121000
Williamsport | 3 | Lycoming | 115026 | Skyline Dr to Old Pike Rd | 15 | 222 | Highway Restoration | CON | 581 | 2027-01-28 |  | 0 | 0 | 1283000 | 3890000 | 0 | 0 | 0 | 0 | 0 | 5173000
Williamsport | 3 | Lycoming | 115091 | Dewey Ave to High St | 3036 | 003 | Highway Restoration | PE | 581 | 2028-01-01 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 115091 | Dewey Ave to High St | 3036 | 003 | Highway Restoration | FD | 581 | 2028-01-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Williamsport | 3 | Lycoming | 115091 | Dewey Ave to High St | 3036 | 003 | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 0 | 0 | 0 | 350000 | 350000 | 0 | 0 | 700000
Williamsport | 3 | Lycoming | 115340 | Beautys Run Rd (SR 3026) to SR 14 | 15 | 224 | Highway Restoration | FD | STP |  |  | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000
Williamsport | 3 | Lycoming | 115340 | Beautys Run Rd (SR 3026) to SR 14 | 15 | 224 | Highway Restoration | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 1153000 | 1023000 | 1069000 | 0 | 3245000
Williamsport | 3 | Lycoming | 115340 | Beautys Run Rd (SR 3026) to SR 14 | 15 | 224 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 700000 | 0 | 0 | 1700000
Williamsport | 3 | Lycoming | 115340 | Beautys Run Rd (SR 3026) to SR 14 | 15 | 224 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 3000000 | 0 | 7000000
Williamsport | 3 | Lycoming | 115343 | Beautys Run Rd (SR 3026) to SR 14 | 15 | 225 | Highway Restoration | FD | STP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000
Williamsport | 3 | Lycoming | 115343 | Beautys Run Rd (SR 3026) to SR 14 | 15 | 225 | Highway Restoration | CON | NHPP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000 | 1000000 | 0 | 2500000
Williamsport | 3 | Lycoming | 115343 | Beautys Run Rd (SR 3026) to SR 14 | 15 | 225 | Highway Restoration | CON | STP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 700000 | 600000 | 0 | 2300000
Williamsport | 3 | Lycoming | 115343 | Beautys Run Rd (SR 3026) to SR 14 | 15 | 225 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 1967000 | 0 | 5967000
Williamsport | 3 | Lycoming | 115344 | SR 14 to SR 284 NB | 15 | 226 | Highway Restoration | FD | 581 | 2029-01-01 |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Williamsport | 3 | Lycoming | 115344 | SR 14 to SR 284 NB | 15 | 226 | Highway Restoration | CON | NHPP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 2673000 | 500000 | 0 | 0 | 0 | 3173000
Williamsport | 3 | Lycoming | 115344 | SR 14 to SR 284 NB | 15 | 226 | Highway Restoration | CON | STP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 2000000 | 500000 | 0 | 0 | 0 | 2500000
Williamsport | 3 | Lycoming | 115344 | SR 14 to SR 284 NB | 15 | 226 | Highway Restoration | CON | 581 | 2029-01-01 |  | 0 | 0 | 0 | 0 | 1755000 | 0 | 0 | 0 | 0 | 1755000
Williamsport | 3 | Lycoming | 115356 | 1/2mile S. of 4 Mile Rd to SR 284 SB | 15 | 228 | Highway Restoration | PE | 581 | 2026-11-05 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Williamsport | 3 | Lycoming | 115356 | 1/2mile S. of 4 Mile Rd to SR 284 SB | 15 | 228 | Highway Restoration | FD | STP | 2026-11-05 |  | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000
Williamsport | 3 | Lycoming | 115356 | 1/2mile S. of 4 Mile Rd to SR 284 SB | 15 | 228 | Highway Restoration | CON | NHPP | 2026-11-05 |  | 0 | 3800000 | 2520000 | 305000 | 0 | 0 | 0 | 0 | 0 | 6625000
Williamsport | 3 | Lycoming | 115356 | 1/2mile S. of 4 Mile Rd to SR 284 SB | 15 | 228 | Highway Restoration | CON | STP | 2026-11-05 |  | 0 | 1000000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000
Williamsport | 3 | Lycoming | 116904 | Wavy Section between SRs 184 and 284 | 15 | 244 | Highway Restoration | CON | NHPP | 2024-07-11 | 2024-07-11 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Williamsport | 3 | Lycoming | 117230 | SR 973 over Tombs Run | 973 | 042 | Bridge Replacement | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000
Williamsport | 3 | Lycoming | 117230 | SR 973 over Tombs Run | 973 | 042 | Bridge Replacement | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Williamsport | 3 | Lycoming | 117230 | SR 973 over Tombs Run | 973 | 042 | Bridge Replacement | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
Williamsport | 3 | Lycoming | 117230 | SR 973 over Tombs Run | 973 | 042 | Bridge Replacement | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
Williamsport | 3 | Lycoming | 117230 | SR 973 over Tombs Run | 973 | 042 | Bridge Replacement | CON | BOF | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000
Williamsport | 3 | Lycoming | 117235 | Group Bridge Painting 2 | 2069 | 005 | Bridge Preservation - Federal | PE | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000
Williamsport | 3 | Lycoming | 117235 | Group Bridge Painting 2 | 2069 | 005 | Bridge Preservation - Federal | FD | 185 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Williamsport | 3 | Lycoming | 117235 | Group Bridge Painting 2 | 2069 | 005 | Bridge Preservation - Federal | CON | BOF | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000 | 0 | 1600000
Williamsport | 3 | Lycoming | 117281 | Group Bridge Painting | 405 | 107 | Bridge Preservation - State Funded | PE | 185 | 2037-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Williamsport | 3 | Lycoming | 117342 | FFY 29 WATS RPM Contract |  |  | Safety Improvement | CON | 581 | 2029-06-01 |  | 0 | 0 | 0 | 0 | 95000 | 0 | 0 | 0 | 0 | 95000
Williamsport | 3 | Lycoming | 117344 | FFY 30 WATS RPM Contract |  |  | Safety Improvement | CON | 581 | 2030-06-01 |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 117346 | FFY 31 WATS RPM Contract |  |  | Safety Improvement | CON | 581 | 2031-06-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 105000
Williamsport | 3 | Lycoming | 117347 | FFY 32 WATS RPM Contract |  |  | Safety Improvement | CON | 581 | 2032-06-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000 | 0 | 110000
Williamsport | 3 | Lycoming | 117348 | FFY 33 WATS RPM Contract |  |  | Safety Improvement | CON | 581 | 2033-06-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000 | 115000
Williamsport | 3 | Lycoming | 117349 | FFY 34 WATS RPM Contract |  |  | Safety Improvement | CON | 581 | 2034-06-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000
Williamsport | 3 | Lycoming | 117409 | I-180 EB On-Ramp to Third St. | 2029 | 009 | Highway Restoration | CON | STP | 2025-01-16 | 2025-01-16 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Williamsport | 3 | Lycoming | 117631 | SR 44 Group Bridge Preservation | 44 | 096 | Bridge Preservation - Federal | CON | BRIP | 2023-08-10 | 2023-08-10 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 117795 | Ramp B Rd (SR 8003) to State St | 2014 | 117 | Highway Restoration | PE | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 200000
Williamsport | 3 | Lycoming | 117795 | Ramp B Rd (SR 8003) to State St | 2014 | 117 | Highway Restoration | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 117795 | Ramp B Rd (SR 8003) to State St | 2014 | 117 | Highway Restoration | CON | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000
Williamsport | 3 | Lycoming | 117795 | Ramp B Rd (SR 8003) to State St | 2014 | 117 | Highway Restoration | CON | STP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000
Williamsport | 3 | Lycoming | 117864 | John Brady Dr to Industrial Park Rd | 2014 | 116 | Highway Restoration | FD | 581 | 2027-01-01 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Williamsport | 3 | Lycoming | 117864 | John Brady Dr to Industrial Park Rd | 2014 | 116 | Highway Restoration | CON | STP | 2027-01-01 |  | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Williamsport | 3 | Lycoming | 117882 | SR 14 over Trib Lycoming Crk | 14 | 130 | Bridge Replacement | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 150000 | 0 | 0 | 200000
Williamsport | 3 | Lycoming | 117882 | SR 14 over Trib Lycoming Crk | 14 | 130 | Bridge Replacement | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 200000
Williamsport | 3 | Lycoming | 117882 | SR 14 over Trib Lycoming Crk | 14 | 130 | Bridge Replacement | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 40000
Williamsport | 3 | Lycoming | 117882 | SR 14 over Trib Lycoming Crk | 14 | 130 | Bridge Replacement | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
Williamsport | 3 | Lycoming | 117882 | SR 14 over Trib Lycoming Crk | 14 | 130 | Bridge Replacement | CON | STP | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Williamsport | 3 | Lycoming | 117883 | SR 14 over Frozen Run | 14 | 131 | Bridge Restoration | PE | 185 | 1935-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 300000
Williamsport | 3 | Lycoming | 117883 | SR 14 over Frozen Run | 14 | 131 | Bridge Restoration | FD | 185 | 1935-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Williamsport | 3 | Lycoming | 117883 | SR 14 over Frozen Run | 14 | 131 | Bridge Restoration | ROW | 185 | 1935-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
Williamsport | 3 | Lycoming | 117883 | SR 14 over Frozen Run | 14 | 131 | Bridge Restoration | UTL | 185 | 1935-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Williamsport | 3 | Lycoming | 117883 | SR 14 over Frozen Run | 14 | 131 | Bridge Restoration | CON | 185 | 1935-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149000 | 149000
Williamsport | 3 | Lycoming | 117884 | SR 15 over Black Hole Creek | 15 | 255 | Bridge Replacement | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 0 | 300000
Williamsport | 3 | Lycoming | 117884 | SR 15 over Black Hole Creek | 15 | 255 | Bridge Replacement | FD | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Williamsport | 3 | Lycoming | 117884 | SR 15 over Black Hole Creek | 15 | 255 | Bridge Replacement | ROW | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
Williamsport | 3 | Lycoming | 117884 | SR 15 over Black Hole Creek | 15 | 255 | Bridge Replacement | UTL | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Williamsport | 3 | Lycoming | 117884 | SR 15 over Black Hole Creek | 15 | 255 | Bridge Replacement | CON | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Williamsport | 3 | Lycoming | 117885 | SR 44 over Norfolk Southern RR | 44 | 098 | Bridge Restoration | PE | 185 | 2027-10-21 |  | 240000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Williamsport | 3 | Lycoming | 117885 | SR 44 over Norfolk Southern RR | 44 | 098 | Bridge Restoration | FD | 185 | 2027-10-21 |  | 0 | 0 | 50000 | 100000 | 0 | 0 | 0 | 0 | 0 | 150000
Williamsport | 3 | Lycoming | 117885 | SR 44 over Norfolk Southern RR | 44 | 098 | Bridge Restoration | UTL | 185 | 2027-10-21 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 117885 | SR 44 over Norfolk Southern RR | 44 | 098 | Bridge Restoration | CON | STP | 2027-10-21 |  | 0 | 0 | 0 | 520000 | 1120000 | 0 | 0 | 0 | 0 | 1640000
Williamsport | 3 | Lycoming | 117887 | SR 220 over Lick Run | 220 | 254 | Bridge Replacement | PE | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 0 | 300000
Williamsport | 3 | Lycoming | 117887 | SR 220 over Lick Run | 220 | 254 | Bridge Replacement | FD | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
Williamsport | 3 | Lycoming | 117887 | SR 220 over Lick Run | 220 | 254 | Bridge Replacement | ROW | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
Williamsport | 3 | Lycoming | 117887 | SR 220 over Lick Run | 220 | 254 | Bridge Replacement | UTL | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Williamsport | 3 | Lycoming | 117887 | SR 220 over Lick Run | 220 | 254 | Bridge Replacement | CON | 185 | 2033-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 1600000
Williamsport | 3 | Lycoming | 117888 | Lycoming Off-System Epoxy Group 2 | 2022 | 014 | Bridge Preservation - State Funded | PE | 185 | 2030-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
Williamsport | 3 | Lycoming | 117923 | SR 1005 over Plunketts Creek | 1005 | 037 | Bridge Restoration | CON | BOF | 2023-12-14 | 2023-12-14 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Williamsport | 3 | Lycoming | 117924 | Lycoming Off System Epoxy Group 1 | 284 | 014 | Bridge Preservation - Federal | CON | BOF | 2024-06-13 | 2024-06-13 | 402000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402000
Williamsport | 3 | Lycoming | 118259 | LVRR RRX Loyal Sock Ave and Commerce Park Drv |  | 17R | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Williamsport | 3 | Lycoming | 118500 | Ramp Rollover Warning System | 8002 | 004 | Safety Improvement | CON | HSIP | 2025-01-16 | 2024-12-12 | 15360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15360
Williamsport | 3 | Lycoming | 118704 | SR 2016 over Lycoming Creek & Ramps | 2016 | 028 | Bridge Restoration | PE | 185 | 2027-09-01 |  | 360000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365000
Williamsport | 3 | Lycoming | 118704 | SR 2016 over Lycoming Creek & Ramps | 2016 | 028 | Bridge Restoration | FD | 185 | 2027-09-01 |  | 0 | 0 | 200000 | 100000 | 0 | 0 | 0 | 0 | 0 | 300000
Williamsport | 3 | Lycoming | 118704 | SR 2016 over Lycoming Creek & Ramps | 2016 | 028 | Bridge Restoration | CON | NHPP | 2027-09-01 |  | 0 | 0 | 0 | 1299000 | 1146000 | 1146000 | 0 | 0 | 0 | 3591000
Williamsport | 3 | Lycoming | 118704 | SR 2016 over Lycoming Creek & Ramps | 2016 | 028 | Bridge Restoration | CON | STP | 2027-09-01 |  | 0 | 0 | 0 | 0 | 0 | 1120000 | 0 | 0 | 0 | 1120000
Williamsport | 3 | Lycoming | 119250 | Northern RAR 2024 |  |  | General Maintenance | CON | 581 | 2024-03-14 | 2024-03-14 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Williamsport | 3 | Lycoming | 119519 | Market St to SR 2014 | 2016 | 029 | Highway Restoration | PE | 581 | 2028-01-01 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Williamsport | 3 | Lycoming | 119519 | Market St to SR 2014 | 2016 | 029 | Highway Restoration | FD | 581 | 2028-01-01 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Williamsport | 3 | Lycoming | 119519 | Market St to SR 2014 | 2016 | 029 | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 900000 | 900000 | 0 | 0 | 0 | 0 | 0 | 1800000
Williamsport | 3 | Lycoming | 119523 | I-180 to SR 2014 NB and SB | 15 | 261 | General Maintenance | CON | BRIP | 2025-01-16 | 2025-01-16 | 307842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307842
Williamsport | 3 | Lycoming | 119523 | I-180 to SR 2014 NB and SB | 15 | 261 | General Maintenance | CON | NHPP | 2025-01-16 | 2025-01-16 | 3258450 | 659856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3918306
Williamsport | 3 | Lycoming | 119523 | I-180 to SR 2014 NB and SB | 15 | 261 | General Maintenance | CON | STP | 2025-01-16 | 2025-01-16 | 921000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 921000
Williamsport | 3 | Lycoming | 119666 | Northern RAR 2025 |  |  | General Maintenance | PE | 581 | 2025-04-17 | 2025-04-17 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Williamsport | 3 | Lycoming | 119681 | Union Co to Sheetz | 15 | 264 | Highway Restoration | CON | NHPP | 2026-02-12 | 2026-02-12 | 0 | 826000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826000
Williamsport | 3 | Lycoming | 119770 | Bowman Field to Campbell Street | 2014 | 120 | Highway Restoration | PE | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0 | 170000
Williamsport | 3 | Lycoming | 119770 | Bowman Field to Campbell Street | 2014 | 120 | Highway Restoration | FD | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 119770 | Bowman Field to Campbell Street | 2014 | 120 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 2000000
Williamsport | 3 | Lycoming | 119773 | Oliver Ave to Arch St | 2014 | 121 | Highway Restoration | PE | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 119773 | Oliver Ave to Arch St | 2014 | 121 | Highway Restoration | FD | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 119773 | Oliver Ave to Arch St | 2014 | 121 | Highway Restoration | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670000 | 670000
Williamsport | 3 | Lycoming | 119773 | Oliver Ave to Arch St | 2014 | 121 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000
Williamsport | 3 | Lycoming | 119774 | Main Street to Susquehanna River | 15 | 267 | Highway Restoration | FD | 581 | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 500000
Williamsport | 3 | Lycoming | 119774 | Main Street to Susquehanna River | 15 | 267 | Highway Restoration | CON | NHPP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600000 | 2600000
Williamsport | 3 | Lycoming | 119774 | Main Street to Susquehanna River | 15 | 267 | Highway Restoration | CON | STP | 2033-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
Williamsport | 3 | Lycoming | 119776 | Via Bella to Third St | 2089 | 002 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000
Williamsport | 3 | Lycoming | 119791 | 3rd St to Four Mile Drive | 2039 | 010 | General Maintenance | FD | 581 | 2025-12-11 | 2025-12-11 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Williamsport | 3 | Lycoming | 119791 | 3rd St to Four Mile Drive | 2039 | 010 | General Maintenance | CON | PRTCT | 2025-12-11 | 2025-12-11 | 936011 | 1370489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2306500
Williamsport | 3 | Lycoming | 119791 | 3rd St to Four Mile Drive | 2039 | 010 | General Maintenance | CON | STP | 2025-12-11 | 2025-12-11 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Williamsport | 3 | Lycoming | 119921 | Near Woodward/Williamsport Line | 220 | 255 | Highway Restoration | PE | 581 | 2027-01-01 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Williamsport | 3 | Lycoming | 119921 | Near Woodward/Williamsport Line | 220 | 255 | Highway Restoration | FD | 581 | 2027-01-01 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Williamsport | 3 | Lycoming | 119921 | Near Woodward/Williamsport Line | 220 | 255 | Highway Restoration | CON | 581 | 2027-01-01 |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Williamsport | 3 | Lycoming | 120077 | Maynard Street Bridge Lighting Upgrades to LED | 2066 | 008 | Bridge Restoration | FD | CRP | 2026-01-15 | 2026-01-15 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 120077 | Maynard Street Bridge Lighting Upgrades to LED | 2066 | 008 | Bridge Restoration | CON | CRP | 2026-01-15 | 2026-01-15 | 150000 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000
Williamsport | 3 | Lycoming | 120574 | Embkmnt Repair Betw Highland Lake & Deer Lake Rds | 220 | 256 | Preventive Maintenance | CON | 581 | 2027-08-26 |  | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
Williamsport | 3 | Lycoming | 120717 | W. 4th St. to PA 287 | 220 | 257 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
Williamsport | 3 | Lycoming | 120721 | SR 284 to Tioga Co NB & SB | 15 | 268 | Highway Restoration | CON | 581 | 2028-01-01 |  | 0 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 1500000
Williamsport | 3 | Lycoming | 120766 | Valley Street Adjacent to Valley Inn | 3004 | 022 | Highway Restoration | ROW | 581 | 2026-02-12 | 2026-03-12 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 120766 | Valley Street Adjacent to Valley Inn | 3004 | 022 | Highway Restoration | CON | 581 | 2026-02-12 | 2026-03-12 | 565000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 565000
Williamsport | 3 | Lycoming | 120852 | Lane Departures | 54 | 124 | Safety Improvement | PE | HSIP | 2027-01-01 |  | 377140 | 253799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630939
Williamsport | 3 | Lycoming | 120852 | Lane Departures | 54 | 124 | Safety Improvement | FD | HSIP | 2027-01-01 |  | 0 | 420619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420619
Williamsport | 3 | Lycoming | 120852 | Lane Departures | 54 | 124 | Safety Improvement | CON | HSIP | 2027-01-01 |  | 0 | 389582 | 1064000 | 1064000 | 111288 | 0 | 0 | 0 | 0 | 2628870
Williamsport | 3 | Lycoming | 120916 | Little Pine Bottom to Camp Blue Jay Dr | 44 | 102 | Highway Restoration | PE | 581 | 2028-01-01 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 120956 | PA 54 to Brick Church Rd | 405 | 113 | Highway Restoration | CON | 581 | 2035-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
Williamsport | 3 | Lycoming | 121165 | Spur to Lyco Mall Dr | 2014 | 122 | Highway Restoration | PE | 581 | 2028-01-01 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Williamsport | 3 | Lycoming | 121166 | Lycoming Mall Rd to John Brady Dr | 2014 | 123 | Highway Restoration | PE | 581 | 2028-01-01 |  | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000
Williamsport | 3 | Lycoming | 121318 | Major Guide Signs 1 | 180 | 154 | Safety Improvement | CON | 581 | 2027-04-08 |  | 0 | 0 | 235000 | 0 | 0 | 0 | 0 | 0 | 0 | 235000
Williamsport | 3 | Lycoming | 121319 | Major Guide Signs 2 | 220 | 263 | Safety Improvement | CON | 581 | 2027-04-08 |  | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 160000
Williamsport | 3 | Lycoming | 121503 | Market St & Maynard St | 180 | 155 | Congestion Reduction | PE | CRP | 2027-01-01 |  | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
Williamsport | 3 | Lycoming | 121503 | Market St & Maynard St | 180 | 155 | Congestion Reduction | FD | CRPU | 2027-01-01 |  | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
Williamsport | 3 | Lycoming | 121503 | Market St & Maynard St | 180 | 155 | Congestion Reduction | CON | CRP | 2027-01-01 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 121503 | Market St & Maynard St | 180 | 155 | Congestion Reduction | CON | CRPU | 2027-01-01 |  | 0 | 0 | 152000 | 0 | 0 | 0 | 0 | 0 | 0 | 152000
Williamsport | 3 | Lycoming | 121677 | Faxon to Maynard Expansion Dams | 180 | 157 | Bridge Restoration | CON | NHPP | 2024-09-12 | 2024-09-12 | 18550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18550
Williamsport | 3 | Lycoming | 122111 | Hazel Alley Improvements |  | MTF | MultiModal | FD | 411 | 2026-01-01 |  | 0 | 71000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71000
Williamsport | 3 | Lycoming | 122111 | Hazel Alley Improvements |  | MTF | MultiModal | CON | 411 | 2026-01-01 |  | 0 | 639691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 639691
Williamsport | 3 | Lycoming | 122112 | Carpenter Street over Glade Run | 7406 | MML | MultiModal | PE | 411 |  |  | 17400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17400
Williamsport | 3 | Lycoming | 122112 | Carpenter Street over Glade Run | 7406 | MML | MultiModal | PE | OTH |  |  | 21100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21100
Williamsport | 3 | Lycoming | 122112 | Carpenter Street over Glade Run | 7406 | MML | MultiModal | CON | 411 |  |  | 104400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104400
Williamsport | 3 | Lycoming | 122112 | Carpenter Street over Glade Run | 7406 | MML | MultiModal | CON | OTH |  |  | 31100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31100
Williamsport | 3 | Lycoming | 122292 | North of Steam Valley to PA 284 | 15 | 282 | Highway Restoration | PE | 581 | 2029-01-04 |  | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000
Williamsport | 3 | Lycoming | 122484 | Lycoming Mall Interchange | 180 | 160 | Congestion Reduction | PE | CRP | 2027-10-01 |  | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000
Williamsport | 3 | Lycoming | 122484 | Lycoming Mall Interchange | 180 | 160 | Congestion Reduction | PE | CRPU | 2027-10-01 |  | 0 | 152000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152000
Williamsport | 3 | Lycoming | 122484 | Lycoming Mall Interchange | 180 | 160 | Congestion Reduction | FD | CRP | 2027-10-01 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 122484 | Lycoming Mall Interchange | 180 | 160 | Congestion Reduction | CON | CRP | 2027-10-01 |  | 0 | 0 | 250000 | 98000 | 0 | 0 | 0 | 0 | 0 | 348000
Williamsport | 3 | Lycoming | 122484 | Lycoming Mall Interchange | 180 | 160 | Congestion Reduction | CON | CRPU | 2027-10-01 |  | 0 | 0 | 0 | 152000 | 0 | 0 | 0 | 0 | 0 | 152000
Williamsport | 3 | Lycoming | 122533 | Rt 14 Marine Corp League Erosion Emergency | 14 | 138 | Highway Restoration | PE | 581 |  |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Williamsport | 3 | Lycoming | 122535 | SR 2001 (Elimsport Rd) TO RAMP B RD | 15 | 285 | Highway Restoration | PE | 581 | 2028-01-01 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 122539 | Rt 14 Marine Corp League Erosion Permanent | 14 | 139 | Highway Restoration | STUDY | 581 | 2027-01-01 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 122848 | SR 220 over Queneshukney Run | 220 | 268 | Bridge Restoration | PE | 185 | 2026-01-15 | 2026-01-15 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 122848 | SR 220 over Queneshukney Run | 220 | 268 | Bridge Restoration | FD | 185 | 2026-01-15 | 2026-01-15 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 122848 | SR 220 over Queneshukney Run | 220 | 268 | Bridge Restoration | CON | 185 | 2026-01-15 | 2026-01-15 | 0 | 757000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757000
Williamsport | 3 | Lycoming | 122996 | SR 220 over Lick Run | 220 | 270 | Bridge Restoration | STUDY | 185 |  |  | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Williamsport | 3 | Lycoming | 123012 | WATS T&E Reserve D3 |  |  | Reserve Line Item | STUDY | 581 |  |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Williamsport | 3 | Lycoming | 123040 | SR 287 to Cogan House Township | 4006 | 021 | Highway Restoration | CON | 581 | 2025-07-01 |  | 310000 | 27522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337522
Williamsport | 3 | Lycoming | 123043 | SR 118 to SR 42 | 239 | 028 | Highway Restoration | CON | 581 | 2025-07-01 |  | 610000 | 119129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729129
Williamsport | 3 | Lycoming | 123097 | I-180 between Twin Run and Lycoming Mall Rd | 180 | 167 | Highway Restoration | PE | 581 |  |  | 3058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3058
Williamsport | 3 | Lycoming | 123097 | I-180 between Twin Run and Lycoming Mall Rd | 180 | 167 | Highway Restoration | CON | 581 |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Williamsport | 3 | Lycoming | 123203 | Northern RAR 2026 |  |  | General Maintenance | PE | 581 | 2026-04-09 |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
Williamsport | 3 | Lycoming | 123206 | I-180 East and West over Loyalsock Creek | 180 | 169 | Bridge Preservation - Federal | PE | 185 | 2026-05-07 |  | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000
Williamsport | 3 | Lycoming | 123206 | I-180 East and West over Loyalsock Creek | 180 | 169 | Bridge Preservation - Federal | FD | BRIP | 2026-05-07 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Williamsport | 3 | Lycoming | 123206 | I-180 East and West over Loyalsock Creek | 180 | 169 | Bridge Preservation - Federal | CON | BRIP | 2026-05-07 |  | 0 | 1775000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1775000
Williamsport | 3 | Lycoming | 123206 | I-180 East and West over Loyalsock Creek | 180 | 169 | Bridge Preservation - Federal | CON | NHPP | 2026-05-07 |  | 0 | 320700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320700
Williamsport | 3 | Lycoming | 123477 | SR 442 to SR 2019 | 2015 | 008 | Highway Restoration | CON | 581 |  |  | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
York | 8 | York | 20652 | Camp Betty Washington/Haines Road Improvement | 2005 | 004 | Highway Reconstruction | FD | STP | 2027-06-24 |  | 0 | 200540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200540
York | 8 | York | 20652 | Camp Betty Washington/Haines Road Improvement | 2005 | 004 | Highway Reconstruction | FD | STU | 2027-06-24 |  | 0 | 485702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485702
York | 8 | York | 20652 | Camp Betty Washington/Haines Road Improvement | 2005 | 004 | Highway Reconstruction | CON | STP | 2027-06-24 |  | 0 | 0 | 6304295 | 0 | 0 | 0 | 0 | 0 | 0 | 6304295
York | 8 | York | 20652 | Camp Betty Washington/Haines Road Improvement | 2005 | 004 | Highway Reconstruction | CON | STU | 2027-06-24 |  | 0 | 0 | 3521405 | 637000 | 0 | 0 | 0 | 0 | 0 | 4158405
York | 8 | York | 20972 | Porters Road Bridge 1 | 3047 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
York | 8 | York | 20976 | Brownton Road ov Pine Run | 2056 | 003 | Bridge Replacement | PE | 185 |  |  | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
York | 8 | York | 20976 | Brownton Road ov Pine Run | 2056 | 003 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
York | 8 | York | 20976 | Brownton Road ov Pine Run | 2056 | 003 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 572613 | 300000 | 0 | 0 | 0 | 0 | 872613
York | 8 | York | 21060 | Jacobs Mill Road over Paradise Run | 7223 | BRG | Bridge Replacement | PE | BOF |  |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
York | 8 | York | 21060 | Jacobs Mill Road over Paradise Run | 7223 | BRG | Bridge Replacement | PE | BRIP |  |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
York | 8 | York | 21060 | Jacobs Mill Road over Paradise Run | 7223 | BRG | Bridge Replacement | FD | BRIP |  |  | 0 | 0 | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 175000
York | 8 | York | 21060 | Jacobs Mill Road over Paradise Run | 7223 | BRG | Bridge Replacement | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 860912 | 0 | 0 | 0 | 0 | 860912
York | 8 | York | 21076 | Marburg Lake Bridge | 216 | 025 | Bridge Preservation - Federal | CON | STP | 2026-02-12 | 2026-02-12 | 500000 | 164951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 664951
York | 8 | York | 21149 | Muddy Creek Forks Rd ov N Brch Muddy Ck | 2044 | 003 | Bridge Restoration | PE | BOF |  |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 21149 | Muddy Creek Forks Rd ov N Brch Muddy Ck | 2044 | 003 | Bridge Restoration | FD | BRIP |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
York | 8 | York | 21149 | Muddy Creek Forks Rd ov N Brch Muddy Ck | 2044 | 003 | Bridge Restoration | ROW | BOF |  |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
York | 8 | York | 21149 | Muddy Creek Forks Rd ov N Brch Muddy Ck | 2044 | 003 | Bridge Restoration | UTL | BOF |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
York | 8 | York | 21149 | Muddy Creek Forks Rd ov N Brch Muddy Ck | 2044 | 003 | Bridge Restoration | CON | BOF |  |  | 0 | 0 | 0 | 412319 | 252440 | 735241 | 0 | 0 | 0 | 1400000
York | 8 | York | 61326 | US 30/Big Mount Rd Safety Improvements | 30 | 040 | Safety Improvement | PE | HSIP | 2027-04-29 |  | 55674 | 188710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244384
York | 8 | York | 61326 | US 30/Big Mount Rd Safety Improvements | 30 | 040 | Safety Improvement | PE | NHPP | 2027-04-29 |  | 0 | 124000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124000
York | 8 | York | 61326 | US 30/Big Mount Rd Safety Improvements | 30 | 040 | Safety Improvement | FD | HSIP | 2027-04-29 |  | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
York | 8 | York | 61326 | US 30/Big Mount Rd Safety Improvements | 30 | 040 | Safety Improvement | ROW | HSIP | 2027-04-29 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
York | 8 | York | 61326 | US 30/Big Mount Rd Safety Improvements | 30 | 040 | Safety Improvement | UTL | HSIP | 2027-04-29 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
York | 8 | York | 61326 | US 30/Big Mount Rd Safety Improvements | 30 | 040 | Safety Improvement | CON | CAQ | 2027-04-29 |  | 0 | 0 | 0 | 1303539 | 0 | 0 | 0 | 0 | 0 | 1303539
York | 8 | York | 61326 | US 30/Big Mount Rd Safety Improvements | 30 | 040 | Safety Improvement | CON | HSIP | 2027-04-29 |  | 0 | 0 | 953136 | 639000 | 1259807 | 324518 | 0 | 0 | 0 | 3176461
York | 8 | York | 63121 | Blue Ball Road Bridge | 2038 | 003 | Bridge Replacement | CON | BRIP | 2024-10-24 | 2024-10-24 | 240758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240758
York | 8 | York | 63121 | Blue Ball Road Bridge | 2038 | 003 | Bridge Replacement | CON | STP | 2024-10-24 | 2024-10-24 | 25968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25968
York | 8 | York | 73962 | Sherman St Br Trib of Cod | 24 | 000 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 73966 | Canal Rd Br over Fox Run | 921 | 012 | Bridge Restoration | PE | BRIP |  |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 73966 | Canal Rd Br over Fox Run | 921 | 012 | Bridge Restoration | FD | BRIP |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
York | 8 | York | 73966 | Canal Rd Br over Fox Run | 921 | 012 | Bridge Restoration | ROW | BRIP |  |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
York | 8 | York | 73966 | Canal Rd Br over Fox Run | 921 | 012 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 260318 | 290744 | 848938 | 0 | 0 | 0 | 1400000
York | 8 | York | 78844 | York Road Bridge | 116 | 049 | Bridge Preservation - Federal | CON | STP | 2023-05-11 | 2023-05-11 | 43589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43589
York | 8 | York | 78846 | SR 177 Over Beaver Creek | 177 | 007 | Bridge Restoration | CON | STP | 2024-02-29 | 2024-02-29 | 0 | 9286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9286
York | 8 | York | 78884 | Emig Road Bridge | 1012 | 011 | Bridge Restoration | PE | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000
York | 8 | York | 78884 | Emig Road Bridge | 1012 | 011 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1926000 | 1926000
York | 8 | York | 78888 | Wago Road Bridge | 1019 | 010 | Bridge Restoration | CON | BRIP | 2024-04-18 | 2024-04-18 | 83539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83539
York | 8 | York | 78888 | Wago Road Bridge | 1019 | 010 | Bridge Restoration | CON | 581 | 2024-04-18 | 2024-04-18 | 20885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20885
York | 8 | York | 78901 | Old Forge Road Bridge | 2048 | 001 | Bridge Replacement | FD | 185 | 2026-02-26 | 2026-02-26 | 0 | 10967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10967
York | 8 | York | 78901 | Old Forge Road Bridge | 2048 | 001 | Bridge Replacement | UTL | 185 | 2026-02-26 | 2026-02-26 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
York | 8 | York | 78901 | Old Forge Road Bridge | 2048 | 001 | Bridge Replacement | CON | 185 | 2026-02-26 | 2026-02-26 | 0 | 1276396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1276396
York | 8 | York | 81039 | Good Road over Toms Run | 2071 | 001 | Bridge Restoration | UTL | STP | 2025-09-25 | 2025-09-25 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
York | 8 | York | 81039 | Good Road over Toms Run | 2071 | 001 | Bridge Restoration | CON | BOF | 2025-09-25 | 2025-09-25 | 1598641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1598641
York | 8 | York | 81040 | Front Street Bridge | 624 | 011 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325000 | 325000
York | 8 | York | 81069 | SR 24 Br PM over N.S. RR | 24 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
York | 8 | York | 82376 | SRTP Rideshare Program |  | RSP | Reserve Line Item | PE | CAQ |  |  | 0 | 314225 | 310855 | 313963 | 309000 | 0 | 0 | 0 | 0 | 1248043
York | 8 | York | 87519 | Baltimore Pike ov Tributary Bermudian Cr | 194 | 026 | Bridge Replacement | FD | 185 | 2027-02-11 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 87519 | Baltimore Pike ov Tributary Bermudian Cr | 194 | 026 | Bridge Replacement | ROW | 581 | 2027-02-11 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
York | 8 | York | 87519 | Baltimore Pike ov Tributary Bermudian Cr | 194 | 026 | Bridge Replacement | UTL | 581 | 2027-02-11 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
York | 8 | York | 87519 | Baltimore Pike ov Tributary Bermudian Cr | 194 | 026 | Bridge Replacement | CON | 185 | 2027-02-11 |  | 0 | 0 | 757884 | 456168 | 0 | 0 | 0 | 0 | 0 | 1214052
York | 8 | York | 87549 | S George St ov Trib to SB of Codorus Ck | 3001 | 061 | Bridge Restoration | PE | 581 | 2027-08-12 |  | 225901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225901
York | 8 | York | 87549 | S George St ov Trib to SB of Codorus Ck | 3001 | 061 | Bridge Restoration | FD | 185 | 2027-08-12 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
York | 8 | York | 87549 | S George St ov Trib to SB of Codorus Ck | 3001 | 061 | Bridge Restoration | ROW | 185 | 2027-08-12 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
York | 8 | York | 87549 | S George St ov Trib to SB of Codorus Ck | 3001 | 061 | Bridge Restoration | UTL | 185 | 2027-08-12 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
York | 8 | York | 87549 | S George St ov Trib to SB of Codorus Ck | 3001 | 061 | Bridge Restoration | CON | 185 | 2027-08-12 |  | 0 | 0 | 608275 | 582570 | 0 | 0 | 0 | 0 | 0 | 1190845
York | 8 | York | 87549 | S George St ov Trib to SB of Codorus Ck | 3001 | 061 | Bridge Restoration | CON | 581 | 2027-08-12 |  | 0 | 0 | 201403 | 237752 | 50000 | 0 | 0 | 0 | 0 | 489155
York | 8 | York | 87552 | MT Olivet Rd Bridge | 2053 | 001 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98000 | 98000
York | 8 | York | 87598 | Trib Bermudian Cr Br 2 | 194 | 022 | Bridge Replacement | CON | 185 | 2024-10-10 | 2024-10-24 | 20764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20764
York | 8 | York | 87599 | Clearview Drive Bridge | 3006 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 87689 | Bull Road ov Little Conewago Ck | 4001 | 019 | Bridge Replacement | FD | 185 | 2027-02-11 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
York | 8 | York | 87689 | Bull Road ov Little Conewago Ck | 4001 | 019 | Bridge Replacement | FD | 581 | 2027-02-11 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
York | 8 | York | 87689 | Bull Road ov Little Conewago Ck | 4001 | 019 | Bridge Replacement | ROW | BRIP | 2027-02-11 |  | 42507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42507
York | 8 | York | 87689 | Bull Road ov Little Conewago Ck | 4001 | 019 | Bridge Replacement | ROW | STP | 2027-02-11 |  | 32493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32493
York | 8 | York | 87689 | Bull Road ov Little Conewago Ck | 4001 | 019 | Bridge Replacement | UTL | BRIP | 2027-02-11 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
York | 8 | York | 87689 | Bull Road ov Little Conewago Ck | 4001 | 019 | Bridge Replacement | CON | BRIP | 2027-02-11 |  | 0 | 0 | 517954 | 2242046 | 0 | 0 | 0 | 0 | 0 | 2760000
York | 8 | York | 87689 | Bull Road ov Little Conewago Ck | 4001 | 019 | Bridge Replacement | CON | 581 | 2027-02-11 |  | 0 | 0 | 690000 | 0 | 0 | 0 | 0 | 0 | 0 | 690000
York | 8 | York | 87696 | South Br Codorus Creek | 616 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 87697 | Springwood Road Bridge ovr Stony Crk | 2002 | 022 | Bridge Replacement | FD | 185 | 2026-08-13 |  | 0 | 35154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35154
York | 8 | York | 87697 | Springwood Road Bridge ovr Stony Crk | 2002 | 022 | Bridge Replacement | CON | PRTCT | 2026-08-13 |  | 0 | 1043232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1043232
York | 8 | York | 87946 | Bridge Reserve |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 527373 | 0 | 0 | 0 | 100000 | 1078638 | 3499000 | 13996000 | 19201011
York | 8 | York | 87946 | Bridge Reserve |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 0 | 0 | 312134 | 0 | 245916 | 2277857 | 1537375 | 12269781 | 16643063
York | 8 | York | 87946 | Bridge Reserve |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 375830 | 0 | 259655 | 126573 | 132418 | 175000 | 2679840 | 6938941 | 10688257
York | 8 | York | 87952 | Highway Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 499525 | 0 | 0 | 0 | 0 | 0 | 14396000 | 14895525
York | 8 | York | 87952 | Highway Reserve |  |  | Reserve Line Item | CON | STP |  |  | 0 | 128100 | 72413 | 2500000 | 4000000 | 0 | 0 | 381076 | 14417000 | 21498589
York | 8 | York | 87952 | Highway Reserve |  |  | Reserve Line Item | CON | 581 |  |  | 416 | 0 | 3661367 | 1327865 | 172505 | 0 | 0 | 1126515 | 3630707 | 9919375
York | 8 | York | 87957 | Congestion Mitigation Implementation |  |  | Reserve Line Item | CON | CAQ |  |  | 0 | 84026 | 0 | 0 | 389054 | 4657000 | 4657000 | 4657000 | 18628000 | 33072080
York | 8 | York | 87958 | Delivery/Consult Assist |  |  | Reserve Line Item | PE | 185 |  |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
York | 8 | York | 87958 | Delivery/Consult Assist |  |  | Reserve Line Item | PE | 581 |  |  | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 5000000
York | 8 | York | 87958 | Delivery/Consult Assist |  |  | Reserve Line Item | CON | 581 |  |  | 800000 | 800000 | 800000 | 800000 | 800000 | 0 | 0 | 0 | 0 | 4000000
York | 8 | York | 87960 | TAP Line Item |  |  | Reserve Line Item | CON | TAU |  |  | 65000 | 0 | 156160 | 523000 | 523000 | 523000 | 523000 | 523000 | 2092000 | 4928160
York | 8 | York | 88056 | York STU Line Item |  |  | Reserve Line Item | CON | STU |  |  | 14724 | 202436 | 0 | 315647 | 1922219 | 0 | 0 | 799552 | 9368058 | 12622636
York | 8 | York | 88951 | US30: PA74 to N George St | 30 | 095 | Highway Restoration | CON | STU | 2024-03-28 | 2024-03-28 | 500000 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300000
York | 8 | York | 88951 | US30: PA74 to N George St | 30 | 095 | Highway Restoration | CON | 581 | 2024-03-28 | 2024-03-28 | 0 | 1050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000
York | 8 | York | 90631 | Kopp Road ov Bunches Ck | 3092 | 003 | Bridge Preservation - Federal | FD | 185 | 2027-01-21 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
York | 8 | York | 90631 | Kopp Road ov Bunches Ck | 3092 | 003 | Bridge Preservation - Federal | ROW | 185 | 2027-01-21 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
York | 8 | York | 90631 | Kopp Road ov Bunches Ck | 3092 | 003 | Bridge Preservation - Federal | CON | 185 | 2027-01-21 |  | 0 | 0 | 628318 | 0 | 0 | 0 | 0 | 0 | 0 | 628318
York | 8 | York | 90930 | Church Street | 3008 | 0 | Highway Restoration | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2139000 | 2139000
York | 8 | York | 90948 | Creek Road Resurface | 4012 | 004 | Highway Restoration | CON | 581 | 2024-09-26 | 2024-09-26 | 56987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56987
York | 8 | York | 91031 | Canal Road Ext Bridge | 921 | 013 | Bridge Replacement | CON | 185 |  |  | 66228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66228
York | 8 | York | 91031 | Canal Road Ext Bridge | 921 | 013 | Bridge Replacement | CON | 581 |  |  | 2896971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2896971
York | 8 | York | 91354 | PA 216 Bridge | 216 | 021 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241000 | 241000
York | 8 | York | 91368 | Iron Ridge Road Bridge | 3047 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 91369 | Pigeon Hill Road Bridge | 3047 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 91372 | Tyler Run Road Bridge | 3056 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 91373 | Westminister Ave Bridge 2 | 3073 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 92562 | Crossroads Ave Bridge | 2079 | 005 | Bridge Replacement | UTL | STP | 2022-05-12 | 2022-05-12 | 18397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18397
York | 8 | York | 92920 | US 15 Safety Improvements - York | 15 | 037 | Safety Improvement | CON | STP | 2020-06-18 | 2020-06-18 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
York | 8 | York | 92920 | US 15 Safety Improvements - York | 15 | 037 | Safety Improvement | CON | 581 | 2020-06-18 | 2020-06-18 | 31293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31293
York | 8 | York | 92923 | Blue-Gray Highway Reconstruction | 15 | 044 | Bridge Preservation - Federal | FD | NHPP | 2028-09-14 |  | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000
York | 8 | York | 92923 | Blue-Gray Highway Reconstruction | 15 | 044 | Bridge Preservation - Federal | FD | 581 | 2028-09-14 |  | 0 | 3050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3050000
York | 8 | York | 92923 | Blue-Gray Highway Reconstruction | 15 | 044 | Bridge Preservation - Federal | ROW | 581 | 2028-09-14 |  | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
York | 8 | York | 92923 | Blue-Gray Highway Reconstruction | 15 | 044 | Bridge Preservation - Federal | UTL | 581 | 2028-09-14 |  | 0 | 1943408 | 2056592 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
York | 8 | York | 92923 | Blue-Gray Highway Reconstruction | 15 | 044 | Bridge Preservation - Federal | CON | BRIP | 2028-09-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1651087 | 0 | 2922219 | 4573306
York | 8 | York | 92923 | Blue-Gray Highway Reconstruction | 15 | 044 | Bridge Preservation - Federal | CON | NHPP | 2028-09-14 |  | 0 | 0 | 4036475 | 4099000 | 4099000 | 4099000 | 4099000 | 5710320 | 0 | 26142795
York | 8 | York | 92923 | Blue-Gray Highway Reconstruction | 15 | 044 | Bridge Preservation - Federal | CON | STP | 2028-09-14 |  | 0 | 0 | 0 | 2435000 | 2435000 | 6435000 | 6435000 | 4442604 | 7000000 | 29182604
York | 8 | York | 92923 | Blue-Gray Highway Reconstruction | 15 | 044 | Bridge Preservation - Federal | CON | STU | 2028-09-14 |  | 0 | 0 | 268259 | 3702664 | 3679781 | 5602000 | 5602000 | 4802448 | 4000000 | 27657152
York | 8 | York | 92923 | Blue-Gray Highway Reconstruction | 15 | 044 | Bridge Preservation - Federal | CON | 581 | 2028-09-14 |  | 0 | 0 | 3175322 | 4334244 | 9234000 | 4034000 | 4034000 | 3738843 | 0 | 28550409
York | 8 | York | 94950 | US 15 Resurfacing - York | 15 | 034 | Highway Restoration | CON | STP | 2020-06-18 | 2020-06-18 | 218776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218776
York | 8 | York | 95325 | Rabbittransit Bus Replacment |  | PT | Public Transit | CON | CAQ |  |  | 2130000 | 579000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2709000
York | 8 | York | 96233 | Holtwood Road Resurface | 372 | 0 | 409 Expanded Maintenance | CON | 409 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000
York | 8 | York | 99941 | Lincoln Highway Resf 3 | 462 | 0 | Highway Restoration | CON | STU |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4815000 | 4815000
York | 8 | York | 99944 | Jefferson Road Resf | 516 | 0 | Highway Restoration | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2408000 | 2408000
York | 8 | York | 100038 | US 30 Trib Beaver Cr 2 | 30 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100038 | US 30 Trib Beaver Cr 2 | 30 | 0 | Bridge Preservation - Federal | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1043059 | 1043059
York | 8 | York | 100043 | PA 216 Tib Codorus Cr 3 | 216 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100075 | Conewago Cr Rd Brdg 1 | 1004 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100077 | Locust Point Road Bridge | 1021 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100088 | Kilgore Road Bridge 1 | 2047 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100091 | Round Hill Bridge 1 | 2067 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100094 | Round Hill Bridge 2 | 2067 | 001 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000
York | 8 | York | 100131 | Richland Avenue Bridge | 3054 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100133 | Glenville Road Bridge 1 | 3060 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100137 | Bermudian Road Bridge 1 | 4006 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100139 | Greenbriar Road Bridge 1 | 4011 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100146 | Campground Road Bridge | 4045 | 002 | Bridge Replacement | ROW | 581 | 2025-12-04 | 2025-12-04 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
York | 8 | York | 100146 | Campground Road Bridge | 4045 | 002 | Bridge Replacement | UTL | 581 | 2025-12-04 | 2025-12-04 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
York | 8 | York | 100146 | Campground Road Bridge | 4045 | 002 | Bridge Replacement | CON | 185 | 2025-12-04 | 2025-12-04 | 783227 | 455244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1238471
York | 8 | York | 100146 | Campground Road Bridge | 4045 | 002 | Bridge Replacement | CON | 581 | 2025-12-04 | 2025-12-04 | 194162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194162
York | 8 | York | 100151 | Carlisle Road Bridge | 74 | 069 | Bridge Replacement | CON | BRIP | 2024-09-12 | 2024-09-12 | 50231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50231
York | 8 | York | 100153 | Blooming Grove Road Brdg | 216 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100157 | Main Street Bridge | 616 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
York | 8 | York | 100159 | Codorus Furnace Road Brdg | 1008 | 006 | Bridge Preservation - Federal | PE | BRIP |  |  | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
York | 8 | York | 100159 | Codorus Furnace Road Brdg | 1008 | 006 | Bridge Preservation - Federal | FD | BRIP |  |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
York | 8 | York | 100159 | Codorus Furnace Road Brdg | 1008 | 006 | Bridge Preservation - Federal | UTL | BRIP |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
York | 8 | York | 100159 | Codorus Furnace Road Brdg | 1008 | 006 | Bridge Preservation - Federal | CON | BRIP |  |  | 0 | 0 | 0 | 260318 | 290744 | 48938 | 0 | 0 | 0 | 600000
York | 8 | York | 100161 | Paper Mill Rd ov NB of Muddy Ck | 2024 | 007 | Bridge Replacement | PE | BOF |  |  | 275000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
York | 8 | York | 100161 | Paper Mill Rd ov NB of Muddy Ck | 2024 | 007 | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 100161 | Paper Mill Rd ov NB of Muddy Ck | 2024 | 007 | Bridge Replacement | ROW | BOF |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
York | 8 | York | 100161 | Paper Mill Rd ov NB of Muddy Ck | 2024 | 007 | Bridge Replacement | UTL | BOF |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
York | 8 | York | 100161 | Paper Mill Rd ov NB of Muddy Ck | 2024 | 007 | Bridge Replacement | CON | BOF |  |  | 0 | 0 | 0 | 412319 | 252439 | 1147244 | 1000000 | 0 | 0 | 2812002
York | 8 | York | 100161 | Paper Mill Rd ov NB of Muddy Ck | 2024 | 007 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 502416 | 2685582 | 0 | 0 | 0 | 3187998
York | 8 | York | 100164 | Canadochly Road Bridge | 2027 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100168 | Cabin Creek Road Bridge | 2033 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100172 | Frosty Hill Road Bridge | 2040 | 0 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100177 | Lewisberry Road Bridge 1 | 114 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100179 | York Street Bridge 2 | 116 | 050 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
York | 8 | York | 100180 | East Prospect Road Bridge | 124 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100182 | Baltimore Pike Bridge 1 | 194 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100187 | East Berlin Road Bridge 1 | 234 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100194 | Market St ov Trib to Kruetz Ck | 462 | 059 | Bridge Replacement | PE | 185 |  |  | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
York | 8 | York | 100194 | Market St ov Trib to Kruetz Ck | 462 | 059 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
York | 8 | York | 100194 | Market St ov Trib to Kruetz Ck | 462 | 059 | Bridge Replacement | CON | 185 |  |  | 0 | 0 | 0 | 0 | 1411280 | 0 | 0 | 0 | 0 | 1411280
York | 8 | York | 100196 | Lincoln Highway ov Kruetz Ck | 462 | 060 | Bridge Restoration | PE | 185 |  |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
York | 8 | York | 100196 | Lincoln Highway ov Kruetz Ck | 462 | 060 | Bridge Restoration | FD | 185 |  |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
York | 8 | York | 100196 | Lincoln Highway ov Kruetz Ck | 462 | 060 | Bridge Restoration | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 931181 | 1103873 | 0 | 2035054
York | 8 | York | 100197 | PA 462/Trib to Kreutz Cr | 462 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100200 | PA 462/Trib to Kreutz Cr4 | 462 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100201 | Craley Road Bridge 1 | 624 | 0 | Bridge Restoration | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100203 | York Road ovr Dogwood Run | 74 | 0 | Bridge Preservation - Federal | PE | 185 | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
York | 8 | York | 100203 | York Road ovr Dogwood Run | 74 | 0 | Bridge Preservation - Federal | CON | STU | 2034-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1684942 | 1684942
York | 8 | York | 100205 | Old York Road Bridge 1 | 1003 | 0 | Bridge Replacement | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000
York | 8 | York | 100207 | George St over Tylers Run | 3001 | 056 | Bridge Replacement | CON | BRIP | 2029-01-01 |  | 0 | 0 | 0 | 0 | 390744 | 1629210 | 0 | 0 | 0 | 2019954
York | 8 | York | 100209 | Loucks Mill Road Bridge 2 | 3029 | 0 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000
York | 8 | York | 100215 | Roosevelt Ave ov Willis Run | 4001 | 024 | Bridge Preservation - Federal | PE | 185 |  |  | 0 | 0 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 230000
York | 8 | York | 100215 | Roosevelt Ave ov Willis Run | 4001 | 024 | Bridge Preservation - Federal | FD | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 125000
York | 8 | York | 100215 | Roosevelt Ave ov Willis Run | 4001 | 024 | Bridge Preservation - Federal | CON | 185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2835819 | 156287 | 0 | 2992106
York | 8 | York | 100227 | Lincoln Highway Rsf 2 | 30 | 168 | Highway Restoration | PE | STU | 2030-01-01 |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
York | 8 | York | 100227 | Lincoln Highway Rsf 2 | 30 | 168 | Highway Restoration | FD | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
York | 8 | York | 100227 | Lincoln Highway Rsf 2 | 30 | 168 | Highway Restoration | CON | 581 | 2030-01-01 |  | 0 | 0 | 0 | 0 | 0 | 3304540 | 0 | 0 | 0 | 3304540
York | 8 | York | 100232 | Green Valley Intersection | 616 | 0 | Safety Improvement | PE | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
York | 8 | York | 100232 | Green Valley Intersection | 616 | 0 | Safety Improvement | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1926000 | 1926000
York | 8 | York | 102398 | Implementation of I-83 Study Reserve |  |  | Reserve Line Item | CON | STU |  |  | 0 | 2611142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2611142
York | 8 | York | 106542 | HSIP Line Item |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 0 | 405769 | 0 | 386518 | 2597482 | 2922000 | 2922000 | 11662985 | 20896754
York | 8 | York | 106552 | Furnace Road Bridge | 7216 | BRG | Bridge Replacement | FD | BRIP | 2026-11-05 |  | 37089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37089
York | 8 | York | 106552 | Furnace Road Bridge | 7216 | BRG | Bridge Replacement | FD | 183 | 2026-11-05 |  | 6955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6955
York | 8 | York | 106552 | Furnace Road Bridge | 7216 | BRG | Bridge Replacement | FD | LOC | 2026-11-05 |  | 2319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2319
York | 8 | York | 106552 | Furnace Road Bridge | 7216 | BRG | Bridge Replacement | ROW | BOF | 2026-11-05 |  | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000
York | 8 | York | 106552 | Furnace Road Bridge | 7216 | BRG | Bridge Replacement | ROW | 183 | 2026-11-05 |  | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000
York | 8 | York | 106552 | Furnace Road Bridge | 7216 | BRG | Bridge Replacement | ROW | LOC | 2026-11-05 |  | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
York | 8 | York | 106552 | Furnace Road Bridge | 7216 | BRG | Bridge Replacement | UTL | BOF | 2026-11-05 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
York | 8 | York | 106552 | Furnace Road Bridge | 7216 | BRG | Bridge Replacement | UTL | 183 | 2026-11-05 |  | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
York | 8 | York | 106552 | Furnace Road Bridge | 7216 | BRG | Bridge Replacement | UTL | LOC | 2026-11-05 |  | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
York | 8 | York | 106552 | Furnace Road Bridge | 7216 | BRG | Bridge Replacement | CON | BRIP | 2026-11-05 |  | 0 | 0 | 1030987 | 0 | 0 | 0 | 0 | 0 | 0 | 1030987
York | 8 | York | 106552 | Furnace Road Bridge | 7216 | BRG | Bridge Replacement | CON | 183 | 2026-11-05 |  | 0 | 0 | 193310 | 0 | 0 | 0 | 0 | 0 | 0 | 193310
York | 8 | York | 106553 | Detters Mill Road ov Tributary to Conewago Ck | 7229 | BRG | Bridge Replacement | PE | BRIP | 2028-08-24 |  | 342000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342000
York | 8 | York | 106553 | Detters Mill Road ov Tributary to Conewago Ck | 7229 | BRG | Bridge Replacement | CON | BOF | 2028-08-24 |  | 0 | 0 | 0 | 675362 | 0 | 0 | 0 | 0 | 0 | 675362
York | 8 | York | 106553 | Detters Mill Road ov Tributary to Conewago Ck | 7229 | BRG | Bridge Replacement | CON | BRIP | 2028-08-24 |  | 0 | 0 | 0 | 198184 | 0 | 0 | 0 | 0 | 0 | 198184
York | 8 | York | 107325 | Iron Stone Hill Rd ov EB of Codorus Ck | 2087 | 004 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000
York | 8 | York | 107952 | Branch of Muddy Creek | 2069 | 007 | Bridge Restoration | PE | BRIP | 2029-01-01 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
York | 8 | York | 107952 | Branch of Muddy Creek | 2069 | 007 | Bridge Restoration | FD | BRIP | 2029-01-01 |  | 0 | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
York | 8 | York | 107952 | Branch of Muddy Creek | 2069 | 007 | Bridge Restoration | ROW | BRIP | 2029-01-01 |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
York | 8 | York | 107952 | Branch of Muddy Creek | 2069 | 007 | Bridge Restoration | UTL | BRIP | 2029-01-01 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
York | 8 | York | 107952 | Branch of Muddy Creek | 2069 | 007 | Bridge Restoration | CON | BRIP | 2029-01-01 |  | 0 | 0 | 0 | 260318 | 290746 | 1798936 | 0 | 0 | 0 | 2350000
York | 8 | York | 108732 | Red Lion Ave Resurface | 2079 | 006 | Highway Restoration | CON | 581 | 2024-09-26 | 2024-09-26 | 125046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125046
York | 8 | York | 108744 | SR 2005 Resurface | 2005 | 016 | Highway Restoration | PE | 581 | 2028-03-23 |  | 0 | 245961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245961
York | 8 | York | 109341 | Clearview Drive ov Trout Run | 3006 | 018 | Bridge Replacement | FD | 185 | 2027-01-21 |  | 200000 | 80324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280324
York | 8 | York | 109341 | Clearview Drive ov Trout Run | 3006 | 018 | Bridge Replacement | ROW | 185 | 2027-01-21 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
York | 8 | York | 109341 | Clearview Drive ov Trout Run | 3006 | 018 | Bridge Replacement | UTL | 185 | 2027-01-21 |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
York | 8 | York | 109341 | Clearview Drive ov Trout Run | 3006 | 018 | Bridge Replacement | CON | 185 | 2027-01-21 |  | 0 | 0 | 351798 | 1528469 | 0 | 0 | 0 | 0 | 0 | 1880267
York | 8 | York | 109341 | Clearview Drive ov Trout Run | 3006 | 018 | Bridge Replacement | CON | 581 | 2027-01-21 |  | 0 | 0 | 0 | 4687 | 0 | 0 | 0 | 0 | 0 | 4687
York | 8 | York | 110280 | College Avenue Bridge | 7301 | BRG | Bridge Replacement | CON | STP | 2026-05-21 |  | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
York | 8 | York | 110280 | College Avenue Bridge | 7301 | BRG | Bridge Replacement | CON | BOF | 2026-05-21 |  | 0 | 2609000 | 2181944 | 0 | 0 | 0 | 0 | 0 | 0 | 4790944
York | 8 | York | 110280 | College Avenue Bridge | 7301 | BRG | Bridge Replacement | CON | BRIP | 2026-05-21 |  | 0 | 2700000 | 1166115 | 0 | 0 | 0 | 0 | 0 | 0 | 3866115
York | 8 | York | 110280 | College Avenue Bridge | 7301 | BRG | Bridge Replacement | CON | STP | 2026-05-21 |  | 0 | 2825760 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 4325760
York | 8 | York | 110280 | College Avenue Bridge | 7301 | BRG | Bridge Replacement | CON | STU | 2026-05-21 |  | 0 | 1412585 | 1644585 | 1292423 | 0 | 0 | 0 | 0 | 0 | 4349593
York | 8 | York | 110480 | PA462 and PA624 Intersection | 462 | 056 | Safety Improvement | FD | STU | 2027-12-09 |  | 138155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138155
York | 8 | York | 110480 | PA462 and PA624 Intersection | 462 | 056 | Safety Improvement | ROW | 581 | 2027-12-09 |  | 92689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92689
York | 8 | York | 110480 | PA462 and PA624 Intersection | 462 | 056 | Safety Improvement | CON | 581 | 2027-12-09 |  | 0 | 0 | 549597 | 1175180 | 1708495 | 0 | 0 | 0 | 0 | 3433272
York | 8 | York | 111023 | Grantham Bridge Replacement | 7219 | BRG | Bridge Replacement | FD | BRIP | 2025-12-04 | 2025-12-04 | 15029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15029
York | 8 | York | 111023 | Grantham Bridge Replacement | 7219 | BRG | Bridge Replacement | FD | 185 | 2025-12-04 | 2025-12-04 | 2818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2818
York | 8 | York | 111023 | Grantham Bridge Replacement | 7219 | BRG | Bridge Replacement | FD | LOC | 2025-12-04 | 2025-12-04 | 939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939
York | 8 | York | 111023 | Grantham Bridge Replacement | 7219 | BRG | Bridge Replacement | ROW | BRIP | 2025-12-04 | 2025-12-04 | 34801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34801
York | 8 | York | 111023 | Grantham Bridge Replacement | 7219 | BRG | Bridge Replacement | ROW | 185 | 2025-12-04 | 2025-12-04 | 6526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6526
York | 8 | York | 111023 | Grantham Bridge Replacement | 7219 | BRG | Bridge Replacement | ROW | LOC | 2025-12-04 | 2025-12-04 | 2173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173
York | 8 | York | 111023 | Grantham Bridge Replacement | 7219 | BRG | Bridge Replacement | CON | BRIP | 2025-12-04 | 2025-12-04 | 1647832 | 339763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1987595
York | 8 | York | 111023 | Grantham Bridge Replacement | 7219 | BRG | Bridge Replacement | CON | STP | 2025-12-04 | 2025-12-04 | 64687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64687
York | 8 | York | 111023 | Grantham Bridge Replacement | 7219 | BRG | Bridge Replacement | CON | 183 | 2025-12-04 | 2025-12-04 | 245884 | 279507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525391
York | 8 | York | 111023 | Grantham Bridge Replacement | 7219 | BRG | Bridge Replacement | CON | LOC | 2025-12-04 | 2025-12-04 | 124870 | 3398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128268
York | 8 | York | 113073 | Rabbit Transit Employment Access |  |  | Public Transit | CON | CAQ |  |  | 112320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112320
York | 8 | York | 113329 | Hanover Road Resurface | 116 | 056 | Highway Restoration | PE | 581 | 2026-02-12 | 2026-02-12 | 86757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86757
York | 8 | York | 113329 | Hanover Road Resurface | 116 | 056 | Highway Restoration | CON | 581 | 2026-02-12 | 2026-02-12 | 2794400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2794400
York | 8 | York | 113517 | E Market St Signal | 462 | 061 | Safety Improvement | CON | 581 | 2024-10-10 | 2024-10-10 | 915007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 915007
York | 8 | York | 113518 | Beaver St ov N Brch Muddy Ck | 7408 | BRG | Bridge Replacement | PE | STP | 2028-11-01 |  | 177000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177000
York | 8 | York | 113518 | Beaver St ov N Brch Muddy Ck | 7408 | BRG | Bridge Replacement | FD | BRIP | 2028-11-01 |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 113518 | Beaver St ov N Brch Muddy Ck | 7408 | BRG | Bridge Replacement | ROW | BRIP | 2028-11-01 |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
York | 8 | York | 113518 | Beaver St ov N Brch Muddy Ck | 7408 | BRG | Bridge Replacement | UTL | BRIP | 2028-11-01 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
York | 8 | York | 113518 | Beaver St ov N Brch Muddy Ck | 7408 | BRG | Bridge Replacement | CON | BRIP | 2028-11-01 |  | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 700000
York | 8 | York | 114208 | E Prospect Rd Improvement | 124 | 016 | Safety Improvement | FD | STP | 2026-01-29 | 2026-01-29 | 92043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92043
York | 8 | York | 114208 | E Prospect Rd Improvement | 124 | 016 | Safety Improvement | ROW | HSIP | 2026-01-29 | 2026-01-29 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65700
York | 8 | York | 114208 | E Prospect Rd Improvement | 124 | 016 | Safety Improvement | UTL | HSIP | 2026-01-29 | 2026-01-29 | 146161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26015 | 172176
York | 8 | York | 114208 | E Prospect Rd Improvement | 124 | 016 | Safety Improvement | UTL | STP | 2026-01-29 | 2026-01-29 | 253839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253839
York | 8 | York | 114208 | E Prospect Rd Improvement | 124 | 016 | Safety Improvement | CON | HSIP | 2026-01-29 | 2026-01-29 | 0 | 0 | 461116 | 0 | 0 | 0 | 0 | 0 | 0 | 461116
York | 8 | York | 114208 | E Prospect Rd Improvement | 124 | 016 | Safety Improvement | CON | STP | 2026-01-29 | 2026-01-29 | 0 | 2370773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2370773
York | 8 | York | 114564 | York County Low Cost Signal Improvements | 3054 | 013 | Safety Improvement | CON | STU | 2022-09-29 | 2022-09-29 | 54536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54536
York | 8 | York | 115621 | Bannister St and Adams St Safety Imp | 3048 | 001 | Safety Improvement | FD | HSIP | 2026-07-30 |  | 438541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438541
York | 8 | York | 115621 | Bannister St and Adams St Safety Imp | 3048 | 001 | Safety Improvement | ROW | HSIP | 2026-07-30 |  | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000
York | 8 | York | 115621 | Bannister St and Adams St Safety Imp | 3048 | 001 | Safety Improvement | UTL | HSIP | 2026-07-30 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 115621 | Bannister St and Adams St Safety Imp | 3048 | 001 | Safety Improvement | CON | HSIP | 2026-07-30 |  | 0 | 1668163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1668163
York | 8 | York | 115621 | Bannister St and Adams St Safety Imp | 3048 | 001 | Safety Improvement | CON | STP | 2026-07-30 |  | 100347 | 883740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 984087
York | 8 | York | 115633 | Fairview Crossroads | 114 | 034 | Highway Reconstruction | CON | 581 |  |  | 1000000 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000
York | 8 | York | 115941 | Delta Rd Resurfacing | 74 | 077 | 409 Expanded Maintenance | FD | 581 | 2026-07-02 |  | 72494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72494
York | 8 | York | 115941 | Delta Rd Resurfacing | 74 | 077 | 409 Expanded Maintenance | UTL | 581 | 2026-07-02 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
York | 8 | York | 115990 | York Bike Share |  |  | Bicycle Pedestrian Highway | CON | CAQ |  |  | 220000 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
York | 8 | York | 116001 | Canal and Bull Rd | 921 | 017 | Congestion Reduction | PE | CAQ | 2027-03-11 |  | 12112 | 178316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190428
York | 8 | York | 116001 | Canal and Bull Rd | 921 | 017 | Congestion Reduction | FD | CAQ | 2027-03-11 |  | 337888 | 262112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
York | 8 | York | 116001 | Canal and Bull Rd | 921 | 017 | Congestion Reduction | ROW | CAQ | 2027-03-11 |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000
York | 8 | York | 116001 | Canal and Bull Rd | 921 | 017 | Congestion Reduction | UTL | CAQ | 2027-03-11 |  | 100000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
York | 8 | York | 116001 | Canal and Bull Rd | 921 | 017 | Congestion Reduction | CON | CAQ | 2027-03-11 |  | 0 | 0 | 1124000 | 400000 | 940000 | 0 | 0 | 0 | 0 | 2464000
York | 8 | York | 116002 | Main and E George St | 616 | 011 | Congestion Reduction | FD | CAQ | 2028-10-05 |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
York | 8 | York | 116002 | Main and E George St | 616 | 011 | Congestion Reduction | ROW | CAQ | 2028-10-05 |  | 0 | 790000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 790000
York | 8 | York | 116002 | Main and E George St | 616 | 011 | Congestion Reduction | UTL | CAQ | 2028-10-05 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 116002 | Main and E George St | 616 | 011 | Congestion Reduction | CON | CAQ | 2028-10-05 |  | 0 | 0 | 0 | 987164 | 0 | 0 | 0 | 0 | 0 | 987164
York | 8 | York | 116002 | Main and E George St | 616 | 011 | Congestion Reduction | CON | CRP | 2028-10-05 |  | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000
York | 8 | York | 116002 | Main and E George St | 616 | 011 | Congestion Reduction | CON | CRPU | 2028-10-05 |  | 0 | 0 | 0 | 516836 | 0 | 0 | 0 | 0 | 0 | 516836
York | 8 | York | 116003 | Exit 24 SB Off Ramp Widening | 8019 | 003 | Congestion Reduction | ROW | CAQ | 2027-10-21 |  | 0 | 182800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182800
York | 8 | York | 116003 | Exit 24 SB Off Ramp Widening | 8019 | 003 | Congestion Reduction | UTL | CAQ | 2027-10-21 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
York | 8 | York | 116003 | Exit 24 SB Off Ramp Widening | 8019 | 003 | Congestion Reduction | CON | CAQ | 2027-10-21 |  | 0 | 0 | 2523334 | 836454 | 490212 | 0 | 0 | 0 | 0 | 3850000
York | 8 | York | 116004 | Church/ Trail WB Widen | 238 | 012 | Congestion Reduction | FD | CAQ | 2027-10-21 |  | 192096 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 842096
York | 8 | York | 116004 | Church/ Trail WB Widen | 238 | 012 | Congestion Reduction | FD | CRP | 2027-10-21 |  | 307904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307904
York | 8 | York | 116004 | Church/ Trail WB Widen | 238 | 012 | Congestion Reduction | ROW | CAQ | 2027-10-21 |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
York | 8 | York | 116004 | Church/ Trail WB Widen | 238 | 012 | Congestion Reduction | UTL | CAQ | 2027-10-21 |  | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
York | 8 | York | 116004 | Church/ Trail WB Widen | 238 | 012 | Congestion Reduction | CON | CAQ | 2027-10-21 |  | 0 | 0 | 698811 | 815880 | 2528734 | 0 | 0 | 0 | 0 | 4043425
York | 8 | York | 116004 | Church/ Trail WB Widen | 238 | 012 | Congestion Reduction | CON | CRP | 2027-10-21 |  | 0 | 0 | 448000 | 448000 | 0 | 0 | 0 | 0 | 0 | 896000
York | 8 | York | 116004 | Church/ Trail WB Widen | 238 | 012 | Congestion Reduction | CON | CRPU | 2027-10-21 |  | 0 | 0 | 543897 | 0 | 0 | 0 | 0 | 0 | 0 | 543897
York | 8 | York | 116008 | US 30 Signal Improvements | 30 | 156 | Intelligent Transportation System | CON | STU | 2022-09-29 | 2022-09-29 | 54536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54536
York | 8 | York | 116104 | Trinity Rd Resur | 616 | 012 | Highway Restoration | PE | 581 | 2026-01-15 | 2026-01-15 | 69992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69992
York | 8 | York | 116104 | Trinity Rd Resur | 616 | 012 | Highway Restoration | UTL | 581 | 2026-01-15 | 2026-01-15 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
York | 8 | York | 116104 | Trinity Rd Resur | 616 | 012 | Highway Restoration | CON | STP | 2026-01-15 | 2026-01-15 | 475455 | 107589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583044
York | 8 | York | 116104 | Trinity Rd Resur | 616 | 012 | Highway Restoration | CON | STU | 2026-01-15 | 2026-01-15 | 1038309 | 163951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1202260
York | 8 | York | 116105 | Susquehanna Trl Resur | 4005 | 018 | Highway Restoration | CON | STP | 2024-08-08 | 2024-08-08 | 155827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155827
York | 8 | York | 116114 | Lincoln HW Resurf | 30 | 0 | Highway Restoration | CON | NHPP | 2036-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
York | 8 | York | 116115 | US 30 Resurfacing | 30 | 169 | Highway Restoration | PE | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 116115 | US 30 Resurfacing | 30 | 169 | Highway Restoration | FD | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 850000 | 0 | 0 | 0 | 850000
York | 8 | York | 116115 | US 30 Resurfacing | 30 | 169 | Highway Restoration | CON | 581 | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9903000 | 10389919 | 0 | 20292919
York | 8 | York | 116116 | Arsenal Rd Resurf 2 | 30 | 159 | Highway Restoration | CON | NHPP | 2025-06-05 | 2025-06-05 | 5425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5425000
York | 8 | York | 116116 | Arsenal Rd Resurf 2 | 30 | 159 | Highway Restoration | CON | STP | 2025-06-05 | 2025-06-05 | 8419009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8419009
York | 8 | York | 116116 | Arsenal Rd Resurf 2 | 30 | 159 | Highway Restoration | CON | STU | 2025-06-05 | 2025-06-05 | 4505470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4505470
York | 8 | York | 117011 | Wheat Road over SB Muddy Cr | 7209 | BRG | Bridge Replacement | PE | BRIP | 2030-03-28 |  | 217994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217994
York | 8 | York | 117011 | Wheat Road over SB Muddy Cr | 7209 | BRG | Bridge Replacement | FD | BOF | 2030-03-28 |  | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275000
York | 8 | York | 117011 | Wheat Road over SB Muddy Cr | 7209 | BRG | Bridge Replacement | CON | BOF | 2030-03-28 |  | 0 | 0 | 0 | 0 | 1494121 | 936877 | 0 | 0 | 0 | 2430998
York | 8 | York | 117013 | Industrial Hwy over 3 M Run | 7227 | BRG | Bridge Replacement | FD | BOF | 2028-09-28 |  | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
York | 8 | York | 117013 | Industrial Hwy over 3 M Run | 7227 | BRG | Bridge Replacement | ROW | BOF | 2028-09-28 |  | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
York | 8 | York | 117013 | Industrial Hwy over 3 M Run | 7227 | BRG | Bridge Replacement | UTL | BOF | 2028-09-28 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
York | 8 | York | 117013 | Industrial Hwy over 3 M Run | 7227 | BRG | Bridge Replacement | CON | BOF | 2028-09-28 |  | 0 | 0 | 0 | 1999000 | 1500000 | 0 | 0 | 0 | 0 | 3499000
York | 8 | York | 117013 | Industrial Hwy over 3 M Run | 7227 | BRG | Bridge Replacement | CON | BRIP | 2028-09-28 |  | 0 | 0 | 0 | 0 | 80954 | 0 | 0 | 0 | 0 | 80954
York | 8 | York | 117526 | York County Systemic Safety Improvements | 24 | 039 | Safety Improvement | PE | HSIP | 2024-09-12 | 2024-09-12 | 6666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6666
York | 8 | York | 117550 | York Service Patrol | 83 | 101 | Intelligent Transportation System | CON | CAQ |  |  | 0 | 496521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496521
York | 8 | York | 117617 | PA 24 and Druck Valley Rd Intersection HSM | 24 | 038 | Safety Improvement | PE | HSIP | 2028-03-02 |  | 52438 | 964780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1017218
York | 8 | York | 117617 | PA 24 and Druck Valley Rd Intersection HSM | 24 | 038 | Safety Improvement | FD | HSIP | 2028-03-02 |  | 115300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115300
York | 8 | York | 117617 | PA 24 and Druck Valley Rd Intersection HSM | 24 | 038 | Safety Improvement | ROW | HSIP | 2028-03-02 |  | 85820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85820
York | 8 | York | 117617 | PA 24 and Druck Valley Rd Intersection HSM | 24 | 038 | Safety Improvement | UTL | HSIP | 2028-03-02 |  | 77600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77600
York | 8 | York | 117617 | PA 24 and Druck Valley Rd Intersection HSM | 24 | 038 | Safety Improvement | CON | HSIP | 2028-03-02 |  | 0 | 0 | 413658 | 546364 | 0 | 0 | 0 | 0 | 0 | 960022
York | 8 | York | 117617 | PA 24 and Druck Valley Rd Intersection HSM | 24 | 038 | Safety Improvement | CON | STP | 2028-03-02 |  | 0 | 0 | 132705 | 0 | 0 | 0 | 0 | 0 | 0 | 132705
York | 8 | York | 117618 | Windsor Road Improvements HSM | 2031 | 017 | Safety Improvement | PE | HSIP | 2028-04-27 |  | 8087 | 100347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108434
York | 8 | York | 117618 | Windsor Road Improvements HSM | 2031 | 017 | Safety Improvement | FD | HSIP | 2028-04-27 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
York | 8 | York | 117618 | Windsor Road Improvements HSM | 2031 | 017 | Safety Improvement | ROW | HSIP | 2028-04-27 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 117618 | Windsor Road Improvements HSM | 2031 | 017 | Safety Improvement | UTL | HSIP | 2028-04-27 |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 117618 | Windsor Road Improvements HSM | 2031 | 017 | Safety Improvement | CON | HSIP | 2028-04-27 |  | 0 | 0 | 784627 | 1736636 | 1275675 | 0 | 0 | 0 | 0 | 3796938
York | 8 | York | 117653 | Long Level Rd over Cabin Creek | 624 | 013 | Bridge Preservation - Federal | PE | BRIP | 2027-12-09 |  | 202310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202310
York | 8 | York | 117653 | Long Level Rd over Cabin Creek | 624 | 013 | Bridge Preservation - Federal | PE | STP | 2027-12-09 |  | 228265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228265
York | 8 | York | 117653 | Long Level Rd over Cabin Creek | 624 | 013 | Bridge Preservation - Federal | FD | 185 | 2027-12-09 |  | 100000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
York | 8 | York | 117653 | Long Level Rd over Cabin Creek | 624 | 013 | Bridge Preservation - Federal | FD | 581 | 2027-12-09 |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
York | 8 | York | 117653 | Long Level Rd over Cabin Creek | 624 | 013 | Bridge Preservation - Federal | ROW | 581 | 2027-12-09 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
York | 8 | York | 117653 | Long Level Rd over Cabin Creek | 624 | 013 | Bridge Preservation - Federal | UTL | 581 | 2027-12-09 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
York | 8 | York | 117653 | Long Level Rd over Cabin Creek | 624 | 013 | Bridge Preservation - Federal | CON | 185 | 2027-12-09 |  | 0 | 0 | 50617 | 0 | 0 | 0 | 0 | 0 | 0 | 50617
York | 8 | York | 117653 | Long Level Rd over Cabin Creek | 624 | 013 | Bridge Preservation - Federal | CON | 581 | 2027-12-09 |  | 0 | 0 | 101000 | 1113383 | 0 | 0 | 0 | 0 | 0 | 1214383
York | 8 | York | 117654 | Locust Grove over Kreutz Creek | 2013 | 009 | Bridge Preservation - State Funded | PE | 185 |  |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
York | 8 | York | 117654 | Locust Grove over Kreutz Creek | 2013 | 009 | Bridge Preservation - State Funded | FD | 185 |  |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
York | 8 | York | 117654 | Locust Grove over Kreutz Creek | 2013 | 009 | Bridge Preservation - State Funded | CON | 185 |  |  | 0 | 0 | 0 | 0 | 423427 | 0 | 0 | 0 | 0 | 423427
York | 8 | York | 117655 | Lucky Rd over Otter Crk | 2018 | 016 | Bridge Replacement | FD | 185 | 2026-05-21 |  | 199098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199098
York | 8 | York | 117655 | Lucky Rd over Otter Crk | 2018 | 016 | Bridge Replacement | ROW | 185 | 2026-05-21 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
York | 8 | York | 117655 | Lucky Rd over Otter Crk | 2018 | 016 | Bridge Replacement | UTL | 185 | 2026-05-21 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
York | 8 | York | 117655 | Lucky Rd over Otter Crk | 2018 | 016 | Bridge Replacement | CON | BOF | 2026-05-21 |  | 1287359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1287359
York | 8 | York | 117655 | Lucky Rd over Otter Crk | 2018 | 016 | Bridge Replacement | CON | STP | 2026-05-21 |  | 376011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376011
York | 8 | York | 117655 | Lucky Rd over Otter Crk | 2018 | 016 | Bridge Replacement | CON | STU | 2026-05-21 |  | 113380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113380
York | 8 | York | 117666 | Toad Valley over Trout Run | 3022 | 006 | Bridge Replacement | PE | 185 |  |  | 200000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
York | 8 | York | 117666 | Toad Valley over Trout Run | 3022 | 006 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
York | 8 | York | 117666 | Toad Valley over Trout Run | 3022 | 006 | Bridge Replacement | CON | 581 |  |  | 0 | 0 | 0 | 236422 | 0 | 0 | 0 | 0 | 0 | 236422
York | 8 | York | 117673 | Lewisberry Rd over Cedar Point Run | 382 | 006 | Bridge Preservation - Federal | PE | 185 |  |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
York | 8 | York | 117673 | Lewisberry Rd over Cedar Point Run | 382 | 006 | Bridge Preservation - Federal | FD | 185 |  |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
York | 8 | York | 117673 | Lewisberry Rd over Cedar Point Run | 382 | 006 | Bridge Preservation - Federal | CON | 185 |  |  | 0 | 0 | 0 | 630460 | 0 | 0 | 0 | 0 | 0 | 630460
York | 8 | York | 117676 | Days Mill Rd over S Br Codorus Crk | 3042 | 002 | Bridge Restoration | PE | STP | 2027-01-21 |  | 260795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260795
York | 8 | York | 117676 | Days Mill Rd over S Br Codorus Crk | 3042 | 002 | Bridge Restoration | FD | BRIP | 2027-01-21 |  | 0 | 210650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210650
York | 8 | York | 117676 | Days Mill Rd over S Br Codorus Crk | 3042 | 002 | Bridge Restoration | FD | STP | 2027-01-21 |  | 0 | 12430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12430
York | 8 | York | 117676 | Days Mill Rd over S Br Codorus Crk | 3042 | 002 | Bridge Restoration | ROW | 185 | 2027-01-21 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
York | 8 | York | 117676 | Days Mill Rd over S Br Codorus Crk | 3042 | 002 | Bridge Restoration | UTL | 185 | 2027-01-21 |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
York | 8 | York | 117676 | Days Mill Rd over S Br Codorus Crk | 3042 | 002 | Bridge Restoration | CON | 185 | 2027-01-21 |  | 0 | 0 | 351798 | 0 | 0 | 0 | 0 | 0 | 0 | 351798
York | 8 | York | 117676 | Days Mill Rd over S Br Codorus Crk | 3042 | 002 | Bridge Restoration | CON | 581 | 2027-01-21 |  | 0 | 0 | 0 | 1589705 | 0 | 0 | 0 | 0 | 0 | 1589705
York | 8 | York | 117683 | Moores Mnt ov Millers Run | 4031 | 001 | Bridge Replacement | PE | 185 |  |  | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
York | 8 | York | 117683 | Moores Mnt ov Millers Run | 4031 | 001 | Bridge Replacement | FD | 581 |  |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
York | 8 | York | 117683 | Moores Mnt ov Millers Run | 4031 | 001 | Bridge Replacement | CON | 581 |  |  | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 117706 | Forks Road over Deer Creek | 7226 | BRG | Bridge Replacement | PE | BRIP |  |  | 0 | 0 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 325000
York | 8 | York | 117706 | Forks Road over Deer Creek | 7226 | BRG | Bridge Replacement | FD | BOF |  |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 117706 | Forks Road over Deer Creek | 7226 | BRG | Bridge Replacement | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 1844812 | 0 | 0 | 0 | 0 | 1844812
York | 8 | York | 117710 | Red Mill Rd over Fishing Creek | 7220 | BRG | Bridge Replacement | PE | STP | 2029-11-01 |  | 242000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242000
York | 8 | York | 117710 | Red Mill Rd over Fishing Creek | 7220 | BRG | Bridge Replacement | CON | BOF | 2029-11-01 |  | 0 | 0 | 0 | 0 | 0 | 579638 | 1420362 | 0 | 0 | 2000000
York | 8 | York | 117712 | Woodbine Road over Fishing Creek | 7224 | BRG | Bridge Replacement | PE | BRIP |  |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 117712 | Woodbine Road over Fishing Creek | 7224 | BRG | Bridge Replacement | FD | BRIP |  |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
York | 8 | York | 117712 | Woodbine Road over Fishing Creek | 7224 | BRG | Bridge Replacement | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1773478 | 0 | 0 | 1773478
York | 8 | York | 117716 | Franklin St over Barshinger Ck | 2085 | 002 | Bridge Preservation - Federal | PE | 185 |  |  | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
York | 8 | York | 117716 | Franklin St over Barshinger Ck | 2085 | 002 | Bridge Preservation - Federal | FD | 185 |  |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
York | 8 | York | 117716 | Franklin St over Barshinger Ck | 2085 | 002 | Bridge Preservation - Federal | CON | 185 |  |  | 0 | 0 | 0 | 541622 | 0 | 0 | 0 | 0 | 0 | 541622
York | 8 | York | 117730 | 7 Valleys ov Krebs Cr | 616 | 013 | Bridge Replacement | PE | 185 |  |  | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
York | 8 | York | 117730 | 7 Valleys ov Krebs Cr | 616 | 013 | Bridge Replacement | FD | 185 |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
York | 8 | York | 117730 | 7 Valleys ov Krebs Cr | 616 | 013 | Bridge Replacement | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 1143967 | 0 | 0 | 0 | 0 | 1143967
York | 8 | York | 117753 | Creek Rd ov N BR Bermudian Cr | 4012 | 005 | Bridge Restoration | PE | 185 |  |  | 0 | 0 | 0 | 119696 | 30304 | 0 | 0 | 0 | 0 | 150000
York | 8 | York | 117753 | Creek Rd ov N BR Bermudian Cr | 4012 | 005 | Bridge Restoration | FD | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 75000
York | 8 | York | 117753 | Creek Rd ov N BR Bermudian Cr | 4012 | 005 | Bridge Restoration | CON | BRIP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 356203 | 0 | 0 | 356203
York | 8 | York | 118068 | Mt Zion Rd 2 | 24 | 040 | 409 Expanded Maintenance | PE | 581 | 2026-06-04 |  | 0 | 115209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115209
York | 8 | York | 118489 | Sheepford Road Ped/Bike Bridge | 7208 | BRD | Bridge Restoration | CON | STP | 2025-05-22 | 2025-05-22 | 268395 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 668395
York | 8 | York | 118489 | Sheepford Road Ped/Bike Bridge | 7208 | BRD | Bridge Restoration | CON | TAP | 2025-05-22 | 2025-05-22 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000
York | 8 | York | 118491 | East Market Street Ped Impr | 462 | 063 | Bicycle Pedestrian Highway | CON | TAP | 2027-08-12 |  | 0 | 0 | 535000 | 0 | 0 | 0 | 0 | 0 | 0 | 535000
York | 8 | York | 119215 | York MPO TIP Funded Bridge Repair Contract |  |  | Bridge Preservation - State Funded | CON | 185 |  |  | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 2000000
York | 8 | York | 119285 | Carbon Reduction Program (CRP) York MPO RSL |  |  | Reserve Line Item | CON | CRP |  |  | 124096 | 448000 | 0 | 0 | 48000 | 448000 | 448000 | 448000 | 1792000 | 3756096
York | 8 | York | 119285 | Carbon Reduction Program (CRP) York MPO RSL |  |  | Reserve Line Item | CON | CRPU |  |  | 533193 | 543897 | 0 | 27061 | 813000 | 813000 | 813000 | 813000 | 3252000 | 7608151
York | 8 | York | 119465 | Codorus Creekside Trail FLAP/DCED |  | FLP | Bicycle Pedestrian Highway | CON | FLAP | 2027-01-01 |  | 0 | 0 | 959000 | 0 | 0 | 0 | 0 | 0 | 0 | 959000
York | 8 | York | 119465 | Codorus Creekside Trail FLAP/DCED |  | FLP | Bicycle Pedestrian Highway | CON | OTH-S | 2027-01-01 |  | 0 | 0 | 624291 | 0 | 0 | 0 | 0 | 0 | 0 | 624291
York | 8 | York | 120103 | Stonewood Road RRX | 2017 | RRX | Rail Highway Grade Crossing | CON | RRX | 2023-10-23 | 2023-10-23 | 348396 | 101690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450086
York | 8 | York | 120709 | US 30 over PA 74 | 30 | 0 | Bridge Preservation - Federal | PE | BRIP |  |  | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 350000
York | 8 | York | 120733 | North George Street RRX Crossing | 3065 | 0 | Rail Highway Grade Crossing | CON | STU |  |  | 0 | 0 | 355415 | 391930 | 0 | 0 | 0 | 0 | 0 | 747345
York | 8 | York | 120745 | West King Street RRX Crossing |  | RRX | Rail Highway Grade Crossing | CON | STP |  |  | 0 | 116747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116747
York | 8 | York | 120750 | Lincoln HWY Resurfacing 3 | 30 | 0 | Highway Restoration | PE | STU |  |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 120750 | Lincoln HWY Resurfacing 3 | 30 | 0 | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 125000
York | 8 | York | 120750 | Lincoln HWY Resurfacing 3 | 30 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 1235844 | 0 | 0 | 0 | 1235844
York | 8 | York | 120751 | Lincoln HWY Resurf 4 | 30 | 0 | Highway Restoration | PE | 581 |  |  | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000
York | 8 | York | 120751 | Lincoln HWY Resurf 4 | 30 | 0 | Highway Restoration | FD | 581 |  |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
York | 8 | York | 120751 | Lincoln HWY Resurf 4 | 30 | 0 | Highway Restoration | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 4514616 | 0 | 34723 | 0 | 4549339
York | 8 | York | 120906 | Glen Rock Borough Safety Improvements | 216 | 026 | Bicycle Pedestrian Highway | CON | TAU | 2027-10-07 |  | 0 | 465616 | 366840 | 0 | 0 | 0 | 0 | 0 | 0 | 832456
York | 8 | York | 120908 | Hanover Trolley Trail Expansion | 3061 | 001 | Bicycle Pedestrian Highway | CON | TAU | 2027-06-24 |  | 512000 | 57384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 569384
York | 8 | York | 121409 | SR 616 (Baltimore Street) Retaining Wall | 616 | 014 | Safety Improvement | PE | PRTCT | 2028-12-14 |  | 99509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99509
York | 8 | York | 121409 | SR 616 (Baltimore Street) Retaining Wall | 616 | 014 | Safety Improvement | FD | PRTCT | 2028-12-14 |  | 370000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370000
York | 8 | York | 121409 | SR 616 (Baltimore Street) Retaining Wall | 616 | 014 | Safety Improvement | UTL | PRTCT | 2028-12-14 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
York | 8 | York | 121409 | SR 616 (Baltimore Street) Retaining Wall | 616 | 014 | Safety Improvement | CON | PRTCT | 2028-12-14 |  | 0 | 0 | 3300000 | 0 | 0 | 0 | 0 | 0 | 0 | 3300000
York | 8 | York | 121481 | Kindig Lane and High Street Temporary Signal |  | LOC | Safety Improvement | CON | STP | 2024-12-12 | 2024-12-12 | 934437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934437
York | 8 | York | 121537 | York City 2023 Safe Routes to School Improvements |  | TAP | Federal Safe Routes to Schools | CON | TAP | 2027-04-08 |  | 0 | 1508220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1508220
York | 8 | York | 122222 | York MPO -District 8-0 Asset Management- Paving | 15 | 0 | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50746293 | 50746293
York | 8 | York | 122837 | Seven Valleys Rd Br Clanker | 214 | 009 | Safety Improvement | CON | 581 |  |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
York | 8 | York | 123343 | York Safe Streets for All 2025 |  |  | Planning/Research/Administration | PE | 581 |  |  | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
York | 8 | York | 123459 | Codorus Creekside Trail RAISE |  | RAI | Bicycle Pedestrian Highway | CON | RAISE | 2027-01-01 |  | 0 | 0 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000
York | 8 | York | 123459 | Codorus Creekside Trail RAISE |  | RAI | Bicycle Pedestrian Highway | CON | OTH-S | 2027-01-01 |  | 0 | 0 | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000000
Interstate | 1 | Erie | 58201 | Beckman Bridge over I-90 - Demolition | 3105 | B01 | Interstate Maintenance Program | CON | 581 | 2025-07-10 | 2025-07-10 | 438378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438378
Interstate | 1 | Erie | 76852 | I-79: MM 165 - MM 178 - Resurfacing | 79 | A11 | Interstate Maintenance Program | PE | 581 | 2026-02-26 | 2026-02-26 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Interstate | 1 | Erie | 76852 | I-79: MM 165 - MM 178 - Resurfacing | 79 | A11 | Interstate Maintenance Program | FD | NHPP | 2026-02-26 | 2026-02-26 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Interstate | 1 | Erie | 76852 | I-79: MM 165 - MM 178 - Resurfacing | 79 | A11 | Interstate Maintenance Program | CON | NHPP | 2026-02-26 | 2026-02-26 | 0 | 31800000 | 8586765 | 0 | 0 | 0 | 0 | 0 | 0 | 40386765
Interstate | 1 | Erie | 99060 | I-79: MM 165 - MM 178 - Patching | 79 | 01M | Interstate Maintenance Program | CON | 581 | 2025-07-24 | 2025-07-24 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Interstate | 1 | Erie | 102039 | I-90: MP 3.5 to 7 Reconstruct - #1 | 90 | A30 | Interstate Maintenance Program | CON | NHPP | 2020-11-05 | 2020-11-13 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000
Interstate | 1 | Erie | 102041 | I-90: MM 10.5 - MM 14.5 - Reconstruction | 90 | A32 | Interstate Maintenance Program | FD | 581 | 2028-04-27 |  | 3000000 | 2477412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5477412
Interstate | 1 | Erie | 102041 | I-90: MM 10.5 - MM 14.5 - Reconstruction | 90 | A32 | Interstate Maintenance Program | ROW | 581 | 2028-04-27 |  | 0 | 0 | 0 | 240707 | 0 | 0 | 0 | 0 | 0 | 240707
Interstate | 1 | Erie | 102041 | I-90: MM 10.5 - MM 14.5 - Reconstruction | 90 | A32 | Interstate Maintenance Program | UTL | 581 | 2028-04-27 |  | 0 | 0 | 77899 | 0 | 0 | 0 | 0 | 0 | 0 | 77899
Interstate | 1 | Erie | 102041 | I-90: MM 10.5 - MM 14.5 - Reconstruction | 90 | A32 | Interstate Maintenance Program | CON | NHPP | 2028-04-27 |  | 0 | 0 | 0 | 29600000 | 24560019 | 0 | 0 | 0 | 0 | 54160019
Interstate | 1 | Erie | 102041 | I-90: MM 10.5 - MM 14.5 - Reconstruction | 90 | A32 | Interstate Maintenance Program | CON | 581 | 2028-04-27 |  | 0 | 0 | 0 | 3053025 | 2728891 | 0 | 0 | 0 | 0 | 5781916
Interstate | 1 | Erie | 102044 | I-90: MM 14.5 - MM 18 - Reconstruction | 90 | A33 | Interstate Maintenance Program | ROW | 581 | 2028-04-27 |  | 0 | 240707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240707
Interstate | 1 | Erie | 102044 | I-90: MM 14.5 - MM 18 - Reconstruction | 90 | A33 | Interstate Maintenance Program | UTL | 581 | 2028-04-27 |  | 77899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77899
Interstate | 1 | Erie | 102044 | I-90: MM 14.5 - MM 18 - Reconstruction | 90 | A33 | Interstate Maintenance Program | CON | NHPP | 2028-04-27 |  | 0 | 0 | 0 | 25000000 | 24686197 | 0 | 0 | 0 | 0 | 49686197
Interstate | 1 | Erie | 109796 | I-90: MM 23 - MM 35 - Preservation | 90 | A38 | Interstate Maintenance Program | PE | NHPP | 2030-05-09 |  | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 1200000
Interstate | 1 | Erie | 109796 | I-90: MM 23 - MM 35 - Preservation | 90 | A38 | Interstate Maintenance Program | FD | NHPP | 2030-05-09 |  | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 800000
Interstate | 1 | Erie | 109796 | I-90: MM 23 - MM 35 - Preservation | 90 | A38 | Interstate Maintenance Program | CON | NHPP | 2030-05-09 |  | 0 | 0 | 0 | 0 | 3000000 | 12000000 | 13350000 | 0 | 0 | 28350000
Interstate | 1 | Erie | 109800 | I-90 MM 18 to MM 23 | 90 | A39 | Interstate Maintenance Program | PE | 581 | 2025-07-24 | 2025-07-24 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Interstate | 1 | Erie | 109800 | I-90 MM 18 to MM 23 | 90 | A39 | Interstate Maintenance Program | FD | NHPP | 2025-07-24 | 2025-07-24 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Interstate | 1 | Erie | 109800 | I-90 MM 18 to MM 23 | 90 | A39 | Interstate Maintenance Program | CON | STP | 2025-07-24 | 2025-07-24 | 9007000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9007000
Interstate | 1 | Erie | 109800 | I-90 MM 18 to MM 23 | 90 | A39 | Interstate Maintenance Program | CON | NHPP | 2025-07-24 | 2025-07-24 | 11229252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11229252
Interstate | 1 | Erie | 109823 | I-90 Bridges Replacement | 90 | B20 | Interstate Maintenance Program | PE | 185 | 2029-01-01 |  | 0 | 1650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650000
Interstate | 1 | Erie | 115467 | I-79 Bridges over NS & CSX RR | 79 | B09 | Interstate Maintenance Program | FD | 185 | 2026-06-18 |  | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
Interstate | 1 | Erie | 115467 | I-79 Bridges over NS & CSX RR | 79 | B09 | Interstate Maintenance Program | ROW | 185 | 2026-06-18 |  | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
Interstate | 1 | Erie | 115467 | I-79 Bridges over NS & CSX RR | 79 | B09 | Interstate Maintenance Program | CON | 185 | 2026-06-18 |  | 15438604 | 22236396 | 967000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 48642000
Interstate | 1 | Erie | 115467 | I-79 Bridges over NS & CSX RR | 79 | B09 | Interstate Maintenance Program | CON | 581 | 2026-06-18 |  | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 1600000
Interstate | 1 | Erie | 122393 | Erie Interstate Ramp Gates |  |  | Interstate Maintenance Program | PE | 581 | 2025-07-10 | 2025-07-10 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Interstate | 1 | Erie | 122393 | Erie Interstate Ramp Gates |  |  | Interstate Maintenance Program | CON | 581 | 2025-07-10 | 2025-07-10 | 650330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650330
Interstate | 1 | Erie | 123777 | Weigh Station Sensors - Concrete Repair/Paving | 9202 | WSP | Highway Restoration | CON | 581 | 2026-05-21 |  | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
Interstate | 1 | Mercer | 51021 | I-80: MM 11 - MM 15 - Reconstruction | 80 | A22 | Interstate Maintenance Program | PE | 581 | 2029-10-18 |  | 1800000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800000
Interstate | 1 | Mercer | 51021 | I-80: MM 11 - MM 15 - Reconstruction | 80 | A22 | Interstate Maintenance Program | FD | 581 | 2029-10-18 |  | 0 | 0 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000
Interstate | 1 | Mercer | 51021 | I-80: MM 11 - MM 15 - Reconstruction | 80 | A22 | Interstate Maintenance Program | CON | NHPP | 2029-10-18 |  | 0 | 0 | 0 | 35000000 | 29800000 | 0 | 0 | 0 | 0 | 64800000
Interstate | 1 | Mercer | 51021 | I-80: MM 11 - MM 15 - Reconstruction | 80 | A22 | Interstate Maintenance Program | CON | 581 | 2029-10-18 |  | 0 | 0 | 0 | 5150000 | 2050000 | 0 | 0 | 0 | 0 | 7200000
Interstate | 1 | Mercer | 51022 | I-80: MP 15 to 27 Patching | 80 | A10 | Interstate Maintenance Program | CON | NHPP | 2024-08-08 | 2024-08-08 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Interstate | 1 | Mercer | 81460 | I-79: MM 126 - MM 136 - Centerline | 79 | 03M | Interstate Maintenance Program | PE | 581 | 2026-06-18 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Interstate | 1 | Mercer | 81460 | I-79: MM 126 - MM 136 - Centerline | 79 | 03M | Interstate Maintenance Program | CON | 581 | 2026-06-18 |  | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Interstate | 1 | Mercer | 81476 | I-80: MM 6 - MM 10 - Reconstruction | 80 | A23 | Interstate Maintenance Program | CON | NHPP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 17762092 | 15000000 | 15000000 | 0 | 0 | 47762092
Interstate | 1 | Mercer | 91569 | I-80: MM 0 to MM 5 - Reconstruct | 80 | A16 | Interstate Maintenance Program | PE | 581 | 2025-01-30 | 2025-02-13 | 1400551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400551
Interstate | 1 | Mercer | 91569 | I-80: MM 0 to MM 5 - Reconstruct | 80 | A16 | Interstate Maintenance Program | FD | 581 | 2025-01-30 | 2025-02-13 | 117293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117293
Interstate | 1 | Mercer | 91569 | I-80: MM 0 to MM 5 - Reconstruct | 80 | A16 | Interstate Maintenance Program | CON | HSIP | 2025-01-30 | 2025-02-13 | 421551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421551
Interstate | 1 | Mercer | 91569 | I-80: MM 0 to MM 5 - Reconstruct | 80 | A16 | Interstate Maintenance Program | CON | NHPP | 2025-01-30 | 2025-02-13 | 124363583 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124513583
Interstate | 1 | Mercer | 109793 | I-79: MM 110 - MM 118 and MM 120 - MM 126 - Pres. | 79 | A18 | Interstate Maintenance Program | PE | 581 | 2026-02-12 | 2026-02-12 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Interstate | 1 | Mercer | 109793 | I-79: MM 110 - MM 118 and MM 120 - MM 126 - Pres. | 79 | A18 | Interstate Maintenance Program | FD | 581 | 2026-02-12 | 2026-02-12 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Interstate | 1 | Mercer | 109793 | I-79: MM 110 - MM 118 and MM 120 - MM 126 - Pres. | 79 | A18 | Interstate Maintenance Program | CON | NHPP | 2026-02-12 | 2026-02-12 | 0 | 16546084 | 5667970 | 0 | 0 | 0 | 0 | 0 | 0 | 22214054
Interstate | 1 | Mercer | 116475 | I-79: MM 118 - MM 119 - Preservation | 79 | A19 | Interstate Maintenance Program | PE | 581 | 2027-01-14 |  | 800000 | 725000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1525000
Interstate | 1 | Mercer | 116475 | I-79: MM 118 - MM 119 - Preservation | 79 | A19 | Interstate Maintenance Program | FD | 581 | 2027-01-14 |  | 400000 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720000
Interstate | 1 | Mercer | 116475 | I-79: MM 118 - MM 119 - Preservation | 79 | A19 | Interstate Maintenance Program | CON | NHPP | 2027-01-14 |  | 0 | 0 | 20077619 | 5024831 | 0 | 0 | 0 | 0 | 0 | 25102450
Interstate | 1 | Mercer | 117601 | I-80: MP 10 to MP 15 - High Friction | 80 | HFT | Highway Restoration | PE | 581 | 2025-05-08 | 2025-05-08 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Interstate | 1 | Mercer | 117601 | I-80: MP 10 to MP 15 - High Friction | 80 | HFT | Highway Restoration | CON | NHPP | 2025-05-08 | 2025-05-08 | 2529831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2529831
Interstate | 1 | Mercer | 120915 | SR 318 over 376 Bridge Replacement | 318 | B07 | Reserve Line Item | CON | FFL | 2024-03-14 | 2024-03-14 | 1381024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381024
Interstate | 1 | Mercer | 120915 | SR 318 over 376 Bridge Replacement | 318 | B07 | Reserve Line Item | CON | 581 | 2024-03-14 | 2024-03-14 | 345256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345256
Interstate | 1 | Mercer | 123301 | I-80/I-79 RWRPM | 80 | RPM | Safety Improvement | CON | NHPP | 2026-05-21 |  | 0 | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475000
Interstate | 2 | Centre | 3120 | Route 220 Reloc (C12) | 220 | C12 | New Alignment | ROW | 581 | 2000-08-24 | 2000-08-10 | 9460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9460
Interstate | 2 | Centre | 3142 | EXIT 161 Bellefonte Interchange | 80 | B18 | Interstate Maintenance Program | CON | APD | 2024-06-06 | 2024-06-06 | 29250000 | 23750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53000000
Interstate | 2 | Centre | 3142 | EXIT 161 Bellefonte Interchange | 80 | B18 | Interstate Maintenance Program | CON | INFRA | 2024-06-06 | 2024-06-06 | 2036235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036235
Interstate | 2 | Centre | 3142 | EXIT 161 Bellefonte Interchange | 80 | B18 | Interstate Maintenance Program | CON | NHPP | 2024-06-06 | 2024-06-06 | 14644976 | 2036235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16681211
Interstate | 2 | Centre | 3142 | EXIT 161 Bellefonte Interchange | 80 | B18 | Interstate Maintenance Program | CON | 185 | 2024-06-06 | 2024-06-06 | 3584527 | 5531600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9116127
Interstate | 2 | Centre | 3142 | EXIT 161 Bellefonte Interchange | 80 | B18 | Interstate Maintenance Program | CON | 581 | 2024-06-06 | 2024-06-06 | 855508 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1855508
Interstate | 2 | Centre | 74912 | I-80 Bridge Replacements | 80 | B38 | Interstate Maintenance Program | CON | 185 | 2023-03-02 | 2023-03-02 | 6127285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6127285
Interstate | 2 | Centre | 88577 | Interstate 80 MM 155 to MM 159 | 80 | B43 | Interstate Maintenance Program | PE | NHPP | 2026-04-09 |  | 643500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 643500
Interstate | 2 | Centre | 88577 | Interstate 80 MM 155 to MM 159 | 80 | B43 | Interstate Maintenance Program | PE | 581 | 2026-04-09 |  | 71500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71500
Interstate | 2 | Centre | 88577 | Interstate 80 MM 155 to MM 159 | 80 | B43 | Interstate Maintenance Program | FD | NHPP | 2026-04-09 |  | 630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630000
Interstate | 2 | Centre | 88577 | Interstate 80 MM 155 to MM 159 | 80 | B43 | Interstate Maintenance Program | FD | 581 | 2026-04-09 |  | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
Interstate | 2 | Centre | 88577 | Interstate 80 MM 155 to MM 159 | 80 | B43 | Interstate Maintenance Program | UTL | 581 | 2026-04-09 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Interstate | 2 | Centre | 88577 | Interstate 80 MM 155 to MM 159 | 80 | B43 | Interstate Maintenance Program | CON | NHPP | 2026-04-09 |  | 0 | 0 | 15440921 | 0 | 0 | 0 | 0 | 0 | 0 | 15440921
Interstate | 2 | Centre | 88577 | Interstate 80 MM 155 to MM 159 | 80 | B43 | Interstate Maintenance Program | CON | 581 | 2026-04-09 |  | 0 | 0 | 1715658 | 0 | 0 | 0 | 0 | 0 | 0 | 1715658
Interstate | 2 | Centre | 109238 | Rehab/Preserv MM 165 to 170 | 80 | B50 | Interstate Maintenance Program | PE | 581 | 2026-05-21 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Interstate | 2 | Centre | 109238 | Rehab/Preserv MM 165 to 170 | 80 | B50 | Interstate Maintenance Program | CON | NHPP | 2026-05-21 |  | 0 | 2000000 | 8500000 | 8000000 | 0 | 0 | 0 | 0 | 0 | 18500000
Interstate | 2 | Centre | 122719 | Interstate Approach Slab | 99 | AS2 | Bridge Restoration | PE | 185 | 2026-07-30 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Interstate | 2 | Centre | 122719 | Interstate Approach Slab | 99 | AS2 | Bridge Restoration | CON | 185 | 2026-07-30 |  | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000
Interstate | 2 | Clearfield | 88579 | I-80 Preservation MM 96 to MM 119 | 80 | B42 | Interstate Maintenance Program | CON | BRIP | 2024-04-18 | 2024-04-18 | 5023000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5023000
Interstate | 2 | Clearfield | 88579 | I-80 Preservation MM 96 to MM 119 | 80 | B42 | Interstate Maintenance Program | CON | NHPP | 2024-04-18 | 2024-04-18 | 6837730 | 725000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7562730
Interstate | 2 | Clinton | 122162 | Exit 185 Ramps | 8008 | RMP | Highway Restoration | CON | NHPP | 2025-06-05 | 2025-06-05 | 805000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805000
Interstate | 3 | Columbia | 93697 | I-80 from SR 487 to SR 11 | 80 | 136 | Interstate Maintenance Program | PE | 581 | 2032-01-01 |  | 0 | 0 | 4114919 | 4000000 | 0 | 0 | 0 | 0 | 0 | 8114919
Interstate | 3 | Columbia | 93697 | I-80 from SR 487 to SR 11 | 80 | 136 | Interstate Maintenance Program | FD | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 5534432 | 0 | 0 | 0 | 0 | 5534432
Interstate | 3 | Columbia | 93697 | I-80 from SR 487 to SR 11 | 80 | 136 | Interstate Maintenance Program | ROW | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 31669 | 0 | 0 | 0 | 31669
Interstate | 3 | Columbia | 93697 | I-80 from SR 487 to SR 11 | 80 | 136 | Interstate Maintenance Program | UTL | 581 | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 95008 | 0 | 0 | 0 | 95008
Interstate | 3 | Columbia | 93697 | I-80 from SR 487 to SR 11 | 80 | 136 | Interstate Maintenance Program | CON | NHPP | 2032-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124000000 | 124000000
Interstate | 3 | Columbia | 97561 | I-80 from Creek Road to SR 487 | 80 | 131 | Interstate Maintenance Program | PE | NHPP | 2026-08-27 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Interstate | 3 | Columbia | 97561 | I-80 from Creek Road to SR 487 | 80 | 131 | Interstate Maintenance Program | FD | NHPP | 2026-08-27 |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Interstate | 3 | Columbia | 97561 | I-80 from Creek Road to SR 487 | 80 | 131 | Interstate Maintenance Program | ROW | 581 | 2026-08-27 |  | 98000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98000
Interstate | 3 | Columbia | 97561 | I-80 from Creek Road to SR 487 | 80 | 131 | Interstate Maintenance Program | CON | NHPP | 2026-08-27 |  | 0 | 20000000 | 39814399 | 35185601 | 0 | 0 | 0 | 0 | 0 | 95000000
Interstate | 3 | Columbia | 97561 | I-80 from Creek Road to SR 487 | 80 | 131 | Interstate Maintenance Program | CON | PRTCT | 2026-08-27 |  | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
Interstate | 3 | Columbia | 97736 | East Bound Rest Area | 80 | 140 | Rest Area/Welcome Center | PE | NHPP | 2027-08-12 |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
Interstate | 3 | Columbia | 97736 | East Bound Rest Area | 80 | 140 | Rest Area/Welcome Center | PE | 581 | 2027-08-12 |  | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 500000
Interstate | 3 | Columbia | 97736 | East Bound Rest Area | 80 | 140 | Rest Area/Welcome Center | FD | NHPP | 2027-08-12 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Interstate | 3 | Columbia | 97736 | East Bound Rest Area | 80 | 140 | Rest Area/Welcome Center | FD | 581 | 2027-08-12 |  | 0 | 0 | 0 | 0 | 0 | 594000 | 120000 | 0 | 0 | 714000
Interstate | 3 | Columbia | 97736 | East Bound Rest Area | 80 | 140 | Rest Area/Welcome Center | UTL | NHPP | 2027-08-12 |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Interstate | 3 | Columbia | 97736 | East Bound Rest Area | 80 | 140 | Rest Area/Welcome Center | CON | NHPP | 2027-08-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3800000 | 5500000 | 0 | 9300000
Interstate | 3 | Columbia | 97736 | East Bound Rest Area | 80 | 140 | Rest Area/Welcome Center | CON | NHPP | 2027-08-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 50000 | 3700000 | 4250000
Interstate | 3 | Columbia | 97736 | East Bound Rest Area | 80 | 140 | Rest Area/Welcome Center | CON | STP | 2027-08-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000
Interstate | 3 | Columbia | 112359 | ITS Camera #2 Buckhorn Interchange | 80 | 183 | Intelligent Transportation System | CON | NHPP | 2026-08-27 |  | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
Interstate | 3 | Columbia | 112362 | DMS ITS Columbia County | 80 | 184 | Intelligent Transportation System | CON | NHPP | 2026-08-27 |  | 690000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 690000
Interstate | 3 | Columbia | 119747 | I-80 Fishing Creek embankment stabilization | 80 | 203 | Preventive Maintenance | CON | PRTCT | 2023-08-10 | 2023-08-10 | 347431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347431
Interstate | 3 | Columbia | 120616 | Recessed Tape Installation | 80 | 208 | Safety Improvement | CON | NHPP | 2024-11-07 | 2024-11-07 | 148491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148491
Interstate | 3 | Lycoming | 105531 | Market St to Warrensville Rd EB | 180 | 131 | Highway Restoration | CON | NHPP | 2025-01-16 | 2025-01-16 | 5130639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5130639
Interstate | 3 | Lycoming | 105532 | Market St to Warrensville Rd WB | 180 | 132 | Highway Restoration | CON | NHPP | 2025-01-16 | 2025-01-16 | 4561361 | 1119188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5680549
Interstate | 3 | Lycoming | 116346 | I-99 Designation Improvements | 15 | 286 | Safety Improvement | PE | 581 | 2025-11-06 | 2025-11-06 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Interstate | 3 | Lycoming | 116346 | I-99 Designation Improvements | 15 | 286 | Safety Improvement | FD | 581 | 2025-11-06 | 2025-11-06 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325000
Interstate | 3 | Lycoming | 116346 | I-99 Designation Improvements | 15 | 286 | Safety Improvement | CON | 581 | 2025-11-06 | 2025-11-06 | 4087049 | 3781793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7868842
Interstate | 3 | Lycoming | 120044 | Recessed Tape Installation | 180 | 150 | Safety Improvement | CON | NHPP | 2024-11-07 | 2024-11-07 | 123544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123544
Interstate | 3 | Lycoming | 120114 | SR 180 ov Muncy Creek, SR 405, 2014, 2044 & 2061 | 180 | 152 | Bridge Preservation - Federal | PE | NHPP | 2027-09-16 |  | 50000 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
Interstate | 3 | Lycoming | 120114 | SR 180 ov Muncy Creek, SR 405, 2014, 2044 & 2061 | 180 | 152 | Bridge Preservation - Federal | FD | NHPP | 2027-09-16 |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Interstate | 3 | Lycoming | 120114 | SR 180 ov Muncy Creek, SR 405, 2014, 2044 & 2061 | 180 | 152 | Bridge Preservation - Federal | CON | NHPP | 2027-09-16 |  | 0 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 2500000
Interstate | 3 | Montour | 120098 | Recessed Pavement Marking | 80 | 205 | Safety Improvement | CON | NHPP | 2024-11-07 | 2024-11-07 | 160950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160950
Interstate | 3 | Northumberland | 120048 | Recessed Pavement Marking Tape | 180 | 151 | Safety Improvement | CON | NHPP | 2024-11-07 | 2024-11-07 | 90336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90336
Interstate | 3 | Northumberland | 120097 | Recessed Pavement Marking Tape | 80 | 204 | Safety Improvement | CON | NHPP | 2024-11-07 | 2024-11-07 | 132815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132815
Interstate | 4 | Lackawanna | 69181 | I-84 ov LackRR/Roaring & 435 | 84 | 282 | Bridge Replacement | CON | NHPP | 2020-02-27 | 2020-02-27 | 6436321 | 3073679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9510000
Interstate | 4 | Lackawanna | 85791 | I-84 EB/WB I-4R Lacka/Wayne | 84 | 0 | Interstate Maintenance Program | PE | 581 | 2033-10-01 |  | 0 | 0 | 7092741 | 4500000 | 0 | 0 | 0 | 0 | 0 | 11592741
Interstate | 4 | Lackawanna | 85791 | I-84 EB/WB I-4R Lacka/Wayne | 84 | 0 | Interstate Maintenance Program | FD | 581 | 2033-10-01 |  | 0 | 0 | 0 | 0 | 4000000 | 5552419 | 0 | 0 | 0 | 9552419
Interstate | 4 | Lackawanna | 85791 | I-84 EB/WB I-4R Lacka/Wayne | 84 | 0 | Interstate Maintenance Program | CON | NHPP | 2033-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172915763 | 172915763
Interstate | 4 | Lackawanna | 87736 | I-81 NB/SB Moosic-Scranton I-4R Lacka | 81 | D46 | Interstate Maintenance Program | FD | NHPP | 2028-09-14 |  | 0 | 7161075 | 7161075 | 0 | 0 | 0 | 0 | 0 | 0 | 14322150
Interstate | 4 | Lackawanna | 87736 | I-81 NB/SB Moosic-Scranton I-4R Lacka | 81 | D46 | Interstate Maintenance Program | FD | 581 | 2028-09-14 |  | 0 | 795675 | 795675 | 0 | 0 | 0 | 0 | 0 | 0 | 1591350
Interstate | 4 | Lackawanna | 87736 | I-81 NB/SB Moosic-Scranton I-4R Lacka | 81 | D46 | Interstate Maintenance Program | ROW | NHPP | 2028-09-14 |  | 0 | 4173387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4173387
Interstate | 4 | Lackawanna | 87736 | I-81 NB/SB Moosic-Scranton I-4R Lacka | 81 | D46 | Interstate Maintenance Program | ROW | 581 | 2028-09-14 |  | 0 | 463710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 463710
Interstate | 4 | Lackawanna | 87736 | I-81 NB/SB Moosic-Scranton I-4R Lacka | 81 | D46 | Interstate Maintenance Program | UTL | NHPP | 2028-09-14 |  | 0 | 101296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101296
Interstate | 4 | Lackawanna | 87736 | I-81 NB/SB Moosic-Scranton I-4R Lacka | 81 | D46 | Interstate Maintenance Program | UTL | 581 | 2028-09-14 |  | 0 | 11255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11255
Interstate | 4 | Lackawanna | 87736 | I-81 NB/SB Moosic-Scranton I-4R Lacka | 81 | D46 | Interstate Maintenance Program | CON | NHPP | 2028-09-14 |  | 0 | 0 | 0 | 0 | 40000000 | 40000000 | 40000000 | 40000000 | 149926568 | 309926568
Interstate | 4 | Lackawanna | 91548 | I-81 Lacka CPR Dunmore | 81 | 0 | Interstate Maintenance Program | PE | NHPP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000
Interstate | 4 | Lackawanna | 91548 | I-81 Lacka CPR Dunmore | 81 | 0 | Interstate Maintenance Program | CON | NHPP | 2029-10-18 |  | 0 | 0 | 0 | 0 | 3600000 | 31000000 | 0 | 0 | 0 | 34600000
Interstate | 4 | Lackawanna | 92435 | I-81 NB/SB Preservation Pavement Replacement Lacka | 81 | 230 | Interstate Maintenance Program | FD | 581 | 2026-01-08 | 2026-01-08 | 3514204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3514204
Interstate | 4 | Lackawanna | 92435 | I-81 NB/SB Preservation Pavement Replacement Lacka | 81 | 230 | Interstate Maintenance Program | UTL | 581 | 2026-01-08 | 2026-01-08 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Interstate | 4 | Lackawanna | 92435 | I-81 NB/SB Preservation Pavement Replacement Lacka | 81 | 230 | Interstate Maintenance Program | CON | NHPP | 2026-01-08 | 2026-01-08 | 0 | 40000000 | 40000000 | 40000000 | 23002825 | 3997175 | 0 | 0 | 0 | 147000000
Interstate | 4 | Lackawanna | 94637 | I-84 EB/WB I-4R Lacka | 84 | 0 | Interstate Maintenance Program | PE | 581 | 2032-10-01 |  | 0 | 4504070 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 9004070
Interstate | 4 | Lackawanna | 94637 | I-84 EB/WB I-4R Lacka | 84 | 0 | Interstate Maintenance Program | FD | 581 | 2032-10-01 |  | 0 | 0 | 7164313 | 0 | 0 | 0 | 0 | 0 | 0 | 7164313
Interstate | 4 | Lackawanna | 94637 | I-84 EB/WB I-4R Lacka | 84 | 0 | Interstate Maintenance Program | CON | NHPP | 2032-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000000 | 160000000
Interstate | 4 | Lackawanna | 106323 | I-81 Mill/Fill Dickson City to Susq County Line | 81 | 248 | Highway Restoration | CON | NHPP | 2022-05-26 | 2022-05-26 | 6780000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6780000
Interstate | 4 | Lackawanna | 106682 | Scranton Beltway/Turnpike | 81 | 246 | Highway Reconstruction | CON | NHPP | 2031-11-07 |  | 0 | 0 | 0 | 0 | 10000000 | 10000000 | 10000000 | 10000000 | 0 | 40000000
Interstate | 4 | Lackawanna | 109304 | I-81 NB/SB Mill/Fill Lacka | 81 | 249 | Interstate Maintenance Program | CON | 581 | 2019-01-31 | 2019-01-31 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
Interstate | 4 | Lackawanna | 122379 | SR 6 Casey Highway Cameras/Message Signs | 6 | CAM | Intelligent Transportation System | CON | NHPP | 2025-10-09 | 2025-10-09 | 1068000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1068000
Interstate | 4 | Luzerne | 67443 | I-81 Dorrance Bridges | 81 | D52 | Bridge Replacement | CON | BRIP | 2024-12-12 | 2024-12-12 | 5513990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5513990
Interstate | 4 | Luzerne | 67443 | I-81 Dorrance Bridges | 81 | D52 | Bridge Replacement | CON | NHPP | 2024-12-12 | 2024-12-12 | 0 | 121000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121000
Interstate | 4 | Luzerne | 81910 | I-81 Luzerne County I-80 to Dorrance I-4R | 81 | 313 | Interstate Maintenance Program | PE | 581 | 2029-05-10 |  | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
Interstate | 4 | Luzerne | 81910 | I-81 Luzerne County I-80 to Dorrance I-4R | 81 | 313 | Interstate Maintenance Program | FD | BRIP | 2029-05-10 |  | 7000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000000
Interstate | 4 | Luzerne | 81910 | I-81 Luzerne County I-80 to Dorrance I-4R | 81 | 313 | Interstate Maintenance Program | CON | NHPP | 2029-05-10 |  | 0 | 0 | 0 | 20000000 | 40000000 | 40000000 | 43600000 | 10000000 | 60000000 | 213600000
Interstate | 4 | Luzerne | 91587 | I-80 EB over I-81 NB/SB | 80 | 350 | Bridge Replacement | CON | BRIP | 2026-01-15 | 2026-01-15 | 20031000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20031000
Interstate | 4 | Luzerne | 91587 | I-80 EB over I-81 NB/SB | 80 | 350 | Bridge Replacement | CON | NHPP | 2026-01-15 | 2026-01-15 | 2199000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2199000
Interstate | 4 | Luzerne | 91587 | I-80 EB over I-81 NB/SB | 80 | 350 | Bridge Replacement | CON | 185 | 2026-01-15 | 2026-01-15 | 2470000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2470000
Interstate | 4 | Luzerne | 106049 | Interstate 81 over Railroad | 81 | 361 | Bridge Replacement | CON | BRIP | 2027-01-14 |  | 0 | 0 | 24711811 | 0 | 0 | 0 | 0 | 0 | 0 | 24711811
Interstate | 4 | Luzerne | 107495 | I-80 Eastbound Reconstruction | 80 | 311 | Interstate Maintenance Program | PE | NHPP | 2026-07-02 |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Interstate | 4 | Luzerne | 107495 | I-80 Eastbound Reconstruction | 80 | 311 | Interstate Maintenance Program | UTL | 581 | 2026-07-02 |  | 0 | 92500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92500
Interstate | 4 | Luzerne | 107495 | I-80 Eastbound Reconstruction | 80 | 311 | Interstate Maintenance Program | CON | NHPP | 2026-07-02 |  | 0 | 25000000 | 38000000 | 50000000 | 30000000 | 0 | 0 | 0 | 0 | 143000000
Interstate | 4 | Luzerne | 111613 | Interstate 81 over West Foothills Drive | 81 | 362 | Bridge Restoration | CON | BRIP | 2025-12-04 | 2025-12-04 | 9544554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9544554
Interstate | 4 | Luzerne | 111613 | Interstate 81 over West Foothills Drive | 81 | 362 | Bridge Restoration | CON | NHPP | 2025-12-04 | 2025-12-04 | 0 | 3155446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3155446
Interstate | 4 | Luzerne | 111770 | I-80 EB/WB over SR 93 | 80 | 353 | Bridge Replacement | CON | BRIP | 2026-07-30 |  | 0 | 20240110 | 11000000 | 0 | 0 | 0 | 0 | 0 | 0 | 31240110
Interstate | 4 | Luzerne | 112307 | I-81 NB over I-80 WB Bridge | 81 | 363 | Bridge Restoration | CON | BRIP |  |  | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700000
Interstate | 4 | Luzerne | 115097 | I-81 Luzerne County Ashley to Arena I4R | 81 | 316 | Highway Reconstruction | FD | NHPP | 2028-09-14 |  | 11101500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11101500
Interstate | 4 | Luzerne | 115097 | I-81 Luzerne County Ashley to Arena I4R | 81 | 316 | Highway Reconstruction | FD | 581 | 2028-09-14 |  | 1233500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1233500
Interstate | 4 | Luzerne | 115097 | I-81 Luzerne County Ashley to Arena I4R | 81 | 316 | Highway Reconstruction | ROW | NHPP | 2028-09-14 |  | 0 | 16000000 | 8861595 | 0 | 0 | 0 | 0 | 0 | 0 | 24861595
Interstate | 4 | Luzerne | 115097 | I-81 Luzerne County Ashley to Arena I4R | 81 | 316 | Highway Reconstruction | ROW | 185 | 2028-09-14 |  | 0 | 1600000 | 1162393 | 0 | 0 | 0 | 0 | 0 | 0 | 2762393
Interstate | 4 | Luzerne | 115097 | I-81 Luzerne County Ashley to Arena I4R | 81 | 316 | Highway Reconstruction | CON | NHPP | 2028-09-14 |  | 0 | 0 | 0 | 0 | 36000000 | 36000000 | 36000000 | 36000000 | 108000000 | 252000000
Interstate | 4 | Luzerne | 115097 | I-81 Luzerne County Ashley to Arena I4R | 81 | 316 | Highway Reconstruction | CON | 185 | 2028-09-14 |  | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 4000000 | 4000000 | 12000000 | 28000000
Interstate | 4 | Luzerne | 116177 | SR 424 at Interstate 81 | 424 | 353 | Highway Restoration | PE | 185 | 2027-07-15 |  | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
Interstate | 4 | Luzerne | 116177 | SR 424 at Interstate 81 | 424 | 353 | Highway Restoration | FD | NHPP | 2027-07-15 |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Interstate | 4 | Luzerne | 116177 | SR 424 at Interstate 81 | 424 | 353 | Highway Restoration | FD | NHPP | 2027-07-15 |  | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
Interstate | 4 | Luzerne | 116177 | SR 424 at Interstate 81 | 424 | 353 | Highway Restoration | ROW | 581 | 2027-07-15 |  | 0 | 365000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365000
Interstate | 4 | Luzerne | 116177 | SR 424 at Interstate 81 | 424 | 353 | Highway Restoration | CON | NHPP | 2027-07-15 |  | 0 | 0 | 8262542 | 0 | 0 | 0 | 0 | 0 | 0 | 8262542
Interstate | 4 | Luzerne | 116177 | SR 424 at Interstate 81 | 424 | 353 | Highway Restoration | CON | NHPP | 2027-07-15 |  | 0 | 0 | 4000000 | 17737458 | 0 | 0 | 0 | 0 | 0 | 21737458
Interstate | 4 | Luzerne | 116496 | I-81 Luzerne County Arena to Lacka Line I-4R | 81 | 365 | Interstate Maintenance Program | PE | NHPP | 2032-03-15 |  | 0 | 626258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626258
Interstate | 4 | Luzerne | 116496 | I-81 Luzerne County Arena to Lacka Line I-4R | 81 | 365 | Interstate Maintenance Program | PE | 581 | 2032-03-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10438186 | 0 | 0 | 10438186
Interstate | 4 | Luzerne | 116496 | I-81 Luzerne County Arena to Lacka Line I-4R | 81 | 365 | Interstate Maintenance Program | FD | 581 | 2032-03-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8063498 | 0 | 8063498
Interstate | 4 | Luzerne | 116496 | I-81 Luzerne County Arena to Lacka Line I-4R | 81 | 365 | Interstate Maintenance Program | CON | NHPP | 2032-03-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000000 | 50000000
Interstate | 4 | Luzerne | 117834 | I-81 Luzerne County Hazleton to I-80 I-4R | 81 | 317 | Interstate Maintenance Program | PE | NHPP | 2029-03-15 |  | 0 | 4250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4250000
Interstate | 4 | Luzerne | 117834 | I-81 Luzerne County Hazleton to I-80 I-4R | 81 | 317 | Interstate Maintenance Program | FD | 581 | 2029-03-15 |  | 0 | 0 | 0 | 0 | 5500000 | 0 | 0 | 0 | 0 | 5500000
Interstate | 4 | Luzerne | 117834 | I-81 Luzerne County Hazleton to I-80 I-4R | 81 | 317 | Interstate Maintenance Program | CON | NHPP | 2029-03-15 |  | 0 | 0 | 0 | 0 | 0 | 20000000 | 20000000 | 20000000 | 140000000 | 200000000
Interstate | 4 | Luzerne | 117835 | I-81 Luzerne County Dorrance to Nuangola I-4R | 81 | 318 | Interstate Maintenance Program | PE | 581 | 2031-03-15 |  | 0 | 0 | 0 | 0 | 4400000 | 0 | 0 | 0 | 0 | 4400000
Interstate | 4 | Luzerne | 117835 | I-81 Luzerne County Dorrance to Nuangola I-4R | 81 | 318 | Interstate Maintenance Program | FD | 581 | 2031-03-15 |  | 0 | 0 | 0 | 0 | 0 | 5500000 | 0 | 0 | 0 | 5500000
Interstate | 4 | Luzerne | 117835 | I-81 Luzerne County Dorrance to Nuangola I-4R | 81 | 318 | Interstate Maintenance Program | CON | NHPP | 2031-03-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000000 | 20000000 | 160000000 | 200000000
Interstate | 4 | Luzerne | 117838 | I-81/ I-80 Concrete Pave Repairs Luzerne County | 81 | 338 | Interstate Maintenance Program | PE | 581 | 2026-09-03 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Interstate | 4 | Luzerne | 117838 | I-81/ I-80 Concrete Pave Repairs Luzerne County | 81 | 338 | Interstate Maintenance Program | CON | NHPP | 2026-09-03 |  | 4662124 | 7397876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12060000
Interstate | 4 | Luzerne | 123439 | I-80 WB Repair - Grinding | 80 | REP | Highway Restoration | CON | 581 | 2025-12-19 | 2024-12-12 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Interstate | 4 | Pike | 85766 | I-84 E&W I-4R MP 40 - E46 | 84 | 494 | Interstate Maintenance Program | CON | NHPP | 2021-12-09 | 2021-12-09 | 1387000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1387000
Interstate | 4 | Pike | 87795 | I-84 E&W I-4R E26 to E34 | 84 | 495 | Interstate Maintenance Program | CON | NHPP | 2022-05-12 | 2022-05-12 | 6120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6120000
Interstate | 4 | Pike | 122483 | Interstate Emergency Bridge Repairs - Pike | 84 | BRG | Bridge Restoration | CON | 185 | 2025-06-02 | 2022-05-12 | 1620000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620000
Interstate | 4 | Susquehanna | 75976 | I-81 Exit 219 | 81 | 590 | Interstate Maintenance Program | FD | NHPP | 2026-04-23 |  | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
Interstate | 4 | Susquehanna | 75976 | I-81 Exit 219 | 81 | 590 | Interstate Maintenance Program | UTL | 581 | 2026-04-23 |  | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Interstate | 4 | Susquehanna | 75976 | I-81 Exit 219 | 81 | 590 | Interstate Maintenance Program | CON | NHPP | 2026-04-23 |  | 0 | 29688660 | 10311340 | 15000000 | 0 | 0 | 0 | 0 | 0 | 55000000
Interstate | 4 | Susquehanna | 109306 | I-81 Mill/Fill Lackawanna Line to New Milford | 81 | 542 | Highway Restoration | CON | NHPP | 2025-02-27 | 2025-02-27 | 40474800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40474800
Interstate | 4 | Susquehanna | 109306 | I-81 Mill/Fill Lackawanna Line to New Milford | 81 | 542 | Highway Restoration | CON | 581 | 2025-02-27 | 2025-02-27 | 4000000 | 0 | 497200 | 0 | 0 | 0 | 0 | 0 | 0 | 4497200
Interstate | 4 | Wayne | 122604 | Interstate 84 Pipe | 84 | REP | Interstate Maintenance Program | CON | 581 | 2025-06-17 | 2020-02-27 | 200000 | 1550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000
Interstate | 5 | Berks | 10605 | I-78 Weigh Station | 78 | SPP | Safety Improvement | CON | NHPP | 2026-08-27 |  | 0 | 7000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000000
Interstate | 5 | Berks | 72807 | I-78 Shrtlesville to Hamb - Resurf | 78 | 22M | Preventive Maintenance | CON | NHPP | 2024-08-22 | 2024-09-12 | 15075169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15075169
Interstate | 5 | Berks | 72807 | I-78 Shrtlesville to Hamb - Resurf | 78 | 22M | Preventive Maintenance | CON | SXF | 2024-08-22 | 2024-09-12 | 21086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21086
Interstate | 5 | Berks | 112354 | Break and Seat SR 568 to SR 422 I/C | 176 | 09M | Highway Restoration | PE | NHPP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
Interstate | 5 | Berks | 112354 | Break and Seat SR 568 to SR 422 I/C | 176 | 09M | Highway Restoration | FD | NHPP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
Interstate | 5 | Berks | 112354 | Break and Seat SR 568 to SR 422 I/C | 176 | 09M | Highway Restoration | ROW | NHPP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
Interstate | 5 | Berks | 112354 | Break and Seat SR 568 to SR 422 I/C | 176 | 09M | Highway Restoration | UTL | NHPP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000
Interstate | 5 | Berks | 112354 | Break and Seat SR 568 to SR 422 I/C | 176 | 09M | Highway Restoration | CON | NHPP | 2031-01-01 |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 25183895 | 0 | 0 | 26183895
Interstate | 5 | Berks | 120121 | Berks County I-78 Concrete Patching | 78 | 32M | Interstate Maintenance Program | CON | NHPP | 2024-04-01 | 2023-04-13 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000
Interstate | 5 | Berks | 120372 | I-78 Grimes Interchange Removal | 78 | 33M | Interstate Maintenance Program | FD | NHPP | 2026-08-27 |  | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
Interstate | 5 | Berks | 120372 | I-78 Grimes Interchange Removal | 78 | 33M | Interstate Maintenance Program | ROW | NHPP | 2026-08-27 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Interstate | 5 | Berks | 120372 | I-78 Grimes Interchange Removal | 78 | 33M | Interstate Maintenance Program | CON | NHPP | 2026-08-27 |  | 0 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000
Interstate | 5 | Carbon | 72746 | I-80 Bridge Improvements | 80 | 19B | Interstate Maintenance Program | PE | 185 | 2027-01-14 |  | 0 | 1038052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1038052
Interstate | 5 | Carbon | 72746 | I-80 Bridge Improvements | 80 | 19B | Interstate Maintenance Program | ROW | 185 | 2027-01-14 |  | 496620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496620
Interstate | 5 | Carbon | 72746 | I-80 Bridge Improvements | 80 | 19B | Interstate Maintenance Program | CON | 185 | 2027-01-14 |  | 0 | 0 | 14000000 | 0 | 0 | 0 | 0 | 0 | 0 | 14000000
Interstate | 5 | Lehigh | 92780 | I-78 Recon-Berks County Line to SR 100 | 78 | 19M | Interstate Maintenance Program | FD | 581 | 2033-06-09 |  | 0 | 0 | 4000000 | 8033151 | 0 | 0 | 0 | 0 | 0 | 12033151
Interstate | 5 | Lehigh | 92780 | I-78 Recon-Berks County Line to SR 100 | 78 | 19M | Interstate Maintenance Program | ROW | 581 | 2033-06-09 |  | 0 | 0 | 0 | 0 | 6754247 | 6000000 | 0 | 0 | 0 | 12754247
Interstate | 5 | Lehigh | 92780 | I-78 Recon-Berks County Line to SR 100 | 78 | 19M | Interstate Maintenance Program | UTL | 581 | 2033-06-09 |  | 0 | 0 | 0 | 0 | 3095690 | 0 | 0 | 0 | 0 | 3095690
Interstate | 5 | Lehigh | 92780 | I-78 Recon-Berks County Line to SR 100 | 78 | 19M | Interstate Maintenance Program | CON | NHPP | 2033-06-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000000 | 40000000
Interstate | 5 | Lehigh | 120648 | I-78 Berks County Line to SR 100 Patching | 78 | 25M | Interstate Maintenance Program | CON | NHPP | 2024-07-11 | 2024-07-11 | 863040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863040
Interstate | 5 | Lehigh | 122987 | LVTS Interstate Truck and Safety Study | 78 | DPS | Study Phase of Project | STUDY | 581 |  |  | 879994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 879994
Interstate | 5 | Monroe | 57921 | I-80/Exit 308 Realignment | 80 | 05S | Highway Restoration | CON | NHPP | 2021-12-09 | 2021-12-09 | 3330572 | 1383657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4714229
Interstate | 5 | Monroe | 76357 | I-80 Reconstruction-Monroe | 80 | 17M | Highway Reconstruction | ROW | 581 | 2032-12-16 |  | 10000000 | 7000000 | 9000000 | 8000000 | 0 | 0 | 0 | 0 | 0 | 34000000
Interstate | 5 | Monroe | 76357 | I-80 Reconstruction-Monroe | 80 | 17M | Highway Reconstruction | UTL | NHPP | 2032-12-16 |  | 0 | 0 | 0 | 2700000 | 0 | 0 | 0 | 0 | 0 | 2700000
Interstate | 5 | Monroe | 76357 | I-80 Reconstruction-Monroe | 80 | 17M | Highway Reconstruction | UTL | 581 | 2032-12-16 |  | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000
Interstate | 5 | Monroe | 76357 | I-80 Reconstruction-Monroe | 80 | 17M | Highway Reconstruction | CON | NHPP | 2032-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259000000 | 259000000
Interstate | 5 | Monroe | 87649 | I-80 - I-380 to Tannersville Resurface | 80 | 23M | Highway Restoration | CON | NHPP | 2021-05-06 | 2021-05-06 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Interstate | 5 | Monroe | 112351 | I 80 Phase 2 - Reconstruction (Bartonsville) | 80 | 26M | Highway Reconstruction | PE | 581 | 2030-03-28 |  | 860000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860000
Interstate | 5 | Monroe | 112351 | I 80 Phase 2 - Reconstruction (Bartonsville) | 80 | 26M | Highway Reconstruction | FD | 581 | 2030-03-28 |  | 0 | 5000000 | 11390905 | 0 | 0 | 0 | 0 | 0 | 0 | 16390905
Interstate | 5 | Monroe | 112351 | I 80 Phase 2 - Reconstruction (Bartonsville) | 80 | 26M | Highway Reconstruction | ROW | 581 | 2030-03-28 |  | 0 | 0 | 0 | 0 | 13911289 | 0 | 0 | 0 | 0 | 13911289
Interstate | 5 | Monroe | 112351 | I 80 Phase 2 - Reconstruction (Bartonsville) | 80 | 26M | Highway Reconstruction | UTL | 581 | 2030-03-28 |  | 0 | 0 | 0 | 3376526 | 0 | 0 | 0 | 0 | 0 | 3376526
Interstate | 5 | Monroe | 112351 | I 80 Phase 2 - Reconstruction (Bartonsville) | 80 | 26M | Highway Reconstruction | CON | NHPP | 2030-03-28 |  | 0 | 0 | 0 | 0 | 0 | 40000000 | 30000000 | 40000000 | 210000000 | 320000000
Interstate | 5 | Monroe | 112355 | I-380 Bridge Improvements | 380 | 07B | Bridge Replacement | PE | 185 | 2028-11-09 |  | 217000 | 217000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434000
Interstate | 5 | Monroe | 112355 | I-380 Bridge Improvements | 380 | 07B | Bridge Replacement | FD | 185 | 2028-11-09 |  | 0 | 0 | 546000 | 0 | 0 | 0 | 0 | 0 | 0 | 546000
Interstate | 5 | Monroe | 112355 | I-380 Bridge Improvements | 380 | 07B | Bridge Replacement | CON | 185 | 2028-11-09 |  | 5444800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5444800
Interstate | 5 | Monroe | 118999 | I-80 Sec 17M Breakout #1 (Exit 303) | 80 | BO1 | Highway Reconstruction | CON | NHPP | 2026-07-02 |  | 0 | 40000000 | 40000000 | 40000000 | 34457600 | 25000000 | 30000000 | 0 | 0 | 209457600
Interstate | 5 | Monroe | 119000 | Interstate 80 Sec 17M Breakout #2 (Exit 304/305) | 80 | BO2 | Highway Reconstruction | UTL | NHPP | 2029-11-08 |  | 0 | 2700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700000
Interstate | 5 | Monroe | 119000 | Interstate 80 Sec 17M Breakout #2 (Exit 304/305) | 80 | BO2 | Highway Reconstruction | UTL | 581 | 2029-11-08 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Interstate | 5 | Monroe | 119000 | Interstate 80 Sec 17M Breakout #2 (Exit 304/305) | 80 | BO2 | Highway Reconstruction | CON | NHPP | 2029-11-08 |  | 0 | 0 | 0 | 0 | 0 | 20000000 | 15000000 | 20000000 | 204000000 | 259000000
Interstate | 5 | Monroe | 122198 | Interstate 80 Demo | 80 | DEM | Highway Reconstruction | CON | NHPP | 2025-07-24 | 2025-07-24 | 567525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 567525
Interstate | 5 | Northampton | 75835 | I-78 - 33 Interchange to Morgan Hill | 78 | 12M | Interstate Maintenance Program | PE | NHPP |  |  | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
Interstate | 5 | Northampton | 75835 | I-78 - 33 Interchange to Morgan Hill | 78 | 12M | Interstate Maintenance Program | FD | NHPP |  |  | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000
Interstate | 5 | Northampton | 75835 | I-78 - 33 Interchange to Morgan Hill | 78 | 12M | Interstate Maintenance Program | CON | NHPP |  |  | 0 | 0 | 0 | 2300000 | 14700000 | 0 | 0 | 0 | 0 | 17000000
Interstate | 5 | Northampton | 75849 | Dual Bridges over Easton Road | 78 | 11B | Interstate Maintenance Program | CON | 185 | 2024-09-26 | 2024-09-26 | 10609000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10609000
Interstate | 5 | Northampton | 109318 | I-78 WB - Easton Rd to SR 33 | 78 | 10M | Interstate Maintenance Program | CON | NHPP | 2026-08-27 |  | 0 | 9000000 | 7319878 | 0 | 0 | 0 | 0 | 0 | 0 | 16319878
Interstate | 5 | Northampton | 116518 | i-78 LVTS Bridge Breakout 2 | 78 | 17B | Preventive Maintenance | PE | NHPP | 2029-06-01 |  | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 900000
Interstate | 5 | Northampton | 116518 | i-78 LVTS Bridge Breakout 2 | 78 | 17B | Preventive Maintenance | FD | NHPP | 2029-06-01 |  | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 900000
Interstate | 5 | Northampton | 116518 | i-78 LVTS Bridge Breakout 2 | 78 | 17B | Preventive Maintenance | CON | NHPP | 2029-06-01 |  | 0 | 0 | 0 | 1400000 | 7900000 | 0 | 0 | 0 | 0 | 9300000
Interstate | 5 | Northampton | 120146 | District Wide Interstate Concrete Patching | 78 | DCP | Interstate Maintenance Program | CON | NHPP | 2025-09-25 | 2025-09-25 | 4740600 | 649452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5390052
Interstate | 5 | Schuylkill | 85911 | I-81 - Pine Grove to Minersville Resurface | 81 | 25M | Interstate Maintenance Program | CON | NHPP | 2023-04-27 | 2023-04-27 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
Interstate | 6 | Delaware | 15477 | I-95/US 322 Interchange Improvements | 95 | 322 | Interstate Maintenance Program | ROW | 581 |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
Interstate | 6 | Delaware | 15477 | I-95/US 322 Interchange Improvements | 95 | 322 | Interstate Maintenance Program | CON | NHPP |  |  | 0 | 0 | 0 | 0 | 0 | 15000000 | 18000000 | 35000000 | 55000000 | 123000000
Interstate | 6 | Delaware | 104821 | I-476 Travel Management | 476 | HSR | Congestion Reduction | PE | NHPP | 2028-05-25 |  | 900000 | 500900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400900
Interstate | 6 | Delaware | 104821 | I-476 Travel Management | 476 | HSR | Congestion Reduction | FD | 581 | 2028-05-25 |  | 0 | 2000000 | 2000000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 5500000
Interstate | 6 | Delaware | 104821 | I-476 Travel Management | 476 | HSR | Congestion Reduction | ROW | 581 | 2028-05-25 |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Interstate | 6 | Delaware | 104821 | I-476 Travel Management | 476 | HSR | Congestion Reduction | UTL | 581 | 2028-05-25 |  | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Interstate | 6 | Delaware | 104821 | I-476 Travel Management | 476 | HSR | Congestion Reduction | CON | NHPP | 2028-05-25 |  | 0 | 0 | 24000000 | 24000000 | 0 | 0 | 0 | 0 | 0 | 48000000
Interstate | 6 | Delaware | 112298 | I-476 Preventative Maintenance: I-76 to I-95 (C) | 476 | IMP | Interstate Maintenance Program | CON | NHPP | 2023-05-25 | 2023-05-25 | 0 | 6210000 | 6210001 | 0 | 0 | 0 | 0 | 0 | 0 | 12420001
Interstate | 6 | Delaware | 112298 | I-476 Preventative Maintenance: I-76 to I-95 (C) | 476 | IMP | Interstate Maintenance Program | CON | 581 | 2023-05-25 | 2023-05-25 | 0 | 961250 | 961250 | 0 | 0 | 0 | 0 | 0 | 0 | 1922500
Interstate | 6 | Delaware | 116225 | I-476 Advance Travel Management(C) | 476 | ATC | Interstate Maintenance Program | CON | NHPP | 2023-10-19 | 2023-10-19 | 0 | 111400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111400
Interstate | 6 | Montgomery | 106662 | I-76 Integrated Corridor Management | 76 | ICM | Congestion Reduction | PE | NHPP |  |  | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
Interstate | 6 | Montgomery | 116838 | I-76 Flex Lanes: US 202 to I-476 | 76 | FL1 | Congestion Reduction | FD | NHPP | 2030-04-11 |  | 0 | 7500000 | 7500000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000
Interstate | 6 | Montgomery | 116838 | I-76 Flex Lanes: US 202 to I-476 | 76 | FL1 | Congestion Reduction | ROW | NHPP | 2030-04-11 |  | 0 | 0 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 10000000
Interstate | 6 | Montgomery | 116838 | I-76 Flex Lanes: US 202 to I-476 | 76 | FL1 | Congestion Reduction | UTL | NHPP | 2030-04-11 |  | 0 | 6000000 | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000000
Interstate | 6 | Montgomery | 116838 | I-76 Flex Lanes: US 202 to I-476 | 76 | FL1 | Congestion Reduction | CON | NHPP | 2030-04-11 |  | 0 | 0 | 0 | 0 | 30000000 | 30000000 | 30000000 | 50000000 | 140000000 | 280000000
Interstate | 6 | Montgomery | 116839 | I-76 Flex Lane WB: US 1-Belmont Ave | 76 | FL3 | Congestion Reduction | FD | NHPP | 2029-06-07 |  | 0 | 11000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000000
Interstate | 6 | Montgomery | 116839 | I-76 Flex Lane WB: US 1-Belmont Ave | 76 | FL3 | Congestion Reduction | ROW | NHPP | 2029-06-07 |  | 0 | 5000000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 8000000
Interstate | 6 | Montgomery | 116839 | I-76 Flex Lane WB: US 1-Belmont Ave | 76 | FL3 | Congestion Reduction | UTL | NHPP | 2029-06-07 |  | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000
Interstate | 6 | Montgomery | 116839 | I-76 Flex Lane WB: US 1-Belmont Ave | 76 | FL3 | Congestion Reduction | CON | NHPP | 2029-06-07 |  | 0 | 0 | 0 | 29185000 | 30815000 | 25000000 | 30000000 | 15000000 | 0 | 130000000
Interstate | 6 | Montgomery | 119500 | Interstate ITS Contract 2023(C) |  |  | Intelligent Transportation System | CON | NHPP | 2023-06-08 | 2023-06-08 | 185770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185770
Interstate | 6 | Philadelphia | 17821 | I-95: Shackamaxon - Ann | 95 | GIR | Highway Reconstruction | PE | NHPP |  |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Interstate | 6 | Philadelphia | 17821 | I-95: Shackamaxon - Ann | 95 | GIR | Highway Reconstruction | PE | 581 |  |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Interstate | 6 | Philadelphia | 17821 | I-95: Shackamaxon - Ann | 95 | GIR | Highway Reconstruction | FD | NHPP |  |  | 19200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200000
Interstate | 6 | Philadelphia | 17821 | I-95: Shackamaxon - Ann | 95 | GIR | Highway Reconstruction | FD | 581 |  |  | 4800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800000
Interstate | 6 | Philadelphia | 46959 | I-95 Design Support Serv | 95 | DSM | Bridge Restoration | PE | NHPP |  |  | 0 | 0 | 0 | 0 | 1600000 | 1600000 | 0 | 0 | 0 | 3200000
Interstate | 6 | Philadelphia | 46959 | I-95 Design Support Serv | 95 | DSM | Bridge Restoration | PE | 581 |  |  | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 0 | 0 | 0 | 2400000
Interstate | 6 | Philadelphia | 47394 | I-95: Levick St - Bleigh | 95 | CPR | Interstate Maintenance Program | ROW | NHPP |  | 2022-02-03 | 162143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162143
Interstate | 6 | Philadelphia | 47811 | I-95 & Bridge Street Interchange DESIGN | 95 | BSR | Interstate Maintenance Program | FD | NHPP |  |  | 5670000 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10170000
Interstate | 6 | Philadelphia | 47811 | I-95 & Bridge Street Interchange DESIGN | 95 | BSR | Interstate Maintenance Program | FD | 581 |  |  | 630000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1130000
Interstate | 6 | Philadelphia | 47812 | I-95 & Betsy Ross Bridge Interchange DESIGN | 95 | BRI | Interstate Maintenance Program | FD | NHPP |  |  | 5600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600000
Interstate | 6 | Philadelphia | 47812 | I-95 & Betsy Ross Bridge Interchange DESIGN | 95 | BRI | Interstate Maintenance Program | FD | 581 |  |  | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
Interstate | 6 | Philadelphia | 47813 | I-95: Ann St - Wheatsheaf | 95 | AFC | Interstate Maintenance Program | FD | 185 |  |  | 6000000 | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000000
Interstate | 6 | Philadelphia | 47813 | I-95: Ann St - Wheatsheaf | 95 | AFC | Interstate Maintenance Program | FD | 581 |  |  | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
Interstate | 6 | Philadelphia | 79828 | I-95 (NB): Race - Shackamaxon | 95 | GR5 | Highway Reconstruction | UTL | 185 | 2028-06-29 |  | 8441316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8441316
Interstate | 6 | Philadelphia | 79828 | I-95 (NB): Race - Shackamaxon | 95 | GR5 | Highway Reconstruction | CON | BRIP | 2028-06-29 |  | 0 | 0 | 12000000 | 0 | 0 | 4018304 | 4185000 | 4185000 | 10542696 | 34931000
Interstate | 6 | Philadelphia | 79828 | I-95 (NB): Race - Shackamaxon | 95 | GR5 | Highway Reconstruction | CON | NFP | 2028-06-29 |  | 0 | 0 | 60360000 | 0 | 0 | 0 | 0 | 0 | 0 | 60360000
Interstate | 6 | Philadelphia | 79828 | I-95 (NB): Race - Shackamaxon | 95 | GR5 | Highway Reconstruction | CON | NHPP | 2028-06-29 |  | 0 | 0 | 0 | 20000000 | 40000000 | 40000000 | 30000000 | 40701000 | 40069000 | 210770000
Interstate | 6 | Philadelphia | 79903 | I-95: Betsy Ross Ramps(C) | 95 | BR0 | Interstate Maintenance Program | CON | NHPP | 2014-10-30 | 2014-10-31 | 502100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502100
Interstate | 6 | Philadelphia | 79905 | I-95: Betsy Ross Mainln NB(C) | 95 | BR3 | Highway Reconstruction | ROW | 185 | 2025-01-30 | 2025-01-30 | 3000000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000
Interstate | 6 | Philadelphia | 79905 | I-95: Betsy Ross Mainln NB(C) | 95 | BR3 | Highway Reconstruction | ROW | 581 | 2025-01-30 | 2025-01-30 | 1000000 | 1000000 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000
Interstate | 6 | Philadelphia | 79905 | I-95: Betsy Ross Mainln NB(C) | 95 | BR3 | Highway Reconstruction | CON | BRIP | 2025-01-30 | 2025-01-30 | 9895189 | 18000000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000000 | 57895189
Interstate | 6 | Philadelphia | 79905 | I-95: Betsy Ross Mainln NB(C) | 95 | BR3 | Highway Reconstruction | CON | NHPP | 2025-01-30 | 2025-01-30 | 120168321 | 10000000 | 18000000 | 8543201 | 30000000 | 30000000 | 30000000 | 35800000 | 47593289 | 330104811
Interstate | 6 | Philadelphia | 79910 | I-95: Margaret-Carver (C) | 95 | BS2 | Highway Reconstruction | CON | NHPP | 2022-06-30 | 2022-06-30 | 92936709 | 3745077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96681786
Interstate | 6 | Philadelphia | 81225 | Girard Point Bridge Rehab - Phases 1 & 2(C) | 95 | GP1 | Bridge Restoration | CON | NHPP | 2025-11-06 | 2025-11-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000000 | 140000000 | 175000000
Interstate | 6 | Philadelphia | 81225 | Girard Point Bridge Rehab - Phases 1 & 2(C) | 95 | GP1 | Bridge Restoration | CON | BRIP | 2025-11-06 | 2025-11-06 | 0 | 1972189 | 0 | 32189546 | 4185000 | 0 | 0 | 0 | 0 | 38346735
Interstate | 6 | Philadelphia | 81225 | Girard Point Bridge Rehab - Phases 1 & 2(C) | 95 | GP1 | Bridge Restoration | CON | NHPP | 2025-11-06 | 2025-11-06 | 0 | 34560000 | 27560000 | 19120000 | 30375000 | 0 | 0 | 0 | 22838267 | 134453267
Interstate | 6 | Philadelphia | 81225 | Girard Point Bridge Rehab - Phases 1 & 2(C) | 95 | GP1 | Bridge Restoration | CON | 185 | 2025-11-06 | 2025-11-06 | 0 | 0 | 0 | 1456000 | 0 | 0 | 0 | 0 | 2384000 | 3840000
Interstate | 6 | Philadelphia | 81225 | Girard Point Bridge Rehab - Phases 1 & 2(C) | 95 | GP1 | Bridge Restoration | CON | 581 | 2025-11-06 | 2025-11-06 | 0 | 3840000 | 3840000 | 3840000 | 3840000 | 0 | 0 | 0 | 0 | 15360000
Interstate | 6 | Philadelphia | 92289 | I-95 Consultant Mgmt | 95 | MGR | Interstate Maintenance Program | PE | NHPP |  |  | 2700000 | 2700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400000
Interstate | 6 | Philadelphia | 92289 | I-95 Consultant Mgmt | 95 | MGR | Interstate Maintenance Program | PE | 581 |  |  | 0 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Interstate | 6 | Philadelphia | 103553 | I-95 (SB): Race-Shackamaxon | 95 | GR6 | Highway Reconstruction | CON | NHPP | 2026-12-10 |  | 0 | 30000000 | 30000000 | 45000000 | 30000000 | 30000000 | 30000000 | 30000000 | 70000000 | 295000000
Interstate | 6 | Philadelphia | 103555 | I-95 Corridor ITS (C) | 95 | GR8 | Intelligent Transportation System | CON | NHPP | 2021-09-16 | 2021-09-16 | 3500000 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000000
Interstate | 6 | Philadelphia | 103556 | I-95 ATMS (GR9) | 95 | GR9 | Intelligent Transportation System | UTL | 581 | 2029-10-25 |  | 0 | 0 | 0 | 0 | 1400000 | 0 | 0 | 0 | 0 | 1400000
Interstate | 6 | Philadelphia | 103556 | I-95 ATMS (GR9) | 95 | GR9 | Intelligent Transportation System | CON | NHPP | 2029-10-25 |  | 0 | 0 | 0 | 0 | 0 | 22500000 | 22500000 | 23400000 | 0 | 68400000
Interstate | 6 | Philadelphia | 103556 | I-95 ATMS (GR9) | 95 | GR9 | Intelligent Transportation System | CON | 581 | 2029-10-25 |  | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000 | 2600000 | 0 | 7600000
Interstate | 6 | Philadelphia | 103557 | I-95: Tioga St north to Wheatsheaf Ln(C) | 95 | AF3 | Highway Reconstruction | UTL | NHPP | 2025-12-11 | 2025-12-11 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Interstate | 6 | Philadelphia | 103557 | I-95: Tioga St north to Wheatsheaf Ln(C) | 95 | AF3 | Highway Reconstruction | CON | NHPP | 2025-12-11 | 2025-12-11 | 0 | 41316520 | 43379647 | 36370542 | 41991644 | 45443438 | 39814729 | 15000000 | 78189893 | 341506413
Interstate | 6 | Philadelphia | 103558 | I-95: Allegheny Ave to Tioga St | 95 | AF4 | Highway Restoration | ROW | 581 | 2029-06-28 |  | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 600000
Interstate | 6 | Philadelphia | 103558 | I-95: Allegheny Ave to Tioga St | 95 | AF4 | Highway Restoration | UTL | 581 | 2029-06-28 |  | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Interstate | 6 | Philadelphia | 103558 | I-95: Allegheny Ave to Tioga St | 95 | AF4 | Highway Restoration | CON | NFP | 2029-06-28 |  | 0 | 0 | 0 | 0 | 0 | 60360000 | 0 | 0 | 0 | 60360000
Interstate | 6 | Philadelphia | 103558 | I-95: Allegheny Ave to Tioga St | 95 | AF4 | Highway Restoration | CON | NHPP | 2029-06-28 |  | 0 | 0 | 0 | 0 | 30000000 | 0 | 30000000 | 50000000 | 29700000 | 139700000
Interstate | 6 | Philadelphia | 103559 | I-95 Btsy Rss Mainln SB | 95 | BR4 | Highway Reconstruction | UTL | 581 | 2029-01-25 |  | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Interstate | 6 | Philadelphia | 103559 | I-95 Btsy Rss Mainln SB | 95 | BR4 | Highway Reconstruction | CON | NFP | 2029-01-25 |  | 0 | 0 | 0 | 60360000 | 60360000 | 0 | 0 | 0 | 0 | 120720000
Interstate | 6 | Philadelphia | 103559 | I-95 Btsy Rss Mainln SB | 95 | BR4 | Highway Reconstruction | CON | NHPP | 2029-01-25 |  | 0 | 0 | 0 | 0 | 15000000 | 46300000 | 8000000 | 0 | 0 | 69300000
Interstate | 6 | Philadelphia | 103560 | I-95 Betsy Ross Conrail Brdgs | 95 | BR5 | Bridge Restoration | ROW | 581 | 2027-01-28 |  | 0 | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000
Interstate | 6 | Philadelphia | 103560 | I-95 Betsy Ross Conrail Brdgs | 95 | BR5 | Bridge Restoration | UTL | 581 | 2027-01-28 |  | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Interstate | 6 | Philadelphia | 103560 | I-95 Betsy Ross Conrail Brdgs | 95 | BR5 | Bridge Restoration | CON | NHPP | 2027-01-28 |  | 0 | 0 | 23000000 | 23000000 | 0 | 0 | 0 | 0 | 0 | 46000000
Interstate | 6 | Philadelphia | 103561 | I95 Betsy Ross Int. Drainage | 95 | BR6 | Highway Reconstruction | CON | NHPP |  |  | 0 | 0 | 0 | 8100000 | 0 | 0 | 0 | 0 | 0 | 8100000
Interstate | 6 | Philadelphia | 112299 | I-76: Rte 1- I 676 Paving/Guiderail (C) | 76 | IMP | Highway Restoration | CON | NHPP | 2023-02-02 | 2023-02-02 | 0 | 10000000 | 5174673 | 0 | 0 | 0 | 0 | 0 | 0 | 15174673
Interstate | 6 | Philadelphia | 113762 | Broad Street Interchange | 95 | BSI | Study Phase of Project | STUDY | NHPP |  |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Interstate | 6 | Philadelphia | 113763 | Walt Whitman Bridge Interchange | 95 | WWB | Study Phase of Project | STUDY | NHPP |  |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Interstate | 6 | Philadelphia | 113764 | Penns Landing Interchange | 95 | PLI | Study Phase of Project | STUDY | NHPP |  |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Interstate | 6 | Philadelphia | 113765 | Christopher Columbus Blvd Corridor | 95 | CCB | Study Phase of Project | STUDY | NHPP |  |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Interstate | 6 | Philadelphia | 115687 | I-95: Allegheny&Castor Ave Int. Connection | 95 | AFR | Highway Reconstruction | ROW | NHPP |  | 2025-12-11 | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000000
Interstate | 6 | Philadelphia | 115805 | I95 Br Rehab: Island Av-Phl Navy Yard | 95 | GPB | Bridge Restoration | PE | NHPP |  |  | 2000000 | 2500000 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 9000000
Interstate | 6 | Philadelphia | 115805 | I95 Br Rehab: Island Av-Phl Navy Yard | 95 | GPB | Bridge Restoration | PE | 185 |  |  | 250000 | 250000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Interstate | 6 | Philadelphia | 116391 | I-95 Bridge Improvements(C) | 95 | MB5 | Bridge Restoration | CON | 185 | 2023-12-14 | 2023-12-14 | 0 | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000
Interstate | 6 | Philadelphia | 117934 | I-95 Traffic Forecasts |  |  | Planning/Research/Administration | PRA | STP |  |  | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000
Interstate | 8 | Cumberland | 116479 | I-81 Culvert | 81 | 096 | Bridge Replacement | FD | 185 | 2027-01-28 |  | 0 | 321159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321159
Interstate | 8 | Cumberland | 116479 | I-81 Culvert | 81 | 096 | Bridge Replacement | CON | 185 | 2027-01-28 |  | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000
Interstate | 8 | Cumberland | 116481 | I-81 over Stone House Rd | 81 | 097 | Bridge Preservation - State Funded | FD | 185 | 2027-01-28 |  | 729773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729773
Interstate | 8 | Cumberland | 116481 | I-81 over Stone House Rd | 81 | 097 | Bridge Preservation - State Funded | CON | BRIP | 2027-01-28 |  | 3360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3360000
Interstate | 8 | Cumberland | 117908 | I-81 Implementation Plan |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000000 | 250000000
Interstate | 8 | Cumberland | 119677 | I-81 MM 47 to 52 Asphalt Patching and Overlay | 81 | 104 | Highway Restoration | PE | 581 | 2025-08-21 | 2025-08-21 | 44547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44547
Interstate | 8 | Cumberland | 119677 | I-81 MM 47 to 52 Asphalt Patching and Overlay | 81 | 104 | Highway Restoration | CON | 581 | 2025-08-21 | 2025-08-21 | 5003405 | 6718755 | 2456112 | 0 | 0 | 0 | 0 | 0 | 0 | 14178272
Interstate | 8 | Dauphin | 92931 | Eisenhower Interchange | 83 | 078 | Highway Reconstruction | FD | 581 | 2027-12-09 |  | 367993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367993
Interstate | 8 | Dauphin | 92931 | Eisenhower Interchange | 83 | 078 | Highway Reconstruction | ROW | NHPP | 2027-12-09 |  | 14500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14500000
Interstate | 8 | Dauphin | 92931 | Eisenhower Interchange | 83 | 078 | Highway Reconstruction | UTL | 581 | 2027-12-09 |  | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000
Interstate | 8 | Dauphin | 92931 | Eisenhower Interchange | 83 | 078 | Highway Reconstruction | CON | NHPP | 2027-12-09 |  | 0 | 61432519 | 56677372 | 22950000 | 16000000 | 9274175 | 0 | 0 | 4050000 | 170384066
Interstate | 8 | Dauphin | 92931 | Eisenhower Interchange | 83 | 078 | Highway Reconstruction | CON | NHPP | 2027-12-09 |  | 0 | 0 | 2189086 | 20000000 | 0 | 0 | 0 | 0 | 31000914 | 53190000
Interstate | 8 | Dauphin | 97828 | I-83 East Shore Section 3 | 83 | 079 | Highway Reconstruction | CON | NHPP | 2023-08-24 | 2023-08-24 | 958580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 958580
Interstate | 8 | Dauphin | 97828 | I-83 East Shore Section 3 | 83 | 079 | Highway Reconstruction | CON | NHPP | 2023-08-24 | 2023-08-24 | 199627 | 2049320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2248947
Interstate | 8 | Dauphin | 97828 | I-83 East Shore Section 3 | 83 | 079 | Highway Reconstruction | CON | 581 | 2023-08-24 | 2023-08-24 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
Interstate | 8 | Dauphin | 113357 | I-83 East Shore Section 3B | 83 | B79 | Highway Reconstruction | FD | 581 | 2025-09-11 | 2025-09-11 | 93448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93448
Interstate | 8 | Dauphin | 113357 | I-83 East Shore Section 3B | 83 | B79 | Highway Reconstruction | CON | NHPP | 2025-09-11 | 2025-09-11 | 74890000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74890000
Interstate | 8 | Dauphin | 113357 | I-83 East Shore Section 3B | 83 | B79 | Highway Reconstruction | CON | NFP | 2025-09-11 | 2025-09-11 | 59177000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59177000
Interstate | 8 | Dauphin | 113357 | I-83 East Shore Section 3B | 83 | B79 | Highway Reconstruction | CON | NHPP | 2025-09-11 | 2025-09-11 | 31823000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31823000
Interstate | 8 | Dauphin | 113357 | I-83 East Shore Section 3B | 83 | B79 | Highway Reconstruction | CON | 581 | 2025-09-11 | 2025-09-11 | 163040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163040
Interstate | 8 | Dauphin | 113376 | I-83 East Shore Section 3C | 83 | C79 | Highway Reconstruction | PE | NHPP | 2026-08-20 |  | 880000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880000
Interstate | 8 | Dauphin | 113378 | Eisenhower Interchange B | 83 | B78 | Highway Reconstruction | FD | 581 | 2031-01-09 |  | 4500000 | 6000000 | 6000000 | 5550000 | 5950000 | 0 | 0 | 0 | 0 | 28000000
Interstate | 8 | Dauphin | 113378 | Eisenhower Interchange B | 83 | B78 | Highway Reconstruction | ROW | NHPP | 2031-01-09 |  | 0 | 0 | 0 | 6600000 | 0 | 0 | 0 | 0 | 0 | 6600000
Interstate | 8 | Dauphin | 113378 | Eisenhower Interchange B | 83 | B78 | Highway Reconstruction | CON | NHPP | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136780000 | 136780000
Interstate | 8 | Dauphin | 113378 | Eisenhower Interchange B | 83 | B78 | Highway Reconstruction | CON | NFP | 2031-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60360000 | 60360000
Interstate | 8 | Dauphin | 113380 | Eisenhower Interchange C | 83 | C78 | Highway Reconstruction | FD | 581 | 2031-09-01 |  | 7000000 | 7000000 | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | 19500000
Interstate | 8 | Dauphin | 113380 | Eisenhower Interchange C | 83 | C78 | Highway Reconstruction | ROW | NHPP | 2031-09-01 |  | 0 | 0 | 0 | 0 | 990000 | 0 | 0 | 0 | 0 | 990000
Interstate | 8 | Dauphin | 113380 | Eisenhower Interchange C | 83 | C78 | Highway Reconstruction | CON | 581 | 2031-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41860819 | 41860819
Interstate | 8 | Dauphin | 113381 | Eisenhower Interchange D | 83 | D78 | Highway Reconstruction | FD | 581 | 2034-01-12 |  | 0 | 0 | 0 | 0 | 17000000 | 18100000 | 0 | 0 | 0 | 35100000
Interstate | 8 | Dauphin | 113381 | Eisenhower Interchange D | 83 | D78 | Highway Reconstruction | ROW | NHPP | 2034-01-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 550000
Interstate | 8 | Dauphin | 113381 | Eisenhower Interchange D | 83 | D78 | Highway Reconstruction | CON | NFP | 2034-01-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120720000 | 120720000
Interstate | 8 | Dauphin | 113381 | Eisenhower Interchange D | 83 | D78 | Highway Reconstruction | CON | 581 | 2034-01-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224595207 | 224595207
Interstate | 8 | Dauphin | 113754 | I-83 South Bridge Replacement | 83 | 094 | Bridge Replacement | PE | 581 | 2026-08-20 |  | 168230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168230
Interstate | 8 | Dauphin | 113754 | I-83 South Bridge Replacement | 83 | 094 | Bridge Replacement | FD | NHPP | 2026-08-20 |  | 6477618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6477618
Interstate | 8 | Dauphin | 113754 | I-83 South Bridge Replacement | 83 | 094 | Bridge Replacement | ROW | 581 | 2026-08-20 |  | 0 | 10170908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10170908
Interstate | 8 | Dauphin | 113754 | I-83 South Bridge Replacement | 83 | 094 | Bridge Replacement | ROW | 185 | 2026-08-20 |  | 4000000 | 29000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000000
Interstate | 8 | Dauphin | 113754 | I-83 South Bridge Replacement | 83 | 094 | Bridge Replacement | ROW | 581 | 2026-08-20 |  | 18863120 | 17000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35863120
Interstate | 8 | Dauphin | 113754 | I-83 South Bridge Replacement | 83 | 094 | Bridge Replacement | UTL | 581 | 2026-08-20 |  | 2121800 | 2622545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4744345
Interstate | 8 | Dauphin | 113754 | I-83 South Bridge Replacement | 83 | 094 | Bridge Replacement | CON | LBIP | 2026-08-20 |  | 0 | 500000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000000
Interstate | 8 | Dauphin | 113754 | I-83 South Bridge Replacement | 83 | 094 | Bridge Replacement | CON | NHPP | 2026-08-20 |  | 0 | 0 | 3500000 | 123000 | 12539458 | 0 | 76650000 | 65000000 | 59449529 | 217261987
Interstate | 8 | Dauphin | 113754 | I-83 South Bridge Replacement | 83 | 094 | Bridge Replacement | CON | STP | 2026-08-20 |  | 0 | 0 | 6587000 | 6587000 | 6587000 | 6587000 | 6587000 | 6587000 | 13174000 | 52696000
Interstate | 8 | Dauphin | 113754 | I-83 South Bridge Replacement | 83 | 094 | Bridge Replacement | CON | NHPP | 2026-08-20 |  | 0 | 0 | 0 | 116458 | 0 | 6194801 | 23008451 | 19000000 | 239040218 | 287359928
Interstate | 8 | Dauphin | 113754 | I-83 South Bridge Replacement | 83 | 094 | Bridge Replacement | CON | 185 | 2026-08-20 |  | 0 | 0 | 14631615 | 14631615 | 14631615 | 14631615 | 38974605 | 34631615 | 51594611 | 183727291
Interstate | 8 | Dauphin | 113754 | I-83 South Bridge Replacement | 83 | 094 | Bridge Replacement | CON | 581 | 2026-08-20 |  | 0 | 0 | 0 | 0 | 0 | 10718835 | 25911758 | 28059837 | 15911758 | 80602188
Interstate | 8 | Dauphin | 114593 | Interstate ITS Maint Contract 2020-2023 |  |  | General Maintenance | CON | NHPP | 2020-04-02 | 2020-04-02 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000
Interstate | 8 | Dauphin | 114698 | I-83 Eisenhower RR Bridge | 3001 | R78 | Bridge Replacement | FD | 185 | 2029-02-15 |  | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
Interstate | 8 | Dauphin | 114698 | I-83 Eisenhower RR Bridge | 3001 | R78 | Bridge Replacement | CON | NHPP | 2029-02-15 |  | 0 | 0 | 16090000 | 21905727 | 4000000 | 0 | 0 | 0 | 0 | 41995727
Interstate | 8 | Dauphin | 116296 | South Bridge Repairs | 83 | 097 | Bridge Restoration | CON | 185 |  | 2018-12-13 | 1326078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1326078
Interstate | 8 | Dauphin | 117968 | Interstate DMS and CCTV TSMO | 81 | 100 | Intelligent Transportation System | CON | NHPP | 2024-05-23 | 2024-05-23 | 1063152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063152
Interstate | 8 | Dauphin | 119485 | ITS Maintenance Contract 24-27 |  |  | General Maintenance | CON | NHPP | 2024-02-01 | 2024-02-01 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Interstate | 8 | Dauphin | 119795 | District 8-0 Interstate Concrete Repairs | 81 | 101 | Highway Restoration | CON | HSIP | 2024-06-13 | 2024-06-13 | 0 | 2032883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2032883
Interstate | 8 | Dauphin | 119795 | District 8-0 Interstate Concrete Repairs | 81 | 101 | Highway Restoration | CON | NHPP | 2024-06-13 | 2024-06-13 | 1685000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1685000
Interstate | 8 | Dauphin | 121921 | I-83 South Bridge AMTRAK Early Action (OCS) | 83 | OCS | Bridge Replacement | CON | 581 | 2025-09-25 |  | 2500000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500000
Interstate | 8 | Franklin | 92006 | I-81 Maryland to Mile 6 | 81 | 099 | Preventive Maintenance | CON | NHPP | 2025-02-13 | 2025-02-13 | 20283267 | 621223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20904490
Interstate | 8 | Lebanon | 123172 | District 8 Interstate RWRPM | 78 | 0 | Interstate Maintenance Program | CON | NHPP | 2026-04-09 |  | 0 | 2455171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2455171
Interstate | 8 | York | 92924 | North York Widening #3 (Exit 21 & 22) | 83 | 070 | Interstate Capacity Adding | FD | 581 | 2028-03-02 |  | 133273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133273
Interstate | 8 | York | 92924 | North York Widening #3 (Exit 21 & 22) | 83 | 070 | Interstate Capacity Adding | CON | NHPP | 2028-03-02 |  | 0 | 0 | 0 | 7589273 | 10000000 | 10000000 | 20685115 | 0 | 0 | 48274388
Interstate | 8 | York | 92924 | North York Widening #3 (Exit 21 & 22) | 83 | 070 | Interstate Capacity Adding | CON | NFP | 2028-03-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 60360000 | 60360000 | 0 | 120720000
Interstate | 8 | York | 106531 | I-83 Newberrytown South Resurf | 83 | 084 | Interstate Maintenance Program | CON | 581 | 2025-09-25 | 2025-09-25 | 0 | 5652315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5652315
Interstate | 8 | York | 110056 | North George Street Improvement | 181 | 017 | Congestion Reduction | CON | NHPP | 2020-08-06 | 2020-08-06 | 386745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 386745
Interstate | 8 | York | 112254 | I-83 Resurface Maryland Line to Exit 4 | 83 | 0 | Interstate Maintenance Program | CON | NHPP | 2028-03-23 |  | 0 | 0 | 0 | 0 | 7000000 | 13000000 | 0 | 0 | 0 | 20000000
Interstate | 8 | York | 112287 | I-83 Resurfacing George St to PA 921 | 83 | 096 | Interstate Maintenance Program | CON | NHPP | 2021-05-20 | 2021-05-20 | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481
Interstate | 8 | York | 112540 | Mill Creek Relocation | 83 | 090 | Stormwater Management | FD | 581 | 2026-07-16 |  | 19069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19069
Interstate | 8 | York | 112540 | Mill Creek Relocation | 83 | 090 | Stormwater Management | ROW | 581 | 2026-07-16 |  | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
Interstate | 8 | York | 112540 | Mill Creek Relocation | 83 | 090 | Stormwater Management | UTL | 581 | 2026-07-16 |  | 2141000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2141000
Interstate | 8 | York | 112540 | Mill Creek Relocation | 83 | 090 | Stormwater Management | CON | NHPP | 2026-07-16 |  | 0 | 6570831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6570831
Interstate | 8 | York | 112548 | Sherman Street & Eberts Lane | 1033 | 008 | Bridge Replacement | FD | 581 | 2023-01-26 | 2023-01-26 | 19069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19069
Interstate | 8 | York | 112548 | Sherman Street & Eberts Lane | 1033 | 008 | Bridge Replacement | CON | NHPP | 2023-01-26 | 2023-01-26 | 4386850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4386850
Interstate | 8 | York | 112548 | Sherman Street & Eberts Lane | 1033 | 008 | Bridge Replacement | CON | 581 | 2023-01-26 | 2023-01-26 | 104000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104000
Interstate | 8 | York | 112549 | North York Widening #1 (Exit 19) | 83 | 092 | Interstate Capacity Adding | FD | 581 | 2030-02-14 |  | 6739469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6739469
Interstate | 8 | York | 112549 | North York Widening #1 (Exit 19) | 83 | 092 | Interstate Capacity Adding | ROW | 581 | 2030-02-14 |  | 0 | 8782438 | 9457406 | 10060156 | 0 | 0 | 0 | 0 | 0 | 28300000
Interstate | 8 | York | 112549 | North York Widening #1 (Exit 19) | 83 | 092 | Interstate Capacity Adding | UTL | 581 | 2030-02-14 |  | 0 | 0 | 6453297 | 7346703 | 0 | 0 | 0 | 0 | 0 | 13800000
Interstate | 8 | York | 112549 | North York Widening #1 (Exit 19) | 83 | 092 | Interstate Capacity Adding | CON | NHPP | 2030-02-14 |  | 0 | 0 | 0 | 0 | 0 | 10725825 | 6787885 | 25223000 | 76342847 | 119079557
Interstate | 8 | York | 112549 | North York Widening #1 (Exit 19) | 83 | 092 | Interstate Capacity Adding | CON | 581 | 2030-02-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000000 | 13200000 | 54323974 | 87523974
Interstate | 8 | York | 112550 | North York Widening #2 (Codorus Creek Bridge) | 83 | 091 | Interstate Capacity Adding | FD | 581 | 2026-07-16 |  | 1061780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1061780
Interstate | 8 | York | 112550 | North York Widening #2 (Codorus Creek Bridge) | 83 | 091 | Interstate Capacity Adding | ROW | 581 | 2026-07-16 |  | 10226000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10226000
Interstate | 8 | York | 112550 | North York Widening #2 (Codorus Creek Bridge) | 83 | 091 | Interstate Capacity Adding | CON | NHPP | 2026-07-16 |  | 0 | 50666650 | 79869318 | 0 | 0 | 0 | 0 | 0 | 0 | 130535968
Interstate | 8 | York | 112550 | North York Widening #2 (Codorus Creek Bridge) | 83 | 091 | Interstate Capacity Adding | CON | NFP | 2026-07-16 |  | 0 | 60360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60360000
Interstate | 8 | York | 116480 | I-83 over Springwood Rd | 83 | 103 | Bridge Preservation - Federal | FD | 185 | 2026-01-29 | 2026-01-29 | 330930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330930
Interstate | 8 | York | 116480 | I-83 over Springwood Rd | 83 | 103 | Bridge Preservation - Federal | UTL | 185 | 2026-01-29 | 2026-01-29 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
Interstate | 8 | York | 116480 | I-83 over Springwood Rd | 83 | 103 | Bridge Preservation - Federal | CON | 185 | 2026-01-29 | 2026-01-29 | 0 | 2202053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2202053
Interstate | 8 | York | 119358 | North York Widening Demo | 83 | DM1 | General Maintenance | CON | 581 | 2023-11-02 | 2023-11-02 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Interstate | 9 | Bedford | 22816 | Breezewood-Fulton Co Line | 70 | 021 | Highway Restoration | CON | NHPP | 2021-04-22 | 2021-04-22 | 0 | 2549800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2549800
Interstate | 9 | Blair | 112238 | I-99 - Bald Eagle Intchg to Co Line | 99 | 027 | Highway Restoration | PE | 581 | 2026-10-01 |  | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
Interstate | 9 | Blair | 112238 | I-99 - Bald Eagle Intchg to Co Line | 99 | 027 | Highway Restoration | CON | NHPP | 2026-10-01 |  | 0 | 0 | 4000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 9000000
Interstate | 9 | Blair | 112239 | I-99 Plank Rd Intchg to Tyrone | 99 | 022 | Highway Restoration | CON | NHPP | 2024-02-15 | 2024-02-15 | 752162 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1352162
Interstate | 9 | Blair | 112239 | I-99 Plank Rd Intchg to Tyrone | 99 | 022 | Highway Restoration | CON | 581 | 2024-02-15 | 2024-02-15 | 25800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25800
Interstate | 9 | Blair | 112241 | I-99 Newry Pulloff to Plank Rd Intchg | 99 | 021 | Highway Restoration | CON | NHPP | 2024-02-15 | 2024-02-15 | 2296851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2296851
Interstate | 9 | Blair | 112241 | I-99 Newry Pulloff to Plank Rd Intchg | 99 | 021 | Highway Restoration | CON | 581 | 2024-02-15 | 2024-02-15 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
Interstate | 9 | Blair | 112242 | I-99 Sproul/Claysburg to Newry Pulloff | 99 | 029 | Highway Restoration | PE | 581 | 2026-02-12 | 2026-02-12 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Interstate | 9 | Blair | 112242 | I-99 Sproul/Claysburg to Newry Pulloff | 99 | 029 | Highway Restoration | CON | NHPP | 2026-02-12 | 2026-02-12 | 0 | 15000000 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000000
Interstate | 9 | Fulton | 91537 | I-70 EB Amaranth to Bdfrd | 70 | 034 | Highway Restoration | CON | NHPP | 2023-04-13 | 2023-04-13 | 0 | 1944524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1944524
Interstate | 9 | Fulton | 112244 | I-70 Amaranth Intchg to MD State Line | 70 | 039 | Highway Restoration | CON | NHPP | 2023-04-13 | 2023-04-13 | 0 | 652186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 652186
Interstate | 9 | Fulton | 122478 | I-70 Amaranth Intchg to MD State Line - Pipe 49 | 70 | 04R | Highway Restoration | ROW | 581 |  |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000
Interstate | 10 | Butler | 106274 | I-79 Southern Section Reconstruction | 79 | 24C | Highway Reconstruction | CON | NHPP | 2028-10-05 |  | 0 | 0 | 0 | 40000000 | 35000000 | 45000000 | 10917319 | 15000000 | 50000000 | 195917319
Interstate | 10 | Butler | 109288 | I-79 Harmony NB/SB | 79 | 257 | Bridge Replacement | PE | 581 | 2034-10-05 |  | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
Interstate | 10 | Butler | 120118 | I-79 Cranberry South Concrete Repairs | 79 | 201 | Interstate Maintenance Program | CON | NHPP | 2025-02-27 | 2025-02-27 | 4793595 | 812071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5605666
Interstate | 10 | Butler | 120118 | I-79 Cranberry South Concrete Repairs | 79 | 201 | Interstate Maintenance Program | CON | 581 | 2025-02-27 | 2025-02-27 | 541413 | 81439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 622852
Interstate | 10 | Butler | 122773 | I-79 - SR 528 Interchange | 79 | 24F | Highway Reconstruction | PE | 581 | 2030-10-24 |  | 0 | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300000
Interstate | 10 | Clarion | 90021 | I-80 Canoe Creek Bridges | 80 | 365 | Bridge Replacement | PE | NHPP |  | 2023-09-25 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Interstate | 10 | Clarion | 90021 | I-80 Canoe Creek Bridges | 80 | 365 | Bridge Replacement | CON | NHPP |  | 2023-09-25 | 0 | 0 | 960000 | 0 | 0 | 0 | 0 | 0 | 0 | 960000
Interstate | 10 | Clarion | 106030 | I-80 Strattanville Reconstruction | 80 | 34B | Highway Reconstruction | PE | NHPP | 2031-10-02 |  | 0 | 4500000 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 9000000
Interstate | 10 | Clarion | 106030 | I-80 Strattanville Reconstruction | 80 | 34B | Highway Reconstruction | PE | 581 | 2031-10-02 |  | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Interstate | 10 | Clarion | 106030 | I-80 Strattanville Reconstruction | 80 | 34B | Highway Reconstruction | FD | 581 | 2031-10-02 |  | 0 | 0 | 4703708 | 0 | 0 | 0 | 0 | 0 | 0 | 4703708
Interstate | 10 | Clarion | 106030 | I-80 Strattanville Reconstruction | 80 | 34B | Highway Reconstruction | ROW | 581 | 2031-10-02 |  | 0 | 0 | 0 | 2851522 | 0 | 0 | 0 | 0 | 0 | 2851522
Interstate | 10 | Clarion | 106030 | I-80 Strattanville Reconstruction | 80 | 34B | Highway Reconstruction | UTL | 581 | 2031-10-02 |  | 0 | 0 | 0 | 2138641 | 0 | 0 | 0 | 0 | 0 | 2138641
Interstate | 10 | Clarion | 106030 | I-80 Strattanville Reconstruction | 80 | 34B | Highway Reconstruction | CON | NHPP | 2031-10-02 |  | 0 | 0 | 0 | 0 | 0 | 9623000 | 0 | 0 | 0 | 9623000
Interstate | 10 | Clarion | 106030 | I-80 Strattanville Reconstruction | 80 | 34B | Highway Reconstruction | CON | NHPP | 2031-10-02 |  | 0 | 0 | 0 | 0 | 0 | 6377000 | 15250000 | 0 | 58000000 | 79627000
Interstate | 10 | Clarion | 116492 | Boyd Run Culvert Rehab | 80 | 366 | Interstate Maintenance Program | PE | 185 | 2026-10-01 |  | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260000
Interstate | 10 | Clarion | 116492 | Boyd Run Culvert Rehab | 80 | 366 | Interstate Maintenance Program | FD | 185 | 2026-10-01 |  | 424360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424360
Interstate | 10 | Clarion | 116492 | Boyd Run Culvert Rehab | 80 | 366 | Interstate Maintenance Program | ROW | 185 | 2026-10-01 |  | 0 | 109273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109273
Interstate | 10 | Clarion | 116492 | Boyd Run Culvert Rehab | 80 | 366 | Interstate Maintenance Program | UTL | 185 | 2026-10-01 |  | 0 | 131127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131127
Interstate | 10 | Clarion | 116492 | Boyd Run Culvert Rehab | 80 | 366 | Interstate Maintenance Program | CON | 185 | 2026-10-01 |  | 0 | 0 | 2898185 | 0 | 0 | 0 | 0 | 0 | 0 | 2898185
Interstate | 10 | Clarion | 116493 | Clarion River Bridge Replacement | 80 | 366 | Interstate Maintenance Program | PE | 581 | 2030-12-12 |  | 4502036 | 2056964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6559000
Interstate | 10 | Jefferson | 106029 | I-80 Brookville West Reconstruction | 80 | 54A | Highway Reconstruction | FD | NHPP | 2031-10-09 |  | 4320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4320000
Interstate | 10 | Jefferson | 106029 | I-80 Brookville West Reconstruction | 80 | 54A | Highway Reconstruction | FD | 581 | 2031-10-09 |  | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000
Interstate | 10 | Jefferson | 106029 | I-80 Brookville West Reconstruction | 80 | 54A | Highway Reconstruction | CON | NHPP | 2031-10-09 |  | 0 | 0 | 0 | 32000000 | 0 | 0 | 6375335 | 6538099 | 3197645 | 48111079
Interstate | 10 | Jefferson | 106029 | I-80 Brookville West Reconstruction | 80 | 54A | Highway Reconstruction | CON | 581 | 2031-10-09 |  | 0 | 0 | 0 | 0 | 14787533 | 29648210 | 0 | 0 | 41453178 | 85888921
Interstate | 10 | Jefferson | 106223 | I-80 Brookville East Reconstruction | 80 | 54B | Highway Reconstruction | FD | NHPP | 2030-10-10 |  | 8910000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8910000
Interstate | 10 | Jefferson | 106223 | I-80 Brookville East Reconstruction | 80 | 54B | Highway Reconstruction | FD | 581 | 2030-10-10 |  | 990000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990000
Interstate | 10 | Jefferson | 106223 | I-80 Brookville East Reconstruction | 80 | 54B | Highway Reconstruction | ROW | NHPP | 2030-10-10 |  | 587772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 587772
Interstate | 10 | Jefferson | 106223 | I-80 Brookville East Reconstruction | 80 | 54B | Highway Reconstruction | ROW | 581 | 2030-10-10 |  | 65308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65308
Interstate | 10 | Jefferson | 106223 | I-80 Brookville East Reconstruction | 80 | 54B | Highway Reconstruction | CON | NHPP | 2030-10-10 |  | 0 | 0 | 36000000 | 36000000 | 36000000 | 30000000 | 46500000 | 20000000 | 102000000 | 306500000
Interstate | 10 | Jefferson | 106223 | I-80 Brookville East Reconstruction | 80 | 54B | Highway Reconstruction | CON | 581 | 2030-10-10 |  | 0 | 0 | 4000000 | 4000000 | 9000000 | 13340000 | 15166667 | 8722222 | 11311111 | 65540000
Interstate | 10 | Jefferson | 121952 | I-80 Brookville East Ph 1 | 80 | 54C | Bridge Replacement | UTL | NHPP | 2026-10-01 |  | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000
Interstate | 10 | Jefferson | 121952 | I-80 Brookville East Ph 1 | 80 | 54C | Bridge Replacement | UTL | 581 | 2026-10-01 |  | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
Interstate | 10 | Jefferson | 121952 | I-80 Brookville East Ph 1 | 80 | 54C | Bridge Replacement | CON | NHPP | 2026-10-01 |  | 0 | 33622348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33622348
Interstate | 10 | Jefferson | 122451 | I-80 Falls Creek Concrete Rehab | 80 | 511 | Highway Restoration | PE | 581 | 2026-04-09 |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Interstate | 10 | Jefferson | 122451 | I-80 Falls Creek Concrete Rehab | 80 | 511 | Highway Restoration | CON | NHPP | 2026-04-09 |  | 0 | 28000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000000
Interstate | 11 | Allegheny | 74454 | I-376, Boyce Road to I-79 | 376 | A79 | Interstate Maintenance Program | CON | NHPP | 2024-06-13 | 2024-06-13 | 809380 | 809099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1618479
Interstate | 11 | Allegheny | 74454 | I-376, Boyce Road to I-79 | 376 | A79 | Interstate Maintenance Program | CON | 581 | 2024-06-13 | 2024-06-13 | 89930 | 89901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179831
Interstate | 11 | Allegheny | 81931 | I-79, Campbell's-Moon Run | 79 | A53 | Highway Restoration | CON | NHPP | 2023-12-14 | 2023-12-14 | 2522173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2522173
Interstate | 11 | Allegheny | 81933 | I-79, I-279 to Butler County | 79 | A73 | Highway Restoration | PE | 581 | 2028-04-13 |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Interstate | 11 | Allegheny | 81933 | I-79, I-279 to Butler County | 79 | A73 | Highway Restoration | FD | 581 | 2028-04-13 |  | 0 | 2652250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2652250
Interstate | 11 | Allegheny | 81933 | I-79, I-279 to Butler County | 79 | A73 | Highway Restoration | CON | NHPP | 2028-04-13 |  | 0 | 0 | 0 | 37000000 | 23024575 | 18176425 | 0 | 0 | 0 | 78201000
Interstate | 11 | Allegheny | 81933 | I-79, I-279 to Butler County | 79 | A73 | Highway Restoration | CON | 185 | 2028-04-13 |  | 0 | 0 | 7000000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 10000000
Interstate | 11 | Allegheny | 81933 | I-79, I-279 to Butler County | 79 | A73 | Highway Restoration | CON | 581 | 2028-04-13 |  | 0 | 0 | 4800000 | 2777777 | 1333333 | 889000 | 0 | 0 | 0 | 9800110
Interstate | 11 | Allegheny | 87754 | I-376, Fort Pitt Br to Squirrel Hill-Br Pres & Pav | 376 | 0 | Interstate Maintenance Program | PE | 185 | 2033-08-11 |  | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 3000000
Interstate | 11 | Allegheny | 87754 | I-376, Fort Pitt Br to Squirrel Hill-Br Pres & Pav | 376 | 0 | Interstate Maintenance Program | PE | 581 | 2033-08-11 |  | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 3000000
Interstate | 11 | Allegheny | 87754 | I-376, Fort Pitt Br to Squirrel Hill-Br Pres & Pav | 376 | 0 | Interstate Maintenance Program | FD | 185 | 2033-08-11 |  | 0 | 0 | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 3500000
Interstate | 11 | Allegheny | 87754 | I-376, Fort Pitt Br to Squirrel Hill-Br Pres & Pav | 376 | 0 | Interstate Maintenance Program | FD | 581 | 2033-08-11 |  | 0 | 0 | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 3500000
Interstate | 11 | Allegheny | 87754 | I-376, Fort Pitt Br to Squirrel Hill-Br Pres & Pav | 376 | 0 | Interstate Maintenance Program | ROW | 185 | 2033-08-11 |  | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 750000
Interstate | 11 | Allegheny | 87754 | I-376, Fort Pitt Br to Squirrel Hill-Br Pres & Pav | 376 | 0 | Interstate Maintenance Program | ROW | 581 | 2033-08-11 |  | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 750000
Interstate | 11 | Allegheny | 87754 | I-376, Fort Pitt Br to Squirrel Hill-Br Pres & Pav | 376 | 0 | Interstate Maintenance Program | UTL | 185 | 2033-08-11 |  | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000
Interstate | 11 | Allegheny | 87754 | I-376, Fort Pitt Br to Squirrel Hill-Br Pres & Pav | 376 | 0 | Interstate Maintenance Program | UTL | 581 | 2033-08-11 |  | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 350000
Interstate | 11 | Allegheny | 87754 | I-376, Fort Pitt Br to Squirrel Hill-Br Pres & Pav | 376 | 0 | Interstate Maintenance Program | CON | NHPP | 2033-08-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20000000 | 36000000 | 89000000 | 145000000
Interstate | 11 | Allegheny | 87767 | I-376, Edgewood to Churchill | 376 | A74 | Highway Restoration | PE | NHPP | 2025-10-23 | 2025-10-23 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
Interstate | 11 | Allegheny | 87767 | I-376, Edgewood to Churchill | 376 | A74 | Highway Restoration | CON | NHPP | 2025-10-23 | 2025-10-23 | 0 | 33917000 | 34000000 | 42000000 | 0 | 0 | 0 | 0 | 0 | 109917000
Interstate | 11 | Allegheny | 87778 | I-376, Churchill to Monroeville | 376 | A72 | Highway Restoration | ROW | 581 | 2023-12-14 | 2023-12-14 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Interstate | 11 | Allegheny | 87778 | I-376, Churchill to Monroeville | 376 | A72 | Highway Restoration | CON | NHPP | 2023-12-14 | 2023-12-14 | 17776905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17776905
Interstate | 11 | Allegheny | 91565 | I-79, Moon Run - Neville Island | 79 | A69 | Interstate Maintenance Program | CON | NHPP | 2022-11-03 | 2022-11-03 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000
Interstate | 11 | Allegheny | 97027 | I-376/Carnegie Interchange | 376 | A68 | Safety Improvement | ROW | 581 | 2032-02-05 |  | 1060900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1060900
Interstate | 11 | Allegheny | 97027 | I-376/Carnegie Interchange | 376 | A68 | Safety Improvement | CON | NHPP | 2032-02-05 |  | 0 | 0 | 0 | 0 | 0 | 27000000 | 27000000 | 27000000 | 27000000 | 108000000
Interstate | 11 | Allegheny | 97027 | I-376/Carnegie Interchange | 376 | A68 | Safety Improvement | CON | 581 | 2032-02-05 |  | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000 | 3000000 | 3000000 | 12000000
Interstate | 11 | Allegheny | 97029 | I-376/Greentree Interchange | 376 | A67 | Safety Improvement | ROW | 581 | 2029-12-20 |  | 1060900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1060900
Interstate | 11 | Allegheny | 97029 | I-376/Greentree Interchange | 376 | A67 | Safety Improvement | CON | NHPP | 2029-12-20 |  | 0 | 0 | 0 | 0 | 22600000 | 25000000 | 25000000 | 5000000 | 20000000 | 97600000
Interstate | 11 | Allegheny | 99874 | Squirrel Hill Interchange | 376 | A76 | Safety Improvement | FD | 581 | 2030-04-25 |  | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Interstate | 11 | Allegheny | 99874 | Squirrel Hill Interchange | 376 | A76 | Safety Improvement | ROW | 581 | 2030-04-25 |  | 3000000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000
Interstate | 11 | Allegheny | 99874 | Squirrel Hill Interchange | 376 | A76 | Safety Improvement | UTL | 581 | 2030-04-25 |  | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
Interstate | 11 | Allegheny | 99874 | Squirrel Hill Interchange | 376 | A76 | Safety Improvement | CON | NHPP | 2030-04-25 |  | 0 | 0 | 0 | 15000000 | 20000000 | 15000000 | 10000000 | 0 | 0 | 60000000
Interstate | 11 | Allegheny | 99874 | Squirrel Hill Interchange | 376 | A76 | Safety Improvement | CON | NHPP | 2030-04-25 |  | 0 | 0 | 0 | 15000000 | 5000000 | 10000000 | 0 | 0 | 0 | 30000000
Interstate | 11 | Allegheny | 100794 | 579 HOV Bridge Emergency | 6579 | A06 | Bridge Restoration | PE | 185 | 2025-02-28 | 2025-02-28 | 1075000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075000
Interstate | 11 | Allegheny | 100794 | 579 HOV Bridge Emergency | 6579 | A06 | Bridge Restoration | CON | 185 | 2025-02-28 | 2025-02-28 | 5750000 | 5150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10900000
Interstate | 11 | Allegheny | 100941 | Neville Island Bridge Ramps - Southern Ramps | 8015 | A02 | Bridge Restoration | PE | NHPP |  |  | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
Interstate | 11 | Allegheny | 105457 | Neville Island Bridge Ramps - Northern Ramps | 8017 | A02 | Bridge Restoration | PE | NHPP |  |  | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
Interstate | 11 | Allegheny | 109270 | Fort Duquesne Bridge Rehab & Preservation | 279 | A89 | Interstate Maintenance Program | FD | NHPP | 2031-04-15 |  | 0 | 9898781 | 4501219 | 0 | 0 | 0 | 0 | 0 | 0 | 14400000
Interstate | 11 | Allegheny | 109270 | Fort Duquesne Bridge Rehab & Preservation | 279 | A89 | Interstate Maintenance Program | FD | 185 | 2031-04-15 |  | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000
Interstate | 11 | Allegheny | 109270 | Fort Duquesne Bridge Rehab & Preservation | 279 | A89 | Interstate Maintenance Program | ROW | 185 | 2031-04-15 |  | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Interstate | 11 | Allegheny | 109270 | Fort Duquesne Bridge Rehab & Preservation | 279 | A89 | Interstate Maintenance Program | UTL | 185 | 2031-04-15 |  | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Interstate | 11 | Allegheny | 109270 | Fort Duquesne Bridge Rehab & Preservation | 279 | A89 | Interstate Maintenance Program | CON | NHPP | 2031-04-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000000 | 60000000
Interstate | 11 | Allegheny | 109293 | I-579, Vets Bridge - 5th Ave to I-279 | 579 | A13 | Highway Restoration | PE | NHPP | 2030-06-13 |  | 0 | 4982304 | 5417696 | 0 | 0 | 0 | 0 | 0 | 0 | 10400000
Interstate | 11 | Allegheny | 109293 | I-579, Vets Bridge - 5th Ave to I-279 | 579 | A13 | Highway Restoration | FD | NHPP | 2030-06-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000000 | 12000000
Interstate | 11 | Allegheny | 109293 | I-579, Vets Bridge - 5th Ave to I-279 | 579 | A13 | Highway Restoration | ROW | NHPP | 2030-06-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000
Interstate | 11 | Allegheny | 109293 | I-579, Vets Bridge - 5th Ave to I-279 | 579 | A13 | Highway Restoration | UTL | NHPP | 2030-06-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
Interstate | 11 | Allegheny | 109293 | I-579, Vets Bridge - 5th Ave to I-279 | 579 | A13 | Highway Restoration | CON | NHPP | 2030-06-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17176105 | 17176105
Interstate | 11 | Allegheny | 112249 | I-376, Bath Tub Flooding | 376 | A69 | Interstate Maintenance Program | PE | 581 | 2026-07-30 |  | 1313150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1313150
Interstate | 11 | Allegheny | 112249 | I-376, Bath Tub Flooding | 376 | A69 | Interstate Maintenance Program | FD | 581 | 2026-07-30 |  | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000
Interstate | 11 | Allegheny | 112249 | I-376, Bath Tub Flooding | 376 | A69 | Interstate Maintenance Program | CON | MEGA | 2026-07-30 |  | 0 | 20007000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20007000
Interstate | 11 | Allegheny | 112249 | I-376, Bath Tub Flooding | 376 | A69 | Interstate Maintenance Program | CON | PRTDG | 2026-07-30 |  | 0 | 6669000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6669000
Interstate | 11 | Allegheny | 112249 | I-376, Bath Tub Flooding | 376 | A69 | Interstate Maintenance Program | CON | 581 | 2026-07-30 |  | 4763394 | 1905606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6669000
Interstate | 11 | Allegheny | 113362 | Frazier Street Bridge | 376 | A77 | Bridge Restoration | PE | 185 | 2030-03-14 |  | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000
Interstate | 11 | Allegheny | 113362 | Frazier Street Bridge | 376 | A77 | Bridge Restoration | FD | 185 | 2030-03-14 |  | 0 | 6500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500000
Interstate | 11 | Allegheny | 113362 | Frazier Street Bridge | 376 | A77 | Bridge Restoration | CON | 185 | 2030-03-14 |  | 0 | 0 | 0 | 25000000 | 10000000 | 10000000 | 10000000 | 18000000 | 62000000 | 135000000
Interstate | 11 | Allegheny | 119746 | ITS Maintenance 2023 (NHPP/PROTECT) | 376 | 0 | Intelligent Transportation System | CON | NHPP | 2023-08-24 | 2023-08-24 | 51386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51386
Interstate | 11 | Allegheny | 120096 | I-376, Fort Pitt Bridge to Squirrel Hill Barrier | 376 | A81 | Safety Improvement | PE | 581 | 2027-06-10 |  | 0 | 2121800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2121800
Interstate | 11 | Allegheny | 120096 | I-376, Fort Pitt Bridge to Squirrel Hill Barrier | 376 | A81 | Safety Improvement | FD | 581 | 2027-06-10 |  | 0 | 0 | 2185454 | 0 | 0 | 0 | 0 | 0 | 0 | 2185454
Interstate | 11 | Allegheny | 120096 | I-376, Fort Pitt Bridge to Squirrel Hill Barrier | 376 | A81 | Safety Improvement | ROW | 581 | 2027-06-10 |  | 0 | 0 | 0 | 1125509 | 0 | 0 | 0 | 0 | 0 | 1125509
Interstate | 11 | Allegheny | 120096 | I-376, Fort Pitt Bridge to Squirrel Hill Barrier | 376 | A81 | Safety Improvement | UTL | 581 | 2027-06-10 |  | 0 | 0 | 546364 | 0 | 0 | 0 | 0 | 0 | 0 | 546364
Interstate | 11 | Allegheny | 120096 | I-376, Fort Pitt Bridge to Squirrel Hill Barrier | 376 | A81 | Safety Improvement | CON | 581 | 2027-06-10 |  | 0 | 0 | 0 | 22510176 | 0 | 0 | 0 | 0 | 0 | 22510176
Interstate | 11 | Allegheny | 121172 | I-376/Banksville Interchange | 376 | A59 | Safety Improvement | CON | NHPP | 2027-05-13 |  | 0 | 16200000 | 13500000 | 0 | 0 | 0 | 0 | 0 | 0 | 29700000
Interstate | 11 | Allegheny | 121172 | I-376/Banksville Interchange | 376 | A59 | Safety Improvement | CON | 581 | 2027-05-13 |  | 0 | 1800000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 3300000
Interstate | 11 | Allegheny | 121530 | 2024 Interstate Longitudinal Joint Rehab | 279 | A90 | Interstate Maintenance Program | CON | NHPP | 2024-08-08 | 2024-08-08 | 200000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000
Interstate | 11 | Allegheny | 121799 | Ft Duquesne Br & N Ramps T1 Steel Repairs & Pres | 65 | A60 | Bridge Preservation - Federal | CON | BRIP | 2026-05-21 |  | 0 | 13000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000000
Interstate | 11 | Allegheny | 123342 | Neville Island Bridge and Ramp Repairs | 79 | 0 | Bridge Preservation - State Funded | CON | 185 | 2026-03-12 | 2026-03-12 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
Interstate | 11 | Beaver | 109296 | I-376, Center to Hopewell Township | 376 | B17 | Highway Restoration | PE | NHPP | 2028-06-15 |  | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
Interstate | 11 | Beaver | 109296 | I-376, Center to Hopewell Township | 376 | B17 | Highway Restoration | FD | NHPP | 2028-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1820000 | 1180000 | 0 | 3000000
Interstate | 11 | Beaver | 109296 | I-376, Center to Hopewell Township | 376 | B17 | Highway Restoration | ROW | NHPP | 2028-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 350000
Interstate | 11 | Beaver | 109296 | I-376, Center to Hopewell Township | 376 | B17 | Highway Restoration | UTL | NHPP | 2028-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000
Interstate | 11 | Beaver | 109296 | I-376, Center to Hopewell Township | 376 | B17 | Highway Restoration | CON | NHPP | 2028-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39370000 | 0 | 39370000
Interstate | 11 | Beaver | 117387 | I-376, ITS Installation - Beaver County - 2 | 376 | B10 | Intelligent Transportation System | CON | NHPP | 2023-09-14 | 2023-09-14 | 0 | 582000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582000
Interstate | 11 | Beaver | 121797 | Vanport Bridge T1 Steel Repair | 376 | B14 | Bridge Preservation - State Funded | CON | 185 | 2025-03-27 | 2025-03-27 | 7700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7700000
Interstate | 11 | Lawrence | 109284 | I-376, SR 224 to Turnpike | 376 | L08 | Highway Restoration | CON | NHPP | 2023-08-10 | 2023-08-10 | 882000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882000
Interstate | 12 | Greene | 91553 | I-79: Waynesburg to Marianna | 79 | 19R | Interstate Maintenance Program | PE | 581 | 2026-04-23 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Interstate | 12 | Greene | 91553 | I-79: Waynesburg to Marianna | 79 | 19R | Interstate Maintenance Program | CON | NHPP | 2026-04-23 |  | 0 | 26000000 | 19500000 | 0 | 0 | 0 | 0 | 0 | 0 | 45500000
Interstate | 12 | Washington | 75945 | I-70: Welcome Center to Taylorstown | 70 | K30 | Interstate Maintenance Program | FD | 185 | 2030-06-13 |  | 0 | 0 | 5796370 | 0 | 0 | 0 | 0 | 0 | 0 | 5796370
Interstate | 12 | Washington | 75945 | I-70: Welcome Center to Taylorstown | 70 | K30 | Interstate Maintenance Program | CON | 185 | 2030-06-13 |  | 0 | 0 | 0 | 0 | 17000000 | 19000000 | 20000000 | 13329000 | 19000000 | 88329000
Interstate | 12 | Washington | 75945 | I-70: Welcome Center to Taylorstown | 70 | K30 | Interstate Maintenance Program | CON | 581 | 2030-06-13 |  | 0 | 0 | 0 | 0 | 12000000 | 12000000 | 12000000 | 14006307 | 0 | 50006307
Interstate | 12 | Washington | 75950 | South Junction to SR 519 | 70 | W31 | Interstate Maintenance Program | CON | NHPP | 2016-11-03 | 2016-11-03 | 0 | 6550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6550000
Interstate | 12 | Washington | 75981 | I-70: Bentleyville to PA 519 | 70 | 32M | Interstate Maintenance Program | CON | NHPP | 2026-04-23 |  | 0 | 14725000 | 8775000 | 0 | 0 | 0 | 0 | 0 | 0 | 23500000
Interstate | 12 | Washington | 106919 | I70: Belle Vernon Bridge to Bentleyville | 70 | 10K | Highway Reconstruction | FD | NHPP | 2028-01-27 |  | 5400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400000
Interstate | 12 | Washington | 106919 | I70: Belle Vernon Bridge to Bentleyville | 70 | 10K | Highway Reconstruction | FD | 581 | 2028-01-27 |  | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Interstate | 12 | Washington | 106919 | I70: Belle Vernon Bridge to Bentleyville | 70 | 10K | Highway Reconstruction | ROW | 581 | 2028-01-27 |  | 0 | 0 | 3477822 | 3477822 | 0 | 0 | 0 | 0 | 0 | 6955644
Interstate | 12 | Washington | 106919 | I70: Belle Vernon Bridge to Bentleyville | 70 | 10K | Highway Reconstruction | UTL | 581 | 2028-01-27 |  | 0 | 0 | 4051500 | 4051500 | 0 | 0 | 0 | 0 | 0 | 8103000
Interstate | 12 | Washington | 106919 | I70: Belle Vernon Bridge to Bentleyville | 70 | 10K | Highway Reconstruction | CON | NHPP | 2028-01-27 |  | 0 | 0 | 0 | 0 | 35000000 | 35000000 | 30000000 | 37215901 | 65284097 | 202499998
Interstate | 12 | Washington | 106919 | I70: Belle Vernon Bridge to Bentleyville | 70 | 10K | Highway Reconstruction | CON | 581 | 2028-01-27 |  | 0 | 0 | 0 | 0 | 3888890 | 3922223 | 3300000 | 4135100 | 7253789 | 22500002
Interstate | 12 | Westmoreland | 75978 | I-70 @ PA 51 Interchange | 70 | E10 | Interstate Maintenance Program | CON | BRIP | 2022-04-21 | 2022-04-21 | 22838267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22838267
Interstate | 12 | Westmoreland | 75978 | I-70 @ PA 51 Interchange | 70 | E10 | Interstate Maintenance Program | CON | NHPP | 2022-04-21 | 2022-04-21 | 9101828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9101828
Interstate | 12 | Westmoreland | 88507 | PA 201 @ I-70 Improvements PEL | 70 | 0 | Interstate Maintenance Program | PE | NHPP | 2030-04-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 0 | 0 | 10000000
Interstate | 12 | Westmoreland | 88507 | PA 201 @ I-70 Improvements PEL | 70 | 0 | Interstate Maintenance Program | FD | NHPP | 2030-04-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 10000000 | 0 | 12000000
Interstate | 12 | Westmoreland | 88507 | PA 201 @ I-70 Improvements PEL | 70 | 0 | Interstate Maintenance Program | ROW | NHPP | 2030-04-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000
Interstate | 12 | Westmoreland | 88507 | PA 201 @ I-70 Improvements PEL | 70 | 0 | Interstate Maintenance Program | UTL | NHPP | 2030-04-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 8000000 | 10000000
Interstate | 12 | Westmoreland | 88508 | I-70 Arnold City Interch | 70 | D10 | Interstate Maintenance Program | CON | NHPP | 2025-01-09 | 2025-01-09 | 85977600 | 17185561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103163161
Interstate | 99 | Central Office | 75891 | Interstate Contingency |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 14402701 | 0 | 0 | 0 | 0 | 0 | 0 | 1457304 | 15860005
Interstate | 99 | Central Office | 75891 | Interstate Contingency |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 6215399 | 23456702 | 16271909 | 0 | 5827400 | 3685271 | 5000000 | 31633060 | 92089741
Interstate | 99 | Central Office | 75891 | Interstate Contingency |  |  | Reserve Line Item | CON | STP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1713959 | 1713959
Interstate | 99 | Central Office | 75891 | Interstate Contingency |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 5513340 | 7417437 | 7593024 | 765170 | 999349 | 1462385 | 133385 | 18914529 | 42798619
Interstate | 99 | Central Office | 75891 | Interstate Contingency |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 10075598 | 8802480 | 13257144 | 1607695 | 10553471 | 13072399 | 23293115 | 20386044 | 101047946
Interstate | 99 | Central Office | 105487 | Interstate Traffic Monitoring Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 1800000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 3600000 | 10800000
Interstate | 99 | Central Office | 110601 | INFRA Support |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 2000000 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 6000000
Interstate | 99 | Central Office | 114586 | Interstate ITS Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 4790392 | 3040000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 16000000 | 43830392
Interstate | 99 | Central Office | 114587 | All-Weather Pavement Marking Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 0 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 16000000 | 40000000
Interstate | 99 | Central Office | 115100 | Concrete Pavement Management Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 32000000 | 88000000
Interstate | 99 | Central Office | 118915 | Major Bridge P3 Package 1 |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 20000000 | 40615000 | 42425454 | 70430000 | 70596696 | 70430000 | 70430000 | 256459000 | 641386150
Interstate | 99 | Central Office | 118915 | Major Bridge P3 Package 1 |  |  | Reserve Line Item | CON | NHPP |  |  | 7310896 | 0 | 0 | 0 | 51980048 | 52618761 | 54000000 | 54000000 | 246095065 | 466004770
Interstate | 99 | Central Office | 118915 | Major Bridge P3 Package 1 |  |  | Reserve Line Item | CON | 185 |  |  | 756376 | 2300000 | 7675000 | 7413361 | 22197215 | 22313036 | 22000000 | 22000000 | 92258782 | 198913770
Interstate | 99 | Central Office | 119230 | Major Bridge P3 Support |  |  | Planning/Research/Administration | PE | NHPP |  |  | 249208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249208
Interstate | 99 | Central Office | 119230 | Major Bridge P3 Support |  |  | Planning/Research/Administration | CON | NHPP |  |  | 14838957 | 2477908 | 8229495 | 0 | 0 | 0 | 0 | 0 | 0 | 25546360
Interstate | 99 | Central Office | 120687 | ITS Modems |  |  | General Maintenance | CON | NHPP |  |  | 618000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618000
Interstate | 99 | Central Office | 122299 | Special Initiative Reserve Line item |  |  | Reserve Line Item | CON | STP |  |  | 153000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153000000
Interstate | 99 | Central Office | 123085 | Bridge Street Facility Enhancements |  |  | Interstate Maintenance Program | CON | NHPP | 2026-09-30 |  | 12200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200000
STWD Items | 6 | Delaware | 112052 | PA 420 Parking Improvements @ John Heinz NWC | 420 | 0 | Transportation Enhancement | CON | FLAP |  |  | 677840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677840
STWD Items | 6 | Delaware | 112052 | PA 420 Parking Improvements @ John Heinz NWC | 420 | 0 | Transportation Enhancement | CON | OTH-F |  |  | 89760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89760
STWD Items | 6 | Philadelphia | 112030 | PA FLAP PHL LNDBRGH(1)(C) | 3025 | FLP | Bicycle Pedestrian Highway | CON | FLAP | 2025-06-26 | 2025-06-26 | 734500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 734500
STWD Items | 6 | Philadelphia | 112030 | PA FLAP PHL LNDBRGH(1)(C) | 3025 | FLP | Bicycle Pedestrian Highway | CON | OTH-F | 2025-06-26 | 2025-06-26 | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41000
STWD Items | 6 | Philadelphia | 112030 | PA FLAP PHL LNDBRGH(1)(C) | 3025 | FLP | Bicycle Pedestrian Highway | CON | LOC | 2025-06-26 | 2025-06-26 | 112884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112884
STWD Items | 6 | Philadelphia | 121301 | Southport Berth Development & Port Expansion |  |  | MultiModal | CON | INFRA |  |  | 49000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49000000
STWD Items | 6 | Philadelphia | 121303 | Tioga Marine Terminal Warehouse & Gate Relocation |  |  | MultiModal | CON | INFRA |  |  | 20341494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20341494
STWD Items | 6 | Philadelphia | 121304 | Connector Bridge at Packer Ave Marine Terminal |  |  | MultiModal | CON | INFRA |  |  | 0 | 13017024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13017024
STWD Items | 6 | Philadelphia | 122293 | SouthPort Berth Phase 2 - CARGO |  |  | MultiModal | CON | MEGA |  |  | 217200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217200000
STWD Items | 99 | Central Office | 10 | DBE Supportive Services |  |  | Reserve Line Item | CON | DBE |  |  | 255000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000
STWD Items | 99 | Central Office | 10 | DBE Supportive Services |  |  | Reserve Line Item | CON | 581 |  |  | 63750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63750
STWD Items | 99 | Central Office | 59763 | Transit Flex Reserve |  |  | Reserve Line Item | CON | STP |  |  | 0 | 1744800 | 1744800 | 1744800 | 1744800 | 1744800 | 1744800 | 1744800 | 6979200 | 19192800
STWD Items | 99 | Central Office | 60469 | TIIF / Econ. Dev. Reserve |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 2734955 | 16400000 | 30510522 | 25000000 | 25000000 | 25000000 | 25000000 | 100000000 | 249645477
STWD Items | 99 | Central Office | 60560 | TAP Reserve |  |  | Reserve Line Item | CON | TAP |  |  | 0 | 1592410 | 659091 | 30604000 | 30604000 | 30604000 | 30604000 | 30604000 | 122416000 | 277687501
STWD Items | 99 | Central Office | 74548 | Pooled Fund Studies LI |  |  | Reserve Line Item | PRA | SPR |  |  | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 2400000 | 7200000
STWD Items | 99 | Central Office | 77786 | Highway Reserve |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 972777 | 18100000 | 17989478 | 30000000 | 35200000 | 30000000 | 30000000 | 164351397 | 326613652
STWD Items | 99 | Central Office | 79725 | ROW Take-up 80/20 |  |  | Reserve Line Item | ROW | STP |  |  | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200
STWD Items | 99 | Central Office | 79725 | ROW Take-up 80/20 |  |  | Reserve Line Item | ROW | 581 |  |  | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550
STWD Items | 99 | Central Office | 82335 | Bridge Reserve |  |  | Reserve Line Item | CON | 185 |  |  | 0 | 0 | 32000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 157487801 | 339487801
STWD Items | 99 | Central Office | 84337 | State (15%) Reserve |  |  | Reserve Line Item | CON | 581 |  |  | 0 | 153477 | 1071309 | 396331 | 0 | 9542 | 680000 | 3389731 | 2294000 | 7994390
STWD Items | 99 | Central Office | 84371 | Bridg Insp Training LI |  |  | Reserve Line Item | PRA | STP |  |  | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 2560000 | 7680000
STWD Items | 99 | Central Office | 84371 | Bridg Insp Training LI |  |  | Reserve Line Item | PRA | 582 |  |  | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 640000 | 1920000
STWD Items | 99 | Central Office | 84372 | Federal SRTS Reserve |  |  | Reserve Line Item | CON | SRTSF |  |  | 0 | 304673 | 273505 | 0 | 0 | 0 | 0 | 0 | 0 | 578178
STWD Items | 99 | Central Office | 84636 | APD/Local Access Reserve |  |  | Reserve Line Item | CON | APD |  |  | 0 | 20679345 | 1045791 | 4111993 | 0 | 0 | 0 | 0 | 0 | 25837129
STWD Items | 99 | Central Office | 87583 | Env Rev US Army Corps |  |  | Reserve Line Item | PE | STP |  |  | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 2080000 | 6240000
STWD Items | 99 | Central Office | 87583 | Env Rev US Army Corps |  |  | Reserve Line Item | PE | 581 |  |  | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 520000 | 1560000
STWD Items | 99 | Central Office | 87584 | Env Rev US F&WS |  |  | Reserve Line Item | PE | STP |  |  | 307186 | 316402 | 325894 | 335590 | 335590 | 335590 | 335590 | 335590 | 1342360 | 3969792
STWD Items | 99 | Central Office | 87584 | Env Rev US F&WS |  |  | Reserve Line Item | PE | 581 |  |  | 76797 | 79100 | 81473 | 83998 | 83998 | 83998 | 83998 | 83998 | 335992 | 993352
STWD Items | 99 | Central Office | 87585 | Env Rev PHMC |  |  | Reserve Line Item | PE | STP |  |  | 313399 | 322800 | 332485 | 342603 | 342603 | 342603 | 342603 | 342603 | 1370412 | 4052111
STWD Items | 99 | Central Office | 87585 | Env Rev PHMC |  |  | Reserve Line Item | PE | 581 |  |  | 78350 | 80701 | 83121 | 85651 | 85651 | 85651 | 85651 | 85651 | 342604 | 1013031
STWD Items | 99 | Central Office | 87586 | Env Rev PA Fish/Boat |  |  | Reserve Line Item | PE | STP |  |  | 252699 | 260249 | 268056 | 276098 | 276098 | 276098 | 276098 | 276098 | 1104392 | 3265886
STWD Items | 99 | Central Office | 87586 | Env Rev PA Fish/Boat |  |  | Reserve Line Item | PE | 581 |  |  | 63168 | 65063 | 67015 | 69025 | 69025 | 69025 | 69025 | 69025 | 276100 | 816471
STWD Items | 99 | Central Office | 87587 | Env Rev PA Game Comm |  |  | Reserve Line Item | PE | STP |  |  | 76156 | 78440 | 80793 | 83216 | 83216 | 83216 | 83216 | 83216 | 332864 | 984333
STWD Items | 99 | Central Office | 87587 | Env Rev PA Game Comm |  |  | Reserve Line Item | PE | 581 |  |  | 19040 | 19611 | 20199 | 20805 | 20805 | 20805 | 20805 | 20805 | 83220 | 246095
STWD Items | 99 | Central Office | 87588 | Env Rev PA DEP |  |  | Reserve Line Item | PE | STP |  |  | 1617601 | 1550769 | 1597292 | 1645210 | 1645210 | 1645210 | 1645210 | 1645210 | 6580840 | 19572552
STWD Items | 99 | Central Office | 87588 | Env Rev PA DEP |  |  | Reserve Line Item | PE | 581 |  |  | 404401 | 387693 | 399323 | 411303 | 411303 | 411303 | 411303 | 411303 | 1645212 | 4893144
STWD Items | 99 | Central Office | 88614 | 179 Fund Closeout |  |  | Reserve Line Item | CON | 179 |  |  | 894022 | 611000 | 742000 | 677000 | 1000000 | 350000 | 0 | 0 | 0 | 4274022
STWD Items | 99 | Central Office | 91407 | Env Rev PA DCNR |  |  | Reserve Line Item | PE | STP |  |  | 106693 | 216588 | 113191 | 116586 | 116586 | 116586 | 116586 | 116586 | 466344 | 1485746
STWD Items | 99 | Central Office | 91407 | Env Rev PA DCNR |  |  | Reserve Line Item | PE | 581 |  |  | 26674 | 54147 | 28298 | 29147 | 29147 | 29147 | 29147 | 29147 | 116588 | 371442
STWD Items | 99 | Central Office | 94921 | Wall/Sign Structure Inspection |  |  | Reserve Line Item | FD | STP |  |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
STWD Items | 99 | Central Office | 94921 | Wall/Sign Structure Inspection |  |  | Reserve Line Item | FD | 582 |  |  | 62500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62500
STWD Items | 99 | Central Office | 98255 | RRX Reserve |  |  | Reserve Line Item | CON | RRX |  |  | 0 | 149368 | 233268 | 0 | 0 | 0 | 1068434 | 685158 | 19032312 | 21168540
STWD Items | 99 | Central Office | 101924 | Planning Reserve |  |  | Reserve Line Item | PRA | SPR |  |  | 380920 | 78197517 | 78197517 | 78197517 | 78197517 | 78197517 | 78197517 | 78197517 | 312790068 | 860553607
STWD Items | 99 | Central Office | 101924 | Planning Reserve |  |  | Reserve Line Item | PRA | 581 |  |  | 2312480 | 9774419 | 9774419 | 9774419 | 9774419 | 9774419 | 9774419 | 9774419 | 39097676 | 109831089
STWD Items | 99 | Central Office | 101924 | Planning Reserve |  |  | Reserve Line Item | PRA | LOC |  |  | 2848480 | 9774419 | 9774419 | 9774419 | 9774419 | 9774419 | 9774419 | 9774419 | 39097676 | 110367089
STWD Items | 99 | Central Office | 101969 | HSIP Set Aside Reserve |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 18313130 | 37977700 | 33472882 | 50000000 | 50000000 | 50000000 | 50000000 | 200000000 | 489763712
STWD Items | 99 | Central Office | 101969 | HSIP Set Aside Reserve |  |  | Reserve Line Item | CON | HSIP |  |  | 0 | 446614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 446614
STWD Items | 99 | Central Office | 102466 | NHPP Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 3093147 | 750000 | 55000 | 343542 | 650000 | 0 | 0 | 10473783 | 15365472
STWD Items | 99 | Central Office | 102620 | STP Reserve |  |  | Reserve Line Item | CON | STP |  |  | 0 | 19111879 | 3843000 | 27000 | 27000 | 27000 | 380776 | 527000 | 99707076 | 123650731
STWD Items | 99 | Central Office | 102893 | Multimodal Reserve |  |  | Reserve Line Item | CON | 411 |  |  | 45117201 | 68495614 | 87340000 | 89867000 | 89867000 | 89867000 | 89867000 | 89867000 | 359468000 | 1009755815
STWD Items | 99 | Central Office | 103866 | Deob Reserve |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 518037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518037
STWD Items | 99 | Central Office | 103866 | Deob Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 60308 | 0 | 243521 | 0 | 0 | 0 | 0 | 0 | 303829
STWD Items | 99 | Central Office | 103866 | Deob Reserve |  |  | Reserve Line Item | CON | STP |  |  | 0 | 430106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430106
STWD Items | 99 | Central Office | 104410 | Local Bridge Inspection |  |  | Reserve Line Item | FD | STP |  |  | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
STWD Items | 99 | Central Office | 104410 | Local Bridge Inspection |  |  | Reserve Line Item | FD | PRIV |  |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
STWD Items | 99 | Central Office | 104411 | TIIF Oversight and Mngmt |  |  | Reserve Line Item | PE | 581 |  |  | 0 | 0 | 6800000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 16600000 | 40400000
STWD Items | 99 | Central Office | 104412 | TAP Oversight & Mngmt |  |  | Reserve Line Item | PRA | TAP |  |  | 68264 | 1170356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1238620
STWD Items | 99 | Central Office | 104412 | TAP Oversight & Mngmt |  |  | Reserve Line Item | PE | STP |  |  | 198057 | 200000 | 1100000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 8000000 | 19498057
STWD Items | 99 | Central Office | 106136 | P3 RBR Payments |  |  | Reserve Line Item | CON | 185 | 2018-01-30 | 2018-01-30 | 15640000 | 15700000 | 15750000 | 15810000 | 15843000 | 15905000 | 15960000 | 16028000 | 64663000 | 191299000
STWD Items | 99 | Central Office | 106136 | P3 RBR Payments |  |  | Reserve Line Item | CON | 581 | 2018-01-30 | 2018-01-30 | 15640000 | 15700000 | 15750000 | 15810000 | 15843000 | 15905000 | 15960000 | 16028000 | 64663000 | 191299000
STWD Items | 99 | Central Office | 106136 | P3 RBR Payments |  |  | Reserve Line Item | CON | 185 | 2018-01-30 | 2018-01-30 | 15640000 | 15700000 | 15750000 | 15810000 | 15843000 | 15905000 | 15960000 | 16028000 | 64663000 | 191299000
STWD Items | 99 | Central Office | 106136 | P3 RBR Payments |  |  | Reserve Line Item | CON | 581 | 2018-01-30 | 2018-01-30 | 15640000 | 15700000 | 15750000 | 15810000 | 15843000 | 15905000 | 15960000 | 16028000 | 64663000 | 191299000
STWD Items | 99 | Central Office | 107082 | LTAP Line Item |  |  | Reserve Line Item | PRA | SPR |  |  | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 1600000 | 4800000
STWD Items | 99 | Central Office | 107087 | DCNR Rec Trails Reserve |  |  | Reserve Line Item | CON | REC |  |  | 183618 | 1752048 | 1991000 | 1991000 | 1991000 | 1991000 | 1991000 | 1991000 | 7964000 | 21845666
STWD Items | 99 | Central Office | 111145 | TSMO Reserve |  |  | Reserve Line Item | CON | CRP |  |  | 0 | 6922942 | 8062064 | 7100000 | 8000000 | 10000000 | 10000000 | 10000000 | 40000000 | 100085006
STWD Items | 99 | Central Office | 112699 | Statewide INRIX Contract |  |  | Planning/Research/Administration | PRA | STP |  |  | 2629936 | 92064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2722000
STWD Items | 99 | Central Office | 113413 | Traffic Monitoring Sites Install and Repair 2024 |  |  | Planning/Research/Administration | CON | SPR | 2024-10-24 | 2024-10-24 | 353000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353000
STWD Items | 99 | Central Office | 114339 | ATCMTD Work Zone Safety and Operation |  |  | Reserve Line Item | CON | SXF |  |  | 130770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130770
STWD Items | 99 | Central Office | 114339 | ATCMTD Work Zone Safety and Operation |  |  | Reserve Line Item | CON | 581 |  |  | 130770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130770
STWD Items | 99 | Central Office | 114537 | Norfolk Southern Statewide LED Upgrades |  |  | Reserve Line Item | CON | RRX |  |  | 22756 | 183100 | 75161 | 13293 | 1157415 | 1148739 | 301951 | 325000 | 0 | 3227415
STWD Items | 99 | Central Office | 114543 | Norfolk Southern Statewide Circuitry Upgrade |  |  | Rail Highway Grade Crossing | CON | RRX |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1524791 | 135963 | 0 | 1660754
STWD Items | 99 | Central Office | 114552 | Historic Metal Truss Bridge Reserve |  |  | Reserve Line Item | CON | STP |  |  | 0 | 933805 | 1175000 | 200000 | 500000 | 2000000 | 2000000 | 2000000 | 8000000 | 16808805
STWD Items | 99 | Central Office | 114961 | State Bridge Inspection |  |  | Reserve Line Item | FD | 581 |  |  | 29963000 | 30787000 | 31604710 | 32477851 | 32477851 | 32477851 | 32477851 | 32477851 | 129911404 | 384655369
STWD Items | 99 | Central Office | 114973 | Local Bridge Inspection |  |  | Reserve Line Item | FD | NHPP |  |  | 7947150 | 7672600 | 9522600 | 9348050 | 8622600 | 8622600 | 8622600 | 8622600 | 34490400 | 103471200
STWD Items | 99 | Central Office | 114973 | Local Bridge Inspection |  |  | Reserve Line Item | FD | STP |  |  | 16605953 | 639247 | 8622600 | 8622600 | 8622600 | 8622600 | 8622600 | 8622600 | 34490400 | 103471200
STWD Items | 99 | Central Office | 114973 | Local Bridge Inspection |  |  | Reserve Line Item | FD | PRIV |  |  | 6307138 | 2315462 | 4311300 | 4311300 | 4311300 | 4311300 | 4311300 | 4311300 | 17245200 | 51735600
STWD Items | 99 | Central Office | 115813 | Wall and Sign Structure Inspection |  |  | Reserve Line Item | FD | STP |  |  | 1920000 | 1920000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3840000
STWD Items | 99 | Central Office | 115813 | Wall and Sign Structure Inspection |  |  | Reserve Line Item | FD | 582 |  |  | 480000 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960000
STWD Items | 99 | Central Office | 117918 | Local Road Traffic Counts for MIRE Sept 2026 |  |  | Safety Improvement | PRA | HSIP |  |  | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
STWD Items | 99 | Central Office | 117944 | New HSIP Application Website |  |  | Safety Improvement | PRA | HSIP |  |  | 1929976 | 70024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
STWD Items | 99 | Central Office | 118052 | PennDOT Pollinator Initiative |  |  | Vegetation Management | CON | STP |  |  | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 2200000 | 6600000
STWD Items | 99 | Central Office | 118322 | PROTECT Reserve |  |  | Reserve Line Item | CON | PRTCT |  |  | 0 | 15570827 | 32670900 | 52039000 | 59639000 | 59639000 | 62639000 | 62639000 | 250556000 | 595392727
STWD Items | 99 | Central Office | 118545 | NEVI Program Support |  |  | Reserve Line Item | PRA | NEVI |  |  | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
STWD Items | 99 | Central Office | 118587 | TSMO Guidebook Updates |  |  | Planning/Research/Administration | PRA | STP |  |  | 65000 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000
STWD Items | 99 | Central Office | 119341 | Federal Carryover Reserve |  |  | Reserve Line Item | CON | BOF |  |  | 0 | 85708833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85708833
STWD Items | 99 | Central Office | 119341 | Federal Carryover Reserve |  |  | Reserve Line Item | CON | BRIP |  |  | 0 | 118701445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118701445
STWD Items | 99 | Central Office | 119341 | Federal Carryover Reserve |  |  | Reserve Line Item | CON | NHPP |  |  | 0 | 19837409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19837409
STWD Items | 99 | Central Office | 119838 | DBE Supportive Services |  |  | Reserve Line Item | CON | DBE |  |  | 420034 | 420034 | 420034 | 420034 | 420034 | 420034 | 420034 | 420034 | 1680136 | 5040408
STWD Items | 99 | Central Office | 119841 | OJT Supportive Services |  |  | Reserve Line Item | CON | OJT |  |  | 537042 | 293521 | 293521 | 50000 | 293521 | 293521 | 293521 | 293521 | 1174084 | 3522252
STWD Items | 99 | Central Office | 120286 | Round 1A Electric Vehicle Infrastructure |  |  | Electric Vehicle Charging Infrastructure | CON | NEVI | 2024-04-11 |  | 22300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22300000
STWD Items | 99 | Central Office | 120880 | 504e Training, Education & Workforce Development |  |  | Reserve Line Item | PRA | NHPP |  |  | 0 | 0 | 0 | 119550 | 0 | 0 | 0 | 0 | 0 | 119550
STWD Items | 99 | Central Office | 121174 | PennDOT Highway Safety Network Screening 2025 |  |  | Safety Improvement | PRA | HSIP |  |  | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
STWD Items | 99 | Central Office | 121176 | MIRE Traffic Volume Count Data Collection |  |  | Safety Improvement | PRA | HSIP |  |  | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
STWD Items | 99 | Central Office | 121177 | HSIP DDSA Support for Districts and Plan Partners |  |  | Safety Improvement | PRA | HSIP |  |  | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
STWD Items | 99 | Central Office | 121484 | Round 1B Electric Vehicle Infrastructure |  |  | Electric Vehicle Charging Infrastructure | CON | NEVI | 2024-04-22 |  | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000000
STWD Items | 99 | Central Office | 121647 | CCPR Asphalt Mix for High Volume Routes |  |  | Planning/Research/Administration | PRA | OTH-F |  |  | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93000
STWD Items | 99 | Central Office | 121647 | CCPR Asphalt Mix for High Volume Routes |  |  | Planning/Research/Administration | PRA | 581 |  |  | 23250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23250
STWD Items | 99 | Central Office | 121648 | EDC7 Next Generation TIM Debris Removal Systems |  |  | Planning/Research/Administration | PRA | OTH-F |  |  | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
STWD Items | 99 | Central Office | 121648 | EDC7 Next Generation TIM Debris Removal Systems |  |  | Planning/Research/Administration | PRA | 581 |  |  | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
STWD Items | 99 | Central Office | 121744 | 504e ConnectU2Jobs Consultant Agreement |  |  | Planning/Research/Administration | PRA | HSIP |  |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
STWD Items | 99 | Central Office | 121745 | 504e ConnectU2Jobs Supportive Services |  |  | Planning/Research/Administration | PRA | HSIP |  |  | 130450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130450
STWD Items | 99 | Central Office | 121761 | 504e CWTP Construction Academy |  |  | Planning/Research/Administration | PRA | NHPP |  |  | 295510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295510
STWD Items | 99 | Central Office | 121761 | 504e CWTP Construction Academy |  |  | Planning/Research/Administration | PRA | HSIP |  |  | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000
STWD Items | 99 | Central Office | 121779 | 504e Human Capital Plan |  |  | Planning/Research/Administration | PRA | HSIP |  |  | 695000 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805000
STWD Items | 99 | Central Office | 122203 | PA Wildlife Crossings Strategic Plan |  |  | Reserve Line Item | STUDY | WCPP |  |  | 840000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840000
STWD Items | 99 | Central Office | 122203 | PA Wildlife Crossings Strategic Plan |  |  | Reserve Line Item | STUDY | 581 |  |  | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
STWD Items | 99 | Central Office | 122207 | 504e OJT Enhanced Supportive Services |  |  | Reserve Line Item | PRA | NHPP |  |  | 250000 | 250000 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 1000000
STWD Items | 99 | Central Office | 122207 | 504e OJT Enhanced Supportive Services |  |  | Reserve Line Item | PRA | STP |  |  | 1500000 | 1500000 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 6000000
STWD Items | 99 | Central Office | 122213 | 2025 DCNR REC TRLS - ADMIN |  |  | Reserve Line Item | CON | REC |  |  | 139389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139389
STWD Items | 99 | Central Office | 122213 | 2025 DCNR REC TRLS - ADMIN |  |  | Reserve Line Item | CON | LOC |  |  | 34847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34847
STWD Items | 99 | Central Office | 122214 | 2025 DCNR REC TRLS - EDU |  |  | Reserve Line Item | CON | REC |  |  | 99563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99563
STWD Items | 99 | Central Office | 122214 | 2025 DCNR REC TRLS - EDU |  |  | Reserve Line Item | CON | LOC |  |  | 24891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24891
STWD Items | 99 | Central Office | 122265 | PL Funds 2025-27 |  |  | Planning/Research/Administration | PRA | PL |  |  | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000
STWD Items | 99 | Central Office | 122265 | PL Funds 2025-27 |  |  | Planning/Research/Administration | PRA | 581 |  |  | 1875000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1875000
STWD Items | 99 | Central Office | 122265 | PL Funds 2025-27 |  |  | Planning/Research/Administration | PRA | LOC |  |  | 1975000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1975000
STWD Items | 99 | Central Office | 122266 | PL Funds Toll Cr 2025-27 |  |  | Planning/Research/Administration | PRA | PL |  |  | 627000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627000
STWD Items | 99 | Central Office | 122267 | SPRPlngCO/Consult 2025-27 |  |  | Planning/Research/Administration | PRA | SPR |  |  | 14600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14600000
STWD Items | 99 | Central Office | 122267 | SPRPlngCO/Consult 2025-27 |  |  | Planning/Research/Administration | PRA | 581 |  |  | 3800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800000
STWD Items | 99 | Central Office | 122267 | SPRPlngCO/Consult 2025-27 |  |  | Planning/Research/Administration | PRA | LOC |  |  | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800000
STWD Items | 99 | Central Office | 122268 | SPRPlngCO/ConsultToll 2025-27 |  |  | Planning/Research/Administration | PRA | SPR |  |  | 24000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000000
STWD Items | 99 | Central Office | 122269 | SPR Research 2025-27 |  |  | Planning/Research/Administration | PRA | SPR |  |  | 4725000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4725000
STWD Items | 99 | Central Office | 122269 | SPR Research 2025-27 |  |  | Planning/Research/Administration | PRA | 581 |  |  | 1325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1325000
STWD Items | 99 | Central Office | 122270 | SPR Research FED/TOLL 2025-27 |  |  | Planning/Research/Administration | PRA | SPR |  |  | 6500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500000
STWD Items | 99 | Central Office | 122271 | FTA/CPG Metro 2025-27 |  |  | Planning/Research/Administration | PRA | PL |  |  | 6100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6100000
STWD Items | 99 | Central Office | 122271 | FTA/CPG Metro 2025-27 |  |  | Planning/Research/Administration | PRA | LOC |  |  | 1525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1525000
STWD Items | 99 | Central Office | 122272 | FTA/CPG Statewide 2025-27 |  |  | Planning/Research/Administration | PRA | SPR |  |  | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1160000
STWD Items | 99 | Central Office | 122272 | FTA/CPG Statewide 2025-27 |  |  | Planning/Research/Administration | PRA | 581 |  |  | 86000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86000
STWD Items | 99 | Central Office | 122272 | FTA/CPG Statewide 2025-27 |  |  | Planning/Research/Administration | PRA | LOC |  |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
STWD Items | 99 | Central Office | 122273 | IIJA/BIL Safe and Accessible Transportation PL |  |  | Planning/Research/Administration | PRA | PL |  |  | 444000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 444000
STWD Items | 99 | Central Office | 122274 | IIJA/BIL Safe and Accessible Transportation SPR |  |  | Planning/Research/Administration | PRA | SPR |  |  | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000
STWD Items | 99 | Central Office | 122275 | 504e CWTP Consultant Support |  |  | Planning/Research/Administration | PRA | HSIP |  |  | 3600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600000
STWD Items | 99 | Central Office | 122278 | SMART V2X Data Exchange OEM Integration |  |  | Reserve Line Item | PRA | SMART |  |  | 1784556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1784556
STWD Items | 99 | Central Office | 122282 | 504e CTC Adult Learning Consultant Agreement |  |  | Planning/Research/Administration | PRA | NHPP |  |  | 1800000 | 1800000 | 800000 | 550000 | 0 | 0 | 0 | 0 | 0 | 4950000
STWD Items | 99 | Central Office | 122283 | 504e CTC Adult Learning Supportive Services |  |  | Planning/Research/Administration | PRA | NHPP |  |  | 2445000 | 3000000 | 3250000 | 3305000 | 0 | 0 | 0 | 0 | 0 | 12000000
STWD Items | 99 | Central Office | 122327 | 2023 AID Demonstration Award |  |  | Planning/Research/Administration | CON | AID |  |  | 759600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759600
STWD Items | 99 | Central Office | 122327 | 2023 AID Demonstration Award |  |  | Planning/Research/Administration | CON | 581 |  |  | 189900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189900
STWD Items | 99 | Central Office | 122361 | ConnectU2Jobs Program-Full Deployment |  |  | General Maintenance | PRA | NHPP |  |  | 1340000 | 2010000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3350000
STWD Items | 99 | Central Office | 122362 | Construction Academy Full Deployment |  |  | General Maintenance | PRA | NHPP |  |  | 430000 | 860000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1290000
STWD Items | 99 | Central Office | 122510 | 2025 DCNR REC TRLS STIP 1 |  |  | Bicycle Pedestrian Highway | CON | REC |  |  | 268430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268430
STWD Items | 99 | Central Office | 122510 | 2025 DCNR REC TRLS STIP 1 |  |  | Bicycle Pedestrian Highway | CON | LOC |  |  | 67109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67109
STWD Items | 99 | Central Office | 122511 | 2025 DCNR REC TRLS STIP 2 |  |  | Bicycle Pedestrian Highway | CON | REC |  |  | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000
STWD Items | 99 | Central Office | 122530 | 2027 Strategic Highway Safety Plan Development |  |  | Safety Improvement | PRA | HSIP | 2026-04-01 |  | 300000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
STWD Items | 99 | Central Office | 122874 | FY25 T2 Program |  |  | Reserve Line Item | PRA | OTH-F |  |  | 9519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9519
STWD Items | 99 | Central Office | 122874 | FY25 T2 Program |  |  | Reserve Line Item | PRA | 581 |  |  | 2380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2380
STWD Items | 99 | Central Office | 123051 | 2026 DCNR REC TRLS - ADMIN |  |  | Reserve Line Item | CON | REC |  |  | 0 | 139389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139389
STWD Items | 99 | Central Office | 123051 | 2026 DCNR REC TRLS - ADMIN |  |  | Reserve Line Item | CON | LOC |  |  | 0 | 34847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34847
STWD Items | 99 | Central Office | 123052 | 2026 DCNR REC TRLS - EDU |  |  | Reserve Line Item | CON | REC |  |  | 0 | 99563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99563
STWD Items | 99 | Central Office | 123052 | 2026 DCNR REC TRLS - EDU |  |  | Reserve Line Item | CON | LOC |  |  | 0 | 24891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24891
STWD Items | 99 | Central Office | 123080 | 504e Railroad Protective Services Workforce Dvlpmt |  |  | Reserve Line Item | PRA | HSIP |  |  | 4750000 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6350000
STWD Items | 99 | Central Office | 123242 | NEVI Corridor Connections |  |  | Electric Vehicle Charging Infrastructure | CON | NEVI |  |  | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000000
STWD Items | 99 | Central Office | 123242 | NEVI Corridor Connections |  |  | Electric Vehicle Charging Infrastructure | CON | LOC |  |  | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000
STWD Items | 99 | Central Office | 123276 | NEVI Community Charging |  |  | Electric Vehicle Charging Infrastructure | CON | NEVI |  |  | 38032188 | 65208444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103240632
STWD Items | 99 | Central Office | 123276 | NEVI Community Charging |  |  | Electric Vehicle Charging Infrastructure | CON | LOC |  |  | 9508047 | 16529398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26037445
STWD Items | 99 | Central Office | 123605 | SMART Freight Signal Priority Project |  |  | Reserve Line Item | PRA | SMART |  |  | 0 | 1327358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1327358
STWD Items | 99 | Central Office | 123975 | NEVI Electric Vehicle Supply Equipment |  |  | Reserve Line Item | CON | NEVI |  |  | 0 | 270489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270489
STWD Items | 99 | Central Office | 123975 | NEVI Electric Vehicle Supply Equipment |  |  | Reserve Line Item | CON | LOC |  |  | 0 | 67623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67623
STWD Items | 99 | Central Office | 124055 | Advancement of Tools for Transp. Asset Management |  |  | Planning/Research/Administration | PRA | SPR |  |  | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000
[12 empty] | 5135465781.4 | 5352326373.3 | 4048404379.3 | 4066212319.9 | 4072622816 | 3993859225 | 4063046506 | 3975072340 | 15933419475 | 50640429215.9
[12 empty] | 5135465781.4 | 5352326373.3 | 4048404379.3 | 4066212319.9 | 4072622816 | 3993859225 | 4063046506 | 3975072340 | 15933419475 | 50640429215.9